P.1001189 | O.1001189.03 | A.1001189.03.01 | Well 3 | GREYMOUTH PETROLEUM |  | Tiger-246 | J.26.000144 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-07-07 03:00 | 2024-06-30 22:00 |  | 2024-07-07 05:00 | 2024-07-16 23:59 |  | 2024-07-16 23:59 | New Plymouth WL | CKok3 | 2024-08-21 17:52 | FDPSystemUser |  | No |  |  |  |  | Ayssar Alsayed |  | 0 | 4 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001189 | O.1001189.03 | A.1001189.03.08 | Kaimiro-20 Pipe Recovery | GREYMOUTH PETROLEUM | KAIMIRO-20 | Tiger-246 | J.24.054849 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-02-21 | 2024-02-21 |  | 2024-02-21 | 2024-02-24 23:59 |  | 2024-02-24 23:59 | New Plymouth WL | CKok3 | 2024-08-21 17:52 | FDPSystemUser |  | No |  |  |  |  | Cheryl Kok |  | 0 | 1 |  | L0 - No RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001189 | O.1001189.03 | A.1001189.03.06 | TURANGI-21 | GREYMOUTH PETROLEUM | TURANGI 21 | Tiger-246 | J.24.024814 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-08-05 | 2024-07-23 |  | 2024-08-05 | 2024-08-15 23:59 |  | 2024-08-16 01:59 | New Plymouth WL | CKok3 | 2024-08-19 10:12 | YLee25 |  | No |  |  |  | ROE WL Mumbai | Cheryl Kok |  | 988194.52 | 5 |  | L2 - Shift RO |  | 100 | 100 | 100 | 100 | 100 |  | 3 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001189 | O.1001189.03 | A.1001189.03.07 | Turangi-17 | GREYMOUTH PETROLEUM | TURANGI 17 | Tiger-246 | J.24.024815 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-06-03 10:00 | 2024-05-30 |  | 2024-06-03 | 2024-06-13 22:59 |  | 2024-06-14 09:59 | New Plymouth WL | CKok3 | 2024-06-20 10:37 | YLee25 |  | No |  |  |  |  | Cheryl Kok |  | 1039451.45 | 5 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 4 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001189 | O.1001189.03 | A.1001189.03.05 | Well #5 | GREYMOUTH PETROLEUM |  | Tiger-246 | J.24.022524 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2024-03-01 |  | 2024-03-01 | 2024-03-11 23:59 |  |  | New Plymouth WL | CKok3 | 2023-11-03 12:01 | CKok3 |  | No |  |  |  |  | Cheryl Kok |  | 0 |  |  | L0 - No RO |  | 8.3 | 0 | 0 | 0 | 2.5 |  | 0 | [7 empty] | Cheryl Kok | WL Evaluation Services
P.1001189 | O.1001189.02 | A.1001189.02.14 | Turangi-2 PNX | GREYMOUTH PETROLEUM | TURANGI 2 | Tiger-246 | J.22.129894 | RPI | PS-WL-Ops | Low | Cancelled | Execute - PSD |  | In Progress | Not Started | In Progress |  | 2023-09-20 |  | 2023-09-30 06:00 | 2024-10-07 05:59 |  |  | New Plymouth WL | CLorenzo | 2024-08-21 17:52 | FDPSystemUser |  | No |  |  |  | ROE WL Abu Dhabi | Ayssar Alsayed |  | 0 | 1 |  | L1 - Support RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1001189 | O.1001189.02 | A.1001189.02.20 | Turangi-2 PNX | GREYMOUTH PETROLEUM | TURANGI 2 | Tiger-246 | J.23.103062 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-09-30 | 2023-09-23 |  | 2023-09-30 | 2023-10-07 23:59 |  | 2023-10-07 23:59 | New Plymouth WL | CKok3 | 2024-08-21 17:52 | FDPSystemUser |  | No |  |  |  |  | Cheryl Kok |  | 0 | 1 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1001189 | O.1001189.02 | A.1001189.02.19 | Turangi-21 | GREYMOUTH PETROLEUM | TURANGI 19 | Tiger-246 | J.23.085265 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-12-01 04:00 | 2023-11-22 23:00 | 2023-11-28 12:00 | 2023-12-01 06:00 | 2023-12-11 00:59 | 2023-12-11 01:00 | 2023-12-11 00:59 | New Plymouth WL | CKok3 | 2023-07-20 16:18 | CKok3 |  | No |  |  |  |  | Cheryl Kok |  | 0 | 4 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001189 | O.1001189.02 | A.1001189.02.18 | Turangi-20 | GREYMOUTH PETROLEUM | TURANGI 19 | Tiger-246 | J.23.085264 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-01 04:00 | 2023-08-23 23:00 | 2023-08-29 11:00 | 2023-09-01 06:00 | 2023-09-11 00:59 | 2023-09-11 | 2023-09-11 00:59 | New Plymouth WL | CKok3 | 2023-07-19 05:51 | CKok3 |  | No |  |  |  |  | Cheryl Kok |  | 0 | 4 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001189 | O.1001189.02 | A.1001189.02.17 | Turang- C-1 | GREYMOUTH PETROLEUM | TURANGI C-1 | Tiger-246 | J.23.034422 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-06-05 05:00 | 2023-05-29 | 2023-06-02 | 2023-06-05 06:00 | 2023-06-14 23:59 | 2023-06-15 02:00 | 2023-06-14 23:59 | New Plymouth WL | CKok3 | 2023-06-30 12:46 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Ayssar Alsayed |  | 187240.92 | 2 |  | L2 - Shift RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001189 | O.1001189.02 | A.1001189.02.16 | Turangi C-2 | GREYMOUTH PETROLEUM | TURANG- C-2 | Tiger-246 | J.23.034421 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-06 05:00 | 2023-05-01 23:00 |  | 2023-05-06 06:00 | 2023-05-15 23:59 |  | 2023-05-20 22:59 | New Plymouth WL | CKok3 | 2023-05-11 14:12 | YLee25 |  | No |  |  |  |  | Ayssar Alsayed |  | 41515.58 | 2 |  | L0 - No RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001189 | O.1001189.02 | A.1001189.02.12 | Turangi-19 | GREYMOUTH PETROLEUM | TURANGI 19 | Tiger-246 | J.23.008596 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-01 04:00 | 2023-03-23 23:00 |  | 2023-04-01 06:00 | 2023-04-10 23:59 |  | 2023-04-10 23:59 | New Plymouth WL | CLorenzo | 2023-04-27 12:00 | YLee25 |  | No |  |  |  |  | Ayssar Alsayed |  | 886426.83 | 4 |  | L0 - No RO |  | 91.7 | 91.7 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001189 | O.1001189.02 | A.1001189.02.15 | Turangi-2 USIT-CBL | GREYMOUTH PETROLEUM | TURANGI 2 | Tiger-246 | J.22.132261 | RPE | ES-CH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-12-26 | 2022-12-03 |  | 2022-12-26 | 2022-12-31 23:59 |  | 2022-12-31 23:59 | New Plymouth WL | CKok3 | 2022-12-27 18:26 | CKok3 |  | No |  |  |  |  | Omar Mosleh |  | 0 | 1 |  | L0 - No RO |  | 75 | 100 | 0 | 0 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001189 | O.1001189.02 | A.1001189.02.10 | Turangi-18 | GREYMOUTH PETROLEUM | TURANGI-18 | Tiger-246 | J.22.110451 | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-07 07:00 | 2022-11-07 |  | 2022-11-07 06:00 | 2022-11-13 23:59 |  | 2022-11-14 00:59 | New Plymouth WL | CLorenzo | 2022-11-28 12:26 | CLorenzo |  | No |  |  |  |  | Omar Mosleh |  | 772396.5 | 5 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Claudio Sanabria | WL Evaluation Services
P.1001189 | O.1001189.02 | A.1001189.02.13 | Tariki-1A | GREYMOUTH PETROLEUM |  | Tiger-246 | J.22.119768 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-01 07:00 | 2022-11-30 |  | 2022-12-01 06:00 | 2022-12-10 23:59 |  | 2022-12-11 00:59 | New Plymouth WL | CLorenzo | 2022-11-21 19:13 | OMosleh |  | Yes |  |  |  | ROE WL Abu Dhabi | Omar Mosleh |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Claudio Sanabria | WL Production Services
P.1001189 | O.1001189.02 | A.1001189.02.11 | Tariki-1A | GREYMOUTH PETROLEUM |  | Tiger-246 | J.22.110870 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2022-09-01 06:00 | 2022-08-31 |  | 2022-09-01 06:00 | 2022-09-10 23:59 |  | 2022-09-10 23:59 | New Plymouth WL | CLorenzo | 2022-10-03 16:57 | FDPSystemUser |  | Yes |  |  |  | ROE WL Abu Dhabi | Omar Mosleh |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Claudio Sanabria | WL Production Services
P.1001189 | O.1001189.02 | A.1001189.02.08 | Turangi-16 | GREYMOUTH PETROLEUM | Turangi-16 | Tiger-246 | J.21.109415 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-12-21 | 2021-12-20 |  | 2021-12-21 | 2021-12-24 23:59 |  | 2021-12-24 23:59 | New Plymouth WL | YLee25 | 2022-10-03 16:57 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 0 | 5 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1001189 | O.1001189.02 | A.1001189.02.03 | Turangi-11 | GREYMOUTH PETROLEUM | TURANGI-11 | Tiger-246 | J.21.109414 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-02-07 22:30 | 2021-02-21 23:00 |  | 2021-02-21 23:30 | 2021-03-06 00:30 |  | 2021-03-05 22:30 | New Plymouth WL | VOliveira5 | 2022-10-03 16:56 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 343609.78 | [10 empty] | 0 | [7 empty] | Paulo Zuliani | WL Evaluation Services
P.1001189 | O.1001189.02 | A.1001189.02.07 | Turangi-? | GREYMOUTH PETROLEUM | TURANGI-11 | Tiger-246 | J.22.110444 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-08-02 23:00 |  | 2022-08-05 23:30 | 2022-08-10 00:30 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Paulo Zuliani |  | 0 | 4 |  |  |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Ansar-Ud-Din Muhammad | WL Evaluation Services
P.1001189 | O.1001189.02 | A.1001189.02.09 | Turangi-15 | GREYMOUTH PETROLEUM | Turangi-15 | Tiger-246 | J.22.110439 | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed |  | 2022-04-30 |  | 2022-05-01 06:00 | 2022-05-10 23:59 |  |  | New Plymouth WL | YLee25 | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  |  | Paulo Zuliani |  | 786346.37 | 5 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Claudio Sanabria | WL Evaluation Services
P.1001189 | O.1001189.02 | A.1001189.02.04 | Turangi-14 | GREYMOUTH PETROLEUM | Turangi-14 | Tiger-246 | J.21.109091 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-08-12 |  | 2021-08-15 23:30 | 2021-08-28 00:30 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 363154 | 6 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1001189 | O.1001189.02 | A.1001189.02.06 | Turangi17 | GREYMOUTH PETROLEUM | TURANGI-11 | Tiger-246 | J.22.110431 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-04-01 01:00 |  | 2022-04-15 00:30 | 2022-04-27 01:30 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 16:18 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Paulo Zuliani |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1001189 | O.1001189.02 | A.1001189.02.01 | 6.75in OH logging | GREYMOUTH PETROLEUM | TURANGI-10 | Tiger-246 | J.21.109086 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-01-02 23:00 |  | 2021-01-02 23:30 | 2021-01-12 00:30 |  |  | New Plymouth WL | MRony2 | 2022-10-03 16:18 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 375897.5 | [10 empty] | 0 | [7 empty] | Paulo Zuliani | WL Evaluation Services
P.1001189 | O.1001189.02 | A.1001189.02.02 | PS Logging | GREYMOUTH PETROLEUM |  | Tiger-246 | J.20.063593 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-10-19 |  | 2020-10-20 | 2020-10-30 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 16:18 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  |  |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 | [7 empty] | Paulo Zuliani | WL Evaluation Services
P.1001189 | O.1001189.02 | A.1001189.02.05 | Turangi-16 | GREYMOUTH PETROLEUM | Turangi-16 | Tiger-246 | J.21.109083 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-12-22 |  | 2021-12-23 00:30 | 2022-01-03 01:30 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 16:18 | FDPSystemUser |  | No |  |  |  |  | Paulo Zuliani |  | 396499 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1001189 | O.1001189.01 | A.1001189.01.01 | Turangi-9 Logging | GREYMOUTH PETROLEUM | Turangi 9 | Tiger-246 | J.20.063633 | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-01-31 | 2020-01-25 |  | 2020-01-31 | 2020-02-04 23:59 |  | 2020-02-08 | New Plymouth WL | MRony2 | 2022-10-03 16:57 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 962390.59 | [10 empty] | 0 | [7 empty] | Paulo Zuliani | WL Evaluation Services
P.1001188 | O.1001188.01 | A.1001188.01.03 | OMV Rental for 2nd well | OMV NEW ZEALAND LTD | TAWHAKI-1 | COSLProspector | J.20.063632 | RPE | ES-OH-NO | High | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-01-21 | 2020-01-16 |  | 2020-01-21 | 2020-03-06 |  | 2020-03-06 | New Plymouth WL | MRony2 | 2022-10-03 16:56 | FDPSystemUser |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | [10 empty] | 0 | [7 empty] | Paulo Zuliani | WL Evaluation Services
P.1001188 | O.1001188.01 | A.1001188.01.04 | OMV 2nd well logging | OMV NEW ZEALAND LTD |  | COSLProspector | J.20.063631 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-02-04 | 2020-01-30 |  | 2020-02-04 | 2020-02-11 |  | 2020-02-11 | New Plymouth WL | MRony2 | 2022-10-03 16:56 | FDPSystemUser |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | [10 empty] | 0 | [7 empty] | Paulo Zuliani | WL Evaluation Services
P.1001188 | O.1001188.01 | A.1001188.01.02 | Rental WL | OMV NEW ZEALAND LTD | GLADSTONE-1 | COSLProspector | J.19.060680 | RPE | ES-OH-NO | High | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2019-11-30 |  | 2019-12-05 | 2020-01-19 |  |  | New Plymouth WL | MRony2 | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | [10 empty] | 0 | [7 empty] | Paulo Zuliani | WL Evaluation Services
P.1001188 | O.1001188.01 | A.1001188.01.06 | Towtowai1 | OMV NEW ZEALAND LTD | TOWTOWAI-1 | COSLProspector | J.20.063594 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-03-25 |  | 2020-03-28 | 2020-04-21 |  |  | New Plymouth WL | PZuliani | 2022-10-03 16:18 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 727637.32 | [10 empty] | 0 | [7 empty] | Paulo Zuliani | WL Evaluation Services
P.1001188 | O.1001188.01 | A.1001188.01.07 | Maui-8 | OMV NEW ZEALAND LTD | Maui-8 | COSLProspector | J.20.063592 | RPE | ES-OH-NO | Medium | Cancelled | Close - PSD |  | Not Required | Not Started | In Progress |  | 2020-06-02 |  | 2020-06-02 | 2020-06-25 |  |  | New Plymouth WL | PZuliani | 2022-10-03 16:18 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 22233.33 |  |  |  |  | 66.7 | 33.3 | 100 | 50 | 55 |  | 0 | [7 empty] | Paulo Zuliani | WL Evaluation Services
P.1001188 | O.1001188.01 | A.1001188.01.05 | Contingent USIT-CBL-VDL | OMV NEW ZEALAND LTD | GLADSTONE-1 | COSLProspector | J.20.063590 | RPE | ES-CH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-01 |  | 2020-02-05 | 2020-02-06 |  |  | New Plymouth WL | MRony2 | 2022-10-03 16:18 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | [10 empty] | 0 | [7 empty] | Paulo Zuliani | WL Evaluation Services
P.1001188 | O.1001188.01 | A.1001188.01.01 | 12.25 in OH Logging | OMV NEW ZEALAND LTD | GLADSTONE-1 | COSLProspector | J.19.060678 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-02 |  | 2019-12-18 | 2019-12-25 |  |  | New Plymouth WL | MRony2 | 2022-10-03 16:18 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 503895.16 | [10 empty] | 0 | [7 empty] | Paulo Zuliani | WL Evaluation Services
P.1001055 | O.1001055.03 | A.1001055.03.01 | Rental and Reimburseables | EXXONMOBIL PNG LIMITED | ANGORE A2, ANGORE A1 | Superior Energy Rig 32 | J.19.060681 | RPE | ES-CH-NO | Low | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2020-01-30 11:18 | 2019-11-21 |  | 2019-11-21 | 2020-10-31 |  | 2020-10-31 | Port Moresby WL | DGemmel | 2022-10-03 13:19 | FDPSystemUser |  | No |  |  |  |  | Danny Gemmell |  | 185982.02 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Danny Gemmell | WL Evaluation Services
P.1001055 | O.1001055.02 | A.1001055.02.02 | iBC in 9.875" | EXXONMOBIL PNG LIMITED |  | Superior Energy Rig 32 | J.20.063630 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2020-04-05 | 2020-04-17 |  | 2020-05-24 | 2020-05-30 |  | 2020-04-11 | Port Moresby WL | DGemmel | 2022-10-03 13:56 | FDPSystemUser |  | No |  |  |  |  | Danny Gemmell |  | 0 |  |  | L0 - No RO |  | 29.2 | 0 | 0 | 0 | 8.8 |  | 0 | [7 empty] | Danny Gemmell | WL Production Services
P.1001055 | O.1001055.02 | A.1001055.02.06 | Angore-A1 IBC and Operations | EXXONMOBIL PNG LIMITED | Angore A1 | Superior Energy Rig 32 | J.20.063628 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress | 2020-06-25 | 2020-05-19 |  | 2020-06-25 | 2020-07-25 |  | 2020-07-25 | Port Moresby WL | LParedes | 2022-10-03 13:56 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1001055 | O.1001055.02 | A.1001055.02.05 | Backoff for Spear | EXXONMOBIL PNG LIMITED | ANGORE A1 | Superior Energy Rig 32 | J.20.063608 | RPI | PS-WL-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2020-03-29 | 2020-04-16 16:00 |  | 2020-05-16 16:00 | 2020-05-22 16:00 |  | 2020-05-16 16:00 | Port Moresby WL | LParedes | 2022-10-03 13:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 33.3 | 50 | 0 | 12.5 | 28.7 |  | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1001055 | O.1001055.02 | A.1001055.02.03 | IBC and 4.72" HSD in 13.375" | EXXONMOBIL PNG LIMITED | Angore A1 | Superior Energy Rig 32 | J.20.063606 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-04-24 |  | 2020-07-25 | 2020-08-07 |  |  | Port Moresby WL | DGemmel | 2022-10-03 13:20 | FDPSystemUser |  | No |  |  |  |  | Luis Cardenas |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1001055 | O.1001055.02 | A.1001055.02.04 | IBC in 16", Perfo in 16" for squeeze | EXXONMOBIL PNG LIMITED | Angore A1 | Superior Energy Rig 32 | J.20.063599 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-05-01 |  | 2020-08-15 | 2020-08-25 |  |  | Port Moresby WL | DGemmel | 2022-10-03 13:19 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1001055 | O.1001055.02 | A.1001055.02.07 | Angore A1 IBC & OPS | EXXONMOBIL PNG LIMITED | Angore A1 | Superior Energy Rig 32 | J.20.063598 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-05-31 |  | 2020-07-12 | 2020-07-25 |  |  | Port Moresby WL | LParedes | 2022-10-03 13:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1001055 | O.1001055.02 | A.1001055.02.01 | 7" Power cut | EXXONMOBIL PNG LIMITED |  | Superior Energy Rig 32 | J.20.063597 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2020-03-29 | 2020-04-17 |  | 2020-05-17 | 2020-05-23 |  | 2020-03-29 | Port Moresby WL | DGemmel | 2022-10-03 13:19 | FDPSystemUser |  | No |  |  |  |  | Danny Gemmell |  | 0 |  |  | L0 - No RO |  | 29.2 | 0 | 0 | 0 | 8.8 |  | 0 | [7 empty] | Danny Gemmell | WL Production Services
P.1001055 | O.1001055.01 | A.1001055.01.09 | Back-off / IBC-GR / 4.72 HSD in 16in | EXXONMOBIL PNG LIMITED | Angore A2 | Superior Energy Rig 32 | J.20.063629 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-06-02 | 2020-05-27 15:00 |  | 2020-06-01 15:00 | 2020-06-25 15:00 |  | 2020-07-09 | Port Moresby WL | LParedes | 2022-10-03 13:56 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 118696.86 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1001055 | O.1001055.01 | A.1001055.01.04 | 16" IBC & Perfo for Squeeze | EXXONMOBIL PNG LIMITED | ANGORE A2 | Superior Energy Rig 32 | J.20.063627 | RPI | PS-WL-Ops | Low | Unconfirmed - 50% | Design - CEC |  | In Progress | In Progress | In Progress | 2020-03-15 | 2020-02-21 |  | 2020-03-29 | 2020-04-04 |  | 2020-04-04 | Port Moresby WL | DGemmel | 2022-10-03 13:56 | FDPSystemUser |  | No |  |  |  |  | Danny Gemmell |  | 118696.86 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Danny Gemmell | WL Production Services
P.1001055 | O.1001055.01 | A.1001055.01.05 | 7" IBC log | EXXONMOBIL PNG LIMITED | Angore A2 | Superior Energy Rig 32 | J.20.063626 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-01-29 | 2020-01-28 |  | 2020-01-31 | 2020-02-01 |  | 2020-02-07 | Port Moresby WL | DGemmel | 2022-10-03 13:56 | FDPSystemUser |  | No |  |  |  |  | Danny Gemmell |  | 99338.2 | [10 empty] | 0 | [7 empty] | Danny Gemmell | WL Production Services
P.1001055 | O.1001055.01 | A.1001055.01.07 | Pipe recovery operations | EXXONMOBIL PNG LIMITED | Angore A2 | Superior Energy Rig 32 | J.20.063607 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-04-18 |  | 2020-04-19 | 2020-04-30 |  |  | Port Moresby WL | DGemmel | 2022-10-03 13:20 | FDPSystemUser |  | No |  |  |  |  | Danny Gemmell |  | 69729.5 | [10 empty] | 0 | [7 empty] | Danny Gemmell | WL Production Services
P.1001055 | O.1001055.01 | A.1001055.01.06 | 9 7/8" Puncher | EXXONMOBIL PNG LIMITED | Angore A2 | Superior Energy Rig 32 | J.20.063605 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-03-19 |  | 2020-03-20 | 2020-03-21 |  |  | Port Moresby WL | DGemmel | 2022-10-03 13:20 | FDPSystemUser |  | No |  |  |  |  | Danny Gemmell |  | 81888.99 | [10 empty] | 0 | [7 empty] | Danny Gemmell | WL Production Services
P.1001055 | O.1001055.01 | A.1001055.01.01 | 7" Power Cut | EXXONMOBIL PNG LIMITED | Angore A2 | Superior Energy Rig 32 | J.20.063603 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-01-07 |  | 2020-02-06 | 2020-02-12 |  |  | Port Moresby WL | DGemmel | 2022-10-03 13:19 | FDPSystemUser |  | No |  |  |  |  | Danny Gemmell |  | 120346.87 | [10 empty] | 0 | [7 empty] | Danny Gemmell | WL Production Services
P.1001055 | O.1001055.01 | A.1001055.01.02 | 9.875" IBC-PLUG-PUNCHER | EXXONMOBIL PNG LIMITED | Angore A2 | Superior Energy Rig 32 | J.20.063604 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-01-07 14:00 |  | 2020-02-18 | 2020-03-21 |  |  | Port Moresby WL | DGemmel | 2022-10-03 13:19 | FDPSystemUser |  | No |  |  |  |  | Danny Gemmell |  | 99338.2 | [10 empty] | 0 | [7 empty] | Danny Gemmell | WL Production Services
P.1001055 | O.1001055.01 | A.1001055.01.03 | 13.375" IBC & Plug | EXXONMOBIL PNG LIMITED | Angore A2 | Superior Energy Rig 32 | J.20.063601 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-15 |  | 2020-04-15 | 2020-04-21 |  |  | Port Moresby WL | DGemmel | 2022-10-03 13:19 | FDPSystemUser |  | No |  |  |  |  | Danny Gemmell |  | 99338.2 | [10 empty] | 0 | [7 empty] | Danny Gemmell | WL Production Services
P.1001055 | O.1001055.01 | A.1001055.01.08 | Backoff for Spear - IBC Logging on 16" x 13-3/8" casing log | EXXONMOBIL PNG LIMITED | Angore A2 | Superior Energy Rig 32 | J.20.063600 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-05-14 |  | 2020-05-19 | 2020-05-30 |  |  | Port Moresby WL | LParedes | 2022-10-03 13:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 21483.64 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1000996 | O.1000996.01 | A.1000996.01.04 | Geothermal FMI Logging | CONTACT ENERGY LTD. |  | Webster Nova 1 | J.20.063595 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-31 00:50 |  | 2020-04-03 | 2020-04-07 12:00 |  |  | New Plymouth WL | MRony2 | 2022-10-03 16:18 | FDPSystemUser |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | [10 empty] | 0 | [7 empty] | Paulo Zuliani | WL Evaluation Services
P.1000996 | O.1000996.01 | A.1000996.01.01 | Geothermal FMI | CONTACT ENERGY LTD. | TH24 | Webster Nova 1 | J.19.060679 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-09 |  | 2019-12-11 23:00 | 2019-12-19 |  |  | New Plymouth WL | MRony2 | 2022-10-03 16:18 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 71324.61 | [10 empty] | 0 | [7 empty] | Paulo Zuliani | WL Evaluation Services
P.1000996 | O.1000996.01 | A.1000996.01.03 | FMI Logging_Geo Thermal | CONTACT ENERGY LTD. | TH26 | Webster Nova 1 | J.20.063589 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-28 23:50 |  | 2020-03-01 23:00 | 2020-03-06 12:00 |  |  | New Plymouth WL | MRony2 | 2022-10-03 16:18 | FDPSystemUser |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 17831.15 | [10 empty] | 0 | [7 empty] | Paulo Zuliani | WL Evaluation Services
P.1000996 | O.1000996.01 | A.1000996.01.02 | FMI Logging_Geo Thermal | CONTACT ENERGY LTD. | TH25 | Webster Nova 1 | J.20.063588 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-09 23:50 |  | 2020-01-11 23:00 | 2020-01-21 12:00 |  |  | New Plymouth WL | MRony2 | 2022-10-03 16:18 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 116249.51 | [10 empty] | 0 | [7 empty] | Paulo Zuliani | WL Evaluation Services
P.1000916 | O.1000916.01 | A.1000916.01.01 | Slickline Ops PLA-07 | NORMAND SAPURA PTY LTD | Pluto-07 | SapuraKencana Constructor |  | RPI | PS-SLK-Ops | InComplete | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2019-09-15 |  | 2019-09-15 | 2019-09-30 |  |  | New Burn WL | frosa2 | 2020-12-23 02:48 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | Wireline Slickline
P.1000916 | O.1000916.01 | A.1000916.01.02 | Slickline PLA-07 | NORMAND SAPURA PTY LTD | Pluto-07 | SapuraKencana Constructor |  | RPI | PS-SLK-Rental-Ops | InComplete | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2019-10-24 |  | 2019-10-24 02:00 | 2019-12-07 |  |  | New Burn WL | RWijaya | 2020-12-23 02:48 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 132553.61 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Luis Cardenas | Wireline Slickline
P.1000908 | O.1000908.02 | A.1000908.02.14 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED | Combabula 400 | SAVANNA DRILLING #406 | J.20.063042 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-29 |  | 2020-01-30 | 2020-01-31 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:06 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1000908 | O.1000908.02 | A.1000908.02.12 | AIT-PEX-GPIT - Combabula 400 | ORIGIN ENERGY RESOURCES LIMITED | COMBABULA 400 | SAVANNA DRILLING #406 | J.20.063041 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2020-01-16 | 2020-01-15 23:00 |  | 2020-01-16 | 2020-01-17 |  | 2020-01-17 | Roma WL | VOliveira5 | 2022-10-03 13:05 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1000908 | O.1000908.02 | A.1000908.02.06 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #406 | J.19.060564 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-11-11 | 2019-11-10 |  | 2019-11-11 | 2019-11-12 |  | 2019-11-12 | Roma WL | VOliveira5 | 2022-10-03 13:05 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1000908 | O.1000908.02 | A.1000908.02.13 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED | Combabula 400 | SAVANNA DRILLING #406 | J.20.063040 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-22 |  | 2020-01-23 | 2020-01-24 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:05 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1000908 | O.1000908.02 | A.1000908.02.10 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #406 | J.19.060563 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-12-02 | 2019-12-01 |  | 2019-12-02 | 2019-12-03 |  | 2019-12-03 | Roma WL | VOliveira5 | 2022-10-03 13:05 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1000908 | O.1000908.02 | A.1000908.02.09 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #406 | J.19.060562 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-11-26 | 2019-11-25 |  | 2019-11-26 | 2019-11-27 |  | 2019-11-27 | Roma WL | VOliveira5 | 2022-10-03 13:05 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1000908 | O.1000908.02 | A.1000908.02.07 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #406 | J.19.060561 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-11-18 | 2019-11-17 |  | 2019-11-18 | 2019-11-19 |  | 2019-11-19 | Roma WL | VOliveira5 | 2022-10-03 13:05 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1000908 | O.1000908.02 | A.1000908.02.15 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED | Combabula 400 | SAVANNA DRILLING #406 | J.20.063039 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-16 |  | 2020-02-17 | 2020-02-18 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:05 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1000908 | O.1000908.02 | A.1000908.02.04 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #406 | J.19.060559 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-28 | 2019-10-27 |  | 2019-10-28 | 2019-10-29 |  | 2019-10-29 | Roma WL | VOliveira5 | 2022-10-03 13:05 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1000908 | O.1000908.02 | A.1000908.02.01 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #406 | J.19.060558 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-14 01:00 | 2019-10-14 01:00 |  | 2019-10-14 01:00 | 2019-10-15 01:00 |  | 2020-01-13 | Roma WL | VOliveira5 | 2022-10-03 13:05 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1000908 | O.1000908.02 | A.1000908.02.11 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED | Combabula 400 | SAVANNA DRILLING #406 | J.19.060557 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-08 |  | 2019-12-09 | 2019-12-10 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:05 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1000908 | O.1000908.02 | A.1000908.02.08 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #406 | J.19.060556 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-11-22 | 2019-11-21 |  | 2019-11-22 | 2019-11-23 |  | 2019-11-23 | Roma WL | VOliveira5 | 2022-10-03 13:04 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1000908 | O.1000908.02 | A.1000908.02.05 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #406 | J.19.060555 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-11-04 | 2019-11-03 |  | 2019-11-04 | 2019-11-05 |  | 2019-11-05 | Roma WL | VOliveira5 | 2022-10-03 13:04 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1000908 | O.1000908.02 | A.1000908.02.03 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #406 | J.19.060554 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-22 | 2019-10-21 |  | 2019-10-22 | 2019-10-23 |  | 2019-10-23 | Roma WL | VOliveira5 | 2022-10-03 13:04 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1000908 | O.1000908.02 | A.1000908.02.02 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #406 | J.19.060553 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-17 01:00 | 2019-10-16 01:00 |  | 2019-10-17 01:00 | 2019-10-18 01:00 |  | 2019-10-18 01:00 | Roma WL | VOliveira5 | 2022-10-03 13:04 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1000908 | O.1000908.01 | A.1000908.01.02 | MDT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #406 | J.19.060565 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-26 23:00 | 2019-11-06 23:00 |  | 2019-11-06 23:00 | 2019-11-08 23:00 |  | 2019-10-28 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:06 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1000908 | O.1000908.01 | A.1000908.01.01 | MDT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #406 | J.19.060560 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-10-18 23:00 |  | 2019-10-19 23:00 | 2019-10-21 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:05 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1000908 | O.1000908.01 | A.1000908.01.03 | MDT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #406 | J.19.060552 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2019-10-26 23:00 | 2019-12-02 23:00 |  | 2019-12-02 23:00 | 2019-12-04 23:00 |  | 2019-10-28 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:04 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1000907 | O.1000907.01 | A.1000907.01.01 | WELL 1X 6in | STRIKE ENERGY LIMITED | Reids 1 | Maersk Discoverer | J.19.060551 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-08-26 |  | 2019-08-29 | 2019-08-31 |  |  | Roma WL | RWijaya | 2022-10-03 13:04 | FDPSystemUser |  | No |  |  |  | ROE WL INDIA | Victor Oliveira |  | 117589.34 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services