## Sheet1
Project Number | Operation Number | Ops Activity Number | Ops Activity Name | Customer | Well Names | Rig | SAP WBS # / SO # | Business Line | Job Types | Risk Level | Booking Status | Business Process Status | HADU Assigned | Equipment Status | P&M Status | Personnel Status | Equipment Leave Base | Resources at Dock/Location | Personnel At Site | Est. Ops Activity Start | Est. Ops Activity End | Personnel Leave Site | Equipment Arrive Back to Base | Ops District | Created By | Last Updated | Last Updated By | Integrated Project Number | Is Critical Job | Customer Facility | Maintenance Location | Job Condition | ROC Location | Customer Engagement Coordinator | PBC Job | Forecast Revenue | # UoA: Stages, Runs, Job | Bit Size | RO Operating Level | CDS Order Number | Design Completion % | Prepare Completion % | Execute Completion % | Close Completion % | Ops Activity Completion % | PPP ID | General Instructions | GAC Id | iSTRIDE Status | iSTRIDE Design Number | Initial Forecast Revenue | Illumina Id | ALDDE ID | Revenue Forecast Dashboard | PSD Manager | Sub Business Line
P.1077724 | O.1077724.01 | A.1077724.01.05 | ShaleAID test5 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  |  | J.26.019759 | RPS | STM-MPUMP | Low | Unconfirmed - 10% | Design - CEC |  | Not Started | In Progress | In Progress |  | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-06 23:59 | 2026-07-07 |  | AUS East Coast WS | HLi30 | 2025-11-05 11:08 | HLi30 |  | No |  |  |  |  | Hao Yan Li |  | 0 | 1 |  | L0 - No RO |  | 56.3 | 33.3 | 100 | 25 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Production Services
P.1077724 | O.1077724.01 | A.1077724.01.04 | ShaleAID test4 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  |  | J.26.019758 | RPS | STM-MPUMP | Low | Unconfirmed - 10% | Design - CEC |  | Not Started | In Progress | In Progress |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-23 23:59 | 2026-06-24 |  | AUS East Coast WS | HLi30 | 2025-11-05 11:08 | HLi30 |  | No |  |  |  |  | Hao Yan Li |  | 0 | 1 |  | L0 - No RO |  | 56.3 | 33.3 | 100 | 25 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Production Services
P.1077724 | O.1077724.01 | A.1077724.01.03 | ShaleAID test3 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  |  | J.26.019757 | RPS | STM-MPUMP | Low | Unconfirmed - 10% | Design - CEC |  | Not Started | In Progress | In Progress |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-16 23:59 | 2026-06-17 |  | AUS East Coast WS | HLi30 | 2025-11-05 11:07 | HLi30 |  | No |  |  |  |  | Hao Yan Li |  | 0 | 1 |  | L0 - No RO |  | 56.3 | 33.3 | 100 | 25 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Production Services
P.1077724 | O.1077724.01 | A.1077724.01.02 | ShaleAID test2 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  |  | J.26.019756 | RPS | STM-MPUMP | Low | Unconfirmed - 10% | Design - CEC |  | Not Started | In Progress | In Progress |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-07 23:59 | 2026-06-08 |  | AUS East Coast WS | HLi30 | 2025-11-05 11:07 | HLi30 |  | No |  |  |  |  | Hao Yan Li |  | 0 | 1 |  | L0 - No RO |  | 56.3 | 33.3 | 100 | 25 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Production Services
P.1077724 | O.1077724.01 | A.1077724.01.01 | ShaleAID treatment | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  |  | J.26.019750 | RPS | STM-MPUMP | Low | Unconfirmed - 10% | Design - CEC |  | Not Started | In Progress | In Progress |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-07 23:59 | 2026-05-08 |  | AUS East Coast WS | HLi30 | 2025-11-05 11:04 | HLi30 |  | No |  |  |  |  | Hao Yan Li |  | 0 | 1 |  | L0 - No RO |  | 56.3 | 33.3 | 100 | 25 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Production Services
P.1077615 | O.1077615.01 | A.1077615.01.01 | ENI_BT P5_Rigless | ENI AUSTRALIA B.V. |  |  | J.26.019998 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | Design Completed | 2026-03-01 | 2026-02-28 | 2026-03-01 | 2026-03-01 | 2026-03-21 23:59 | 2026-03-22 | 2026-03-21 23:59 | New Burn WL | MElsanousi | 2025-11-26 10:26 | APutra7 |  | No |  |  |  |  | Edmund Brobbey |  | 0 | 7 |  | L0 - No RO |  | 66.7 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1076618 | O.1076618.01 | A.1076618.01.02 | Pine Creek 2 | WESTSIDE CORPORATION LTD | PINE CREEK 1, PINE CREEK 2 | ENSIGN 958 | J.25.160791 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Not Required | Design Completed | 2023-10-08 11:00 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-12-15 23:59 | 2025-12-16 | 2025-12-15 23:59 | Roma WL | CKok3 | 2025-11-26 16:01 | ESchmidtke |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 6 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 25 | 60 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1076618 | O.1076618.01 | A.1076618.01.01 | Pine Creek 1 | WESTSIDE CORPORATION LTD | PINE CREEK 1, PINE CREEK 2 | ENSIGN 958 | J.25.160763 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-09-22 10:00 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-22 23:59 | 2025-11-23 | 2025-11-22 23:59 | Roma WL | CKok3 | 2025-11-20 20:42 | LDoudilim |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 184535.41 | 6 |  | L2 - Shift RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1076554 | O.1076554.01 | A.1076554.01.01 | Jadestone ¦ Stag-48H ¦ WLPS ¦ CIS | JADESTONE ENERGY (EAGLE) PTY LTD | STAG 48H, STAG 12H | RIGLESS - AUSTRALIA | J.25.159833 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-10-26 | 2025-10-25 | 2025-10-26 | 2025-10-26 | 2025-12-17 23:59 | 2025-12-18 | 2025-12-17 23:59 | New Burn WL | EBrobbey | 2025-11-21 15:15 | WMaung |  | No |  |  |  | ROE WL Mumbai | Edmund Brobbey |  | 247800 | 1 |  | L2 - Shift RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1076040 | O.1076040.01 | A.1076040.01.02 | PER04,02 & AP4,3,2 | WOODSIDE ENERGY LTD |  | TRANSOCEAN ENDURANCE | J.26.013202 | RPI | PS-SLK-Ops | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2026-05-01 |  | 2026-05-01 | 2026-05-22 23:59 |  |  | New Burn WL | KKeese | 2025-09-16 13:23 | KKeese |  | Yes |  |  |  |  | Edmund Brobbey |  | 0 | 0 |  | L0 - No RO |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | Wireline Slickline
P.1076040 | O.1076040.01 | A.1076040.01.01 | TPA03 | WOODSIDE ENERGY LTD |  | TRANSOCEAN ENDURANCE | J.26.013201 | RPI | PS-SLK-Ops | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2026-04-01 |  | 2026-04-01 | 2026-04-22 23:59 |  |  | New Burn WL | KKeese | 2025-09-16 10:37 | KKeese |  | Yes |  |  |  |  | Edmund Brobbey |  | 0 | 0 |  | L0 - No RO |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | Wireline Slickline
P.1075437 | O.1075437.01 | A.1075437.01.01 | PNA AP 04 | WOODSIDE ENERGY LTD |  | TRANSOCEAN ENDURANCE | J.26.012893 | RPI | CT-CEM | High | Confirmed | Design - CEC |  | In Progress | Not Required | In Progress | 2026-02-15 | 2026-04-11 | 2026-04-25 | 2026-04-25 | 2026-05-09 23:59 | 2026-05-10 | 2026-11-30 23:59 | AUS West Coast WS | CNevarez2 | 2025-09-14 19:08 | CNevarez2 |  | Yes |  |  |  |  | Cesar Nevarez Carmona |  | 0 | 1 |  | L0 - No RO |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1075437 | O.1075437.01 | A.1075437.01.02 | PNA AP 03 | WOODSIDE ENERGY LTD |  | TRANSOCEAN ENDURANCE | J.26.012894 | RPI | CT-CEM | High | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2026-05-10 |  | 2026-05-11 | 2026-05-25 23:59 |  |  | AUS West Coast WS | CNevarez2 | 2025-09-11 10:18 | CNevarez2 |  | Yes |  |  |  |  | Cesar Nevarez Carmona |  | 0 | 1 |  | L0 - No RO |  | 12.5 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1075437 | O.1075437.01 | A.1075437.01.03 | PNA AP 02 | WOODSIDE ENERGY LTD |  | TRANSOCEAN ENDURANCE | J.26.012895 | RPI | CT-CEM | High | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2026-05-25 |  | 2026-05-26 | 2026-06-10 23:59 |  |  | AUS West Coast WS | CNevarez2 | 2025-09-11 10:18 | CNevarez2 |  | Yes |  |  |  |  | Cesar Nevarez Carmona |  | 0 | 1 |  | L0 - No RO |  | 6.3 | 0 | 0 | 0 | 2.5 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1075437 | O.1075437.01 | A.1075437.01.04 | PNA PER 04 | WOODSIDE ENERGY LTD |  | TRANSOCEAN ENDURANCE | J.26.012896 | RPI | CT-CEM | High | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2026-06-15 |  | 2026-06-15 | 2026-06-30 23:59 |  |  | AUS West Coast WS | CNevarez2 | 2025-09-11 10:18 | CNevarez2 |  | Yes |  |  |  |  | Cesar Nevarez Carmona |  | 0 | 1 |  | L0 - No RO |  | 6.3 | 0 | 0 | 0 | 2.5 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1075365 | O.1075365.01 | A.1075365.01.01 | Fugro Subsea Sampling | FUGRO AUSTRALIA PTY LTD |  |  | J.25.143807 | RPE | FSA-SF-JOB | Medium | Unconfirmed - 50% | Design - CEC |  | Design Completed | Not Started | Not Started | 2025-10-01 | 2025-09-30 |  | 2025-10-01 | 2025-11-30 23:59 |  | 2025-11-30 23:59 | APG TS | AEl-wakil | 2025-08-27 11:00 | RUrfandez |  | No |  |  |  |  | Ahmed El-Wakil |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Ahmed El-Wakil | TS Downhole Reservoir Testing
P.1075148 | O.1075148.01 | A.1075148.01.01 | Enniskillen 1 | GEOSCIENCE AUSTRALIA (AGSO) | GA ENNISKILLEN 1 | ENSIGN 974 | J.25.141287 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-09-22 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-23 23:59 | 2025-12-05 | 2025-11-23 23:59 | Roma WL | CKok3 | 2025-11-26 09:46 | LKenzhegulova |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 523129.3 | 7 |  | L2 - Shift RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1075147 | O.1075147.01 | A.1075147.01.01 | PNG Offshore Well 1 | TOTALENERGIES EP PNG LIMITED |  | VALARIS 107 | J.25.141275 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2025-12-01 |  | 2025-12-01 | 2025-12-31 23:59 |  |  | Port Moresby WL | CKok3 | 2025-08-20 13:31 | CKok3 |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 0 |  | L0 - No RO |  | 8.3 | 0 | 0 | 0 | 2.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074248 | O.1074248.01 | A.1074248.01.01 | Annulus Inspection | WOODSIDE ENERGY LTD |  |  | J.25.128853 | RPI | PS-WL-Ops | InComplete | Confirmed | Prepare - Mob |  | Not Started | Not Started | Not Started |  | 2025-08-05 |  | 2025-11-22 | 2025-12-12 23:59 |  |  | New Burn WL | ymoradi2 | 2025-10-31 11:09 | KKeese |  | No |  |  |  | ROE WL Mumbai | Yasser Moradi |  | 0 | 0 |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1074004 | O.1074004.13 | A.1074004.13.03 | Origin Adhoc Dec 2026 | AUSTRALIA PACIFIC LNG PTY LTD |  | SLR 168 | J.26.022201 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress |  | 2026-11-25 23:55 |  | 2026-11-26 | 2026-12-26 23:59 |  |  | Roma WL | CKok3 | 2025-11-26 15:29 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 5 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.13 | A.1074004.13.02 | Origin Adhoc Nov 2026 | AUSTRALIA PACIFIC LNG PTY LTD |  | SLR 168 | J.26.022200 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress |  | 2026-10-25 23:55 |  | 2026-10-26 | 2026-11-25 23:59 |  |  | Roma WL | CKok3 | 2025-11-26 15:28 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 5 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.13 | A.1074004.13.01 | Origin Adhoc Oct 2026 | AUSTRALIA PACIFIC LNG PTY LTD |  | SLR 168 | J.26.022199 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress |  | 2026-09-25 23:55 |  | 2026-09-26 | 2026-10-26 23:59 |  |  | Roma WL | CKok3 | 2025-11-26 15:28 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 5 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.12 | A.1074004.12.03 | Origin Adhoc Sep 2026 | AUSTRALIA PACIFIC LNG PTY LTD |  | SLR 168 | J.26.022198 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress |  | 2026-08-25 23:55 |  | 2026-08-26 | 2026-09-25 23:59 |  |  | Roma WL | CKok3 | 2025-11-26 15:27 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 5 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.12 | A.1074004.12.02 | Origin Adhoc Aug 2026 | AUSTRALIA PACIFIC LNG PTY LTD |  | SLR 168 | J.26.022197 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress |  | 2026-07-25 23:55 |  | 2026-07-26 | 2026-08-25 23:59 |  |  | Roma WL | CKok3 | 2025-11-26 15:27 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 5 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.12 | A.1074004.12.01 | Origin Adhoc Jul 2026 | AUSTRALIA PACIFIC LNG PTY LTD |  | SLR 168 | J.26.022196 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress |  | 2026-06-25 23:55 |  | 2026-06-26 | 2026-07-26 23:59 |  |  | Roma WL | CKok3 | 2025-11-26 15:27 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 5 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.11 | A.1074004.11.03 | Origin Adhoc Jun 2026 | AUSTRALIA PACIFIC LNG PTY LTD |  | SLR 168 | J.26.022195 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress |  | 2026-05-25 23:55 |  | 2026-05-26 | 2026-06-25 23:59 |  |  | Roma WL | CKok3 | 2025-11-26 15:26 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 5 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.11 | A.1074004.11.02 | Origin Adhoc May 2026 | AUSTRALIA PACIFIC LNG PTY LTD |  | SLR 168 | J.26.022194 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress |  | 2026-04-25 23:55 |  | 2026-04-26 | 2026-05-26 23:59 |  |  | Roma WL | CKok3 | 2025-11-26 15:25 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 5 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.11 | A.1074004.11.01 | Origin Adhoc Apr 2026 | AUSTRALIA PACIFIC LNG PTY LTD |  | SLR 168 | J.26.022193 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress |  | 2026-03-25 23:55 |  | 2026-03-26 | 2026-04-25 23:59 |  |  | Roma WL | CKok3 | 2025-11-26 15:24 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 5 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.10 | A.1074004.10.03 | Origin Adhoc Mar 2026 | AUSTRALIA PACIFIC LNG PTY LTD |  | SLR 168 | J.26.022192 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress |  | 2026-02-25 23:55 |  | 2026-02-26 | 2026-03-28 23:59 |  |  | Roma WL | CKok3 | 2025-11-26 15:24 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 5 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.10 | A.1074004.10.02 | Origin Adhoc Feb 2026 | AUSTRALIA PACIFIC LNG PTY LTD |  | SLR 168 | J.26.022191 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress |  | 2026-01-25 23:55 |  | 2026-01-26 | 2026-02-25 23:59 |  |  | Roma WL | CKok3 | 2025-11-26 15:23 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 5 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.10 | A.1074004.10.01 | Origin Adhoc Jan 2026 | AUSTRALIA PACIFIC LNG PTY LTD |  | SLR 168 | J.25.181362 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress |  | 2025-12-25 23:55 |  | 2025-12-26 | 2026-01-25 23:59 |  |  | Roma WL | CKok3 | 2025-11-26 15:22 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 5 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.08 | A.1074004.08.03 | Origin Dedicated OH Sep 2026 | AUSTRALIA PACIFIC LNG PTY LTD |  | SAVANNA DRILLING #449 | J.26.022209 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-08-25 14:00 | 2026-08-25 | 2026-08-25 14:00 | 2026-08-26 | 2026-09-23 23:59 | 2026-09-25 13:00 | 2026-09-24 22:59 | Roma WL | CKok3 | 2025-11-26 15:57 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.08 | A.1074004.08.02 | Origin Dedicated OH Aug 2026 | AUSTRALIA PACIFIC LNG PTY LTD |  | SAVANNA DRILLING #449 | J.26.022208 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-07-25 14:00 | 2026-07-25 | 2026-07-25 14:00 | 2026-07-26 | 2026-08-23 23:59 | 2026-08-25 13:00 | 2026-08-24 22:59 | Roma WL | CKok3 | 2025-11-26 15:57 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.08 | A.1074004.08.01 | Origin Dedicated OH Jul 2026 | AUSTRALIA PACIFIC LNG PTY LTD |  | SAVANNA DRILLING #449 | J.26.022207 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-06-25 14:00 | 2026-06-25 | 2026-06-25 14:00 | 2026-06-26 | 2026-07-24 23:59 | 2026-07-26 13:00 | 2026-07-25 22:59 | Roma WL | CKok3 | 2025-11-26 15:57 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.07 | A.1074004.07.03 | Origin Dedicated OH Jun 2026 | AUSTRALIA PACIFIC LNG PTY LTD |  | SAVANNA DRILLING #449 | J.26.022206 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-05-25 14:00 | 2026-05-25 | 2026-05-25 14:00 | 2026-05-26 | 2026-06-23 23:59 | 2026-06-25 13:00 | 2026-06-24 22:59 | Roma WL | CKok3 | 2025-11-26 15:56 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.07 | A.1074004.07.02 | Origin Dedicated OH May 2026 | AUSTRALIA PACIFIC LNG PTY LTD |  | SAVANNA DRILLING #449 | J.26.022205 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-04-25 14:00 | 2026-04-25 | 2026-04-25 14:00 | 2026-04-26 | 2026-05-24 23:59 | 2026-05-26 13:00 | 2026-05-25 22:59 | Roma WL | CKok3 | 2025-11-26 15:56 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.07 | A.1074004.07.01 | Origin Dedicated OH Apr 2026 | AUSTRALIA PACIFIC LNG PTY LTD |  | SAVANNA DRILLING #449 | J.26.022204 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-03-25 14:00 | 2026-03-25 | 2026-03-25 15:00 | 2026-03-26 | 2026-04-23 23:59 | 2026-04-25 13:00 | 2026-04-24 21:59 | Roma WL | CKok3 | 2025-11-26 15:55 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.06 | A.1074004.06.03 | Origin Dedicated OH Mar 2026 | AUSTRALIA PACIFIC LNG PTY LTD |  | SAVANNA DRILLING #449 | J.26.022203 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-02-25 14:00 | 2026-02-25 | 2026-02-25 15:00 | 2026-02-26 | 2026-03-26 23:59 | 2026-03-28 14:00 | 2026-03-27 22:59 | Roma WL | CKok3 | 2025-11-26 15:55 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.06 | A.1074004.06.02 | Origin Dedicated OH Feb 2026 | AUSTRALIA PACIFIC LNG PTY LTD |  | SAVANNA DRILLING #449 | J.26.022202 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-01-25 14:00 | 2026-01-25 | 2026-01-25 15:00 | 2026-01-26 | 2026-02-23 23:59 | 2026-02-25 14:00 | 2026-02-24 22:59 | Roma WL | CKok3 | 2025-11-26 15:54 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.06 | A.1074004.06.01 | Origin Dedicated OH Jan 2026 | AUSTRALIA PACIFIC LNG PTY LTD |  | SAVANNA DRILLING #449 | J.25.181371 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2025-12-25 14:00 | 2025-12-25 | 2025-12-25 15:00 | 2025-12-26 | 2026-01-23 23:59 | 2026-01-25 14:00 | 2026-01-24 22:59 | Roma WL | CKok3 | 2025-11-26 15:54 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.05 | A.1074004.05.04 | Origin Adhoc Nov 2025- No RO | AUSTRALIA PACIFIC LNG PTY LTD | CONDABRI NORTH DEEP 042, CONDABRI NORTH DEEP 211, DALWOGAN DEEP 002 | RIGLESS - AUSTRALIA | J.25.177319 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2025-11-14 | 2025-11-09 23:55 | 2025-11-10 | 2025-11-10 | 2025-12-10 23:59 | 2025-12-11 | 2025-12-10 23:59 | Roma WL | CKok3 | 2025-11-24 17:05 | EKondratiev |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 43352.83 | 4 |  | L3 - Full RO |  | 91.7 | 66.7 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.05 | A.1074004.05.02 | Origin Adhoc Nov 2025 | AUSTRALIA PACIFIC LNG PTY LTD | CONDABRI NORTH DEEP 042, CONDABRI NORTH DEEP 211, DALWOGAN DEEP 002 | RIGLESS - AUSTRALIA | J.25.157843 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-10-31 | 2025-10-26 23:55 | 2025-10-27 | 2025-10-27 | 2025-11-26 23:59 | 2025-11-27 | 2025-11-26 23:59 | Roma WL | CKok3 | 2025-11-21 11:59 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L3 - Full RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.05 | A.1074004.05.01 | Origin Adhoc Oct 2025 | AUSTRALIA PACIFIC LNG PTY LTD | PHS 104, PHS261 | RIGLESS - AUSTRALIA | J.25.157841 | RPE | ES-CH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2025-10-25 | 2025-09-25 23:55 | 2025-10-24 | 2025-10-25 | 2025-11-24 23:59 | 2025-11-25 | 2025-11-24 23:59 | Roma WL | CKok3 | 2025-11-09 19:05 | LDoudilim |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.05 | A.1074004.05.03 | Origin Adhoc Dec 2025 | AUSTRALIA PACIFIC LNG PTY LTD |  | RIGLESS - AUSTRALIA | J.25.157845 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress |  | 2025-11-26 23:55 |  | 2025-11-27 | 2025-12-27 23:59 |  |  | Roma WL | CKok3 | 2025-09-26 16:22 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 5 |  | L2 - Shift RO |  | 41.7 | 33.3 | 0 | 25 | 30 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.04 | A.1074004.04.03 | Peat 448 | AUSTRALIA PACIFIC LNG PTY LTD |  | RIGLESS - AUSTRALIA | J.25.151076 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2025-12-01 |  | 2025-12-01 | 2025-12-03 23:59 |  |  | Roma WL | CKok3 | 2025-10-25 02:06 | CKok3 |  | No |  |  |  |  | Irwan Wongso |  | 0 | 0 |  | L0 - No RO |  | 8.3 | 0 | 0 | 0 | 2.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1074004 | O.1074004.04 | A.1074004.04.02 | Peat 450 | AUSTRALIA PACIFIC LNG PTY LTD |  | RIGLESS - AUSTRALIA | J.25.151075 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-01-10 | 2025-09-29 | 2025-09-29 | 2025-10-05 | 2025-11-03 23:59 | 2025-10-29 01:00 | 2025-11-03 23:59 | Roma WL | CKok3 | 2025-10-25 02:05 | CKok3 |  | No |  |  |  |  | Irwan Wongso |  | 0 | 11 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1074004 | O.1074004.04 | A.1074004.04.01 | Peat 449 | AUSTRALIA PACIFIC LNG PTY LTD |  | RIGLESS - AUSTRALIA | J.25.151074 | RPI | PS-WL-Ops | High | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2024-11-15 | 2025-07-25 | 2025-09-09 | 2025-09-09 | 2025-10-03 23:59 | 2025-10-17 23:00 | 2025-10-03 21:59 | Roma WL | CKok3 | 2025-09-09 16:17 | CKok3 |  | No |  |  |  |  | Irwan Wongso |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1074004 | O.1074004.03 | A.1074004.03.03 | Origin Dedicated OH Dec 2025 | AUSTRALIA PACIFIC LNG PTY LTD | TALINGA 314 | SAVANNA DRILLING #449 | J.25.125549 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | Design Completed | 2025-11-26 14:00 | 2025-11-26 | 2025-11-26 15:00 | 2025-11-27 | 2025-12-25 23:59 | 2025-12-27 14:00 | 2025-12-26 22:59 | Roma WL | CKok3 | 2025-11-28 11:02 | JDagdag |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 25 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.03 | A.1074004.03.02 | Origin Dedicated OH Nov 2025 | AUSTRALIA PACIFIC LNG PTY LTD | ORANA NORTH 366, IB-MB 006, IB-MB 009, ORANA NORTH 025, ORANA NORTH 026, ORANA NORTH 027, ORANA NORTH 028, TALINGA 309, TALINGA 314 | SAVANNA DRILLING #449 | J.25.125548 | RPE | ES-OH-Ops | InComplete | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2025-11-02 14:00 | 2025-11-03 | 2025-11-02 15:00 | 2025-11-03 | 2025-12-01 23:59 | 2025-12-03 14:00 | 2025-12-02 22:59 | Roma WL | CKok3 | 2025-11-27 12:10 | JDagdag |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 70.8 | 78.8 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.03 | A.1074004.03.06 | Origin Dedicated OH Dec 2026 | AUSTRALIA PACIFIC LNG PTY LTD |  | SAVANNA DRILLING #449 | J.26.022212 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-11-25 14:00 | 2026-11-25 | 2026-11-25 15:00 | 2026-11-26 | 2026-12-24 23:59 | 2026-12-26 14:00 | 2026-12-25 22:59 | Roma WL | CKok3 | 2025-11-26 15:59 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.03 | A.1074004.03.05 | Origin Dedicated OH Nov 2026 | AUSTRALIA PACIFIC LNG PTY LTD |  | SAVANNA DRILLING #449 | J.26.022211 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-10-25 14:00 | 2026-10-25 | 2026-10-25 15:00 | 2026-10-26 | 2026-11-23 23:59 | 2026-11-25 14:00 | 2026-11-24 22:59 | Roma WL | CKok3 | 2025-11-26 15:58 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.03 | A.1074004.03.04 | Origin Dedicated OH Oct 2026 | AUSTRALIA PACIFIC LNG PTY LTD |  | SAVANNA DRILLING #449 | J.26.022210 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-09-25 14:00 | 2026-09-25 | 2026-09-25 14:00 | 2026-09-26 | 2026-10-24 23:59 | 2026-10-26 14:00 | 2026-10-25 23:59 | Roma WL | CKok3 | 2025-11-26 15:58 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.03 | A.1074004.03.01 | Origin Dedicated OH Oct 2025 | AUSTRALIA PACIFIC LNG PTY LTD | DURHAM RANCH 864, ORANA NORTH 335, ORANA NORTH 344, ORANA NORTH 357, ORANA NORTH 368, ORN367, ORN356, ORANA NORTH 355, ORANA NORTH 333, ORANA NORTH 365, ORANA NORTH 366 | SAVANNA DRILLING #449 | J.25.125547 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-11-28 11:00 | 2025-09-25 | 2025-09-25 14:00 | 2025-09-26 | 2025-10-31 23:59 | 2025-11-02 14:00 | 2025-05-08 09:59 | Roma WL | CKok3 | 2025-10-28 22:28 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 91.7 | 83.3 | 100 | 100 | 92.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.02 | A.1074004.02.01 | Origin Dedicated OH Aug 2025 | AUSTRALIA PACIFIC LNG PTY LTD | ORN 484, ORN 502, ORN483, DURHAM RANCH 344, DURHAM RANCH 345, DURHAM RANCH 334 | SAVANNA DRILLING #449 | J.25.125543 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-07-25 14:00 | 2025-07-25 | 2025-07-25 14:00 | 2025-07-26 | 2025-08-23 23:59 | 2025-08-25 13:00 | 2025-08-24 22:59 | Roma WL | CKok3 | 2025-10-16 13:51 | ESchmidtke |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 91.7 | 83.3 | 100 | 83.3 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.02 | A.1074004.02.02 | Origin Dedicated OH Sep 2025 | AUSTRALIA PACIFIC LNG PTY LTD | DURHAM RANCH 345, DURHAM RANCH 294, DURHAM RANCH 334, DURHAM RANCH 343, DURHAM RANCH 336 | SAVANNA DRILLING #449 | J.25.125545 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-04-29 23:00 | 2025-08-25 | 2025-08-25 14:00 | 2025-08-26 | 2025-09-23 23:59 | 2025-09-25 13:00 | 2025-09-24 22:59 | Roma WL | CKok3 | 2025-09-26 16:01 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 100 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.01 | A.1074004.01.03 | Origin Adhoc Sep 2025 | AUSTRALIA PACIFIC LNG PTY LTD | CONDABRI NORTH 42, CONDABRI NORTH DEEP 042, DAD 002 | SAVANNA DRILLING #449 | J.25.125540 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-03-13 13:00 | 2025-09-07 23:55 | 2025-09-07 23:00 | 2025-09-08 | 2025-10-08 23:59 | 2025-10-10 | 2025-10-08 23:59 | Roma WL | CKok3 | 2025-10-05 11:58 | SMccauley |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 43352.83 | 5 |  | L2 - Shift RO |  | 91.7 | 100 | 100 | 87.5 | 93.8 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.01 | A.1074004.01.02 | Origin Adhoc Aug 2025 | AUSTRALIA PACIFIC LNG PTY LTD | CONDABRI NORTH DEEP 211, CONDABRI NORTH DEEP 042 | SAVANNA DRILLING #449 | J.25.125539 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-02-12 | 2025-08-07 23:55 | 2025-08-07 | 2025-08-08 | 2025-09-07 23:59 | 2025-09-08 23:00 | 2025-09-07 23:59 | Roma WL | CKok3 | 2025-09-04 10:51 | MEketone |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 4450.94 | 1 |  | L3 - Full RO |  | 91.7 | 83.3 | 100 | 100 | 92.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1074004 | O.1074004.01 | A.1074004.01.01 | Origin Adhoc July 2025 | AUSTRALIA PACIFIC LNG PTY LTD | CONDABRI NORTH DEEP 211 | SAVANNA DRILLING #449 | J.25.125538 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-01-11 | 2025-07-06 23:55 | 2025-07-06 23:00 | 2025-07-07 | 2025-08-06 23:59 | 2025-08-07 23:00 | 2025-08-06 23:59 | Roma WL | CKok3 | 2025-08-12 15:58 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 7667.32 | 5 |  | L2 - Shift RO |  | 91.7 | 66.7 | 100 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1073765 | O.1073765.02 | A.1073765.02.01 | BEL ¦ TW1 ¦ WLPS ¦ Intervention | BEACH ENERGY (OPERATIONS) LTD | THYLACINE WEST 1 | TRANSOCEAN EQUINOX | J.26.012966 | RPI | PS-WL-Ops | High | Confirmed | Design - CEC |  | Design Completed | Not Started | Not Started | 2026-03-15 | 2026-03-01 |  | 2026-03-15 | 2026-04-16 23:59 |  | 2026-04-16 23:59 | New Burn WL | MElsanousi | 2025-11-24 17:49 | EBrobbey |  | No |  |  |  |  | Edmund Brobbey |  | 0 | 6 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1073765 | O.1073765.02 | A.1073765.02.02 | BEL ¦ La Bella 2 ¦ WLPS ¦ Intervention | BEACH ENERGY (OPERATIONS) LTD | LA BELLA 2 | TRANSOCEAN EQUINOX | J.26.013777 | RPI | PS-WL-Ops | High | Confirmed | Design - CEC |  | In Progress | Not Started | Not Started | 2026-04-22 | 2026-04-21 |  | 2026-04-22 | 2026-05-24 23:59 |  | 2026-05-24 23:59 | New Burn WL | EBrobbey | 2025-11-24 13:56 | EBrobbey |  | No |  |  |  |  | Edmund Brobbey |  | 0 | 13 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1073765 | O.1073765.02 | A.1073765.02.04 | BEL ¦ Hercules 1 ¦ WLPS ¦ Intervention | BEACH ENERGY (OPERATIONS) LTD | HERCULES 1 | TRANSOCEAN EQUINOX | J.26.013779 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2026-07-06 |  | 2026-07-07 | 2026-08-08 23:59 |  |  | New Burn WL | EBrobbey | 2025-09-30 17:02 | EBrobbey |  | No |  |  |  |  | Edmund Brobbey |  | 0 | 0 |  | L0 - No RO |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1073765 | O.1073765.02 | A.1073765.02.03 | BEL ¦ Artisan 1 ¦ WLPS ¦ Intervention | BEACH ENERGY (OPERATIONS) LTD | ARTISAN-1 | TRANSOCEAN EQUINOX | J.26.013778 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2026-05-30 |  | 2026-05-31 | 2026-07-02 23:59 |  |  | New Burn WL | EBrobbey | 2025-09-30 17:02 | EBrobbey |  | No |  |  |  |  | Edmund Brobbey |  | 0 | 0 |  | L0 - No RO |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1073765 | O.1073765.01 | A.1073765.01.03 | BEL ¦ TSX Equinox ¦ WLES_8.5in OH_Hercules-1 | BEACH ENERGY (OPERATIONS) LTD | HERCULES 1 | TRANSOCEAN EQUINOX | J.25.122286 | RPE | ES-OH-Ops | High | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2025-08-27 | 2025-08-19 | 2025-08-27 | 2025-08-27 | 2025-10-07 23:59 | 2025-10-08 | 2025-10-07 23:59 | New Burn WL | MElsanousi | 2025-11-18 11:58 | MElsanousi | M.1000384.06.53 | No |  |  |  |  | Edmund Brobbey |  | 540091.5 | 5 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1073765 | O.1073765.01 | A.1073765.01.04 | BEL ¦ TSX Equinox ¦ WLPS EPLG - White IBIS-1 | BEACH ENERGY (OPERATIONS) LTD | WHITE IBIS 1 | TRANSOCEAN EQUINOX | J.25.143786 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2025-10-04 | 2025-10-13 | 2025-10-15 | 2025-10-15 | 2025-11-02 23:59 | 2025-11-03 | 2025-11-02 23:59 | New Burn WL | MElsanousi | 2025-11-12 12:35 | MElsanousi |  | No |  |  |  |  | Edmund Brobbey |  | 228840.25 | 4 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1073765 | O.1073765.01 | A.1073765.01.02 | BEL ¦ TSX Equniox ¦ WLPS EPLG - Thyacline-1 | BEACH ENERGY (OPERATIONS) LTD | THYLACINE-1 | TRANSOCEAN EQUINOX | J.25.122275 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2025-07-29 | 2025-08-07 | 2025-08-09 | 2025-08-09 | 2025-08-27 23:59 | 2025-08-28 | 2025-08-27 23:59 | New Burn WL | MElsanousi | 2025-09-03 12:17 | MElsanousi |  | No |  |  |  |  | Edmund Brobbey |  | 360112.5 | 4 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1073765 | O.1073765.01 | A.1073765.01.01 | BEL ¦ TSX Equinox ¦ WLPS EPLG - Geographe 1 | BEACH ENERGY (OPERATIONS) LTD | GEOGRAPHE-1 | TRANSOCEAN EQUINOX | J.25.122274 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2025-06-28 | 2025-07-01 | 2025-07-09 | 2025-07-20 | 2025-08-16 23:59 | 2025-08-06 | 2025-08-05 23:59 | New Burn WL | MElsanousi | 2025-08-15 20:35 | MBu2 |  | No |  |  |  |  | Edmund Brobbey |  | 446540.5 | 4 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1072420 | O.1072420.02 | A.1072420.02.01 | Amplitude Energy ¦ TSX Equinox ¦ Intervention | AMPLITUDE ENERGY LTD | ELANORA-1ST1 | TRANSOCEAN EQUINOX | J.26.012965 | RPI | PS-WL-Ops | High | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2026-02-20 | 2026-02-15 | 2026-02-20 | 2026-02-20 | 2026-03-01 23:59 | 2026-03-02 | 2026-03-01 23:59 | New Burn WL | MElsanousi | 2025-11-26 13:04 | crowand |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 5 |  | L0 - No RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1072420 | O.1072420.01 | A.1072420.01.01 | Amplitude Energy ¦ TSX Equinox ¦ Elanora-1 | AMPLITUDE ENERGY LTD | ELANORA-1 | TRANSOCEAN EQUINOX | J.25.103333 | RPE | ES-OH-Ops | High | Confirmed | Design - CEC |  | Design Completed | Not Started | In Progress | 2026-01-28 | 2026-01-20 | 2026-01-28 | 2026-01-28 | 2026-04-02 23:59 | 2026-04-03 | 2026-04-02 23:59 | New Burn WL | MElsanousi | 2025-09-19 11:55 | FDPSystemUser |  | No |  |  |  |  | Edmund Brobbey |  | 0 | 6 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1072420 | O.1072420.01 | A.1072420.01.02 | Amplitude Energy ¦ TSX Equinox ¦ Elanora 1 ST1 | AMPLITUDE ENERGY LTD | ELANORA-1ST1 | TRANSOCEAN EQUINOX | J.26.009063 | RPE | ES-OH-Ops | High | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-08-01 | 2026-07-26 | 2026-08-01 | 2026-08-01 | 2026-09-01 23:59 | 2026-09-02 | 2026-09-01 23:59 | New Burn WL | EBrobbey | 2025-09-12 10:39 | MElsanousi |  | No |  |  |  |  | Edmund Brobbey |  | 0 | 6 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1072334 | O.1072334.01 | A.1072334.01.01 | (Transferred) Origin Dedicated OH July 2025 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.25.101963 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-05-24 14:00 | 2025-05-24 | 2025-05-24 14:00 | 2025-05-25 | 2025-06-25 23:59 | 2025-06-24 13:00 | 2025-06-23 22:59 | Port Moresby WL | CKok3 | 2025-05-23 18:00 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Cheryl Kok |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1071946 | O.1071946.01 | A.1071946.01.01 | JULA-J | WOODSIDE ENERGY LTD | JULA-J | TRANSOCEAN ENDURANCE | J.25.096237 | RPS | SMS-OHGP-APS | Medium | Unconfirmed - 90% | Design - CEC |  | Design Completed | Design Completed | In Progress | 2026-08-01 | 2026-08-01 | 2026-08-01 | 2026-08-01 | 2026-08-27 23:59 | 2026-08-28 | 2026-08-27 23:59 | AUS West Coast WS | ISafarli | 2025-05-15 11:46 | radinegara |  | No |  |  |  |  | Ramadhani Adi Negara |  | 0 | 1 |  | L0 - No RO |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Production Services
P.1071713 | O.1071713.01 | A.1071713.01.01 | Sundagas_V247_12.25in OH | SUNDAGAS BANDA UNIPESSOAL, LDA |  | VALARIS 247 | J.25.093316 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Not Started | Not Started | 2025-08-20 | 2025-08-05 |  | 2025-08-20 | 2025-08-31 23:59 |  | 2025-08-31 23:59 | New Burn WL | MElsanousi | 2025-05-24 16:20 | KKeese |  | No |  |  |  |  | Edmund Brobbey |  | 0 | 3 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1070590 | O.1070590.01 | A.1070590.01.01 | BEL ¦ TSX Equinox ¦ WLES ¦ Hercules-1 | BEACH ENERGY LTD | HERCULES 1 | TRANSOCEAN EQUINOX | J.25.089597 | RPE | ES-OH-Ops | High | Cancelled | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-09-25 | 2025-09-19 | 2025-09-25 | 2025-09-25 | 2025-11-16 23:59 | 2025-11-17 | 2025-11-16 23:59 | New Burn WL | EBrobbey | 2025-09-12 11:39 | WMaung | M.1000384.06.53 | No |  |  |  |  | Edmund Brobbey |  | 0 | 4 |  | L0 - No RO |  | 70.8 | 8.3 | 0 | 0 | 23.8 |  | 2 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1070590 | O.1070590.01 | A.1070590.01.03 | BEL ¦ TSX Equinox ¦ WLPS EPLG - Thylacine 1 | BEACH ENERGY LTD |  | TRANSOCEAN EQUINOX | J.25.114677 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2025-07-10 |  | 2025-07-11 | 2025-07-22 23:59 |  |  | New Burn WL | EBrobbey | 2025-07-02 11:32 | MElsanousi |  | No |  |  |  |  | Edmund Brobbey |  | 0 | 3 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1070590 | O.1070590.01 | A.1070590.01.02 | BEL ¦ TSX Equinox ¦ WLPS EPLG - Geographe 1 | BEACH ENERGY LTD | HERCULES 1 | TRANSOCEAN EQUINOX | J.25.092107 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | Design Completed | 2025-06-28 | 2025-06-27 | 2025-06-27 16:00 | 2025-06-28 | 2025-07-09 23:59 | 2025-07-10 | 2025-07-28 23:59 | New Burn WL | MElsanousi | 2025-07-02 09:39 | MElsanousi |  | No |  |  |  |  | Edmund Brobbey |  | 0 | 3 |  | L0 - No RO |  | 66.7 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1070205 | O.1070205.01 | A.1070205.01.02 | Slim Epilogue Tuna Wells | ESSO AUSTRALIA LTD | TUNA A 33P, TUNA A21, TUNA A 15, TUNA A 3A | TUNA | J.25.127201 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-08-31 | 2025-07-18 | 2025-08-25 08:00 | 2025-08-26 | 2025-09-15 23:59 | 2025-09-16 | 2025-09-15 23:59 | New Burn WL | KKeese | 2025-09-18 04:08 | NCandra |  | No |  |  |  |  | Yasser Moradi |  | 0 | 1 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1070205 | O.1070205.01 | A.1070205.01.03 | ESSO Rigless | ESSO AUSTRALIA LTD | TUNA A 33P, TUNA A21, TUNA A 15, TUNA A 3A | TUNA | J.25.143265 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-01-06 | 2025-11-23 | 2025-12-31 08:00 | 2026-01-01 | 2026-03-17 23:59 | 2026-03-18 | 2026-03-17 23:59 | New Burn WL | KKeese | 2025-08-25 14:49 | FDPSystemUser |  | No |  |  |  |  | Edmund Brobbey |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1070205 | O.1070205.01 | A.1070205.01.01 | Slim Epilogue Wells | ESSO AUSTRALIA LTD | BREAM A 4B, KFA A1, W26A, W8B, WKF15 | TUNA | J.25.074217 | RPI | PS-WL-Ops | Medium | Operationally Complete | Execute - PSD |  | Design Completed | Not Required | In Progress | 2025-03-24 | 2025-03-19 | 2025-03-18 08:00 | 2025-03-19 | 2025-05-24 23:59 | 2025-05-25 | 2025-05-24 23:59 | New Burn WL | KKeese | 2025-05-24 15:55 | FDPSystemUser |  | No |  |  |  |  | Yasser Moradi |  | 417550 | 1 |  | L0 - No RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1070123 | O.1070123.01 | A.1070123.01.04 | Muzic Essington-1 | CONOCOPHILLIPS AUSTRALIA SH2 PTY LTD | ESSINGTON 1 | TRANSOCEAN EQUINOX | J.25.100067 | RPE | DDA-WIRELESS-JOB | High | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2025-09-01 | 2025-07-01 | 2025-09-01 | 2025-09-01 | 2025-10-15 23:59 | 2025-10-16 | 2025-10-15 23:59 | APG TS | DMunoz5 | 2025-09-02 14:47 | AEl-wakil |  | No |  | [AUJN-DST] - AU - Jandakot TST |  |  | Ahmed El-Wakil |  | 0 | 1 |  |  |  | 45.8 | 0 | 0 | 0 | 13.8 |  | 0 |  |  |  | 0 |  |  |  | Muhammad Fahd Waseem | TS Downhole Reservoir Testing
P.1070123 | O.1070123.01 | A.1070123.01.01 | DST Essington-1 | CONOCOPHILLIPS AUSTRALIA SH2 PTY LTD | ESSINGTON 1 | TRANSOCEAN EQUINOX | J.25.088430 | RPE | DST-CH-JOB | High | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2025-09-01 | 2025-07-01 | 2025-09-01 | 2025-09-01 | 2025-10-15 23:59 | 2025-10-16 | 2025-10-15 23:59 | APG TS | DMunoz5 | 2025-09-02 14:47 | AEl-wakil |  | Yes |  | [AUJN-DST] - AU - Jandakot TST |  |  | Ahmed El-Wakil |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 11.3 |  | 0 |  |  |  | 0 |  |  |  | Muhammad Fahd Waseem | TS Downhole Reservoir Testing
P.1070123 | O.1070123.01 | A.1070123.01.02 | TCP Essington-1 | CONOCOPHILLIPS AUSTRALIA SH2 PTY LTD | ESSINGTON 1 | TRANSOCEAN EQUINOX | J.25.100066 | RPI | TCP-TEMP-JOB | Medium | Cancelled | Close - PSD |  | Not Started | Design Completed | In Progress |  | 2025-07-01 | 2025-09-01 | 2025-09-01 | 2025-10-15 23:59 | 2025-10-16 |  | APG TS | DMunoz5 | 2025-09-02 14:47 | AEl-wakil |  | No |  |  |  |  | Ahmed El-Wakil |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 11.3 |  | 0 |  |  |  | 0 |  |  |  | Muhammad Fahd Waseem | TCP - Tubing-Conveyed Perforation
P.1070123 | O.1070123.01 | A.1070123.01.03 | RSA Essington-1 | CONOCOPHILLIPS AUSTRALIA SH2 PTY LTD | ESSINGTON 1 | TRANSOCEAN EQUINOX | J.25.100063 | RPE | FSA-CH-JOB | High | Cancelled | Close - PSD |  | Design Completed | Not Started | Not Started | 2025-09-01 | 2025-07-01 |  | 2025-09-01 | 2025-10-15 23:59 |  | 2025-10-15 23:59 | APG TS | DMunoz5 | 2025-06-09 15:37 | AEl-wakil |  | No |  |  |  |  | Ahmed El-Wakil |  | 0 | 1 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Muhammad Fahd Waseem | TS Downhole Reservoir Testing
P.1070118 | O.1070118.01 | A.1070118.01.01 | WARREGO ¦ EP-512 ¦ WLES | WARREGO ENERGY PTY LTD |  | SILVER CITY RIG 24 | J.25.073123 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Not Started | Design Completed | 2025-11-01 | 2025-10-25 | 2025-11-01 | 2025-11-01 | 2026-01-30 23:59 | 2026-01-31 | 2026-03-25 23:59 | New Burn WL | EBrobbey | 2025-09-16 10:58 | EBrobbey |  | No |  |  |  |  | Edmund Brobbey |  | 0 | 5 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1069546 | O.1069546.01 | A.1069546.01.01 | Non HC Intervention | SHELL AUSTRALIA PTY LTD. |  |  | J.26.002031 | RPI | PS-WL-Ops | High | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2024-08-07 | 2026-03-01 | 2026-04-03 | 2026-04-03 | 2026-04-29 23:59 | 2026-04-30 | 2026-04-29 23:59 | New Burn WL | ymoradi2 | 2025-09-19 13:54 | KKeese |  | Yes |  |  |  |  | Yasser Moradi |  | 0 | 4 |  | L0 - No RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1069123 | O.1069123.01 | A.1069123.01.01 | KP ¦ BECOS-1 ¦ WLES | KEY PETROLEUM (AUST) PTY LTD (L7) | BECOS 1 | SILVER CITY RIG 24 | J.25.064322 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-04-18 | 2025-04-01 | 2025-04-18 | 2025-04-18 | 2025-04-25 23:59 | 2025-04-26 | 2025-04-25 23:59 | New Burn WL | EBrobbey | 2025-05-26 09:03 | MElsanousi |  | No |  |  |  | ROE WL Mumbai | Edmund Brobbey |  | 210756.99 | 3 |  | L3 - Full RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1069095 | O.1069095.01 | A.1069095.01.03 | AJ Lucas Surat Basin Well 1 | AJ LUCAS SERVICES PTY LTD |  | VENTIA 33 | J.25.102029 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | Not Started | 2025-11-01 01:00 | 2025-11-01 |  | 2025-11-01 | 2025-11-18 23:59 |  | 2025-11-19 00:59 | Roma WL | CKok3 | 2025-08-20 13:58 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1069095 | O.1069095.01 | A.1069095.01.01 | Surat Basin Well 1 | AJ LUCAS SERVICES PTY LTD |  | VENTIA 33 | J.25.057271 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | Not Started | 2025-06-01 01:00 | 2025-06-01 |  | 2025-06-01 | 2025-06-18 23:59 |  | 2025-06-19 00:59 | Roma WL | JEsmeralda | 2025-05-23 19:17 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 3 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1069095 | O.1069095.01 | A.1069095.01.02 | Surat Basin Well 2 | AJ LUCAS SERVICES PTY LTD |  | VENTIA 33 | J.25.059710 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | Not Started | 2025-07-02 | 2025-07-02 |  | 2025-07-02 | 2025-07-19 23:59 |  | 2025-07-20 01:59 | Roma WL | CKok3 | 2025-05-16 08:46 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1069094 | O.1069094.01 | A.1069094.01.04 | Killanoola-2 | CONDOR ENERGY SERVICES LTD | WILSON RIVER 1, KILLANOOLA 2 | CONDOR RIG 1 | J.25.102026 | RPE | ES-OH-Ops | InComplete | Confirmed | Prepare - TLM/OP |  | Design Completed | Not Required | Design Completed | 2025-07-30 01:00 | 2025-10-20 | 2025-07-30 | 2025-10-28 | 2025-11-15 23:59 | 2025-11-16 | 2025-08-20 00:59 | Roma WL | CKok3 | 2025-11-04 17:06 | SMccauley |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 151517.48 | 1 |  | L3 - Full RO |  | 100 | 83.3 | 0 | 50 | 70 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1069094 | O.1069094.01 | A.1069094.01.05 | Tasmania Project | CONDOR ENERGY SERVICES LTD | WILSON RIVER 1 | CONDOR RIG 1 | J.25.102027 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2025-11-30 | 2025-12-01 | 2025-11-30 22:00 | 2025-12-01 | 2025-12-09 23:59 | 2025-12-09 23:00 | 2025-12-10 23:59 | Roma WL | CKok3 | 2025-08-20 13:59 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 2 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1069094 | O.1069094.01 | A.1069094.01.02 | Wilson River-1 CH | CONDOR ENERGY SERVICES LTD | WILSON RIVER 1 | CONDOR RIG 1 | J.25.087849 | RPE | ES-CH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-15 23:59 | 2025-05-16 | 2025-05-15 23:59 | Roma WL | JEsmeralda | 2025-05-28 20:40 | YN |  | No |  |  |  |  | Irwan Wongso |  | 0 | 1 |  | L0 - No RO |  | 75 | 66.7 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1069094 | O.1069094.01 | A.1069094.01.03 | Penola Project (SA) | CONDOR ENERGY SERVICES LTD | WILSON RIVER 1 | CONDOR RIG 1 | J.25.102025 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2025-07-07 01:00 | 2025-07-08 | 2025-07-07 23:00 | 2025-07-08 | 2025-07-16 23:59 | 2025-07-17 | 2025-07-18 00:59 | Roma WL | CKok3 | 2025-05-23 19:06 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1069094 | O.1069094.01 | A.1069094.01.01 | Condor Eromanga Exploration Well | CONDOR ENERGY SERVICES LTD | WILSON RIVER 1 | CONDOR RIG 1 | J.25.057263 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2025-03-16 01:00 | 2025-03-17 |  | 2025-03-17 | 2025-03-25 23:59 |  | 2025-03-27 00:59 | Roma WL | JEsmeralda | 2025-03-21 20:05 | ysaeedabadian |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 92917.48 | 1 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1068929 | O.1068929.01 | A.1068929.01.01 | WHEATSTONE DEEP-1¦ 8.5"¦ CVX¦ NOBLE APEX | CHEVRON APG ABU PERTH. | WHEATSTONE DEEP-1 | OCEAN APEX | J.25.055543 | RPE | ES-OH-Ops | High | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2025-06-30 16:00 | 2025-06-25 | 2025-07-06 | 2025-06-26 | 2025-07-05 | 2025-08-07 | 2025-07-06 15:59 | New Burn WL | KKeese | 2025-08-28 12:52 | NCandra |  | No |  |  |  |  | Edmund Brobbey |  | 241906.5 | 5 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 2 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1068929 | O.1068929.01 | A.1068929.01.02 | DINO SOUTH-1¦ CVX ¦ NOBLE APEX | CHEVRON APG ABU PERTH. | DINO SOUTH-1 | OCEAN APEX | J.25.055792 | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-11-24 16:00 | 2025-06-15 16:00 | 2025-07-05 | 2025-07-29 08:00 | 2025-09-29 08:00 | 2025-09-30 | 2026-02-23 15:59 | New Burn WL | EBrobbey | 2025-08-10 13:57 | AHermawan |  | Yes |  |  |  | ROE WL Mumbai | Edmund Brobbey |  | 869424.29 | 5 |  | L1 - Support RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 4 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1068929 | O.1068929.01 | A.1068929.01.03 | WHEATSTONE DEEP-1¦ 12.25"¦ CVX¦ NOBEL APEX | CHEVRON APG ABU PERTH. | WHEATSTONE DEEP-1 | OCEAN APEX | J.25.110526 | RPE | ES-OH-Ops | High | Cancelled | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-06-13 | 2025-06-10 | 2025-06-13 | 2025-06-13 | 2025-06-21 23:59 | 2025-06-22 | 2025-06-21 23:59 | New Burn WL | WMaung | 2025-07-06 12:58 | WMaung |  | No |  |  |  |  | Edmund Brobbey |  | 0 | 2 |  | L0 - No RO |  | 83.3 | 66.7 | 0 | 0 | 45 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1068871 | O.1068871.01 | A.1068871.01.01 | Esso Hides F2 TCP | EXXONMOBIL PNG LIMITED | HIDES F2 | NABORS 702 | J.25.073023 | RPI | TCP-PERM-JOB | High | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2025-03-20 |  | 2025-03-20 | 2025-04-05 23:59 |  |  | Port Moresby TS | ZGao2 | 2025-03-21 12:06 | MWaseem2 |  | Yes |  | [PGPM-TCP] - PGPOM-TCPF |  |  | Zhong Wei Gao |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Muhammad Fahd Waseem | TCP - Tubing-Conveyed Perforation
P.1068821 | O.1068821.01 | A.1068821.01.04 | Woodside Endurance PLACEHOLDER | WOODSIDE ENERGY GLOBAL PTY LTD | MINERVA-1, MINERVA-3, MINERVA-4 | TRANSOCEAN EQUINOX | J.25.143271 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-01-01 | 2025-12-19 | 2026-01-01 | 2026-01-01 | 2026-03-18 23:59 | 2026-03-19 | 2026-03-18 23:59 | New Burn WL | KKeese | 2025-08-25 14:54 | FDPSystemUser |  | No |  |  |  |  | Edmund Brobbey |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1068821 | O.1068821.01 | A.1068821.01.02 | Minerva 3 | WOODSIDE ENERGY GLOBAL PTY LTD | MINERVA-1, MINERVA-3, MINERVA-4 | TRANSOCEAN EQUINOX | J.25.102766 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-06-08 | 2025-05-26 | 2025-06-08 | 2025-06-08 | 2025-06-22 23:59 | 2025-06-23 | 2025-06-22 23:59 | New Burn WL | KKeese | 2025-06-23 14:17 | MRahadian3 |  | No |  |  |  |  | Edmund Brobbey |  | 117183 | 3 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1068821 | O.1068821.01 | A.1068821.01.03 | Minerva-3 Interwell DECT CBL | WOODSIDE ENERGY GLOBAL PTY LTD | MINERVA-3 | TRANSOCEAN EQUINOX | J.25.107812 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2025-05-19 |  | 2025-06-02 | 2025-08-14 23:59 |  |  | New Burn WL | crowand | 2025-06-02 14:05 | KKeese |  | No |  |  |  |  | Edmund Brobbey |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1068821 | O.1068821.01 | A.1068821.01.01 | Minerva 1, 3 & 4 | WOODSIDE ENERGY GLOBAL PTY LTD | MINERVA-1, MINERVA-3, MINERVA-4 | TRANSOCEAN EQUINOX | J.25.055012 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2025-03-15 | 2025-03-01 | 2025-03-14 16:00 | 2025-03-15 | 2025-05-27 23:59 | 2025-05-28 | 2025-05-27 23:59 | New Burn WL | KKeese | 2025-05-27 13:56 | KKeese |  | No |  |  |  |  | Edmund Brobbey |  | 151066.92 | 3 |  | L0 - No RO |  | 100 | 100 | 0 | 100 | 90 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1068359 | O.1068359.01 | A.1068359.01.01 | ConocoPhillips ¦ TSX Equinox ¦ WLES ¦ Essington-1 | CONOCOPHILLIPS AUSTRALIA SH2 PTY LTD | ESSINGTON 1 | TRANSOCEAN EQUINOX | J.25.049681 | RPE | ES-OH-Ops | High | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2025-11-01 | 2025-10-27 | 2025-11-04 | 2025-11-01 | 2025-12-02 23:59 | 2025-12-06 | 2025-12-02 23:59 | New Burn WL | MElsanousi | 2025-11-30 16:39 | APutra7 | M.1000384.08.53 | Yes |  |  |  | ROE WL Mumbai | Edmund Brobbey |  | 5704624.25 | 7 |  | L2 - Shift RO |  | 100 | 100 | 0 | 62.5 | 78.8 |  | 3 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1068359 | O.1068359.01 | A.1068359.01.03 | ConocoPhillips ¦ TSX Equinox ¦ WLES ¦ Charlemont-1 | CONOCOPHILLIPS AUSTRALIA SH2 PTY LTD | CHARLEMONT 1 | TRANSOCEAN EQUINOX | J.25.138500 | RPE | ES-OH-Ops | High | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2025-12-10 | 2025-12-05 | 2025-12-10 | 2025-12-10 | 2026-01-10 23:59 | 2026-01-11 | 2026-01-10 23:59 | New Burn WL | EBrobbey | 2025-08-26 10:16 | MElsanousi |  | No |  |  |  |  | Edmund Brobbey |  | 0 | 7 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 2 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1068359 | O.1068359.01 | A.1068359.01.02 | ConocoPhillips ¦ TSX Equinox ¦ WLES ¦ Charlemont-1 | CONOCOPHILLIPS AUSTRALIA SH2 PTY LTD | CHARLEMONT 1 | TRANSOCEAN EQUINOX | J.25.101827 | RPE | ES-OH-Ops | High | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2025-11-12 | 2025-11-07 | 2025-11-12 | 2025-11-12 | 2025-12-13 23:59 | 2025-11-13 | 2025-11-12 23:59 | New Burn WL | MElsanousi | 2025-08-13 13:27 | EBrobbey |  | No |  |  |  |  | Edmund Brobbey |  | 0 | 6 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 2 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1065903 | O.1065903.01 | A.1065903.01.05 | Q1 Chevron Epilogue Activity | CHEVRON APG ABU PERTH. |  | VENTIA 19 | J.25.143260 | RPI | PS-WL-Ops | High | Confirmed | Design - CEC |  | Design Completed | Not Started | Not Started | 2026-01-01 | 2025-12-26 |  | 2026-01-01 | 2026-03-28 23:59 |  | 2026-03-28 23:59 | New Burn WL | KKeese | 2025-11-28 08:44 | KKeese |  | Yes |  |  |  | ROE WL Mumbai | Edmund Brobbey |  | 0 |  |  | L1 - Support RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Kelly Keese | WL Production Services
P.1065903 | O.1065903.01 | A.1065903.01.06 | Slotted Casing Std Epilogue | CHEVRON APG ABU PERTH. | B31A, B41A, E14, G34A, J46, M86 | VENTIA 19 | J.25.151402 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-11-08 | 2025-09-02 | 2025-09-12 | 2025-09-12 | 2025-10-19 23:59 | 2025-10-20 | 2024-12-06 23:59 | New Burn WL | KKeese | 2025-10-09 16:14 | KKeese |  | No |  |  |  |  | Edmund Brobbey |  | 1118724 | 2 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1065903 | O.1065903.01 | A.1065903.01.03 | Slim Epilogue Q4 activity | CHEVRON APG ABU PERTH. |  | VENTIA 19 | J.25.103386 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2025-09-25 |  | 2025-10-01 | 2025-10-16 23:59 |  |  | New Burn WL | KKeese | 2025-09-09 17:06 | KKeese |  | Yes |  |  |  | ROE WL Mumbai | Edmund Brobbey |  | 0 | 0 |  | L1 - Support RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1065903 | O.1065903.01 | A.1065903.01.02 | Q3 Activity | CHEVRON APG ABU PERTH. |  | VENTIA 19 | J.25.102466 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2025-07-26 |  | 2025-07-01 | 2025-08-18 23:59 |  |  | New Burn WL | KKeese | 2025-09-09 17:03 | KKeese |  | Yes |  |  |  | ROE WL Mumbai | Edmund Brobbey |  | 0 |  |  | L1 - Support RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 2 | [7 empty] | Kelly Keese | WL Production Services
P.1065903 | O.1065903.01 | A.1065903.01.04 | Std Epilogue Wells | CHEVRON APG ABU PERTH. | F61A, Q16, Q76, Q87A, K66, E33A, G15A, G12A, G16A, G21A, H78A, G54A, K61, L18A, L66, P81, L28A, Q65A, Q87 | VENTIA 19 | J.25.130986 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-09-27 | 2025-07-22 | 2025-08-01 | 2025-08-01 | 2025-09-07 23:59 | 2025-09-08 | 2024-10-25 23:59 | New Burn WL | KKeese | 2025-09-05 14:35 | WMaung |  | No |  |  |  | ROE WL Mumbai | Edmund Brobbey |  | 1329178 | 2 |  | L2 - Shift RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1065903 | O.1065903.01 | A.1065903.01.01 | Validation Ops 1 | CHEVRON APG ABU PERTH. | F61A, Q16, Q76, Q87A, K66 | VENTIA 19 | J.25.092838 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-06-11 | 2025-06-01 | 2025-06-11 | 2025-06-11 | 2025-07-18 23:59 | 2025-07-19 | 2025-07-18 23:59 | New Burn WL | JSedmak | 2025-07-31 10:12 | CClark9 |  | No |  |  |  |  | Edmund Brobbey |  | 965057 | 2 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1065473 | O.1065473.01 | A.1065473.01.01 | P&A Wells | STRIKE ENERGY LIMITED |  |  | J.25.026340 | RPI | PS-WL-Ops | Low | Unconfirmed - 50% | Design - CEC |  | Not Started | Not Started | Not Started |  | 2025-01-31 |  | 2025-01-31 | 2025-02-06 23:59 |  |  | Roma WL | JEsmeralda | 2024-11-25 12:07 | FDPSystemUser |  | No |  |  |  |  | Irwan Wongso |  | 0 | 0 |  | L0 - No RO |  | 8.3 | 0 | 0 | 0 | 2.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1065036 | O.1065036.01 | A.1065036.01.01 | RST Gas Annulus Logging | WOODSIDE ENERGY JULIMAR PTY LTD |  |  | J.25.026943 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2025-06-07 | 2025-04-13 | 2025-06-07 | 2025-06-07 | 2025-07-05 23:59 | 2025-07-06 | 2025-07-05 23:59 | New Burn WL | MElsanousi | 2025-05-31 14:52 | KKeese |  | Yes |  |  |  | ROE WL Mumbai | Jarrod Sedmak |  | 0 | 2 |  | L3 - Full RO |  | 58.3 | 33.3 | 0 | 0 | 27.5 |  | 3 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1064651 | O.1064651.01 | A.1064651.01.01 | Tillbrook-11 OH | AIRLIE ENERGY PTY LTD | TILBROOK 11 | SILVER CITY RIG 24 | J.24.179693 | RPE | ES-CH-Ops | High | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2024-11-18 | 2024-11-12 |  | 2024-11-18 | 2024-11-23 23:59 |  | 2024-11-23 23:59 | Roma WL | JEsmeralda | 2024-12-07 14:11 | ESchmidtke |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 184470.44 | 3 |  | L3 - Full RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1064323 | O.1064323.01 | A.1064323.01.06 | Crux CIRP operations | SHELL AUSTRALIA PTY LTD. | CRUX C1 | RIGLESS - AUSTRALIA | J.26.013285 | RPI | TCP-TEMP-JOB | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-04-01 | 2026-01-01 | 2026-06-01 | 2026-04-01 | 2026-06-30 23:59 | 2026-09-02 | 2026-06-30 23:59 | APG TS | EKondratiev | 2025-09-19 13:49 | AEl-wakil |  | Yes |  |  |  |  | Evgeniy Kondratiev |  | 0 | 8 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Muhammad Fahd Waseem | TCP - Tubing-Conveyed Perforation
P.1064323 | O.1064323.01 | A.1064323.01.03 | TCP Crux | SHELL AUSTRALIA PTY LTD. |  | RIGLESS - AUSTRALIA | J.25.155064 | RPI | TCP-NON-OP | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2025-06-29 |  | 2025-06-29 | 2025-09-26 23:59 |  |  | APG TS | EKondratiev | 2025-09-19 13:28 | AEl-wakil |  | Yes |  |  |  |  | Evgeniy Kondratiev |  | 0 | 5 |  |  |  | 25 | 33.3 | 100 | 50 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Muhammad Fahd Waseem | TCP - Tubing-Conveyed Perforation
P.1064323 | O.1064323.01 | A.1064323.01.02 | TCP Crux | SHELL AUSTRALIA PTY LTD. |  | RIGLESS - AUSTRALIA | J.25.104077 | RPI | TCP-NON-OP | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2025-05-01 |  | 2025-05-01 | 2025-07-01 23:59 |  |  | APG TS | EKondratiev | 2025-05-27 17:45 | ABorkin |  | No |  |  |  |  | Evgeniy Kondratiev |  | 0 | 5 |  |  |  | 33.3 | 33.3 | 100 | 50 | 45 |  | 1 |  |  |  | 0 |  |  |  | Muhammad Fahd Waseem | TCP - Tubing-Conveyed Perforation
P.1064323 | O.1064323.01 | A.1064323.01.01 | TCP Crux | SHELL AUSTRALIA PTY LTD. |  | RIGLESS - AUSTRALIA | J.25.020416 | RPI | TCP-NO-OP | Medium | Unconfirmed - 90% | Design - CEC |  | Not Started | Not Started | Not Started |  | 2025-02-01 |  | 2025-02-01 | 2025-05-02 23:59 |  |  | APG TS | EKondratiev | 2025-02-26 21:30 | MWaseem2 |  | Yes |  |  |  |  | Evgeniy Kondratiev |  | 0 | 1 |  |  |  | 25 | 33.3 | 100 | 50 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1064323 | O.1064323.01 | A.1064323.01.05 | TCP Crux | SHELL AUSTRALIA PTY LTD. |  | RIGLESS - AUSTRALIA |  | RPI | TCP-NON-OP | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2025-12-26 |  | 2025-12-26 | 2026-03-25 23:59 |  |  | APG TS | EKondratiev | 2025-02-20 12:20 | EKondratiev |  | No |  |  |  |  | Evgeniy Kondratiev |  | 0 | 5 |  |  |  | 25 | 33.3 | 100 | 50 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Muhammad Fahd Waseem | TCP - Tubing-Conveyed Perforation
P.1064323 | O.1064323.01 | A.1064323.01.04 | TCP Crux | SHELL AUSTRALIA PTY LTD. |  | RIGLESS - AUSTRALIA |  | RPI | TCP-NON-OP | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2025-09-27 |  | 2025-09-27 | 2025-12-25 23:59 |  |  | APG TS | EKondratiev | 2025-02-20 12:20 | EKondratiev |  | No |  |  |  |  | Evgeniy Kondratiev |  | 0 | 5 |  |  |  | 25 | 33.3 | 100 | 50 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Muhammad Fahd Waseem | TCP - Tubing-Conveyed Perforation
P.1064319 | O.1064319.01 | A.1064319.01.01 | TCP Operations | LOCHARD ENERGY (IONA OPERATIONS) TRUST |  | RIGLESS - AUSTRALIA | J.25.020410 | RPI | TCP-PERM-JOB | Medium | Unconfirmed - 10% | Design - CEC |  | Not Started | Not Started | In Progress |  | 2025-01-01 | 2025-05-25 | 2025-05-25 | 2025-06-24 23:59 | 2025-06-25 |  | APG TS | EKondratiev | 2025-06-27 17:30 | AEl-wakil |  | No |  |  |  |  | Muhammad Fahd Waseem |  | 0 | 1 |  |  |  | 25 | 16.7 | 0 | 0 | 12.5 |  | 3 |  |  |  | 0 |  |  |  | Muhammad Fahd Waseem | TCP - Tubing-Conveyed Perforation
P.1064318 | O.1064318.01 | A.1064318.01.02 | Inpex LABR stuff | INPEX OPERATIONS AUSTRALIA PTY LTD |  | VALARIS 247 | J.25.101270 | RPE | SRLR-NON-OP | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2025-09-15 |  | 2025-09-15 | 2025-12-14 23:59 |  |  | APG TS | MWaseem2 | 2025-05-22 12:11 | MWaseem2 |  | No |  |  |  |  | Ahmed El-Wakil |  | 0 | 1 |  |  |  | 33.3 | 33.3 | 100 | 50 | 45 |  | 0 |  |  |  | 0 |  |  |  | Muhammad Fahd Waseem | TS Laboratories
P.1064318 | O.1064318.01 | A.1064318.01.01 | Sampling operations | INPEX OPERATIONS AUSTRALIA PTY LTD |  | VALARIS 247 | J.25.020409 | RPE | FSA-SF-JOB | High | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2025-01-01 |  | 2025-05-25 | 2025-06-24 23:59 |  |  | APG TS | EKondratiev | 2025-03-28 09:23 | MWaseem2 |  | No |  | [AUJN-FSA] - AU - Jandakot OLP |  |  | Evgeniy Kondratiev |  | 0 | 1 |  |  |  | 16.7 | 0 | 0 | 0 | 5 |  | 1 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Downhole Reservoir Testing
P.1064301 | O.1064301.01 | A.1064301.01.03 | Skua-11 ST1_V247 Contingency | JADESTONE ENERGY (EAGLE) PTY LTD | SKUA11 ST1 | VALARIS 247 | J.25.095640 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2025-07-20 | 2025-07-03 | 2025-07-20 | 2025-07-20 | 2025-09-17 23:59 | 2025-09-18 | 2025-09-17 23:59 | New Burn WL | WMaung | 2025-08-22 09:52 | MElsanousi |  | No |  |  |  |  | Edmund Brobbey |  | 1777916.86 | 3 |  | L0 - No RO |  | 100 | 100 | 100 | 75 | 92.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1064301 | O.1064301.01 | A.1064301.01.04 | Skua-11_V247_ST1 P&A | JADESTONE ENERGY (EAGLE) PTY LTD | SKUA11 ST1 | VALARIS 247 | J.25.121640 | RPI | PS-SLK-Rental-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-06-17 | 2025-07-01 | 2025-06-14 | 2025-07-07 | 2025-08-15 23:59 | 2025-09-02 | 2025-08-15 23:59 | New Burn WL | MElsanousi | 2025-07-21 19:37 | VQuoc |  | No |  |  |  |  | Edmund Brobbey |  | 0 | 2 |  | L0 - No RO |  | 83.3 | 100 | 100 | 75 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1064301 | O.1064301.01 | A.1064301.01.02 | Skua-11_V247_P&A SLK | JADESTONE ENERGY (EAGLE) PTY LTD | SKUA11 ST1 | VALARIS 247 | J.25.059680 | RPI | PS-SLK-Rental-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2025-03-18 | 2025-04-01 | 2025-03-15 | 2025-04-07 | 2025-07-03 23:59 | 2025-07-04 | 2025-07-03 23:59 | New Burn WL | MElsanousi | 2025-07-01 11:35 | VQuoc |  | No |  |  |  |  | Ihab Wahbi |  | 0 | 2 |  | L0 - No RO |  | 75 | 100 | 0 | 50 | 67.5 |  | 2 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1064301 | O.1064301.01 | A.1064301.01.01 | Skua-11_V247 P&A | JADESTONE ENERGY (EAGLE) PTY LTD | SKUA11 ST1 | VALARIS 247 | J.25.020336 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-11-28 | 2025-03-01 | 2025-04-19 | 2025-04-21 | 2025-06-19 23:59 | 2025-07-12 | 2025-06-10 23:59 | New Burn WL | MElsanousi | 2025-05-12 07:55 | APutra7 |  | No |  |  |  |  | Ihab Wahbi |  | 430404.27 | 4 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 4 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1064022 | O.1064022.01 | A.1064022.01.01 | Crux-5 | SHELL AUSTRALIA PTY LTD. | CRUX C5 ST1 |  | J.26.000911 | RPI | CT-ACT-PERF,CT-ACT-FISHING,CT-ACT-LIFT | High | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2026-04-01 | 2025-12-01 | 2026-04-01 | 2026-04-01 | 2026-04-30 23:59 | 2026-05-01 | 2026-04-30 23:59 | AUS West Coast WS | CNevarez2 | 2025-09-11 11:58 | JPazzi |  | Yes |  |  |  |  | Jorge Pazzi |  | 0 | 2 |  | L0 - No RO |  | 46.9 | 8.3 | 0 | 0 | 21.3 |  | 3 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1064022 | O.1064022.01 | A.1064022.01.09 | Crux-4 | SHELL AUSTRALIA PTY LTD. | CRUX C4 |  | J.26.005422 | RPI | CT-ACT-PERF,CT-ACT-FISHING | High | Confirmed | Design - CEC |  | Not Started | In Progress | Not Started |  | 2026-07-01 |  | 2026-07-01 | 2026-07-31 23:59 |  |  | AUS West Coast WS | JPazzi | 2025-09-11 11:10 | JPazzi |  | Yes |  |  |  |  | Jorge Pazzi |  | 0 | 2 |  | L0 - No RO |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 4 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1064022 | O.1064022.01 | A.1064022.01.10 | Crux-3 | SHELL AUSTRALIA PTY LTD. | CRUX C3 |  | J.26.005423 | RPI | CT-ACT-PERF,CT-ACT-FISHING | High | Confirmed | Design - CEC |  | Not Started | In Progress | Not Started |  | 2026-08-01 |  | 2026-08-01 | 2026-08-31 23:59 |  |  | AUS West Coast WS | JPazzi | 2025-09-11 11:10 | JPazzi |  | Yes |  |  |  |  | Jorge Pazzi |  | 0 | 2 |  | L0 - No RO |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 4 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1064022 | O.1064022.01 | A.1064022.01.11 | Crux-1 | SHELL AUSTRALIA PTY LTD. | CRUX C1 |  | J.26.002372 | RPI | CT-ACT-PERF,CT-ACT-FISHING | High | Confirmed | Design - CEC |  | Not Started | In Progress | Not Started |  | 2026-09-01 |  | 2026-09-01 | 2026-10-31 23:59 |  |  | AUS West Coast WS | JPazzi | 2025-09-11 11:10 | JPazzi |  | Yes |  |  |  |  | Jorge Pazzi |  | 0 | 2 |  | L0 - No RO |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 2 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1064022 | O.1064022.01 | A.1064022.01.08 | Crux-7 | SHELL AUSTRALIA PTY LTD. | CRUX C7 |  | J.26.005421 | RPI | CT-ACT-PERF,CT-ACT-FISHING | High | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-06-30 23:59 | 2026-07-01 | 2026-06-30 23:59 | AUS West Coast WS | JPazzi | 2025-09-11 11:10 | JPazzi |  | Yes |  |  |  |  | Jorge Pazzi |  | 0 | 3 |  | L0 - No RO |  | 46.9 | 8.3 | 0 | 0 | 21.3 |  | 3 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1064022 | O.1064022.01 | A.1064022.01.05 | DESC Charges prior project execution | SHELL AUSTRALIA PTY LTD. | CRUX C1 |  |  | RPI | CT-NONSERV | Low | Confirmed | Design - CEC |  | Not Started | In Progress | Not Started |  | 2025-08-01 |  | 2025-08-01 | 2025-10-30 23:59 |  |  | AUS West Coast WS | JPazzi | 2025-07-24 15:40 | JPazzi |  | No |  |  |  |  | Jorge Pazzi |  | 41150 | 0 |  | L0 - No RO |  | 68.8 | 33.3 | 100 | 25 | 52.5 |  | 1 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1064022 | O.1064022.01 | A.1064022.01.03 | DESC Charges prior project execution | SHELL AUSTRALIA PTY LTD. |  |  | J.25.079567 | RPI | CT-NONSERV | Low | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2025-01-31 |  | 2025-01-31 | 2025-05-01 23:59 |  |  | AUS West Coast WS | JPazzi | 2025-05-28 14:21 | CNevarez2 |  | No |  |  |  |  | Jorge Pazzi |  | 0 | 1 |  | L0 - No RO |  | 50 | 33.3 | 100 | 25 | 45 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1064022 | O.1064022.01 | A.1064022.01.04 | DESC Charge prior project execution | SHELL AUSTRALIA PTY LTD. |  |  | J.25.104836 | RPI | CT-NONSERV | Low | Cancelled | Close - PSD |  | Not Started | Not Required | In Progress |  | 2025-05-02 | 2025-05-02 | 2025-05-02 | 2025-07-31 23:59 | 2025-08-01 |  | AUS West Coast WS | JPazzi | 2025-05-28 14:20 | FDPSystemUser |  | No |  |  |  |  | Jorge Pazzi |  | 0 | 1 |  | L0 - No RO |  | 68.8 | 33.3 | 100 | 25 | 52.5 |  | 2 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1064022 | O.1064022.01 | A.1064022.01.07 | DESC Charges prior project execution | SHELL AUSTRALIA PTY LTD. |  |  |  | RPI | CT-NONSERV | Low | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2026-01-30 |  | 2026-01-30 | 2026-04-30 23:59 |  |  | AUS West Coast WS | JPazzi | 2024-10-25 15:10 | JPazzi |  | No |  |  |  |  | Jorge Pazzi |  | 0 | 1 |  | L0 - No RO |  | 50 | 33.3 | 100 | 25 | 45 |  | 1 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1064022 | O.1064022.01 | A.1064022.01.12 | DESC Charges during project execution | SHELL AUSTRALIA PTY LTD. |  |  |  | RPI | CT-NONSERV | Low | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2026-05-01 |  | 2026-05-01 | 2026-07-30 23:59 |  |  | AUS West Coast WS | JPazzi | 2024-10-25 15:06 | JPazzi |  | No |  |  |  |  | Jorge Pazzi |  | 0 | 1 |  | L0 - No RO |  | 50 | 33.3 | 100 | 25 | 45 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1064022 | O.1064022.01 | A.1064022.01.06 | DESC Charges prior project execution | SHELL AUSTRALIA PTY LTD. |  |  |  | RPI | CT-NONSERV | Low | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2025-10-31 |  | 2025-10-31 | 2026-01-29 23:59 |  |  | AUS West Coast WS | JPazzi | 2024-10-25 11:20 | JPazzi |  | No |  |  |  |  | Jorge Pazzi |  | 0 | 1 |  | L0 - No RO |  | 50 | 33.3 | 100 | 25 | 45 |  | 1 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1064022 | O.1064022.01 | A.1064022.01.02 | CEC Charges prior project execution | SHELL AUSTRALIA PTY LTD. |  |  | J.24.174041 | RPI | CT-NONSERV | Low | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2024-11-01 |  | 2024-11-01 | 2025-01-30 23:59 |  |  | AUS West Coast WS | CNevarez2 | 2024-10-25 10:56 | JPazzi |  | No |  |  |  |  | Jorge Pazzi |  | 0 | 1 |  | L0 - No RO |  | 50 | 33.3 | 100 | 25 | 45 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1063793 | O.1063793.01 | A.1063793.01.01 | 8.5 in PEX-MDT logging | BURU ENERGY LIMITED | RAFAEL SHALLOW 1 | SILVER CITY RIG 24 | J.24.170476 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-10-16 | 2024-10-16 |  | 2024-10-16 | 2024-11-01 23:59 |  | 2024-11-01 23:59 | New Burn WL | ALegenkyy | 2024-11-01 12:49 | ALegenkyy |  | No |  |  |  | ROE WL Jakarta | Ihab Wahbi |  | 417174.79 | 3 |  | L2 - Shift RO |  | 100 | 91.7 | 100 | 87.5 | 93.8 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1063641 | O.1063641.01 | A.1063641.01.02 | Blacktip P5 Operations | ENI AUSTRALIA B.V. | BLACKTIP P5 | VALARIS 247 | J.25.018307 | RPI | CT-N2ONLY,CT-LIFT,CT-MTX | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-12-16 | 2025-02-18 | 2025-02-19 16:00 | 2025-02-27 | 2025-03-23 23:59 | 2025-03-25 | 2025-04-07 23:59 | AUS West Coast WS | ISoares2 | 2025-04-17 17:47 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 2341340 | 3 |  | L0 - No RO |  | 93.8 | 66.7 | 100 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1063641 | O.1063641.01 | A.1063641.01.01 | Rental Acid Equipment | ENI AUSTRALIA B.V. | BLACKTIP P5 | VALARIS 247 | J.24.168565 | RPI | CT-NONSERV | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | Not Required |  | 2024-10-06 |  | 2024-10-06 | 2025-01-04 23:59 |  |  | AUS West Coast WS | ISoares2 | 2025-04-17 17:39 | CNevarez2 |  | No |  |  |  |  | Mariana Salamanca |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 66.7 | 100 | 50 | 75 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1062592 | O.1062592.01 | A.1062592.01.01 | Tri-Star USIT-CBL | TRI-STAR OPCO PTY LTD | FAIRFIELDS 2 | SWS-2 | J.24.154640 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-09-11 | 2024-09-06 |  | 2024-09-06 | 2024-09-14 23:59 |  | 2024-09-14 23:59 | Roma WL | KKeese | 2024-09-11 14:32 | ysaeedabadian |  | No |  |  |  |  | Irwan Wongso |  | 45061.73 | 1 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1062500 | O.1062500.01 | A.1062500.01.12 | Marlin 1 | ESSO AUSTRALIA LTD | MARLIN 1 | VALARIS 107 | J.25.171345 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2025-10-11 | 2025-09-23 | 2025-10-09 | 2025-11-11 | 2025-11-16 23:59 | 2025-12-21 | 2025-10-16 23:59 | New Burn WL | KKeese | 2025-12-01 08:36 | KKeese | M.1000400.02.60 | No |  |  |  |  | Edmund Brobbey |  | 114800 | 3 |  | L0 - No RO |  | 100 | 100 | 0 | 75 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1062500 | O.1062500.01 | A.1062500.01.07 | Halibut 1 | ESSO AUSTRALIA LTD | HALIBUT-1 | VALARIS 107 | J.25.102467 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Design Completed | Design Completed | 2025-09-14 | 2025-08-27 | 2025-09-12 | 2025-10-15 | 2025-10-20 23:59 | 2025-11-24 | 2025-09-19 23:59 | New Burn WL | KKeese | 2025-10-24 07:39 | ALegenkyy | M.1000400.04.60 | No |  |  |  |  | Yasser Moradi |  | 114800 | 3 |  | L0 - No RO |  | 91.7 | 100 | 100 | 75 | 90 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1062500 | O.1062500.01 | A.1062500.01.04 | Kipper - Resolve | ESSO AUSTRALIA LTD | KIPPER A3 | VALARIS 107 | J.25.045960 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2025-06-23 | 2025-06-15 | 2025-06-22 | 2025-09-16 | 2025-09-24 23:59 | 2025-08-23 | 2025-08-22 23:59 | New Burn WL | KKeese | 2025-10-07 04:29 | KKeese | M.1000400.03.60 | No |  |  |  |  | Yasser Moradi |  | 58619.46 | 5 |  | L0 - No RO |  | 91.7 | 100 | 0 | 75 | 80 |  | 5 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1062500 | O.1062500.01 | A.1062500.01.01 | ESSO_Bream B_P&A | ESSO AUSTRALIA LTD | BREAM B 11, BREAM B 16, DOLPHIN A-3 | VALARIS 107 | J.24.162088 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Design Completed | Design Completed | 2024-10-30 | 2024-10-22 | 2024-10-30 | 2024-10-30 | 2024-12-31 23:59 | 2025-01-01 | 2024-12-31 23:59 | New Burn WL | MElsanousi | 2025-09-30 15:27 | KKeese |  | No |  |  |  |  | Yasser Moradi |  | 96240.84 | 1 |  | L0 - No RO |  | 91.7 | 100 | 0 | 25 | 65 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1062500 | O.1062500.01 | A.1062500.01.06 | Aug V-107 | ESSO AUSTRALIA LTD | MULLOWAY-1, WHIPTAIL 1A | VALARIS 107 | J.25.151139 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-08-11 | 2025-08-03 | 2025-08-09 | 2025-08-11 | 2025-08-16 23:59 | 2025-10-21 | 2025-08-16 23:59 | New Burn WL | KKeese | 2025-09-09 17:02 | KKeese |  | No |  |  |  |  | Yasser Moradi |  | 0 | 2 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1062500 | O.1062500.01 | A.1062500.01.10 | IBC-CBL 9 5/8" Casing | ESSO AUSTRALIA LTD | KIPPER A3 | VALARIS 107 | J.25.136608 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2025-08-03 | 2025-07-16 | 2025-08-02 | 2025-08-25 | 2025-09-04 23:59 | 2025-09-05 | 2025-09-04 23:59 | New Burn WL | KKeese | 2025-08-29 17:23 | ALegenkyy | M.1000400.03.60 | No |  |  |  |  | Yasser Moradi |  | 151800 | 1 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1062500 | O.1062500.01 | A.1062500.01.03 | Subsea Wells | ESSO AUSTRALIA LTD | MULLOWAY-1, WHIPTAIL 1A | VALARIS 107 | J.25.045958 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2025-03-10 | 2025-03-02 | 2025-03-08 16:00 | 2025-03-10 | 2025-05-20 23:59 | 2025-05-21 | 2025-05-20 23:59 | New Burn WL | KKeese | 2025-08-28 12:09 | KKeese |  | No |  |  |  |  | Edmund Brobbey |  | 671085 | 2 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1062500 | O.1062500.01 | A.1062500.01.11 | Q1 Esso V-107 | ESSO AUSTRALIA LTD | MULLOWAY-1, WHIPTAIL 1A | VALARIS 107 | J.25.143263 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2026-01-01 | 2025-12-24 | 2025-12-30 | 2026-01-01 | 2026-03-25 23:59 | 2026-03-13 | 2026-03-25 23:59 | New Burn WL | KKeese | 2025-08-25 14:40 | KKeese |  | No |  |  |  |  | Edmund Brobbey |  | 0 | 2 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1062500 | O.1062500.01 | A.1062500.01.09 | Q4 V-107 SLK Activity | ESSO AUSTRALIA LTD | MULLOWAY-1, WHIPTAIL 1A | VALARIS 107 | J.25.103407 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-10-01 | 2025-09-23 | 2025-09-29 | 2025-10-01 | 2025-12-23 23:59 | 2025-12-11 | 2025-12-23 23:59 | New Burn WL | KKeese | 2025-08-25 14:24 | KKeese |  | No |  |  |  |  | Yasser Moradi |  | 0 | 2 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1062500 | O.1062500.01 | A.1062500.01.05 | IBC-CBL-EMA V-107 | ESSO AUSTRALIA LTD | MULLOWAY-1, WHIPTAIL 1A, EAST PILCHARD-1 | VALARIS 107 | J.25.102445 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2025-06-03 | 2025-06-02 | 2025-06-01 | 2025-06-03 | 2025-06-08 23:59 | 2025-08-13 | 2025-06-08 23:59 | New Burn WL | KKeese | 2025-06-30 14:27 | NCandra |  | No |  |  |  |  | Yasser Moradi |  | 272100 | 2 |  | L0 - No RO |  | 95.8 | 100 | 0 | 100 | 88.8 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1062500 | O.1062500.01 | A.1062500.01.08 | Q4 V-107 Activity WL | ESSO AUSTRALIA LTD | MULLOWAY-1, WHIPTAIL 1A | VALARIS 107 | J.25.103405 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2025-10-01 | 2025-09-23 | 2025-09-29 | 2025-10-01 | 2025-12-23 23:59 | 2025-12-11 | 2025-12-23 23:59 | New Burn WL | KKeese | 2025-05-26 16:44 | KKeese |  | No |  |  |  |  | Yasser Moradi |  | 0 | 2 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1062500 | O.1062500.01 | A.1062500.01.02 | ESSO_V07_P&A | ESSO AUSTRALIA LTD | BREAM B 2, BREAM B 3 ST1, BREAM B 17 | VALARIS 107 | J.25.020160 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2025-01-02 | 2024-12-25 |  | 2025-01-02 | 2025-03-31 23:59 |  | 2025-03-31 23:59 | New Burn WL | MElsanousi | 2025-03-11 11:23 | CClark9 |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 56256.06 | 1 |  | L0 - No RO |  | 100 | 100 | 0 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1062416 | O.1062416.02 | A.1062416.02.01 | Epilogue-Tractor | WOODSIDE BURRUP PTY. LTD | PLA08 | VALARIS DPS-1 | J.24.152009 | RPE | ES-CH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-09-06 | 2024-09-05 |  | 2024-09-06 | 2024-09-13 23:59 |  | 2024-09-13 23:59 | New Burn WL | JSedmak | 2024-09-09 17:10 | APutra7 |  | No |  |  |  |  | Arie Hidaya Putra |  | 245580.98 | 2 |  | L0 - No RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1062416 | O.1062416.01 | A.1062416.01.01 | Epilogue-Tractor | WOODSIDE BURRUP PTY. LTD |  | VALARIS DPS-1 | J.24.151997 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Not Started | Not Started | Not Started |  | 2024-09-05 |  | 2024-09-09 16:00 | 2024-09-13 23:59 |  |  | New Burn WL | JSedmak | 2024-09-04 18:09 | FDPSystemUser |  | No |  |  |  |  | Arie Hidaya Putra |  | 0 | 0 |  | L0 - No RO |  | 20.8 | 0 | 0 | 0 | 6.3 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1062213 | O.1062213.01 | A.1062213.01.01 | PnA Well #1 | JADESTONE ENERGY (EAGLE) PTY LTD | SKUA11 ST1 | VALARIS 247 | J.24.148279 | RPI | TSWT-NOSEPNOVX-JOB | High | Confirmed | Design - CEC |  | Design Completed | Not Started | In Progress | 2024-11-30 | 2024-09-01 |  | 2024-11-30 | 2025-03-02 23:59 |  | 2025-03-02 23:59 | APG TS | EKondratiev | 2025-02-26 20:50 | MWaseem2 |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Ahmed El-Wakil |  | 0 | 2 |  | L0 - No RO |  | 58.3 | 0 | 0 | 25 | 25 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1062038 | O.1062038.02 | A.1062038.02.01 | Jadestone-Rigless_USIT-XTRA | JADESTONE ENERGY (AUSTRALIA) PTY LTD |  |  | J.24.149387 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2024-10-17 | 2024-10-15 |  | 2024-10-17 | 2024-11-15 23:59 |  | 2024-11-15 23:59 | New Burn WL | MElsanousi | 2024-10-28 20:05 | MElsanousi |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 1 |  | L0 - No RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1061663 | O.1061663.01 | A.1061663.01.02 | Carpenteria-5H CBL-VDL | IMPERIAL OIL AND GAS PTY LTD | CARPENTARIA-5H | ENSIGN 965 | J.24.142272 | RPE | ES-CH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-11-27 | 2024-11-27 |  | 2024-11-27 | 2024-12-13 23:59 |  | 2024-12-13 23:59 | Roma WL | KKeese | 2024-11-29 17:04 | SAli112 |  | No |  |  |  |  | Irwan Wongso |  | 44385.96 | 2 |  | L0 - No RO |  | 91.7 | 83.3 | 100 | 100 | 92.5 |  | 3 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1061663 | O.1061663.01 | A.1061663.01.01 | CBL | IMPERIAL OIL AND GAS PTY LTD |  | ENSIGN 965 | J.24.142270 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2024-11-01 | 2024-11-01 |  | 2024-11-01 | 2024-11-08 23:59 |  | 2024-11-08 23:59 | Roma WL | KKeese | 2024-10-22 10:32 | KKeese |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1061395 | O.1061395.01 | A.1061395.01.01 | Sapura Pumping campaign | NORMAND SAPURA PTY LTD | LAMINARIA 2, LAMINARIA 5, LAMINARIA 6, LAMINARIA 8, CORALLINA 2 ST3 | SAPURAKENCANA CONSTRUCTOR | J.24.146939 | RPI | CT-MPUMP | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-12-13 | 2024-08-23 | 2024-09-15 | 2024-09-06 | 2024-12-05 23:59 | 2024-12-06 | 2025-03-12 23:59 | AUS West Coast WS | radinegara | 2025-04-08 15:16 | CNevarez2 |  | No |  |  |  |  | Ramadhani Adi Negara |  | 0 | 1 |  | L0 - No RO |  | 81.3 | 83.3 | 100 | 75 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1061395 | O.1061395.01 | A.1061395.01.08 | Sapura pumping campaign | NORMAND SAPURA PTY LTD | CORALLINA 2 ST3, LAMINARIA 5, LAMINARIA 6 | SAPURAKENCANA CONSTRUCTOR | J.24.192388 | RPI | CT-MPUMP | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-12-17 | 2024-12-13 |  | 2024-12-13 | 2025-02-10 23:59 |  | 2025-03-13 23:59 | AUS West Coast WS | CNevarez2 | 2025-03-13 10:55 | CNevarez2 |  | No |  |  |  |  | Edgar Acosta |  | 0 | 0 |  | L0 - No RO |  | 81.3 | 100 | 100 | 50 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1061395 | O.1061395.01 | A.1061395.01.06 | Well 6 Pumping | NORMAND SAPURA PTY LTD | CORALLINA 2 ST3 | SAPURAKENCANA CONSTRUCTOR | J.24.147647 | RPI | CT-MPUMP | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-10-21 | 2024-10-12 |  | 2024-10-21 | 2024-10-30 23:59 |  | 2024-10-30 23:59 | AUS West Coast WS | radinegara | 2024-08-28 10:01 | FDPSystemUser |  | No |  |  |  |  | Ramadhani Adi Negara |  | 0 | 1 |  | L0 - No RO |  | 62.5 | 33.3 | 100 | 25 | 50 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1061395 | O.1061395.01 | A.1061395.01.07 | Well 7 Pumping | NORMAND SAPURA PTY LTD | Well #7 | SAPURAKENCANA CONSTRUCTOR | J.24.147645 | RPI | CT-MPUMP | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-10-31 | 2024-10-22 |  | 2024-10-31 | 2024-11-09 23:59 |  | 2024-11-09 23:59 | AUS West Coast WS | radinegara | 2024-08-28 10:01 | FDPSystemUser |  | No |  |  |  |  | Ramadhani Adi Negara |  | 0 | 1 |  | L0 - No RO |  | 62.5 | 33.3 | 100 | 25 | 50 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1061395 | O.1061395.01 | A.1061395.01.05 | Well 5 Pumping | NORMAND SAPURA PTY LTD | Well #5 | SAPURAKENCANA CONSTRUCTOR | J.24.147644 | RPI | CT-MPUMP | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-10-11 | 2024-10-02 |  | 2024-10-11 | 2024-10-20 23:59 |  | 2024-10-20 23:59 | AUS West Coast WS | radinegara | 2024-08-28 10:00 | FDPSystemUser |  | No |  |  |  |  | Ramadhani Adi Negara |  | 0 | 1 |  | L0 - No RO |  | 62.5 | 33.3 | 100 | 25 | 50 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1061395 | O.1061395.01 | A.1061395.01.03 | Well 3 Pumping | NORMAND SAPURA PTY LTD | LAMINARIA 5 | SAPURAKENCANA CONSTRUCTOR | J.24.147643 | RPI | CT-MPUMP | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-09-21 | 2024-09-12 |  | 2024-09-21 | 2024-09-30 23:59 |  | 2024-09-30 23:59 | AUS West Coast WS | radinegara | 2024-08-28 10:00 | FDPSystemUser |  | No |  |  |  |  | Ramadhani Adi Negara |  | 0 | 1 |  | L0 - No RO |  | 62.5 | 33.3 | 100 | 25 | 50 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1061395 | O.1061395.01 | A.1061395.01.04 | Well 4 Pumping | NORMAND SAPURA PTY LTD | LAMINARIA 6 | SAPURAKENCANA CONSTRUCTOR | J.24.147642 | RPI | CT-MPUMP | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-10-01 | 2024-09-22 |  | 2024-10-01 | 2024-10-10 23:59 |  | 2024-10-10 23:59 | AUS West Coast WS | radinegara | 2024-08-28 09:59 | FDPSystemUser |  | No |  |  |  |  | Ramadhani Adi Negara |  | 0 | 1 |  | L0 - No RO |  | 62.5 | 33.3 | 100 | 25 | 50 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1061395 | O.1061395.01 | A.1061395.01.02 | Well 2 Pump | NORMAND SAPURA PTY LTD | LAMINARIA 8 | SAPURAKENCANA CONSTRUCTOR | J.24.147641 | RPI | CT-MPUMP | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-09-11 | 2024-09-02 |  | 2024-09-11 | 2024-09-20 23:59 |  | 2024-09-20 23:59 | AUS West Coast WS | radinegara | 2024-08-28 09:59 | FDPSystemUser |  | No |  |  |  |  | Ramadhani Adi Negara |  | 0 | 1 |  | L0 - No RO |  | 62.5 | 33.3 | 100 | 25 | 50 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1061087 | O.1061087.02 | A.1061087.02.07 | ENI BTP SLK | ENI AUSTRALIA B.V. | BLACKTIP P5 | VALARIS 247 | J.25.052616 | RPE | ES-CH-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | Not Started |  | 2025-01-15 |  | 2025-02-22 | 2025-03-07 23:59 |  |  | New Burn WL | MElsanousi | 2025-05-16 12:13 | MElsanousi |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1061087 | O.1061087.02 | A.1061087.02.06 | ENI BT-P5 SLK Opertaions | ENI AUSTRALIA B.V. | BLACKTIP P5, BLACKTIP P3 | VALARIS 247 | J.25.052615 | RPI | PS-SLK-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-08-04 | 2025-02-14 | 2025-02-19 | 2025-02-19 | 2025-03-05 23:59 | 2025-03-06 | 2025-03-05 23:59 | New Burn WL | CStevens6 | 2025-05-14 09:57 | MElsanousi |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 100 | 100 | 75 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1061087 | O.1061087.02 | A.1061087.02.04 | ENI BT-P3_CH_Perforation & PLT | ENI AUSTRALIA B.V. | BLACKTIP P3 | VALARIS 247 | J.24.188042 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2025-03-07 | 2024-12-20 | 2025-03-07 | 2025-03-07 | 2025-03-25 23:59 | 2025-03-26 | 2025-03-25 23:59 | New Burn WL | MElsanousi | 2025-04-15 06:28 | APutra7 |  | No |  |  |  |  | Jarrod Sedmak |  | 610238.65 | 5 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1061087 | O.1061087.02 | A.1061087.02.05 | ENI BT-P5_CH_Perforation & PLT | ENI AUSTRALIA B.V. | BLACKTIP P5 | VALARIS 247 | J.25.050591 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2025-03-02 | 2025-01-21 | 2025-02-28 | 2025-03-02 | 2025-03-15 23:59 | 2025-03-14 | 2025-03-22 23:59 | New Burn WL | WMaung | 2025-03-25 07:53 | WMaung |  | No |  |  |  |  | Jarrod Sedmak |  | 792998.95 | 3 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1061087 | O.1061087.02 | A.1061087.02.02 | ENI BT-P5_IBC-CBL_7in-9.625in-13.625in | ENI AUSTRALIA B.V. | BLACKTIP P5 | VALARIS 247 | J.24.136289 | RPE | ES-CH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2025-02-22 | 2025-01-15 |  | 2025-02-22 | 2025-03-07 23:59 |  | 2025-03-14 23:59 | New Burn WL | MElsanousi | 2025-02-18 20:34 | WMaung |  | No |  |  |  |  | Jarrod Sedmak |  | 118960 | 1 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 5 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1061087 | O.1061087.02 | A.1061087.02.03 | ENI BT-P5_9.625in & 7in Casing_CHDT | ENI AUSTRALIA B.V. | BLACKTIP P5 | VALARIS 247 | J.24.147084 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2025-01-05 | 2024-12-29 |  | 2025-03-01 | 2025-03-15 23:59 |  | 2025-03-15 23:59 | New Burn WL | MElsanousi | 2025-02-10 11:08 | WMaung |  | No |  |  |  | ROE WL Abu Dhabi | Jarrod Sedmak |  | 0 | 2 |  | L1 - Support RO |  | 62.5 | 0 | 0 | 0 | 18.8 |  | 2 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1061087 | O.1061087.02 | A.1061087.02.01 | ENI BT-P5_8.5 & 12.25in OH | ENI AUSTRALIA B.V. | BLACKTIP P5 | VALARIS 247 | J.24.136240 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Not Required | Design Completed | 2025-02-02 | 2025-01-27 |  | 2025-02-02 | 2025-02-18 23:59 |  | 2025-02-18 23:59 | New Burn WL | OAzarenko | 2025-01-31 09:23 | FDPSystemUser |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 2 |  | L0 - No RO |  | 83.3 | 100 | 0 | 0 | 55 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1061087 | O.1061087.01 | A.1061087.01.01 | ENI_12.25in OH_BT-P5 | ENI AUSTRALIA B.V. | BLACKTIP P5 | VALARIS 247 | J.24.134535 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | Not Started | 2024-09-25 | 2024-09-15 |  | 2024-09-25 | 2024-10-15 23:59 |  | 2024-10-15 23:59 | New Burn WL | MElsanousi | 2024-08-01 10:23 | OAzarenko |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1060975 | O.1060975.01 | A.1060975.01.02 | Sapura | SAPURA AUSTRALIA PTY LTD | CORALLINA 2 ST3, LAMINARIA 5 ST1, LAMINARIA 6, LAMINARIA 8, LAMINARIA 2 | FPSO - NORTHERN ENDEAVOR | J.25.046496 | RPI | TSWT-BLEEDOFF-JOB | High | Confirmed | Design - CEC |  | Design Completed | Not Started | In Progress | 2025-01-23 | 2024-12-25 | 2025-01-22 | 2025-01-23 | 2025-04-23 23:59 | 2025-03-01 | 2025-04-11 23:59 | APG TS | EKondratiev | 2025-06-27 17:30 | AEl-wakil |  | No |  |  |  |  | Ahmed El-Wakil |  | 499410 | 1 |  | L0 - No RO |  | 58.3 | 16.7 | 0 | 25 | 30 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1060975 | O.1060975.01 | A.1060975.01.01 | SAPURA | SAPURA AUSTRALIA PTY LTD | CORALLINA 2 ST3, LAMINARIA 5 ST1, LAMINARIA 6, LAMINARIA 8, LAMINARIA 2 | FPSO - NORTHERN ENDEAVOR | J.24.133200 | RPI | TSWT-BLEEDOFF-JOB | High | Confirmed | Design - CEC |  | Design Completed | Not Required | Design Completed | 2024-08-30 | 2024-08-01 |  | 2024-08-30 | 2025-01-27 18:23 |  | 2025-02-12 18:24 | APG TS | EKondratiev | 2025-01-27 18:25 | FDPSystemUser |  | No |  |  |  |  | Evgeniy Kondratiev |  | 1341102 | 1 |  | L0 - No RO |  | 91.7 | 83.3 | 100 | 50 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1060890 | O.1060890.01 | A.1060890.01.08 | Slim Epliogue - Rigless | ESSO AUSTRALIA LTD | COBIA A 14B, COBIA A 15B, COBIA A 28, BREAM A 4B | ISLAND PERFORMER LWI | J.25.055006 | RPI | PS-WL-NO | Medium | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2025-02-27 16:00 | 2025-02-21 | 2025-02-22 16:00 | 2025-02-28 | 2025-03-30 23:59 | 2025-03-31 | 2025-03-30 15:59 | New Burn WL | KKeese | 2025-03-31 09:05 | KKeese |  | No |  |  |  |  | Edmund Brobbey |  | 174000 | 1 |  | L0 - No RO |  | 91.7 | 83.3 | 100 | 75 | 85 |  | 2 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1060890 | O.1060890.01 | A.1060890.01.01 | Halibut_A7/A3_Slim Epilogue/DEC | ESSO AUSTRALIA LTD | HALIBUT A 7A, HALIBUT A-3A | ISLAND PERFORMER LWI | J.24.132265 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-07-27 | 2024-07-20 | 2024-07-22 | 2024-07-27 | 2024-08-05 23:59 | 2024-08-06 | 2024-08-05 23:59 | New Burn WL | MElsanousi | 2025-03-24 07:24 | VCao2 |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 71500 | 1 |  | L0 - No RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1060890 | O.1060890.01 | A.1060890.01.06 | ESSO_Barcauda Platform-Slim Epilogue | ESSO AUSTRALIA LTD | COBIA A 14B, COBIA A 15B, COBIA A 28 | ISLAND PERFORMER LWI | J.25.020161 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-02-01 | 2025-02-01 |  | 2025-02-01 | 2025-03-31 23:59 |  | 2025-03-31 23:59 | New Burn WL | MElsanousi | 2025-02-24 16:53 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1060890 | O.1060890.01 | A.1060890.01.07 | Morpho Logging | ESSO AUSTRALIA LTD | COBIA A 14B, COBIA A 15B, COBIA A 28 | ISLAND PERFORMER LWI | J.24.186012 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-01-01 | 2024-12-25 |  | 2025-01-01 | 2025-01-10 23:59 |  | 2025-01-10 23:59 | New Burn WL | KKeese | 2024-11-26 12:06 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1060890 | O.1060890.01 | A.1060890.01.03 | ESSO_KingFish Platform_Slim Epilogue-Gowell Memory | ESSO AUSTRALIA LTD | WKF W12A | ISLAND PERFORMER LWI | J.24.138658 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-10-16 | 2024-10-15 |  | 2024-10-16 | 2024-10-31 23:59 |  | 2024-10-31 23:59 | New Burn WL | MElsanousi | 2024-11-07 07:28 | MElsanousi |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 149500 | 1 |  | L0 - No RO |  | 91.7 | 83.3 | 100 | 100 | 92.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1060890 | O.1060890.01 | A.1060890.01.05 | ESSO-Rigless | ESSO AUSTRALIA LTD | COBIA A 14B, COBIA A 15B, COBIA A 28 | ISLAND PERFORMER LWI | J.24.148452 | RPI | PS-WL-Ops | High | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2024-11-22 | 2024-11-15 |  | 2024-11-22 | 2024-12-01 23:59 |  | 2024-12-01 23:59 | New Burn WL | MElsanousi | 2024-10-28 19:51 | MElsanousi |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1060890 | O.1060890.01 | A.1060890.01.02 | ESSO_Cobia Platform_Slim Epilogue-Gowell Memory | ESSO AUSTRALIA LTD | COBIA A 14B, COBIA A 15B, COBIA A 28, COBIA A 19A, COBIA F 27, COBIA A17, COBIA A 33, COBIA A 21A, COBIA F 1A, COBIA F 35, COBIA F 8A, COBIA F 8, WKF W12A | ISLAND PERFORMER LWI | J.24.135005 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-08-01 | 2024-07-25 |  | 2024-08-01 | 2024-10-30 23:59 |  | 2024-10-30 23:59 | New Burn WL | MElsanousi | 2024-10-19 06:53 | VCao2 |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 149500 | 1 |  | L2 - Shift RO |  | 91.7 | 83.3 | 100 | 100 | 92.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1060890 | O.1060890.01 | A.1060890.01.04 | ESSO_Baracuda Platform_Slim Epilogue-Gowell Memory | ESSO AUSTRALIA LTD | COBIA A 14B, COBIA A 15B, COBIA A 28 | ISLAND PERFORMER LWI | J.24.138659 | RPI | PS-WL-Ops | High | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2024-10-05 | 2024-09-28 |  | 2024-10-05 | 2024-10-14 23:59 |  | 2024-10-14 23:59 | New Burn WL | MElsanousi | 2024-08-29 15:06 | MElsanousi |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1060483 | O.1060483.01 | A.1060483.01.01 | Gorgon & Janz_Resolve Stroker | WELL OPS (UK) LTD | JZI-3D, GOR-1A, GOR-1B, GOR-1G | HELIX Q7000 | J.24.126883 | RPI | PS-WL-NO | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-10-01 | 2024-09-26 |  | 2024-10-01 | 2024-11-01 23:59 |  | 2024-11-01 23:59 | New Burn WL | MElsanousi | 2024-12-11 17:24 | MElsanousi |  | No |  |  |  |  | Peter Roche |  | 0 | 1 |  | L0 - No RO |  | 91.7 | 83.3 | 100 | 75 | 85 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1060483 | O.1060483.01 | A.1060483.01.02 | Gorgon & Janz-SLK Ops | WELL OPS (UK) LTD | JZI-3D, GOR-1A, GOR-1B, GOR-1G | HELIX Q7000 | J.24.148414 | RPI | PS-SLK-Rental-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-10-01 | 2024-09-26 |  | 2024-10-01 | 2024-11-07 23:59 |  | 2024-11-07 23:59 | New Burn WL | MElsanousi | 2024-10-27 13:31 | VQuoc |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 1 |  | L0 - No RO |  | 75 | 100 | 100 | 75 | 85 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1059480 | O.1059480.01 | A.1059480.01.02 | No OPS | WOODSIDE ENERGY GLOBAL PTY LTD |  | TRANSOCEAN LEGEND | J.24.112339 | RPI | PS-WL-NO | High | Confirmed | Design - CEC |  | Design Completed | Not Started | In Progress | 2024-08-07 | 2025-03-11 | 2025-03-16 | 2025-03-16 | 2025-03-17 23:59 | 2025-03-18 | 2025-03-17 23:59 | New Burn WL | MElsanousi | 2025-05-16 13:09 | MElsanousi |  | No |  |  |  |  | Jarrod Sedmak |  | 194663.28 | 5 |  | L0 - No RO |  | 75 | 66.7 | 100 | 100 | 82.5 |  | 6 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1059480 | O.1059480.01 | A.1059480.01.01 | Woodside_Transocean_Epilogue | WOODSIDE ENERGY GLOBAL PTY LTD | STYBARROW 10H | TRANSOCEAN LEGEND | J.24.112338 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-11-17 | 2024-11-15 |  | 2024-12-01 | 2024-12-16 23:59 |  | 2024-12-15 23:59 | New Burn WL | MElsanousi | 2024-12-01 13:52 | ALegenkyy |  | No |  |  |  |  | Jarrod Sedmak |  | 162200 | 2 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 6 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1058576 | O.1058576.01 | A.1058576.01.01 | InGauge TCP | CO2CRC LIMITED | CRC-4 | WILD DESERT RIG 4 | J.24.097323 | RPI | TCP-TEMP-JOB | Medium | Operationally Complete | Close - PSD |  | Not Required | Design Completed | Design Completed |  | 2024-05-27 |  | 2024-06-04 | 2024-06-18 23:59 |  |  | APG TS | EKondratiev | 2024-11-19 20:07 | FDPSystemUser |  | No |  |  |  |  | Evgeniy Kondratiev |  | 119199 | 1 |  |  |  | 91.7 | 83.3 | 100 | 100 | 92.5 |  | 0 |  | Working | D23052408650¦R01 | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1058371 | O.1058371.01 | A.1058371.01.02 | USIT & PBMS Logging | TRI-STAR OPCO PTY LTD | FAIRFIELDS 1, FAIRFIELDS 1X, FAIRFIELDS 2 | SWMS RIG 3 | J.24.147599 | RPI | PS-WL-NO | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-09-05 | 2024-09-01 |  | 2024-09-01 | 2024-09-04 23:59 |  | 2024-09-27 23:59 | Roma WL | KKeese | 2024-10-22 10:36 | KKeese |  | No |  |  |  |  | Irwan Wongso |  | 74805.07 | 2 |  | L0 - No RO |  | 66.7 | 33.3 | 100 | 50 | 55 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1058371 | O.1058371.01 | A.1058371.01.01 | Fairfields-1x, Fairfields-1, Fairfields-2 | TRI-STAR OPCO PTY LTD | FAIRFIELDS 1, FAIRFIELDS 1X, FAIRFIELDS 2 | SWMS RIG 3 | J.24.096859 | RPI | PS-WL-NO | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-05-10 | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-06-01 23:59 | 2024-06-02 | 2024-06-01 23:59 | Roma WL | NAndilla | 2024-05-25 10:21 | KKeese |  | No |  |  |  |  | Irwan Wongso |  | 0 | 2 |  | L0 - No RO |  | 91.7 | 66.7 | 100 | 75 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1057866 | O.1057866.01 | A.1057866.01.01 | TCP Hanging Wall | EXXONMOBIL PNG LIMITED | HIDES F2 | NABORS 702 | J.25.003755 | RPI | TCP-PERM-JOB | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2025-02-15 | 2024-10-01 | 2025-02-13 | 2025-02-15 | 2025-03-14 23:59 | 2025-04-01 | 2025-03-14 23:59 | APG TS | MSwara | 2025-05-06 09:17 | MWaseem2 |  | No |  | [AUSG-TCP] - |  |  | Yudha Swara |  | 0 | 1 |  |  |  | 83.3 | 100 | 100 | 75 | 87.5 |  | 2 |  |  |  | 0 |  |  |  | Muhammad Fahd Waseem | TCP - Tubing-Conveyed Perforation
P.1057195 | O.1057195.01 | A.1057195.01.01 | SLK-GS2 | CHEVRON APG ABU PERTH. |  | HELIX Q7000 | J.24.112857 | RPI | PS-SLK-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Not Required | Design Completed | 2024-07-21 | 2024-07-17 |  | 2024-07-21 | 2024-08-25 23:59 |  | 2024-08-25 23:59 | New Burn WL | MElsanousi | 2024-06-05 15:42 | MElsanousi |  | No |  |  |  |  | Peter Roche |  | 0 | 2 |  | L0 - No RO |  | 66.7 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1056886 | O.1056886.01 | A.1056886.01.35 | Schmoo Cleanout L38 | CHEVRON APG ABU PERTH. | BARROW_L38 |  | J.25.170651 | RPI | CT-WBCLEAN | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2025-11-26 13:00 | 2025-11-26 13:00 | 2025-11-26 | 2025-11-26 13:00 | 2025-12-02 23:59 | 2025-12-03 11:00 | 2025-12-03 23:59 | AUS West Coast WS | ISoares2 | 2025-12-01 07:56 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 100 | 0 | 0 | 65 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.22 | Schmoo cleanout K18 | CHEVRON APG ABU PERTH. | BARROW_K18 |  | J.25.099466 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-26 12:00 | 2025-11-27 | 2025-11-26 23:59 | AUS West Coast WS | CNevarez2 | 2025-11-28 14:36 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 669783.75 | 1 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.33 | Schmoo cleanout K16 | CHEVRON APG ABU PERTH. | BARROW_K16 |  | J.25.099507 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-23 23:59 | 2025-11-25 | 2025-11-25 23:59 | AUS West Coast WS | CNevarez2 | 2025-11-25 17:00 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 100 | 100 | 75 | 90 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.32 | Schmoo cleanout G16 | CHEVRON APG ABU PERTH. | BARROW_G16 |  | J.25.099506 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-11-18 | 2025-11-18 | 2025-11-17 12:00 | 2025-11-18 | 2025-11-20 23:59 | 2025-11-20 12:00 | 2025-11-20 23:59 | AUS West Coast WS | CNevarez2 | 2025-11-25 16:41 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 100 | 100 | 75 | 90 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.31 | Schmoo cleanout F14 | CHEVRON APG ABU PERTH. | BARROW_F14 |  | J.25.099505 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-11-14 06:00 | 2025-11-14 06:00 | 2025-11-13 18:00 | 2025-11-14 06:00 | 2025-11-17 23:59 | 2025-11-19 12:00 | 2025-11-18 17:59 | AUS West Coast WS | CNevarez2 | 2025-11-25 13:57 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 100 | 100 | 75 | 90 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.30 | L46A cementing | CHEVRON APG ABU PERTH. | BARROW_L46A |  | J.25.099504 | RPI | CT-CEM | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-11-11 12:00 | 2025-11-11 12:00 | 2025-11-11 | 2025-11-11 12:00 | 2025-11-13 11:59 | 2025-11-14 | 2025-11-14 11:59 | AUS West Coast WS | CNevarez2 | 2025-11-14 12:00 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 100 | 100 | 75 | 90 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.28 | P73 Plug Milling | CHEVRON APG ABU PERTH. | BARROW_P73 |  | J.25.099495 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-10 12:00 | 2025-11-10 12:01 | 2025-11-08 23:59 | AUS West Coast WS | CNevarez2 | 2025-11-14 09:59 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 100 | 100 | 75 | 90 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.29 | E16 Cementing | CHEVRON APG ABU PERTH. | E16 |  | J.25.099503 | RPI | CT-CEM | Medium | Confirmed | Design - CEC |  | Design Completed | Not Required | Design Completed | 2025-12-09 12:00 | 2025-12-08 12:00 | 2025-12-09 12:00 | 2025-12-09 12:00 | 2025-12-12 11:59 | 2025-12-12 12:00 | 2025-12-12 11:59 | AUS West Coast WS | CNevarez2 | 2025-11-14 08:35 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 66.7 | 0 | 0 | 55 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.38 | L32J Cementing | CHEVRON APG ABU PERTH. |  |  | J.25.170655 | RPI | CT-WBCLEAN,CT-CEM | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-16 23:59 | 2025-12-18 | 2025-12-17 23:59 | AUS West Coast WS | ISoares2 | 2025-10-28 10:12 | ISoares2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.39 | L51J Cementing | CHEVRON APG ABU PERTH. |  |  | J.25.170656 | RPI | CT-WBCLEAN,CT-CEM | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-20 23:59 | 2025-12-22 | 2025-12-21 23:59 | AUS West Coast WS | ISoares2 | 2025-10-28 10:12 | ISoares2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.40 | B31 Fishing | CHEVRON APG ABU PERTH. |  |  | J.25.170657 | RPI | CT-WBCLEAN, CT-FISHING | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2025-12-21 | 2025-12-21 | 2025-12-21 | 2025-12-21 | 2025-12-31 23:59 | 2026-01-02 | 2026-01-01 23:59 | AUS West Coast WS | ISoares2 | 2025-10-28 10:12 | FDPSystemUser |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.37 | Schmoo Cleanout F14 | CHEVRON APG ABU PERTH. |  |  | J.25.170654 | RPI | CT-WBCLEAN | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-12 23:59 | 2025-12-14 | 2025-12-13 23:59 | AUS West Coast WS | ISoares2 | 2025-10-28 10:05 | ISoares2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.36 | Schmoo Cleanout R58 | CHEVRON APG ABU PERTH. |  |  | J.25.170653 | RPI | CT-WBCLEAN | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-08 23:59 | 2025-12-10 | 2025-12-09 23:59 | AUS West Coast WS | ISoares2 | 2025-10-28 10:05 | ISoares2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.34 | PWC campaign for FDP purposes | CHEVRON APG ABU PERTH. |  |  | J.25.101931 | RPI | CT-WBCLEAN | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2026-06-01 |  | 2026-06-01 | 2026-07-16 23:59 |  |  | AUS West Coast WS | CNevarez2 | 2025-10-28 09:59 | ISoares2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.26 | schomoo cleanout Q32 | CHEVRON APG ABU PERTH. | BARROW_Q17 |  | J.25.099487 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-15 23:59 | 2025-09-16 | 2025-09-15 23:59 | AUS West Coast WS | CNevarez2 | 2025-09-30 18:15 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 83.3 | 100 | 75 | 85 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.25 | schmoo cleanout G12 | CHEVRON APG ABU PERTH. | G61 |  | J.25.099485 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-11 23:59 | 2025-09-12 | 2025-09-11 23:59 | AUS West Coast WS | CNevarez2 | 2025-09-30 17:34 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 83.3 | 100 | 75 | 85 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.27 | schmoo cleanout Q66 | CHEVRON APG ABU PERTH. | BARROW_B32 |  | J.25.099490 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-09-16 | 2025-09-16 | 2025-09-16 | 2025-09-16 | 2025-09-24 23:59 | 2025-09-26 | 2025-09-24 23:59 | AUS West Coast WS | CNevarez2 | 2025-09-25 17:13 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 614641.62 | 1 |  | L0 - No RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.21 | Schmoo cleanout G63A | CHEVRON APG ABU PERTH. | G61 |  | J.25.099464 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-07 23:59 | 2025-09-08 | 2025-09-07 23:59 | AUS West Coast WS | CNevarez2 | 2025-09-19 16:04 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 100 | 100 | 75 | 90 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.23 | Schmoo cleanout G15 | CHEVRON APG ABU PERTH. | G61 |  | J.25.099472 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-08-31 | 2025-08-30 | 2025-08-31 | 2025-08-31 | 2025-09-03 23:59 | 2025-09-04 | 2025-09-03 23:59 | AUS West Coast WS | CNevarez2 | 2025-09-19 15:50 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 0 |  | L0 - No RO |  | 87.5 | 83.3 | 0 | 75 | 75 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.20 | Schmoo cleanout B22 | CHEVRON APG ABU PERTH. | BARROW_B32 |  | J.25.099462 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-08-27 | 2025-08-26 | 2025-08-26 | 2025-08-27 | 2025-08-30 23:59 | 2025-08-31 | 2025-08-30 23:59 | AUS West Coast WS | CNevarez2 | 2025-09-19 15:21 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 100 | 100 | 75 | 90 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.24 | Schmoo cleanout P35 | CHEVRON APG ABU PERTH. | BARROW_P35 |  | J.25.099479 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-08-17 | 2025-08-17 | 2025-08-17 | 2025-08-17 | 2025-08-21 23:59 | 2025-08-22 | 2025-08-21 23:59 | AUS West Coast WS | CNevarez2 | 2025-08-29 16:48 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 100 | 100 | 75 | 90 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.19 | schmoo cleanout B32 | CHEVRON APG ABU PERTH. | BARROW_B32 |  | J.25.099453 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-08-26 23:59 | 2025-08-26 | 2025-08-26 23:59 | AUS West Coast WS | CNevarez2 | 2025-08-27 15:35 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 480422.66 | 1 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.18 | Schmoo cleanout Q72 | CHEVRON APG ABU PERTH. | BARROW_Q72 |  | J.25.099447 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-16 23:59 | 2025-08-17 | 2025-08-16 23:59 | AUS West Coast WS | CNevarez2 | 2025-08-19 16:39 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 100 | 100 | 75 | 90 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.17 | Schmoo cleanout H77 | CHEVRON APG ABU PERTH. | BARROW_H77 |  | J.25.099441 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-07-02 | 2025-07-03 | 2025-07-03 | 2025-07-03 | 2025-07-17 23:59 | 2025-07-19 | 2025-07-05 23:59 | AUS West Coast WS | CNevarez2 | 2025-08-04 15:20 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 377747.45 | 1 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.14 | Schmoo cleanout Q48 | CHEVRON APG ABU PERTH. | BARROW_Q48 |  | J.25.099376 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-19 23:59 | 2025-06-20 | 2025-06-19 23:59 | AUS West Coast WS | CNevarez2 | 2025-07-03 16:46 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 83.3 | 100 | 75 | 85 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.16 | Schmoo Cleanout E31 | CHEVRON APG ABU PERTH. | BARROW_F46A |  | J.25.099427 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-07-02 23:59 | 2025-07-03 | 2025-06-30 23:59 | AUS West Coast WS | CNevarez2 | 2025-07-03 14:01 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 83.3 | 100 | 75 | 85 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.15 | Schmoo cleanout Q37 | CHEVRON APG ABU PERTH. | BARROW_Q37 |  | J.25.099412 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-26 23:59 | 2025-06-27 | 2025-06-23 23:59 | AUS West Coast WS | CNevarez2 | 2025-06-29 19:43 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 664321.04 | 1 |  | L0 - No RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.12 | Schmoo cleanout P32 | CHEVRON APG ABU PERTH. | BARROW_P32 |  | J.25.099361 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-06-05 | 2025-06-05 | 2025-06-04 16:00 | 2025-06-05 | 2025-06-10 23:59 | 2025-06-11 | 2025-06-08 23:59 | AUS West Coast WS | CNevarez2 | 2025-06-20 16:58 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 83.3 | 100 | 75 | 85 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.08 | Schmoo Cleanout K37 | CHEVRON APG ABU PERTH. | BARROW_K37 |  | J.25.091652 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-05-15 23:59 | 2025-05-17 | 2025-05-16 23:59 | AUS West Coast WS | CNevarez2 | 2025-06-17 13:47 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 66.7 | 100 | 75 | 80 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.13 | Schmoo cleanout T88 | CHEVRON APG ABU PERTH. | BARROW_T88 |  | J.25.099369 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-06-11 | 2025-06-11 | 2025-06-10 16:00 | 2025-06-11 | 2025-06-15 23:59 | 2025-06-16 | 2025-06-15 23:59 | AUS West Coast WS | CNevarez2 | 2025-06-16 15:24 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 83.3 | 100 | 75 | 85 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.11 | Schmoo cleanout Q17 | CHEVRON APG ABU PERTH. | BARROW_Q17 |  | J.25.099358 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-05-27 | 2025-05-26 | 2025-05-26 08:00 | 2025-05-27 | 2025-06-04 23:59 | 2025-06-05 | 2025-05-31 23:59 | AUS West Coast WS | CNevarez2 | 2025-06-09 16:18 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 66.7 | 100 | 75 | 80 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.10 | Schmoo Cleanout P34 | CHEVRON APG ABU PERTH. | BARROW_P34 |  | J.25.091654 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2025-05-20 | 2025-05-20 | 2025-05-20 | 2025-05-20 | 2025-05-26 23:59 | 2025-05-27 | 2025-05-24 23:59 | AUS West Coast WS | CNevarez2 | 2025-06-05 10:23 | ISoares2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 645576.16 | 1 |  | L0 - No RO |  | 93.8 | 66.7 | 100 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.09 | Schmoo cleanout K34 | CHEVRON APG ABU PERTH. | BARROW_K34 |  | J.25.091653 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-19 23:59 | 2025-05-21 | 2025-05-20 23:59 | AUS West Coast WS | CNevarez2 | 2025-06-04 15:22 | ISoares2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 66.7 | 100 | 75 | 80 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.06 | Cleanout water injector P56 | CHEVRON APG ABU PERTH. | BARROW_P56 |  | J.25.091649 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-02-20 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-05 23:59 | 2025-05-06 | 2025-12-01 23:59 | AUS West Coast WS | CNevarez2 | 2025-05-22 13:59 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 66.7 | 100 | 75 | 80 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.07 | Schmoo cleanout L24 | CHEVRON APG ABU PERTH. | BARROW_L24 |  | J.25.091650 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-05-06 | 2025-05-06 | 2025-05-06 | 2025-05-06 | 2025-05-11 23:59 | 2025-05-12 | 2025-05-10 23:59 | AUS West Coast WS | CNevarez2 | 2025-05-22 13:53 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 93.8 | 66.7 | 100 | 75 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.04 | Water injector cleanout L074 | CHEVRON APG ABU PERTH. | BARROW_L74 |  | J.25.056011 | RPI | CT-CEM,CT-WBCLEAN, CT-MILLSLB | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2025-05-02 | 2025-04-28 | 2025-04-28 | 2025-04-28 | 2025-04-30 23:59 | 2025-05-03 | 2025-05-04 | AUS West Coast WS | ISoares2 | 2025-05-19 17:45 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.03 | Tag TOC -G61 | CHEVRON APG ABU PERTH. | G61 |  | J.25.056009 | RPI | CT-CIRC | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-05-02 | 2025-04-22 | 2025-04-21 | 2025-04-22 | 2025-04-27 23:59 | 2025-04-28 | 2025-05-04 | AUS West Coast WS | ISoares2 | 2025-05-19 17:43 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 584061.01 | 1 |  | L0 - No RO |  | 100 | 66.7 | 100 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.02 | Tag TOC - L27A | CHEVRON APG ABU PERTH. | L27A |  | J.25.056008 | RPI | CT-CIRC | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-05-01 | 2025-04-08 | 2025-04-07 08:00 | 2025-04-08 | 2025-04-21 23:59 | 2025-04-22 | 2025-05-03 | AUS West Coast WS | ISoares2 | 2025-05-02 17:41 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 66.7 | 100 | 75 | 80 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.05 | Multiple interventions | CHEVRON APG ABU PERTH. |  |  | J.25.081313 | RPI | CT-MPUMP,CT-WBCLEAN,CT-CEM | Medium | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2025-05-03 |  | 2025-05-03 | 2025-05-17 23:59 |  |  | AUS West Coast WS | CNevarez2 | 2025-05-01 17:15 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 3 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056886 | O.1056886.01 | A.1056886.01.01 | Unit Preparation in Island | CHEVRON APG ABU PERTH. | G61, L27A |  | J.24.079735 | RPI | CT-EQPRNT | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-02-20 | 2025-03-20 | 2025-03-16 | 2025-03-20 | 2025-04-07 23:59 | 2025-04-08 | 2025-12-09 23:59 | AUS West Coast WS | ISoares2 | 2025-04-08 15:18 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 0 |  | L0 - No RO |  | 87.5 | 100 | 100 | 75 | 90 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056828 | O.1056828.01 | A.1056828.01.02 | PnA part 2 (halibut and Marlin) | ESSO AUSTRALIA LTD | HALIBUT-1, MARLIN 1 | VALARIS 107 | J.24.102627 | RPI | TSWT-BLEEDOFF-JOB | High | Confirmed | Execute - PSD |  | Design Completed | Not Required | Not Started | 2025-10-01 | 2025-06-02 | 2025-09-30 | 2025-10-01 | 2025-12-31 23:59 | 2026-01-01 | 2025-12-31 23:59 | APG TS | EKondratiev | 2025-11-27 10:05 | AEl-wakil |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Farhad Kianifar |  | 0 | 2 |  | L0 - No RO |  | 75 | 83.3 | 100 | 25 | 65 |  | 1 |  |  |  | 0 |  |  |  | Ahmed El-Wakil | TS Surface Testing
P.1056828 | O.1056828.01 | A.1056828.01.01 | ESSO PnA campaign Part 1 | ESSO AUSTRALIA LTD | MULLOWAY-1, EAST PILCHARD-1, WHIPTAIL 1A | VALARIS 107 | J.24.078879 | RPI | TSWT-BLEEDOFF-JOB | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-03-01 | 2025-03-01 | 2025-02-28 | 2025-03-01 | 2025-07-04 23:59 | 2025-09-12 | 2025-07-04 23:59 | APG TS | EKondratiev | 2025-07-07 14:37 | AEl-wakil |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Ahmed El-Wakil |  | 192325 | 3 |  | L0 - No RO |  | 100 | 100 | 100 | 75 | 92.5 |  | 2 |  |  |  | 0 |  |  |  | Muhammad Fahd Waseem | TS Surface Testing
P.1056828 | O.1056828.01 | A.1056828.01.03 | PnA Part 3 | ESSO AUSTRALIA LTD |  | VALARIS 107 | J.25.004899 | RPI | TSWT-SEPONLY-JOB | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-09-30 | 2025-08-31 | 2025-09-29 16:00 | 2025-09-30 | 2025-12-30 23:59 | 2025-12-31 | 2025-12-30 23:59 | APG TS | EKondratiev | 2025-05-22 11:35 | MWaseem2 |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Evgeniy Kondratiev |  | 0 | 3 |  | L0 - No RO |  | 25 | 33.3 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1056628 | O.1056628.01 | A.1056628.01.02 | ESSO PWC_A 17 | ESSO AUSTRALIA LTD | FLOUNDER A 17A |  | J.24.118042 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-06-22 | 2024-06-14 |  | 2024-06-22 | 2024-08-05 23:59 |  | 2024-08-05 23:59 | New Burn WL | MElsanousi | 2024-12-13 15:43 | MElsanousi |  | No |  |  |  |  | Peter Roche |  | 54000 | 3 |  | L0 - No RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1056628 | O.1056628.01 | A.1056628.01.05 | ESSO PWC Logging - A9 | ESSO AUSTRALIA LTD | FLOUNDER A 9 |  | J.24.167295 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-10-20 | 2024-10-20 |  | 2024-10-20 | 2024-12-31 23:59 |  | 2024-12-31 23:59 | New Burn WL | ALegenkyy | 2024-11-21 10:21 | ALegenkyy |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 1 |  | L0 - No RO |  | 95.8 | 100 | 100 | 100 | 98.8 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1056628 | O.1056628.01 | A.1056628.01.04 | ESSO-PWC Logging A21 | ESSO AUSTRALIA LTD | FLOUNDER A 15, FLOUNDER A 26 ST1 |  | J.24.148442 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2024-09-01 | 2024-08-29 |  | 2024-09-01 | 2024-10-27 23:59 |  | 2024-10-27 23:59 | New Burn WL | MElsanousi | 2024-08-29 14:54 | MElsanousi |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 3 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1056628 | O.1056628.01 | A.1056628.01.03 | ESSO Post-PWC A15 / Pre-Post PWC A26 | ESSO AUSTRALIA LTD | FLOUNDER A 15, FLOUNDER A 26 ST1 |  | J.24.123575 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-06-30 | 2024-06-27 |  | 2024-06-30 | 2024-08-25 23:59 |  | 2024-08-25 23:59 | New Burn WL | CClark9 | 2024-08-12 09:25 | ALegenkyy |  | No |  |  |  |  | Peter Roche |  | 108000 | 3 |  | L0 - No RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1056628 | O.1056628.01 | A.1056628.01.01 | ESSO PWC Flounder | ESSO AUSTRALIA LTD | FLOUNDER A 15 |  | J.24.076807 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-06-07 | 2024-06-05 |  | 2024-06-07 | 2024-08-02 23:59 |  | 2024-08-02 23:59 | New Burn WL | APutri | 2024-07-24 10:55 | CClark9 |  | No |  |  |  |  | Ade Kusuma Putri |  | 0 | 3 |  | L0 - No RO |  | 75 | 83.3 | 100 | 75 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1056334 | O.1056334.01 | A.1056334.01.01 | E-WI4 | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 WATER INJECTION WELL E-WI4 |  | J.24.079744 | RPI | CT-LIFT | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-10-08 | 2025-10-06 | 2025-10-08 | 2025-10-08 | 2025-10-31 | 2025-11-01 | 2025-10-31 | AUS West Coast WS | ISoares2 | 2025-10-27 14:43 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 803404.44 | 0 |  | L0 - No RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056334 | O.1056334.01 | A.1056334.01.03 | E-WI2 ST1 | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 WATER INJECTION WELL E-WI2 |  | J.24.099107 | RPI | CT-LIFT,CT-MTX | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-10-07 23:00 | 2025-10-08 | 2025-10-07 23:00 | AUS West Coast WS | AKohr | 2025-10-20 13:59 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 3 |  | L0 - No RO |  | 87.5 | 100 | 100 | 75 | 90 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056334 | O.1056334.01 | A.1056334.01.04 | D-WI3 | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 WATER INJECTION WELL D-WI3 |  | J.24.099108 | RPI | CT-LIFT | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-07-27 | 2025-07-27 | 2025-07-27 | 2025-07-27 | 2025-08-12 23:59 | 2025-08-13 | 2025-08-12 23:59 | AUS West Coast WS | AKohr | 2025-08-27 11:27 | ISoares2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 612850.21 | 0 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 1 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056334 | O.1056334.01 | A.1056334.01.05 | D-WI1 ST1 | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 WATER INJECTION WELL D-WI1 |  | J.25.004268 | RPI | CT-LIFT,CT-MTX | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-26 23:59 | 2025-08-03 | 2025-08-02 23:59 | AUS West Coast WS | AKohr | 2025-07-31 08:45 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 659555.38 | 1 |  | L0 - No RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056334 | O.1056334.01 | A.1056334.01.08 | Quarantine and Standby | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 WATER INJECTION WELL D-WI1 |  | J.25.109609 | RPI | CT-N2ONLY | Low | Cancelled | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-05-31 | 2025-05-31 | 2025-06-03 | 2025-05-31 | 2025-06-28 23:59 | 2025-06-13 | 2025-06-28 23:59 | AUS West Coast WS | ISoares2 | 2025-06-04 12:19 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 65.6 | 8.3 | 0 | 0 | 28.7 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056334 | O.1056334.01 | A.1056334.01.02 | Quarantine | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 WATER INJECTION WELL D-WI1 |  | J.24.097789 | RPI | CT-NONSERV | Low | Cancelled | Close - PSD |  | Not Required | Not Required | In Progress |  | 2025-04-04 |  | 2025-04-04 | 2025-04-30 23:59 |  |  | AUS West Coast WS | ISoares2 | 2025-04-08 15:38 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 0 |  | L0 - No RO |  | 81.3 | 66.7 | 100 | 50 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056334 | O.1056334.01 | A.1056334.01.06 | Z-WI2 Clay Stabilization | CHEVRON APG ABU PERTH. |  |  | J.24.144029 | RPI | CT-MPUMP | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-11-01 | 2024-11-04 |  | 2024-11-06 | 2024-11-20 23:59 |  | 2024-11-23 23:59 | AUS West Coast WS | ISoares2 | 2024-11-29 10:03 | ISoares2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 55500 | 0 |  | L0 - No RO |  | 100 | 83.3 | 100 | 75 | 90 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056334 | O.1056334.01 | A.1056334.01.07 | Unit Set-up and Preparation | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 WATER INJECTION WELL D-WI1 |  | J.24.146734 | RPI | CT-NONSERV | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-09-01 | 2024-08-28 |  | 2024-08-28 | 2024-09-11 23:59 |  | 2024-09-11 23:59 | AUS West Coast WS | ISoares2 | 2024-09-25 10:56 | ISoares2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 175000 | 0 |  | L0 - No RO |  | 100 | 66.7 | 100 | 50 | 80 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056110 | O.1056110.01 | A.1056110.01.01 | Blacktip P5 kickoff | ENI AUSTRALIA LIMITED | BLACKTIP P5 | VALARIS 247 | J.24.079213 | RPI | CT-LIFT,CT-MTX | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2024-11-15 | 2024-11-15 |  | 2025-01-10 | 2025-03-03 23:59 |  | 2025-02-28 23:59 | AUS West Coast WS | CNevarez2 | 2024-10-18 11:39 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  | L0 - No RO |  | 59.4 | 8.3 | 0 | 0 | 26.3 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056110 | O.1056110.01 | A.1056110.01.03 | Rental Acid equipment | ENI AUSTRALIA LIMITED | BLACKTIP P5 | VALARIS 247 | J.24.098269 | RPI | CT-NONSERV | Low | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2024-10-10 |  | 2024-10-10 | 2025-02-07 23:59 |  |  | AUS West Coast WS | CNevarez2 | 2024-10-18 11:39 | CNevarez2 |  | No |  |  |  |  | Mariana Salamanca |  | 0 | 1 |  | L0 - No RO |  | 50 | 33.3 | 100 | 25 | 45 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1056110 | O.1056110.01 | A.1056110.01.02 | Rental Acid equipment | ENI AUSTRALIA LIMITED | BLACKTIP P5 | VALARIS 247 | J.24.098268 | RPI | CT-NONSERV | Low | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2024-07-15 |  | 2024-07-15 | 2024-07-31 23:59 |  |  | AUS West Coast WS | CNevarez2 | 2024-09-25 16:39 | EAcosta |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 1 |  |  |  | 43.8 | 33.3 | 100 | 25 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1055580 | O.1055580.01 | A.1055580.01.01 | Tariki-5A 6.125" Logging | NEW ZEALAND ENERGY CORPORATION | TARIKI-5A | NOVA-1 | J.24.058772 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-11-29 01:00 | 2024-10-14 |  | 2024-11-29 | 2024-12-09 23:59 |  | 2024-12-10 00:59 | New Plymouth WL | CKok3 | 2024-12-04 09:18 | YLee25 |  | No |  |  |  |  | Cheryl Kok |  | 556250 | 3 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 4 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1055244 | O.1055244.01 | A.1055244.01.04 | Inpex-CSS WP 2_8.5" OH | INPEX OPERATIONS AUSTRALIA PTY LTD | WEST PERON-1, WEST PERON-2 | VALARIS 247 | J.24.154950 | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-10-12 | 2024-10-16 | 2024-10-21 | 2024-10-31 | 2025-01-09 23:59 | 2025-01-04 | 2025-01-09 23:59 | New Burn WL | CKok3 | 2025-04-14 21:55 | WMaung |  | Yes |  |  |  | ROE WL Jakarta | Jarrod Sedmak |  | 0 | 13 |  | L1 - Support RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1055244 | O.1055244.01 | A.1055244.01.03 | Inpex-CSS WP 2_12.25in OH | INPEX OPERATIONS AUSTRALIA PTY LTD | WEST PERON-2 | VALARIS 247 | J.24.154949 | RPE | ES-OH-NO | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-10-01 | 2024-09-17 |  | 2024-10-01 | 2024-10-09 23:59 |  | 2024-10-09 23:59 | New Burn WL | CKok3 | 2024-12-11 17:30 | MElsanousi |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 4 |  | L0 - No RO |  | 91.7 | 100 | 100 | 75 | 90 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1055244 | O.1055244.01 | A.1055244.01.02 | Inpex CSS WP 1_ 8.5in OH | INPEX OPERATIONS AUSTRALIA PTY LTD | WEST PERON-1, WEST PERON-2 | VALARIS 247 | J.24.054044 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-08-01 | 2024-08-05 |  | 2024-08-20 | 2024-09-18 23:59 |  | 2024-09-18 23:59 | New Burn WL | MElsanousi | 2024-09-18 19:06 | miqbal13 |  | Yes |  |  |  | ROE WL Jakarta | Jarrod Sedmak |  | 37388.98 | 12 |  | L1 - Support RO |  | 100 | 100 | 100 | 100 | 100 |  | 2 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1055244 | O.1055244.01 | A.1055244.01.01 | Inpex-CSS WP 1 _ 12.25in OH | INPEX OPERATIONS AUSTRALIA PTY LTD | WEST PERON-1, WEST PERON-2 | VALARIS 247 | J.24.054033 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-07-31 | 2024-07-20 |  | 2024-07-31 | 2024-08-08 23:59 |  | 2024-08-08 23:59 | New Burn WL | MElsanousi | 2024-09-16 10:13 | MBu2 |  | No |  |  |  |  | Jarrod Sedmak |  | 247999.82 | 4 |  | L0 - No RO |  | 100 | 100 | 0 | 100 | 90 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1055015 | O.1055015.01 | A.1055015.01.01 | SLK ops for CO2 injection Test | AWE PERTH PTY LTD | DONGARA-23 | RIGLESS - AUSTRALIA | J.24.051364 | RPI | PS-SLK-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-02-22 | 2024-02-20 | 2024-02-21 16:00 | 2024-02-22 | 2024-02-26 23:59 | 2024-02-27 | 2024-02-26 23:59 | New Burn WL | PRoche | 2024-08-21 13:52 | FDPSystemUser | M.1000188.02.55 | No |  |  |  |  | Peter Roche |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1054254 | O.1054254.01 | A.1054254.01.01 | Jan-2024_Operation | SANTOS LIMITED | MOOMBA 316, MOOMBA 317, NEPHRITE SOUTH 14, COCINERO 16 |  | J.24.041717 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2024-02-13 | 2024-01-16 |  | 2024-01-17 | 2024-02-29 23:59 |  | 2024-02-29 23:59 | Moomba WL | ymoradi2 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 17 |  | L0 - No RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Adel Mohammad Alhashemi | WL Production Services
P.1054254 | O.1054254.01 | A.1054254.01.02 | 2nd SCMT | SANTOS LIMITED | MOOMBA 316, MOOMBA 317 |  | J.24.041816 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-01-29 | 2024-01-19 | 2024-01-20 | 2024-01-20 | 2024-01-29 23:59 | 2024-01-30 | 2024-01-29 23:59 | Moomba WL | ymoradi2 | 2024-05-23 15:43 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 1 |  | L0 - No RO |  | 75 | 0 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Adel Mohammad Alhashemi | WL Production Services
P.1053849 | O.1053849.01 | A.1053849.01.01 | ENI_BT P5 | ENI AUSTRALIA B.V. | BLACKTIP P4 | VALARIS 247 | J.24.037212 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2024-09-15 | 2024-09-01 |  | 2024-09-15 | 2024-12-01 23:59 |  | 2024-12-01 23:59 | New Burn WL | JDukas | 2024-08-01 10:26 | OAzarenko |  | No |  |  |  |  | Justin Dukas |  | 0 | 23 |  | L0 - No RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1053849 | O.1053849.01 | A.1053849.01.02 | ENI_BTP P5_OH | ENI AUSTRALIA B.V. | BLACKTIP P4 | VALARIS 247 | J.24.104600 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2024-08-17 | 2024-08-15 |  | 2024-08-17 | 2024-09-05 23:59 |  | 2024-09-05 23:59 | New Burn WL | MElsanousi | 2024-08-01 10:25 | FDPSystemUser |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 0 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1053459 | O.1053459.03 | A.1053459.03.01 | chevron choke Line package | CHEVRON APG ABU PERTH. |  | RIGLESS - AUSTRALIA | J.25.033788 | RPI | PSVS-PRODX-RENTAL | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Started | Not Required | 2025-01-24 | 2025-01-24 |  | 2025-01-24 | 2025-04-24 23:59 |  | 2025-07-31 23:59 | APG TS | AEl-wakil | 2025-04-16 13:48 | MWaseem2 |  | No |  | [AUJN-PSVS] - AU - Jandakot PSVS |  |  | Ahmed El-Wakil |  | 0 | 1 |  | L0 - No RO |  | 58.3 | 100 | 100 | 75 | 80 |  | 0 |  |  |  | 0 |  |  |  | Muhammad Fahd Waseem | TS Production Testing
P.1053459 | O.1053459.02 | A.1053459.02.03 | 2nd Pad Barrow Island | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 WATER INJECTION WELL D-WI1 | RIGLESS - AUSTRALIA | J.25.004898 | RPI | TSWT-FLOWBACK-JOB | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-03-15 | 2025-06-26 | 2025-09-23 | 2025-09-23 | 2025-11-22 23:59 | 2025-11-23 | 2025-07-14 23:59 | APG TS | EKondratiev | 2025-11-06 20:21 | IVargas3 |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Akashdeep Saini |  | 443377 | 2 |  | L0 - No RO |  | 100 | 83.3 | 50 | 75 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Ahmed El-Wakil | TS Surface Testing
P.1053459 | O.1053459.02 | A.1053459.02.01 | SWT Barrow Island 1st Pad | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 WATER INJECTION WELL D-WI1 | RIGLESS - AUSTRALIA | J.24.054967 | RPI | TSWT-FLOWBACK-JOB | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-06-19 | 2025-03-15 | 2025-06-29 16:00 | 2025-06-30 | 2025-10-16 23:59 | 2025-09-17 | 2025-10-01 23:59 | APG TS | EKondratiev | 2025-08-19 10:08 | EKondratiev |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Ahmed El-Wakil |  | 0 | 1 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 3 |  |  |  | 0 |  |  |  | Muhammad Fahd Waseem | TS Surface Testing
P.1053459 | O.1053459.02 | A.1053459.02.02 | Design - CEC | CHEVRON APG ABU PERTH. |  | RIGLESS - AUSTRALIA | J.24.097337 | RPI | TSWT-NO-OP | High | Confirmed | Design - CEC |  | Not Required | Not Required | Design Completed |  | 2024-06-17 |  | 2024-06-17 | 2024-06-22 23:59 |  |  | APG TS | EKondratiev | 2024-06-24 18:27 | fkomul |  | No |  |  |  |  | Evgeniy Kondratiev |  | 0 | 4 |  |  |  | 75 | 66.7 | 100 | 50 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1053459 | O.1053459.01 | A.1053459.01.02 | TCP Barrow island E-WI2 | CHEVRON APG ABU PERTH. |  | RIGLESS - AUSTRALIA | J.24.057210 | RPI | TCP-PERM-JOB | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2024-03-01 |  | 2025-03-01 | 2025-04-15 23:59 |  |  | APG TS | EKondratiev | 2025-02-20 10:50 | MWaseem2 |  | No |  |  |  |  | Evgeniy Kondratiev |  | 0 | 1 |  |  |  | 20.8 | 0 | 0 | 0 | 6.3 |  | 3 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1053459 | O.1053459.01 | A.1053459.01.03 | Product sale | CHEVRON APG ABU PERTH. |  | RIGLESS - AUSTRALIA | J.24.082566 | RPI | TCP-NO-OP | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2024-07-01 |  | 2024-07-01 | 2024-09-30 23:59 |  |  | APG TS | EKondratiev | 2024-08-29 08:00 | EKondratiev |  | No |  |  |  |  | Evgeniy Kondratiev |  | 0 | 1 |  |  |  | 25 | 33.3 | 100 | 50 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1053459 | O.1053459.01 | A.1053459.01.01 | TCP operations | CHEVRON APG ABU PERTH. |  | RIGLESS - AUSTRALIA | J.24.034701 | RPI | TCP-PERM-JOB | Medium | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2024-03-01 | 2025-01-31 16:00 | 2025-02-01 | 2025-02-14 23:59 | 2025-02-15 |  | APG TS | EKondratiev | 2024-05-03 11:03 | EKondratiev |  | No |  |  |  |  | Evgeniy Kondratiev |  | 0 | 1 |  |  |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1053176 | O.1053176.01 | A.1053176.01.01 | ENI BT Intervention 2024 (Commercial) | ENI AUSTRALIA B.V. | BLACKTIP P1, BLACKTIP P2, BLACKTIP P3 |  | J.24.124338 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2024-07-26 | 2024-06-27 |  | 2024-06-27 | 2024-08-07 23:59 |  | 2024-08-07 23:59 | New Burn WL | JSedmak | 2024-07-31 10:54 | AMuhammad9 |  | Yes |  |  |  |  | Olesia Azarenko |  | 1001360.34 | 1 |  | L0 - No RO |  | 58.3 | 16.7 | 0 | 50 | 37.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1052473 | O.1052473.02 | A.1052473.02.02 | Lorelle-3 | ENERGYCAPTURE PTY LIMITED |  | SAVANNA 185 | J.25.102024 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Required | Design Completed | 2024-01-09 11:00 | 2026-02-06 | 2026-02-07 | 2026-02-07 | 2026-02-10 23:59 | 2026-02-11 | 2026-02-17 | Roma WL | CKok3 | 2025-11-08 12:11 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 4 |  | L3 - Full RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1052473 | O.1052473.02 | A.1052473.02.01 | Elixir OH Well 1 2025 | ENERGYCAPTURE PTY LIMITED |  | SAVANNA 185 | J.25.102023 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2025-09-16 | 2025-09-16 | 2025-09-15 23:00 | 2025-09-16 | 2025-09-19 23:59 | 2025-09-19 23:00 | 2025-09-26 | Roma WL | CKok3 | 2025-05-23 19:02 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1052473 | O.1052473.01 | A.1052473.01.01 | ELIXIR 8.5" Section | ENERGYCAPTURE PTY LIMITED | DAYDREAM-2 | SLR 185 | J.23.167741 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-11-20 | 2023-11-20 |  | 2023-11-20 | 2023-11-23 23:59 |  | 2023-11-30 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 224119.56 | 2 |  | L3 - Full RO |  | 91.7 | 66.7 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1052370 | O.1052370.01 | A.1052370.01.01 | 6.125in TD_DayDream-2 | ENERGYCAPTURE PTY LIMITED | DAYDREAM-2 | SLR 185 | J.23.169303 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-12-07 | 2023-12-07 |  | 2023-12-07 | 2023-12-12 23:59 |  | 2023-12-15 | Roma WL | SAli63 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 192066.28 | 4 |  | L2 - Shift RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1051694 | O.1051694.01 | A.1051694.01.01 | Esso P&A Cased Hole HELIX Q7000_PA (Remaining 2 Wells) | ESSO AUSTRALIA LTD | GUDGEON-1, TERAKIHI-1 | HELIX Q7000 | J.24.022742 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-06-20 05:00 | 2024-05-25 |  | 2024-06-20 05:00 | 2024-08-14 04:59 |  | 2024-08-14 04:59 | New Burn WL | VOliveira5 | 2024-08-15 13:33 | MSayed8 |  | No |  |  |  |  | Peter Roche |  | 1111953 | 21 |  | L0 - No RO |  | 100 | 100 | 0 | 100 | 90 |  | 7 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1051694 | O.1051694.01 | A.1051694.01.02 | ESSO P&A SLK Ops_Q7000 | ESSO AUSTRALIA LTD | GUDGEON-1, TERAKIHI-1 | HELIX Q7000 | J.24.103008 | RPI | PS-SLK-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Not Required | Design Completed | 2024-06-24 | 2024-05-25 |  | 2024-06-21 | 2024-08-14 23:59 |  | 2024-08-14 23:59 | New Burn WL | MElsanousi | 2024-06-25 01:54 | MRahadian3 |  | No |  |  |  |  | Chris Rowand |  | 0 | 6 |  | L0 - No RO |  | 79.2 | 33.3 | 0 | 0 | 33.8 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1051680 | O.1051680.01 | A.1051680.01.03 | North Endeavour_SLK | SAPURA AUSTRALIA PTY LTD | LAMINARIA 2, LAMINARIA 8, CORALLINA 3 ST1, EAST CORALLINA 1, CORALLINA 2 ST3, LAMINARIA 6, LAMINARIA 5 ST1 | SAPURAKENCANA CONSTRUCTOR | J.24.149358 | RPI | PS-SLK-Rental-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2024-09-30 | 2024-09-12 |  | 2024-09-30 | 2025-02-28 23:59 |  | 2025-02-28 23:59 | New Burn WL | MElsanousi | 2025-02-25 12:32 | FDPSystemUser |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 3 |  | L0 - No RO |  | 79.2 | 83.3 | 0 | 12.5 | 52.5 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1051680 | O.1051680.01 | A.1051680.01.02 | North Endeavour_WL CIS | SAPURA AUSTRALIA PTY LTD | LAMINARIA 2, LAMINARIA 8, EAST CORALLINA 1, CORALLINA 3 ST1, LAMINARIA 6, CORALLINA 2 ST3, LAMINARIA 5 ST1 | SAPURAKENCANA CONSTRUCTOR | J.24.135020 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-09-30 | 2024-09-13 |  | 2024-09-30 | 2024-12-29 23:59 |  | 2024-12-29 23:59 | New Burn WL | MElsanousi | 2025-02-25 12:30 | LDoudilim |  | No |  |  |  |  | Yasser Moradi |  | 165650 | 1 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 2 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1051680 | O.1051680.01 | A.1051680.01.04 | North Endeavour_WL CIS 2025 | SAPURA AUSTRALIA PTY LTD | EAST CORALLINA 1, LAMINARIA 6, LAMINARIA 5 ST1 | SAPURAKENCANA CONSTRUCTOR | J.24.193143 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-12-30 | 2024-12-13 |  | 2024-12-30 | 2025-03-30 23:59 |  | 2025-03-30 23:59 | New Burn WL | MElsanousi | 2025-02-20 13:10 | LDoudilim |  | No |  |  |  |  | Ihab Wahbi |  | 429750 | 1 |  | L0 - No RO |  | 100 | 66.7 | 100 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1051680 | O.1051680.01 | A.1051680.01.01 | 7 x wells - Suspension | SAPURA AUSTRALIA PTY LTD | LAMINARIA 2 | SAPURAKENCANA CONSTRUCTOR | J.24.022650 | RPI | PS-SLK-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-09-01 | 2024-08-25 08:00 |  | 2024-09-01 | 2024-09-08 23:59 |  | 2024-09-08 23:59 | New Burn WL | PRoche | 2024-08-02 11:16 | MAlhashemi |  | No |  |  |  |  | Mohammad Adel Mohammad Alhashemi |  | 0 | 1 |  | L0 - No RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 2 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1051673 | O.1051673.01 | A.1051673.01.02 | Bleed off package for PNG | EXXONMOBIL PNG LIMITED | ANGORE C1, ANGORE C2 | NABORS 702 | J.24.148257 | RPI | TSWT-NO-OP | High | Operationally Complete | Close - PSD |  | Not Required | Not Required | Design Completed |  | 2024-04-12 |  | 2024-09-10 | 2024-11-08 23:59 |  |  | Port Moresby TS | EKondratiev | 2025-01-02 15:24 | EKondratiev |  | No |  | [PGPM-TSWT] - PGPOM-TSW |  |  | Evgeniy Kondratiev |  | 47029 | 1 |  |  |  | 100 | 50 | 100 | 100 | 85 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1051673 | O.1051673.01 | A.1051673.01.01 | Bleed-off package | EXXONMOBIL PNG LIMITED | ANGORE C1, ANGORE C2 | NABORS 702 | J.24.022620 | RPI | TSWT-NOSEPNOVX-JOB | High | Confirmed | Design - CEC |  | Not Required | Not Required | In Progress |  | 2024-01-01 |  | 2024-05-31 | 2024-07-29 23:59 |  |  | Port Moresby TS | EKondratiev | 2025-01-02 15:21 | EKondratiev |  | No |  | [PGPM-TSWT] - PGPOM-TSW |  |  | Evgeniy Kondratiev |  | 148354 | 0 |  | L0 - No RO |  | 91.7 | 83.3 | 100 | 25 | 70 |  | 1 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1051534 | O.1051534.01 | A.1051534.01.01 | TCP Halyard-2 | SANTOS LIMITED | HALYARD-2 | OCEAN APEX | J.24.021004 | RPI | TCP-PERM-JOB | High | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2024-10-07 | 2024-03-01 |  | 2024-10-07 | 2024-11-06 23:59 |  | 2024-11-06 23:59 | APG TS | EKondratiev | 2024-10-29 10:24 | EKondratiev |  | No |  | [AUSG-TCP] - |  |  | Evgeniy Kondratiev |  | 96527.06 | 1 |  |  |  | 100 | 100 | 100 | 87.5 | 96.3 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1051391 | O.1051391.01 | A.1051391.01.04 | Maintenance in Karratha | WOODSIDE ENERGY LTD |  | TRANSOCEAN ENDURANCE | J.25.155776 | RPS | STM-EQPRNT | Low | Confirmed | Design - CEC |  | In Progress | Not Required | In Progress | 2025-09-18 | 2025-09-18 | 2025-09-14 | 2025-09-18 | 2025-09-26 | 2025-09-24 | 2025-10-18 23:59 | AUS West Coast WS | ARahi | 2025-10-01 16:13 | CNevarez2 |  | No |  |  |  |  | Ramadhani Adi Negara |  | 0 | 0 |  | L0 - No RO |  | 75 | 50 | 100 | 25 | 60 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Production Services
P.1051391 | O.1051391.01 | A.1051391.01.01 | Lambert West OHGP | WOODSIDE ENERGY LTD | LDA-02 | TRANSOCEAN ENDURANCE | J.24.043103 | RPS | SMS-OHGP-APS | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2025-06-17 | 2025-06-15 | 2025-06-15 | 2025-06-17 | 2025-06-30 23:59 | 2025-07-24 | 2025-10-27 23:59 | AUS West Coast WS | radinegara | 2025-08-29 15:23 | CNevarez2 |  | Yes |  |  |  |  | Ramadhani Adi Negara |  | 413351 | 1 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 11 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Production Services
P.1051391 | O.1051391.01 | A.1051391.01.03 | LDA-02 Commissioning | WOODSIDE ENERGY LTD | LDA-02 | TRANSOCEAN ENDURANCE | J.25.099481 | RPS | STM-EQPRNT | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-06-01 23:59 | 2025-06-02 | 2025-06-01 23:59 | AUS West Coast WS | ISafarli | 2025-07-03 12:26 | ISafarli |  | No |  |  |  |  | Ramadhani Adi Negara |  | 0 | 0 |  | L0 - No RO |  | 87.5 | 100 | 100 | 50 | 85 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Production Services
P.1051391 | O.1051391.01 | A.1051391.01.02 | SMS Equipment Rent & Personnel Retainer | WOODSIDE ENERGY LTD |  | TRANSOCEAN ENDURANCE | J.25.083208 | RPS | STM-EQPRNT | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2025-04-13 | 2025-04-13 | 2025-04-13 | 2025-04-13 | 2025-05-11 23:59 | 2025-05-14 | 2025-05-13 23:59 | AUS West Coast WS | radinegara | 2025-05-01 10:27 | FDPSystemUser |  | No |  |  |  |  | Ramadhani Adi Negara |  | 0 | 0 |  | L0 - No RO |  | 81.3 | 50 | 100 | 25 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Production Services
P.1051253 | O.1051253.02 | A.1051253.02.01 | Pipe Recovery for POW-04B | OMV NEW ZEALAND LTD |  |  | J.24.140938 | RPE | ES-OH-Ops | InComplete | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2024-11-01 |  | 2024-11-01 | 2025-01-01 23:59 |  |  | New Plymouth WL | CKok3 | 2025-05-21 13:56 | CKok3 |  | No |  |  |  |  | Cheryl Kok |  | 0 | 0 |  | L0 - No RO |  | 8.3 | 0 | 0 | 0 | 2.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1051253 | O.1051253.01 | A.1051253.01.01 | POS-01B Sonic Scanner | OMV NEW ZEALAND LTD |  |  | J.24.019743 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-09-01 | 2024-09-01 |  | 2024-09-01 | 2024-10-01 23:59 |  | 2024-10-01 23:59 | New Plymouth WL | CKok3 | 2024-07-31 14:33 | CKok3 |  | No |  |  |  |  | Cheryl Kok |  | 0 | 1 |  | L0 - No RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1051132 | O.1051132.01 | A.1051132.01.02 | Well 2 | QGC | Well #1 |  | J.24.019282 | RPI | CT-SCTRL | Medium | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2024-02-01 |  | 2025-01-01 | 2025-01-09 23:59 |  |  | AUS East Coast WS | radinegara | 2024-05-14 12:03 | CNevarez2 |  | No |  |  |  |  | Feras Manja |  | 0 | 1 |  |  |  | 6.3 | 0 | 0 | 0 | 2.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1051132 | O.1051132.01 | A.1051132.01.03 | Well 3 | QGC | Well #1 |  | J.24.019283 | RPI | CT-SCTRL | Medium | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2024-06-01 |  | 2024-06-01 | 2024-06-09 23:59 |  |  | AUS East Coast WS | radinegara | 2024-05-14 10:53 | CNevarez2 |  | No |  |  |  |  | Feras Manja |  | 0 | 1 |  |  |  | 6.3 | 0 | 0 | 0 | 2.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1051132 | O.1051132.01 | A.1051132.01.01 | Well 1 | QGC | Well #1 |  | J.23.156451 | RPI | CT-SCTRL | Medium | Unconfirmed - 50% | Design - CEC |  | Not Started | Not Started | Not Started |  | 2024-01-01 |  | 2024-01-01 | 2024-01-09 23:59 |  |  | AUS East Coast WS | radinegara | 2023-10-19 19:59 | radinegara |  | No |  |  |  |  | Feras Manja |  | 0 | 1 |  |  |  | 6.3 | 0 | 0 | 0 | 2.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1050952 | O.1050952.01 | A.1050952.01.01 | Blacktip P3 - RSA SRS | ENI AUSTRALIA B.V. | BLACKTIP P3 | VALARIS 247 | J.24.018486 | RPE | FSA-CH-JOB | High | Cancelled | Close - PSD |  | Design Completed | Not Started | Not Started | 2024-01-01 | 2023-12-01 |  | 2024-01-01 | 2024-03-31 23:59 |  | 2024-03-31 23:59 | APG TS | fkomul | 2023-10-30 16:40 | EKondratiev |  | No |  |  |  |  | Ferly Komul |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Downhole Reservoir Testing
P.1050717 | O.1050717.01 | A.1050717.01.01 | Ramsay-1_OH | GOLD HYDROGEN LTD | RAMSAY 1 | SAVANNA DRILLING #406 | J.23.152928 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-10-22 22:00 | 2023-10-21 15:00 |  | 2023-10-22 22:00 | 2023-10-29 21:59 |  | 2023-11-01 | Moomba WL | SAli63 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 257426.9 | 3 |  | L3 - Full RO |  | 100 | 83.3 | 0 | 100 | 85 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1050717 | O.1050717.01 | A.1050717.01.02 | Ramsay-2_OH | GOLD HYDROGEN LTD | RAMSAY 2 | SAVANNA DRILLING #406 | J.23.167253 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2023-11-17 22:00 | 2023-11-16 15:00 |  | 2023-11-17 22:00 | 2023-11-24 21:59 |  | 2023-11-27 | Moomba WL | AKavooris | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 327719.3 | 3 |  | L3 - Full RO |  | 100 | 66.7 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1050717 | O.1050717.01 | A.1050717.01.03 | Ramsay 2 - Suite 2 | GOLD HYDROGEN LTD | RAMSAY 2, RAMSAY 1 | SAVANNA DRILLING #406 | J.23.169305 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-11-25 22:00 | 2023-11-17 |  | 2023-11-25 22:00 | 2023-12-02 21:59 |  | 2023-12-05 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Jakarta | Shameer Mumtaz Ali |  | 327719.3 | 6 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1050390 | O.1050390.01 | A.1050390.01.02 | ENI Blacktip P5 - RSA | ENI AUSTRALIA B.V. | BLACKTIP P5 | VALARIS 247 | J.24.069623 | RPE | FSA-SF-JOB | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-03-01 | 2024-09-05 | 2025-03-01 | 2025-03-01 | 2025-05-10 23:59 | 2025-05-11 | 2025-05-10 23:59 | APG TS | fkomul | 2025-04-23 09:14 | MWaseem2 |  | No |  | [AUJN-DST] - AU - Jandakot TST |  |  | Ferly Komul |  | 122031 | 1 |  |  |  | 100 | 83.3 | 100 | 100 | 95 |  | 3 |  |  |  | 0 |  |  |  | Muhammad Fahd Waseem | TS Downhole Reservoir Testing
P.1050390 | O.1050390.01 | A.1050390.01.01 | ENI Blacktip P5 - SWT | ENI AUSTRALIA B.V. | BLACKTIP P5 | VALARIS 247 | J.24.017373 | RPI | TSWT-FLOWBACK-JOB | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-01-31 | 2025-01-30 | 2025-01-30 16:00 | 2025-01-31 | 2025-05-03 23:59 | 2025-05-04 | 2025-05-03 23:59 | APG TS | fkomul | 2025-04-23 08:49 | MWaseem2 |  | No |  |  |  | APG TS | Ferly Komul |  | 1329835.73 | 3 |  | L3 - Full RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 2 |  |  |  | 0 |  |  |  | Muhammad Fahd Waseem | TS Surface Testing
P.1049009 | O.1049009.02 | A.1049009.02.12 | Q2-2025_WL_MEFF | SANTOS LIMITED | EXETER 4, FINUCANE SOUTH 2H, FINUCANE SOUTH 3H, MUTINEER 12, MUTINEER 15H, MUTINEER 4, MUTINEER 5, MUTINEER 9 | NOBLE APEX | J.25.059679 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2025-01-05 | 2025-02-01 | 2025-01-30 16:00 | 2025-04-23 | 2025-06-26 23:59 | 2025-06-16 | 2025-07-21 23:59 | New Burn WL | ymoradi2 | 2025-07-04 12:29 | NCandra |  | No |  |  |  | ROE WL Mumbai | Yasser Moradi |  | 0 | 4 |  | L3 - Full RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1049009 | O.1049009.02 | A.1049009.02.11 | Q2-2025_SLK_MEFF | SANTOS LIMITED | MUTINEER 15H, MUTINEER 4, MUTINEER 5, MUTINEER 9, MUTINEER 12, EXETER 4 | NOBLE APEX | J.25.059677 | RPI | PS-SLK-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-03-12 | 2025-02-01 | 2025-03-30 16:00 | 2025-03-31 | 2025-05-14 23:59 | 2025-07-14 | 2025-05-15 23:59 | New Burn WL | ymoradi2 | 2025-04-27 02:12 | VQuoc |  | No |  |  |  |  | Yasser Moradi |  | 0 | 2 |  | L0 - No RO |  | 83.3 | 100 | 100 | 75 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1049009 | O.1049009.02 | A.1049009.02.10 | Q1-2025_WL_MEFF | SANTOS LIMITED | EXETER 4, FINUCANE SOUTH 2H, FINUCANE SOUTH 3H, MUTINEER 12, MUTINEER 15H, MUTINEER 4, MUTINEER 5, MUTINEER 9 | NOBLE APEX | J.24.172568 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-11-13 | 2025-01-01 | 2025-01-01 | 2025-03-01 | 2025-03-30 00:59 | 2025-04-04 | 2025-04-01 23:59 | New Burn WL | ymoradi2 | 2025-03-27 15:04 | NCandra |  | No |  |  |  | ROE WL Mumbai | Yasser Moradi |  | 74480 | 5 |  | L1 - Support RO |  | 100 | 100 | 100 | 100 | 100 |  | 4 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1049009 | O.1049009.02 | A.1049009.02.09 | H2Q4-2024_SLK_MEFF | SANTOS LIMITED | FINUCANE SOUTH 2H, FINUCANE SOUTH 3H, MUTINEER 15H, MUTINEER 4, MUTINEER 5 | NOBLE APEX | J.24.172565 | RPI | PS-SLK-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-10-26 | 2024-10-22 |  | 2024-10-26 | 2025-01-05 23:59 |  | 2025-01-05 23:59 | New Burn WL | ymoradi2 | 2025-03-15 21:47 | miqbal13 |  | No |  |  |  |  | Yasser Moradi |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 100 | 100 | 75 | 87.5 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1049009 | O.1049009.02 | A.1049009.02.08 | Q1-2025_SLK_MEFF | SANTOS LIMITED | MUTINEER 15H, MUTINEER 4, MUTINEER 5, MUTINEER 9, MUTINEER 12, EXETER 4 | NOBLE APEX | J.24.148539 | RPI | PS-SLK-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-02-09 | 2025-01-01 |  | 2025-02-28 | 2025-03-15 06:00 |  | 2025-02-25 06:00 | New Burn WL | ymoradi2 | 2025-03-15 19:36 | VQuoc |  | No |  |  |  |  | Yasser Moradi |  | 0 | 2 |  | L0 - No RO |  | 83.3 | 100 | 100 | 75 | 87.5 |  | 6 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1049009 | O.1049009.02 | A.1049009.02.07 | MEFF_P&A_WL_Cont'd | SANTOS LIMITED | EXETER 4, FINUCANE SOUTH 2H, FINUCANE SOUTH 3H, MUTINEER 12, MUTINEER 15H, MUTINEER 4, MUTINEER 5, MUTINEER 9 | NOBLE APEX | J.24.148533 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-08-28 | 2024-09-06 |  | 2024-11-22 | 2025-01-06 00:59 |  | 2025-01-08 23:59 | New Burn WL | ymoradi2 | 2025-02-19 13:48 | NCandra |  | No |  |  |  | ROE WL Mumbai | Yasser Moradi |  | 74480 | 5 |  | L2 - Shift RO |  | 100 | 100 | 100 | 100 | 100 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1049009 | O.1049009.02 | A.1049009.02.06 | MEFF P&A SLK | SANTOS LIMITED | FINUCANE SOUTH 2H, FINUCANE SOUTH 3H | NOBLE APEX | J.24.134290 | RPI | PS-SLK-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-07-29 | 2024-07-24 |  | 2024-07-29 | 2024-08-30 23:59 |  | 2024-08-30 23:59 | New Burn WL | VQuoc | 2024-10-07 19:00 | ymoradi2 |  | No |  |  |  |  | Mohammad Adel Mohammad Alhashemi |  | 0 | 2 |  | L0 - No RO |  | 75 | 100 | 100 | 75 | 85 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1049009 | O.1049009.02 | A.1049009.02.03 | MEFF P&A SLK | SANTOS LIMITED | FLETCHER 5H, EXETER 4, FINUCANE SOUTH 3H, MUTINEER 15H, FINUCANE SOUTH 2H, MUTINEER 12, MUTINEER 4, MUTINEER 5, MUTINEER 9 | NOBLE APEX | J.24.106177 | RPI | PS-SLK-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-06-28 | 2024-06-02 |  | 2024-06-28 | 2024-09-02 12:00 |  | 2024-11-05 23:59 | New Burn WL | JDukas | 2024-10-04 15:28 | FDPSystemUser |  | Yes |  |  |  |  | Justin Dukas |  | 0 | 2 |  | L0 - No RO |  | 83.3 | 100 | 100 | 75 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1049009 | O.1049009.02 | A.1049009.02.01 | MEFF P&A | SANTOS LIMITED | FLETCHER 5H, EXETER 4, FINUCANE SOUTH 2H, FINUCANE SOUTH 3H, MUTINEER 12, MUTINEER 15H, MUTINEER 4, MUTINEER 5, MUTINEER 9 | NOBLE APEX | J.24.011212 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2024-06-28 | 2024-05-20 |  | 2024-06-28 | 2024-09-19 23:59 |  | 2024-09-25 23:59 | New Burn WL | JDukas | 2024-09-05 20:57 | APutra7 |  | Yes |  |  |  | ROE WL Mumbai | Jarrod Sedmak |  | 71332 | 3 |  | L1 - Support RO |  | 91.7 | 66.7 | 0 | 75 | 70 |  | 10 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1049009 | O.1049009.02 | A.1049009.02.02 | MEFF P&A part 2 | SANTOS LIMITED |  | NOBLE APEX | J.24.106175 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-11-03 | 2024-11-02 |  | 2024-11-03 | 2024-11-04 23:59 |  | 2024-11-04 23:59 | New Burn WL | JDukas | 2024-08-29 17:58 | ymoradi2 |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 0 | 1 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1049009 | O.1049009.02 | A.1049009.02.04 | MEFF P&A part 2 SLK | SANTOS LIMITED |  | NOBLE APEX | J.24.106180 | RPI | PS-SLK-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-11-01 | 2025-01-26 |  | 2025-01-26 | 2025-06-26 23:59 |  | 2025-04-01 23:59 | New Burn WL | JDukas | 2024-08-29 16:07 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 0 | 0 |  | L2 - Shift RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1049009 | O.1049009.02 | A.1049009.02.05 | WL Ops_Finucane South-2H & 3H | SANTOS LIMITED | EXETER 4, FINUCANE SOUTH 2H, FINUCANE SOUTH 3H, MUTINEER 12, MUTINEER 15H, MUTINEER 4, MUTINEER 5, MUTINEER 9 | NOBLE APEX | J.24.133307 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2024-05-07 | 2024-05-18 |  | 2024-08-01 | 2024-08-30 00:59 |  | 2024-09-01 23:59 | New Burn WL | ymoradi2 | 2024-08-21 12:00 | APutra7 |  | No |  |  |  | ROE WL Mumbai | Jarrod Sedmak |  | 0 | 5 |  | L1 - Support RO |  | 100 | 58.3 | 0 | 87.5 | 73.8 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1049009 | O.1049009.01 | A.1049009.01.01 | Halyard-2 Infill well-WL | SANTOS LIMITED | HALYARD-2 | NOBLE APEX | J.24.011211 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-09-18 | 2024-10-01 |  | 2024-10-05 | 2024-10-23 23:59 |  | 2024-10-23 23:59 | New Burn WL | JDukas | 2025-02-19 13:47 | NCandra |  | No |  |  |  | ROE WL Mumbai | Yasser Moradi |  | 127934 | 4 |  | L2 - Shift RO |  | 100 | 100 | 0 | 100 | 90 |  | 4 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1049009 | O.1049009.01 | A.1049009.01.02 | Halyard-2_Infill well_SLK | SANTOS LIMITED | HALYARD-2 | NOBLE APEX | J.24.106178 | RPI | PS-SLK-Ops | Medium | Confirmed | Prepare - Mob |  | Design Completed | Not Required | Design Completed | 2024-10-25 | 2024-10-07 |  | 2024-10-25 | 2024-11-26 23:59 |  | 2024-11-26 23:59 | New Burn WL | JDukas | 2024-10-28 08:59 | SGriffin6 |  | No |  |  |  | ROE WL Mumbai | Yasser Moradi |  | 0 | 4 |  | L2 - Shift RO |  | 83.3 | 100 | 0 | 0 | 55 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1048941 | O.1048941.01 | A.1048941.01.01 | Well test of Hydrogen | GOLD HYDROGEN PTY LTD |  | RIGLESS - AUSTRALIA | J.23.128846 | RPI | TSWT-SEPONLY-JOB | High | Unconfirmed - 10% | Design - CEC |  | In Progress | Not Started | In Progress | 2023-12-01 | 2023-11-15 |  | 2023-12-01 | 2023-12-31 23:59 |  | 2023-12-31 23:59 | APG TS | EKondratiev | 2024-11-19 20:14 | FDPSystemUser |  | No |  |  |  |  | Evgeniy Kondratiev |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 1 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1048623 | O.1048623.01 | A.1048623.01.08 | Cooper Equipment charge | COOPER ENERGY LIMITED |  | HELIX Q7000 | J.24.068724 | RPI | CT-NONSERV | Low | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2024-04-26 |  | 2024-04-26 | 2024-05-21 23:59 |  |  | AUS West Coast WS | SLuepongpattana | 2024-09-02 16:47 | CNevarez2 |  | No |  |  |  |  | Sureerat Luepongpattana |  | 0 | 1 |  |  |  | 50 | 33.3 | 100 | 25 | 45 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1048623 | O.1048623.01 | A.1048623.01.05 | BMG Manta 2A P&A | COOPER ENERGY LIMITED | MANTA 2A | HELIX Q7000 | J.23.129214 | RPI | CT-CEM | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2024-03-26 | 2024-03-26 |  | 2024-03-26 | 2024-04-25 23:59 |  | 2024-04-01 23:59 | AUS West Coast WS | SLuepongpattana | 2024-07-09 14:01 | CNevarez2 |  | Yes |  |  |  |  | Sureerat Luepongpattana |  | 439217.77 | 2 |  |  |  | 93.8 | 66.7 | 100 | 100 | 87.5 |  | 3 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1048623 | O.1048623.01 | A.1048623.01.04 | BMG Basker 6 | COOPER ENERGY LIMITED | BASKER 6 ST1 | HELIX Q7000 | J.23.129213 | RPI | CT-CEM | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2024-03-12 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-25 23:59 | 2024-03-28 | 2024-03-21 23:59 | AUS West Coast WS | SLuepongpattana | 2024-04-25 19:10 | CNevarez2 |  | Yes |  |  |  |  | Sureerat Luepongpattana |  | 332089.15 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 3 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1048623 | O.1048623.01 | A.1048623.01.07 | BMG Basker 5 P&A | COOPER ENERGY LIMITED | BASKER 5 | HELIX Q7000 | J.23.129230 | RPI | CT-CEM,CT-WBCLEAN, CT-MILLNOSLB,CT-PERF | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2024-03-04 | 2024-03-04 | 2024-03-04 | 2024-03-04 | 2024-03-11 23:59 | 2024-03-11 | 2024-03-21 23:59 | AUS West Coast WS | SLuepongpattana | 2024-04-25 19:07 | CNevarez2 |  | Yes |  |  |  |  | Sureerat Luepongpattana |  | 208110.46 | 2 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 4 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1048623 | O.1048623.01 | A.1048623.01.06 | BMG Basker 2 P&A | COOPER ENERGY LIMITED | BASKER 2 | HELIX Q7000 | J.23.129215 | RPI | CT-CEM | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2024-02-26 | 2024-02-26 | 2024-02-25 | 2024-02-26 | 2024-03-04 23:59 | 2024-03-08 | 2024-03-07 23:59 | AUS West Coast WS | SLuepongpattana | 2024-04-25 19:06 | CNevarez2 |  | Yes |  |  |  |  | Sureerat Luepongpattana |  | 222212.4 | 2 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 2 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1048623 | O.1048623.01 | A.1048623.01.03 | BMG Basker 4 P&A | COOPER ENERGY LIMITED | BASKER 4 | HELIX Q7000 | J.23.129212 | RPI | CT-CEM | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2024-03-08 | 2024-01-01 | 2024-02-06 16:00 | 2024-02-08 | 2024-02-25 23:59 | 2024-02-29 | 2024-03-15 | AUS West Coast WS | SLuepongpattana | 2024-04-25 19:04 | CNevarez2 |  | No |  |  |  |  | Sureerat Luepongpattana |  | 413397.84 | 2 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1048623 | O.1048623.01 | A.1048623.01.02 | BMG Basker 7 P&A | COOPER ENERGY LIMITED | BASKER 7 | HELIX Q7000 | J.23.129211 | RPI | CT-CEM | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2024-01-29 | 2023-09-27 | 2024-02-01 | 2024-02-01 | 2024-02-08 23:59 | 2024-02-09 | 2024-02-05 23:59 | AUS West Coast WS | SLuepongpattana | 2024-04-25 19:03 | CNevarez2 |  | Yes |  |  |  |  | Sureerat Luepongpattana |  | 272965.01 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1048623 | O.1048623.01 | A.1048623.01.01 | BMG Basker 3 P&A | COOPER ENERGY LIMITED | BASKER 3 | HELIX Q7000 | J.23.125448 | RPI | CT-CEM | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-11-28 | 2023-11-28 | 2023-11-30 16:00 | 2023-11-28 | 2024-01-28 23:59 | 2024-02-19 | 2024-01-28 23:59 | AUS West Coast WS | SLuepongpattana | 2024-04-25 19:02 | CNevarez2 |  | Yes |  |  |  |  | Sureerat Luepongpattana |  | 835536.51 | 2 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1048603 | O.1048603.01 | A.1048603.01.03 | HJV P&A - Bambra-3 SLK | SANTOS LIMITED |  | VALARIS 107 | J.24.051047 | RPI | PS-SLK-Rental-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-03-01 | 2024-02-25 | 2024-02-29 | 2024-03-01 | 2024-04-02 23:59 | 2024-06-30 | 2024-04-02 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 0 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1048603 | O.1048603.01 | A.1048603.01.09 | HJV P&A Gibson Platform - V107 - SLK | SANTOS LIMITED | BMA03 | VALARIS 107 | J.24.074798 | RPI | PS-SLK-Rental-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2024-08-07 | 2024-07-31 | 2024-08-05 | 2024-08-07 | 2024-10-08 23:59 | 2024-10-11 | 2024-09-05 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 3 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 2 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1048603 | O.1048603.01 | A.1048603.01.08 | HJV P&A - Simpson Bravo V107 SLK | SANTOS LIMITED | BMA03 | VALARIS 107 | J.24.074796 | RPI | PS-SLK-Rental-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2024-06-16 | 2024-06-09 | 2024-06-14 | 2024-06-16 | 2024-08-01 23:59 | 2024-08-07 | 2024-07-04 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 3 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1048603 | O.1048603.01 | A.1048603.01.07 | V107 Simpson Alpha platform P&A SLK | SANTOS LIMITED | BMA03 | VALARIS 107 | J.24.074794 | RPI | PS-SLK-Rental-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2024-04-11 | 2024-04-04 | 2024-04-09 | 2024-04-11 | 2024-06-11 23:59 | 2024-06-20 | 2024-06-11 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1048603 | O.1048603.01 | A.1048603.01.05 | HJV P&A - Gibson_V107 Operations | SANTOS LIMITED | PLATO-2, SOUTH GIBSON 1, SOUTH PLATO 03, SOUTH PLATO 01 | VALARIS 107 | J.24.056055 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-06-25 | 2024-06-25 |  | 2024-06-25 | 2024-08-02 23:59 |  | 2024-08-02 23:59 | New Burn WL | JDukas | 2024-08-07 06:30 | ALegenkyy |  | No |  |  |  |  | Mohammad Adel Mohammad Alhashemi |  | 204996 | 3 |  | L0 - No RO |  | 100 | 100 | 0 | 100 | 90 |  | 5 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1048603 | O.1048603.01 | A.1048603.01.02 | HJV P&A – Bambra-3 | SANTOS LIMITED | BAMBRA 3, TANAMI 4, TANAMI 5, SIMPSON 7, WEST SIMPSON 1 | VALARIS 107 | J.24.051038 | RPI | PS-WL-Ops | Medium | Confirmed | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-03-24 | 2024-03-12 |  | 2024-03-29 | 2024-05-14 23:59 |  | 2024-05-14 23:59 | New Burn WL | JDukas | 2024-07-15 11:55 | miqbal13 |  | No |  |  |  |  | Justin Dukas |  | 11000 | 3 |  | L0 - No RO |  | 100 | 100 | 0 | 100 | 90 |  | 3 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1048603 | O.1048603.01 | A.1048603.01.04 | Simpson Bravo P&A Operation | SANTOS LIMITED | MONET 2H, SIMPSON 4H, SIMPSON 10, SIMPSON 9 | VALARIS 107 | J.24.056053 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2024-05-18 | 2024-04-04 |  | 2024-05-18 | 2024-07-31 23:59 |  | 2024-07-08 23:59 | New Burn WL | JDukas | 2024-07-06 11:57 | miqbal13 |  | No |  |  |  |  | Justin Dukas |  | 68332 | 3 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 5 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1048603 | O.1048603.01 | A.1048603.01.06 | HJV P&A - Gibson platofrm | SANTOS LIMITED | BMA03 | VALARIS 107 | J.24.056054 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | Design Completed | 2024-08-06 | 2024-07-30 |  | 2024-08-06 | 2024-10-09 23:59 |  | 2024-10-01 23:59 | New Burn WL | JDukas | 2024-06-04 15:14 | PZuliani |  | No |  |  |  |  | Justin Dukas |  | 0 | 3 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 4 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1048603 | O.1048603.01 | A.1048603.01.01 | HJV rig based P&A | SANTOS LIMITED |  | VALARIS 107 | J.24.010545 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-07-05 | 2024-06-30 |  | 2024-07-05 | 2024-11-22 23:59 |  | 2024-10-22 23:59 | New Burn WL | JDukas | 2024-03-19 21:33 | JDukas |  | No |  |  |  |  | Justin Dukas |  | 0 | 6 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 7 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1048238 | O.1048238.01 | A.1048238.01.01 | Well Testing | MITSUI E&P AUSTRALIA PTY LTD. |  |  | J.23.121644 | RPI | TSWT-VXONLY-JOB | High | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2023-09-01 |  | 2023-09-01 | 2023-11-30 23:59 |  |  | APG TS | EKondratiev | 2024-11-19 20:21 | FDPSystemUser |  | No |  | [AUNB-TSWT] - Perth- New Burn STT |  |  | Evgeniy Kondratiev |  | 0 | 1 |  | L0 - No RO |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1048069 | O.1048069.01 | A.1048069.01.01 | Downhole sampling | SANTOS LIMITED |  | RIGLESS - AUSTRALIA | J.23.119496 | RPE | FSA-CH-JOB | High | Cancelled | Close - PSD |  | Design Completed | Not Started | Not Started | 2023-10-01 | 2023-09-01 |  | 2023-10-01 | 2023-10-31 23:59 |  | 2023-10-31 23:59 | APG TS | EKondratiev | 2023-08-29 16:54 | EKondratiev |  | No |  |  |  |  | Evgeniy Kondratiev |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Downhole Reservoir Testing
P.1047494 | O.1047494.01 | A.1047494.01.01 | Tidepole LWI Pumping Package | NORMAND SAPURA PTY LTD | TIDEPOLE 2 | SAPURAKENCANA CONSTRUCTOR | J.23.111995 | RPS | STM-MPUMP | Low | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2025-12-31 14:00 | 2026-01-01 | 2025-12-31 14:00 | 2026-01-01 | 2026-02-15 23:59 | 2026-02-15 14:00 | 2026-02-15 13:59 | AUS West Coast WS | radinegara | 2025-05-01 10:28 | CNevarez2 |  | No |  |  |  |  | Ramadhani Adi Negara |  | 0 | 0 |  |  |  | 81.3 | 33.3 | 100 | 25 | 57.5 |  | 4 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1047035 | O.1047035.02 | A.1047035.02.02 | CT P&A Terakihi-1 | ESSO AUSTRALIA LTD | TERAKIHI-1 | HELIX Q7000 | J.24.008181 | RPI | CT-CEM,CT-CIRC, CT-TOOLCON | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-07-07 | 2024-07-07 |  | 2024-07-09 07:00 | 2024-08-15 23:59 |  | 2024-08-15 23:59 | AUS West Coast WS | THahijary | 2024-09-06 15:44 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 1620327.55 | 1 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 3 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1047035 | O.1047035.02 | A.1047035.02.01 | CT P&A Gudgeon-1 | ESSO AUSTRALIA LTD | GUDGEON-1 | HELIX Q7000 | J.23.106954 | RPI | CT-CEM,CT-CIRC, CT-TOOLCON | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-05-26 | 2024-05-25 |  | 2024-05-26 07:00 | 2024-07-08 23:59 |  | 2024-07-02 23:59 | AUS West Coast WS | THahijary | 2024-09-05 13:52 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 1909667.65 | 1 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 4 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1047035 | O.1047035.02 | A.1047035.02.03 | CEC charges | ESSO AUSTRALIA LTD |  | HELIX Q7000 | J.24.048912 | RPI | CT-NONSERV | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | Not Required |  | 2024-03-03 |  | 2024-03-03 | 2024-05-03 23:59 |  |  | AUS West Coast WS | CNevarez2 | 2024-09-02 16:52 | CNevarez2 |  | No |  |  |  |  | Isabelle Lavinsky Soares |  | 0 | 1 |  |  |  | 87.5 | 66.7 | 100 | 50 | 75 |  | 2 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1047035 | O.1047035.01 | A.1047035.01.01 | Gudgeon-1 | ESSO AUSTRALIA LTD |  | HELIX Q7000 | J.23.105887 | RPI | CT-CEM | Low | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2023-12-01 |  | 2023-12-01 | 2023-12-15 23:59 |  |  | AUS West Coast WS | HFerdjallah | 2023-08-17 14:26 | THahijary |  | No |  |  |  |  | Elvira Oates-Boardman |  | 0 | 0 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1046862 | O.1046862.01 | A.1046862.01.05 | JDP3 JUB1B OHGP | WOODSIDE ENERGY JULIMAR PTY LTD | JUB1B | TRANSOCEAN ENDURANCE | J.24.015059 | RPS | SMS-OHGP-APS | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | Design Completed | 2025-11-22 | 2025-11-22 | 2025-11-22 | 2025-11-22 | 2025-12-06 23:59 | 2025-12-07 | 2025-12-06 23:59 | AUS West Coast WS | radinegara | 2025-11-19 09:49 | ZAbbasov2 |  | No |  |  |  |  | Ramadhani Adi Negara |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 100 | 100 | 0 | 75 |  | 21 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Production Services
P.1046862 | O.1046862.01 | A.1046862.01.06 | JDP3 Well 4 | WOODSIDE ENERGY JULIMAR PTY LTD | Well #1 | TRANSOCEAN ENDURANCE | J.24.015060 | RPS | SMS-OHGP-APS | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | Not Started | 2026-01-01 | 2026-01-01 |  | 2026-01-01 | 2026-01-15 23:59 |  | 2026-01-15 23:59 | AUS West Coast WS | radinegara | 2025-11-14 21:03 | ZAbbasov2 |  | No |  |  |  |  | Ramadhani Adi Negara |  | 0 | 1 |  | L0 - No RO |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 23 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Production Services
P.1046862 | O.1046862.01 | A.1046862.01.03 | Woodside JDP3 Gravel Pack Preparation | WOODSIDE ENERGY JULIMAR PTY LTD | Well #1 | TRANSOCEAN ENDURANCE | J.23.127759 | RPS | STM-EQPRNT | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2026-11-04 | 2026-09-10 | 2026-10-01 08:00 | 2026-10-02 | 2028-01-02 23:59 | 2028-01-03 | 2028-01-02 23:59 | AUS West Coast WS | radinegara | 2025-10-31 23:01 | radinegara |  | No |  |  |  |  | Ramadhani Adi Negara |  | 0 | 0 |  | L0 - No RO |  | 81.3 | 33.3 | 100 | 25 | 57.5 |  | 8 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Production Services
P.1046862 | O.1046862.01 | A.1046862.01.02 | Woodside JDP3 Gravel Pack Preparation Q3 | WOODSIDE ENERGY JULIMAR PTY LTD | Well #1 | TRANSOCEAN ENDURANCE | J.23.127758 | RPS | SMS-OHGP-APS | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2026-11-13 | 2026-11-13 | 2026-11-13 | 2026-12-12 23:59 | 2026-12-13 |  | AUS West Coast WS | radinegara | 2025-10-31 23:01 | radinegara |  | No |  |  |  |  | Ramadhani Adi Negara |  | 0 | 1 |  |  |  | 12.5 | 0 | 0 | 0 | 5 |  | 6 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1046862 | O.1046862.01 | A.1046862.01.07 | Equipment rental | WOODSIDE ENERGY JULIMAR PTY LTD | Well #1 | TRANSOCEAN ENDURANCE | J.24.174933 | RPS | STM-EQPRNT | Low | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2026-09-23 |  | 2026-09-23 | 2026-12-21 23:59 |  |  | AUS West Coast WS | CNevarez2 | 2025-10-31 23:01 | radinegara |  | No |  |  |  |  | Edgar Acosta |  | 0 | 1 |  | L0 - No RO |  | 50 | 33.3 | 100 | 25 | 45 |  | 5 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Production Services
P.1046862 | O.1046862.01 | A.1046862.01.04 | JDP 3 Well 2 | WOODSIDE ENERGY JULIMAR PTY LTD | JUA1E | TRANSOCEAN ENDURANCE | J.24.014794 | RPS | SMS-OHGP-APS | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-10-14 23:59 | 2025-10-11 | 2025-10-15 23:59 | AUS West Coast WS | radinegara | 2025-10-17 17:40 | ZAbbasov2 |  | No |  |  |  |  | Ramadhani Adi Negara |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 83.3 | 100 | 75 | 85 |  | 14 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Production Services
P.1046862 | O.1046862.01 | A.1046862.01.01 | JDP3 JULA-J | WOODSIDE ENERGY JULIMAR PTY LTD | JULA-J | TRANSOCEAN ENDURANCE | J.24.007977 | RPS | SMS-OHGP-APS | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2025-09-12 | 2025-09-12 | 2025-10-20 | 2025-09-12 | 2025-09-26 23:59 | 2025-11-22 | 2025-09-26 23:59 | AUS West Coast WS | radinegara | 2025-09-22 13:11 | ARahi |  | No |  |  |  |  | Ramadhani Adi Negara |  | 0 | 1 |  | L0 - No RO |  | 65.6 | 8.3 | 0 | 0 | 28.7 |  | 11 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Production Services
P.1046862 | O.1046862.01 | A.1046862.01.08 | rentals SMS | WOODSIDE ENERGY JULIMAR PTY LTD |  | TRANSOCEAN ENDURANCE | J.25.101952 | RPS | STM-EQPRNT | Low | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2025-07-01 |  | 2025-07-01 | 2025-07-30 23:59 |  |  | AUS West Coast WS | CNevarez2 | 2025-05-23 15:27 | CNevarez2 |  | No |  |  |  |  | Ramadhani Adi Negara |  | 0 | 1 |  | L0 - No RO |  | 50 | 33.3 | 100 | 25 | 45 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Production Services
P.1046285 | O.1046285.01 | A.1046285.01.01 | Kinetic Rental | KINETIC WELL SERVICES LTD |  |  | J.23.133996 | RPI | PS-WL-NO | InComplete | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2023-11-01 |  | 2023-11-02 | 2023-11-09 23:59 |  |  | New Plymouth WL | CKok3 | 2024-08-21 17:52 | FDPSystemUser |  | No |  |  |  |  | Cheryl Kok |  | 0 | 0 |  | L0 - No RO |  | 25 | 33.3 | 100 | 50 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1046020 | O.1046020.01 | A.1046020.01.01 | ROV sampling | WOODSIDE ENERGY LTD |  | ENSCO DPS-1 | J.23.088202 | RPE | FSA-OH-JOB | High | Unconfirmed - 50% | Design - CEC |  | Design Completed | Not Required | In Progress | 2023-06-10 | 2023-06-01 |  | 2023-06-10 | 2023-11-03 23:59 |  | 2023-11-03 23:59 | APG TS | EKondratiev | 2023-11-28 10:35 | EKondratiev |  | No |  | [AUJN-FSA] - AU - Jandakot OLP |  |  | Evgeniy Kondratiev |  | 229685.8 | 1 |  |  |  | 83.3 | 83.3 | 0 | 62.5 | 68.8 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Downhole Reservoir Testing
P.1045991 | O.1045991.04 | A.1045991.04.03 | CRC3/ CRC8 PNX Q1 2026 | CO2CRC LIMITED |  | RIGLESS - AUSTRALIA | J.25.140785 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Not Started | In Progress | 2026-02-15 | 2026-02-13 | 2026-02-14 13:00 | 2026-02-15 | 2026-04-16 23:59 | 2026-04-17 01:00 | 2026-04-17 00:59 | Roma WL | CKok3 | 2025-11-21 12:12 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 50 | 0 | 0 | 0 | 15 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1045991 | O.1045991.04 | A.1045991.04.01 | CRC 3/ CRC 8 PNX Q4 2025 | CO2CRC LIMITED |  | RIGLESS - AUSTRALIA | J.25.102017 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-10-25 | 2025-10-23 | 2025-10-24 13:00 | 2025-10-25 | 2025-12-24 23:59 | 2025-12-25 | 2025-12-24 23:59 | Roma WL | CKok3 | 2025-08-19 16:44 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1045991 | O.1045991.04 | A.1045991.04.02 | CRC 3/CRC 8 PNX Q3 2025 | CO2CRC LIMITED |  | RIGLESS - AUSTRALIA | J.25.128743 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-09-01 | 2025-09-01 | 2025-08-31 13:00 | 2025-09-01 | 2025-10-31 23:59 | 2025-11-01 | 2025-10-31 23:59 | Roma WL | CKok3 | 2025-08-13 14:24 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1045991 | O.1045991.03 | A.1045991.03.01 | CRC 3/ CRC 8 PNX Q3 2025 | CO2CRC LIMITED |  | RIGLESS - AUSTRALIA | J.25.102015 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-07-26 | 2025-07-24 | 2025-07-25 12:00 | 2025-07-26 | 2025-09-24 23:59 | 2025-09-24 23:00 | 2025-09-24 23:59 | Roma WL | CKok3 | 2025-07-11 09:54 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1045991 | O.1045991.02 | A.1045991.02.02 | CRC-8 CRC-3 PNX 2025 | CO2CRC LIMITED | CRC 3, CRC 8 | RIGLESS - AUSTRALIA | J.24.196634 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-01-01 | 2024-11-21 01:00 | 2025-01-01 | 2025-01-01 | 2025-02-26 23:59 | 2025-03-01 | 2025-02-27 23:59 | Roma WL | JEsmeralda | 2025-05-19 14:21 | ABazilah |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 75 | 80 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1045991 | O.1045991.02 | A.1045991.02.03 | CRCCO2 PNX 2025 | CO2CRC LIMITED | CRC 3, CRC 8 | RIGLESS - AUSTRALIA | J.25.063218 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2025-02-03 | 2025-02-01 | 2025-02-02 13:00 | 2025-02-03 | 2025-04-04 23:59 | 2025-04-05 | 2025-04-04 23:59 | Roma WL | RDell | 2025-04-26 19:21 | AVadladi |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 75 | 83.3 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1045991 | O.1045991.02 | A.1045991.02.01 | CRC-8 CRC-3 PNX Campaign | CO2CRC LIMITED | CRC 3, CRC 8 | RIGLESS - AUSTRALIA | J.24.041373 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-10-28 | 2024-09-17 |  | 2024-10-28 | 2025-01-01 23:59 |  | 2025-01-01 23:59 | Roma WL | KKeese | 2025-01-15 14:52 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 358673 | 2 |  | L3 - Full RO |  | 91.7 | 100 | 100 | 75 | 90 |  | 3 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1045991 | O.1045991.01 | A.1045991.01.01 | CO2CRC December | CO2CRC LIMITED | CRC 8 | SLR 166 | J.23.087909 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-12-09 | 2023-12-09 | 2023-12-02 13:00 | 2023-12-09 | 2023-12-18 23:59 | 2023-12-19 | 2023-12-18 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 147612.74 | 3 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045991 | O.1045991.01 | A.1045991.01.02 | CCS Perfo 1 | CO2CRC LIMITED |  | SLR 166 | J.24.022183 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2024-06-06 01:00 | 2024-06-06 |  | 2024-06-06 | 2024-06-13 23:59 |  | 2024-06-14 00:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 10 |  | L0 - No RO |  | 62.5 | 0 | 0 | 0 | 18.8 |  | 5 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1045991 | O.1045991.01 | A.1045991.01.05 | CO2CRC - Sienna 1 RST | CO2CRC LIMITED | CRC 8 | SLR 166 | J.24.089252 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2024-05-20 |  | 2024-06-25 | 2024-06-26 23:59 |  |  | Roma WL | KKeese | 2024-06-12 08:00 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 |  |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 2 | [7 empty] | Kelly Keese | WL Evaluation Services
P.1045991 | O.1045991.01 | A.1045991.01.04 | CCS Perfo 3 | CO2CRC LIMITED |  | SLR 166 | J.24.022185 | RPI | PS-WL-NO | Low | Confirmed | Execute - PSD |  | In Progress | In Progress | In Progress | 2024-03-15 | 2024-03-15 |  | 2024-03-15 | 2024-03-22 23:59 |  | 2024-03-22 23:59 | Roma WL | KKeese | 2024-06-10 15:25 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 25964.91 | 10 |  | L0 - No RO |  | 75 | 33.3 | 100 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1045991 | O.1045991.01 | A.1045991.01.03 | CCS Perfo 2 | CO2CRC LIMITED |  | SLR 166 | J.24.022184 | RPI | PS-WL-NO | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-04-01 | 2024-04-01 |  | 2024-04-01 | 2024-04-08 23:59 |  | 2024-04-09 00:59 | Roma WL | KKeese | 2024-01-05 10:25 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 10 |  | L0 - No RO |  | 58.3 | 33.3 | 100 | 50 | 52.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1045904 | O.1045904.01 | A.1045904.01.01 | NSW Dedicated Unit August | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.085737 | RPE | ES-CH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2023-08-14 | 2023-08-14 | 2023-08-14 | 2023-08-14 | 2023-08-28 23:59 | 2023-08-29 | 2023-08-28 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 12 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045904 | O.1045904.01 | A.1045904.01.03 | NSW Dedicated Unit October | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.087874 | RPE | ES-CH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-10-09 | 2023-10-09 |  | 2023-10-09 | 2023-10-23 23:59 |  | 2023-10-23 23:59 | Roma WL | KKeese | 2023-05-21 18:23 | FDPSystemUser |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 12 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045904 | O.1045904.01 | A.1045904.01.02 | NSW Dedicated Unit September | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.085743 | RPE | ES-CH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-11 | 2023-09-11 |  | 2023-09-11 | 2023-09-25 23:59 |  | 2023-09-25 23:59 | Roma WL | KKeese | 2023-05-21 18:23 | KKeese |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 12 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.13 | A.1045863.13.03 | Origin Adhoc Sep 2025 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.25.124734 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-03-14 | 2025-09-07 23:55 | 2025-09-07 23:00 | 2025-09-08 | 2025-10-08 23:59 | 2025-10-10 | 2025-10-09 00:59 | Roma WL | CKok3 | 2025-07-11 09:44 | CKok3 |  | No |  |  |  |  | Irwan Wongso |  | 0 | 5 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.13 | A.1045863.13.02 | Origin Adhoc Aug 2025 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.25.124733 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-02-10 | 2025-08-05 23:55 | 2025-08-05 23:00 | 2025-08-06 | 2025-09-05 23:59 | 2025-09-06 23:00 | 2025-09-05 23:59 | Roma WL | CKok3 | 2025-07-11 09:44 | CKok3 |  | No |  |  |  |  | Irwan Wongso |  | 0 | 5 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.13 | A.1045863.13.01 | Origin Adhoc July 2025 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.25.124728 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-01-09 | 2025-07-04 23:55 | 2025-07-04 23:00 | 2025-07-05 | 2025-08-04 23:59 | 2025-08-05 23:00 | 2025-08-04 23:59 | Roma WL | CKok3 | 2025-07-11 09:43 | CKok3 |  | No |  |  |  |  | Irwan Wongso |  | 0 | 5 |  | L0 - No RO |  | 66.7 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.12 | A.1045863.12.01 | Origin Dedicated OH Jun 2025 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | PHS 084, PHS 064, PHS 065, PHS 086, PHS 087, PHS 108, PHS 202, PHS 233, PHS 265 | SAVANNA DRILLING #449 | J.25.112895 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2025-06-07 14:00 | 2025-06-07 | 2025-06-07 14:00 | 2025-06-08 | 2025-07-06 23:59 | 2025-07-08 13:00 | 2025-07-07 22:59 | Roma WL | CKok3 | 2025-06-29 16:50 | JDagdag |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 83.3 | 75 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.11 | A.1045863.11.03 | Origin Dedicated OH Dec 2025 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.25.101976 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-11-25 14:00 | 2025-11-25 | 2025-11-25 15:00 | 2025-11-26 | 2025-12-24 23:59 | 2025-12-26 14:00 | 2025-12-25 22:59 | Roma WL | CKok3 | 2025-07-11 09:53 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.11 | A.1045863.11.02 | Origin Dedicated OH Nov 2025 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.25.101975 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-10-25 14:00 | 2025-10-25 | 2025-10-25 15:00 | 2025-10-26 | 2025-11-23 23:59 | 2025-11-25 14:00 | 2025-11-24 22:59 | Roma WL | CKok3 | 2025-07-11 09:53 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.11 | A.1045863.11.01 | Origin Dedicated OH Oct 2025 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.25.101973 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-09-25 14:00 | 2025-09-25 | 2025-09-25 14:00 | 2025-09-26 | 2025-10-24 23:59 | 2025-10-26 14:00 | 2025-10-25 23:59 | Roma WL | CKok3 | 2025-07-11 09:53 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.10 | A.1045863.10.01 | Origin Dedicated OH July 2025 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | PHS 147, PHS 166, PHS 198, PHS 199, PHS 201, PHS 262, PHS 263, PHS 108, ORN483, ORN486 | SAVANNA DRILLING #449 | J.25.101970 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-11-28 | 2025-06-25 | 2025-06-25 14:00 | 2025-06-26 | 2025-07-31 23:59 | 2025-08-02 13:00 | 2025-08-01 22:59 | Roma WL | CKok3 | 2025-07-30 10:26 | FShallal |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 100 | 83.3 | 85 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.10 | A.1045863.10.03 | Origin Dedicated OH Sep 2025 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.25.101972 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-08-25 14:00 | 2025-08-25 | 2025-08-25 14:00 | 2025-08-26 | 2025-09-23 23:59 | 2025-09-25 13:00 | 2025-09-24 22:59 | Roma WL | CKok3 | 2025-07-11 09:49 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 33.3 | 0 | 25 | 30 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.10 | A.1045863.10.02 | Origin Dedicated OH Aug 2025 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.25.101971 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-07-25 14:00 | 2025-07-25 | 2025-07-25 14:00 | 2025-07-26 | 2025-08-23 23:59 | 2025-08-25 13:00 | 2025-08-24 22:59 | Roma WL | CKok3 | 2025-07-11 09:49 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 33.3 | 0 | 25 | 30 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.09 | A.1045863.09.01 | Origin Dedicated OH July 2025 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.25.101962 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-05-24 14:00 | 2025-05-24 | 2025-05-24 14:00 | 2025-05-25 | 2025-06-25 23:59 | 2025-06-24 13:00 | 2025-06-23 22:59 | Roma WL | CKok3 | 2025-05-23 18:01 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.08 | A.1045863.08.06 | Origin Dedicated OH Jun 2025 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | PHS 150, PHS 128, PHS 129, PHS 105, PHS 107, PHS 085 | SAVANNA DRILLING #449 | J.25.058853 | RPE | ES-OH-Ops | InComplete | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2025-05-24 14:00 | 2025-05-24 | 2025-05-24 14:00 | 2025-05-25 | 2025-06-22 23:59 | 2025-06-24 13:00 | 2025-06-23 22:59 | Roma WL | JEsmeralda | 2025-06-11 14:14 | FShallal |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 100 | 83.3 | 85 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.08 | A.1045863.08.05 | Origin Dedicated OH May 2025 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | PHS 125, PHS 126, PHS 127, PHS 103, PHS 104, PHS 203, PHS 106, PHS 172, PHS 151, PHS 168, PHS 167, PHS 149 | SAVANNA DRILLING #449 | J.25.058851 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-08-26 23:00 | 2025-04-25 09:55 | 2025-04-23 14:00 | 2025-04-25 10:00 | 2025-06-01 09:59 | 2025-06-02 | 2025-06-02 08:59 | Roma WL | JEsmeralda | 2025-06-04 10:12 | RDell |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 100 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.08 | A.1045863.08.07 | Origin OH Dedicated Q3 2025 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.25.101955 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2025-06-25 |  | 2025-06-25 | 2025-09-24 |  |  | Roma WL | CKok3 | 2025-05-23 17:52 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 0 |  | L3 - Full RO |  | 8.3 | 0 | 0 | 0 | 2.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.08 | A.1045863.08.04 | Origin Dedicated OH Apr 2025 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | PHS261, PHS 230, PHS 200 | SAVANNA DRILLING #449 | J.25.058846 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-08-26 23:00 | 2025-04-01 09:55 | 2025-03-29 13:00 | 2025-04-01 10:00 | 2025-04-24 09:59 | 2025-04-25 | 2025-04-24 23:59 | Roma WL | JEsmeralda | 2025-05-03 09:07 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L2 - Shift RO |  | 91.7 | 83.3 | 100 | 100 | 92.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.08 | A.1045863.08.03 | Origin Dedicated OH Mar 2025 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | PHS 231, PHS 264 | SAVANNA DRILLING #449 | J.25.025342 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2025-03-01 | 2025-03-01 09:55 |  | 2025-03-01 10:00 | 2025-03-31 09:59 |  | 2025-03-30 09:59 | Roma WL | JEsmeralda | 2025-03-07 12:24 | handoko |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 83.3 | 70 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.08 | A.1045863.08.02 | Origin Dedicated OH Feb 2025 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | PHS204, PHS267, PHS296, PHS295, PHS235, PHS 234, PHS 236, PHS 386, PHS 266, PHS 232 | SAVANNA DRILLING #449 | J.25.025341 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-02-02 | 2025-01-31 09:55 |  | 2025-01-31 10:00 | 2025-02-28 09:59 |  | 2025-02-28 09:59 | Roma WL | JEsmeralda | 2025-03-03 16:11 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 104353.48 | 2 |  | L3 - Full RO |  | 100 | 100 | 100 | 83.3 | 95 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.08 | A.1045863.08.01 | Origin Dedicated OH Jan 2025 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | RCS 134, RCS151, PHS 169, PHS 170, PHS 171 | SAVANNA DRILLING #449 | J.25.025340 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-08-26 23:00 | 2024-12-31 09:55 |  | 2024-12-31 10:00 | 2025-01-31 09:59 |  | 2025-01-31 09:59 | Roma WL | JEsmeralda | 2025-02-25 19:26 | SMccauley |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 104353.48 | 2 |  | L3 - Full RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.07 | A.1045863.07.01 | Origin 449_TC MDT_Sep24 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.25.014987 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-03-05 01:00 | 2025-03-09 02:00 |  | 2025-05-01 01:00 | 2025-06-05 23:59 |  | 2025-04-09 23:59 | Roma WL | KKeese | 2025-02-26 14:37 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 3 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.07 | A.1045863.07.04 | Origin Dedicated OH Dec24 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | ORANA NORTH 479, ORANA NORTH 503, RCS 114, RCS 110 | SAVANNA DRILLING #449 | J.24.182529 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-08-26 23:00 | 2024-11-26 10:55 |  | 2024-11-26 11:00 | 2024-12-27 10:59 |  | 2024-12-27 10:59 | Roma WL | JEsmeralda | 2025-01-02 12:09 | ESchmidtke |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L3 - Full RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.07 | A.1045863.07.03 | Origin 449_TC MDT_Nov24 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | MUGGLETON 120, EC-MB003, EC-MB002, SG-MB024, SG-MB022, SG-MB023, ORANA NORTH 482, ORANA NORTH 480, ORANA NORTH 481, ORANA NORTH 485, ORANA NORTH 475, ORANA NORTH 476, ORANA NORTH 477, ORANA NORTH 478, ORANA NORTH 479, DURHAM RANCH 920 | SAVANNA DRILLING #449 | J.24.171681 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2024-10-21 01:00 | 2024-10-25 10:55 |  | 2024-10-25 11:00 | 2024-11-25 10:59 |  | 2024-11-25 10:59 | Roma WL | JEsmeralda | 2024-12-07 12:04 | ESchmidtke |  | No |  |  |  |  | Irwan Wongso |  | 0 | 1 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.07 | A.1045863.07.02 | Origin Dedicated October | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | MUGGLETON 120, EC-MB003, EC-MB002, SG-MB024, SG-MB022, SG-MB023 | SAVANNA DRILLING #449 | J.24.159200 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-09-25 01:00 | 2024-09-29 10:55 |  | 2024-09-29 11:00 | 2024-10-30 10:59 |  | 2024-10-24 23:59 | Roma WL | KKeese | 2024-12-05 17:33 | AVadladi |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 100 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.06 | A.1045863.06.01 | Origin Sav449 September TC MDT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | RAMYARD 164, MUGGLETON 075, MUGGLETON 103 | SAVANNA DRILLING #449 | J.24.155728 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-05-01 23:00 | 2024-09-09 |  | 2024-09-09 | 2024-10-01 23:59 |  | 2024-10-01 23:59 | Roma WL | KKeese | 2024-09-30 15:07 | HCannon |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 6 |  | L3 - Full RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.06 | A.1045863.06.02 | Origin 449_TC MDT_Oct24 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.24.159636 | RPE | ES-OH-Ops | High | Confirmed | Design - CEC |  | Design Completed | Not Started | In Progress | 2023-05-17 23:00 | 2024-09-25 |  | 2024-09-25 | 2024-10-18 00:59 |  | 2024-10-18 00:59 | Roma WL | JEsmeralda | 2024-09-27 20:58 | ELionts |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 6 |  | L3 - Full RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.05 | A.1045863.05.02 | Oct 2024 Origin Dedicated | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.25.002539 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-05-19 23:00 | 2025-05-19 23:00 |  | 2025-05-19 23:00 | 2025-06-19 21:59 |  | 2025-06-19 22:59 | Roma WL | JEsmeralda | 2025-02-26 14:37 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.05 | A.1045863.05.07 | Origin 449_TC_Aug24 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI 503, CONDABRI 483, CONDABRI 505, CONDABRI 530, CONDABRI 514, CONDABRI 528, CONDABRI 417, CONDABRI 199, CONDABRI 204 | SAVANNA DRILLING #449 | J.24.131353 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-05-01 23:00 | 2024-07-18 |  | 2024-07-25 23:00 | 2024-08-30 22:59 |  | 2024-08-30 23:59 | Roma WL | JEsmeralda | 2024-11-26 15:13 | SNiang |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L2 - Shift RO |  | 91.7 | 83.3 | 100 | 100 | 92.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.05 | A.1045863.05.10 | Mar 2025 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI 503, CONDABRI 483, CONDABRI 505, CONDABRI 530, CONDABRI 514, CONDABRI 528, CONDABRI 417 | SAVANNA DRILLING #449 | J.25.008354 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-06-10 23:00 | 2025-02-22 |  | 2025-03-01 23:00 | 2025-03-31 22:59 |  | 2025-03-31 22:59 | Roma WL | KKeese | 2024-11-16 16:40 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.05 | A.1045863.05.09 | Feb 2025 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI 503, CONDABRI 483, CONDABRI 505, CONDABRI 530, CONDABRI 514, CONDABRI 528, CONDABRI 417 | SAVANNA DRILLING #449 | J.25.008353 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-01-24 | 2025-01-25 |  | 2025-02-01 23:00 | 2025-02-28 22:59 |  | 2025-02-28 23:59 | Roma WL | KKeese | 2024-11-16 16:40 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.05 | A.1045863.05.11 | Origin 449_TC MDT_Sep24 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI 200, CONDABRI 201, DURHAM RANCH 378, CONDABRI 529, CONDABRI 511, CONDABRI 484 | SAVANNA DRILLING #449 | J.24.142740 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-08-26 23:00 | 2024-08-26 |  | 2024-08-26 23:00 | 2024-10-01 22:59 |  | 2024-10-01 22:59 | Roma WL | JEsmeralda | 2024-11-15 00:28 | SNiang |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 3 |  | L2 - Shift RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.05 | A.1045863.05.08 | Jan 2025 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI 503, CONDABRI 483, CONDABRI 505, CONDABRI 530, CONDABRI 514, CONDABRI 528, CONDABRI 417 | SAVANNA DRILLING #449 | J.25.008352 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-08 23:00 | 2024-12-25 |  | 2025-01-01 23:00 | 2025-01-31 22:59 |  | 2025-01-31 23:59 | Roma WL | KKeese | 2024-10-29 11:46 | KKeese |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.05 | A.1045863.05.05 | Origin 449_TC-MDT_Jun24 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI SOUTH 503, CONDABRI SOUTH 502, CONDABRI SOUTH 292, CONDABRI SOUTH 310, CONDABRI SOUTH 295, IRONBARK 194, DURHAM RANCH 356, IRONBARK 189, IRONBARK 279, IRONBARK 223 | SAVANNA DRILLING #449 | J.24.105211 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2024-06-01 23:00 | 2024-05-25 |  | 2024-06-01 23:00 | 2024-07-03 22:59 |  | 2024-07-03 23:59 | Roma WL | JEsmeralda | 2024-09-30 15:14 | SLie4 |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 3 |  | L2 - Shift RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.05 | A.1045863.05.01 | Origin 449_TC-MDT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | IRB 088 | SAVANNA DRILLING #449 | J.24.073537 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2024-03-24 23:00 | 2024-03-23 |  | 2024-03-24 23:00 | 2024-04-24 22:59 |  | 2024-04-24 22:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 6 |  | L3 - Full RO |  | 50 | 33.3 | 0 | 0 | 25 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.05 | A.1045863.05.03 | AIT-PEX_GPIT-MDT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | IRB 088, IRONBARK 134, IRONBARK 43, IRONBARK 223, IRONBARK 189, IRONBARK 194, CNS 312 | SAVANNA DRILLING #449 | J.24.086924 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2024-03-24 23:00 | 2024-03-23 |  | 2024-03-24 23:00 | 2024-04-24 22:59 |  | 2024-04-24 22:59 | Roma WL | RDell | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 15009.75 | 4 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.05 | A.1045863.05.04 | Origin 449_TC_May24 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CNS 291, CONDABRI 502, CONDABRI 509, CONDABRI 482, CONDABRI 497, MURRUNGAMA 15, CONDABRI SOUTH 301, CONDABRI SOUTH 294, CONDABRI SOUTH 302, CONDABRI SOUTH 310 | SAVANNA DRILLING #449 | J.24.087496 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-04-29 23:00 | 2024-04-29 |  | 2024-04-29 23:00 | 2024-05-31 22:59 |  | 2024-05-31 23:59 | Roma WL | JEsmeralda | 2024-08-12 16:21 | SNiang |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 3 |  | L3 - Full RO |  | 83.3 | 83.3 | 50 | 100 | 85 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.05 | A.1045863.05.06 | Origin 449_TC-MDT_Jul24 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | IRONBARK 134, IRC 043, CONDABRI SOUTH 292 | SAVANNA DRILLING #449 | J.24.117859 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-09-30 | 2024-06-12 |  | 2024-06-19 23:00 | 2024-07-25 22:59 |  | 2024-07-25 23:59 | Roma WL | JEsmeralda | 2024-08-12 14:02 | SNiang |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 3 |  | L3 - Full RO |  | 91.7 | 83.3 | 100 | 100 | 92.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.04 | A.1045863.04.01 | PDP Peat 449-450 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA 185 | J.24.027775 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2025-09-17 01:00 | 2025-09-17 | 2025-09-17 01:00 | 2025-09-17 | 2025-10-01 23:59 | 2025-10-02 | 2025-10-01 23:59 | Roma WL | KKeese | 2025-05-16 08:46 | CKok3 |  | Yes |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 4 |  | L0 - No RO |  | 45.8 | 0 | 0 | 0 | 13.8 |  | 3 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1045863 | O.1045863.04 | A.1045863.04.03 | Tractor Peat 449-450 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | PEAT 450, PEAT-449 | SAVANNA 185 | J.24.053877 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-07-01 01:00 | 2024-07-01 |  | 2024-11-01 | 2024-11-15 23:59 |  | 2024-11-15 23:59 | Roma WL | KKeese | 2024-12-09 18:16 | LKenzhegulova |  | Yes |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 155223.52 | 4 |  | L2 - Shift RO |  | 100 | 75 | 100 | 100 | 92.5 |  | 3 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1045863 | O.1045863.04 | A.1045863.04.02 | PDP Peat 449-450 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA 185 | J.24.053876 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-06-03 01:00 | 2024-06-03 | 2024-06-03 01:00 | 2024-06-03 | 2024-06-17 23:59 | 2024-06-18 | 2024-06-17 23:59 | Roma WL | KKeese | 2024-05-10 09:07 | KKeese |  | Yes |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 4 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 2 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1045863 | O.1045863.03 | A.1045863.03.01 | COMB-7 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COM-MB7-H | SAVANNA DRILLING #449 | J.23.160445 | RPI | PS-WL-NO | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | Design Completed | 2023-10-25 | 2023-10-25 |  | 2023-10-25 | 2023-10-26 23:59 |  | 2023-10-26 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 4450.94 | 1 |  | L3 - Full RO |  | 83.3 | 66.7 | 100 | 75 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1045863 | O.1045863.02 | A.1045863.02.02 | Mount Kingsley 56 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | SPRING GULLY 126 | SLR 185 | J.24.125022 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2024-07-05 | 2024-07-05 |  | 2024-07-05 | 2024-07-30 23:59 |  | 2024-07-30 23:59 | Roma WL | KKeese | 2024-07-24 07:40 | KKeese |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.02 | A.1045863.02.01 | SLR 186 June | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | SPRING GULLY 126 | SLR 185 | J.23.097338 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-05 | 2023-06-05 |  | 2023-06-05 | 2023-06-30 23:59 |  | 2023-06-30 23:59 | Roma WL | KKeese | 2023-06-07 23:47 | NMoore2 |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 43534.76 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.27 | Origin OH Dedicated Jan 2025 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.24.171852 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-01-01 | 2025-01-01 |  | 2025-01-01 | 2025-01-30 23:59 |  | 2025-01-30 23:59 | Roma WL | CKok3 | 2024-11-16 16:33 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.24 | Dec 2024 Origin Dedicated | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.24.023106 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-12-01 | 2024-12-01 |  | 2024-12-01 | 2024-12-31 23:59 |  | 2024-12-31 23:59 | Roma WL | KKeese | 2024-11-16 14:43 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.28 | Origin OH Dedicated Feb 2025 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.25.018811 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-02-01 | 2025-02-01 |  | 2025-02-01 | 2025-02-28 23:59 |  | 2025-02-28 23:59 | Roma WL | CKok3 | 2024-10-29 11:49 | KKeese |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.26 | Origin Dedicated OH Nov 2024 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.24.171851 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-11-01 | 2024-11-01 |  | 2024-11-01 | 2024-11-30 23:59 |  | 2024-11-30 23:59 | Roma WL | CKok3 | 2024-10-29 11:23 | KKeese |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.23 | Nov 2024 Origin Dedicated | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.24.023105 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-11-01 | 2024-11-01 |  | 2024-11-01 | 2024-12-01 23:59 |  | 2024-12-01 23:59 | Roma WL | KKeese | 2024-08-28 15:05 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.21 | Sep 2024 Origin Dedicated | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.24.023103 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-09-01 | 2024-09-01 |  | 2024-09-01 | 2024-09-29 23:59 |  | 2024-09-29 23:59 | Roma WL | KKeese | 2024-08-27 17:40 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.01 | Origin Tripple Combo | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.23.085259 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Required | Not Started | 2023-08-03 | 2023-08-03 |  | 2023-08-03 | 2023-08-09 23:59 |  | 2023-08-09 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 1 |  | L3 - Full RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.02 | Super Combo_Durham Ranch 342 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | DURHAM RANCH 342 | SAVANNA DRILLING #449 | J.23.085636 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-09-12 | 2023-09-09 |  | 2023-09-12 | 2023-09-18 23:59 |  | 2023-09-18 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 49870.05 | 1 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.05 | Origin Deep Full Suit | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | PEA 448 | SAVANNA DRILLING #449 | J.23.087901 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-10-21 | 2023-11-05 | 2023-11-05 | 2023-11-06 | 2023-11-11 23:59 | 2023-11-12 | 2023-11-11 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 399181.29 | 3 |  | L1 - Support RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 3 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.10 | Dedicated November | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | ORANA 105, ORANA 116, ORANA 94, ORANA 104, ORANA 106, ORANA 131, ORANA 117, ORANA 149, ORANA 160, ORANA NORTH 113, ORANA 134 | SAVANNA DRILLING #449 | J.23.127766 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-10-22 | 2023-10-21 | 2023-10-21 | 2023-10-22 | 2023-11-20 23:59 | 2023-11-21 | 2023-11-20 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.11 | Dedicated December | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | PEAT-449, ORN103, ORANA NORTH 160, ORANA NORTH 131, ORANA NORTH 149, ORANA NORTH 171 | SAVANNA DRILLING #449 | J.23.127767 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-12-03 | 2023-12-03 | 2023-11-27 | 2023-12-03 | 2023-12-25 23:59 | 2023-12-26 | 2023-12-25 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 100 | 100 | 90 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.12 | Origin Dedicated | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COM-MB7-H, PEA 448, ORANA 105, IRB057, ORN103, IRB 129, ORN106, ORN113, ORANA 116, ORANA NORTH 131, ORANA NORTH 149, ORANA NORTH 160, ORANA NORTH 171, SG-MB096, ORANA 117, ORANA 134 | SAVANNA DRILLING #449 | J.23.152380 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-10-11 | 2023-10-08 |  | 2023-10-11 | 2023-10-17 23:59 |  | 2023-10-25 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.13 | January 2024 Origin Dedicated | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | ORANA NORTH 171, PEA 448, PEAT-449, MURRUNGAMA 25 | SAVANNA DRILLING #449 | J.23.160226 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-01-01 | 2024-01-01 |  | 2024-01-01 | 2024-01-31 23:59 |  | 2024-01-31 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 228962.51 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.15 | March 2024 Origin Dedicated | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | IRB057, PEA 448, IRB 129 | SAVANNA DRILLING #449 | J.24.021426 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-02-28 | 2024-02-28 |  | 2024-02-28 | 2024-03-29 23:59 |  | 2024-03-29 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 62560.1 | 5 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.14 | February 2024 Origin Dedicated | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | MURRUNGAMA 24, MURRUNGAMA 26, MURRUNGAMA 19, MURRUNGAMA 23, PEA 448, MURRUNGAMA 22, PEAT 450, MURRUNGAMA 21 | SAVANNA DRILLING #449 | J.24.021425 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | In Progress | Not Required | In Progress | 2024-01-22 | 2024-01-22 |  | 2024-01-22 | 2024-02-29 23:59 |  | 2024-02-29 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 7 |  | L3 - Full RO |  | 83.3 | 100 | 100 | 100 | 95 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.25 | Peat449/448 IBC CBL | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | PEAT-449, PEA 448 | SAVANNA DRILLING #449 | J.23.172747 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-12-07 | 2023-12-03 |  | 2023-12-07 | 2024-02-29 23:59 |  | 2024-02-29 23:59 | Roma WL | SAli63 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 8966.86 | 2 |  | L3 - Full RO |  | 79.2 | 41.7 | 0 | 58.3 | 53.8 |  | 2 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.18 | Jun 2024 Origin Dedicated | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.24.023100 | RPE | ES-CH-NO | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress | 2024-06-01 | 2024-06-01 |  | 2024-06-01 | 2024-06-27 23:59 |  | 2024-06-27 23:59 | Roma WL | KKeese | 2024-07-26 15:39 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 171539.96 | 2 |  | L3 - Full RO |  | 66.7 | 33.3 | 100 | 75 | 62.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.20 | Aug 2024 Origin Dedicated | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.24.023102 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-08-01 | 2024-08-01 |  | 2024-08-01 | 2024-08-31 23:59 |  | 2024-08-31 23:59 | Roma WL | KKeese | 2024-07-24 16:18 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.19 | Jul 2024 Origin Dedicated | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.24.023101 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-07-01 | 2024-07-01 |  | 2024-07-01 | 2024-07-31 23:59 |  | 2024-07-31 23:59 | Roma WL | KKeese | 2024-07-24 07:40 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.17 | May 2024 Origin Dedicated | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.24.023099 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2024-05-01 | 2024-05-01 | 2024-04-30 23:00 | 2024-05-01 | 2024-05-02 23:59 | 2024-05-02 23:00 | 2024-05-02 23:59 | Roma WL | KKeese | 2024-05-24 07:49 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 171539.96 | 2 |  | L3 - Full RO |  | 50 | 0 | 0 | 25 | 22.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.22 | Oct 2024 Origin Dedicated | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.24.023104 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2024-10-01 | 2024-10-01 | 2024-09-30 23:00 | 2024-10-01 | 2024-10-31 23:59 | 2024-11-01 | 2024-11-01 00:59 | Roma WL | KKeese | 2024-05-10 08:46 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.16 | Apr 2024 Origin Dedicated | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.24.023098 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2024-04-01 | 2024-04-01 |  | 2024-04-01 | 2024-04-30 23:59 |  | 2024-04-30 22:59 | Roma WL | KKeese | 2024-04-02 12:50 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 171539.96 | 2 |  | L3 - Full RO |  | 50 | 0 | 0 | 25 | 22.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.04 | Origin Advance Sep | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.23.085638 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | Not Started | 2023-09-23 | 2023-09-23 |  | 2023-09-23 | 2023-09-29 23:59 |  | 2023-09-29 23:59 | Roma WL | KKeese | 2023-09-26 09:26 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 1 |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.09 | DM337 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.23.118330 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | Not Started | 2023-10-11 | 2023-10-11 |  | 2023-10-11 | 2023-10-17 23:59 |  | 2023-10-17 23:59 | Roma WL | KKeese | 2023-09-26 09:26 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.08 | DM342 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.23.128172 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | Not Started | 2023-09-30 | 2023-09-30 |  | 2023-09-30 | 2023-10-06 23:59 |  | 2023-10-06 23:59 | Roma WL | KKeese | 2023-09-26 09:25 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.07 | DMR 468 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.23.118329 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | Not Started | 2023-09-16 | 2023-09-16 |  | 2023-09-16 | 2023-09-22 23:59 |  | 2023-09-22 23:59 | Roma WL | KKeese | 2023-09-26 09:16 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.06 | DMR 469 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.23.118328 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | Not Started | 2023-08-22 | 2023-08-22 |  | 2023-08-22 | 2023-08-28 23:59 |  | 2023-08-28 23:59 | Roma WL | KKeese | 2023-08-29 11:25 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045863 | O.1045863.01 | A.1045863.01.03 | Origin Advance | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.23.085637 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | Not Started | 2023-08-21 | 2023-08-21 |  | 2023-08-21 | 2023-08-27 23:59 |  | 2023-08-27 23:59 | Roma WL | KKeese | 2023-07-31 15:14 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 1 |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1045695 | O.1045695.01 | A.1045695.01.01 | Tidepole Light Well Intervention Project_Bleed off Package | NORMAND SAPURA PTY LTD | TPA 03 | SAPURAKENCANA CONSTRUCTOR | J.23.083167 | RPI | TSWT-NO-OP | High | Unconfirmed - 10% | Design - CEC |  | Design Completed | Not Started | Not Started | 2023-12-14 | 2023-05-08 |  | 2024-08-15 | 2024-08-15 23:59 |  | 2024-08-15 23:59 | APG TS | IHafeez | 2024-07-25 09:59 | FDPSystemUser |  | No |  |  |  |  | Iftikhar Hafeez |  | 155862.25 | 1 |  |  |  | 66.7 | 33.3 | 100 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1045586 | O.1045586.03 | A.1045586.03.01 | Shell Engineer Charges | SHELL AUSTRALIA PTY LTD. | Well #1 | TRANSOCEAN EQUINOX | J.24.048905 | RPI | CT-PERF | High | Confirmed | Execute - PSD |  | Not Started | Not Started | Not Started |  | 2024-02-01 |  | 2024-02-01 | 2024-02-29 23:59 |  |  | AUS East Coast WS | JHernandez246 | 2024-06-27 15:42 | JPazzi |  | No |  |  |  |  | Jose Luis Tejeda |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1045586 | O.1045586.03 | A.1045586.03.02 | DESC charges | SHELL AUSTRALIA PTY LTD. | Well #1 | TRANSOCEAN EQUINOX |  | RPI | CT-NONSERV | Low | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2024-02-28 |  | 2024-02-28 | 2024-02-29 23:59 |  |  | AUS East Coast WS | JPazzi | 2024-06-27 15:42 | JPazzi |  | No |  |  |  |  | Jorge Pazzi |  | 0 | 1 |  |  |  | 50 | 33.3 | 100 | 25 | 45 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1045586 | O.1045586.02 | A.1045586.02.02 | CEC and Dwellop eng | SHELL AUSTRALIA PTY LTD. |  | TRANSOCEAN EQUINOX | J.24.048907 | RPI | CT-NONSERV | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2024-02-01 |  | 2024-02-01 | 2025-02-01 23:59 |  |  | AUS East Coast WS | CNevarez2 | 2024-10-25 15:02 | CNevarez2 |  | No |  |  |  |  | Jose Luis Tejeda |  | 0 | 1 |  |  |  | 50 | 33.3 | 100 | 25 | 45 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1045586 | O.1045586.02 | A.1045586.02.01 | Crux C5 | SHELL AUSTRALIA PTY LTD. |  | TRANSOCEAN EQUINOX | J.25.000982 | RPI | CT-ACT-PERF | High | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2026-03-15 | 2025-07-01 |  | 2026-03-15 | 2026-05-18 23:59 |  | 2026-05-18 23:59 | AUS East Coast WS | EGafieva | 2024-10-22 21:03 | CNevarez2 |  | Yes |  |  |  |  | Jorge Pazzi |  | 0 | 1 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1045586 | O.1045586.01 | A.1045586.01.01 | 36" Conductor Cementing | SHELL AUSTRALIA PTY LTD. | Well #1 | TRANSOCEAN EQUINOX | J.24.005123 | WCF | PRI-COND | Medium | Cancelled | Close - PSD |  | Not Required | Design Completed | In Progress |  | 2024-01-08 |  | 2024-01-15 | 2024-01-15 12:00 |  |  | AUS East Coast WS | HNarainasamy | 2024-06-27 15:42 | JPazzi |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 56.3 | 0 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1045586 | O.1045586.01 | A.1045586.01.03 | 36" Conductor Cementing | SHELL AUSTRALIA PTY LTD. | Well #3 | TRANSOCEAN EQUINOX | J.24.007783 | WCF | PRI-COND | Medium | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2024-01-12 |  | 2024-01-19 | 2024-01-19 12:00 |  |  | AUS East Coast WS | HNarainasamy | 2024-06-27 15:42 | JPazzi |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1045586 | O.1045586.01 | A.1045586.01.04 | 36" Conductor Cementing | SHELL AUSTRALIA PTY LTD. | Well #4 | TRANSOCEAN EQUINOX | J.24.007784 | WCF | PRI-COND | Medium | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2024-01-14 |  | 2024-01-21 | 2024-01-21 12:00 |  |  | AUS East Coast WS | HNarainasamy | 2024-06-27 15:42 | JPazzi |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1045586 | O.1045586.01 | A.1045586.01.06 | 26" Surface Casing Cementing | SHELL AUSTRALIA PTY LTD. | Well #5 | TRANSOCEAN EQUINOX | J.24.007786 | WCF | PRI-COND,PRI-SURF | Medium | Cancelled | Close - PSD |  | Not Required | Design Completed | In Progress |  | 2024-01-18 |  | 2024-01-25 | 2024-01-25 12:00 |  |  | AUS East Coast WS | HNarainasamy | 2024-06-27 15:42 | JPazzi |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 0 |  |  |  | 56.3 | 0 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1045586 | O.1045586.01 | A.1045586.01.05 | 36" Conductor Cementing | SHELL AUSTRALIA PTY LTD. | Well #5 | TRANSOCEAN EQUINOX | J.24.007785 | WCF | PRI-COND | Medium | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2024-01-16 |  | 2024-01-23 | 2024-01-23 12:00 |  |  | AUS East Coast WS | HNarainasamy | 2024-06-27 15:42 | JPazzi |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1045586 | O.1045586.01 | A.1045586.01.02 | 36" Conductor Cementing | SHELL AUSTRALIA PTY LTD. | Well #2 | TRANSOCEAN EQUINOX | J.24.007782 | WCF | PRI-COND | Medium | Cancelled | Close - PSD |  | Not Required | Design Completed | In Progress |  | 2024-01-10 |  | 2024-01-17 | 2024-01-17 12:00 |  |  | AUS East Coast WS | HNarainasamy | 2024-06-27 15:42 | JPazzi |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 56.3 | 0 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1045586 | O.1045586.01 | A.1045586.01.07 | 26" Surface Casing Cementing | SHELL AUSTRALIA PTY LTD. | Well #4 | TRANSOCEAN EQUINOX | J.24.007909 | WCF | PRI-COND,PRI-SURF | Medium | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2024-01-21 |  | 2024-01-28 | 2024-01-28 12:00 |  |  | AUS East Coast WS | HNarainasamy | 2024-06-27 15:42 | JPazzi |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1045478 | O.1045478.01 | A.1045478.01.02 | HOLO-1 - 16in | INPEX OPERATIONS AUSTRALIA PTY LTD | HOLONEMA-1 | OCEAN APEX | J.23.084817 | WCF | PRI-SURF | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-12-05 | 2023-11-01 | 2023-12-05 | 2023-12-05 | 2023-12-05 23:59 | 2023-12-06 | 2023-12-05 23:59 | AUS East Coast WS | NKhoa | 2023-07-11 11:18 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 |  |  |  | 62.5 | 0 | 0 | 0 | 25 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1045478 | O.1045478.01 | A.1045478.01.01 | HOLO-1 - 36in Conductor | INPEX OPERATIONS AUSTRALIA PTY LTD | HOLONEMA-1 | OCEAN APEX | J.23.084813 | WCF | PRI-COND | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-11-20 | 2023-11-01 | 2023-11-20 | 2023-11-20 | 2023-11-20 23:59 | 2023-11-21 | 2023-11-20 23:59 | AUS East Coast WS | NKhoa | 2023-07-11 11:18 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 |  |  |  | 62.5 | 0 | 0 | 0 | 25 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1045354 | O.1045354.01 | A.1045354.01.01 | Perth Basin Perforation | BEACH ENERGY LTD |  | EASTERNWELL 106 | J.23.078577 | RPI | TCP-TEMP-JOB | Medium | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2023-06-01 | 2025-01-10 | 2026-01-01 | 2026-01-15 23:59 | 2025-01-25 |  | APG TS | EKondratiev | 2025-05-26 11:01 | MWaseem2 |  | No |  |  |  |  | Evgeniy Kondratiev |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 11.3 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1045298 | O.1045298.01 | A.1045298.01.14 | Reindeer_Updated | SANTOS LIMITED | REINDEER 3, REINDEER 2, REINDEER 4 |  | J.25.132837 | RPI | PS-SLK-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2025-08-19 | 2025-08-10 | 2025-08-19 | 2025-08-19 | 2025-10-02 23:59 | 2025-10-30 | 2025-10-02 23:59 | New Burn WL | ymoradi2 | 2025-11-19 12:48 | MElsanousi |  | No |  |  |  |  | Yasser Moradi |  | 385907.45 | 2 |  | L0 - No RO |  | 100 | 100 | 0 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1045298 | O.1045298.01 | A.1045298.01.12 | Harriet Bravo | SANTOS LIMITED | BAMBRA - 8, HARRIET BRAVO 5H, BAMBRA-7H |  | J.25.082275 | RPI | PS-WL-Ops | High | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2025-06-26 | 2025-06-25 | 2025-06-26 | 2025-06-26 | 2025-09-24 23:59 | 2025-09-25 | 2025-09-24 23:59 | New Burn WL | ymoradi2 | 2025-09-25 15:47 | VCao2 |  | No |  |  |  |  | Yasser Moradi |  | 343745.88 | 2 |  | L0 - No RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1045298 | O.1045298.01 | A.1045298.01.13 | Q4-2025_Rigless | SANTOS LIMITED |  |  | J.25.103256 | RPI | PS-WL-Ops | High | Unconfirmed - 50% | Design - CEC |  | Design Completed | Not Started | Design Completed | 2025-11-01 | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-12-22 23:59 | 2025-12-23 | 2025-12-22 23:59 | New Burn WL | ymoradi2 | 2025-08-26 10:34 | MElsanousi |  | No |  |  |  |  | Yasser Moradi |  | 0 | 2 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1045298 | O.1045298.01 | A.1045298.01.11 | Do not use | SANTOS LIMITED |  |  | J.25.081279 | RPI | PS-SLK-Rental-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-08-11 | 2025-08-07 | 2025-08-11 | 2025-08-11 | 2025-10-09 23:59 | 2025-10-10 | 2025-10-09 23:59 | New Burn WL | ymoradi2 | 2025-07-30 15:52 | ymoradi2 |  | No |  |  |  |  | Yasser Moradi |  | 0 | 1 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1045298 | O.1045298.01 | A.1045298.01.08 | JUB Victoria-SLK Ops | SANTOS LIMITED | MONET 2H, VICTORY 1, REINDEER 2, REINDEER 3 |  | J.24.138011 | RPI | PS-SLK-NO | High | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2024-08-25 | 2024-08-19 | 2024-08-16 | 2024-08-25 | 2024-10-10 23:59 | 2024-10-15 | 2024-10-10 23:59 | New Burn WL | MElsanousi | 2025-07-28 16:30 | ymoradi2 |  | No |  |  |  |  | Mohammad Adel Mohammad Alhashemi |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 83.3 | 100 | 50 | 75 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1045298 | O.1045298.01 | A.1045298.01.09 | Santos ¦ John Brookes 2025 ¦ WLPS | SANTOS LIMITED | JOHN BROOKES 2, JOHN BROOKES 6 |  | J.25.019195 | RPI | PS-WL-Ops | High | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2024-04-05 | 2025-04-14 | 2025-05-03 | 2025-04-24 | 2025-07-23 23:59 | 2025-06-16 | 2025-07-29 23:59 | New Burn WL | ymoradi2 | 2025-06-23 13:01 | MElsanousi |  | No |  |  |  |  | Edmund Brobbey |  | 895659.12 | 5 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1045298 | O.1045298.01 | A.1045298.01.10 | Santos ¦ John Brookes 2025 ¦ SLK | SANTOS LIMITED | JOHN BROOKES 2, JOHN BROOKES 6 |  | J.25.059712 | RPI | PS-SLK-Rental-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-04-30 | 2025-04-14 | 2025-04-30 | 2025-04-30 | 2025-06-30 23:59 | 2025-07-30 | 2025-07-29 23:59 | New Burn WL | EBrobbey | 2025-05-26 21:07 | VQuoc |  | No |  |  |  |  | Edmund Brobbey |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 100 | 100 | 75 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1045298 | O.1045298.01 | A.1045298.01.07 | HJV pre-rig Gibson Platform - SLK | SANTOS LIMITED | SOUTH PLATO 01, SOUTH PLATO 03 |  | J.24.072198 | RPI | PS-SLK-Rental-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-05-08 | 2024-05-04 |  | 2024-05-08 | 2024-06-29 23:59 |  | 2024-06-29 23:59 | New Burn WL | JDukas | 2024-08-22 15:37 | MElsanousi |  | No |  |  |  |  | Justin Dukas |  | 0 | 7 |  | L0 - No RO |  | 83.3 | 83.3 | 100 | 75 | 82.5 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1045298 | O.1045298.01 | A.1045298.01.01 | Placeholder - HJV rigless ops | SANTOS LIMITED |  |  | J.23.075859 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-11-01 | 2023-10-27 |  | 2023-11-01 | 2024-03-02 23:59 |  | 2024-03-02 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1045298 | O.1045298.01 | A.1045298.01.03 | HJV-B Simpson Alpha P&A | SANTOS LIMITED | SIMPSON 7, TANAMI 4, TANAMI 5, WEST SIMPSON 1 |  | J.23.123554 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-01-28 | 2024-01-28 | 2024-01-22 | 2024-01-28 | 2024-03-20 23:59 | 2024-03-15 | 2024-03-24 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 416160 | 7 |  | L1 - Support RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 8 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1045298 | O.1045298.01 | A.1045298.01.05 | Simpson Bravo SLK | SANTOS LIMITED | MONET 2H, SIMPSON 4H, SIMPSON 10, SIMPSON 9 |  | J.24.010330 | RPI | PS-SLK-Rental-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-03-21 | 2024-03-15 | 2024-03-18 | 2024-03-21 | 2024-05-06 23:59 | 2024-05-11 | 2024-05-06 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  | L0 - No RO |  | 79.2 | 83.3 | 100 | 75 | 81.3 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1045298 | O.1045298.01 | A.1045298.01.06 | Simpson Alpha SLK | SANTOS LIMITED | SIMPSON 7, TANAMI 4, TANAMI 5, WEST SIMPSON 1 |  | J.24.043229 | RPI | PS-SLK-Rental-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-02-07 | 2024-01-14 | 2024-01-30 | 2024-02-02 | 2024-03-20 23:59 | 2024-03-21 | 2024-03-20 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  | L0 - No RO |  | 75 | 83.3 | 100 | 75 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1045298 | O.1045298.01 | A.1045298.01.02 | HJV pre-rig is Gibson Plaform | SANTOS LIMITED | SOUTH PLATO 01, SOUTH PLATO 03, SOUTH GIBSON 1, PLATO-2 |  | J.23.121547 | RPI | PS-SLK-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-01-01 | 2024-04-30 |  | 2024-05-05 | 2024-06-26 23:59 |  | 2024-06-26 23:59 | New Burn WL | JDukas | 2024-06-13 09:39 | APutra7 |  | No |  |  |  |  | Justin Dukas |  | 0 | 7 |  | L0 - No RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 4 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1045298 | O.1045298.01 | A.1045298.01.04 | HJV-B Simpson Bravo | SANTOS LIMITED | SIMPSON 4H, MONET 2H, SIMPSON 10, SIMPSON 9 |  | J.24.010329 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2024-03-07 | 2024-04-28 | 2024-03-14 16:00 | 2024-04-28 | 2024-05-23 23:59 | 2024-04-16 | 2024-04-15 23:59 | New Burn WL | JDukas | 2024-05-27 14:27 | JDukas |  | No |  |  |  |  | Justin Dukas |  | 381880 | 6 |  | L0 - No RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 11 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1045268 | O.1045268.01 | A.1045268.01.01 | 5in MAXR with 3.38" guns | BEACH ENERGY RESOURCES NZ (HOLDINGS) LIMITED | KUPE SOUTH 09 | VALARIS 107 | J.23.172795 | RPI | TCP-PERM-JOB | InComplete | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2023-12-10 |  | 2023-12-14 | 2024-02-29 23:59 |  |  | New Plymouth TS | EKondratiev | 2024-03-08 05:19 | FDPSystemUser |  | No |  | [NZNP-TCP] - NZNPL-TCPF |  |  | Evgeniy Kondratiev |  | 125000 | 1 |  |  |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1045161 | O.1045161.01 | A.1045161.01.01 | PWC | COOPER ENERGY LIMITED |  | RIGLESS - AUSTRALIA | J.23.074618 | RPI | TCP-PERM-JOB | Medium | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2023-08-10 | 2024-04-15 | 2024-04-15 | 2024-05-14 23:59 | 2024-05-15 |  | APG TS | EKondratiev | 2024-04-29 08:00 | EKondratiev |  | No |  |  |  |  | Evgeniy Kondratiev |  | 0 | 1 |  |  |  | 29.2 | 8.3 | 0 | 0 | 11.3 |  | 1 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1045160 | O.1045160.01 | A.1045160.01.01 | PWC | WOODSIDE ENERGY LTD | ENE 03 ST1 | VALARIS MS-1 | J.23.074610 | RPI | TCP-TEMP-JOB | Medium | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2023-05-10 |  | 2023-06-08 | 2023-12-25 23:59 |  |  | APG TS | EKondratiev | 2024-11-19 20:07 | FDPSystemUser |  | No |  |  |  |  | Evgeniy Kondratiev |  | 196976.43 | 1 |  |  |  | 83.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1045159 | O.1045159.01 | A.1045159.01.01 | Hector 1 | SANTOS LIMITED | HECTOR 1 | RIGLESS - AUSTRALIA | J.23.074595 | RPI | TCP-TEMP-JOB | Medium | Operationally Complete | Close - PSD |  | Not Required | Design Completed | In Progress |  | 2023-07-01 |  | 2023-10-01 | 2023-10-11 23:59 |  |  | APG TS | EKondratiev | 2024-11-19 20:07 | FDPSystemUser |  | No |  |  |  |  | Evgeniy Kondratiev |  | 79047.04 | 1 |  |  |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1044884 | O.1044884.03 | A.1044884.03.01 | Flowback Gynatrix-01 | AWE PERTH PTY LTD | GYNATRIX 1 | RIGLESS - AUSTRALIA | J.24.011012 | RPI | TSWT-VXONLY-JOB | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-02-01 | 2024-01-22 |  | 2024-02-01 | 2024-02-21 23:59 |  | 2024-02-21 23:59 | APG TS | EKondratiev | 2024-11-19 20:21 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Qasim Malik |  | 133088.87 | 1 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 2 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1044884 | O.1044884.02 | A.1044884.02.06 | BSD-03 | AWE PERTH PTY LTD | BEHARRA SPRINGS DEEP 3 | RIGLESS - AUSTRALIA | J.24.015443 | RPI | TSWT-VXONLY-JOB | High | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2025-12-01 | 2025-12-01 | 2025-04-01 | 2025-12-01 | 2026-01-31 | 2026-02-01 | 2025-12-21 23:59 | APG TS | EKondratiev | 2025-06-03 14:30 | fkomul |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  | APG TS | Ahmed El-Wakil |  | 82306.69 | 1 |  | L3 - Full RO |  | 75 | 16.7 | 0 | 25 | 35 |  | 3 |  |  |  | 0 |  |  |  | Muhammad Fahd Waseem | TS Surface Testing
P.1044884 | O.1044884.02 | A.1044884.02.05 | Waitsia-13 | AWE PERTH PTY LTD |  | RIGLESS - AUSTRALIA | J.24.015442 | RPI | TSWT-VXONLY-JOB | High | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2025-06-01 | 2024-11-25 | 2025-06-01 | 2025-06-01 | 2025-06-21 23:59 | 2025-06-22 | 2025-06-21 23:59 | APG TS | EKondratiev | 2025-05-01 17:28 | MWaseem2 |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Qasim Malik |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 2 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1044884 | O.1044884.02 | A.1044884.02.04 | Waitsia-17 | AWE PERTH PTY LTD | WAITSIA-17 | RIGLESS - AUSTRALIA | J.24.015441 | RPI | TSWT-VXONLY-JOB | High | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2024-12-14 | 2024-10-26 |  | 2024-12-14 | 2025-01-03 23:59 |  | 2025-01-03 23:59 | APG TS | EKondratiev | 2025-02-03 09:35 | FKianifar |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  | TS ROC Abu Dhabi | Farhad Kianifar |  | 138022.47 | 1 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 62.5 | 63.7 |  | 2 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1044884 | O.1044884.02 | A.1044884.02.03 | Waitsia-16 | AWE PERTH PTY LTD | WAITSIA-16 | RIGLESS - AUSTRALIA | J.24.015440 | RPI | TSWT-VXONLY-JOB | High | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2024-11-19 | 2024-09-05 |  | 2024-11-18 | 2024-12-08 23:59 |  | 2024-12-08 23:59 | APG TS | EKondratiev | 2024-12-25 19:47 | AGabra |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  | TS ROC Abu Dhabi | Evgeniy Kondratiev |  | 122413.67 | 1 |  | L3 - Full RO |  | 91.7 | 75 | 100 | 87.5 | 86.3 |  | 2 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1044884 | O.1044884.02 | A.1044884.02.02 | Waitsia-12 | AWE PERTH PTY LTD | WAITSIA-12 | RIGLESS - AUSTRALIA | J.24.015439 | RPI | TSWT-VXONLY-JOB | High | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2024-10-22 | 2024-06-15 |  | 2024-10-22 | 2024-11-11 23:59 |  | 2024-11-11 23:59 | APG TS | EKondratiev | 2024-12-25 19:40 | AGabra |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  | TS ROC Abu Dhabi | Evgeniy Kondratiev |  | 125871.17 | 2 |  | L3 - Full RO |  | 91.7 | 83.3 | 100 | 50 | 77.5 |  | 1 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1044884 | O.1044884.02 | A.1044884.02.01 | Flowback Waitsia-11 | AWE PERTH PTY LTD | WAITSIA-11 | RIGLESS - AUSTRALIA | J.23.128821 | RPI | TSWT-VXONLY-JOB | High | Operationally Complete | Close - PSD |  | In Progress | Not Required | Design Completed | 2023-12-01 | 2023-11-15 |  | 2023-12-01 | 2024-01-31 23:59 |  | 2024-01-31 23:59 | APG TS | EKondratiev | 2024-11-19 20:21 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Qasim Malik |  | 109779.92 | 1 |  | L0 - No RO |  | 83.3 | 100 | 0 | 100 | 85 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1044884 | O.1044884.02 | A.1044884.02.07 | Design - CEC | AWE PERTH PTY LTD |  | RIGLESS - AUSTRALIA | J.24.097340 | RPI | TSWT-NO-OP | High | Unconfirmed - 50% | Design - CEC |  | Not Required | Not Required | Design Completed |  | 2024-05-07 |  | 2024-05-07 | 2024-12-31 23:59 |  |  | APG TS | EKondratiev | 2024-09-05 10:06 | EKondratiev |  | No |  |  |  |  | Evgeniy Kondratiev |  | 0 | 1 |  |  |  | 83.3 | 66.7 | 100 | 50 | 70 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1044884 | O.1044884.01 | A.1044884.01.01 | Vx Campaign | AWE PERTH PTY LTD |  | RIGLESS - AUSTRALIA | J.23.071936 | RPI | PSVS-VXONLY | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2024-04-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | 2024-04-30 23:59 | 2024-05-01 | 2024-04-30 23:59 | APG TS | EKondratiev | 2024-04-05 23:15 | FDPSystemUser |  | No |  | [AUJN-PSVS] - AU - Jandakot PSVS |  |  | Evgeniy Kondratiev |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Production Testing
P.1044870 | O.1044870.06 | A.1044870.06.01 | Equipment & Personnel For June & July | WELL OPS (UK) LTD | TUI 02H | HELIX Q7000 | J.23.106955 | WCF | CMT-EQPRNT,CMT-PERS | Low | Confirmed | Execute - PSD |  | Not Required | Not Required | Design Completed |  | 2023-06-28 | 2023-05-31 12:00 | 2023-06-28 | 2023-08-31 23:59 | 2023-08-23 |  | New Plymouth WS | GVang2 | 2023-08-03 12:48 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 0 |  |  |  | 87.5 | 50 | 100 | 25 | 65 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1044870 | O.1044870.05 | A.1044870.05.01 | Cement Plug @ 3085m | WELL OPS (UK) LTD | PATEKE 03H | HELIX Q7000 | J.23.116224 | WCF | REM-PA | High | Cancelled | Close - PSD |  | Not Required | In Progress | In Progress |  | 2023-08-10 | 2023-08-08 | 2023-08-15 | 2023-08-15 23:59 | 2023-08-23 |  | New Plymouth WS | MAlsaman | 2023-07-31 15:24 | MAlsaman |  | Yes |  |  |  |  | Tareq AlSaman |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1044870 | O.1044870.04 | A.1044870.04.01 | Cement Plug @ 3085m | WELL OPS (UK) LTD | PATEKE 04H | HELIX Q7000 | J.23.116227 | WCF | REM-PA | High | Cancelled | Close - PSD |  | Not Required | In Progress | In Progress |  | 2023-08-05 | 2023-08-03 | 2023-08-10 | 2023-08-10 23:59 | 2023-08-18 |  | New Plymouth WS | MAlsaman | 2023-07-31 15:26 | MAlsaman |  | Yes |  |  |  |  | Tareq AlSaman |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1044870 | O.1044870.03 | A.1044870.03.01 | Cement Plug @ 3085m | WELL OPS (UK) LTD | AMOKURA 2H | HELIX Q7000 | J.23.102117 | WCF | REM-PA | High | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2023-07-11 18:00 | 2023-06-22 | 2023-07-01 | 2023-07-11 18:00 | 2023-07-12 17:59 | 2023-07-16 | 2023-07-12 17:59 | New Plymouth WS | MAlsaman | 2023-07-11 12:32 | FDPSystemUser |  | Yes |  |  |  |  | Tareq AlSaman |  | 0 | 1 |  |  |  | 75 | 33.3 | 0 | 0 | 40 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1044870 | O.1044870.02 | A.1044870.02.01 | Cement Plug @ 3360m | WELL OPS (UK) LTD | TUI 02H | HELIX Q7000 | J.23.084134 | WCF | REM-PA | High | Confirmed | Design - CEC |  | Design Completed | Design Completed | Design Completed | 2023-06-22 | 2023-05-25 | 2023-06-13 | 2023-06-22 | 2023-06-22 23:59 | 2023-06-28 | 2023-06-22 23:59 | New Plymouth WS | MAlsaman | 2023-07-07 15:06 | MAlsaman |  | Yes |  |  |  |  | Tareq AlSaman |  | 121104.11 | 1 |  |  |  | 93.8 | 33.3 | 0 | 50 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1044870 | O.1044870.01 | A.1044870.01.01 | Equipment & Personnel For Apr, May | WELL OPS (UK) LTD | TUI 02H | HELIX Q7000 | J.23.071873 | WCF | CMT-EQPRNT,CMT-PERS | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | Design Completed |  | 2023-04-19 |  | 2023-04-19 | 2023-05-31 23:59 |  |  | New Plymouth WS | MAlsaman | 2023-05-29 20:49 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 0 |  |  |  | 87.5 | 50 | 100 | 25 | 65 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1044821 | O.1044821.01 | A.1044821.01.01 | Halyard-2 | SANTOS LIMITED |  | OCEAN APEX | J.24.002696 | RPI | TSWT-SEPONLY-JOB | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-02-01 | 2023-11-01 |  | 2024-02-01 | 2024-03-31 23:59 |  | 2024-03-31 23:59 | APG TS | EKondratiev | 2024-11-19 20:14 | FDPSystemUser |  | No |  |  |  |  | Evgeniy Kondratiev |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1044819 | O.1044819.01 | A.1044819.01.01 | HJV P&A Campaign | SANTOS LIMITED |  | VALARIS 107 | J.23.071240 | RPI | TSWT-NOSEPNOVX-JOB | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-11-01 | 2023-08-01 |  | 2023-11-01 | 2024-02-29 23:59 |  | 2024-02-29 23:59 | APG TS | EKondratiev | 2023-05-22 16:56 | EKondratiev |  | No |  |  |  |  | Evgeniy Kondratiev |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1044816 | O.1044816.01 | A.1044816.01.01 | MEFF P&A | SANTOS LIMITED |  | OCEAN APEX | J.24.002695 | RPI | TSWT-NOSEPNOVX-JOB | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-04-01 | 2023-11-01 |  | 2024-04-01 | 2025-01-31 23:59 |  | 2025-01-31 23:59 | APG TS | EKondratiev | 2023-05-22 17:01 | EKondratiev |  | No |  |  |  |  | Evgeniy Kondratiev |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1044586 | O.1044586.02 | A.1044586.02.01 | MEG Analyzer commissioning | BW OFFSHORE EPC FZCO |  | RIGLESS - AUSTRALIA | J.25.058915 | RPI | PSVS-SALE | High | Confirmed | Design - PSD |  | Not Required | Not Required | In Progress |  | 2025-02-21 |  | 2025-02-21 | 2025-02-28 23:59 |  |  | APG TS | MWaseem2 | 2025-02-28 10:03 | MWaseem2 |  | No |  | [AUJN-PSVS] - AU - Jandakot PSVS |  |  | Ahmed El-Wakil |  | 57055.45 | 1 |  |  |  | 83.3 | 100 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Muhammad Fahd Waseem | TS Production Testing
P.1044304 | O.1044304.01 | A.1044304.01.01 | Bleed off 2023 | SAPURA AUSTRALIA PTY LTD |  | SAPURAKENCANA CONSTRUCTOR | J.23.062383 | RPI | TSWT-NOSEPNOVX-JOB | High | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2023-07-20 | 2023-04-01 |  | 2023-07-20 | 2023-08-20 23:59 |  | 2023-08-20 23:59 | APG TS | EKondratiev | 2023-05-29 12:23 | EKondratiev |  | No |  |  |  |  | Evgeniy Kondratiev |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1044279 | O.1044279.01 | A.1044279.01.03 | RA source change and calibration | JADESTONE ENERGY (AUSTRALIA) PTY LTD | STAG 12H, STAG 15H, STAG 37H, STAG 49H, STAG 50H, STAG 45H, STAG 51H | STAG SNUBBING UNIT 1 | J.24.185611 | RPI | PSVS-VXSERVICE | High | Operationally Complete | Close - PSD |  | Not Required | Not Required | Design Completed |  | 2024-11-25 |  | 2024-12-03 | 2024-12-10 23:59 |  |  | APG TS | EKondratiev | 2025-02-03 13:55 | FDPSystemUser |  | No |  | [AUJN-PSVS] - AU - Jandakot PSVS |  |  | Evgeniy Kondratiev |  | 15147.5 | 1 |  | L0 - No RO |  | 91.7 | 66.7 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Production Testing
P.1044279 | O.1044279.01 | A.1044279.01.02 | 2024 Campaign | JADESTONE ENERGY (AUSTRALIA) PTY LTD | STAG 15H | STAG SNUBBING UNIT 1 | J.24.098920 | RPI | PSVS-SERVICES | High | Confirmed | Execute - PSD |  | Not Required | Not Required | Design Completed |  | 2024-05-11 |  | 2024-07-29 | 2024-08-28 23:59 |  |  | APG TS | EKondratiev | 2024-08-29 21:18 | FDPSystemUser |  | No |  | [AUJN-PSVS] - AU - Jandakot PSVS |  |  | Evgeniy Kondratiev |  | 20358.67 | 1 |  | L0 - No RO |  | 91.7 | 66.7 | 0 | 100 | 77.5 |  | 2 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Production Testing
P.1044279 | O.1044279.01 | A.1044279.01.01 | Vx Calibration | JADESTONE ENERGY (AUSTRALIA) PTY LTD | STAG 12H, STAG 15H, STAG 37H, STAG 49H, STAG 45H, STAG 51H, STAG 50H | STAG SNUBBING UNIT 1 | J.23.062143 | RPI | PSVS-SERVICES | High | Confirmed | Execute - PSD |  | Not Required | Not Required | Design Completed |  | 2023-04-01 |  | 2023-04-07 15:00 | 2023-06-12 15:00 |  |  | APG TS | EKondratiev | 2023-06-16 16:44 | EKondratiev |  | No |  | [AUJN-PSVS] - AU - Jandakot PSVS |  |  | Evgeniy Kondratiev |  | 20267.71 | 1 |  | L0 - No RO |  | 83.3 | 66.7 | 0 | 87.5 | 71.3 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Production Testing
P.1044216 | O.1044216.01 | A.1044216.01.01 | TPA-03 LWI vessel | NORMAND SAPURA PTY LTD | TPA 03 | SAPURAKENCANA CONSTRUCTOR | J.23.061615 | RPI | PS-WL-NO | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-28 | 2023-08-15 |  | 2023-08-28 | 2023-09-02 23:59 |  | 2023-09-02 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 0 | 5 |  | L1 - Support RO |  | 75 | 50 | 100 | 50 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1044216 | O.1044216.01 | A.1044216.01.02 | Sapura TPA-03 LWI opportunity | NORMAND SAPURA PTY LTD | TPA 03 | SAPURAKENCANA CONSTRUCTOR | J.23.130590 | RPI | PS-WL-Ops | High | Unconfirmed - 50% | Design - CEC |  | In Progress | Not Started | In Progress | 2024-12-29 | 2025-01-01 | 2024-12-30 | 2025-01-01 | 2025-01-25 23:59 | 2025-02-14 | 2025-02-08 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 5 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 5 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1043950 | O.1043950.01 | A.1043950.01.01 | Dongara 23 - CO2 Injection | AWE PERTH PTY LTD | DONGARA-23 |  | J.23.074559 | RPS | STM-MPUMP,STM-WELLKL | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-02-20 | 2024-02-20 |  | 2024-02-23 | 2024-02-26 23:59 |  | 2024-03-01 23:59 | AUS West Coast WS | AKohr | 2024-12-17 18:19 | CNevarez2 | M.1000188.02.64 | Yes |  |  |  |  | Aidan Flynn Kohr |  | 0 | 1 |  | L0 - No RO |  | 93.8 | 83.3 | 100 | 75 | 87.5 |  | 4 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Production Services
P.1043840 | O.1043840.01 | A.1043840.01.04 | Well #2 - GRE Casing | LABRADOR PETRO-MANAGEMENT PTY LTD | HASTINGS WATER BORE 2 | SWMS RIG 3 | J.23.057871 | WCF | PRI-LONG | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2023-04-08 06:00 | 2023-05-10 23:00 |  | 2023-05-11 06:00 | 2023-05-12 06:00 |  | 2023-05-12 06:00 | AUS East Coast WS | HNarainasamy | 2023-05-30 14:33 | GSingh54 |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 367.45 | 1 |  |  |  | 87.5 | 33.3 | 0 | 50 | 55 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1043840 | O.1043840.01 | A.1043840.01.01 | Hastings Water Bore #1 - 13-3/8" Surface Casing | LABRADOR PETRO-MANAGEMENT PTY LTD | HASTINGS WATER BORE 1 | SWMS RIG 3 | J.23.057860 | WCF | PRI-SURF, CMT-EQPRNT | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-26 06:00 | 2023-03-25 |  | 2023-03-26 06:00 | 2023-03-27 06:00 |  | 2023-03-27 06:00 | AUS East Coast WS | HNarainasamy | 2023-05-29 19:55 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 129954.52 | 1 |  |  |  | 81.3 | 83.3 | 0 | 75 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1043840 | O.1043840.01 | A.1043840.01.03 | Well #1 - GRE Casing | LABRADOR PETRO-MANAGEMENT PTY LTD | HASTINGS WATER BORE 1 | SWMS RIG 3 | J.23.057865 | WCF | PRI-LONG | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2023-04-01 06:00 | 2023-04-19 01:00 |  | 2023-04-20 06:00 | 2023-04-21 06:00 |  | 2023-04-21 06:00 | AUS East Coast WS | HNarainasamy | 2023-05-27 15:31 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 1023.39 | 1 |  |  |  | 81.3 | 50 | 0 | 50 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1043840 | O.1043840.01 | A.1043840.01.02 | Well #2 - 13-3/8" Surface Casing | LABRADOR PETRO-MANAGEMENT PTY LTD | HASTINGS WATER BORE 2 | SWMS RIG 3 | J.23.057861 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-03-29 06:00 | 2023-03-31 |  | 2023-04-01 06:00 | 2023-04-02 06:00 |  | 2023-04-02 06:00 | AUS East Coast WS | HNarainasamy | 2023-04-26 11:19 | GSingh54 |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 75 | 66.7 | 0 | 25 | 55 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1043748 | O.1043748.01 | A.1043748.01.01 | Wheatstone Deep 1 | CHEVRON APG ABU PERTH. | Wheatstone Deep 1 | OCEAN APEX | J.23.056965 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | Not Started | 2023-12-01 | 2023-11-26 |  | 2023-12-01 | 2024-01-25 23:59 |  | 2024-01-25 23:59 | New Burn WL | OAzarenko | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 0 | 6 |  | L2 - Shift RO |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1043748 | O.1043748.01 | A.1043748.01.02 | Dino South 1 | CHEVRON APG ABU PERTH. | Dino South 1 | OCEAN APEX | J.23.056969 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | Not Started | 2023-10-01 | 2023-12-22 |  | 2024-01-26 | 2024-03-19 23:59 |  | 2023-11-23 23:59 | New Burn WL | OAzarenko | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 0 | 5 |  | L2 - Shift RO |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1043700 | O.1043700.01 | A.1043700.01.01 | Packer setting | TAMBORAN RESOURCES LIMITED | AMUNGEE NW-2H, RM96-05-1 | VENTIA 33 | J.23.056233 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-10 23:00 | 2023-04-09 |  | 2023-04-13 | 2023-04-23 23:59 |  | 2023-04-21 21:59 | Roma WL | MRony2 | 2023-05-20 20:35 | KKeese |  | No |  |  |  |  | Jon Lawrie |  | 141723.85 | 1 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1043632 | O.1043632.01 | A.1043632.01.18 | QGC 2nd Well TD Section | QGC | BATHURST 5 | ENSIGN 965 | J.24.022179 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-02-22 | 2024-02-21 |  | 2024-02-22 | 2024-02-26 23:59 |  | 2024-02-27 00:59 | Roma WL | KKeese | 2024-12-12 17:11 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 8 |  | L3 - Full RO |  | 87.5 | 83.3 | 100 | 100 | 91.3 |  | 3 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1043632 | O.1043632.01 | A.1043632.01.01 | 1st Well_12.25inOH | QGC | Well #1 | ENSIGN 965 | J.23.055417 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2023-07-15 | 2023-07-13 |  | 2023-07-15 | 2023-07-17 23:59 |  | 2023-07-17 23:59 | Roma WL | SAli63 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 2 |  | L0 - No RO |  | 45.8 | 0 | 0 | 0 | 13.8 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1043632 | O.1043632.01 | A.1043632.01.02 | QGC Intermediate (12.25" & 13.625") | QGC | Well #1 | ENSIGN 965 | J.23.055421 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2023-07-11 | 2023-08-30 |  | 2023-08-30 | 2023-09-03 23:59 |  | 2023-09-03 23:59 | Roma WL | SAli63 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 7 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1043632 | O.1043632.01 | A.1043632.01.03 | 1st Well_7in_USIT-CBL | QGC | Well #1 | ENSIGN 965 | J.23.055791 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-05 | 2023-09-03 |  | 2023-09-05 | 2023-09-06 23:59 |  | 2023-09-06 23:59 | Roma WL | SAli63 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1043632 | O.1043632.01 | A.1043632.01.07 | 3rd Well_12.25inOH | QGC | Well #1 | ENSIGN 965 | J.23.055800 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-27 | 2023-09-25 |  | 2023-09-27 | 2023-09-29 23:59 |  | 2023-09-29 23:59 | Roma WL | SAli63 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1043632 | O.1043632.01 | A.1043632.01.06 | 2nd Well_7in_USIT-CBL | QGC | Well #1 | ENSIGN 965 | J.23.055799 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-16 | 2023-09-14 |  | 2023-09-16 | 2023-09-17 23:59 |  | 2023-09-17 23:59 | Roma WL | SAli63 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1043632 | O.1043632.01 | A.1043632.01.08 | 3rd Well_8.5inOH Pilot | QGC | Well #1 | ENSIGN 965 | J.23.055801 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2023-10-30 | 2023-10-28 |  | 2023-10-30 | 2023-11-03 23:59 |  | 2023-11-04 00:59 | Roma WL | SAli63 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 8 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 1 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1043632 | O.1043632.01 | A.1043632.01.05 | 2nd Well_8.5inOH Pilot | QGC | Well #1 | ENSIGN 965 | J.23.055797 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-08-27 | 2023-08-26 |  | 2023-08-27 | 2023-09-01 23:59 |  | 2023-09-01 23:59 | Roma WL | SAli63 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 7 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1043632 | O.1043632.01 | A.1043632.01.09 | 3rd Well_7in_USIT-CBL | QGC | Well #1 | ENSIGN 965 | J.23.055802 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-21 | 2023-10-19 |  | 2023-10-21 | 2023-10-22 23:59 |  | 2023-10-22 23:59 | Roma WL | SAli63 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1043632 | O.1043632.01 | A.1043632.01.10 | QGC Production (9.5" & 9 5/8") | QGC | Well #1 | ENSIGN 965 | J.23.084145 | RPE | ES-OH-Ops | Low | Cancelled | Execute - PSD |  | In Progress | Not Started | In Progress | 2023-08-08 | 2023-08-08 |  | 2023-08-08 | 2023-08-12 23:59 |  | 2023-08-12 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 8 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1043632 | O.1043632.01 | A.1043632.01.12 | QGC_Overstone-6_Full Well | QGC | OVERSTON 6 | ENSIGN 965 | J.23.084146 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-11-04 23:00 | 2023-11-04 |  | 2023-11-05 | 2023-12-04 |  | 2023-12-04 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 2 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 50 | 65 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1043632 | O.1043632.01 | A.1043632.01.13 | QGC 8.5in Production November | QGC | OVERSTON 6 | ENSIGN 965 | J.23.085721 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-11-30 | 2023-11-13 | 2023-11-29 | 2023-11-30 | 2023-12-04 23:59 | 2023-12-06 | 2023-12-04 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 7 |  | L1 - Support RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1043632 | O.1043632.01 | A.1043632.01.17 | QGC Production December | QGC | Well #1, OVERSTON 6 | ENSIGN 965 | J.23.087907 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-12-18 | 2023-12-16 | 2023-12-17 03:00 | 2023-12-18 | 2023-12-26 23:59 | 2023-12-27 01:00 | 2023-12-27 00:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 8 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 25 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1043632 | O.1043632.01 | A.1043632.01.20 | QGC 2nd Well Intermediate | QGC | BATHURST 5 | ENSIGN 965 | J.24.022181 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-02-03 13:00 | 2024-02-04 |  | 2024-02-04 | 2024-02-08 23:59 |  | 2024-02-08 12:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 300933.35 | 2 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1043632 | O.1043632.01 | A.1043632.01.22 | QGC Bathurst 5 Production | QGC | Well #1, OVERSTON 6, BATHURST 5 | ENSIGN 965 | J.24.069818 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2024-04-01 | 2024-03-10 |  | 2024-04-01 | 2024-04-09 23:59 |  | 2024-04-10 00:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 50 | 65 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1043632 | O.1043632.01 | A.1043632.01.21 | QGC Dunk 5 Intermediate | QGC | DUNK 5 | ENSIGN 965 | J.24.022182 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2024-05-12 07:00 | 2024-05-10 |  | 2024-05-12 06:00 | 2024-05-17 05:59 |  | 2024-05-17 06:59 | Roma WL | KKeese | 2024-08-08 18:49 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L2 - Shift RO |  | 83.3 | 83.3 | 100 | 75 | 82.5 |  | 3 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1043632 | O.1043632.01 | A.1043632.01.23 | QGC Dunk 5 Production | QGC | OVERSTON 6, BATHURST 5, DUNK 5 | ENSIGN 965 | J.24.105212 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-05-25 | 2024-05-03 |  | 2024-05-25 | 2024-06-02 23:59 |  | 2024-06-15 | Roma WL | JEsmeralda | 2024-07-05 17:13 | LKenzhegulova |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 40689.76 | 1 |  | L1 - Support RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1043632 | O.1043632.01 | A.1043632.01.19 | QGC 3nd Well TD Section | QGC | DUNK 5 | ENSIGN 965 | J.24.022180 | RPE | ES-OH-Ops | InComplete | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2024-05-19 01:00 | 2024-05-15 |  | 2024-05-19 | 2024-05-20 23:59 |  | 2024-05-21 01:59 | Roma WL | KKeese | 2024-06-15 16:26 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 180131.9 | 8 |  | L2 - Shift RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 2 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1043632 | O.1043632.01 | A.1043632.01.16 | 3rd Well USIT-CBL | QGC | Well #1 | ENSIGN 965 | J.24.004124 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-12-11 | 2023-12-09 |  | 2023-12-11 | 2023-12-12 23:59 |  | 2023-12-12 23:59 | Roma WL | KKeese | 2023-12-30 08:21 | KKeese |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1043632 | O.1043632.01 | A.1043632.01.15 | 2nd Well USIT-CBL | QGC | Well #1 | ENSIGN 965 | J.23.085724 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2023-10-23 | 2023-10-21 | 2023-10-23 01:00 | 2023-10-23 | 2023-10-24 23:59 | 2023-10-25 01:00 | 2023-10-24 23:59 | Roma WL | KKeese | 2023-09-26 12:13 | KKeese |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 2 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1043632 | O.1043632.01 | A.1043632.01.04 | 2nd Well_12.25inOH | QGC | Well #1 | ENSIGN 965 | J.23.055795 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-12 | 2023-09-10 | 2023-09-12 | 2023-09-12 | 2023-09-14 23:59 | 2023-09-15 | 2023-09-14 23:59 | Roma WL | SAli63 | 2023-08-28 10:45 | KKeese |  | No |  |  |  |  | Jon Lawrie |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1043632 | O.1043632.01 | A.1043632.01.14 | 2nd Well_7in USIT-CBL | QGC | Well #1 | ENSIGN 965 | J.23.085722 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-09 | 2023-10-07 |  | 2023-10-09 | 2023-10-10 23:59 |  | 2023-10-10 23:59 | Roma WL | KKeese | 2023-05-18 12:33 | KKeese |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1043632 | O.1043632.01 | A.1043632.01.11 | QGC USIT-CBL (7") | QGC | Well #1 | ENSIGN 965 | J.23.084144 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-08-16 | 2023-08-16 |  | 2023-08-16 | 2023-08-20 23:59 |  | 2023-08-20 23:59 | Roma WL | KKeese | 2023-05-15 17:48 | KKeese |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 8 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1043473 | O.1043473.01 | A.1043473.01.01 | SA Casing Patch Perforation Campaign | SANTOS LIMITED | MERANJI 21, NAPOWIE 009 |  | J.23.052714 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-03-10 | 2023-03-09 |  | 2023-03-10 | 2023-03-17 23:59 |  | 2023-03-17 23:59 | Moomba WL | ymoradi2 | 2023-03-07 14:51 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 66.7 | 66.7 | 0 | 0 | 40 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1043334 | O.1043334.02 | A.1043334.02.01 | Backoff_Colliding RM13-71-1 | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.23.071462 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | Not Started | 2023-04-16 20:00 | 2023-04-16 |  | 2023-04-16 20:00 | 2023-04-18 23:59 |  | 2023-04-18 23:59 | Roma WL | SAli63 | 2023-04-18 13:56 | SAli63 |  | No |  |  |  |  | Jon Lawrie |  | 0 | 1 |  | L0 - No RO |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1043334 | O.1043334.01 | A.1043334.01.02 | 407_QC | SANTOS LIMITED | RM13-30-1, RM13-71-1 | SAVANNA DRILLING #407 | J.23.062898 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-06 06:00 | 2023-04-06 |  | 2023-04-06 06:00 | 2023-04-25 23:59 |  | 2023-04-25 23:59 | Roma WL | SAli63 | 2023-04-18 21:03 | NSchwenke |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 4 |  | L3 - Full RO |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1043334 | O.1043334.01 | A.1043334.01.01 | SAV407_Quad Combo | SANTOS LIMITED | RM08-78-1, RM12-43-1, RM12-48-1 | SAVANNA DRILLING #407 | J.23.050152 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-03-06 06:00 | 2023-03-06 |  | 2023-03-06 06:00 | 2023-03-24 23:59 |  | 2023-03-24 23:59 | Roma WL | SAli63 | 2023-03-18 17:22 | NMoore2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 8 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1043268 | O.1043268.01 | A.1043268.01.01 | Kupe South TCP with MAXR | BEACH ENERGY RESOURCES NZ (HOLDINGS) LIMITED | KUPE SOUTH 09 | VALARIS 107 | J.23.048398 | RPI | TCP-PERM-JOB | High | Confirmed | Design - CEC |  | Not Started | In Progress | In Progress |  | 2023-03-15 |  | 2023-12-01 | 2023-12-25 23:59 |  |  | APG TS | RWallis | 2023-12-04 19:38 | EKondratiev |  | No |  | [AUSG-TCP] - |  |  | Evgeniy Kondratiev |  | 0 | 1 |  |  |  | 29.2 | 25 | 0 | 0 | 16.3 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TCP - Tubing-Conveyed Perforation
P.1043268 | O.1043268.01 | A.1043268.01.02 | Kupe South Product Sale | BEACH ENERGY RESOURCES NZ (HOLDINGS) LIMITED |  | VALARIS 107 | J.23.048452 | RPI | TCP-SALE | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2023-03-01 |  | 2023-03-01 | 2023-06-30 23:59 |  |  | APG TS | RWallis | 2023-03-31 17:23 | PZuliani |  | No |  |  |  |  | Evgeniy Kondratiev |  | 0 | 1 |  |  |  | 33.3 | 33.3 | 100 | 50 | 45 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TCP - Tubing-Conveyed Perforation
P.1043205 | O.1043205.01 | A.1043205.01.01 | Beehive-1 Stimulation | EOG RESOURCES AUSTRALIA BLOCK WA-488 PTY LTD | BEEHIVE-1 | VALARIS 107 | J.23.047265 | RPS | MTX-ACID | Medium | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2024-12-24 |  | 2025-01-01 | 2025-01-22 23:59 |  |  | AUS East Coast WS | AKohr | 2024-09-09 17:20 | CNevarez2 |  | Yes |  |  |  |  | Aidan Flynn Kohr |  | 0 | 2 |  |  |  | 56.3 | 0 | 0 | 0 | 22.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1043153 | O.1043153.03 | A.1043153.03.01 | Basker-7 P&A Cased Hole Operations | COOPER ENERGY LIMITED | BASKER 7 | HELIX Q7000 | J.24.047237 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2024-01-29 |  | 2024-01-29 | 2024-03-18 23:59 |  |  | New Burn WL | MSayed8 | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 0 |  | L0 - No RO |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1043153 | O.1043153.02 | A.1043153.02.01 | Helix Cooper | COOPER ENERGY LIMITED | Well #1, Well #2, Well #3, Well #4, Well #5, Well #6, Well #7 | HELIX Q7000 | J.24.047228 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-05-18 | 2024-06-15 | 2024-05-21 | 2024-06-25 | 2024-11-16 23:59 | 2024-11-17 | 2024-11-16 23:59 | New Burn WL | MSayed8 | 2024-04-09 17:02 | MElsanousi |  | No |  |  |  |  | Justin Dukas |  | 0 | 18 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1043153 | O.1043153.01 | A.1043153.01.01 | COOPER P&A Cased Hole Operations (Basker-3) | COOPER ENERGY LIMITED | BASKER 2, BASKER 3, BASKER 4, BASKER 5, BASKER 6 ST1, BASKER 7, MANTA 2 | HELIX Q7000 | J.23.045968 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | In Progress | Design Completed | Design Completed | 2023-11-26 | 2023-12-24 |  | 2024-01-03 | 2024-05-26 23:59 |  | 2024-05-26 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 647250 | 18 |  | L0 - No RO |  | 91.7 | 50 | 0 | 100 | 72.5 |  | 2 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1043153 | O.1043153.01 | A.1043153.01.03 | Cooper P&A Cased Hole Operations Remaining 6 Wells Phase-2 (6-Apr-2024) | COOPER ENERGY LIMITED | BASKER 2, BASKER 3, BASKER 4, BASKER 5, BASKER 6 ST1, BASKER 7, MANTA 2 | HELIX Q7000 | J.24.083191 | RPI | PS-SLK-Rental-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | Design Completed | 2024-04-10 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-05-31 23:59 | 2024-06-01 | 2024-05-31 23:59 | New Burn WL | MSayed8 | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 4 |  | L0 - No RO |  | 79.2 | 91.7 | 50 | 0 | 56.3 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1043153 | O.1043153.01 | A.1043153.01.02 | COOPER P&A Cased Hole Operations (Remaining 6 Wells) | COOPER ENERGY LIMITED | BASKER 7, BASKER 2, BASKER 4, BASKER 6 ST1, MANTA 2, BASKER 5, BASKER 3 | HELIX Q7000 | J.24.047240 | RPI | PS-WL-Ops | High | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2024-01-29 | 2024-01-29 | 2024-01-28 | 2024-01-29 | 2024-04-30 23:59 | 2024-05-01 | 2024-04-30 23:59 | New Burn WL | MSayed8 | 2024-05-06 17:15 | MSayed8 |  | No |  |  |  |  | Justin Dukas |  | 1516887 | 6 |  | L0 - No RO |  | 91.7 | 83.3 | 100 | 100 | 92.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1042556 | O.1042556.01 | A.1042556.01.01 | CO2 Injection | AWE PERTH PTY LTD | DONGARA-23 |  | J.23.043053 | RPI | TSWT-NOSEPNOVX-JOB | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-02-20 | 2024-02-03 | 2024-02-20 | 2024-02-20 | 2024-02-28 23:59 | 2024-02-29 | 2024-02-28 23:59 | APG TS | QMalik2 | 2024-04-12 16:24 | EKondratiev | M.1000188.02.57 | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Qasim Malik |  | 224361.28 | 1 |  | L0 - No RO |  | 95.8 | 83.3 | 100 | 75 | 86.3 |  | 1 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1042515 | O.1042515.01 | A.1042515.01.01 | 7 X 9 5/8" IBC-CBL | JADESTONE ENERGY (AUSTRALIA) PTY LTD | STAG 48H | RIGLESS - AUSTRALIA | J.23.044749 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2023-03-01 |  | 2023-03-04 | 2023-03-31 23:59 |  |  | New Burn WL | PRoche | 2023-02-27 10:26 | FDPSystemUser |  | No |  |  |  | ROE WL Jakarta | Justin Dukas |  | 0 | 0 |  | L1 - Support RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1042472 | O.1042472.01 | A.1042472.01.01 | Rigless John Brookes | SANTOS LIMITED | JOHN BROOKES 2, JOHN BROOKES 3, JOHN BROOKES 6, JOHN BROOKES 5 | RIGLESS - AUSTRALIA | J.23.037040 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2023-06-28 | 2023-06-19 |  | 2023-06-28 | 2023-08-08 23:59 |  | 2023-08-08 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Jarrod Sedmak |  | 75200 | 2 |  | L0 - No RO |  | 75 | 66.7 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1042472 | O.1042472.01 | A.1042472.01.02 | John Brookes trip 2 | SANTOS LIMITED | JOHN BROOKES 2, JOHN BROOKES 5, JOHN BROOKES 3, JOHN BROOKES 6 | RIGLESS - AUSTRALIA | J.23.061613 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2023-10-02 | 2023-10-01 |  | 2023-10-02 | 2023-11-13 23:59 |  | 2023-11-13 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 432104 | 3 |  | L0 - No RO |  | 75 | 100 | 100 | 62.5 | 81.3 |  | 1 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1042472 | O.1042472.01 | A.1042472.01.03 | John Brookes Rig Visit | SANTOS LIMITED |  | RIGLESS - AUSTRALIA | J.23.073846 | RPI | PS-SLK-NO | Low | Operationally Complete | Close - PSD |  | Not Required | Not Started | In Progress |  | 2023-04-18 05:15 | 2023-04-19 | 2023-04-19 | 2023-04-24 23:59 | 2023-04-25 |  | New Burn WL | crowand | 2023-08-11 17:45 | VOliveira5 |  | No |  |  |  |  | Justin Dukas |  | 0 | 0 |  | L0 - No RO |  | 58.3 | 33.3 | 100 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1042288 | O.1042288.02 | A.1042288.02.01 | Canyon-2 Pulsar | OMEGA OIL AND GAS LIMITED | CANYON 2 | RIGLESS - AUSTRALIA | J.24.185472 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2025-04-08 | 2025-04-08 | 2025-04-08 | 2025-04-08 | 2025-04-14 23:59 | 2025-04-15 | 2025-04-15 00:59 | Roma WL | JEsmeralda | 2025-04-15 10:12 | NAndilla |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 3 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1042288 | O.1042288.01 | A.1042288.01.04 | Canyon-1_TD | OMEGA OIL AND GAS LIMITED | CANYON 1 | SLR 185 | J.23.044418 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-23 | 2023-05-23 |  | 2023-05-23 | 2023-05-26 23:59 |  | 2023-05-26 23:59 | Roma WL | MRony2 | 2023-06-21 12:49 | KKeese |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 87735.54 | 3 |  | L2 - Shift RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1042288 | O.1042288.01 | A.1042288.01.02 | Intermediate_2nd Well | OMEGA OIL AND GAS LIMITED | CANYON 1 | SLR 185 | J.23.044412 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-08 | 2023-05-07 |  | 2023-05-09 | 2023-05-11 23:59 |  | 2023-05-13 23:59 | Roma WL | MRony2 | 2023-05-13 13:10 | ysaeedabadian |  | No |  |  |  |  | Jon Lawrie |  | 0 | 3 |  | L0 - No RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1042288 | O.1042288.01 | A.1042288.01.03 | 1st well TD | OMEGA OIL AND GAS LIMITED | CANYON 2 | SLR 185 | J.23.044414 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-13 | 2023-04-12 |  | 2023-04-13 | 2023-04-15 23:59 |  | 2023-04-15 23:59 | Roma WL | MRony2 | 2023-04-15 09:18 | RDell |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 205708.59 | 3 |  | L2 - Shift RO |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1042288 | O.1042288.01 | A.1042288.01.01 | QuadCombo_1st_Intermediate | OMEGA OIL AND GAS LIMITED | CANYON 2 | SLR 185 | J.23.044410 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-03-29 17:00 | 2023-03-29 |  | 2023-03-30 | 2023-04-02 23:59 |  | 2023-04-02 16:59 | Roma WL | MRony2 | 2023-04-03 11:07 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 39580.9 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 87.5 | 76.3 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1042141 | O.1042141.01 | A.1042141.01.01 | BW Offshore FPSO | BW OFFSHORE EPC FZE |  | VALARIS MS-1 | J.23.061970 | RPI | TSWT-SALE | High | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2023-03-25 |  | 2023-03-25 | 2023-12-31 23:59 |  |  | APG TS | RWallis | 2023-09-20 08:39 | EKondratiev |  | No |  |  |  |  | Dmitrii Musiiako |  | 0 | 1 |  |  |  | 25 | 33.3 | 100 | 50 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1041909 | O.1041909.02 | A.1041909.02.01 | West Peron 2 Gun Loading and Operation | INPEX OPERATIONS AUSTRALIA PTY LTD | WEST PERON-2 | VALARIS-247 | J.23.030435 | RPI | TCP-PERM-JOB | Medium | Confirmed | Execute - PSD |  | Not Required | Design Completed | In Progress |  | 2024-01-01 |  | 2024-06-09 | 2025-01-31 23:59 |  |  | APG TS | MSwara | 2025-01-24 14:18 | MSwara |  | No |  | [AUSG-TCP] - |  |  | Yudha Swara |  | 328080.28 | 2 |  |  |  | 91.7 | 83.3 | 100 | 87.5 | 88.8 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1041909 | O.1041909.01 | A.1041909.01.01 | Basset Deep-1 | INPEX OPERATIONS AUSTRALIA PTY LTD | BASSETT DEEP-1 | OCEAN APEX | J.23.030427 | RPI | TCP-NO-OP | High | Confirmed | Execute - PSD |  | Not Required | Not Required | Design Completed |  | 2023-10-04 |  | 2024-02-01 | 2024-05-31 23:59 |  |  | APG TS | MSwara | 2024-12-31 21:03 | EKondratiev |  | No |  | [AUSG-TCP] - |  |  | Yudha Swara |  | 206610.97 | 1 |  |  |  | 100 | 83.3 | 100 | 75 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1041909 | O.1041909.01 | A.1041909.01.02 | Holonema-1 | INPEX OPERATIONS AUSTRALIA PTY LTD | Holonema-1 | OCEAN APEX | J.23.030432 | RPI | TCP-NO-OP | High | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2023-10-10 | 2023-10-25 | 2023-10-25 | 2023-12-25 23:59 | 2023-12-31 |  | APG TS | MSwara | 2024-04-03 17:52 | EKondratiev |  | No |  | [AUSG-TCP] - |  |  | Yudha Swara |  | 97559.82 | 1 |  |  |  | 58.3 | 50 | 100 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1041755 | O.1041755.01 | A.1041755.01.03 | 7in Production Liner | STRIKE ENERGY LIMITED |  | EASTERNWELL 106 | J.23.028783 | WCF | PRI-INTER,PRI-LIN, CMT-MATSAL | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-08-13 | 2023-08-12 12:00 | 2023-08-12 23:00 | 2023-08-13 | 2023-08-13 23:59 | 2023-08-13 23:00 | 2023-08-13 23:59 | AUS East Coast WS | HNarainasamy | 2023-07-20 16:06 | GSingh54 |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1041755 | O.1041755.01 | A.1041755.01.02 | 9-5/8in Intermediate Casing | STRIKE ENERGY LIMITED |  | EASTERNWELL 106 | J.23.028781 | WCF | PRI-INTER, CMT-MATSAL | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-08-03 | 2023-08-02 12:00 | 2023-08-03 | 2023-08-03 | 2023-08-03 23:59 | 2023-08-04 | 2023-08-03 23:59 | AUS East Coast WS | HNarainasamy | 2023-07-20 16:06 | GSingh54 |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1041755 | O.1041755.01 | A.1041755.01.01 | 13-3/8in Surface Casing | STRIKE ENERGY LIMITED | Well #1 | EASTERNWELL 106 | J.23.028778 | WCF | PRI-SURF, CMT-MATSAL | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-24 | 2023-07-23 12:00 | 2023-07-24 | 2023-07-24 | 2023-07-24 23:59 | 2023-07-25 | 2023-07-24 23:59 | AUS East Coast WS | HNarainasamy | 2023-07-20 16:06 | GSingh54 |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1041720 | O.1041720.02 | A.1041720.02.01 | PNX | ESSO AUSTRALIA LTD |  |  | J.23.085270 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2023-07-01 | 2023-07-01 |  | 2023-07-01 | 2023-07-31 23:59 |  | 2023-07-31 23:59 | New Burn WL | VOliveira5 | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1041720 | O.1041720.02 | A.1041720.02.02 | Slim Epilogue - Bass Strait | ESSO AUSTRALIA LTD |  |  | J.23.122021 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | Not Started | 2023-10-29 | 2023-10-29 |  | 2023-11-22 | 2023-12-22 23:59 |  | 2023-12-22 23:59 | New Burn WL | VOliveira5 | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 3 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1041720 | O.1041720.01 | A.1041720.01.04 | Q4 PEAK OPS | ESSO AUSTRALIA LTD |  |  | J.25.103306 | RPI | PS-SLK-NO | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2025-10-01 |  | 2025-10-01 | 2025-12-30 23:59 |  |  | New Burn WL | MElsanousi | 2025-05-26 14:24 | FDPSystemUser |  | No |  |  |  |  | Yasser Moradi |  | 0 |  |  | L0 - No RO |  | 25 | 33.3 | 100 | 50 | 42.5 |  | 0 | [7 empty] | Kelly Keese | Wireline Slickline
P.1041720 | O.1041720.01 | A.1041720.01.03 | Q3 PEAK Ops | ESSO AUSTRALIA LTD |  |  | J.25.102468 | RPI | PS-SLK-NO | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2025-07-01 |  | 2025-07-01 | 2025-09-29 23:59 |  |  | New Burn WL | KKeese | 2025-05-24 18:59 | FDPSystemUser |  | No |  |  |  |  | Yasser Moradi |  | 0 |  |  | L0 - No RO |  | 33.3 | 33.3 | 100 | 50 | 45 |  | 0 | [7 empty] | Kelly Keese | Wireline Slickline
P.1041720 | O.1041720.01 | A.1041720.01.02 | PEAK Rev Forecast Q2 | ESSO AUSTRALIA LTD |  |  | J.25.059681 | RPI | PS-SLK-NO | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2025-04-01 |  | 2025-04-01 | 2025-06-30 23:59 |  |  | New Burn WL | KKeese | 2025-02-26 09:57 | KKeese |  | No |  |  |  |  | Edmund Brobbey |  | 0 |  |  | L0 - No RO |  | 33.3 | 33.3 | 100 | 50 | 45 |  | 0 | [7 empty] | Kelly Keese | Wireline Slickline
P.1041720 | O.1041720.01 | A.1041720.01.01 | REV Forecast PEAK | ESSO AUSTRALIA LTD |  |  | J.23.162522 | RPI | PS-SLK-NO | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2023-03-01 |  | 2023-03-01 | 2025-03-01 23:59 |  |  | New Burn WL | VOliveira5 | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Ally Bell |  | 0 | 0 |  | L0 - No RO |  | 33.3 | 33.3 | 100 | 50 | 45 |  | 1 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1041315 | O.1041315.02 | A.1041315.02.01 | Dedicated 409_QC_Feb24 | SANTOS LIMITED | RM90-167-1, RM90-166-1, RM90-165-1, RM90-164-1, RM90-153-1, RM90-152-1, RM90-169-1, RM40-116-1, RM90-170-1, RM40-117-1 | SAVANNA DRILLING #406 | J.24.043093 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-01-19 | 2024-02-26 |  | 2024-02-26 | 2024-04-05 23:59 |  | 2024-02-24 23:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1041315 | O.1041315.02 | A.1041315.02.02 | Dedicated 406_QC_Mar24 | SANTOS LIMITED | RM90-167-1, RM90-166-1, RM90-165-1, RM90-164-1, RM90-153-1, RM90-152-1, RM90-169-1, RM40-116-1, RM90-170-1, RM40-117-1, RM40-118-1, RM40-107-1, RM40-108-1, RM40-99-1, RM40-98-1, RM40-87-1, RM40-88-1 | SAVANNA DRILLING #406 | J.24.060083 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-01-23 | 2024-02-29 |  | 2024-03-01 | 2024-04-09 23:59 |  | 2024-02-28 22:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1041315 | O.1041315.02 | A.1041315.02.04 | Dedicated 406_QC_June 24 | SANTOS LIMITED | RM90-167-1, RM90-166-1, RM90-165-1, RM90-164-1, RM90-153-1, RM90-152-1, RM90-169-1, RM40-116-1, RM90-170-1, RM40-117-1, RM40-118-1, RM40-107-1, RM40-108-1, RM40-99-1, RM40-98-1, RM40-87-1, RM40-78-1, RM40-89-1, RM40-100-1, RM40-114-1, RM40-122-1, RM40-121-1, RM40-110-1, RM40-111-1, RM40-102-1, RM40-104-1, RM40-91-1, RM40-92-1, RM40-112-1, RM40-80-1 | SAVANNA DRILLING #406 | J.24.087490 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-03-18 01:00 | 2024-04-24 |  | 2024-04-25 | 2024-05-26 23:59 |  | 2024-04-23 22:59 | Roma WL | JEsmeralda | 2024-08-08 20:17 | SNiang |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1041315 | O.1041315.02 | A.1041315.02.05 | Dedicated 406_QC_Jun24 | SANTOS LIMITED | RM40-123-1, RM40-80-1, RM40-70-1, RM40-79-1, DULACCA WEST 2 | SAVANNA DRILLING #406 | J.24.105193 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-02-28 23:00 | 2024-05-24 |  | 2024-05-25 | 2024-06-25 23:59 |  | 2024-06-25 23:59 | Roma WL | JEsmeralda | 2024-06-24 22:40 | LKenzhegulova |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1041315 | O.1041315.02 | A.1041315.02.03 | Dedicated 406_QC_Apr24 | SANTOS LIMITED | RM90-167-1, RM90-166-1, RM90-165-1, RM90-164-1, RM90-153-1, RM90-152-1, RM90-169-1, RM40-116-1, RM90-170-1, RM40-117-1, RM40-118-1, RM40-107-1, RM40-108-1, RM40-99-1, RM40-98-1, RM40-87-1, RM40-78-1, RM40-89-1, RM40-100-1, RM40-114-1 | SAVANNA DRILLING #406 | J.24.073533 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-02-16 | 2024-03-24 | 2024-03-24 | 2024-03-25 | 2024-04-25 23:59 | 2024-05-08 23:00 | 2024-03-23 22:59 | Roma WL | JEsmeralda | 2024-05-06 08:08 | BLima7 |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 100 | 83.3 | 50 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1041315 | O.1041315.01 | A.1041315.01.13 | Dedicated December | SANTOS LIMITED | RM90-64-1, RM90-75-1, RM90-65-1, RM90-85-1, RM90-97-1, RM90-109-1, RM90-108-1, RM90-130-1, RM90-134-1, RM90-171-1, RM90-168-1 | SAVANNA DRILLING #409 | J.23.174392 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-12-09 | 2023-12-09 |  | 2023-12-09 | 2024-01-31 23:59 |  | 2024-01-31 23:59 | Roma WL | KKeese | 2024-08-26 14:25 | SNiang |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1041315 | O.1041315.01 | A.1041315.01.07 | Dedicated Unit July | SANTOS LIMITED | REEDY CREEK SOUTH 2, BBNML02, RM27-47-1 | SAVANNA DRILLING #409 | J.23.084106 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-07 | 2023-07-01 |  | 2023-07-01 | 2023-07-27 23:59 |  | 2023-07-27 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 137751.79 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1041315 | O.1041315.01 | A.1041315.01.09 | Dedicated Unit September | SANTOS LIMITED | RM90-63-1, RM90-61-1, RM90-40-1, RM90-50-1, RM40-45-1, RM90-90-1, RM90-101-1, RM90-89-1, RM90-88-1, RM90-124-1 | SAVANNA DRILLING #409 | J.23.084108 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-09-01 | 2023-09-01 |  | 2023-09-01 | 2023-09-30 23:59 |  | 2023-09-30 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1041315 | O.1041315.01 | A.1041315.01.08 | Dedicated Unit August | SANTOS LIMITED | BRUMBY 23, RM90-72-1, RM90-73-1, RM90-38-1, RM40-155-1, RM90-62-1, RM90-39-1, RM90-49-1, RM90-63-1 | SAVANNA DRILLING #409 | J.23.084107 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-08-04 | 2023-08-01 |  | 2023-08-01 | 2023-08-27 23:59 |  | 2023-08-27 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 1 |  | L3 - Full RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1041315 | O.1041315.01 | A.1041315.01.11 | Dedicated Unit November | SANTOS LIMITED | BUNDALEER 5, BUNDALEER SOUTH 1 | SAVANNA DRILLING #409 | J.23.085714 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-10-25 | 2023-10-25 |  | 2023-10-25 | 2023-11-20 23:59 |  | 2023-11-20 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1041315 | O.1041315.01 | A.1041315.01.10 | Dedicated Unit October | SANTOS LIMITED | RM90-133-1, RM90-142-1, RM90-54-1, RM90-55-1, RLHGWG01, RLHML01 | SAVANNA DRILLING #409 | J.23.085713 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Not Required | Not Required | In Progress |  | 2023-10-01 | 2023-09-30 02:00 | 2023-10-01 | 2023-10-31 23:59 | 2023-11-01 |  | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1041315 | O.1041315.01 | A.1041315.01.12 | Dedicated Unit December | SANTOS LIMITED | RM90-63-1 | SAVANNA DRILLING #409 | J.23.085715 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2023-09-01 | 2023-09-01 | 2023-08-31 13:00 | 2023-09-01 | 2023-09-27 23:59 | 2023-09-28 | 2023-09-27 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 1 |  | L3 - Full RO |  | 79.2 | 25 | 0 | 0 | 31.3 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1041315 | O.1041315.01 | A.1041315.01.06 | Dedicated June | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.23.041613 | RPE | ES-OH-NO | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2023-06-01 |  | 2023-06-01 | 2023-06-27 23:59 |  |  | Roma WL | MRony2 | 2023-06-19 08:12 | SAli63 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 137751.79 |  |  | L3 - Full RO |  | 50 | 33.3 | 100 | 75 | 57.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1041315 | O.1041315.01 | A.1041315.01.04 | Dedicated truck April | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.23.041606 | RPE | ES-OH-NO | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2023-04-01 |  | 2023-04-01 | 2023-04-27 23:59 |  |  | Roma WL | MRony2 | 2023-04-11 11:59 | SAli63 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 137751.79 |  |  | L3 - Full RO |  | 50 | 33.3 | 100 | 75 | 57.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1041315 | O.1041315.01 | A.1041315.01.05 | Dedicated May OH | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.23.041607 | RPE | ES-OH-NO | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2023-05-01 |  | 2023-05-01 | 2023-05-27 23:59 |  |  | Roma WL | MRony2 | 2023-03-02 23:24 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 137751.79 |  |  | L3 - Full RO |  | 50 | 33.3 | 100 | 100 | 65 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1041315 | O.1041315.01 | A.1041315.01.03 | Dedicated truck March | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.23.041605 | RPE | ES-OH-NO | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2023-03-01 02:00 |  | 2023-03-01 02:00 | 2023-03-28 01:59 |  |  | Roma WL | MRony2 | 2023-02-24 10:45 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 137751.79 |  |  | L3 - Full RO |  | 50 | 33.3 | 100 | 75 | 57.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1041315 | O.1041315.01 | A.1041315.01.02 | Dedicated for Feb | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.23.035736 | RPE | ES-OH-NO | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2023-02-02 |  | 2023-02-02 | 2023-02-28 23:59 |  |  | Roma WL | MRony2 | 2023-02-06 12:45 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 137751.79 | 0 |  | L3 - Full RO |  | 50 | 33.3 | 100 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1041315 | O.1041315.01 | A.1041315.01.01 | OH dedicated truck | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.22.137378 | RPE | ES-OH-NO | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2023-01-01 |  | 2023-01-01 | 2023-01-31 23:59 |  |  | Roma WL | MRony2 | 2023-02-02 16:00 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 143237.65 | 0 |  | L3 - Full RO |  | 50 | 33.3 | 100 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1041221 | O.1041221.01 | A.1041221.01.09 | Plug 3 - Balanced Plug | OMEGA OIL AND GAS LIMITED |  | SLR 185 | J.23.091257 | WCF | CMT-MATSAL, REM-KOP,REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-14 08:00 | 2023-05-21 |  | 2023-05-28 08:00 | 2023-05-29 08:00 |  | 2023-05-15 08:00 | AUS East Coast WS | MMendoza26 | 2023-06-01 10:28 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 81.3 | 16.7 | 0 | 0 | 37.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1041221 | O.1041221.01 | A.1041221.01.08 | Plug 2 - KOP | OMEGA OIL AND GAS LIMITED |  | SLR 185 | J.23.091256 | WCF | CMT-MATSAL, REM-KOP,REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-13 08:00 | 2023-05-20 |  | 2023-05-27 08:00 | 2023-05-28 08:00 |  | 2023-05-14 08:00 | AUS East Coast WS | MMendoza26 | 2023-06-01 10:15 | MMendoza26 |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 |  |  |  | 81.3 | 16.7 | 0 | 0 | 37.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1041221 | O.1041221.01 | A.1041221.01.07 | Plug 1 - Balanced Plug | OMEGA OIL AND GAS LIMITED |  | SLR 185 | J.23.090802 | WCF | CMT-MATSAL, REM-KOP,REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-12 08:00 | 2023-05-19 |  | 2023-05-26 08:00 | 2023-05-27 08:00 |  | 2023-05-13 08:00 | AUS East Coast WS | MMendoza26 | 2023-06-01 10:08 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 81.3 | 16.7 | 0 | 0 | 37.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1041221 | O.1041221.01 | A.1041221.01.06 | Well #2 - 4-1/2" Production Casing | OMEGA OIL AND GAS LIMITED | CANYON 1 | SLR 185 | J.23.024630 | WCF | PRI-INTER,PRI-LONG, CMT-MATSAL | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-05-22 08:00 | 2023-05-29 |  | 2023-06-05 08:00 | 2023-06-06 08:00 |  | 2023-05-23 08:00 | AUS East Coast WS | HNarainasamy | 2023-05-30 12:05 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 37673.29 | 1 |  |  |  | 93.8 | 16.7 | 0 | 100 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1041221 | O.1041221.01 | A.1041221.01.02 | 7" Intermediate Casing | OMEGA OIL AND GAS LIMITED | CANYON 2 | SLR 185 | J.23.023281 | WCF | PRI-INTER, CMT-MATSAL | Low | Unconfirmed - 90% | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-24 08:00 | 2023-03-26 |  | 2023-04-01 08:00 | 2023-04-02 08:00 |  | 2023-04-02 08:00 | AUS East Coast WS | HNarainasamy | 2023-05-27 15:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 12437.1 | 1 |  |  |  | 87.5 | 16.7 | 0 | 100 | 60 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1041221 | O.1041221.01 | A.1041221.01.04 | Well #2 - 9-5/8in Surface Casing | OMEGA OIL AND GAS LIMITED | CANYON 1 | SLR 185 | J.23.024628 | WCF | PRI-SURF, CMT-MATSAL | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2023-04-30 08:00 | 2023-05-07 |  | 2023-05-14 08:00 | 2023-05-15 08:00 |  | 2023-05-01 08:00 | AUS East Coast WS | HNarainasamy | 2023-05-27 14:53 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 82262.83 | 1 |  |  |  | 93.8 | 16.7 | 0 | 100 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1041221 | O.1041221.01 | A.1041221.01.05 | Well #2 - 7" Intermediate Casing | OMEGA OIL AND GAS LIMITED | CANYON 1 | SLR 185 | J.23.024629 | WCF | PRI-SURF,PRI-INTER, CMT-MATSAL | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-05-08 08:00 | 2023-05-15 |  | 2023-05-22 08:00 | 2023-05-23 08:00 |  | 2023-05-09 08:00 | AUS East Coast WS | HNarainasamy | 2023-05-25 10:41 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 57604.55 | 1 |  |  |  | 93.8 | 66.7 | 100 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1041221 | O.1041221.01 | A.1041221.01.03 | 4-1/2" Production Casing | OMEGA OIL AND GAS LIMITED | CANYON 2 | SLR 185 | J.23.023282 | WCF | PRI-INTER,PRI-LONG, CMT-MATSAL | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-14 08:00 | 2023-04-12 |  | 2023-04-15 08:00 | 2023-04-16 08:00 |  | 2023-04-17 08:00 | AUS East Coast WS | HNarainasamy | 2023-04-24 15:09 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 32194.83 | 1 |  |  |  | 68.8 | 33.3 | 0 | 100 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1041221 | O.1041221.01 | A.1041221.01.01 | 9-5/8in Surface Casing | OMEGA OIL AND GAS LIMITED | CANYON 2 | SLR 185 | J.23.023280 | WCF | PRI-SURF, CMT-MATSAL | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-16 | 2023-03-22 |  | 2023-03-29 08:00 | 2023-03-30 08:00 |  | 2023-03-22 23:59 | AUS East Coast WS | HNarainasamy | 2023-03-29 15:06 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 30706.76 | 1 |  |  |  | 81.3 | 16.7 | 0 | 75 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1040971 | O.1040971.01 | A.1040971.01.02 | 12.25" ES | BEACH ENERGY RESOURCES NZ (HOLDINGS) LIMITED | KUPE SOUTH 09 | VALARIS 107 | J.23.021304 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Required | In Progress | 2023-09-08 | 2023-09-01 |  | 2023-09-08 | 2023-09-09 23:59 |  | 2023-09-09 23:59 | New Plymouth WL | CKok3 | 2024-08-21 17:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1040971 | O.1040971.01 | A.1040971.01.03 | 8.5" ES | BEACH ENERGY RESOURCES NZ (HOLDINGS) LIMITED | KUPE SOUTH 09 | VALARIS 107 | J.23.021316 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-11-15 | 2023-11-25 |  | 2023-11-27 | 2023-12-11 23:59 |  | 2023-12-11 23:59 | New Plymouth WL | CKok3 | 2024-08-21 17:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 5 |  | L0 - No RO |  | 91.7 | 50 | 100 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1040971 | O.1040971.01 | A.1040971.01.01 | 17.5" ES | BEACH ENERGY RESOURCES NZ (HOLDINGS) LIMITED | KUPE SOUTH 09 | VALARIS 107 | J.23.021303 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Required | In Progress | 2023-09-01 | 2023-08-25 |  | 2023-09-01 | 2023-09-02 23:59 |  | 2023-09-02 23:59 | New Plymouth WL | CKok3 | 2024-08-21 17:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1040971 | O.1040971.01 | A.1040971.01.04 | KS-9 Completion | BEACH ENERGY RESOURCES NZ (HOLDINGS) LIMITED | KUPE SOUTH 09 | VALARIS 107 | J.23.120416 | RPE | ES-CH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2023-12-19 | 2023-11-19 |  | 2023-12-19 | 2024-01-03 23:59 |  | 2024-01-03 23:59 | New Plymouth WL | CKok3 | 2024-08-21 17:52 | FDPSystemUser |  | No |  |  |  |  | Cheryl Kok |  | 0 | 2 |  | L0 - No RO |  | 83.3 | 50 | 100 | 100 | 80 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1040971 | O.1040971.01 | A.1040971.01.05 | Gyro in 22" | BEACH ENERGY RESOURCES NZ (HOLDINGS) LIMITED | KUPE SOUTH 09 | VALARIS 107 | J.23.154686 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-10-23 | 2023-10-20 |  | 2023-10-23 | 2023-10-24 23:59 |  | 2023-10-24 23:59 | New Plymouth WL | CKok3 | 2024-08-21 17:52 | FDPSystemUser |  | No |  |  |  |  | Cheryl Kok |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 100 | 100 | 75 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1040789 | O.1040789.03 | A.1040789.03.01 | Tamboran OH/ CH | TAMBORAN RESOURCES LIMITED |  | H&P 469 | J.25.102031 | RPE | ES-CH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-04-19 01:00 | 2025-06-20 01:00 | 2025-08-05 23:00 | 2025-08-31 | 2025-10-16 23:59 | 2025-10-17 | 2025-10-17 00:59 | Roma WL | CKok3 | 2025-08-13 14:23 | CKok3 |  | No |  |  |  |  | Irwan Wongso |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1040789 | O.1040789.02 | A.1040789.02.04 | Tamboran Well 2 CBL PPC | TAMBORAN RESOURCES LIMITED | SHENANDOAH SOUTH 2-2H, SHENANDOAH SOUTH 2-1H, SHENANDOAH S2-4H | H&P 469 | J.24.169285 | RPE | ES-CH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2024-07-04 | 2024-09-04 |  | 2024-11-15 | 2024-12-31 23:59 |  | 2024-12-31 23:59 | Roma WL | JEsmeralda | 2025-01-31 12:22 | JEsmeralda |  | No |  |  |  |  | Irwan Wongso |  | 713472.38 | 2 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1040789 | O.1040789.02 | A.1040789.02.02 | Shenandoah South 2 CBL PPC | TAMBORAN RESOURCES LIMITED | SHENANDOAH S-1, SHENANDOAH SOUTH 2-1H, SHENANDOAH SOUTH 2-2H | H&P 469 | J.24.096878 | RPE | ES-CH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2024-07-04 | 2024-07-07 |  | 2024-08-23 | 2024-10-08 23:59 |  | 2024-10-08 23:59 | Roma WL | KKeese | 2024-09-21 19:06 | BLima7 |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 356736.19 | 2 |  | L0 - No RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 4 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1040789 | O.1040789.02 | A.1040789.02.03 | Q4 Activity - 6 wells | TAMBORAN RESOURCES LIMITED | SHENANDOAH S-1 | H&P 469 | J.24.096879 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-11-22 | 2024-11-22 |  | 2024-11-22 | 2025-01-19 23:59 |  | 2025-01-24 23:00 | Roma WL | KKeese | 2024-08-27 17:47 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 3 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 2 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1040789 | O.1040789.02 | A.1040789.02.01 | Shenandoah South 1 | TAMBORAN RESOURCES LIMITED | SHENANDOAH S-1 | H&P 469 | J.23.125119 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-08-23 | 2023-08-23 | 2023-08-23 | 2023-08-23 | 2023-08-30 23:59 | 2023-08-31 | 2023-10-26 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 216025.99 | 3 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1040789 | O.1040789.01 | A.1040789.01.02 | SS1_USIT PPC CBL | TAMBORAN RESOURCES LIMITED | AMUNGEE NW-2H, SHENANDOAH S-1 | SILVER CITY 40 | J.23.117765 | RPE | ES-CH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress |  | 2023-07-30 | 2023-08-01 23:00 | 2023-08-02 | 2023-08-06 23:59 | 2023-08-06 23:00 |  | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 51535.41 | 3 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1040789 | O.1040789.01 | A.1040789.01.03 | Shenandoah South-1 OH Section | TAMBORAN RESOURCES LIMITED | SHENANDOAH S-1 | SILVER CITY 40 | J.23.121549 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2023-08-16 |  | 2023-08-17 | 2023-08-20 23:59 |  |  | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 0 |  | L2 - Shift RO |  | 8.3 | 0 | 0 | 0 | 2.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1040789 | O.1040789.01 | A.1040789.01.01 | CBL (2 section) | TAMBORAN RESOURCES LIMITED | AMUNGEE NW-2H | SILVER CITY 40 | J.22.134066 | RPE | ES-CH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-12-17 | 2022-12-14 |  | 2022-12-17 | 2022-12-21 23:59 |  | 2022-12-21 23:59 | Roma WL | MRony2 | 2022-12-25 12:35 | SLie4 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 94087.07 | 2 |  | L3 - Full RO |  | 75 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1040460 | O.1040460.03 | A.1040460.03.08 | Apex - CMT Service - Nov | WOODSIDE ENERGY JULIMAR PTY LTD | JULIMAR SOUTH-1 | OCEAN APEX | J.23.035764 | WCF | CMT-PERS,CMT-EQPRNT,CMT-MPUMP | Low | Cancelled | Close - PSD |  | In Progress | Not Required | In Progress | 2023-10-21 01:00 | 2023-10-21 01:00 | 2023-10-19 | 2023-10-21 01:00 | 2023-11-20 00:59 | 2023-11-22 | 2023-11-21 00:59 | AUS East Coast WS | NKhoa | 2023-07-31 12:32 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1040460 | O.1040460.03 | A.1040460.03.07 | Apex - CMT Service - Oct | WOODSIDE ENERGY JULIMAR PTY LTD | JULIMAR SOUTH-1 | OCEAN APEX | J.23.020391 | WCF | CMT-PERS,CMT-EQPRNT,CMT-MPUMP | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-21 01:00 | 2023-09-21 01:00 | 2023-09-19 | 2023-09-21 01:00 | 2023-10-21 00:59 | 2023-10-22 23:00 | 2023-10-22 00:59 | AUS East Coast WS | NKhoa | 2023-07-31 12:32 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1040460 | O.1040460.03 | A.1040460.03.06 | Apex - CMT Service - Dec | WOODSIDE ENERGY JULIMAR PTY LTD | JULIMAR SOUTH-1 | OCEAN APEX | J.23.020390 | WCF | CMT-PERS,CMT-EQPRNT,CMT-MPUMP | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-11-21 | 2023-11-21 | 2023-11-19 | 2023-11-21 | 2023-12-20 00:59 | 2023-12-22 23:00 | 2023-12-21 23:59 | AUS East Coast WS | NKhoa | 2023-07-31 12:32 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1040460 | O.1040460.03 | A.1040460.03.04 | PnA | WOODSIDE ENERGY JULIMAR PTY LTD | JULIMAR SOUTH-1 | OCEAN APEX | J.23.020388 | WCF | REM-PA | High | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-01 01:00 | 2023-10-04 01:00 | 2023-11-01 | 2023-11-01 01:00 | 2023-11-03 00:59 | 2023-11-03 | 2023-11-03 00:59 | AUS East Coast WS | NKhoa | 2023-07-31 12:32 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1040460 | O.1040460.03 | A.1040460.03.03 | 9 5/8in Liner | WOODSIDE ENERGY JULIMAR PTY LTD | JULIMAR SOUTH-1 | OCEAN APEX | J.23.020387 | WCF | PRI-LIN | Low | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress | 2023-10-25 01:00 | 2023-10-04 01:00 | 2023-10-25 | 2023-10-25 01:00 | 2023-10-27 00:59 | 2023-10-27 | 2023-10-27 00:59 | AUS East Coast WS | NKhoa | 2023-07-31 12:32 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1040460 | O.1040460.03 | A.1040460.03.02 | 13 5/8in casing | WOODSIDE ENERGY JULIMAR PTY LTD | JULIMAR SOUTH-1 | OCEAN APEX | J.23.020386 | WCF | PRI-INTER | Medium | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress | 2023-10-15 01:00 | 2023-09-14 01:00 | 2023-10-15 | 2023-10-15 01:00 | 2023-10-17 00:59 | 2023-10-17 | 2023-10-17 00:59 | AUS East Coast WS | NKhoa | 2023-07-31 12:32 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1040460 | O.1040460.03 | A.1040460.03.01 | 36in Conductor | WOODSIDE ENERGY JULIMAR PTY LTD | JULIMAR SOUTH-1 | OCEAN APEX | J.23.020385 | WCF | PRI-COND | Medium | Cancelled | Close - PSD |  | In Progress | Design Completed | Design Completed | 2023-10-05 01:00 | 2023-09-14 01:00 | 2023-10-05 | 2023-10-05 01:00 | 2023-10-07 00:59 | 2023-10-07 | 2023-10-07 00:59 | AUS East Coast WS | NKhoa | 2023-07-31 12:32 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 |  |  |  | 56.3 | 0 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1040460 | O.1040460.03 | A.1040460.03.05 | 20in Casing - CANCELLED | WOODSIDE ENERGY JULIMAR PTY LTD | JULIMAR SOUTH-1 | OCEAN APEX | J.23.020389 | WCF | CMT-PERS, PRI-SURF | Medium | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress | 2023-10-06 | 2023-07-13 |  | 2023-10-06 | 2023-10-07 23:59 |  | 2023-10-07 23:59 | AUS East Coast WS | NKhoa | 2023-06-22 14:20 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1040460 | O.1040460.01 | A.1040460.01.05 | Apex - CMT Service - July | WOODSIDE ENERGY JULIMAR PTY LTD | GEMTREE-01 | OCEAN APEX | J.23.020380 | WCF | CMT-PERS | Low | Confirmed | Execute - PSD |  | In Progress | Not Required | In Progress | 2023-06-21 | 2023-06-21 | 2023-06-19 14:00 | 2023-06-21 | 2023-07-20 23:59 | 2023-07-22 | 2023-07-20 23:59 | AUS East Coast WS | NKhoa | 2025-04-22 16:56 | SToorpu2 |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 |  |  |  | 75 | 33.3 | 100 | 50 | 60 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1040460 | O.1040460.01 | A.1040460.01.09 | Apex - CMT service - Aug | WOODSIDE ENERGY JULIMAR PTY LTD | GEMTREE-01 | OCEAN APEX | J.23.104245 | WCF | CMT-PERS | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2023-07-21 | 2023-07-21 | 2023-07-19 04:00 | 2023-07-21 | 2023-08-20 23:59 | 2023-08-22 | 2023-08-20 23:59 | AUS East Coast WS | NKhoa | 2023-08-18 13:59 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 16391.1 | 0 |  |  |  | 93.8 | 50 | 100 | 75 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1040460 | O.1040460.01 | A.1040460.01.11 | Apex - CMT Service - Oct | WOODSIDE ENERGY JULIMAR PTY LTD | GEMTREE-01 | OCEAN APEX | J.23.104248 | WCF | CMT-PERS | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-21 | 2023-09-21 | 2023-09-19 | 2023-09-21 | 2023-10-20 23:59 | 2023-10-23 01:00 | 2023-10-22 00:59 | AUS East Coast WS | NKhoa | 2023-07-31 12:29 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 |  |  |  | 56.3 | 33.3 | 100 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1040460 | O.1040460.01 | A.1040460.01.10 | Apex - CMT Service - Sep | WOODSIDE ENERGY JULIMAR PTY LTD | GEMTREE-01 | OCEAN APEX | J.23.104246 | WCF | CMT-PERS | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-08-21 | 2023-08-21 | 2023-08-19 04:00 | 2023-08-21 | 2023-09-20 23:59 | 2023-09-22 | 2023-09-20 23:59 | AUS East Coast WS | NKhoa | 2023-07-31 12:29 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 |  |  |  | 62.5 | 33.3 | 100 | 50 | 55 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1040460 | O.1040460.01 | A.1040460.01.04 | PnA | WOODSIDE ENERGY JULIMAR PTY LTD | GEMTREE-01 | OCEAN APEX | J.23.020379 | WCF | REM-PA | High | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress | 2023-09-10 | 2023-08-13 | 2023-09-10 | 2023-09-10 | 2023-09-11 23:59 | 2023-09-12 | 2023-09-11 23:59 | AUS East Coast WS | NKhoa | 2023-07-31 12:29 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1040460 | O.1040460.01 | A.1040460.01.03 | 9 5/8in Liner | WOODSIDE ENERGY JULIMAR PTY LTD | GEMTREE-01 | OCEAN APEX | J.23.020378 | WCF | PRI-LIN | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-09-03 | 2023-08-13 | 2023-09-03 | 2023-09-03 | 2023-09-04 23:59 | 2023-09-05 | 2023-09-04 23:59 | AUS East Coast WS | NKhoa | 2023-07-31 12:29 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1040460 | O.1040460.01 | A.1040460.01.02 | 13 5/8in casing | WOODSIDE ENERGY JULIMAR PTY LTD | GEMTREE-01 | OCEAN APEX | J.23.020377 | WCF | PRI-INTER | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-08-24 | 2023-07-25 | 2023-08-24 | 2023-08-24 | 2023-08-25 23:59 | 2023-08-26 | 2023-08-25 23:59 | AUS East Coast WS | NKhoa | 2023-07-31 12:29 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 |  |  |  | 56.3 | 0 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1040460 | O.1040460.01 | A.1040460.01.01 | 36in Conductor | WOODSIDE ENERGY JULIMAR PTY LTD | GEMTREE-01 | OCEAN APEX | J.23.020370 | WCF | PRI-COND | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-08-15 | 2023-07-25 | 2023-08-15 | 2023-08-15 | 2023-08-16 23:59 | 2023-08-17 | 2023-08-16 23:59 | AUS East Coast WS | NKhoa | 2023-07-31 12:29 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 |  |  |  | 56.3 | 0 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1040460 | O.1040460.01 | A.1040460.01.08 | Apex - CMT Service - Jun | WOODSIDE ENERGY JULIMAR PTY LTD | GEMTREE-01 | OCEAN APEX | J.23.020383 | WCF | CMT-PERS,CMT-MPUMP | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2023-05-21 | 2023-05-21 |  | 2023-05-21 | 2023-06-20 23:59 |  | 2023-06-20 23:59 | AUS East Coast WS | NKhoa | 2022-12-13 15:01 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1040460 | O.1040460.01 | A.1040460.01.06 | Apex - CMT Service - Apr | WOODSIDE ENERGY JULIMAR PTY LTD | GEMTREE-01 | OCEAN APEX | J.23.020381 | WCF | CMT-PERS,CMT-EQPRNT,CMT-MPUMP | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2023-03-21 | 2023-03-21 |  | 2023-03-21 | 2023-04-20 23:59 |  | 2023-04-20 22:59 | AUS East Coast WS | NKhoa | 2022-12-13 14:59 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1040460 | O.1040460.01 | A.1040460.01.07 | Apex - CMT Service - May | WOODSIDE ENERGY JULIMAR PTY LTD | GEMTREE-01 | OCEAN APEX | J.23.020382 | WCF | CMT-PERS,CMT-EQPRNT,CMT-MPUMP | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2023-04-21 | 2023-04-21 |  | 2023-04-21 | 2023-05-20 23:59 |  | 2023-05-21 23:59 | AUS East Coast WS | NKhoa | 2022-12-13 14:59 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1040436 | O.1040436.02 | A.1040436.02.01 | Moomba pad SCMT | SANTOS LIMITED | MOOMBA 289, MOOMBA 288, MOOMBA 287, MOOMBA 290 |  | J.23.033389 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-02-10 09:00 | 2023-02-01 |  | 2023-02-10 09:00 | 2023-02-14 08:59 |  | 2023-02-14 08:59 | Moomba WL | ymoradi2 | 2023-02-10 09:17 | eismail |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 7220.86 | 2 |  | L3 - Full RO |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1040436 | O.1040436.01 | A.1040436.01.01 | Raffle 1 MPBT-DB | SANTOS LIMITED | RAFFLE 1 |  | J.22.131478 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-04 | 2022-12-04 |  | 2022-12-04 | 2022-12-09 23:59 |  | 2022-12-09 23:59 | Moomba WL | ymoradi2 | 2022-12-11 18:23 | ymoradi2 |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1040246 | O.1040246.02 | A.1040246.02.03 | Oru-2 | TAMARIND NZ ONSHORE LIMITED | ORU 2 | NOVA-1 | J.25.048766 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-06-01 23:00 | 2025-04-20 14:00 | 2025-04-29 01:00 | 2025-04-27 14:00 | 2025-05-01 13:59 | 2025-05-04 | 2025-05-02 07:59 | New Plymouth WL | CKok3 | 2025-03-28 12:22 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Cheryl Kok |  | 0 | 2 |  | L2 - Shift RO |  | 66.7 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1040246 | O.1040246.02 | A.1040246.02.01 | Cheal B-11 | TAMARIND NZ ONSHORE LIMITED | Well #1 | NOVA-1 | J.24.018954 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-07-02 09:00 | 2024-06-24 14:00 |  | 2024-07-01 14:00 | 2024-07-05 13:59 |  | 2024-07-06 08:59 | New Plymouth WL | CKok3 | 2024-08-21 17:52 | FDPSystemUser |  | No |  |  |  |  | Ayssar Alsayed |  | 0 | 2 |  | L0 - No RO |  | 75 | 0 | 0 | 0 | 22.5 |  | 2 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1040246 | O.1040246.02 | A.1040246.02.02 | Cheal B-12 | TAMARIND NZ ONSHORE LIMITED | CHEAL B-12 | NOVA-1 | J.24.060126 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-09-14 | 2024-08-06 14:00 |  | 2024-08-08 14:00 | 2024-08-12 13:59 |  | 2024-08-13 08:59 | New Plymouth WL | CKok3 | 2024-08-20 16:59 | YLee25 |  | No |  |  |  | ROE WL Mumbai | Cheryl Kok |  | 279643.99 | 2 |  | L2 - Shift RO |  | 100 | 100 | 100 | 100 | 100 |  | 2 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1040246 | O.1040246.01 | A.1040246.01.02 | Cheal B-11 IBC-CBL | TAMARIND NZ ONSHORE LIMITED | CHEAL B-11 | NOVA-1 | J.23.076124 | RPE | ES-CH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-29 | 2023-05-27 |  | 2023-05-29 | 2023-06-01 23:59 |  | 2023-06-01 23:59 | New Plymouth WL | CKok3 | 2023-05-16 16:53 | CKok3 |  | No |  |  |  |  | Cheryl Kok |  | 0 | 1 |  | L0 - No RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1040246 | O.1040246.01 | A.1040246.01.01 | Cheal B-11 | TAMARIND NZ ONSHORE LIMITED | CHEAL B-11 | NOVA-1 | J.23.019185 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Required | In Progress | 2023-04-16 | 2023-04-15 14:00 |  | 2023-04-15 14:00 | 2023-04-19 13:59 |  | 2023-04-19 23:59 | New Plymouth WL | CLorenzo | 2023-05-02 14:39 | YLee25 |  | No |  |  |  |  | Ayssar Alsayed |  | 846183.79 | 2 |  | L0 - No RO |  | 83.3 | 100 | 0 | 100 | 85 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1040135 | O.1040135.01 | A.1040135.01.01 | Angore C1 Explosive shipment | MOBIL PNG GAS HOLDINGS PTY LTD |  | NABORS 702 |  | RPE | ES-OH-NO | Low | Unconfirmed - 90% | Design - CEC |  | Not Started | Not Started | In Progress |  | 2022-11-20 |  | 2022-11-23 | 2025-12-13 17:25 |  |  | New Burn WL | miqbal13 | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 10000 | 0 |  | L0 - No RO |  | 50 | 33.3 | 100 | 58.3 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1040096 | O.1040096.03 | A.1040096.03.01 | Conductor Casing | TAMBORAN RESOURCES LIMITED | SHENANDOAH S-1 | SILVER CITY 40 | J.23.110669 | WCF | PRI-COND | Low | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2023-07-20 |  | 2023-08-03 | 2023-08-03 23:59 |  |  | AUS East Coast WS | MAlsaman | 2023-08-17 10:54 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 |  |  |  | 12.5 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1040096 | O.1040096.02 | A.1040096.02.01 | Remote Package - Chemicals & Equipment | TAMBORAN RESOURCES LIMITED | AMUNGEE NW-2H | SILVER CITY 40 | J.24.000680 | WCF | CMT-MATSAL,CMT-EQPRNT, CMT-TOOLS, REM-KOP | Low | Confirmed | Execute - PSD |  | In Progress | Design Completed | In Progress | 2022-11-19 23:00 | 2022-11-20 |  | 2022-11-20 | 2023-01-07 22:59 |  | 2023-01-26 22:59 | AUS East Coast WS | ALyons | 2023-05-27 15:31 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 615322.69 | 1 |  |  |  | 56.3 | 33.3 | 0 | 50 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1040096 | O.1040096.01 | A.1040096.01.06 | Remote Package - Chemicals & Equipment | TAMBORAN RESOURCES LIMITED | AMUNGEE NW 1H | SILVER CITY 40 | J.22.129156 | WCF | CMT-MATSAL,CMT-EQPRNT, CMT-TOOLS | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-01 22:00 | 2023-08-02 20:00 |  | 2023-08-02 20:00 | 2023-10-02 19:59 |  | 2023-10-02 20:59 | AUS East Coast WS | ALyons | 2023-07-11 11:10 | MAlsaman |  | No |  |  |  |  | Ariel Lyons |  | 0 | 0 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1040096 | O.1040096.01 | A.1040096.01.05 | 5 1/2" HZ Production | TAMBORAN RESOURCES LIMITED | Well #1 | SILVER CITY 40 | J.23.019031 | WCF | PRI-LONG, CMT-MATSAL | Medium | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2023-07-28 23:00 | 2023-09-28 20:00 | 2023-09-29 22:00 | 2023-10-04 20:59 | 2023-10-05 20:00 |  | AUS East Coast WS | ALyons | 2023-07-11 11:10 | MAlsaman |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1040096 | O.1040096.01 | A.1040096.01.04 | PlugBack & KickOff | TAMBORAN RESOURCES LIMITED | Well #1 | SILVER CITY 40 | J.23.019032 | WCF | REM-PA | Low | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2023-07-28 22:00 | 2023-08-31 20:00 | 2023-09-01 22:00 | 2023-09-06 21:59 | 2023-09-08 20:00 |  | AUS East Coast WS | ALyons | 2023-07-11 11:10 | MAlsaman |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1040096 | O.1040096.01 | A.1040096.01.03 | 9 5/8" Intermediate | TAMBORAN RESOURCES LIMITED | Well #1 | SILVER CITY 40 | J.23.019033 | WCF | PRI-INTER, CMT-MATSAL | Low | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2023-08-01 22:00 | 2023-09-17 09:00 | 2023-09-16 21:00 | 2023-09-22 20:59 | 2023-09-22 20:00 |  | AUS East Coast WS | ALyons | 2023-07-11 11:10 | MAlsaman |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1040096 | O.1040096.01 | A.1040096.01.02 | 13 3/8" surface | TAMBORAN RESOURCES LIMITED | Well #1 | SILVER CITY 40 | J.22.129155 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2023-08-01 23:00 | 2023-08-12 | 2023-08-12 23:00 | 2023-08-17 21:59 | 2023-08-16 23:00 |  | AUS East Coast WS | ALyons | 2023-07-11 11:10 | MAlsaman |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1040096 | O.1040096.01 | A.1040096.01.01 | 18 5/8 Conductor | TAMBORAN RESOURCES LIMITED | Well #1 | SILVER CITY 40 | J.22.129154 | WCF | PRI-COND, CMT-MATSAL | Low | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2023-04-11 23:00 | 2023-04-15 | 2023-08-01 23:00 | 2023-08-06 22:59 | 2023-04-24 |  | AUS East Coast WS | ALyons | 2023-07-11 11:10 | MAlsaman |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1040088 | O.1040088.02 | A.1040088.02.01 | Pateke 3H P&A | WELL OPS (UK) LTD |  | HELIX Q7000 | J.23.053735 | RPI | CT-CEM | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-30 01:00 | 2023-06-01 |  | 2023-06-30 01:00 | 2023-08-24 00:59 |  | 2023-08-24 00:59 | New Plymouth WS | HFerdjallah | 2023-03-07 14:31 | HFerdjallah |  | Yes |  |  |  |  | Caio Henrique Teixeira Fancio |  | 0 | 2 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1040088 | O.1040088.01 | A.1040088.01.02 | Pateke 3H P&A | WELL OPS (UK) LTD | PATEKE 03H | HELIX Q7000 | J.23.053729 | RPI | CT-CEM | High | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2023-09-03 06:00 | 2023-06-14 23:00 |  | 2023-09-03 | 2023-11-06 23:59 |  | 2023-11-02 05:59 | New Plymouth WS | HFerdjallah | 2023-11-02 22:07 | JHernandez246 |  | Yes |  |  |  |  | Jose Luis Tejeda |  | 0 | 2 |  |  |  | 87.5 | 66.7 | 0 | 50 | 65 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1040088 | O.1040088.01 | A.1040088.01.03 | Pateke 4H P&A | WELL OPS (UK) LTD | PATEKE 04H | HELIX Q7000 | J.23.053759 | RPI | CT-CEM | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-20 04:00 | 2023-07-08 23:00 | 2023-08-08 | 2023-08-13 | 2023-09-03 23:59 | 2023-09-04 | 2023-07-25 03:59 | New Plymouth WS | HFerdjallah | 2023-09-07 15:33 | HFerdjallah |  | Yes |  |  |  |  | Caio Henrique Teixeira Fancio |  | 0 | 2 |  |  |  | 87.5 | 83.3 | 100 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1040088 | O.1040088.01 | A.1040088.01.01 | AMOKURA 2H CT P&A | WELL OPS (UK) LTD | AMOKURA 2H | HELIX Q7000 | J.23.033995 | RPI | CT-CEM | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-06-29 | 2023-05-01 23:00 | 2023-06-19 | 2023-06-29 | 2023-07-17 23:59 | 2023-07-13 | 2023-08-07 11:42 | New Plymouth WS | HFerdjallah | 2023-09-01 11:09 | HFerdjallah |  | Yes |  |  |  |  | Jose Luis Tejeda |  | 45729.2 | 2 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1040088 | O.1040088.01 | A.1040088.01.05 | Tui-2H Milling | WELL OPS (UK) LTD | TUI 02H | HELIX Q7000 | J.23.112422 | RPI | CT-MILLNOSLB | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-19 | 2023-07-18 | 2023-07-18 12:00 | 2023-07-19 | 2023-07-31 23:59 | 2023-08-03 | 2023-07-31 23:59 | New Plymouth WS | JHernandez246 | 2023-08-23 15:46 | HFerdjallah |  | Yes |  |  |  |  | Jose Luis Tejeda |  | 0 | 1 |  |  |  | 75 | 66.7 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1040088 | O.1040088.01 | A.1040088.01.04 | Tui 2H P&A | WELL OPS (UK) LTD | TUI 02H | HELIX Q7000 | J.23.053760 | RPI | CT-CEM,CT-CIRC,CT-CONFORM, CT-TOOLCON | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-06-12 10:00 | 2023-04-19 23:00 | 2023-05-17 | 2023-06-12 | 2023-06-25 23:59 | 2023-06-26 | 2023-06-19 11:59 | New Plymouth WS | HFerdjallah | 2023-08-11 11:00 | HFerdjallah |  | Yes |  |  |  |  | Jose Luis Tejeda |  | 1744400 | 1 |  |  |  | 93.8 | 66.7 | 0 | 75 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1039709 | O.1039709.01 | A.1039709.01.01 | GB Energy (VIC) exploration well | GB ENERGY | GB-2 | VALARIS 107 | J.23.018158 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-07 | 2023-07-04 |  | 2023-07-07 | 2023-08-12 23:59 |  | 2023-08-12 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Jarrod Sedmak |  | 871790.3 | 6 |  | L0 - No RO |  | 91.7 | 66.7 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1039708 | O.1039708.01 | A.1039708.01.01 | Inpex Exploration Holonema-1 | INPEX OPERATIONS AUSTRALIA PTY LTD | HOLONEMA-1 | OCEAN APEX | J.23.018155 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-12-08 | 2023-12-08 |  | 2023-12-08 | 2024-01-26 23:59 |  | 2024-01-26 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | Yes |  |  |  |  | Jarrod Sedmak |  | 1516199.98 | 5 |  | L0 - No RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1039708 | O.1039708.01 | A.1039708.01.02 | Inpex Exploration Well Basset Deep-1 | INPEX OPERATIONS AUSTRALIA PTY LTD | BASSETT DEEP-1 | OCEAN APEX | J.23.018156 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-02-04 | 2024-01-28 | 2024-05-05 | 2024-05-20 | 2024-06-01 23:59 | 2024-06-07 | 2024-07-25 23:59 | New Burn WL | JDukas | 2024-05-28 15:56 | LThanh2 |  | No |  |  |  |  | Jarrod Sedmak |  | 159783 | 7 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 3 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1039676 | O.1039676.01 | A.1039676.01.01 | EOG Exploration Well | EOG RESOURCES AUSTRALIA BLOCK WA-488 PTY LTD |  | VALARIS 107 | J.23.018100 | RPE | ES-OH-Ops | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-07-01 | 2025-07-01 |  | 2025-07-01 | 2025-09-23 23:59 |  | 2025-06-24 23:59 | New Burn WL | JDukas | 2025-05-24 16:15 | KKeese |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 7 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 4 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1039672 | O.1039672.01 | A.1039672.01.04 | Strike Perth basin Well 14 | STRIKE ENERGY LIMITED |  | ENSIGN 974 | J.23.018097 | RPE | ES-OH-Ops | High | Unconfirmed - 50% | Design - CEC |  | In Progress | Not Started | In Progress | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-05-13 23:59 | 2026-05-14 | 2026-05-13 23:59 | New Burn WL | JDukas | 2025-11-10 10:29 | EBrobbey |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 7 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 2 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1039672 | O.1039672.01 | A.1039672.01.06 | Strike Perth basin Well 6 | STRIKE ENERGY LIMITED |  | ENSIGN 974 | J.24.000638 | RPE | ES-OH-Ops | High | Unconfirmed - 50% | Design - CEC |  | In Progress | Not Started | In Progress | 2026-08-01 | 2026-08-01 | 2026-08-01 | 2026-08-01 | 2026-09-12 23:59 | 2026-09-13 | 2026-09-12 23:59 | New Burn WL | JDukas | 2025-08-27 16:29 | MElsanousi |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 6 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 2 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1039672 | O.1039672.01 | A.1039672.01.05 | Strike Perth basin Well 5 | STRIKE ENERGY LIMITED |  | ENSIGN 974 | J.23.018098 | RPE | ES-OH-Ops | High | Unconfirmed - 50% | Design - CEC |  | In Progress | Not Started | In Progress | 2026-05-31 | 2026-05-31 | 2026-05-31 | 2026-05-31 | 2026-07-12 23:59 | 2026-07-13 | 2026-07-12 23:59 | New Burn WL | JDukas | 2025-08-27 16:29 | MElsanousi |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 6 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 2 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1039672 | O.1039672.01 | A.1039672.01.01 | Strike Perth basin Well 1 | STRIKE ENERGY LIMITED |  | ENSIGN 974 | J.23.018088 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-01 | 2023-09-01 |  | 2023-09-01 | 2023-10-13 23:59 |  | 2023-10-13 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 7 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1039672 | O.1039672.01 | A.1039672.01.03 | Strike Perth basin Well 3 | STRIKE ENERGY LIMITED |  | ENSIGN 974 | J.23.018096 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-10-23 | 2024-10-23 |  | 2024-10-23 | 2024-12-04 23:59 |  | 2024-12-04 23:59 | New Burn WL | JDukas | 2023-11-14 17:51 | JDukas |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 6 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1039672 | O.1039672.01 | A.1039672.01.02 | Strike Perth basin Well 2 | STRIKE ENERGY LIMITED |  | ENSIGN 974 | J.23.018095 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-08-23 | 2024-08-23 | 2024-08-23 | 2024-08-23 | 2024-10-04 23:59 | 2024-10-05 | 2024-10-04 23:59 | New Burn WL | JDukas | 2023-09-20 12:42 | JDukas |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 6 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1039562 | O.1039562.01 | A.1039562.01.01 | WL-ES Julimar South-1 | WOODSIDE ENERGY JULIMAR PTY LTD |  | OCEAN APEX | J.23.017776 | RPE | ES-OH-Ops | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-04 | 2023-10-10 |  | 2023-10-20 | 2023-11-01 23:59 |  | 2023-11-01 23:59 | New Burn WL | VOliveira5 | 2024-08-21 13:52 | FDPSystemUser |  | Yes |  |  |  | ROE WL Mumbai | Jarrod Sedmak |  | 0 | 4 |  | L1 - Support RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1039562 | O.1039562.01 | A.1039562.01.02 | WL-ES Gemtree | WOODSIDE ENERGY JULIMAR PTY LTD | GEMTREE-01 | OCEAN APEX | J.23.038719 | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-09-06 | 2023-09-16 |  | 2023-09-17 | 2023-09-29 23:59 |  | 2023-09-29 23:59 | New Burn WL | APutri | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jarrod Sedmak |  | 1237144.84 | 5 |  | L1 - Support RO |  | 100 | 100 | 100 | 50 | 85 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1039474 | O.1039474.01 | A.1039474.01.01 | 1st Well | LOCHARD ENERGY (IONA OPERATIONS) TRUST |  | EASTERNWELL 17 | J.23.016533 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2023-03-01 | 2023-02-26 |  | 2023-03-01 | 2023-03-25 23:59 |  | 2023-03-25 23:59 | Roma WL | MRony2 | 2023-02-03 14:40 | MRony2 |  | No |  |  |  |  | Jon Lawrie |  | 0 | 8 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1039473 | O.1039473.01 | A.1039473.01.04 | Santos NSW Dedicated September | SANTOS LIMITED | BIBBLEWINDI 15, BIBBLEWINDI 6, BOHENA SOUTH 1, BOHENA 7, DEWHURST 9 | EASTERNWELL 24 | J.23.087872 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-09-01 | 2023-09-01 02:00 | 2023-09-01 | 2023-09-01 02:00 | 2023-09-26 01:59 | 2023-10-01 | 2023-09-26 01:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 6433.4 | 27 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1039473 | O.1039473.01 | A.1039473.01.12 | Santos NSW Dedicated August | SANTOS LIMITED | TINTSFIELD 5, TINTSFIELD 6, TINTSFIELD 7 | EASTERNWELL 24 | J.23.087892 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-08-20 | 2023-07-25 02:00 | 2023-08-01 | 2023-08-20 02:00 | 2023-09-14 01:59 | 2023-08-26 | 2023-09-13 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 6765.3 | 60 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1039473 | O.1039473.01 | A.1039473.01.13 | Santos NSW Dedicated October | SANTOS LIMITED | BOHENA 7, COONARAH 4, BRAWBOY 2, BOHENA 3, KAHLUA 2, KAHLUA 5, KAHLUA 3, KAHLUA 4 | EASTERNWELL 24 | J.23.128169 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-10-01 01:00 | 2023-09-24 02:00 | 2023-09-30 14:00 | 2023-10-01 03:00 | 2023-12-05 01:59 | 2023-12-06 | 2023-12-05 01:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 16 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1039473 | O.1039473.01 | A.1039473.01.14 | Santos NSW Dedicated November | SANTOS LIMITED | BOHENA 3, KAHLUA 2, KAHLUA 3, KAHLUA 4, KAHLUA 5 | EASTERNWELL 24 | J.23.157949 | RPI | PS-WL-Ops | InComplete | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-11-06 23:00 | 2023-11-05 03:00 |  | 2023-11-07 | 2023-11-21 01:59 |  | 2023-12-01 22:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 18 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1039473 | O.1039473.01 | A.1039473.01.02 | Mar, 23 | SANTOS LIMITED |  | EASTERNWELL 24 | J.23.016524 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-08-01 | 2023-07-25 02:00 | 2023-08-01 | 2023-08-01 02:00 | 2023-08-26 01:59 | 2023-08-26 | 2023-08-25 23:59 | Roma WL | MRony2 | 2023-07-31 08:12 | KKeese |  | No |  |  |  |  | Jon Lawrie |  | 0 | 16 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1039473 | O.1039473.01 | A.1039473.01.03 | June | SANTOS LIMITED |  | EASTERNWELL 24 | J.23.045046 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-01 | 2023-05-25 02:00 |  | 2023-06-01 02:00 | 2023-06-26 01:59 |  | 2023-06-25 23:59 | Roma WL | MRony2 | 2023-05-22 10:35 | KKeese |  | No |  |  |  |  | Jon Lawrie |  | 0 | 16 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1039473 | O.1039473.01 | A.1039473.01.06 | Santos NSW Dedicated Sep | SANTOS LIMITED |  | EASTERNWELL 24 | J.23.087873 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-01 | 2023-08-25 02:00 |  | 2023-09-01 02:00 | 2023-09-26 01:59 |  | 2023-09-25 23:59 | Roma WL | KKeese | 2023-05-21 18:24 | KKeese |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 16 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1039473 | O.1039473.01 | A.1039473.01.01 | Feb, 23 | SANTOS LIMITED |  | EASTERNWELL 24 | J.23.016521 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2023-04-01 | 2023-03-25 |  | 2023-04-01 | 2023-04-25 23:59 |  | 2023-04-25 23:59 | Roma WL | MRony2 | 2023-02-03 14:40 | MRony2 |  | No |  |  |  |  | Jon Lawrie |  | 0 | 16 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1039257 | O.1039257.04 | A.1039257.04.04 | Equipment & Personnel | AGI TUBRIDGI PTY LIMITED | Well #1 | ATLAS DRLG 2 | J.23.013775 | WCF | PRI-COND, CMT-DSL | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-10-13 23:59 | 2023-10-14 | 2023-10-13 23:59 | AUS East Coast WS | ALyons | 2023-07-14 11:03 | HNarainasamy |  | No |  |  |  |  | Ariel Lyons |  | 0 | 0 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1039257 | O.1039257.04 | A.1039257.04.03 | Production | AGI TUBRIDGI PTY LIMITED | TCW-11 | ATLAS DRLG 2 | J.23.013773 | WCF | PRI-LONG | Low | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2023-10-07 23:00 |  | 2023-10-10 | 2023-10-12 23:59 |  |  | AUS East Coast WS | ALyons | 2023-07-14 11:03 | HNarainasamy |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1039257 | O.1039257.04 | A.1039257.04.02 | Surface | AGI TUBRIDGI PTY LIMITED | TCW-11 | ATLAS DRLG 2 | J.23.013774 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2023-09-29 |  | 2023-10-01 | 2023-10-03 23:59 |  |  | AUS East Coast WS | ALyons | 2023-07-14 11:03 | HNarainasamy |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1039257 | O.1039257.04 | A.1039257.04.01 | Conductor | AGI TUBRIDGI PTY LIMITED | TCW-11 | ATLAS DRLG 2 | J.23.019968 | WCF | PRI-COND | Low | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2023-09-26 |  | 2023-09-28 | 2023-09-30 23:59 |  |  | AUS East Coast WS | ALyons | 2023-07-14 11:03 | HNarainasamy |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1039257 | O.1039257.03 | A.1039257.03.04 | Equipment & Personnel | AGI TUBRIDGI PTY LIMITED | Well #1 | ATLAS DRLG 2 | J.23.019969 | WCF | PRI-COND, CMT-DSL | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-07 | 2023-09-07 | 2023-09-07 | 2023-09-07 | 2023-09-24 23:59 | 2023-09-25 | 2023-09-24 23:59 | AUS East Coast WS | ALyons | 2023-07-14 11:03 | HNarainasamy |  | No |  |  |  |  | Ariel Lyons |  | 0 | 0 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1039257 | O.1039257.03 | A.1039257.03.03 | Production | AGI TUBRIDGI PTY LIMITED | TRW-8 | ATLAS DRLG 2 | J.23.013772 | WCF | PRI-LONG | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-09-21 | 2023-09-19 | 2023-09-21 | 2023-09-21 | 2023-09-23 23:59 | 2023-09-24 | 2023-09-23 23:59 | AUS East Coast WS | ALyons | 2023-07-14 11:03 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 56.3 | 0 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1039257 | O.1039257.03 | A.1039257.03.02 | Surface | AGI TUBRIDGI PTY LIMITED | TRW-8 | ATLAS DRLG 2 | J.23.013770 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-09-12 | 2023-09-10 | 2023-09-12 | 2023-09-12 | 2023-09-14 23:59 | 2023-09-15 | 2023-09-14 23:59 | AUS East Coast WS | ALyons | 2023-07-14 11:03 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 56.3 | 0 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1039257 | O.1039257.03 | A.1039257.03.01 | Conductor | AGI TUBRIDGI PTY LIMITED | TRW-8 | ATLAS DRLG 2 | J.23.013769 | WCF | PRI-COND | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-09-09 | 2023-09-07 | 2023-09-09 | 2023-09-09 | 2023-09-11 23:59 | 2023-09-12 | 2023-09-11 23:59 | AUS East Coast WS | ALyons | 2023-07-14 11:03 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 56.3 | 0 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1039257 | O.1039257.02 | A.1039257.02.04 | Equipment & Personnel | AGI TUBRIDGI PTY LIMITED | TRW-2 | ATLAS DRLG 2 | J.23.013768 | WCF | PRI-COND, CMT-DSL | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-20 | 2023-08-20 | 2023-08-20 | 2023-08-20 | 2023-09-06 23:59 | 2023-09-07 | 2023-09-06 23:59 | AUS East Coast WS | ALyons | 2023-07-14 11:03 | HNarainasamy |  | No |  |  |  |  | Ariel Lyons |  | 0 | 0 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1039257 | O.1039257.02 | A.1039257.02.03 | Production | AGI TUBRIDGI PTY LIMITED | TRW-2 | ATLAS DRLG 2 | J.23.013767 | WCF | PRI-LONG | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-09-03 | 2023-09-01 | 2023-09-03 | 2023-09-03 | 2023-09-05 23:59 | 2023-09-06 | 2023-09-05 23:59 | AUS East Coast WS | ALyons | 2023-07-14 11:03 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 56.3 | 0 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1039257 | O.1039257.02 | A.1039257.02.02 | Surface | AGI TUBRIDGI PTY LIMITED | TRW-2 | ATLAS DRLG 2 | J.23.013765 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-08-25 | 2023-08-23 | 2023-08-25 | 2023-08-25 | 2023-08-27 23:59 | 2023-08-28 | 2023-08-27 23:59 | AUS East Coast WS | ALyons | 2023-07-14 11:03 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 56.3 | 0 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1039257 | O.1039257.02 | A.1039257.02.01 | Conductor | AGI TUBRIDGI PTY LIMITED | TRW-2 | ATLAS DRLG 2 | J.23.013766 | WCF | PRI-COND | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-08-22 | 2023-08-20 | 2023-08-22 | 2023-08-22 | 2023-08-24 23:59 | 2023-08-25 | 2023-08-24 23:59 | AUS East Coast WS | ALyons | 2023-07-14 11:03 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 56.3 | 0 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1039257 | O.1039257.01 | A.1039257.01.03 | Production | AGI TUBRIDGI PTY LIMITED | TRW-10 | ATLAS DRLG 2 | J.23.013681 | WCF | PRI-LONG | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-08-15 | 2023-08-13 | 2023-08-15 | 2023-08-15 | 2023-08-17 23:59 | 2023-08-18 | 2023-08-17 23:59 | AUS East Coast WS | ALyons | 2023-07-14 10:52 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 56.3 | 0 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1039257 | O.1039257.01 | A.1039257.01.02 | Surface | AGI TUBRIDGI PTY LIMITED | TRW-10 | ATLAS DRLG 2 | J.23.013680 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-08-06 | 2023-08-04 | 2023-08-06 | 2023-08-06 | 2023-08-08 23:59 | 2023-08-09 | 2023-08-08 23:59 | AUS East Coast WS | ALyons | 2023-07-14 10:52 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 56.3 | 0 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1039257 | O.1039257.01 | A.1039257.01.01 | Conductor | AGI TUBRIDGI PTY LIMITED | TRW-10 | ATLAS DRLG 2 | J.23.013678 | WCF | PRI-COND | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-08-03 | 2023-08-01 | 2023-08-03 | 2023-08-03 | 2023-08-05 23:59 | 2023-08-06 | 2023-08-05 23:59 | AUS East Coast WS | ALyons | 2023-07-14 10:52 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 56.3 | 0 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1039257 | O.1039257.01 | A.1039257.01.04 | Equipment & Personnel | AGI TUBRIDGI PTY LIMITED | TRW-10 | ATLAS DRLG 2 | J.23.013682 | WCF | PRI-COND, CMT-DSL | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-08-01 | 2023-08-01 | 2023-08-01 | 2023-08-01 | 2023-08-18 23:59 | 2023-08-19 | 2023-08-18 23:59 | AUS East Coast WS | ALyons | 2023-07-11 10:54 | SJha3 |  | No |  |  |  |  | Ariel Lyons |  | 0 | 0 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1039135 | O.1039135.01 | A.1039135.01.01 | RPI-WIS X11 | MINISTRY OF BUSINESS, INNOVATION AND EMPLOYMENT | TUI 02H | HELIX Q7000 | J.23.012681 | WCF | CMT-TOOLS | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2023-03-01 |  | 2023-03-15 | 2023-04-30 23:59 |  |  | New Plymouth WS | OMosleh | 2023-06-23 11:23 | HFerdjallah |  | Yes |  |  |  |  | Feras Manja |  | 0 | 0 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Integrity
P.1039134 | O.1039134.01 | A.1039134.01.01 | PATEKE-3H | WELL OPS (UK) LTD | PATEKE 03H | HELIX Q7000 | J.23.012682 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-08-01 05:00 | 2023-07-18 19:00 |  | 2023-08-01 | 2023-11-30 23:59 |  | 2023-12-01 04:59 | New Plymouth WL | OMosleh | 2024-08-21 17:52 | FDPSystemUser |  | No |  |  |  |  | Ayssar Alsayed |  | 0 | 4 |  | L0 - No RO |  | 91.7 | 66.7 | 100 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1039134 | O.1039134.01 | A.1039134.01.04 | AMOKURA-2H | WELL OPS (UK) LTD | AMOKURA 2H | HELIX Q7000 | J.23.021215 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-06-25 07:00 | 2023-06-07 23:00 |  | 2023-06-25 06:00 | 2023-07-15 05:59 |  | 2023-07-15 06:59 | New Plymouth WL | CKok3 | 2024-08-21 17:52 | FDPSystemUser |  | No |  |  |  |  | Ayssar Alsayed |  | 0 | 3 |  | L0 - No RO |  | 83.3 | 100 | 100 | 75 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1039134 | O.1039134.01 | A.1039134.01.02 | PATEKE-4H | WELL OPS (UK) LTD | PATEKE 04H | HELIX Q7000 | J.23.021213 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-18 07:00 | 2023-07-06 23:00 |  | 2023-07-18 06:00 | 2023-07-29 05:59 |  | 2023-08-19 | New Plymouth WL | CKok3 | 2024-08-21 17:52 | FDPSystemUser |  | No |  |  |  |  | Ayssar Alsayed |  | 0 | 2 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 75 | 75 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1039134 | O.1039134.01 | A.1039134.01.03 | TUI-2H | WELL OPS (UK) LTD | TUI 02H, TUI 03H | HELIX Q7000 | J.23.021214 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-31 01:00 | 2023-05-15 |  | 2023-05-31 | 2023-08-25 23:59 |  | 2023-08-26 00:59 | New Plymouth WL | CKok3 | 2024-08-21 17:52 | FDPSystemUser |  | No |  |  |  |  | Ayssar Alsayed |  | 0 | 2 |  | L0 - No RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1039134 | O.1039134.01 | A.1039134.01.05 | SLK Helix | WELL OPS (UK) LTD | AMOKURA 2H, PATEKE 03H, PATEKE 04H, TUI 02H | HELIX Q7000 | J.23.057828 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-26 01:00 | 2023-05-18 23:00 |  | 2023-05-26 | 2023-07-26 23:59 |  | 2023-07-27 00:59 | New Plymouth WL | OMosleh | 2024-08-21 17:52 | FDPSystemUser |  | No |  |  |  |  | Ayssar Alsayed |  | 0 | 1 |  | L0 - No RO |  | 58.3 | 50 | 0 | 0 | 32.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1039134 | O.1039134.01 | A.1039134.01.06 | CETT Logging | WELL OPS (UK) LTD | PATEKE 03H | HELIX Q7000 | J.23.136592 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-09-16 | 2023-09-13 |  | 2023-09-16 | 2023-09-18 23:59 |  | 2023-09-18 23:59 | New Plymouth WL | CKok3 | 2024-08-21 17:52 | FDPSystemUser |  | Yes |  |  |  |  | Cheryl Kok |  | 0 | 1 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1039133 | O.1039133.02 | A.1039133.02.04 | TCP NR-3 | ENERGY RESOURCES LIMITED |  | ENSIGN 970 | J.24.034710 | RPI | TCP-PERM-JOB | Medium | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2025-01-01 | 2025-07-14 16:00 | 2025-07-15 | 2025-07-25 23:59 | 2025-07-26 |  | APG TS | EKondratiev | 2025-05-22 11:35 | MWaseem2 |  | No |  |  |  |  | Evgeniy Kondratiev |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 2 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1039133 | O.1039133.02 | A.1039133.02.02 | Moriary-2 | ENERGY RESOURCES LIMITED | MORIARY-2 | ENSIGN 970 | J.23.019188 | RPI | TCP-PERM-JOB | Medium | Unconfirmed - 50% | Design - CEC |  | Not Required | Design Completed | Design Completed |  | 2023-06-01 |  | 2024-12-20 | 2025-01-25 23:59 |  |  | APG TS | RWallis | 2025-01-18 13:12 | DNyamache |  | No |  |  |  |  | Evgeniy Kondratiev |  | 61669.92 | 1 |  |  |  | 100 | 100 | 100 | 62.5 | 88.8 |  | 1 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1039133 | O.1039133.02 | A.1039133.02.03 | Lokyer-4 | ENERGY RESOURCES LIMITED |  | ENSIGN 970 | J.24.034709 | RPI | TCP-PERM-JOB | Medium | Unconfirmed - 50% | Design - CEC |  | Not Started | Not Started | In Progress |  | 2024-06-01 |  | 2024-10-01 | 2024-10-21 23:59 |  |  | APG TS | EKondratiev | 2024-07-19 09:09 | EKondratiev |  | No |  | [AUSG-TCP] - |  |  | Evgeniy Kondratiev |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 1 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1039133 | O.1039133.02 | A.1039133.02.05 | Product sale | ENERGY RESOURCES LIMITED |  | ENSIGN 970 | J.24.082568 | RPI | TCP-NO-OP | Medium | Unconfirmed - 10% | Design - CEC |  | Not Started | Not Started | Not Started |  | 2024-10-01 |  | 2024-10-01 | 2024-10-31 23:59 |  |  | APG TS | EKondratiev | 2024-07-19 09:09 | EKondratiev |  | No |  |  |  |  | Evgeniy Kondratiev |  | 0 | 1 |  |  |  | 33.3 | 33.3 | 100 | 50 | 45 |  | 1 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1039133 | O.1039133.02 | A.1039133.02.01 | Lockyer-5 | ENERGY RESOURCES LIMITED | LOCKYER-5 | ENSIGN 970 | J.23.019187 | RPI | TCP-PERM-JOB | Medium | Operationally Complete | Close - PSD |  | Not Required | Design Completed | Design Completed |  | 2023-02-28 | 2024-03-03 16:00 | 2024-03-04 | 2024-04-01 23:59 | 2024-04-02 |  | APG TS | RWallis | 2024-04-04 14:26 | EKondratiev |  | No |  |  |  |  | Evgeniy Kondratiev |  | 61481.96 | 1 |  |  |  | 91.7 | 83.3 | 100 | 100 | 92.5 |  | 0 |  | Working | D2812024722¦R01 | 0 |  |  |  | Wayne Wallis | TCP - Tubing-Conveyed Perforation
P.1039133 | O.1039133.01 | A.1039133.01.01 | NED-1 | ENERGY RESOURCES LIMITED | NORTH ERREGULLA DEEP-1 | ENSIGN 970 | J.23.012676 | RPI | TCP-PERM-JOB | Medium | Operationally Complete | Close - PSD |  | Not Required | Design Completed | Design Completed |  | 2023-04-01 |  | 2023-06-09 | 2023-07-27 23:59 |  |  | APG TS | RWallis | 2024-03-02 13:32 | EKondratiev |  | No |  |  |  |  | Evgeniy Kondratiev |  | 125979.03 | 1 |  |  |  | 91.7 | 66.7 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TCP - Tubing-Conveyed Perforation
P.1039131 | O.1039131.01 | A.1039131.01.01 | Beach Land OH - Rental and Reimbursables | BEACH ENERGY LTD |  | VENTIA 106 | J.23.012669 | RPE | ES-OH-NO | Medium | Confirmed | Design - PSD |  | Design Completed | Not Required | Design Completed | 2023-01-01 08:52 | 2023-01-01 |  | 2023-01-01 08:52 | 2023-12-31 08:52 |  | 2024-05-31 08:52 | New Burn WL | VOliveira5 | 2024-08-21 13:52 | FDPSystemUser |  | Yes |  |  |  |  | Justin Dukas |  | 0 | 6 |  | L0 - No RO |  | 75 | 33.3 | 100 | 50 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1039131 | O.1039131.01 | A.1039131.01.02 | BEL ¦ Trigg 1 ¦ Easternwell 106 ¦ HT OH | BEACH ENERGY LTD | TRIGG 1 | VENTIA 106 | J.23.038838 | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-25 | 2023-05-07 |  | 2023-06-08 | 2023-07-09 23:59 |  | 2023-07-09 23:59 | New Burn WL | EBrobbey | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 345307.99 | 4 |  | L1 - Support RO |  | 91.7 | 100 | 50 | 75 | 85 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1039131 | O.1039131.01 | A.1039131.01.03 | BEL ¦ Tarantula Deep 1 (TD 1) ¦ Easternwell 106 ¦ HPHT OH | BEACH ENERGY LTD |  | VENTIA 106 | J.23.053786 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2023-07-01 |  | 2023-07-15 | 2023-09-15 23:59 |  |  | New Burn WL | EBrobbey | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 0 |  | L0 - No RO |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1039131 | O.1039131.01 | A.1039131.01.04 | Trigg-1 OH Logging | BEACH ENERGY LTD | TRIGG 1 | VENTIA 106 | J.23.072179 | RPE | ES-OH-NO | Low | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2023-08-31 |  | 2023-08-31 | 2023-09-30 23:59 |  |  | New Burn WL | miqbal13 | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 345307.99 | 0 |  | L2 - Shift RO |  | 41.7 | 33.3 | 100 | 50 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1039131 | O.1039131.01 | A.1039131.01.05 | Trigg NorthWest 1 | BEACH ENERGY LTD | TRIGG NORTHWEST 1 | VENTIA 106 | J.23.085234 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | Design Completed | 2023-07-21 | 2023-07-04 |  | 2023-08-05 | 2023-09-05 23:59 |  | 2023-09-05 23:59 | New Burn WL | VOliveira5 | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 885490.29 | 4 |  | L1 - Support RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1039131 | O.1039131.01 | A.1039131.01.08 | RedbackDeep1 | BEACH ENERGY LTD | REDBACK DEEP 1 | VENTIA 106 | J.23.085237 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-02-14 | 2024-02-02 |  | 2024-02-14 | 2024-04-06 23:59 |  | 2024-04-06 23:59 | New Burn WL | VOliveira5 | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Peter Roche |  | 315114.69 | 5 |  | L1 - Support RO |  | 100 | 100 | 100 | 100 | 100 |  | 3 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1039131 | O.1039131.01 | A.1039131.01.07 | BSD-2 | BEACH ENERGY LTD | BEHARRA SPRINGS DEEP 2 | VENTIA 106 | J.23.085236 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-01-19 | 2023-12-20 |  | 2024-01-22 | 2024-02-22 23:59 |  | 2024-02-22 23:59 | New Burn WL | VOliveira5 | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Peter Roche |  | 783084.28 | 5 |  | L1 - Support RO |  | 100 | 100 | 100 | 100 | 100 |  | 2 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1039131 | O.1039131.01 | A.1039131.01.06 | Tarantula Deep 1 | BEACH ENERGY LTD | TARANTULA DEEP | VENTIA 106 | J.23.085235 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-09-13 | 2023-09-01 |  | 2023-09-25 | 2023-10-26 23:59 |  | 2023-10-26 23:59 | New Burn WL | VOliveira5 | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 967680.96 | 5 |  | L1 - Support RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1039131 | O.1039131.01 | A.1039131.01.09 | MLC Dummy Activity | BEACH ENERGY LTD | TRIGG NORTHWEST 1 | VENTIA 106 | J.23.138592 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-19 18:00 | 2023-09-18 20:00 | 2023-09-19 | 2023-09-19 18:00 | 2023-09-22 22:00 | 2023-09-23 | 2023-09-22 22:00 | New Burn WL | miqbal13 | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L2 - Shift RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1038436 | O.1038436.01 | A.1038436.01.02 | 18-5-8_USIT-CBL_SS1 | TAMBORAN RESOURCES LIMITED | SHENANDOAH S-1 | RIGLESS - AUSTRALIA | J.23.010547 | RPE | ES-CH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-08-02 01:00 | 2023-08-01 02:00 |  | 2023-08-04 02:00 | 2023-08-17 01:59 |  | 2023-08-15 01:59 | Roma WL | MRony2 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Jakarta | Shameer Mumtaz Ali |  | 51535.41 | 1 |  | L3 - Full RO |  | 75 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1038436 | O.1038436.01 | A.1038436.01.03 | Tamboran CBL | TAMBORAN RESOURCES LIMITED |  | RIGLESS - AUSTRALIA | J.23.085247 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-12 01:00 | 2023-09-08 02:00 | 2023-09-12 01:00 | 2023-09-12 02:00 | 2023-09-27 01:59 | 2023-09-27 01:00 | 2023-09-27 00:59 | Roma WL | KKeese | 2023-09-26 09:19 | KKeese |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 20 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1038436 | O.1038436.01 | A.1038436.01.05 | Tamboran (20 Stages) | TAMBORAN RESOURCES LIMITED |  | RIGLESS - AUSTRALIA | J.23.087904 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-12 01:00 | 2023-11-08 02:00 | 2023-11-12 02:00 | 2023-11-12 02:00 | 2023-11-27 01:59 | 2023-11-27 02:00 | 2023-11-27 01:59 | Roma WL | KKeese | 2023-08-28 16:46 | KKeese |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 40 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1038436 | O.1038436.01 | A.1038436.01.04 | Tamboran USIT 18 5/8" Casing | TAMBORAN RESOURCES LIMITED |  | RIGLESS - AUSTRALIA | J.23.085248 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-11 02:00 | 2023-09-07 02:00 |  | 2023-09-11 02:00 | 2023-09-26 01:59 |  | 2023-09-26 01:59 | Roma WL | KKeese | 2023-05-21 18:32 | KKeese |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1038436 | O.1038436.01 | A.1038436.01.01 | 1st well | TAMBORAN RESOURCES LIMITED | AMUNGEE NW-2H | RIGLESS - AUSTRALIA | J.23.010546 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2023-02-13 | 2023-02-07 |  | 2023-02-13 | 2023-03-24 23:59 |  | 2023-03-24 23:59 | Roma WL | MRony2 | 2023-04-10 16:02 | MRony2 |  | Yes |  |  |  |  | Jon Lawrie |  | 826979.69 | 25 |  | L0 - No RO |  | 75 | 83.3 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1038114 | O.1038114.01 | A.1038114.01.01 | Hides-1 | EXXONMOBIL PNG LIMITED | HIDES D1 |  | J.22.116142 | RPI | TCP-SALE | InComplete | Operationally Complete | Close - PSD |  | Not Started | Design Completed | In Progress |  | 2022-10-09 |  | 2022-10-09 | 2022-12-31 23:59 |  |  | Port Moresby TS | RWallis | 2022-11-14 17:32 | RWallis |  | No |  |  |  |  | Yudha Swara |  | 171421.3 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TCP - Tubing-Conveyed Perforation
P.1038062 | O.1038062.05 | A.1038062.05.01 | Judga 3 TCP Job | SANTOS LIMITED |  | RIGLESS - AUSTRALIA | J.25.020412 | RPI | TCP-PERM-JOB | Medium | Unconfirmed - 50% | Design - CEC |  | Not Started | Not Started | In Progress |  | 2025-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-31 23:59 | 2026-02-01 |  | APG TS | EKondratiev | 2025-08-20 13:57 | AEl-wakil |  | No |  |  |  |  | Evgeniy Kondratiev |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 2 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1038062 | O.1038062.04 | A.1038062.04.01 | Gidgealpa 69 TCP | SANTOS LIMITED | GIDGEALPA 69 | RIGLESS - AUSTRALIA | J.24.054973 | RPI | TCP-PERM-JOB | Medium | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2024-02-20 | 2024-03-10 | 2024-03-10 | 2024-04-09 23:59 | 2024-04-10 |  | APG TS | EKondratiev | 2024-04-24 16:16 | EKondratiev |  | No |  |  |  |  | Evgeniy Kondratiev |  | 45782.98 | 1 |  |  |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  | Working | D2312024962¦R01 | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1038062 | O.1038062.03 | A.1038062.03.01 | Dorodilo 8 | SANTOS LIMITED | DORODILLO 8 | RIGLESS - AUSTRALIA | J.23.100809 | RPI | TCP-PERM-JOB | Medium | Confirmed | Execute - PSD |  | Not Required | Design Completed | In Progress |  | 2023-06-12 | 2023-06-14 | 2023-06-14 16:00 | 2023-06-18 15:59 | 2023-06-19 |  | APG TS | EKondratiev | 2023-07-13 17:28 | EKondratiev |  | No |  |  |  |  | Evgeniy Kondratiev |  | 26416.78 | 1 |  |  |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1038062 | O.1038062.02 | A.1038062.02.01 | East Cook TCP | SANTOS LIMITED | COOK EAST 1 | RIGLESS - AUSTRALIA | J.23.069685 | RPI | TCP-PERM-JOB | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-05-22 | 2023-04-10 | 2023-05-21 | 2023-05-22 | 2023-06-01 23:59 | 2023-06-02 | 2023-06-01 23:59 | APG TS | EKondratiev | 2023-06-30 12:19 | EKondratiev |  | No |  | [AUSG-TCP] - |  |  | Evgeniy Kondratiev |  | 63658.49 | 1 |  |  |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1038062 | O.1038062.01 | A.1038062.01.04 | 6th CCS well | SANTOS LIMITED |  | RIGLESS - AUSTRALIA | J.24.054972 | RPI | TCP-PERM-JOB | Medium | Unconfirmed - 90% | Design - CEC |  | Not Started | Not Started | In Progress |  | 2024-04-01 | 2026-01-15 | 2026-01-15 | 2026-02-14 23:59 | 2026-02-15 |  | APG TS | EKondratiev | 2025-03-28 09:08 | MWaseem2 |  | No |  |  |  |  | Evgeniy Kondratiev |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 2 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1038062 | O.1038062.01 | A.1038062.01.03 | TCP Strzelecki 37 | SANTOS LIMITED | STRZELECKI 37 | RIGLESS - AUSTRALIA | J.24.054971 | RPI | TCP-PERM-JOB | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2024-08-02 | 2024-05-01 |  | 2024-08-01 | 2024-08-21 23:59 |  | 2024-08-21 23:59 | APG TS | EKondratiev | 2024-08-29 08:47 | EKondratiev |  | No |  |  |  |  | Evgeniy Kondratiev |  | 59739.44 | 3 |  |  |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 1 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1038062 | O.1038062.01 | A.1038062.01.01 | CCS TCP Perforation | SANTOS LIMITED | MARABOOKA 19, STRZELECKI 34, STRZELECKI 35, STRZELECKI 36 | RIGLESS - AUSTRALIA | J.23.010198 | RPI | TCP-PERM-JOB | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-08-13 | 2023-03-01 |  | 2023-08-10 | 2023-09-21 23:59 |  | 2023-09-19 23:59 | APG TS | EKondratiev | 2024-03-02 14:38 | EKondratiev |  | No |  |  |  |  | Evgeniy Kondratiev |  | 140968.16 | 4 |  |  |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1038062 | O.1038062.01 | A.1038062.01.02 | CCS TCP Perforation | SANTOS LIMITED |  | RIGLESS - AUSTRALIA | J.23.010199 | RPI | TCP-PERM-JOB | Medium | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2023-02-01 |  | 2023-02-01 | 2023-07-01 23:59 |  |  | APG TS | EKondratiev | 2022-10-12 13:41 | EKondratiev |  | No |  |  |  |  | Evgeniy Kondratiev |  | 0 | 4 |  |  |  | 25 | 33.3 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TCP - Tubing-Conveyed Perforation
P.1037609 | O.1037609.01 | A.1037609.01.01 | BucketJobTestOpsActivity_segmentName_9 | SCHLUMBERGER IPM | BINGO 24-10TFH | NAM RIGLESS - FOR RIGLESS WORK | J.22.099550 | WCF | CMT-BONUS | Low | Confirmed | Design - PSD |  | Not Started | Not Started | In Progress |  | 2022-10-11 |  | 2022-10-12 00:01 | 2022-12-12 23:59 |  |  | AUS East Coast WS | FDPAutoTestUser | 2022-10-02 20:06 | VYadav13 |  | No |  |  |  |  | FDP AutomatedTest |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | FDP AutomatedTest | WS Well Integrity
P.1037602 | O.1037602.01 | A.1037602.01.01 | BucketJobTestOpsActivity_segmentName_3 | SCHLUMBERGER IPM | BINGO 24-10TFH | NAM RIGLESS - FOR RIGLESS WORK | J.22.099544 | WCF | CMT-BONUS | Low | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-10-11 |  | 2022-10-12 00:01 | 2022-12-12 23:59 |  |  | AUS East Coast WS | FDPAutoTestUser | 2023-07-20 23:45 | FDPTestUser4 |  | No |  |  |  |  | FDP AutomatedTest |  | 0 | 1 |  |  |  | 50 | 33.3 | 100 | 50 | 50 |  | 0 |  |  |  | 0 |  |  |  | FDP AutomatedTest | WS Well Integrity
P.1037585 | O.1037585.01 | A.1037585.01.01 | BucketJobTestOpsActivity_segmentName_1 | SCHLUMBERGER IPM | BINGO 24-10TFH | NAM RIGLESS - FOR RIGLESS WORK | J.22.099448 | WCF | CMT-BONUS | Low | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-10-11 |  | 2022-10-12 00:01 | 2022-12-12 23:59 |  |  | AUS East Coast WS | FDPAutoTestUser | 2023-07-20 23:35 | FDPTestUser4 |  | No |  |  |  |  | FDP AutomatedTest |  | 0 | 1 |  |  |  | 50 | 33.3 | 100 | 50 | 50 |  | 0 |  |  |  | 0 |  |  |  | FDP AutomatedTest | WS Well Integrity
P.1037431 | O.1037431.01 | A.1037431.01.01 | BucketJobTestOpsActivity_segmentName_4 | SCHLUMBERGER IPM | BINGO 24-10TFH | NAM RIGLESS - FOR RIGLESS WORK | J.22.098823 | RPE | ES-CH-NO | Low | Confirmed | Design - PSD |  | Not Started | Not Started | In Progress |  | 2022-11-09 |  | 2022-12-10 00:01 | 2023-04-10 23:59 |  |  | New Burn WL | FDPAutoTestUser | 2022-09-29 21:28 | VYadav13 |  | No |  |  |  | ROE WL Doha | FDP AutomatedTest |  | 0 | 0 |  | L3 - Full RO | [7 empty] | 0 |  |  |  | 0 |  |  |  | FDP AutomatedTest | WL Evaluation Services
P.1037398 | O.1037398.01 | A.1037398.01.01 | BucketJobTestOpsActivity_segmentName_0 | SCHLUMBERGER IPM | BINGO 24-10TFH | NAM RIGLESS - FOR RIGLESS WORK | J.22.098794 | RPI | PS-WL-NO | Low | Confirmed | Design - PSD |  | Not Started | Not Started | In Progress |  | 2022-11-09 |  | 2022-12-10 00:01 | 2023-04-10 23:59 |  |  | Port Moresby WL | FDPAutoTestUser | 2022-09-29 23:24 | VYadav13 |  | No |  |  |  | ROE WL Doha | FDP AutomatedTest |  | 0 | 0 |  | L3 - Full RO | [7 empty] | 0 |  |  |  | 0 |  |  |  | FDP AutomatedTest | WL Production Services
P.1037396 | O.1037396.01 | A.1037396.01.01 | BucketJobTestOpsActivity_segmentName_2 | SCHLUMBERGER IPM | BINGO 24-10TFH | NAM RIGLESS - FOR RIGLESS WORK | J.22.098793 | RPE | ES-CH-NO | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-11-09 |  | 2022-12-10 00:01 | 2023-04-10 23:59 |  |  | New Plymouth WL | FDPAutoTestUser | 2022-10-24 10:46 | CLorenzo |  | No |  |  |  | ROE WL Doha | FDP AutomatedTest |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | FDP AutomatedTest | WL Evaluation Services
P.1037395 | O.1037395.01 | A.1037395.01.01 | BucketJobTestOpsActivity_segmentName_1 | SCHLUMBERGER IPM | BINGO 24-10TFH | NAM RIGLESS - FOR RIGLESS WORK | J.22.098792 | RPI | PS-WL-NO | Low | Confirmed | Design - PSD |  | Not Started | Not Started | In Progress |  | 2022-11-09 |  | 2022-12-10 00:01 | 2023-03-31 23:59 |  |  | Moomba WL | FDPAutoTestUser | 2023-02-19 11:53 | KKeese |  | No |  |  |  | ROE WL Doha | FDP AutomatedTest |  | 0 | 0 |  | L3 - Full RO |  | 33.3 | 33.3 | 100 | 50 | 45 |  | 0 |  |  |  | 0 |  |  |  | FDP AutomatedTest | WL Production Services
P.1037394 | O.1037394.01 | A.1037394.01.01 | BucketJobTestOpsActivity_segmentName_0 | SCHLUMBERGER IPM | BINGO 24-10TFH | NAM RIGLESS - FOR RIGLESS WORK | J.22.098791 | RPI | TCP-SALE | Low | Confirmed | Design - PSD |  | Not Started | Not Started | In Progress |  | 2022-11-09 |  | 2022-12-10 00:01 | 2023-04-10 23:59 |  |  | APG TS | FDPAutoTestUser | 2022-09-29 21:24 | VYadav13 |  | No |  |  |  |  | FDP AutomatedTest |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | FDP AutomatedTest | TCP - Tubing-Conveyed Perforation
P.1037381 | O.1037381.01 | A.1037381.01.01 | BucketJobTestOpsActivity_segmentName_6 | SCHLUMBERGER IPM | BINGO 24-10TFH | NAM RIGLESS - FOR RIGLESS WORK | J.22.098790 | RPI | PS-WL-NO | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-11-09 |  | 2022-12-10 00:01 | 2023-04-10 23:59 |  |  | Roma WL | FDPAutoTestUser | 2022-10-28 15:51 | MRony2 |  | No |  |  |  | ROE WL Doha | FDP AutomatedTest |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | FDP AutomatedTest | WL Production Services
P.1037380 | O.1037380.01 | A.1037380.01.01 | BucketJobTestOpsActivity_segmentName_5 | SCHLUMBERGER IPM | BINGO 24-10TFH | NAM RIGLESS - FOR RIGLESS WORK | J.22.098789 | RPI | PS-WL-NO | Low | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-11-09 |  | 2022-12-10 00:01 | 2023-12-10 23:59 |  |  | New Burn WL | FDPAutoTestUser | 2024-06-20 00:35 | FDPAutoTestUser |  | No |  |  |  | ROE WL Doha | FDP AutomatedTest |  | 0 | 0 |  | L3 - Full RO |  | 33.3 | 33.3 | 100 | 50 | 45 |  | 0 |  |  |  | 0 |  |  |  | FDP AutomatedTest | WL Production Services
P.1037379 | O.1037379.01 | A.1037379.01.01 | BucketJobTestOpsActivity_segmentName_4 | SCHLUMBERGER IPM | BINGO 24-10TFH | NAM RIGLESS - FOR RIGLESS WORK | J.22.098788 | RPE | ES-CH-NO | Low | Confirmed | Design - PSD |  | Not Started | Not Started | In Progress |  | 2022-11-09 |  | 2022-12-10 00:01 | 2023-03-31 23:59 |  |  | Moomba WL | FDPAutoTestUser | 2023-02-19 11:54 | KKeese |  | No |  |  |  | ROE WL Doha | FDP AutomatedTest |  | 0 | 0 |  | L3 - Full RO |  | 33.3 | 33.3 | 100 | 50 | 45 |  | 0 |  |  |  | 0 |  |  |  | FDP AutomatedTest | WL Evaluation Services
P.1037378 | O.1037378.01 | A.1037378.01.01 | BucketJobTestOpsActivity_segmentName_3 | SCHLUMBERGER IPM | BINGO 24-10TFH | NAM RIGLESS - FOR RIGLESS WORK | J.22.098787 | RPE | ES-CH-NO | Low | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-11-09 |  | 2022-12-10 00:01 | 2023-04-10 23:59 |  |  | New Burn WL | FDPAutoTestUser | 2023-07-21 06:57 | PMohapatra3 |  | No |  |  |  | ROE WL Doha | FDP AutomatedTest |  | 0 | 0 |  | L3 - Full RO |  | 33.3 | 33.3 | 100 | 50 | 45 |  | 0 |  |  |  | 0 |  |  |  | FDP AutomatedTest | WL Evaluation Services
P.1037376 | O.1037376.01 | A.1037376.01.01 | BucketJobTestOpsActivity_segmentName_1 | SCHLUMBERGER IPM | BINGO 24-10TFH | NAM RIGLESS - FOR RIGLESS WORK | J.22.098786 | RPE | ES-CH-NO | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-11-09 |  | 2022-12-10 00:01 | 2023-04-10 23:59 |  |  | Roma WL | FDPAutoTestUser | 2022-10-28 15:50 | MRony2 |  | No |  |  |  | ROE WL Doha | FDP AutomatedTest |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | FDP AutomatedTest | WL Evaluation Services
P.1037375 | O.1037375.01 | A.1037375.01.01 | BucketJobTestOpsActivity_segmentName_0 | SCHLUMBERGER IPM | BINGO 24-10TFH | NAM RIGLESS - FOR RIGLESS WORK | J.22.098785 | RPE | DDA-STB | Medium | Confirmed | Design - PSD |  | Not Started | Not Started | In Progress |  | 2022-11-09 |  | 2022-12-10 00:01 | 2023-04-10 23:59 |  |  | APG TS | FDPAutoTestUser | 2022-09-29 21:23 | VYadav13 |  | No |  |  |  |  | FDP AutomatedTest |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | FDP AutomatedTest | TS Downhole Reservoir Testing
P.1037332 | O.1037332.01 | A.1037332.01.01 | BucketJobTestOpsActivity_segmentName_5 | SCHLUMBERGER IPM | BINGO 24-10TFH | NAM RIGLESS - FOR RIGLESS WORK | J.22.098759 | RPS | FRAC-ACID | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-11-08 |  | 2022-12-09 00:01 | 2023-04-09 23:59 |  |  | AUS East Coast WS | FDPAutoTestUser | 2023-02-28 15:38 | HFerdjallah |  | No |  |  |  |  | FDP AutomatedTest |  | 0 | 1 |  |  |  | 12.5 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | FDP AutomatedTest | WS Production Services
P.1037331 | O.1037331.01 | A.1037331.01.01 | BucketJobTestOpsActivity_segmentName_4 | SCHLUMBERGER IPM | BINGO 24-10TFH | NAM RIGLESS - FOR RIGLESS WORK | J.22.098758 | WCF | CMT-BONUS | Low | Confirmed | Design - PSD |  | Not Started | Not Started | In Progress |  | 2022-11-08 |  | 2022-12-09 00:01 | 2023-04-09 23:59 |  |  | AUS West Coast WS | FDPAutoTestUser | 2022-09-29 23:19 | VYadav13 |  | No |  |  |  |  | FDP AutomatedTest |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | FDP AutomatedTest | WS Well Integrity
P.1037330 | O.1037330.01 | A.1037330.01.01 | BucketJobTestOpsActivity_segmentName_3 | SCHLUMBERGER IPM | BINGO 24-10TFH | NAM RIGLESS - FOR RIGLESS WORK | J.22.098757 | WCF | CMT-BONUS | Low | Confirmed | Design - PSD |  | Not Started | Not Started | In Progress |  | 2022-11-08 |  | 2022-12-09 00:01 | 2023-04-09 23:59 |  |  | AUS West Coast WS | FDPAutoTestUser | 2022-09-29 23:19 | VYadav13 |  | No |  |  |  |  | FDP AutomatedTest |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | FDP AutomatedTest | WS Well Integrity
P.1037329 | O.1037329.01 | A.1037329.01.01 | BucketJobTestOpsActivity_segmentName_2 | SCHLUMBERGER IPM | BINGO 24-10TFH | NAM RIGLESS - FOR RIGLESS WORK | J.22.098753 | WCF | CMT-BONUS | Low | Confirmed | Design - PSD |  | Not Started | Not Started | In Progress |  | 2022-11-08 |  | 2022-12-09 00:01 | 2023-04-09 23:59 |  |  | AUS West Coast WS | FDPAutoTestUser | 2022-09-29 23:19 | VYadav13 |  | No |  |  |  |  | FDP AutomatedTest |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | FDP AutomatedTest | WS Well Integrity
P.1037323 | O.1037323.01 | A.1037323.01.01 | BucketJobTestOpsActivity_segmentName_0 | SCHLUMBERGER IPM | BINGO 24-10TFH | NAM RIGLESS - FOR RIGLESS WORK | J.22.098748 | RPS | FRAC-ACID | Low | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-11-08 |  | 2022-12-09 00:01 | 2023-04-09 23:59 |  |  | AUS East Coast WS | FDPAutoTestUser | 2023-11-17 01:45 | FDPTestUser4 |  | No |  |  |  |  | FDP AutomatedTest |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | FDP AutomatedTest | WS Production Services
P.1037279 | O.1037279.01 | A.1037279.01.01 | AGIG Tubridgi TRW-10 | AGI TUBRIDGI PTY LIMITED | TRW 10 | RIGLESS - AUSTRALIA | J.23.133237 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-09-15 | 2023-09-01 |  | 2023-10-09 | 2023-10-20 23:59 |  | 2023-10-20 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jarrod Sedmak |  | 109746.59 | 4 |  | L3 - Full RO |  | 91.7 | 66.7 | 100 | 100 | 87.5 |  | 2 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1037279 | O.1037279.01 | A.1037279.01.02 | AGIG Tubridgi TRW-02 | AGI TUBRIDGI PTY LIMITED | TRW 2 | RIGLESS - AUSTRALIA | J.23.160973 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-11-07 | 2023-11-06 |  | 2023-11-07 | 2023-11-21 23:59 |  | 2023-11-21 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jarrod Sedmak |  | 109746.59 | 4 |  | L2 - Shift RO |  | 91.7 | 66.7 | 100 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1037279 | O.1037279.01 | A.1037279.01.03 | AGIG Tubridgi TRW-08 | AGI TUBRIDGI PTY LIMITED | TRW 8 | RIGLESS - AUSTRALIA | J.23.170786 | RPE | ES-OH-Ops | Medium | Confirmed | Design - PSD |  | Design Completed | Design Completed | In Progress | 2023-12-14 | 2023-11-29 |  | 2023-12-14 | 2023-12-28 23:59 |  | 2023-12-28 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jarrod Sedmak |  | 109746.59 | 4 |  | L2 - Shift RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1037279 | O.1037279.01 | A.1037279.01.07 | AGIG - Demonstration Only | AGI TUBRIDGI PTY LIMITED | Well #1 | RIGLESS - AUSTRALIA | J.23.138871 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | In Progress | In Progress | 2024-01-15 | 2024-01-13 |  | 2024-01-15 | 2024-01-29 23:59 |  | 2024-01-29 23:59 | New Burn WL | VOliveira5 | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 0 | 1 |  | L2 - Shift RO |  | 50 | 0 | 0 | 0 | 15 |  | 2 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1037279 | O.1037279.01 | A.1037279.01.05 | AGIG - EnA | AGI TUBRIDGI PTY LIMITED | Well #1 | RIGLESS - AUSTRALIA | J.23.138870 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-06 | 2023-10-31 |  | 2023-11-06 | 2023-11-20 23:59 |  | 2023-11-20 23:59 | New Burn WL | VOliveira5 | 2023-11-02 14:31 | VOliveira5 |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 0 | 6 |  | L2 - Shift RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 3 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1037279 | O.1037279.01 | A.1037279.01.06 | AGIG | AGI TUBRIDGI PTY LIMITED | Well #1 | RIGLESS - AUSTRALIA | J.23.138872 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2023-12-05 | 2023-11-29 | 2023-12-05 | 2023-12-05 | 2023-12-19 23:59 | 2023-12-20 | 2023-12-19 23:59 | New Burn WL | VOliveira5 | 2023-10-09 09:53 | VOliveira5 |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 0 | 6 |  | L2 - Shift RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 2 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1037279 | O.1037279.01 | A.1037279.01.08 | AGIG EnA | AGI TUBRIDGI PTY LIMITED | Well #1 | RIGLESS - AUSTRALIA |  | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-01 | 2023-08-26 |  | 2023-09-01 | 2023-09-15 23:59 |  | 2023-09-15 23:59 | New Burn WL | VOliveira5 | 2023-02-02 11:08 | JDukas |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 0 | 6 |  | L2 - Shift RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1037279 | O.1037279.01 | A.1037279.01.04 | AGIG 4 | AGI TUBRIDGI PTY LIMITED | Well #1 | RIGLESS - AUSTRALIA |  | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-07-30 | 2023-07-24 |  | 2023-07-30 | 2023-08-13 23:59 |  | 2023-08-13 23:59 | New Burn WL | JDukas | 2023-01-30 13:47 | VOliveira5 |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 0 | 6 |  | L2 - Shift RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1037048 | O.1037048.02 | A.1037048.02.11 | Hovea-8_P&A_Plug#1 | AWE PERTH PTY LTD | HOVEA-08 | EASTERNWELL 106 | J.23.024117 | WCF | REM-PA | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-25 09:00 | 2023-02-24 12:00 |  | 2023-02-25 09:00 | 2023-03-01 21:00 |  | 2023-03-01 21:00 | AUS East Coast WS | HNarainasamy | 2023-03-28 12:12 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 10491.46 | 1 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037048 | O.1037048.02 | A.1037048.02.12 | Hovea-8_P&A_Plug#2 | AWE PERTH PTY LTD | GYNATRIX 1 | EASTERNWELL 106 | J.23.024622 | WCF | REM-PA | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-02 09:00 | 2023-03-01 12:00 |  | 2023-03-02 09:00 | 2023-03-02 21:00 |  | 2023-03-02 21:00 | AUS East Coast WS | HNarainasamy | 2023-03-10 01:38 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037048 | O.1037048.02 | A.1037048.02.13 | Hovea-8_P&A_Plug#3 | AWE PERTH PTY LTD | GYNATRIX 1 | EASTERNWELL 106 | J.23.024623 | WCF | REM-PA | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-03 09:00 | 2023-03-02 12:00 |  | 2023-03-03 09:00 | 2023-03-03 21:00 |  | 2023-03-03 21:00 | AUS East Coast WS | HNarainasamy | 2023-02-28 14:21 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037048 | O.1037048.02 | A.1037048.02.15 | Hovea-8_P&A_Plug#5 | AWE PERTH PTY LTD | GYNATRIX 1 | EASTERNWELL 106 | J.23.024625 | WCF | REM-PA | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-07 09:00 | 2023-03-06 12:00 |  | 2023-03-07 09:00 | 2023-03-07 21:00 |  | 2023-03-07 21:00 | AUS East Coast WS | HNarainasamy | 2023-02-28 14:20 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037048 | O.1037048.02 | A.1037048.02.14 | Hovea-8_P&A_Plug#4 | AWE PERTH PTY LTD | GYNATRIX 1 | EASTERNWELL 106 | J.23.024624 | WCF | REM-PA | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-05 09:00 | 2023-03-04 12:00 |  | 2023-03-05 09:00 | 2023-03-05 21:00 |  | 2023-03-05 21:00 | AUS East Coast WS | HNarainasamy | 2023-02-28 14:19 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037048 | O.1037048.02 | A.1037048.02.08 | Gynatrix-1_7in Liner Cementing | AWE PERTH PTY LTD | GYNATRIX 1 | EASTERNWELL 106 | J.23.011918 | WCF | PRI-LIN, CMT-MATSAL | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-08 17:00 | 2023-01-08 06:00 |  | 2023-01-08 17:00 | 2023-01-09 17:00 |  | 2023-01-09 17:00 | AUS East Coast WS | HNarainasamy | 2023-01-12 12:43 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 48689.93 | 1 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037048 | O.1037048.02 | A.1037048.02.06 | Gynatrix-1_9-5/8in Intermediate Casing | AWE PERTH PTY LTD | GYNATRIX 1 | EASTERNWELL 106 | J.23.011916 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-08 | 2023-01-08 |  | 2023-01-08 | 2023-01-09 |  | 2023-01-09 | AUS East Coast WS | HNarainasamy | 2023-01-12 12:28 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 52128.79 | 1 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037048 | O.1037048.02 | A.1037048.02.07 | Gynatrix-1_P&A_Plug 1-3 | AWE PERTH PTY LTD | GYNATRIX 1 | EASTERNWELL 106 | J.23.011917 | WCF | REM-PA | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-11 09:00 | 2023-01-10 12:00 |  | 2023-01-11 09:00 | 2023-01-12 09:00 |  | 2023-01-12 09:00 | AUS East Coast WS | HNarainasamy | 2023-01-09 17:52 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037048 | O.1037048.02 | A.1037048.02.10 | Gynatrix-1_P&A_Plug 4 | AWE PERTH PTY LTD | GYNATRIX 1 | EASTERNWELL 106 | J.23.022415 | WCF | REM-PA | Low | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2023-01-04 20:00 | 2023-01-03 23:00 |  | 2023-01-04 20:00 | 2023-01-05 06:00 |  | 2023-01-05 06:00 | AUS East Coast WS | HNarainasamy | 2022-12-30 18:26 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037048 | O.1037048.02 | A.1037048.02.05 | Gynatrix-1_13-3/8in Surface Casing | AWE PERTH PTY LTD | GYNATRIX 1 | EASTERNWELL 106 | J.23.011915 | WCF | PRI-SURF, CMT-DSL | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-17 05:00 | 2022-12-15 23:00 |  | 2022-12-16 08:00 | 2022-12-17 08:00 |  | 2022-12-18 05:00 | AUS East Coast WS | HNarainasamy | 2022-12-22 17:26 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 54921.86 | 1 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037048 | O.1037048.02 | A.1037048.02.04 | Elegans-1_Plug and Abandon | AWE PERTH PTY LTD | ELEGANS-1 | EASTERNWELL 106 | J.22.121747 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-30 15:00 | 2022-11-29 15:00 |  | 2022-11-30 15:00 | 2022-12-01 15:00 |  | 2022-12-01 15:00 | AUS East Coast WS | HNarainasamy | 2022-12-13 19:22 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 40399.68 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037048 | O.1037048.02 | A.1037048.02.09 | Elegans-1_Plug and Abandon - Plug 5 | AWE PERTH PTY LTD | ELEGANS-1 | EASTERNWELL 106 | J.22.130619 | WCF | REM-PA | Low | Confirmed | Design - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-05 12:00 | 2022-12-04 13:00 |  | 2022-12-05 12:00 | 2022-12-06 12:00 |  | 2022-12-06 12:00 | AUS East Coast WS | HNarainasamy | 2022-12-12 15:36 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 3 |  |  |  | 68.8 | 16.7 | 0 | 0 | 32.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037048 | O.1037048.02 | A.1037048.02.03 | Elegans-1_7in Liner | AWE PERTH PTY LTD |  | EASTERNWELL 106 | J.22.121746 | WCF | PRI-LIN | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-01 12:00 | 2022-11-30 12:00 |  | 2022-12-01 12:00 | 2022-12-02 12:00 |  | 2022-12-02 12:00 | AUS East Coast WS | HNarainasamy | 2022-11-30 15:06 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037048 | O.1037048.02 | A.1037048.02.02 | Elegans-1_9-5/8in Intermediate Casing | AWE PERTH PTY LTD | ELEGANS-1 | EASTERNWELL 106 | J.22.121745 | WCF | PRI-INTER | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-19 09:00 | 2022-11-19 |  | 2022-11-19 09:00 | 2022-11-20 09:00 |  | 2022-11-20 09:00 | AUS East Coast WS | HNarainasamy | 2022-11-29 18:32 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 56506.1 | 1 |  |  |  | 81.3 | 16.7 | 0 | 25 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037048 | O.1037048.02 | A.1037048.02.01 | Elegans-1_13-3/8in Surface Casing | AWE PERTH PTY LTD | ELEGANS-1 | EASTERNWELL 106 | J.22.121744 | WCF | PRI-SURF, CMT-MATSAL | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-13 | 2022-11-12 12:00 |  | 2022-11-13 | 2022-11-14 |  | 2022-11-14 | AUS East Coast WS | HNarainasamy | 2022-11-29 13:50 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 62450.94 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037048 | O.1037048.01 | A.1037048.01.07 | Services and Personnel - March 2023 | AWE PERTH PTY LTD | HOVEA-08 | EASTERNWELL 106 | J.23.030725 | WCF | CMT-PERS,CMT-EQPRNT,CMT-RECHARGE | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2023-02-21 |  | 2023-02-21 | 2023-03-23 23:59 |  |  | AUS East Coast WS | HNarainasamy | 2023-03-27 13:08 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 121707.89 | 1 |  |  |  | 87.5 | 50 | 100 | 50 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037048 | O.1037048.01 | A.1037048.01.06 | Services and Personnel - Feb 2023 | AWE PERTH PTY LTD | HOVEA-08 | EASTERNWELL 106 | J.23.022416 | WCF | CMT-PERS,CMT-EQPRNT | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2023-01-21 |  | 2023-01-21 | 2023-02-20 23:59 |  |  | AUS East Coast WS | HNarainasamy | 2023-02-26 23:18 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 61435.78 | 0 |  |  |  | 87.5 | 50 | 100 | 50 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037048 | O.1037048.01 | A.1037048.01.05 | Services and Personnel - Jan 2023 - Hovea-08 | AWE PERTH PTY LTD | HOVEA-08 | EASTERNWELL 106 | J.23.022417 | WCF | CMT-PERS,CMT-EQPRNT | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2023-01-12 00:01 |  | 2023-01-12 00:01 | 2023-01-20 23:59 |  |  | AUS East Coast WS | HNarainasamy | 2023-01-24 12:16 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 26483.97 | 0 |  |  |  | 87.5 | 50 | 100 | 50 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037048 | O.1037048.01 | A.1037048.01.04 | Services - Personnel & Equipment - January 2023 | AWE PERTH PTY LTD | GYNATRIX 1 | EASTERNWELL 106 | J.23.011919 | WCF | CMT-PERS,CMT-EQPRNT | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-12-21 |  | 2022-12-21 | 2023-01-12 |  |  | AUS East Coast WS | HNarainasamy | 2023-01-23 17:15 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 115319.85 | 0 |  |  |  | 87.5 | 50 | 100 | 50 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037048 | O.1037048.01 | A.1037048.01.03 | Services - Personnel & Equipment - Dec 2022 Gynatrix | AWE PERTH PTY LTD | GYNATRIX 1 | EASTERNWELL 106 | J.22.121750 | WCF | CMT-PERS,CMT-EQPRNT | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-12-10 |  | 2022-12-10 | 2022-12-20 23:59 |  |  | AUS East Coast WS | HNarainasamy | 2022-12-22 18:47 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 89595.98 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037048 | O.1037048.01 | A.1037048.01.02 | Services - Personnel & Equipment - December 2022 Elegans-1 | AWE PERTH PTY LTD | ELEGANS-1 | EASTERNWELL 106 | J.22.121749 | WCF | CMT-PERS,CMT-EQPRNT | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-11-21 |  | 2022-11-21 | 2022-12-10 23:59 |  |  | AUS East Coast WS | HNarainasamy | 2022-12-15 12:52 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 86031.02 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037048 | O.1037048.01 | A.1037048.01.01 | Services - Personnel & Equipment - November 2022 | AWE PERTH PTY LTD | ELEGANS-1 | EASTERNWELL 106 | J.22.121748 | WCF | CMT-PERS,CMT-EQPRNT | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-10-31 |  | 2022-10-31 | 2022-11-20 23:59 |  |  | AUS East Coast WS | HNarainasamy | 2022-11-24 14:19 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 101936.92 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037047 | O.1037047.03 | A.1037047.03.08 | Yoorn-1_Plug and Abandon_Plug #3 | SANTOS LIMITED | Yoorn-1 | NOBLE TOM PROSSER | J.22.115810 | WCF | REM-PA | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-08 18:00 | 2022-12-07 18:00 |  | 2022-12-08 18:00 | 2022-12-09 18:00 |  | 2022-12-09 18:00 | AUS East Coast WS | HNarainasamy | 2022-10-20 15:19 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037047 | O.1037047.03 | A.1037047.03.07 | Yoorn-1_Plug and Abandon_Plug #2 | SANTOS LIMITED | Yoorn-1 | NOBLE TOM PROSSER | J.22.115787 | WCF | REM-PA | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-06 18:00 | 2022-12-05 18:00 |  | 2022-12-06 18:00 | 2022-12-07 18:00 |  | 2022-12-07 18:00 | AUS East Coast WS | HNarainasamy | 2022-10-20 15:19 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037047 | O.1037047.03 | A.1037047.03.06 | Yoorn-1_Plug and Abandon_Plug #1 | SANTOS LIMITED | Yoorn-1 | NOBLE TOM PROSSER | J.22.115780 | WCF | REM-PA | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-05 12:00 | 2022-12-04 12:00 |  | 2022-12-05 12:00 | 2022-12-06 12:00 |  | 2022-12-06 12:00 | AUS East Coast WS | HNarainasamy | 2022-10-20 15:18 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037047 | O.1037047.03 | A.1037047.03.05 | Yoorn-1_9-5/8in Liner Cementing | SANTOS LIMITED | Yoorn-1 | NOBLE TOM PROSSER | J.22.115750 | WCF | PRI-LIN | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-24 12:00 | 2022-11-23 12:00 |  | 2022-11-24 12:00 | 2022-11-25 12:00 |  | 2022-11-25 12:00 | AUS East Coast WS | HNarainasamy | 2022-10-20 15:18 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037047 | O.1037047.03 | A.1037047.03.04 | Yoorn-1_11-3/4in Liner Cementing | SANTOS LIMITED | Yoorn-1 | NOBLE TOM PROSSER | J.22.115737 | WCF | PRI-LIN | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-15 12:00 | 2022-11-15 12:00 |  | 2022-11-15 12:00 | 2022-11-16 12:00 |  | 2022-11-16 12:00 | AUS East Coast WS | HNarainasamy | 2022-10-20 15:18 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037047 | O.1037047.03 | A.1037047.03.03 | Yoorn-1_13-5/8in Intermediate Casing Cementing | SANTOS LIMITED | Yoorn-1 | NOBLE TOM PROSSER | J.22.115730 | WCF | PRI-INTER | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-04 12:00 | 2022-11-03 12:00 |  | 2022-11-04 12:00 | 2022-11-05 12:00 |  | 2022-11-05 12:00 | AUS East Coast WS | HNarainasamy | 2022-10-20 15:17 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037047 | O.1037047.03 | A.1037047.03.02 | Yoorn-1_20" Surface Casing Cementing | SANTOS LIMITED | Yoorn-1 | NOBLE TOM PROSSER | J.22.115724 | WCF | PRI-SURF | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-25 12:00 | 2022-10-24 12:00 |  | 2022-10-25 12:00 | 2022-10-26 12:00 |  | 2022-10-26 12:00 | AUS East Coast WS | HNarainasamy | 2022-10-20 15:17 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037047 | O.1037047.03 | A.1037047.03.01 | Yoorn-1_30" Conductor Cementing | SANTOS LIMITED | Yoorn-1 | NOBLE TOM PROSSER | J.22.115722 | WCF | PRI-COND | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-21 12:00 | 2022-10-20 12:00 |  | 2022-10-21 12:00 | 2022-10-22 12:00 |  | 2022-10-22 12:00 | AUS East Coast WS | HNarainasamy | 2022-10-20 15:17 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037047 | O.1037047.02 | A.1037047.02.08 | Spartan-2 ST1_9-5/8in Casing | SANTOS LIMITED | SPARTAN-2 | NOBLE TOM PROSSER | J.22.132700 | WCF | PRI-INTER, CMT-MATSAL | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-12-13 07:00 | 2022-12-14 |  | 2022-12-14 11:00 | 2022-12-15 10:59 |  | 2022-12-17 06:59 | AUS East Coast WS | HNarainasamy | 2023-05-27 15:31 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 36350 | 1 |  |  |  | 81.3 | 50 | 0 | 50 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037047 | O.1037047.02 | A.1037047.02.09 | Spartan-2 ST1 - 9-5/8in DLT Inflow Test | SANTOS LIMITED | SPARTAN-2 | NOBLE TOM PROSSER | J.22.134305 | WCF | CMT-TOOLS | High | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2023-01-19 02:00 | 2023-01-21 |  | 2023-01-21 17:00 | 2023-01-22 02:59 |  | 2023-01-24 01:59 | AUS East Coast WS | HNarainasamy | 2023-01-25 16:25 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 68.8 | 50 | 0 | 25 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037047 | O.1037047.02 | A.1037047.02.10 | 9-5/8in DLT Cyclone Suspension | SANTOS LIMITED | SPARTAN-2 | NOBLE TOM PROSSER | J.22.137102 | WCF | CMT-TOOLS | High | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2022-12-28 08:00 | 2022-12-29 20:00 |  | 2022-12-30 23:00 | 2022-12-31 08:59 |  | 2023-01-02 07:59 | AUS East Coast WS | HNarainasamy | 2022-12-30 21:54 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 68.8 | 66.7 | 0 | 25 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037047 | O.1037047.02 | A.1037047.02.04 | Spartan-2_7in Liner Cementing | SANTOS LIMITED | SPARTAN-2 | NOBLE TOM PROSSER | J.22.120847 | WCF | PRI-LIN, CMT-MATSAL | Low | Confirmed | Design - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-24 18:00 | 2022-12-24 08:00 |  | 2022-12-24 18:00 | 2022-12-25 17:59 |  | 2022-12-25 17:59 | AUS East Coast WS | HNarainasamy | 2022-12-23 23:06 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 68.8 | 50 | 0 | 25 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037047 | O.1037047.02 | A.1037047.02.06 | 7in Cement Retainer | SANTOS LIMITED | Spartan-2 | NOBLE TOM PROSSER | J.22.131340 | WCF | CMT-TOOLS | High | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-12-05 15:00 | 2022-12-04 12:00 |  | 2022-12-05 15:00 | 2022-12-06 00:59 |  | 2022-12-06 00:59 | AUS East Coast WS | HNarainasamy | 2022-12-07 14:57 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037047 | O.1037047.02 | A.1037047.02.07 | Spartan-2 - KOP | SANTOS LIMITED | SPARTAN-2 | NOBLE TOM PROSSER | J.22.131810 | WCF | REM-PA,REM-KOP | High | Confirmed | Design - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-07 18:00 | 2022-12-07 13:00 |  | 2022-12-07 18:00 | 2022-12-08 17:59 |  | 2022-12-08 17:59 | AUS East Coast WS | HNarainasamy | 2022-12-07 14:56 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 62.5 | 66.7 | 0 | 0 | 45 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037047 | O.1037047.02 | A.1037047.02.05 | Plug 1A+ 1B | SANTOS LIMITED | SPARTAN-2 | NOBLE TOM PROSSER | J.22.131328 | WCF | CMT-MATSAL, REM-PA | High | Confirmed | Design - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-05 12:00 | 2022-12-05 06:00 |  | 2022-12-05 12:00 | 2022-12-05 23:59 |  | 2022-12-05 23:59 | AUS East Coast WS | HNarainasamy | 2022-12-06 02:28 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 2 |  |  |  | 68.8 | 50 | 0 | 25 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037047 | O.1037047.02 | A.1037047.02.03 | Spartan-2_9-5/8in Intermediate Casing | SANTOS LIMITED | Spartan-2 | NOBLE TOM PROSSER | J.22.120844 | WCF | PRI-INTER, CMT-MATSAL | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-22 12:00 | 2022-11-21 20:00 |  | 2022-11-26 | 2022-11-26 23:59 |  | 2022-11-26 23:59 | AUS East Coast WS | HNarainasamy | 2022-11-30 12:42 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 39621.5 | 0 |  |  |  | 81.3 | 50 | 0 | 50 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037047 | O.1037047.02 | A.1037047.02.02 | Spartan-2_13-3/8" Surface Casing | SANTOS LIMITED | SPARTAN-2 | NOBLE TOM PROSSER | J.22.114311 | WCF | PRI-SURF | Medium | Confirmed | Design - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-13 04:00 | 2022-11-13 20:00 |  | 2022-11-14 12:00 | 2022-11-15 11:59 |  | 2022-11-14 03:59 | AUS East Coast WS | HNarainasamy | 2022-11-14 19:44 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 68.8 | 50 | 0 | 25 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037047 | O.1037047.02 | A.1037047.02.01 | Spartan-2_30" Conductor Casing | SANTOS LIMITED | SPARTAN-2 | NOBLE TOM PROSSER | J.22.110738 | WCF | PRI-COND | Medium | Confirmed | Design - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-06 20:00 | 2022-11-05 23:00 |  | 2022-11-06 23:00 | 2022-11-07 11:00 |  | 2022-11-07 08:00 | AUS East Coast WS | HNarainasamy | 2022-11-04 11:27 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 68.8 | 50 | 0 | 0 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037047 | O.1037047.01 | A.1037047.01.05 | Personnel and Equipment - Feb 2022 | SANTOS LIMITED | Spartan-2 | NOBLE TOM PROSSER | J.23.030271 | WCF | CMT-EQPRNT,CMT-PERS | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2023-01-21 |  | 2023-01-21 | 2023-02-20 23:59 |  |  | AUS East Coast WS | HNarainasamy | 2023-02-17 14:21 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 44290.06 | 1 |  |  |  | 87.5 | 50 | 100 | 50 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037047 | O.1037047.01 | A.1037047.01.04 | Services - Personnel and Equipment - Jan 2022 | SANTOS LIMITED | Spartan-2 | NOBLE TOM PROSSER | J.22.133821 | WCF | CMT-EQPRNT,CMT-PERS | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-12-21 |  | 2022-12-21 | 2023-01-20 23:59 |  |  | AUS East Coast WS | HNarainasamy | 2023-01-23 12:36 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 164671.58 | 1 |  |  |  | 50 | 33.3 | 0 | 25 | 35 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037047 | O.1037047.01 | A.1037047.01.03 | Services - Personnel and Equipment - Dec 2022 - Spartan 2 | SANTOS LIMITED | Spartan-2 | NOBLE TOM PROSSER | J.22.120850 | WCF | CMT-EQPRNT,CMT-PERS | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-11-21 |  | 2022-11-21 | 2022-12-20 23:59 |  |  | AUS East Coast WS | HNarainasamy | 2022-12-21 14:23 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 165885.4 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037047 | O.1037047.01 | A.1037047.01.02 | Services - Personnel and Equipment - Nov 2022 - Spartan-2 | SANTOS LIMITED | Spartan-2 | NOBLE TOM PROSSER | J.22.115842 | WCF | CMT-EQPRNT,CMT-PERS | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-10-21 |  | 2022-10-21 | 2022-11-20 23:59 |  |  | AUS East Coast WS | HNarainasamy | 2022-11-24 12:04 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 164593.58 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037047 | O.1037047.01 | A.1037047.01.01 | Services - Personnel and Equipment - Oct 2022 - Yoorn-1 | SANTOS LIMITED | Yoorn-1 | NOBLE TOM PROSSER | J.22.115837 | WCF | CMT-EQPRNT,CMT-PERS | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-10-12 |  | 2022-10-12 | 2022-10-20 23:59 |  |  | AUS East Coast WS | HNarainasamy | 2022-10-26 16:32 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037002 | O.1037002.01 | A.1037002.01.03 | Stickle-4H1 - 9 5/8in casing | BHP PETROLEUM PTY LTD | STICKLE 4 H1 | OCEAN APEX | J.22.110737 | WCF | PRI-LONG | High | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-30 | 2023-01-17 |  | 2023-01-30 | 2023-01-31 23:59 |  | 2023-01-31 23:59 | AUS East Coast WS | NKhoa | 2023-05-27 15:31 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 70685.5 | 1 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037002 | O.1037002.01 | A.1037002.01.01 | Stickle-4H1 - Cased hole PnA 1 | BHP PETROLEUM PTY LTD | STICKLE 4 H1 | OCEAN APEX | J.22.110740 | WCF | REM-PA | High | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-22 | 2022-10-15 |  | 2022-12-22 | 2022-12-23 23:59 |  | 2022-12-23 23:59 | AUS East Coast WS | NKhoa | 2023-05-27 15:31 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 131011 | 1 |  |  |  | 81.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037002 | O.1037002.01 | A.1037002.01.05 | Apex Service - Dec | BHP PETROLEUM PTY LTD | STICKLE 4 H1 | OCEAN APEX | J.22.122431 | WCF | CMT-EQPRNT,CMT-PERS,CMT-MPUMP | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-11-25 | 2022-11-21 |  | 2022-11-21 | 2022-12-20 23:59 |  | 2022-12-20 23:59 | AUS East Coast WS | NKhoa | 2023-05-27 15:31 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 3887.4 | 1 |  |  |  | 87.5 | 33.3 | 100 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037002 | O.1037002.01 | A.1037002.01.10 | Apex Service - April | BHP PETROLEUM PTY LTD | STICKLE 4 H1 | OCEAN APEX | J.23.057805 | WCF | CMT-EQPRNT,CMT-PERS,CMT-MPUMP | Low | Confirmed | Design - CEC |  | In Progress | Not Required | In Progress | 2023-03-25 | 2023-03-21 |  | 2023-03-21 | 2023-04-20 23:59 |  | 2023-04-23 22:59 | AUS East Coast WS | NKhoa | 2023-04-04 10:44 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 2 |  |  |  | 31.3 | 16.7 | 0 | 25 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037002 | O.1037002.01 | A.1037002.01.09 | Stickle-4H1 - OH Pump and Pull PnA | BHP PETROLEUM PTY LTD | STI-4H1 | OCEAN APEX | J.23.044727 | WCF | REM-PA | High | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-21 12:00 | 2023-02-28 |  | 2023-03-21 12:00 | 2023-03-23 11:59 |  | 2023-03-23 11:59 | AUS East Coast WS | NKhoa | 2023-03-15 18:06 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037002 | O.1037002.01 | A.1037002.01.07 | Apex Service - Feb | BHP PETROLEUM PTY LTD | STICKLE 4 H1 | OCEAN APEX | J.23.019656 | WCF | CMT-EQPRNT,CMT-PERS,CMT-MPUMP | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2023-01-25 | 2023-01-21 |  | 2023-01-21 | 2023-02-20 23:59 |  | 2023-02-20 23:59 | AUS East Coast WS | NKhoa | 2023-02-21 12:28 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 25 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037002 | O.1037002.01 | A.1037002.01.08 | Apex Service - Mar | BHP PETROLEUM PTY LTD | STICKLE 4 H1 | OCEAN APEX | J.23.041481 | WCF | CMT-EQPRNT,CMT-PERS,CMT-MPUMP | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2023-02-25 | 2023-02-21 |  | 2023-02-21 | 2023-03-20 23:59 |  | 2023-03-23 23:59 | AUS East Coast WS | NKhoa | 2023-02-20 14:22 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 2 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037002 | O.1037002.01 | A.1037002.01.02 | Stickle-4H1 - Cased hole PnA 2 | BHP PETROLEUM PTY LTD | STICKLE 4 H1 | OCEAN APEX | J.22.111048 | WCF | REM-PA | High | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-12-27 12:00 | 2022-10-15 |  | 2022-12-27 12:00 | 2022-12-29 11:59 |  | 2022-12-29 11:59 | AUS East Coast WS | NKhoa | 2022-12-26 18:30 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 |  |  |  | 68.8 | 50 | 0 | 25 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037002 | O.1037002.01 | A.1037002.01.04 | Apex Service - Nov | BHP PETROLEUM PTY LTD | STI-4H1 | OCEAN APEX | J.22.122426 | WCF | CMT-EQPRNT,CMT-PERS,CMT-MPUMP | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-10-31 | 2022-10-27 |  | 2022-10-27 | 2022-11-20 23:59 |  | 2022-11-20 23:59 | AUS East Coast WS | NKhoa | 2022-12-05 14:23 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 168815.26 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1037002 | O.1037002.01 | A.1037002.01.06 | Apex service - Jan | BHP PETROLEUM PTY LTD | STICKLE 4 H1 | OCEAN APEX | J.22.122433 | WCF | CMT-EQPRNT,CMT-PERS,CMT-MPUMP | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2022-12-25 | 2022-12-21 |  | 2022-12-21 | 2023-01-20 23:59 |  | 2023-01-20 23:59 | AUS East Coast WS | NKhoa | 2022-10-31 11:23 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1036765 | O.1036765.01 | A.1036765.01.01 | EOG Beehive-1 - SWT | EOG RESOURCES AUSTRALIA BLOCK WA-488 PTY LTD |  | VALARIS 107 | J.23.008523 | RPI | TSWT-FLOWBACK-JOB | High | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2026-01-01 | 2023-04-01 | 2026-01-01 | 2026-01-01 | 2026-04-01 23:59 | 2026-04-02 | 2026-04-01 23:59 | APG TS | DMusiiako | 2025-05-14 16:16 | MWaseem2 |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Dmitrii Musiiako |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 1 |  |  |  | 0 |  |  |  | Muhammad Fahd Waseem | TS Surface Testing
P.1036765 | O.1036765.01 | A.1036765.01.02 | EOG Beehive-1 - RSA | EOG RESOURCES AUSTRALIA BLOCK WA-488 PTY LTD |  | VALARIS 107 | J.23.008524 | RPE | FSA-SF-JOB | High | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2026-01-01 | 2023-04-01 |  | 2026-01-01 | 2026-04-01 23:59 |  | 2026-04-01 23:59 | APG TS | DMusiiako | 2025-05-14 16:16 | MWaseem2 |  | No |  | [AUJN-DST] - AU - Jandakot TST |  |  | Dmitrii Musiiako |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 1 |  |  |  | 0 |  |  |  | Muhammad Fahd Waseem | TS Downhole Reservoir Testing
P.1036765 | O.1036765.01 | A.1036765.01.04 | EOG Beehive-1 - TCP | EOG RESOURCES AUSTRALIA BLOCK WA-488 PTY LTD |  | VALARIS 107 | J.23.008526 | RPI | TCP-TEMP-JOB | High | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2023-03-18 |  | 2023-04-01 | 2023-04-15 23:59 |  |  | APG TS | DMusiiako | 2024-11-19 20:07 | FDPSystemUser |  | No |  |  |  |  | Dmitrii Musiiako |  | 0 | 1 |  |  |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TCP - Tubing-Conveyed Perforation
P.1036765 | O.1036765.01 | A.1036765.01.05 | EOG Beehive-1 - Project Coordinator | EOG RESOURCES AUSTRALIA BLOCK WA-488 PTY LTD |  | VALARIS 107 | J.22.116133 | RPI | TSWT-STB | High | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2022-10-13 |  | 2022-10-13 | 2023-06-02 23:59 |  |  | APG TS | DMusiiako | 2023-03-05 11:15 | RWallis |  | No |  | [AUNB-TSWT] - Perth- New Burn STT |  |  | Dmitrii Musiiako |  | 115312.5 | 2 |  |  |  | 50 | 33.3 | 100 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1036765 | O.1036765.01 | A.1036765.01.03 | EOG Beehive-1 - DST | EOG RESOURCES AUSTRALIA BLOCK WA-488 PTY LTD |  | VALARIS 107 | J.23.008525 | RPE | DST-RENTAL | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-04-01 | 2023-04-01 |  | 2023-04-01 | 2023-04-15 23:59 |  | 2023-04-15 23:59 | APG TS | DMusiiako | 2022-10-21 10:02 | DMusiiako |  | No |  |  |  |  | Dmitrii Musiiako |  | 0 | 1 |  |  |  | 41.7 | 33.3 | 100 | 50 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Downhole Reservoir Testing
P.1036326 | O.1036326.02 | A.1036326.02.03 | PnA 2A + 2B - Shallow | WOODSIDE ENERGY JULIMAR PTY LTD | BAL 5H | OCEAN APEX | J.22.117240 | WCF | REM-PA | High | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-10-20 | 2022-10-01 |  | 2022-10-20 | 2022-10-21 23:59 |  | 2022-10-21 23:59 | AUS East Coast WS | NKhoa | 2022-10-17 17:43 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1036326 | O.1036326.02 | A.1036326.02.02 | PnA 1 - Deep | WOODSIDE ENERGY JULIMAR PTY LTD | BAL 5H | OCEAN APEX | J.22.117239 | WCF | REM-PA | High | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-10-18 01:00 | 2022-10-01 |  | 2022-10-18 01:00 | 2022-10-19 23:59 |  | 2022-10-19 23:59 | AUS East Coast WS | NKhoa | 2022-10-17 17:43 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 96016.16 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1036326 | O.1036326.02 | A.1036326.02.01 | Inflow test - 9 5/8in packer | WOODSIDE ENERGY JULIMAR PTY LTD | BAL 5H | OCEAN APEX | J.22.117237 | WCF | CMT-TOOLS | High | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2022-10-15 01:00 | 2022-10-01 |  | 2022-10-15 01:00 | 2022-10-17 00:59 |  | 2022-10-17 00:59 | AUS East Coast WS | NKhoa | 2022-10-17 17:43 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1036326 | O.1036326.01 | A.1036326.01.03 | PnA 2A + 2B - Shallow | WOODSIDE ENERGY JULIMAR PTY LTD | BALNAVES BAL-8GI | OCEAN APEX | J.22.117236 | WCF | REM-PA | High | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-10-06 | 2022-08-27 |  | 2022-10-06 | 2022-10-07 23:59 |  | 2022-10-07 23:59 | AUS East Coast WS | NKhoa | 2022-10-17 17:43 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1036326 | O.1036326.01 | A.1036326.01.02 | PnA 1 - Deep | WOODSIDE ENERGY JULIMAR PTY LTD | BALNAVES BAL-8GI | OCEAN APEX | J.22.117235 | WCF | REM-PA | High | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-10-04 | 2022-08-27 |  | 2022-10-04 | 2022-10-05 23:59 |  | 2022-10-05 23:59 | AUS East Coast WS | NKhoa | 2022-10-17 17:43 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1036326 | O.1036326.01 | A.1036326.01.01 | Inflow test - 9 5/8in packer | WOODSIDE ENERGY JULIMAR PTY LTD | BALNAVES BAL-8GI | OCEAN APEX | J.22.117234 | WCF | CMT-TOOLS | High | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2022-10-02 | 2022-08-27 |  | 2022-10-02 | 2022-10-03 23:59 |  | 2022-10-04 00:59 | AUS East Coast WS | NKhoa | 2022-10-17 17:43 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1036278 | O.1036278.01 | A.1036278.01.01 | Well-1 Tamboran NT - Frac | TAMBORAN RESOURCES LIMITED | Well #1 |  |  | RPS | FRAC-COMB,FRAC-PROP,FRAC-SLICK, STM-RECHARGE, MTX-MATSAL | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-02-01 01:00 | 2024-02-01 |  | 2024-02-01 | 2024-02-29 23:59 |  | 2024-03-01 00:59 | AUS East Coast WS | radinegara | 2023-08-28 10:05 | HFerdjallah |  | Yes |  |  |  |  | Aidan Flynn Kohr |  | 0 | 20 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1036278 | O.1036278.01 | A.1036278.01.02 | Well-1 Tamboran NT - CT | TAMBORAN RESOURCES LIMITED | Well #1 |  |  | RPI | CT-CIRC | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-04-15 01:00 | 2023-04-15 |  | 2023-04-15 | 2023-05-13 23:59 |  | 2023-05-14 00:59 | AUS East Coast WS | radinegara | 2023-03-03 17:41 | OMosleh |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 1 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1036181 | O.1036181.01 | A.1036181.01.03 | Beaufort 1 | SANTOS LIMITED | BEAUFORT 1 | WILD DESERT RIG 4 | J.22.110405 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2022-10-15 | 2022-10-14 01:00 |  | 2022-10-15 | 2022-10-21 23:59 |  | 2022-10-21 23:59 | Roma WL | JEsmeralda | 2023-03-01 17:34 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 4 |  |  |  | 58.3 | 83.3 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1036181 | O.1036181.01 | A.1036181.01.04 | Beaufort 7 | SANTOS LIMITED | BEAUFORT 7 | WILD DESERT RIG 4 | J.22.110411 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-10-01 23:00 |  | 2022-10-03 | 2022-10-13 00:59 |  |  | Roma WL | JEsmeralda | 2022-10-23 14:04 | MRony2 |  | No |  |  |  |  | Jon Lawrie |  | 0 | 4 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1036181 | O.1036181.01 | A.1036181.01.05 | Plug_MSLC | SANTOS LIMITED | Daldowie 13, Collingwood 18, Glen Evis 7 | WILD DESERT RIG 4 | J.22.110430 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-09-09 |  | 2022-09-09 | 2022-09-17 23:59 |  |  | Roma WL | ysaeedabadian | 2022-10-19 21:26 | MRony2 |  | No |  |  |  |  | Jon Lawrie |  | 8641.98 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1036181 | O.1036181.01 | A.1036181.01.01 | Grafton Range 3 | SANTOS LIMITED | GRafton Range 19, Grafton Range 3 | WILD DESERT RIG 4 | J.22.110413 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-08-29 |  | 2022-08-30 | 2022-09-05 23:59 |  |  | Roma WL | MRony2 | 2022-10-19 14:18 | MRony2 |  | No |  |  |  |  | Jon Lawrie |  | 0 | 4 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1036181 | O.1036181.01 | A.1036181.01.02 | Grafton Range 4 | SANTOS LIMITED | GRAFTON RANGE 4 | WILD DESERT RIG 4 | J.22.110422 | RPI | PS-WL-Ops | Low | Unconfirmed - 90% | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-09-22 | 2022-09-20 |  | 2022-09-22 | 2022-09-28 23:59 |  | 2022-09-28 23:59 | Roma WL | JEsmeralda | 2022-10-03 14:18 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 22068.42 | 4 |  | L0 - No RO |  | 75 | 0 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1035813 | O.1035813.01 | A.1035813.01.02 | Blacktip TCP Operation | ENI AUSTRALIA B.V. |  | VALARIS 107 | J.22.109477 | RPE | DST-CH-JOB | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-11-27 | 2022-08-15 |  | 2022-11-27 | 2023-01-25 23:59 |  | 2023-01-25 23:59 | APG TS | IHafeez | 2024-11-19 20:24 | FDPSystemUser |  | No |  |  |  |  | Iftikhar Hafeez |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Downhole Reservoir Testing
P.1035813 | O.1035813.01 | A.1035813.01.01 | Blacktip TCP Design | ENI AUSTRALIA B.V. |  | VALARIS 107 | J.22.109476 | RPI | TCP-DSGN | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-08-14 |  | 2022-08-14 | 2023-02-15 23:59 |  |  | APG TS | IHafeez | 2022-10-03 06:31 | FDPSystemUser |  | No |  |  |  |  | Iftikhar Hafeez |  | 0 | 4 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TCP - Tubing-Conveyed Perforation
P.1035747 | O.1035747.03 | A.1035747.03.01 | QGC TGS Phase 2 Part 1 | QGC |  |  | J.25.006683 | RPI | TSWT-SEPVX-JOB | High | Confirmed | Design - CEC |  | Design Completed | Not Started | Not Started | 2025-11-01 | 2025-10-31 |  | 2025-11-01 | 2026-01-29 23:59 |  | 2026-01-30 23:59 | APG TS | EKondratiev | 2025-12-01 11:01 | ASaini |  | No |  |  |  | APG TS | Ahmed El-Wakil |  | 0 | 1 |  | L1 - Support RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ahmed El-Wakil | TS Surface Testing
P.1035747 | O.1035747.02 | A.1035747.02.01 | Frac Support / CTU / Bleed Off Package | QGC | DUNK 1, OVERSTON 6, BATHURST 5, Dunk 5 |  | J.23.018502 | RPI | TSWT-NOSEPNOVX-JOB | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-01-28 | 2023-12-06 |  | 2024-01-01 | 2024-07-15 23:59 |  | 2024-07-14 23:59 | APG TS | QMalik2 | 2025-01-02 14:29 | MSwara |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Qasim Malik |  | 216396.85 | 1 |  | L0 - No RO |  | 91.7 | 66.7 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1035747 | O.1035747.01 | A.1035747.01.08 | QGC Examine Part 4 | QGC | DUNK 5, BATHURST 5 |  | J.24.175504 | RPI | TSWT-SEPONLY-JOB | High | Confirmed | Design - CEC |  | Design Completed | Not Started | In Progress | 2023-12-27 | 2024-08-31 | 2024-11-29 16:00 | 2024-12-01 | 2025-02-14 23:59 | 2025-03-03 | 2024-03-27 23:59 | APG TS | EKondratiev | 2025-03-31 16:36 | YBibby |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  | APG TS | Evgeniy Kondratiev |  | 1292415.91 | 1 |  | L2 - Shift RO |  | 66.7 | 16.7 | 0 | 50 | 40 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1035747 | O.1035747.01 | A.1035747.01.07 | QGC Phase 1 Part 3 | QGC | DUNK 5, BATHURST 5 |  | J.24.107507 | RPI | TSWT-SEPONLY-JOB | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-09-27 | 2024-06-01 |  | 2024-09-01 | 2024-12-01 23:59 |  | 2023-12-27 23:59 | APG TS | EKondratiev | 2024-12-12 12:14 | EKondratiev |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Qasim Malik |  | 1849786.11 | 1 |  | L0 - No RO |  | 91.7 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1035747 | O.1035747.01 | A.1035747.01.03 | Well Test Package #1 ( 3rd Well ) | QGC | BATHURST 5 |  | J.23.008522 | RPI | TSWT-SEPONLY-JOB | High | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2024-07-01 | 2024-06-01 |  | 2024-07-01 | 2024-09-14 23:59 |  | 2024-09-14 23:59 | APG TS | RWallis | 2024-11-19 20:14 | FDPSystemUser |  | No |  |  |  |  | Qasim Malik |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1035747 | O.1035747.01 | A.1035747.01.01 | Well Test Package #1 | QGC | OVERSTON 6, BATHURST 5, DUNK 5 |  | J.23.008520 | RPI | TSWT-SEPONLY-JOB | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-02-26 | 2023-11-01 |  | 2024-02-01 | 2024-05-31 23:59 |  | 2023-06-26 23:59 | APG TS | RWallis | 2024-11-19 20:14 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Qasim Malik |  | 233278.96 | 1 |  | L0 - No RO |  | 91.7 | 75 | 100 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1035747 | O.1035747.01 | A.1035747.01.02 | Well Test Package #2 | QGC | DUNK 5 |  | J.23.008521 | RPI | TSWT-SEPONLY-JOB | High | Cancelled | Close - PSD |  | Design Completed | Not Started | Design Completed | 2023-03-12 | 2023-11-01 |  | 2024-02-01 | 2024-05-01 23:59 |  | 2024-05-16 23:59 | APG TS | RWallis | 2024-11-19 20:14 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Qasim Malik |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1035747 | O.1035747.01 | A.1035747.01.06 | QGC Phase 1 Part 2 | QGC | OVERSTON 6, BATHURST 5, DUNK 5 |  | J.24.107506 | RPI | TSWT-SEPONLY-JOB | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-06-23 | 2024-05-26 |  | 2024-06-01 | 2024-08-31 23:59 |  | 2024-08-31 23:59 | APG TS | EKondratiev | 2024-11-19 20:14 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Qasim Malik |  | 201491.91 | 1 |  | L0 - No RO |  | 91.7 | 66.7 | 50 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1035747 | O.1035747.01 | A.1035747.01.04 | Engineering | QGC | BATHURST 5, DUNK 5, Overston-6 |  | J.23.031928 | RPI | TSWT-NO-OP | High | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2024-01-01 |  | 2024-01-01 | 2024-07-22 23:59 |  |  | APG TS | QMalik2 | 2024-07-15 19:14 | QMalik2 |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Qasim Malik |  | 280340.33 | 0 |  |  |  | 58.3 | 50 | 100 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1035747 | O.1035747.01 | A.1035747.01.05 | Frac Support Package | QGC | BATHURST 5, Overston-6, DUNK 5 |  | J.23.100113 | RPI | TSWT-NOSEPNOVX-JOB | High | Cancelled | Close - PSD |  | Not Required | Not Started | Not Started |  | 2024-01-01 |  | 2024-02-01 | 2024-07-31 23:59 |  |  | APG TS | QMalik2 | 2024-07-15 19:14 | QMalik2 |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Qasim Malik |  | 0 | 1 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1035720 | O.1035720.01 | A.1035720.01.01 | Dewhurst 43 | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.22.110410 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-01-02 | 2024-01-01 |  | 2024-01-02 | 2024-01-07 23:59 |  | 2024-01-07 23:59 | Roma WL | MRony2 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  | L2 - Shift RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1035720 | O.1035720.01 | A.1035720.01.03 | BIBBLEWINDI 31 | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.23.008593 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-01-13 | 2024-01-12 | 2024-01-13 | 2024-01-13 | 2024-01-18 23:59 | 2024-01-19 | 2024-01-18 23:59 | Roma WL | MRony2 | 2023-10-28 17:01 | KKeese |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 4 |  | L2 - Shift RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1035720 | O.1035720.01 | A.1035720.01.05 | BIBBLEWINDI 30 | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.23.008590 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-01-28 | 2024-01-27 | 2024-01-28 | 2024-01-28 | 2024-02-02 23:59 | 2024-02-03 | 2024-02-02 23:59 | Roma WL | MRony2 | 2023-10-28 17:01 | KKeese |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  | L2 - Shift RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1035720 | O.1035720.01 | A.1035720.01.04 | DEWHURST 34 | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.23.008592 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-02-05 | 2024-02-04 | 2024-02-05 | 2024-02-05 | 2024-02-10 23:59 | 2024-02-11 | 2024-02-10 23:59 | Roma WL | MRony2 | 2023-10-28 17:01 | KKeese |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  | L2 - Shift RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1035720 | O.1035720.01 | A.1035720.01.08 | DEWHURST 41 | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.23.008591 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-02-14 | 2024-02-13 | 2024-02-14 | 2024-02-14 | 2024-02-19 23:59 | 2024-02-20 | 2024-02-19 23:59 | Roma WL | MRony2 | 2023-10-28 17:01 | KKeese |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  | L2 - Shift RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1035720 | O.1035720.01 | A.1035720.01.07 | DEWHURST 41 | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.23.008594 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-02-18 | 2024-02-17 | 2024-02-18 | 2024-02-18 | 2024-02-23 23:59 | 2024-02-24 | 2024-02-23 23:59 | Roma WL | MRony2 | 2023-10-28 17:01 | KKeese |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  | L2 - Shift RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1035720 | O.1035720.01 | A.1035720.01.06 | DEWHURST 40 | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.23.008595 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-02-27 | 2024-02-26 | 2024-02-27 | 2024-02-27 | 2024-03-03 23:59 | 2024-03-04 | 2024-03-03 23:59 | Roma WL | MRony2 | 2023-10-28 17:01 | KKeese |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  | L2 - Shift RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1035720 | O.1035720.01 | A.1035720.01.02 | DEWHURST 35 | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.22.110394 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-20 | 2022-12-19 |  | 2022-12-20 | 2022-12-25 23:59 |  | 2022-12-25 23:59 | Roma WL | MRony2 | 2022-12-01 11:20 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 4 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1035703 | O.1035703.02 | A.1035703.02.01 | ENI Blacktip ¦ FSA | ENI AUSTRALIA B.V. |  | VALARIS 107 | J.22.109478 | RPE | FSA-WA-JOB | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-11-27 | 2022-09-01 |  | 2022-11-27 | 2023-02-15 23:59 |  | 2023-02-15 23:59 | APG TS | IHafeez | 2022-10-03 06:32 | FDPSystemUser |  | No |  |  |  |  | Iftikhar Hafeez |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Downhole Reservoir Testing
P.1035703 | O.1035703.01 | A.1035703.01.03 | DST | ENI AUSTRALIA B.V. | BLACKTIP P3 | VALARIS 107 | J.22.109479 | RPE | DST-CH-JOB | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-27 | 2022-09-08 |  | 2022-11-27 | 2023-02-15 23:59 |  | 2023-02-15 23:59 | APG TS | IHafeez | 2024-11-19 20:24 | FDPSystemUser |  | No |  |  |  |  | Iftikhar Hafeez |  | 0 | 1 |  |  |  | 58.3 | 66.7 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Downhole Reservoir Testing
P.1035703 | O.1035703.01 | A.1035703.01.02 | SWT | ENI AUSTRALIA B.V. | BLACKTIP P3 | VALARIS 107 | J.22.109475 | RPI | TSWT-SEPONLY-JOB | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-27 | 2022-08-25 |  | 2022-11-27 | 2023-06-30 23:59 |  | 2023-06-30 23:59 | APG TS | IHafeez | 2024-11-19 20:14 | FDPSystemUser |  | No |  |  |  |  | Iftikhar Hafeez |  | 4447589.92 | 4 |  | L0 - No RO |  | 83.3 | 66.7 | 50 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1035703 | O.1035703.01 | A.1035703.01.06 | ENI_SWT_BTP1 | ENI AUSTRALIA B.V. | BLACKTIP P1 | VALARIS 107 | J.22.109482 | RPI | TSWT-SEPONLY-JOB | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-03-31 | 2023-03-30 |  | 2023-03-31 | 2023-05-08 23:59 |  | 2023-05-08 23:59 | APG TS | IHafeez | 2024-11-19 20:14 | FDPSystemUser |  | No |  |  |  |  | Iftikhar Hafeez |  | 0 | 1 |  | L0 - No RO |  | 75 | 66.7 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1035703 | O.1035703.01 | A.1035703.01.05 | TCP | ENI AUSTRALIA B.V. | BLACKTIP P3 | VALARIS 107 | J.22.109481 | RPI | TCP-TEMP-JOB | High | Operationally Complete | Close - PSD |  | Not Required | In Progress | In Progress |  | 2022-09-08 |  | 2022-11-27 | 2023-03-31 23:59 |  |  | APG TS | IHafeez | 2024-11-19 20:07 | FDPSystemUser |  | No |  |  |  |  | Iftikhar Hafeez |  | 0 | 1 |  |  |  | 58.3 | 66.7 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1035703 | O.1035703.01 | A.1035703.01.08 | P1 TCP Shoot & Pull_Blacktip | ENI AUSTRALIA B.V. | BLACKTIP P1 | VALARIS 107 | J.23.047703 | RPI | TCP-TEMP-JOB | Medium | Operationally Complete | Close - PSD |  | Not Required | Design Completed | In Progress |  | 2023-03-07 |  | 2023-03-15 | 2023-04-30 23:59 |  |  | APG TS | IHafeez | 2024-11-19 20:07 | FDPSystemUser |  | No |  |  |  |  | Iftikhar Hafeez |  | 112000 | 1 |  |  |  | 75 | 66.7 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1035703 | O.1035703.01 | A.1035703.01.07 | ENI_FSA_BTP1 | ENI AUSTRALIA B.V. | BLACKTIP P1 | VALARIS 107 | J.22.109483 | RPE | FSA-SF-JOB | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-01 | 2023-03-31 | 2023-03-31 | 2023-04-01 | 2023-05-08 23:59 | 2023-06-27 | 2023-05-08 23:59 | APG TS | IHafeez | 2023-08-07 15:38 | IHafeez |  | No |  |  |  |  | Iftikhar Hafeez |  | 33055 | 1 |  |  |  | 75 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Downhole Reservoir Testing
P.1035703 | O.1035703.01 | A.1035703.01.01 | Blacktip flowback Design | ENI AUSTRALIA B.V. | BLACKTIP P3, BLACKTIP P1 | VALARIS 107 | J.22.109474 | RPI | TSWT-RECHARGE | Medium | Operationally Complete | Close - PSD |  | Not Required | Design Completed | In Progress |  | 2022-08-15 |  | 2022-08-15 | 2023-06-30 23:59 |  |  | APG TS | IHafeez | 2023-06-22 19:29 | IHafeez |  | No |  |  |  |  | Iftikhar Hafeez |  | 58764 | 1 |  |  |  | 91.7 | 83.3 | 100 | 100 | 92.5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Surface Testing
P.1035703 | O.1035703.01 | A.1035703.01.04 | FSA | ENI AUSTRALIA B.V. | BLACKTIP P3 | VALARIS 107 | J.22.109480 | RPE | FSA-SF-JOB | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-27 | 2022-09-08 |  | 2022-11-27 | 2023-06-30 23:59 |  | 2023-06-30 23:59 | APG TS | IHafeez | 2023-06-18 18:44 | IHafeez |  | No |  |  |  |  | Iftikhar Hafeez |  | 121178 | 1 |  |  |  | 75 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TS Downhole Reservoir Testing
P.1035675 | O.1035675.03 | A.1035675.03.01 | BAL-8GI - Product Consumption | WOODSIDE ENERGY JULIMAR PTY LTD | BALNAVES BAL-8GI | OCEAN APEX | J.22.116490 | WCF | CMT-MPUMP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-14 | 2022-10-10 |  | 2022-10-10 | 2022-10-20 23:59 |  | 2022-10-23 14:20 | AUS West Coast WS | NKhoa | 2022-10-24 16:25 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 67819.7 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1035675 | O.1035675.02 | A.1035675.02.01 | PnA 1 - Deep | WOODSIDE ENERGY JULIMAR PTY LTD | BAL-6H | OCEAN APEX | J.22.110859 | WCF | REM-PA | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-10 | 2022-08-14 |  | 2022-09-10 | 2022-09-11 23:59 |  | 2022-09-11 23:59 | AUS West Coast WS | NKhoa | 2023-03-28 12:05 | NKhoa |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 117532.76 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1035675 | O.1035675.02 | A.1035675.02.02 | PnA 2 - Shallow | WOODSIDE ENERGY JULIMAR PTY LTD | BAL 6H | OCEAN APEX | J.22.110849 | WCF | REM-PA | High | Confirmed | Design - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-13 | 2022-08-14 |  | 2022-09-13 | 2022-09-14 23:59 |  | 2022-09-14 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1035675 | O.1035675.02 | A.1035675.02.03 | Inflow test - 9 5/8in | WOODSIDE ENERGY JULIMAR PTY LTD | BAL 6H | OCEAN APEX | J.22.110842 | WCF | CMT-TOOLS | High | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2022-09-08 | 2022-08-14 |  | 2022-09-08 | 2022-09-09 23:59 |  | 2022-09-10 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1035675 | O.1035675.01 | A.1035675.01.01 | BAL-7WI - Product consumption | WOODSIDE ENERGY JULIMAR PTY LTD | BAL 7WI | OCEAN APEX | J.22.110855 | WCF | CMT-MPUMP | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-13 | 2022-07-24 |  | 2022-08-09 | 2022-08-31 23:59 |  | 2022-08-31 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:39 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 103076.12 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1035485 | O.1035485.01 | A.1035485.01.21 | Denison BC-03 OH | DENISON GAS | BAFFLE CREEK 1 | ENSIGN 974 | J.25.070023 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2025-06-28 | 2025-12-09 03:00 | 2025-12-08 14:00 | 2025-12-10 02:00 | 2025-12-18 01:59 | 2025-12-20 | 2025-07-08 23:59 | Roma WL | JEsmeralda | 2025-11-26 12:37 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 3 |  | L1 - Support RO |  | 33.3 | 33.3 | 0 | 25 | 27.5 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1035485 | O.1035485.01 | A.1035485.01.23 | Denison Baffle Creek 7 OH | DENISON GAS | BAFFLE CREEK 1 | ENSIGN 974 | J.25.102001 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-10-31 | 2025-10-31 03:00 | 2025-10-30 15:00 | 2025-11-01 02:00 | 2025-11-09 01:59 | 2025-11-11 01:00 | 2025-11-10 23:59 | Roma WL | CKok3 | 2025-09-30 08:45 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 3 |  | L1 - Support RO |  | 33.3 | 33.3 | 0 | 25 | 27.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1035485 | O.1035485.01 | A.1035485.01.24 | Denison BC-04A | DENISON GAS | BAFFLE CREEK 1, BAFFLE CREEK 4, BAFFLE CREEK 04 ST2 | ENSIGN 974 | J.25.151465 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-09-08 22:00 | 2025-09-09 01:00 | 2025-09-07 | 2025-09-10 | 2025-10-09 23:59 | 2025-11-01 | 2025-10-11 22:59 | Roma WL | CKok3 | 2025-09-29 14:50 | AJaved15 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 87562.05 | 3 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 75 | 75 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1035485 | O.1035485.01 | A.1035485.01.20 | Denison BC-02 OH | DENISON GAS | BAFFLE CREEK 1, BAFFLE CREEK 02 | ENSIGN 974 | J.25.070022 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2025-06-14 | 2025-06-14 03:00 | 2025-06-13 14:00 | 2025-08-19 02:00 | 2025-11-04 01:59 | 2025-11-05 23:00 | 2025-11-05 22:59 | Roma WL | JEsmeralda | 2025-09-03 16:30 | SAli112 |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 3 |  | L3 - Full RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 2 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1035485 | O.1035485.01 | A.1035485.01.19 | Denison BC-04 OH | DENISON GAS | BAFFLE CREEK 1, BAFFLE CREEK 4 | ENSIGN 974 | J.25.059708 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-05-31 | 2025-05-31 03:00 | 2025-05-29 14:00 | 2025-06-01 02:00 | 2025-07-01 01:59 | 2025-07-22 | 2025-07-02 23:59 | Roma WL | CKok3 | 2025-07-11 12:05 | SAli112 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 87562.05 | 3 |  | L3 - Full RO |  | 100 | 100 | 100 | 100 | 100 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1035485 | O.1035485.01 | A.1035485.01.22 | Denison Baffle Creek 6 OH | DENISON GAS | BAFFLE CREEK 1 | ENSIGN 974 | J.25.102000 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2025-07-31 | 2025-07-31 03:00 | 2025-07-30 14:00 | 2025-08-01 02:00 | 2025-08-09 01:59 | 2025-08-11 | 2025-08-10 23:59 | Roma WL | CKok3 | 2025-05-23 18:38 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 3 |  | L1 - Support RO |  | 33.3 | 33.3 | 0 | 25 | 27.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1035485 | O.1035485.01 | A.1035485.01.15 | Baffle Creek 1 | DENISON GAS | BAFFLE CREEK 1 | ENSIGN 974 | J.24.116200 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-09-30 | 2024-09-21 03:00 | 2024-09-26 14:00 | 2024-09-22 02:00 | 2024-10-31 01:59 | 2024-11-08 | 2024-10-31 01:59 | Roma WL | KKeese | 2025-03-26 15:58 | NSchwenke |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 3 |  | L2 - Shift RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 3 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1035485 | O.1035485.01 | A.1035485.01.18 | Denison May 2025- OH | DENISON GAS | THE CRESCENT 1, YANDINA 6 | ENSIGN 974 | J.25.020330 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-05-02 | 2025-05-02 03:00 |  | 2025-05-03 02:00 | 2025-05-06 01:59 |  | 2025-05-25 23:59 | Roma WL | KKeese | 2025-03-13 17:02 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L1 - Support RO |  | 33.3 | 33.3 | 0 | 25 | 27.5 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1035485 | O.1035485.01 | A.1035485.01.08 | Denison Gas 1 | DENISON GAS | METEOR CREEK 1 | ENSIGN 974 | J.24.022189 | RPE | ES-OH-Ops | Low | Cancelled | Execute - PSD |  | In Progress | Not Started | In Progress | 2024-01-21 | 2024-01-20 01:00 |  | 2024-01-21 | 2024-01-22 23:59 |  | 2024-01-24 23:59 | Roma WL | KKeese | 2025-01-20 12:53 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L2 - Shift RO |  | 41.7 | 33.3 | 0 | 25 | 30 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1035485 | O.1035485.01 | A.1035485.01.10 | Denison Gas 3 | DENISON GAS | YANDINA 5 | ENSIGN 974 | J.24.022191 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-12-17 08:00 | 2024-05-14 01:00 |  | 2024-05-15 | 2024-05-16 23:59 |  | 2024-05-19 00:59 | Roma WL | KKeese | 2024-12-12 17:08 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 2 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1035485 | O.1035485.01 | A.1035485.01.16 | Springton 10A | DENISON GAS | THE CRESCENT 1, YANDINA 6, SPRINGTON 11 | ENSIGN 974 | J.24.122061 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-09-26 | 2024-08-20 03:00 |  | 2024-08-21 02:00 | 2024-08-24 01:59 |  | 2024-08-24 01:59 | Roma WL | KKeese | 2024-10-04 18:52 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L1 - Support RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 2 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1035485 | O.1035485.01 | A.1035485.01.17 | Springton 10B | DENISON GAS | THE CRESCENT 1, YANDINA 6 | ENSIGN 974 | J.24.122062 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2023-10-13 01:00 | 2024-10-27 03:00 |  | 2024-10-28 02:00 | 2024-10-31 01:59 |  | 2024-09-08 01:59 | Roma WL | KKeese | 2024-09-13 14:44 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L1 - Support RO |  | 33.3 | 33.3 | 0 | 25 | 27.5 |  | 2 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1035485 | O.1035485.01 | A.1035485.01.05 | SuperCombo-MDT_Meteor Creek 1 | DENISON GAS | METEOR CREEK 1 | ENSIGN 974 | J.23.084131 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-02 | 2023-07-01 01:00 |  | 2023-07-02 | 2023-07-03 23:59 |  | 2023-07-05 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 2 |  | L2 - Shift RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1035485 | O.1035485.01 | A.1035485.01.07 | SuperCombo-MDT_One Mile 1 | DENISON GAS | ONE MILE 1 | ENSIGN 974 | J.23.114907 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-25 06:00 | 2023-07-24 13:00 | 2023-07-25 | 2023-07-25 06:00 | 2023-07-27 05:59 | 2023-08-01 | 2023-07-29 05:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 27810.27 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1035485 | O.1035485.01 | A.1035485.01.14 | Denison Final Well | DENISON GAS | THE CRESCENT 1, YANDINA 6 | ENSIGN 974 | J.24.096873 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-09-29 | 2024-06-11 03:00 |  | 2024-06-12 02:00 | 2024-06-15 01:59 |  | 2024-06-15 01:59 | Roma WL | KKeese | 2024-06-17 15:22 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 40968.16 | 1 |  | L3 - Full RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1035485 | O.1035485.01 | A.1035485.01.13 | Denison Springton 10 TD | DENISON GAS | SPRINGTON 10, YANDINA 6 | ENSIGN 974 | J.24.053499 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2024-05-29 | 2024-05-28 03:00 |  | 2024-05-29 02:00 | 2024-06-01 01:59 |  | 2024-06-01 01:59 | Roma WL | KKeese | 2024-06-14 11:12 | JEsmeralda |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1035485 | O.1035485.01 | A.1035485.01.09 | Denison Gas 2 | DENISON GAS | METEOR CREEK 1, YANDINA 5 | ENSIGN 974 | J.24.022190 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-05-01 01:00 | 2024-04-30 01:00 |  | 2024-05-01 | 2024-05-02 23:59 |  | 2024-05-05 00:59 | Roma WL | KKeese | 2024-06-05 11:34 | NSchwenke |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 40968.16 | 2 |  | L2 - Shift RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 4 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1035485 | O.1035485.01 | A.1035485.01.12 | May Denison | DENISON GAS | SPRINGTON 10 | ENSIGN 974 | J.24.053498 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-05-24 | 2024-05-23 03:00 | 2024-05-23 | 2024-05-24 02:00 | 2024-05-27 01:59 | 2024-05-28 | 2024-05-27 01:59 | Roma WL | KKeese | 2024-05-30 12:12 | RRanjan3 |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 87108.84 | 2 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1035485 | O.1035485.01 | A.1035485.01.11 | April Denison | DENISON GAS | THE CRESCENT 1, PUNCHBOWL GULLY 17 | ENSIGN 974 | J.24.053497 | RPE | ES-OH-Ops | Low | Operationally Complete | Execute - PSD |  | Design Completed | Not Required | In Progress | 2024-04-13 | 2024-04-10 03:00 | 2024-04-12 | 2024-04-13 02:00 | 2024-04-16 01:59 | 2024-04-29 | 2024-04-16 01:59 | Roma WL | KKeese | 2024-05-16 02:22 | LKenzhegulova |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 72833.01 | 2 |  | L2 - Shift RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1035485 | O.1035485.01 | A.1035485.01.03 | QC-MDT Crescent 1 | DENISON GAS | THE CRESCENT 1 | ENSIGN 974 | J.22.110404 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-06-20 | 2023-06-19 03:00 | 2023-06-19 | 2023-06-20 02:00 | 2023-06-23 01:59 | 2023-06-24 | 2023-06-23 01:59 | Roma WL | MRony2 | 2023-07-03 10:24 | ysaeedabadian |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 71595.19 | 2 |  | L2 - Shift RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1035485 | O.1035485.01 | A.1035485.01.06 | Denison (6 1/8) PEX-HRLA-SSCAN-FMI, MDT_2 | DENISON GAS |  | ENSIGN 974 | J.23.084132 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2023-07-18 | 2023-07-17 01:00 | 2023-07-18 04:00 | 2023-07-18 | 2023-07-19 23:59 | 2023-07-20 04:00 | 2023-07-19 23:59 | Roma WL | KKeese | 2023-06-30 16:58 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 4 |  | L2 - Shift RO |  | 25 | 33.3 | 0 | 25 | 25 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1035485 | O.1035485.01 | A.1035485.01.02 | 2nd Well | DENISON GAS | URANUS 1 | ENSIGN 974 | J.22.110389 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-12 14:00 | 2023-06-11 03:00 | 2023-06-12 | 2023-06-12 16:00 | 2023-06-14 15:59 | 2023-06-15 | 2023-06-14 15:59 | Roma WL | MRony2 | 2023-06-28 09:04 | SAli63 |  | No |  |  |  |  | Jon Lawrie |  | 100418.45 | 2 |  | L0 - No RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1035485 | O.1035485.01 | A.1035485.01.01 | OH_CSG | DENISON GAS |  | ENSIGN 974 | J.22.110399 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2023-05-31 06:00 | 2023-05-30 07:00 |  | 2023-05-31 06:00 | 2023-06-02 05:59 |  | 2023-06-02 05:59 | Roma WL | MRony2 | 2023-05-22 10:37 | KKeese |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 4 |  | L2 - Shift RO |  | 33.3 | 33.3 | 0 | 25 | 27.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1035485 | O.1035485.01 | A.1035485.01.04 | 4th Well | DENISON GAS |  | ENSIGN 974 | J.22.111047 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-28 | 2023-06-27 01:00 |  | 2023-06-28 | 2023-06-29 23:59 |  | 2023-06-29 23:59 | Roma WL | MRony2 | 2023-05-22 10:37 | KKeese |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 4 |  | L2 - Shift RO |  | 25 | 33.3 | 0 | 25 | 25 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1035430 | O.1035430.04 | A.1035430.04.01 | Plug & Abandonment - TUI 2H | MINISTRY OF BUSINESS, INNOVATION AND EMPLOYMENT | TUI 02H | HELIX Q7000 | J.23.008732 | WCF | REM-PA | High | Cancelled | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-04-26 | 2023-06-12 |  | 2023-06-26 | 2023-06-26 23:59 |  | 2023-04-26 23:59 | New Plymouth WS | MAlsaman | 2023-06-15 21:50 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 |  |  |  | 59.4 | 8.3 | 0 | 0 | 26.3 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1035430 | O.1035430.03 | A.1035430.03.01 | Plug & Abandonment - PATEKE 4H | MINISTRY OF BUSINESS, INNOVATION AND EMPLOYMENT | PATEKE 04H | HELIX Q7000 | J.23.008735 | WCF | REM-PA | High | Cancelled | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-04-11 | 2023-06-12 |  | 2023-07-12 | 2023-07-12 23:59 |  | 2023-04-11 23:59 | New Plymouth WS | MAlsaman | 2023-06-15 21:52 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1035430 | O.1035430.02 | A.1035430.02.01 | Plug & Abandonment - Pateke 3H | MINISTRY OF BUSINESS, INNOVATION AND EMPLOYMENT | PATEKE 03H | HELIX Q7000 | J.23.008737 | WCF | REM-PA | High | Cancelled | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-03-19 | 2023-06-12 |  | 2023-07-03 | 2023-07-03 23:59 |  | 2023-03-19 23:59 | New Plymouth WS | MAlsaman | 2023-06-15 21:51 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1035430 | O.1035430.01 | A.1035430.01.02 | Pateke 3H | MINISTRY OF BUSINESS, INNOVATION AND EMPLOYMENT | AMOKURA 2H | HELIX Q7000 | J.23.008734 | WCF | REM-PA, CMT-EQPRNT,CMT-PERS,CMT-MPUMP | High | Cancelled | Close - PSD |  | In Progress | Not Required | In Progress | 2023-04-11 | 2023-06-22 |  | 2023-07-01 | 2023-08-09 23:59 |  | 2023-04-11 23:59 | New Plymouth WS | MAlsaman | 2023-06-15 21:53 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 |  |  |  | 43.8 | 16.7 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1035430 | O.1035430.01 | A.1035430.01.01 | Plug & Abandonment - AMOKURA 2H | MINISTRY OF BUSINESS, INNOVATION AND EMPLOYMENT | AMOKURA 2H | HELIX Q7000 | J.23.008736 | WCF | REM-PA | High | Cancelled | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-03-12 | 2023-06-12 |  | 2023-08-10 | 2023-08-10 23:59 |  | 2023-03-12 23:59 | New Plymouth WS | MAlsaman | 2023-06-15 21:52 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1035094 | O.1035094.01 | A.1035094.01.01 | Design Q3 2022 | ENI AUSTRALIA LIMITED | Black Tip P3 | VALARIS 107 | J.22.109472 | RPI | TCP-RENTAL | Medium | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-09-01 |  | 2022-10-01 | 2023-01-31 23:59 |  |  | APG TS | MSwara | 2023-02-20 15:35 | RWallis |  | No |  |  |  |  | Yudha Swara |  | 0 | 4 |  |  |  | 50 | 33.3 | 100 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TCP - Tubing-Conveyed Perforation
P.1034327 | O.1034327.01 | A.1034327.01.01 | MPBT | BENGAL ENERGY (AUSTRALIA) PTY LTD | Wareena 1 | RIGLESS - AUSTRALIA | J.22.110386 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed |  | 2022-08-17 15:00 |  | 2022-08-18 06:00 | 2022-08-22 05:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 112332.68 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1033338 | O.1033338.02 | A.1033338.02.01 | PNX Campaign | SANTOS LIMITED | WINNINIA NORTH 6, COLOY 1 | Rigless - Australia | J.24.009221 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2024-05-10 | 2024-05-10 |  | 2024-09-01 | 2024-09-21 23:59 |  | 2024-09-21 23:59 | Moomba WL | eismail | 2024-08-27 17:28 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 1 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 2 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.02 | A.1033338.02.02 | CBL Campaign_CCS wells | SANTOS LIMITED | MARABOOKA 19, STRZELECKI 34, STRZELECKI 35, STRZELECKI 36 | Rigless - Australia | J.24.009222 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-07-30 08:00 | 2023-07-30 06:00 | 2023-07-30 | 2023-07-30 08:00 | 2023-07-31 07:59 | 2023-08-01 | 2023-07-31 07:59 | Moomba WL | AMuhammad9 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Abu Dhabi | Mazhar Iqbal |  | 6080.58 | 1 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.02 | A.1033338.02.10 | USIT job rig WD 60 | SANTOS LIMITED | GIDGEALPA 60 | Rigless - Australia | J.23.124789 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-08-20 20:00 | 2023-08-19 16:00 | 2023-08-19 | 2023-08-19 20:00 | 2023-09-02 19:59 | 2023-09-03 | 2023-09-02 19:59 | Moomba WL | NAndilla | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 17800.53 | 1 |  | L3 - Full RO |  | 100 | 100 | 0 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.02 | A.1033338.02.11 | PNX job campaign_Aug | SANTOS LIMITED | NANIMA 2, MARABOOKA 6, WANARA 1, STRZELECKI 10, MARABOOKA 5, WATKINS NORTH 1, WATKINS NORTH 2 | Rigless - Australia | J.23.124933 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-08-21 | 2023-08-20 | 2023-08-20 14:00 | 2023-08-21 | 2023-09-26 23:59 | 2023-09-27 | 2023-09-26 23:59 | Moomba WL | NAndilla | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 12493.18 | 2 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Adel Mohammad Alhashemi | WL Production Services
P.1033338 | O.1033338.02 | A.1033338.02.03 | PNX Well 1 | SANTOS LIMITED |  | Rigless - Australia | J.24.009223 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-06-04 | 2024-06-04 |  | 2024-06-04 | 2024-06-06 23:59 |  | 2024-06-06 23:59 | Moomba WL | AMuhammad9 | 2024-02-06 13:51 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.02 | A.1033338.02.05 | PNX Well 3 | SANTOS LIMITED |  | Rigless - Australia | J.24.050641 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-06-10 | 2024-06-10 |  | 2024-06-10 | 2024-06-12 23:59 |  | 2024-06-12 23:59 | Moomba WL | AManivasagar | 2024-02-06 13:51 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.02 | A.1033338.02.04 | PNX Well 2 | SANTOS LIMITED |  | Rigless - Australia | J.24.009224 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-06-07 | 2024-06-07 |  | 2024-06-07 | 2024-06-09 23:59 |  | 2024-06-09 23:59 | Moomba WL | AMuhammad9 | 2024-02-06 13:51 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.02 | A.1033338.02.09 | PNX Well 7 | SANTOS LIMITED |  | Rigless - Australia | J.24.023013 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-06-22 | 2024-06-22 |  | 2024-08-02 | 2024-08-04 23:59 |  | 2024-06-24 23:59 | Moomba WL | SNour2 | 2023-10-31 14:41 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.02 | A.1033338.02.08 | PNX Well 6 | SANTOS LIMITED |  | Rigless - Australia | J.24.023012 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-06-19 | 2024-06-19 |  | 2024-07-30 | 2024-08-01 23:59 |  | 2024-06-21 23:59 | Moomba WL | SNour2 | 2023-10-31 14:41 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.02 | A.1033338.02.07 | PNX Well 5 | SANTOS LIMITED |  | Rigless - Australia | J.24.023011 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-06-16 | 2024-06-16 |  | 2024-07-27 | 2024-07-29 23:59 |  | 2024-06-18 23:59 | Moomba WL | SNour2 | 2023-10-31 14:41 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.02 | A.1033338.02.06 | PNX Well 4 | SANTOS LIMITED |  | Rigless - Australia | J.24.023010 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-06-13 | 2024-06-13 |  | 2024-07-23 | 2024-07-25 23:59 |  | 2024-06-15 23:59 | Moomba WL | AManivasagar | 2023-10-31 14:41 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.63 | PNX Well 2 | SANTOS LIMITED |  | Rigless - Australia | J.23.041186 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-06-13 | 2023-06-13 |  | 2023-07-24 | 2023-07-26 23:59 |  | 2023-06-15 23:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.60 | Well 11 Q2 2023 | SANTOS LIMITED | LIGER 1 | Rigless - Australia | J.23.041183 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | In Progress | In Progress | 2023-05-31 22:00 | 2023-06-01 |  | 2023-07-10 | 2023-07-12 23:59 |  | 2023-06-03 22:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 54.2 | 25 | 0 | 0 | 23.8 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.62 | PNX Well 1 | SANTOS LIMITED |  | Rigless - Australia | J.23.041185 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-06-10 | 2023-06-10 |  | 2023-07-21 | 2023-07-23 23:59 |  | 2023-06-12 23:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.64 | PNX Well 3 | SANTOS LIMITED |  | Rigless - Australia | J.23.041187 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2023-06-16 | 2023-06-16 |  | 2023-07-27 | 2023-07-29 23:59 |  | 2023-06-18 23:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.75 | Jackson 37 USIT | SANTOS LIMITED | JACKSON 37 | Rigless - Australia | J.24.066437 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-02-29 | 2024-02-29 |  | 2024-02-29 | 2024-03-16 23:59 |  | 2024-03-16 23:59 | Moomba WL | JDagdag | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 100 | 100 | 0 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.01 | MSLC3148 | SANTOS LIMITED | KAPPA 2, KURUNDA 5, BOBS WELL 4, MOOMBA 294, MOOMBA 293, MOOMBA 292, MOOMBA 291, ROTI 5 | Rigless - Australia | J.22.109918 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-15 05:00 | 2023-03-14 18:00 |  | 2023-03-15 06:00 | 2023-04-19 05:59 |  | 2023-04-19 06:59 | Moomba WL | KKeese | 2024-02-05 14:34 | JDagdag |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | 3 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.36 | SCMT U5874 | SANTOS LIMITED | TIRRAWARRA 99, BIG LAKE 162 | Rigless - Australia | J.23.012154 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-09 | 2023-01-09 | 2023-01-09 | 2023-01-09 | 2023-01-11 23:59 | 2023-01-12 01:00 | 2023-01-11 23:59 | Moomba WL | eismail | 2023-08-06 13:41 | JDagdag |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 10539.68 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.74 | PNX Well 7 | SANTOS LIMITED |  | Rigless - Australia | J.23.079999 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-07-18 | 2023-07-20 23:59 | 2023-06-10 | 2023-06-09 23:59 | Moomba WL | KKeese | 2023-07-31 08:09 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.73 | PNX Well 6 | SANTOS LIMITED |  | Rigless - Australia | J.23.079998 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-07-15 | 2023-07-17 23:59 | 2023-06-07 | 2023-06-06 23:59 | Moomba WL | KKeese | 2023-07-31 08:09 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.72 | PNX Well 5 | SANTOS LIMITED |  | Rigless - Australia | J.23.080000 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-07-12 | 2023-07-14 23:59 | 2023-06-04 | 2023-06-03 23:59 | Moomba WL | KKeese | 2023-07-31 08:09 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.71 | PNX Well 4 | SANTOS LIMITED |  | Rigless - Australia | J.23.079997 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-05-29 | 2023-05-29 | 2023-05-29 | 2023-07-08 | 2023-07-10 23:59 | 2023-06-01 | 2023-05-31 23:59 | Moomba WL | KKeese | 2023-07-31 08:09 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.61 | Well 12 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041184 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-06-05 22:00 | 2023-06-06 |  | 2023-06-06 | 2023-06-08 23:59 |  | 2023-06-08 23:59 | Moomba WL | KKeese | 2023-06-13 09:28 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.68 | PNX Well 1 | SANTOS LIMITED |  | Rigless - Australia | J.23.079994 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-05-20 | 2023-05-20 |  | 2023-05-20 | 2023-05-22 23:59 |  | 2023-05-22 23:59 | Moomba WL | KKeese | 2023-05-29 21:00 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.69 | PNX Well 2 | SANTOS LIMITED |  | Rigless - Australia | J.23.079995 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-05-23 | 2023-05-23 |  | 2023-05-23 | 2023-05-25 23:59 |  | 2023-05-25 23:59 | Moomba WL | KKeese | 2023-05-29 21:00 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.70 | PNX Well 3 | SANTOS LIMITED |  | Rigless - Australia | J.23.079996 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-05-26 | 2023-05-26 |  | 2023-05-26 | 2023-05-28 23:59 |  | 2023-05-28 23:59 | Moomba WL | KKeese | 2023-05-29 21:00 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.59 | Well 10 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041179 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-05-23 22:00 | 2023-05-24 |  | 2023-05-24 | 2023-05-26 23:59 |  | 2023-05-26 23:59 | Moomba WL | KKeese | 2023-04-27 18:35 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.58 | Well 9 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041180 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-05-16 22:00 | 2023-05-17 |  | 2023-05-17 | 2023-05-19 23:59 |  | 2023-05-19 23:59 | Moomba WL | KKeese | 2023-04-27 18:35 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.56 | Well 7 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.075449 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-05-06 22:00 | 2023-05-07 |  | 2023-05-07 | 2023-05-09 23:59 |  | 2023-05-09 23:59 | Moomba WL | KKeese | 2023-04-27 18:35 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.57 | Well 8 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041178 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-05-11 22:00 | 2023-05-12 |  | 2023-05-12 | 2023-05-14 23:59 |  | 2023-05-14 23:59 | Moomba WL | KKeese | 2023-04-27 18:35 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.55 | Well 6 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041177 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-04-30 22:00 | 2023-05-01 |  | 2023-05-01 | 2023-05-03 23:59 |  | 2023-05-03 23:59 | Moomba WL | KKeese | 2023-04-27 18:35 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.54 | Well 5 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041020 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-04-25 22:00 | 2023-04-26 |  | 2023-04-26 | 2023-04-28 23:59 |  | 2023-04-28 23:59 | Moomba WL | KKeese | 2023-04-17 09:00 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.53 | Well 4 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041019 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-04-20 22:00 | 2023-04-21 |  | 2023-04-21 | 2023-04-23 23:59 |  | 2023-04-23 23:59 | Moomba WL | KKeese | 2023-04-17 09:00 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.52 | Well 3 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041018 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-04-13 22:00 | 2023-04-14 |  | 2023-04-14 | 2023-04-16 23:59 |  | 2023-04-16 23:59 | Moomba WL | KKeese | 2023-04-17 09:00 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.51 | Well 2 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.066763 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-04-07 22:00 | 2023-04-08 |  | 2023-04-08 | 2023-04-10 23:59 |  | 2023-04-10 23:59 | Moomba WL | KKeese | 2023-04-02 11:43 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.50 | Well 1 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041017 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-04-03 23:00 | 2023-04-04 |  | 2023-04-04 | 2023-04-06 22:59 |  | 2023-04-06 23:59 | Moomba WL | KKeese | 2023-04-02 11:43 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.46 | Q1 2023 Well 12 | SANTOS LIMITED | FORTANNA 2 | Rigless - Australia | J.23.012165 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2023-03-06 22:00 | 2023-03-07 |  | 2023-03-07 | 2023-03-09 23:59 |  | 2023-03-09 21:59 | Moomba WL | eismail | 2023-03-22 08:06 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.49 | Q1 2023 Well 15 | SANTOS LIMITED |  | Rigless - Australia | J.23.012168 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-03-27 22:00 | 2023-03-28 |  | 2023-03-28 | 2023-03-30 23:59 |  | 2023-03-30 23:59 | Moomba WL | eismail | 2023-03-22 08:06 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.48 | Q1 2023 Well 14 | SANTOS LIMITED |  | Rigless - Australia | J.23.012167 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-03-18 22:00 | 2023-03-19 |  | 2023-03-19 | 2023-03-21 23:59 |  | 2023-03-21 23:59 | Moomba WL | eismail | 2023-03-22 08:06 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.47 | SCMT January | SANTOS LIMITED | TIRRAWARRA 99, BIG LAKE 162 | Rigless - Australia | J.23.012166 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-03-12 22:00 | 2023-03-13 |  | 2023-03-13 | 2023-03-15 23:59 |  | 2023-03-15 23:59 | Moomba WL | eismail | 2023-03-22 08:06 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 12542.22 | 3 |  | L3 - Full RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.21 | Q4 2022 Well 6 | SANTOS LIMITED |  | Rigless - Australia | J.22.110074 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-10-31 22:00 | 2022-11-01 |  | 2022-11-01 | 2022-11-03 23:59 |  | 2022-11-03 23:59 | Moomba WL | KKeese | 2023-03-07 18:38 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.22 | Q4 2022 Well 7 | SANTOS LIMITED |  | Rigless - Australia | J.22.110075 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-11-06 22:00 | 2022-11-07 |  | 2022-11-07 | 2022-11-09 23:59 |  | 2022-11-09 23:59 | Moomba WL | KKeese | 2023-03-07 18:38 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.23 | Q4 2022 Well 8 | SANTOS LIMITED |  | Rigless - Australia | J.22.110076 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-11-11 22:00 | 2022-11-12 |  | 2022-11-12 | 2022-11-14 23:59 |  | 2022-11-14 23:59 | Moomba WL | KKeese | 2023-03-07 18:38 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.24 | Q4 2022 Well 9 | SANTOS LIMITED |  | Rigless - Australia | J.22.110077 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-11-16 22:00 | 2022-11-17 |  | 2022-11-17 | 2022-11-19 23:59 |  | 2022-11-19 23:59 | Moomba WL | KKeese | 2023-03-07 18:38 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.26 | Q4 2022 Well 11 | SANTOS LIMITED |  | Rigless - Australia | J.22.110079 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-11-25 22:00 | 2022-11-26 |  | 2022-11-26 | 2022-11-28 23:59 |  | 2022-11-28 23:59 | Moomba WL | KKeese | 2023-03-07 18:37 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.30 | Q4 2022 Well 15 | SANTOS LIMITED |  | Rigless - Australia | J.22.110083 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-12-18 22:00 | 2022-12-19 |  | 2022-12-19 | 2022-12-21 23:59 |  | 2022-12-21 23:59 | Moomba WL | KKeese | 2023-03-07 18:31 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.29 | Q4 2022 Well 14 | SANTOS LIMITED |  | Rigless - Australia | J.22.110082 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-12-13 22:00 | 2022-12-14 |  | 2022-12-14 | 2022-12-16 23:59 |  | 2022-12-16 23:59 | Moomba WL | KKeese | 2023-03-07 18:31 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.27 | Q4 2022 Well 12 | SANTOS LIMITED |  | Rigless - Australia | J.22.110080 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-12-01 22:00 | 2022-12-02 |  | 2022-12-02 | 2022-12-04 23:59 |  | 2022-12-04 23:59 | Moomba WL | KKeese | 2023-03-07 18:30 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.43 | Q1 2023 Well 09 | SANTOS LIMITED |  | Rigless - Australia | J.23.012162 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-02-20 22:00 | 2023-02-21 |  | 2023-02-21 | 2023-02-23 23:59 |  | 2023-02-23 23:59 | Moomba WL | eismail | 2023-03-07 18:30 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.44 | Q1 2023 Well 10 | SANTOS LIMITED |  | Rigless - Australia | J.23.012163 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-02-25 22:00 | 2023-02-26 |  | 2023-02-26 | 2023-02-28 23:59 |  | 2023-02-28 23:59 | Moomba WL | eismail | 2023-03-07 18:26 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.40 | Q1 2023 Well 06 | SANTOS LIMITED |  | Rigless - Australia | J.23.012159 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-01-31 22:00 | 2023-02-01 |  | 2023-02-01 | 2023-02-03 23:59 |  | 2023-02-03 23:59 | Moomba WL | eismail | 2023-03-07 18:26 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.39 | Q1 2023 Well 05 | SANTOS LIMITED |  | Rigless - Australia | J.23.012158 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-01-26 22:00 | 2023-01-27 |  | 2023-01-27 | 2023-01-29 23:59 |  | 2023-01-29 23:59 | Moomba WL | eismail | 2023-03-07 18:23 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.38 | Q1 2023 Well 04 | SANTOS LIMITED |  | Rigless - Australia | J.23.012157 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-01-20 22:00 | 2023-01-21 |  | 2023-01-21 | 2023-01-23 23:59 |  | 2023-01-23 23:59 | Moomba WL | eismail | 2023-03-07 18:23 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.37 | Q1 2023 Well 03 | SANTOS LIMITED |  | Rigless - Australia | J.23.012156 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-01-14 22:00 | 2023-01-15 |  | 2023-01-15 | 2023-01-17 23:59 |  | 2023-01-17 23:59 | Moomba WL | eismail | 2023-03-07 18:23 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.35 | Q1 2023 Well 01 | SANTOS LIMITED |  | Rigless - Australia | J.22.122249 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-12-31 22:00 | 2023-01-01 |  | 2023-01-01 | 2023-01-03 23:59 |  | 2023-01-03 23:59 | Moomba WL | eismail | 2023-03-07 18:19 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.65 | PNX Well 4 | SANTOS LIMITED |  | Rigless - Australia | J.23.045794 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-07-01 | 2023-07-01 |  | 2023-07-01 | 2023-07-03 23:59 |  | 2023-07-03 23:59 | Moomba WL | KKeese | 2023-03-07 11:01 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.66 | PNX Well 5 | SANTOS LIMITED |  | Rigless - Australia | J.23.045795 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2023-07-05 | 2023-07-05 |  | 2023-07-05 | 2023-07-07 23:59 |  | 2023-07-07 23:59 | Moomba WL | KKeese | 2023-03-07 11:01 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.67 | Fortanna 2 | SANTOS LIMITED | FORTANNA 2 | Rigless - Australia | J.23.049297 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-03-05 | 2023-03-05 |  | 2023-03-05 | 2023-03-09 23:59 |  | 2023-03-09 23:59 | Moomba WL | YPouryan | 2023-03-06 11:25 | YPouryan |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 75 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.45 | Europa 1 CBL | SANTOS LIMITED | EUROPA 1 | Rigless - Australia | J.23.012164 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-03-01 | 2023-03-01 |  | 2023-03-01 | 2023-03-03 23:59 |  | 2023-03-03 23:59 | Moomba WL | eismail | 2023-03-01 16:15 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 1 |  | L3 - Full RO |  | 58.3 | 16.7 | 0 | 100 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.42 | Tirra_BigLake_SCMT | SANTOS LIMITED | TIRRAWARRA 101, TIRRAWARRA 102, BIG LAKE 163, BIG LAKE 164 | Rigless - Australia | J.23.012161 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-13 | 2023-02-13 |  | 2023-02-13 | 2023-02-20 23:59 |  | 2023-02-20 23:59 | Moomba WL | eismail | 2023-02-25 14:23 | YPouryan |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.41 | Dullingari 42DW1 - Perf | SANTOS LIMITED | DULLINGARI 42 | Rigless - Australia | J.23.012160 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-12 10:00 | 2023-02-12 06:00 |  | 2023-02-12 12:00 | 2023-02-15 11:59 |  | 2023-02-15 11:59 | Moomba WL | eismail | 2023-02-11 15:16 | MAlhashemi |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.28 | Q4 2022 Well 13 | SANTOS LIMITED | BIG LAKE 160, BIG LAKE 21 | Rigless - Australia | J.22.110081 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-12 08:00 | 2022-12-07 |  | 2022-12-12 08:00 | 2022-12-27 07:59 |  | 2022-12-27 07:59 | Moomba WL | KKeese | 2022-12-21 15:09 | YPouryan |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO | [7 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.25 | Swan Lake 11 | SANTOS LIMITED | SWAN LAKE 11, QUASAR 2, FAVELA 001, DILCHEE 6 | Rigless - Australia | J.22.110078 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-20 | 2022-11-20 |  | 2022-11-20 | 2022-12-03 23:59 |  | 2022-12-04 00:59 | Moomba WL | KKeese | 2022-12-05 11:49 | ASamokhin |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 3 |  |  |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.34 | Ragno 2 | SANTOS LIMITED | RAGNO 2, RAGNO 4, MARSILEA 002, SECCANTE 8, LANE 1, RAFFLE 1, DULLINGARI NORTH 8, BIG LAKE 77 | Rigless - Australia | J.22.119550 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-24 | 2022-10-24 |  | 2022-10-24 | 2022-11-12 23:59 |  | 2022-11-12 23:59 | Moomba WL | NAndilla | 2022-11-25 02:14 | ssultan |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.31 | Woolkina 3 | SANTOS LIMITED | WOOLKINA 003 | Rigless - Australia | J.22.117169 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2022-10-19 | 2022-10-18 |  | 2022-10-19 | 2022-10-24 23:59 |  | 2022-10-24 23:59 | Moomba WL | NAndilla | 2022-10-23 16:11 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 25306.82 | 6 |  | L0 - No RO |  | 79.2 | 58.3 | 0 | 0 | 41.3 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.32 | Tirrawarra 47 | SANTOS LIMITED | TIRRAWARRA 47 | Rigless - Australia | J.22.118256 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Not Started | In Progress | 2022-10-20 | 2022-10-20 |  | 2022-10-20 | 2022-10-24 23:59 |  | 2022-10-24 23:59 | Moomba WL | NAndilla | 2022-10-23 15:50 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 11306.3 | 2 |  | L0 - No RO |  | 54.2 | 25 | 0 | 0 | 23.8 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.33 | Tindilpie 12 | SANTOS LIMITED |  | Rigless - Australia | J.22.118697 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Not Started | In Progress | 2022-10-19 | 2022-10-19 |  | 2022-10-19 | 2022-10-23 23:59 |  | 2022-10-23 23:59 | Moomba WL | NAndilla | 2022-10-23 15:49 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 45.8 | 25 | 0 | 0 | 21.3 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.20 | Q4 2022 Well 5 | SANTOS LIMITED |  | Rigless - Australia | J.22.110073 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-10-17 22:00 | 2022-10-18 |  | 2022-10-18 | 2022-10-20 23:59 |  | 2022-10-20 23:59 | Moomba WL | KKeese | 2022-10-03 12:38 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.19 | Q4 2022 Well 4 | SANTOS LIMITED |  | Rigless - Australia | J.22.110071 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-10-12 22:00 | 2022-10-13 |  | 2022-10-13 | 2022-10-15 23:59 |  | 2022-10-15 23:59 | Moomba WL | KKeese | 2022-10-03 12:38 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.18 | Q4 2022 Well 3 | SANTOS LIMITED |  | Rigless - Australia | J.22.110070 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-10-07 22:00 | 2022-10-08 |  | 2022-10-08 | 2022-10-10 23:59 |  | 2022-10-10 23:59 | Moomba WL | KKeese | 2022-10-03 12:37 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.17 | Q4 2022 Well 2 | SANTOS LIMITED |  | Rigless - Australia | J.22.110069 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-10-01 23:00 | 2022-10-02 |  | 2022-10-02 | 2022-10-05 00:59 |  | 2022-10-05 00:59 | Moomba WL | KKeese | 2022-10-03 12:37 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.16 | Q4 2022 Well 1 | SANTOS LIMITED |  | Rigless - Australia | J.22.110068 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-09-26 23:00 | 2022-09-27 |  | 2022-09-27 | 2022-09-29 23:59 |  | 2022-09-30 00:59 | Moomba WL | KKeese | 2022-10-03 12:37 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.15 | Well 15 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109932 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-09-20 23:00 | 2022-09-21 |  | 2022-09-21 | 2022-09-23 23:59 |  | 2022-09-24 00:59 | Moomba WL | KKeese | 2022-10-03 12:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.14 | Well 14 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109931 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-09-17 23:00 | 2022-09-18 |  | 2022-09-18 | 2022-09-20 23:59 |  | 2022-09-21 00:59 | Moomba WL | KKeese | 2022-10-03 12:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.13 | Well 13 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109930 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-09-13 23:00 | 2022-09-14 |  | 2022-09-14 | 2022-09-16 23:59 |  | 2022-09-17 00:59 | Moomba WL | KKeese | 2022-10-03 12:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.12 | Well 12 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109929 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-09-08 23:00 | 2022-09-09 |  | 2022-09-09 | 2022-09-11 23:59 |  | 2022-09-12 00:59 | Moomba WL | KKeese | 2022-10-03 12:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.11 | Well 11 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109928 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-09-04 23:00 | 2022-09-05 |  | 2022-09-05 | 2022-09-07 23:59 |  | 2022-09-08 00:59 | Moomba WL | KKeese | 2022-10-03 12:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.10 | Well 10 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109927 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-08-20 23:00 | 2022-08-21 |  | 2022-08-21 | 2022-08-23 23:59 |  | 2022-08-24 00:59 | Moomba WL | KKeese | 2022-10-03 12:23 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.09 | Well 9 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109926 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-08-14 23:00 | 2022-08-15 |  | 2022-08-15 | 2022-08-17 23:59 |  | 2022-08-18 00:59 | Moomba WL | KKeese | 2022-10-03 12:23 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.08 | Well 8 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109925 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-08-07 23:00 | 2022-08-08 |  | 2022-08-08 | 2022-08-10 23:59 |  | 2022-08-11 00:59 | Moomba WL | KKeese | 2022-10-03 12:23 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.07 | Meranji 16_CBL Job | SANTOS LIMITED | Meranji 16 | Rigless - Australia | J.22.109924 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-08-01 23:00 | 2022-08-02 |  | 2022-08-02 | 2022-08-04 23:59 |  | 2022-08-04 22:59 | Moomba WL | KKeese | 2022-10-03 12:23 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.06 | Well 6 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109923 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-07-26 23:00 | 2022-07-27 |  | 2022-07-27 | 2022-07-29 23:59 |  | 2022-07-30 00:59 | Moomba WL | KKeese | 2022-10-03 12:23 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.05 | Well 5 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109922 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-07-22 23:00 | 2022-07-23 |  | 2022-07-23 | 2022-07-25 23:59 |  | 2022-07-26 00:59 | Moomba WL | KKeese | 2022-10-03 12:23 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.04 | Well 4 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109921 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-07-18 23:00 | 2022-07-19 |  | 2022-07-19 | 2022-07-21 23:59 |  | 2022-07-22 00:59 | Moomba WL | KKeese | 2022-10-03 12:23 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.03 | Well 3 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109920 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-07-15 23:00 | 2022-07-16 |  | 2022-07-16 | 2022-07-18 23:59 |  | 2022-07-19 00:59 | Moomba WL | KKeese | 2022-10-03 12:23 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033338 | O.1033338.01 | A.1033338.01.02 | Well 2 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109919 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-07-10 23:00 | 2022-07-11 |  | 2022-07-11 | 2022-07-13 23:59 |  | 2022-07-14 00:59 | Moomba WL | KKeese | 2022-10-03 12:23 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033328 | O.1033328.01 | A.1033328.01.06 | Well-3_TD | DEPARTMENT OF REGIONAL NSW - RESOURCES | Hampton 1 | EASTERNWELL 101 | J.23.021985 | RPE | ES-CH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-01-31 23:00 | 2023-01-29 01:00 |  | 2023-02-01 | 2023-02-04 23:59 |  | 2023-03-01 | Roma WL | MRony2 | 2023-02-27 16:27 | ysaeedabadian |  | No |  |  |  |  | Jon Lawrie |  | 92268.86 | 5 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1033328 | O.1033328.01 | A.1033328.01.04 | Well-1_TD | DEPARTMENT OF REGIONAL NSW - RESOURCES | Coona Coona 2 | EASTERNWELL 101 | J.22.136648 | RPE | ES-CH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-28 | 2022-11-27 01:00 |  | 2022-11-28 | 2022-12-01 23:59 |  | 2022-12-02 00:59 | Roma WL | MRony2 | 2023-02-04 16:07 | SSabatini |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 63325.54 | 4 |  | L2 - Shift RO |  | 66.7 | 33.3 | 0 | 100 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1033328 | O.1033328.01 | A.1033328.01.02 | Well-2_ Intermediate | DEPARTMENT OF REGIONAL NSW - RESOURCES | COONA COONA 1 | EASTERNWELL 101 | J.22.136647 | RPE | ES-CH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-12-11 01:00 | 2022-12-08 01:00 |  | 2022-12-11 | 2022-12-14 23:59 |  | 2022-12-15 00:59 | Roma WL | MRony2 | 2023-02-04 14:36 | SSabatini |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 18526.31 | 1 |  | L3 - Full RO |  | 66.7 | 16.7 | 0 | 100 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1033328 | O.1033328.01 | A.1033328.01.03 | Well-3_Intermediate | DEPARTMENT OF REGIONAL NSW - RESOURCES | Hampton 1 | EASTERNWELL 101 | J.23.021983 | RPE | ES-CH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-01-19 23:00 | 2023-01-17 01:00 |  | 2023-01-20 | 2023-01-23 23:59 |  | 2023-01-23 23:59 | Roma WL | MRony2 | 2023-01-26 09:38 | PLima7 |  | No |  |  |  |  | Jon Lawrie |  | 40059.4 | 1 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1033328 | O.1033328.01 | A.1033328.01.05 | Well-2_TD | DEPARTMENT OF REGIONAL NSW - RESOURCES | COONA COONA 1 | EASTERNWELL 101 | J.23.021984 | RPE | ES-CH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-12-30 01:00 | 2022-12-27 01:00 |  | 2022-12-30 | 2023-01-05 23:59 |  | 2023-01-06 00:59 | Roma WL | MRony2 | 2023-01-08 19:53 | SLie4 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 224132.73 | 3 |  | L2 - Shift RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1033328 | O.1033328.01 | A.1033328.01.01 | Well 1_ Intermediate | DEPARTMENT OF REGIONAL NSW - RESOURCES | Coona Coona 2 | EASTERNWELL 101 | J.22.136646 | RPE | ES-CH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-09-03 | 2022-08-31 |  | 2022-09-03 | 2022-09-14 23:59 |  | 2022-09-14 23:59 | Roma WL | MRony2 | 2022-12-28 12:04 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 45323.44 | 1 |  |  |  | 66.7 | 50 | 0 | 50 | 50 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1033320 | O.1033320.03 | A.1033320.03.01 | SCMT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 378, COMBABULA 380, COMBABULA 399, COMBABULA 401, COMBABULA 402, COMBABULA 424, COMBABULA 492, COMBABULA 494, REEDY CREEK 105, REEDY CREEK 284, REEDY CREEK 75, COMBABULA 375, COMBABULA 376, COMBABULA 377, COMBABULA 379, COMBABULA 396, COMBABULA 398, COMBABULA 420, COMBABULA 421, COMBABULA 422, COMBABULA 491, COMBABULA 493, REEDY CREEK 72 | Rigless - Australia | J.22.110414 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2022-08-17 06:00 | 2022-08-16 |  | 2022-08-17 06:00 | 2022-09-01 23:59 |  | 2022-09-01 23:59 | Roma WL | MRony2 | 2023-02-04 11:36 | SSabatini |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 7 |  | L3 - Full RO |  | 75 | 66.7 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1033320 | O.1033320.03 | A.1033320.03.02 | SCMT_Oct22 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | Rigless - Australia | J.22.111046 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-10-09 |  | 2022-10-10 06:00 | 2022-10-25 23:59 |  |  | Roma WL | JEsmeralda | 2022-10-03 15:39 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 7 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1033320 | O.1033320.02 | A.1033320.02.01 | DFIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | Rigless - Australia | J.22.111045 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-09-14 |  | 2022-09-15 | 2022-09-20 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:39 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1033320 | O.1033320.01 | A.1033320.01.01 | WAP | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | Rigless - Australia | J.22.111044 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2022-11-01 |  | 2022-11-01 06:00 | 2022-11-23 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:38 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 30 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1033319 | O.1033319.01 | A.1033319.01.07 | 7th well | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.22.111043 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-10-13 01:00 |  | 2022-10-14 01:00 | 2022-10-17 00:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:38 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1033319 | O.1033319.01 | A.1033319.01.06 | 6th well | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.22.111042 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-10-01 |  | 2022-10-02 | 2022-10-05 00:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:38 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1033319 | O.1033319.01 | A.1033319.01.04 | 4th Well | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.22.110375 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-09-20 |  | 2022-09-21 | 2022-09-23 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1033319 | O.1033319.01 | A.1033319.01.08 | 8th Well | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.22.110371 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-10-20 01:00 |  | 2022-10-21 01:00 | 2022-10-24 00:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1033319 | O.1033319.01 | A.1033319.01.02 | 2nd well | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.22.110367 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-09-11 |  | 2022-09-12 | 2022-09-14 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1033319 | O.1033319.01 | A.1033319.01.09 | 9th well | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.22.110365 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-10-27 01:00 |  | 2022-10-28 01:00 | 2022-10-31 00:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1033319 | O.1033319.01 | A.1033319.01.05 | 5th Well | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.22.110364 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-09-26 |  | 2022-09-27 | 2022-09-29 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1033319 | O.1033319.01 | A.1033319.01.03 | 3rd well | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.22.110361 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-09-15 |  | 2022-09-16 | 2022-09-18 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1033319 | O.1033319.01 | A.1033319.01.01 | 1st Wll | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.22.110359 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-09-06 |  | 2022-09-07 | 2022-09-09 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1033318 | O.1033318.21 | A.1033318.21.03 | Santos Dedicated SWPT Dec 2025 | SANTOS LIMITED |  | RIGLESS - AUSTRALIA | J.26.022223 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-11-26 | 2026-11-26 | 2026-11-26 01:00 | 2026-11-26 | 2026-12-25 23:59 | 2026-12-26 01:00 | 2026-12-25 23:59 | Roma WL | CKok3 | 2025-11-26 16:18 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.21 | A.1033318.21.02 | Santos Dedicated SWPT Nov 2025 | SANTOS LIMITED |  | RIGLESS - AUSTRALIA | J.26.022222 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-10-26 | 2026-10-26 | 2026-10-26 01:00 | 2026-10-26 | 2026-11-24 23:59 | 2026-11-25 01:00 | 2026-11-24 23:59 | Roma WL | CKok3 | 2025-11-26 16:17 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.21 | A.1033318.21.01 | Santos Dedicated SWPT Oct 2025 | SANTOS LIMITED |  | RIGLESS - AUSTRALIA | J.26.022221 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-09-26 | 2026-09-26 | 2026-09-26 | 2026-09-26 | 2026-10-25 23:59 | 2026-10-26 01:00 | 2026-10-26 00:59 | Roma WL | CKok3 | 2025-11-26 16:17 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.20 | A.1033318.20.03 | Santos Dedicated SWPT Sep 2025 | SANTOS LIMITED |  | RIGLESS - AUSTRALIA | J.26.022220 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-09-24 23:59 | 2026-09-25 | 2026-09-24 23:59 | Roma WL | CKok3 | 2025-11-26 16:16 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.20 | A.1033318.20.02 | Santos Dedicated SWPT Aug 2025 | SANTOS LIMITED |  | RIGLESS - AUSTRALIA | J.26.022219 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-07-26 | 2026-07-26 | 2026-07-26 | 2026-07-26 | 2026-08-24 23:59 | 2026-08-25 | 2026-08-24 23:59 | Roma WL | CKok3 | 2025-11-26 16:14 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.20 | A.1033318.20.01 | Santos Dedicated SWPT Jul 2025 | SANTOS LIMITED |  | RIGLESS - AUSTRALIA | J.26.022218 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-07-25 23:59 | 2026-07-26 | 2026-07-25 23:59 | Roma WL | CKok3 | 2025-11-26 16:14 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.19 | A.1033318.19.03 | Santos Dedicated SWPT Jun 2025 | SANTOS LIMITED |  | RIGLESS - AUSTRALIA | J.26.022217 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-06-24 23:59 | 2026-06-25 | 2026-06-24 23:59 | Roma WL | CKok3 | 2025-11-26 16:13 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.19 | A.1033318.19.02 | Santos Dedicated SWPT May 2025 | SANTOS LIMITED |  | RIGLESS - AUSTRALIA | J.26.022216 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-04-26 | 2026-04-26 | 2026-04-26 | 2026-04-26 | 2026-05-25 23:59 | 2026-05-26 | 2026-05-25 23:59 | Roma WL | CKok3 | 2025-11-26 16:13 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.19 | A.1033318.19.01 | Santos Dedicated SWPT Apr 2025 | SANTOS LIMITED |  | RIGLESS - AUSTRALIA | J.26.022215 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-03-26 | 2026-03-26 | 2026-03-26 01:00 | 2026-03-26 | 2026-04-24 23:59 | 2026-04-25 | 2026-04-24 22:59 | Roma WL | CKok3 | 2025-11-26 16:13 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.18 | A.1033318.18.03 | Santos Dedicated SWPT Mar 2025 | SANTOS LIMITED |  | RIGLESS - AUSTRALIA | J.26.022214 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-02-26 | 2026-02-26 | 2026-02-26 01:00 | 2026-02-26 | 2026-03-27 23:59 | 2026-03-28 01:00 | 2026-03-27 23:59 | Roma WL | CKok3 | 2025-11-26 16:12 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.18 | A.1033318.18.02 | Santos Dedicated SWPT Feb 2025 | SANTOS LIMITED |  | RIGLESS - AUSTRALIA | J.26.022213 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-01-26 | 2026-01-26 | 2026-01-26 01:00 | 2026-01-26 | 2026-02-24 23:59 | 2026-02-25 01:00 | 2026-02-24 23:59 | Roma WL | CKok3 | 2025-11-26 16:12 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.18 | A.1033318.18.01 | Santos Dedicated SWPT Jan 2025 | SANTOS LIMITED |  | RIGLESS - AUSTRALIA | J.25.181380 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2025-12-26 | 2025-12-26 | 2025-12-26 01:00 | 2025-12-26 | 2026-01-24 23:59 | 2026-01-25 01:00 | 2026-01-24 23:59 | Roma WL | CKok3 | 2025-11-26 16:11 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.17 | A.1033318.17.02 | Santos Dedicated SWPT Nov 2025 | SANTOS LIMITED | FV08-19-2, FV13-97-2, FV17-91-1, FV18-177-1, FV18-177-2, FV18-178-1, RM13-87-2, GLENELG 5, GLENELG 6, FV18-179-1, FV08-30-2 | RIGLESS - AUSTRALIA | J.25.101996 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Not Started | 2024-01-09 22:00 | 2025-10-27 | 2025-11-01 | 2025-10-27 | 2025-12-30 23:59 | 2026-01-01 | 2025-12-30 23:59 | Roma WL | CKok3 | 2025-11-30 11:47 | MEketone |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L3 - Full RO |  | 83.3 | 100 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.17 | A.1033318.17.03 | Santos Dedicated SWPT Dec 2025 | SANTOS LIMITED | FV08-30-2 | RIGLESS - AUSTRALIA | J.25.101998 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | Not Started | 2025-11-27 | 2025-11-27 | 2025-11-30 | 2025-11-27 | 2025-12-26 23:59 | 2025-12-31 | 2025-12-26 23:59 | Roma WL | CKok3 | 2025-11-30 11:41 | MEketone |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 66.7 | 66.7 | 0 | 25 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.17 | A.1033318.17.01 | Santos Dedicated SWPT Oct 2025 | SANTOS LIMITED | FV18-149-1, FV18-149-2, KELSALL 27, KELSALL 28, KELSALL 31, FV17-92-1, FV17-91-1, FV13-111-1, FV13-113-1, KELSALL 39A, FV13-97-1, FV13-97-2, KELSALL 29, KELSALL 30 | RIGLESS - AUSTRALIA | J.25.101997 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-10-29 23:59 | 2025-10-30 01:00 | 2025-10-30 00:59 | Roma WL | CKok3 | 2025-10-24 18:49 | SAli112 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 91.7 | 83.3 | 100 | 83.3 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.16 | A.1033318.16.03 | Santos Dedicated SWPT Sep 2025 | SANTOS LIMITED | FV13-112-1, FV18-146-1, FV18-156-3, FV18-144-1, FV13-109-1, FV18-145-1, FV08-35-2, KELSALL 39A | RIGLESS - AUSTRALIA | J.25.101995 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-09-25 23:59 | 2025-09-26 | 2025-09-25 23:59 | Roma WL | CKok3 | 2025-09-26 11:47 | RDell |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.16 | A.1033318.16.01 | Santos Dedicated SWPT July 2025 | SANTOS LIMITED | FV13-105-1, FV13-108-1, FV08-35-1, FV13-107-1, FV08-36-1, FV10-06-21, FV18-154-1, FV18-159-1, FV08-25-1, FV18-151-1, FV08-35-2, FV08-25-2 | RIGLESS - AUSTRALIA | J.25.101993 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2025-03-01 | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-07-25 23:59 | 2025-07-26 | 2025-07-25 23:59 | Roma WL | CKok3 | 2025-09-05 14:14 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.16 | A.1033318.16.02 | Santos Dedicated SWPT Aug 2025 | SANTOS LIMITED | FV18-152-1, FV18-153-1, FV13-110-1, FV18-156-1, FV18-146-1, FV18-156-2, FV18-156-3, FV18-147-1, FV18-148-1, FV18-150-1 | RIGLESS - AUSTRALIA | J.25.101994 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-05-01 23:00 | 2025-07-27 | 2025-07-27 | 2025-07-27 | 2025-08-25 23:59 | 2025-08-26 | 2025-08-25 23:59 | Roma WL | CKok3 | 2025-08-28 21:23 | SAli112 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 4 |  | L3 - Full RO |  | 91.7 | 83.3 | 100 | 100 | 92.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.15 | A.1033318.15.05 | Santos Dedicated SWPT Jul 2025 | SANTOS LIMITED |  | Rigless - Australia | J.25.070972 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-30 23:59 | 2025-07-31 | 2025-07-30 23:59 | Roma WL | JEsmeralda | 2025-07-07 18:39 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.15 | A.1033318.15.03 | Santos Dedicated SWPT Jun 2025 | SANTOS LIMITED | FV13-96-2, FV13-96-1, FV08-36-1, FV13-106-1, FV13-100-1 | Rigless - Australia | J.25.058959 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-30 23:59 | 2025-07-01 | 2025-06-30 23:59 | Roma WL | JEsmeralda | 2025-07-02 12:00 | handoko |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L3 - Full RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 3 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.15 | A.1033318.15.04 | Santos Dedicated SWPT Apr 2025 | SANTOS LIMITED | FV11-109-21, FV13-96-2, FV08-24-1, FV08-36-1, FV08-37-1, FV08-37-2, FV08-36-2, FV13-100-1, FV13-96-1, FV13-102-1 | Rigless - Australia | J.25.070971 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-04-22 | 2025-04-22 | 2025-02-15 | 2025-04-22 | 2025-04-29 23:59 | 2025-05-25 02:00 | 2025-05-23 01:59 | Roma WL | CKok3 | 2025-06-15 15:19 | RDell |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 83.3 | 77.5 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.15 | A.1033318.15.02 | Santos Dedicated SWPT May 2025 | SANTOS LIMITED | FV08-36-1, FV08-37-1, FV13-102-1, FV08-37-2, FV13-96-1, FV13-103-1, FV13-104-1 | Rigless - Australia | J.25.058958 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-30 23:59 | 2025-05-31 | 2025-05-30 23:59 | Roma WL | JEsmeralda | 2025-06-03 18:05 | SAli112 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 100 | 100 | 0 | 100 | 90 |  | 3 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.15 | A.1033318.15.01 | Santos Dedicated SWPT Mar 2025 | SANTOS LIMITED | FV11-109-21, FV10-47-21, FV13-95-1, FV13-95-2 | Rigless - Australia | J.25.058932 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-03-04 | 2025-03-04 | 2025-01-07 | 2025-03-04 | 2025-04-03 23:59 | 2025-04-06 02:00 | 2025-04-04 01:59 | Roma WL | JEsmeralda | 2025-03-22 16:41 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 3 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.14 | A.1033318.14.01 | Dedicated SWPT_Oct24 | SANTOS LIMITED |  | Rigless - Australia | J.25.015290 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-04-04 01:00 | 2025-04-04 01:00 |  | 2025-04-04 01:00 | 2025-05-09 23:59 |  | 2025-05-09 23:59 | Roma WL | KKeese | 2025-02-26 14:35 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 0 |  | L3 - Full RO |  | 41.7 | 33.3 | 0 | 25 | 30 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.14 | A.1033318.14.03 | Dedicated SWPT_Nov24 | SANTOS LIMITED | HARDENLEY 4, HARDENLEY 7, HARDENLEY 12, HARDENLEY 33, HARDENLEY 34, HARDENLEY 5, HARDENLEY 6, HARDENLEY 39, HARDENLEY 40, FV18-93-2, HARDENLEY 41, FV18-90-1, FV18-100-1 | Rigless - Australia | J.24.171680 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-10-26 | 2024-10-25 |  | 2024-10-25 | 2024-11-25 23:59 |  | 2024-11-25 22:59 | Roma WL | JEsmeralda | 2024-12-06 18:31 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 50 | 60 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.14 | A.1033318.14.02 | SWPT October | SANTOS LIMITED | HARDENLEY 4, HARDENLEY 7, HARDENLEY 12, HARDENLEY 33, HARDENLEY 34, HARDENLEY 5, HARDENLEY 6, HARDENLEY 39, HARDENLEY 40, FV18-93-2, HARDENLEY 41, FV18-90-1, HARDENLEY 44, HARDENLEY 35, HARDENLEY 21, FV18-93-1, FV18-94-1, FV18-100-1, AVALON 35, AVALON 36, GLEN EVIS 13, FV18-84-1, FV18-84-3, FV18-84-2, HARDENLEY 43, HARDENLEY-13, GLEN EVIS 11, HARDENLEY 8 | Rigless - Australia | J.24.161630 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2024-10-01 | 2024-09-30 |  | 2024-09-30 | 2024-11-19 23:59 |  | 2024-11-19 23:59 | Roma WL | KKeese | 2024-11-22 07:15 | SAli112 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.14 | A.1033318.14.04 | Santos SWPT Dedicated Nov24 | SANTOS LIMITED | HARDENLEY 4, HARDENLEY 7, HARDENLEY 12, HARDENLEY 33, HARDENLEY 34, HARDENLEY 5, HARDENLEY 6, HARDENLEY 39, HARDENLEY 40, FV18-93-2, HARDENLEY 41, FV18-90-1, HARDENLEY 44, HARDENLEY 35, HARDENLEY 21, FV18-93-1, FV18-94-1, FV18-100-1, AVALON 35, AVALON 36, GLEN EVIS 13, FV18-84-1, FV18-84-3, FV18-84-2, HARDENLEY 43, HARDENLEY-13 | Rigless - Australia | J.24.179274 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2024-11-05 |  | 2024-11-05 | 2024-12-15 23:59 |  |  | Roma WL | JEsmeralda | 2024-11-07 22:45 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 |  |  | L3 - Full RO |  | 16.7 | 33.3 | 0 | 25 | 22.5 |  | 0 | [7 empty] | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.13 | A.1033318.13.01 | June Santos Dedicated SWPT | SANTOS LIMITED |  | Rigless - Australia | J.26.000420 | RPI | PS-WL-NO | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2026-04-11 07:00 | 2026-04-11 01:00 | 2026-04-11 01:00 | 2026-04-11 07:00 | 2026-05-05 23:59 | 2026-05-06 | 2026-05-05 23:59 | Roma WL | KKeese | 2025-07-11 09:45 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 50 | 66.7 | 100 | 75 | 67.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.13 | A.1033318.13.04 | Santos Dedicated SWPT Mar 2025 | SANTOS LIMITED |  | Rigless - Australia | J.25.008272 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2025-02-01 | 2025-02-24 | 2025-02-24 | 2025-02-24 00:10 | 2025-03-27 00:09 | 2025-03-28 | 2025-03-21 | Roma WL | KKeese | 2025-07-02 15:06 | ESchmidtke |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 3 |  | L3 - Full RO |  | 75 | 66.7 | 0 | 50 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.13 | A.1033318.13.03 | Santos Dedicated SWPT Feb 2025 | SANTOS LIMITED | THE ROCK 52, THE ROCK 54, HARDENLEY 40, THE ROCK 53 | Rigless - Australia | J.25.008271 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2025-02-01 | 2025-02-01 | 2025-02-01 | 2025-02-01 | 2025-02-28 23:59 | 2025-03-01 | 2025-03-21 | Roma WL | KKeese | 2025-03-25 10:00 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 8614.68 | 3 |  | L3 - Full RO |  | 83.3 | 66.7 | 100 | 100 | 85 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.13 | A.1033318.13.02 | Santos Dedicated SWPT Jan 2025 | SANTOS LIMITED | DALDOWIE 23, KELSALL 35, KELSALL 36, KELSALL 33, HARDENLEY 21, HARDENLEY 14, HARDENLEY 29, HARDENLEY 31, HARDENLEY 32, HARDENLEY 33, HARDENLEY 15, HARDENLEY 18, HARDENLEY 23, HARDENLEY 22, HARDENLEY 37, HARDENLEY 19, HARDENLEY 20, HARDENLEY 26, HARDENLEY 27, HARDENLEY 25, HARDENLEY 24, THE ROCK 52, THE ROCK 54, HARDENLEY 42, THE ROCK 36, HARDENLEY 30, KELSALL 32 | Rigless - Australia | J.24.141721 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-05-30 | 2025-01-01 |  | 2025-01-01 | 2025-01-31 23:59 |  | 2024-05-31 22:59 | Roma WL | KKeese | 2025-03-03 16:05 | CKok3 |  | No |  |  |  |  | Irwan Wongso |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.13 | A.1033318.13.05 | Santos Dedicated SWPT Dec 24 | SANTOS LIMITED | GLEN EVIS 9, HARDENLEY 8, HARDENLEY 38, HARDENLEY 31, HARDENLEY 32, DALDOWIE 21, DALDOWIE 22, HARDENLEY 28, KELSALL 38, THE ROCK 36 | Rigless - Australia | J.24.171847 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2024-11-24 | 2024-11-01 |  | 2024-11-24 | 2024-12-28 23:59 |  | 2024-12-28 23:59 | Roma WL | CKok3 | 2024-12-28 10:10 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 91.7 | 83.3 | 100 | 100 | 92.5 |  | 3 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.12 | A.1033318.12.07 | Dedicated SWPT_Sep24 | SANTOS LIMITED | RM40-96-2, RM40-96-3, RM40-84-2, THE ROCK 34, THE ROCK 33, THE ROCK 35, THE ROCK 28, THE ROCK 26, THE ROCK 39, RM40-82-1, THE ROCK 38, THE ROCK 25, RM40-76-1 | Rigless - Australia | J.24.143482 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-07-25 23:00 | 2024-08-25 23:00 |  | 2024-08-25 23:00 | 2024-09-30 22:59 |  | 2024-09-23 23:59 | Roma WL | JEsmeralda | 2025-01-07 16:44 | MPerrtiangha |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 3 |  | L3 - Full RO |  | 100 | 83.3 | 100 | 87.5 | 91.3 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.12 | A.1033318.12.03 | Dedicated SWPT_Jun24 | SANTOS LIMITED | RM90-108-1, RM90-109-1, RM90-149-1, RM23-41-1, RM23-46-1, RM90-150-1, DULACCA WEST-1, FV16-75-1, BUNGAWARRA SOUTH 1, BASALT CREEK 1, BUNGUWARRA 3, BASALT CREEK EAST 1, KELSALL 12, RM90-13-1, RM40-119-1, MOUNT KINGSLEY 45, MOUNT KINGSLEY 56 | Rigless - Australia | J.24.105209 | RPE | ES-CH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-05-25 23:00 | 2024-05-25 23:00 |  | 2024-05-25 23:00 | 2024-07-06 22:59 |  | 2024-07-06 23:59 | Roma WL | JEsmeralda | 2024-12-29 14:43 | MPerrtiangha |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 227.42 | 7 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 87.5 | 76.3 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1033318 | O.1033318.12 | A.1033318.12.08 | Dedicated SWPT_Oct24 | SANTOS LIMITED | THE ROCK 38 | Rigless - Australia | J.24.159635 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-09-25 23:00 | 2024-09-25 23:00 |  | 2024-09-25 23:00 | 2024-10-31 23:59 |  | 2024-10-31 23:59 | Roma WL | JEsmeralda | 2024-12-17 17:17 | MPerrtiangha |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 0 |  | L3 - Full RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.12 | A.1033318.12.06 | Dedicated SWPT_Aug24 | SANTOS LIMITED | SUNNYHOLT 63, THE ROCK 27, THE ROCK 28, HARDENLEY 14, THE ROCK 26, THE ROCK 25, THE ROCK 39 | Rigless - Australia | J.24.131359 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-07-25 23:00 | 2024-07-25 23:00 |  | 2024-07-25 23:00 | 2024-08-31 22:59 |  | 2024-08-31 23:59 | Roma WL | JEsmeralda | 2024-12-17 17:00 | MPerrtiangha |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 4 |  | L3 - Full RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.12 | A.1033318.12.01 | Dedicated SWPT_Apr24 | SANTOS LIMITED | RM90-108-1, RM90-109-1, RM90-149-1, RM23-41-1, RM23-46-1 | Rigless - Australia | J.24.073536 | RPE | ES-CH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-04-05 23:00 | 2024-04-05 23:00 |  | 2024-04-05 23:00 | 2024-05-01 22:59 |  | 2024-05-01 22:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 227.42 | 1 |  | L3 - Full RO |  | 100 | 83.3 | 0 | 100 | 85 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1033318 | O.1033318.12 | A.1033318.12.05 | Dedicated SWPT_Jul24 | SANTOS LIMITED | MOUNT KINGSLEY 46, MOUNT KINGSLEY 48, THE ROCK 30, THE ROCK 31, THE ROCK 32, MOUNT KINGSLEY 49, THE ROCK 29 | Rigless - Australia | J.24.126281 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-07-03 23:00 | 2024-07-03 23:00 |  | 2024-07-03 23:00 | 2024-07-31 22:59 |  | 2024-07-31 23:59 | Roma WL | JEsmeralda | 2024-07-30 11:32 | MPerrtiangha |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 227.42 | 13 |  | L3 - Full RO |  | 91.7 | 83.3 | 100 | 100 | 92.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.12 | A.1033318.12.04 | Dedicated SWPT_Jul24 | SANTOS LIMITED | RM90-108-1, RM90-109-1, RM90-149-1, RM23-41-1, RM23-46-1, RM90-150-1, DULACCA WEST-1, FV16-75-1, BUNGAWARRA SOUTH 1, BASALT CREEK 1, BUNGUWARRA 3, BASALT CREEK EAST 1, KELSALL 12 | Rigless - Australia | J.24.117858 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-06-20 23:00 | 2024-06-20 23:00 |  | 2024-06-20 23:00 | 2024-06-26 22:59 |  | 2024-06-26 23:59 | Roma WL | JEsmeralda | 2024-06-26 14:54 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 7 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.12 | A.1033318.12.02 | Dedicated SWPT_May24 | SANTOS LIMITED | RM90-108-1, RM90-109-1, RM90-149-1, RM23-41-1, RM23-46-1, RM90-150-1, DULACCA WEST-1 | Rigless - Australia | J.24.087495 | RPE | ES-CH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2024-04-25 23:00 | 2024-04-25 23:00 | 2024-03-23 13:00 | 2024-04-25 23:00 | 2024-05-01 22:59 | 2024-05-07 | 2024-05-01 23:59 | Roma WL | JEsmeralda | 2024-05-24 08:18 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 227.42 | 3 |  | L3 - Full RO |  | 91.7 | 83.3 | 100 | 100 | 92.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1033318 | O.1033318.11 | A.1033318.11.03 | Dedicated SWPT_Feb24 | SANTOS LIMITED | FV18-136-1, FV18-137-1, FV18-88-1, FV18-82-1, FV18-139-1, FV18-140-1, FV18-140-2, FV18-122-1, FV18-101-1, SUNNYHOLT 60, SUNNYHOLT 64, FV18-109-1, FV18-110-1, FV18-110-2, CASTLE HILL 90, FV18-95-1, FV18-103-1, OKSGWBA 01, RM90-108-1, FV18-124-1, FV18-123-1, FV18-126-1, FV18-125-1, RM90-166-1, RM90-165-1, FV18-102-1, KELSALL 12 | Rigless - Australia | J.24.043680 | RPE | ES-CH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-01-20 | 2024-01-20 |  | 2024-01-20 | 2024-02-29 23:59 |  | 2024-03-05 | Roma WL | JEsmeralda | 2024-12-12 17:06 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 227.42 | 3 |  | L3 - Full RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1033318 | O.1033318.11 | A.1033318.11.01 | SWPT Dec 2023 | SANTOS LIMITED | FV18-136-1, FV18-137-1, FV18-88-1, FV18-82-1, FV18-139-1, FV18-140-1, FV18-140-2, FV18-122-1, FV18-101-1, SUNNYHOLT 65, SUNNYHOLT 61, SUNNYHOLT 51, SUNNYHOLT 57, SUNNYHOLT 58, SUNNYHOLT 59, SUNNYHOLT 60, SUNNYHOLT 64 | Rigless - Australia | J.23.169504 | RPE | ES-CH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2023-11-30 | 2023-11-29 |  | 2023-11-30 | 2023-12-31 23:59 |  | 2023-12-31 23:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 227.42 | 2 |  | L3 - Full RO |  | 100 | 83.3 | 0 | 100 | 85 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1033318 | O.1033318.11 | A.1033318.11.02 | Jan SWPT CSG | SANTOS LIMITED | FV18-136-1, FV18-137-1, FV18-88-1, FV18-82-1, FV18-139-1, FV18-140-1, FV18-140-2, FV18-122-1, FV18-101-1, SUNNYHOLT 65, SUNNYHOLT 61, SUNNYHOLT 51, SUNNYHOLT 57, SUNNYHOLT 58, SUNNYHOLT 59, SUNNYHOLT 60, SUNNYHOLT 64, FV18-109-1, FV18-110-1, FV18-110-2, CASTLE HILL 90, FV18-95-1 | Rigless - Australia | J.24.039029 | RPE | ES-CH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-01-09 | 2024-01-08 |  | 2024-01-09 | 2024-02-09 23:59 |  | 2024-02-09 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 227.42 | 2 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1033318 | O.1033318.11 | A.1033318.11.04 | Dedicated SWPT March 2024 | SANTOS LIMITED | KELSALL 12, MEDML01, MOUNT KINGSLEY 51, MOUNT KINGSLEY 55, MOUNT KINGSLEY 59, LONGVALE 1 | Rigless - Australia | J.24.062843 | RPE | ES-CH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-04-01 | 2024-03-01 |  | 2024-04-01 | 2024-04-30 23:59 |  | 2024-04-30 23:59 | Roma WL | NAndilla | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 227.42 | 5 |  | L3 - Full RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1033318 | O.1033318.10 | A.1033318.10.01 | SWPT Sep 2023 | SANTOS LIMITED | FV18-107-1, KAIMANNA 48, BRUMBY PLAINS 1, BRUMBY 23, BRUMBY 22, FV17-80-1, FV18-120-1, FV17-79-1, FV18-114-1, KAIMANNA 35, OBGML 01 | Rigless - Australia | J.23.136595 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-09-15 09:00 | 2023-09-14 03:00 | 2023-09-14 01:00 | 2023-09-14 09:00 | 2023-10-09 01:59 | 2023-10-15 01:00 | 2023-10-10 02:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.10 | A.1033318.10.02 | SWPT Oct 2023 | SANTOS LIMITED | FV18-107-1, KAIMANNA 48, BRUMBY PLAINS 1, BRUMBY 23, BRUMBY 22, FV17-80-1, FV18-120-1, FV17-79-1, FV18-114-1, KAIMANNA 35, FV17-83-1, FV17-81-1, FV18-128-1, BRUMBY 21, FV18-131-1, FV18-133-1, FV18-130-1, FV18-129-1A, FV18-80-1, FV13-80-1, FV18-19-2, FV13-89-1, BUNDALEER 3, BUNDALEER 4, BUNDALEER 6, FV18-134-1, BUNDALEER 2, BUNDALEER 5 | Rigless - Australia | J.23.139519 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2023-09-28 08:00 | 2023-09-27 03:00 |  | 2023-09-27 09:00 | 2023-10-31 01:59 |  | 2023-11-01 02:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.10 | A.1033318.10.03 | SWPT Nov 2023 | SANTOS LIMITED | FV18-107-1, KAIMANNA 48, BRUMBY PLAINS 1, BRUMBY 23, BRUMBY 22, FV17-80-1, FV18-120-1, FV17-79-1, FV18-114-1, KAIMANNA 35, FV17-83-1, FV17-81-1, FV18-128-1, BRUMBY 21, FV18-131-1, FV18-133-1, FV18-130-1, FV18-129-1A, FV18-80-1, FV13-80-1, FV18-19-2, FV13-86-1, FV13-87-1, FV18-138-1, FV18-134-1, BBNML02, LINGA LONGA 4, FV18-132-1, FV18-135-1, FV13-77-1, FV13-88-1, FV18-85-1 | Rigless - Australia | J.23.157454 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-10-26 08:00 | 2023-10-25 03:00 |  | 2023-10-25 09:00 | 2023-11-30 01:59 |  | 2023-12-01 01:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.09 | A.1033318.09.01 | SWPT July | SANTOS LIMITED | FV17-74-1, FV17-75-1, FV17-77-1, FV17-82-1, FV18-108-1 | RIGLESS - AUSTRALIA | J.23.109840 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-07-09 08:00 | 2023-07-08 02:00 | 2023-07-10 01:00 | 2023-07-08 08:00 | 2023-08-02 01:59 | 2023-08-04 01:00 | 2023-08-03 01:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.09 | A.1033318.09.02 | SWPT Aug 2023 | SANTOS LIMITED | FV18-106-1, FV17-66-1, KAIMANNA 33, KAIMANNA 38, CASTLE HILL 89, KAIMANNA 57, KAIMANNA 61, FV18-113-1, FV18-141-1, FV17-72-1, BRUMBY 21, BRUMBY 24, FV17-74-1, BRUMBY 15, BRUMBY 16, BRUMBY 17, BRUMBY 18, BRUMBY 19, BRUMBY 20, FV18-96-1, BRUMBY 22, FV17-34-3, FV18-116-1, FV18-99-1, FV17-66-1 | RIGLESS - AUSTRALIA | J.23.116744 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-28 08:00 | 2023-07-27 02:00 | 2023-07-27 | 2023-07-27 08:00 | 2023-08-21 01:59 | 2023-08-27 | 2023-08-22 01:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.09 | A.1033318.09.03 | SWPT Sep 2023 | SANTOS LIMITED | FV18-111-1, FV18-112-1, FV18-117-1, FV18-118-1, FV18-127-1, FV18-27-2, FV18-30-2, FV18-121-1, FV18-119-1, FV18-119-2 | RIGLESS - AUSTRALIA | J.23.135288 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-09-12 08:00 | 2023-09-11 02:00 | 2023-09-11 | 2023-09-11 08:00 | 2023-09-29 01:59 | 2023-10-05 02:00 | 2023-09-30 03:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.08 | A.1033318.08.01 | SWPT Dedicated June - Continuation | SANTOS LIMITED | KAIMANNA 32, KAIMANNA 43, KAIMANNA 48 | Rigless - Australia | J.23.101148 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-13 | 2023-06-13 |  | 2023-06-13 | 2023-06-30 23:59 |  | 2023-06-30 23:59 | Roma WL | KKeese | 2023-06-15 08:37 | MEketone |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 227.42 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.07 | A.1033318.07.21 | Nov Santos Dedicated SWPT | SANTOS LIMITED |  | Rigless - Australia | J.24.096863 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-11-01 06:00 | 2024-11-01 |  | 2024-11-01 06:00 | 2024-11-25 23:59 |  | 2024-11-25 23:59 | Roma WL | KKeese | 2024-10-29 11:59 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.07 | A.1033318.07.22 | Dec Santos Dedicated SWPT | SANTOS LIMITED |  | Rigless - Australia | J.24.096864 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-12-01 06:00 | 2024-12-01 |  | 2024-12-01 06:00 | 2024-12-25 23:59 |  | 2024-12-25 23:59 | Roma WL | KKeese | 2024-10-29 11:41 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033318 | O.1033318.07 | A.1033318.07.19 | Sep Santos Dedicated SWPT | SANTOS LIMITED |  | Rigless - Australia | J.24.096861 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-09-01 06:00 | 2024-09-01 |  | 2024-09-01 06:00 | 2024-09-25 23:59 |  | 2024-09-25 23:59 | Roma WL | KKeese | 2024-10-22 10:35 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.07 | A.1033318.07.02 | SWPT June | SANTOS LIMITED | FV17-26-2, KAIMANNA 23, KAIMANNA 26, KAIMANNA 18, KAIMANNA 22, KAIMANNA 34, FV17-78-1, KAIMANNA 29, KAIMANNA 30 | Rigless - Australia | J.23.048652 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-01 06:00 | 2023-06-01 |  | 2023-06-01 06:00 | 2023-06-25 23:59 |  | 2023-06-25 23:59 | Roma WL | MRony2 | 2024-10-03 11:25 | AKavooris |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 75 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1033318 | O.1033318.07 | A.1033318.07.07 | SWPT September | SANTOS LIMITED |  | Rigless - Australia | J.23.084113 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2023-09-01 06:00 | 2023-09-01 |  | 2023-09-01 06:00 | 2023-09-25 23:59 |  | 2023-09-25 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 129954.52 | 1 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 25 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.07 | A.1033318.07.05 | SWPT July | SANTOS LIMITED |  | Rigless - Australia | J.23.084111 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2023-07-01 06:00 | 2023-07-01 |  | 2023-07-01 06:00 | 2023-07-25 23:59 |  | 2023-07-25 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.07 | A.1033318.07.06 | SWPT August | SANTOS LIMITED |  | Rigless - Australia | J.23.084112 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-08-01 06:00 | 2023-08-01 |  | 2023-08-01 06:00 | 2023-08-25 23:59 |  | 2023-08-25 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.07 | A.1033318.07.20 | Oct Santos Dedicated SWPT | SANTOS LIMITED |  | Rigless - Australia | J.24.096862 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2024-10-01 06:00 | 2024-10-01 |  | 2024-10-01 06:00 | 2024-10-25 23:59 |  | 2024-10-26 00:59 | Roma WL | KKeese | 2024-08-16 11:35 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.07 | A.1033318.07.16 | June Santos Dedicated SWPT | SANTOS LIMITED |  | Rigless - Australia | J.24.050644 | RPI | PS-WL-NO | Low | Operationally Complete | Execute - PSD |  | In Progress | Not Started | In Progress | 2024-06-01 06:00 | 2024-06-01 |  | 2024-06-01 06:00 | 2024-06-25 23:59 |  | 2024-06-25 23:59 | Roma WL | KKeese | 2024-07-26 15:35 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 129954.52 | 2 |  | L3 - Full RO |  | 66.7 | 33.3 | 100 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.07 | A.1033318.07.18 | Aug Santos Dedicated SWPT | SANTOS LIMITED |  | Rigless - Australia | J.24.050646 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-08-01 06:00 | 2024-08-01 |  | 2024-08-01 06:00 | 2024-08-25 23:59 |  | 2024-08-25 23:59 | Roma WL | KKeese | 2024-07-24 16:30 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.07 | A.1033318.07.17 | July Santos Dedicated SWPT | SANTOS LIMITED |  | Rigless - Australia | J.24.050645 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-07-01 06:00 | 2024-07-01 |  | 2024-07-01 06:00 | 2024-07-25 23:59 |  | 2024-07-25 23:59 | Roma WL | KKeese | 2024-07-24 07:41 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.07 | A.1033318.07.15 | May Santos Dedicated SWPT | SANTOS LIMITED |  | Rigless - Australia | J.24.103639 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-05-01 06:00 | 2024-05-01 | 2024-05-01 | 2024-05-01 06:00 | 2024-05-25 23:59 | 2024-05-26 | 2024-05-25 23:59 | Roma WL | KKeese | 2024-05-23 15:21 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.07 | A.1033318.07.12 | SWPT Dedicated Feb 2024 | SANTOS LIMITED |  | Rigless - Australia | J.24.021427 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-02-01 06:00 | 2024-02-01 |  | 2024-02-01 06:00 | 2024-02-25 23:59 |  | 2024-02-25 23:59 | Roma WL | KKeese | 2024-04-02 14:59 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.07 | A.1033318.07.14 | April Dedicated Santos SWPT | SANTOS LIMITED |  | Rigless - Australia | J.24.050643 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2024-04-01 06:00 | 2024-04-01 |  | 2024-04-01 06:00 | 2024-04-25 23:59 |  | 2024-04-25 22:59 | Roma WL | KKeese | 2024-02-14 17:42 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 129954.52 | 2 |  | L3 - Full RO |  | 50 | 0 | 0 | 25 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.07 | A.1033318.07.10 | SWPT December | SANTOS LIMITED |  | Rigless - Australia | J.23.085720 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-12-01 06:00 | 2023-12-01 |  | 2023-12-01 06:00 | 2023-12-25 23:59 |  | 2023-12-25 23:59 | Roma WL | KKeese | 2023-12-30 08:21 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.07 | A.1033318.07.13 | SWPT Dedicated Mar 2024 | SANTOS LIMITED |  | Rigless - Australia | J.24.021428 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2024-03-01 06:00 | 2024-03-01 |  | 2024-03-01 06:00 | 2024-03-25 23:59 |  | 2024-03-25 23:59 | Roma WL | KKeese | 2023-10-29 14:30 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 129954.52 | 2 |  | L3 - Full RO |  | 50 | 0 | 0 | 25 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.07 | A.1033318.07.11 | SWPT Dedicated Jan 2024 | SANTOS LIMITED |  | Rigless - Australia | J.23.160227 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2024-01-01 06:00 | 2024-01-01 | 2024-01-01 01:00 | 2024-01-01 06:00 | 2024-01-25 23:59 | 2024-01-26 01:00 | 2024-01-25 23:59 | Roma WL | KKeese | 2023-10-29 14:30 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 125762.44 | 2 |  | L3 - Full RO |  | 50 | 0 | 0 | 25 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.07 | A.1033318.07.08 | SWPT October | SANTOS LIMITED |  | Rigless - Australia | J.23.085718 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-01 06:00 | 2023-10-01 | 2023-10-01 | 2023-10-01 06:00 | 2023-10-25 23:59 | 2023-10-26 01:00 | 2023-10-25 23:59 | Roma WL | KKeese | 2023-09-22 10:47 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.07 | A.1033318.07.04 | SWPT_May-1 | SANTOS LIMITED | FV06-57-1, FV17-65-1, FV18-97-1, FV17-70-1, FV17-73-1, FV18-06-4, AC23-66-1, KAIMANNA 24, KAIMANNA 25, KAIMANNA 27, FV17-67-1, FV17-71-1, FV06-55-1, FV17-76-1, RM13-27-1 | Rigless - Australia | J.23.075400 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-01 06:00 | 2023-04-30 |  | 2023-05-01 06:00 | 2023-05-31 23:59 |  | 2023-06-06 23:59 | Roma WL | SAli63 | 2023-06-25 21:42 | WMcconkey |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1033318 | O.1033318.07 | A.1033318.07.03 | Perf | SANTOS LIMITED |  | Rigless - Australia | J.23.048666 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2023-06-06 | 2023-06-02 |  | 2023-06-06 | 2023-06-15 23:59 |  | 2023-06-15 23:59 | Roma WL | MRony2 | 2023-05-22 10:47 | KKeese |  | No |  |  |  |  | Jon Lawrie |  | 0 | 9 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1033318 | O.1033318.07 | A.1033318.07.09 | SWPT November | SANTOS LIMITED |  | Rigless - Australia | J.23.085719 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2023-11-01 06:00 | 2023-11-01 |  | 2023-11-01 06:00 | 2023-11-25 23:59 |  | 2023-11-25 23:59 | Roma WL | KKeese | 2023-05-18 11:54 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 113186.19 | 2 |  | L3 - Full RO |  | 50 | 0 | 0 | 25 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033318 | O.1033318.07 | A.1033318.07.01 | SWPTApr-2 | SANTOS LIMITED | FV07-54-1, FV07-54-2, FV12-85-1, FV18-86-1, FV18-87-1, FV18-96-1, KAIMANNA 54, KAIMANNA 42, KAIMANNA 45, KAIMANNA 55, FV17-68-1, KAIMANNA 65, FV18-115-1, KAIMANNA 51, KAIMANNA 49, FV17-69-1 | Rigless - Australia | J.23.048644 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-08 06:00 | 2023-04-07 |  | 2023-04-08 06:00 | 2023-05-01 23:59 |  | 2023-05-02 23:59 | Roma WL | MRony2 | 2023-04-30 15:19 | MEketone |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 129954.52 | 2 |  | L3 - Full RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1033318 | O.1033318.06 | A.1033318.06.01 | SWPT_Mar23 | SANTOS LIMITED | FV07-43-1, FV07-43-2, FV07-53-1, FV07-55-1, CASTLE HILL 34, CASTLE HILL 81, CASTLE HILL 61, FV07-52-01, FV07-10-6, CASTLE HILL 88, CASTLE HILL 86, CASTLE HILL 24, KAIMANNA 21, KAIMANNA 13, KAIMANNA 11, KAIMANNA 20, KAIMANNA 31, KAIMANNA 46, KAIMANNA 1, KAIMANNA 70, KAIMANNA 16, KAIMANNA 28, KAIMANNA 12, KAIMANNA 19, KAIMANNA 71, KAIMANNA 14, KAIMANNA 15, KAIMANNA 66, KAIMANNA 67, KAIMANNA 40, KAIMANNA 68 | Rigless - Australia | J.23.016516 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-03-01 | 2023-01-30 |  | 2023-03-01 | 2023-03-31 23:59 |  | 2023-03-31 23:59 | Roma WL | MRony2 | 2023-04-20 08:44 | SAli63 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 134405.46 | 3 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1033318 | O.1033318.06 | A.1033318.06.02 | SWPT_Apr23 | SANTOS LIMITED | KAIMANNA 50, KAIMANNA 52, KAIMANNA 53, KAIMANNA 69, KAIMANNA 59, KAIMANNA 58, KAIMANNA 40, KAIMANNA 41, KAIMANNA 60 | Rigless - Australia | J.23.016518 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-04 | 2023-03-02 |  | 2023-04-05 | 2023-04-28 23:59 |  | 2023-04-28 23:59 | Roma WL | MRony2 | 2023-04-11 13:27 | JEsmeralda |  | No |  |  |  |  | Jon Lawrie |  | 3573.75 | 20 |  | L0 - No RO |  | 83.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1033318 | O.1033318.05 | A.1033318.05.01 | SWPT, Nov | SANTOS LIMITED |  | Rigless - Australia | J.22.137376 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-01-01 | 2022-12-30 |  | 2023-01-01 | 2023-01-24 23:59 |  | 2023-01-24 23:59 | Roma WL | MRony2 | 2023-01-04 23:34 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 20 |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1033318 | O.1033318.04 | A.1033318.04.02 | SWPT Feb 23 | SANTOS LIMITED | FV06-51-1, MOUNT ALDIS 2, AC23-64-1, BOTTLE TREE 10, AC23-60-1, AC23-67-1, CASTLE HILL 51, CASTLE HILL 61, CASTLE HILL 82, CASTLE HILL 85, FV06-52-1, CASTLE HILL 54, CASTLE HILL 87, Castle Hill 55, Castle Hill 59, KAIMANNA 3, KAIMANNA 4, KAIMANNA 5, FV07-43-1, FV07-56-1 | Rigless - Australia | J.23.016514 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-02-01 | 2023-01-30 |  | 2023-02-01 | 2023-02-24 23:59 |  | 2023-02-24 23:59 | Roma WL | MRony2 | 2023-03-12 14:10 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 163882.08 | 20 |  | L3 - Full RO |  | 75 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1033318 | O.1033318.04 | A.1033318.04.01 | SWPT, Jan 23 | SANTOS LIMITED | FV07-44-1, FV07-57-1, FV06-54-1, FV07-45-2, FV06-52-1, FV06-51-1, FV07-48-1, FV07-49-1 | Rigless - Australia | J.22.124602 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-01-05 | 2022-12-30 |  | 2023-01-05 | 2023-02-03 23:59 |  | 2023-02-03 23:59 | Roma WL | MRony2 | 2023-02-15 17:49 | MEketone |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 80991.06 | 20 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1033318 | O.1033318.03 | A.1033318.03.02 | Dec | SANTOS LIMITED | FV07-57-1, FV07-57-2, FV07-50-1, FV07-44-1, FV07-44-2, FV06-53-1, FV12-121-21 | Rigless - Australia | J.22.122506 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-12-16 | 2022-12-16 |  | 2022-12-16 | 2023-01-08 23:59 |  | 2023-01-08 23:59 | Roma WL | MRony2 | 2023-02-04 14:53 | SSabatini |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 20 |  | L3 - Full RO |  | 75 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1033318 | O.1033318.03 | A.1033318.03.01 | SWPT, Nov | SANTOS LIMITED | ARCADIA VALLEY 1, OMEO 2, FV12-122-21, FV12-121-21, BGDML-01, FV12-123-21, FV12-18-22, FV12-18-21, FV12-14-3, COLLINGWOOD 21, SCOTIA 72, SCOTIA 73, WOODROYD 5, WOODROYD 8 | Rigless - Australia | J.22.121725 | RPI | PS-WL-Ops | Low | Operationally Complete | Execute - PSD |  | Design Completed | Not Required | In Progress | 2022-11-02 | 2022-11-01 |  | 2022-11-02 | 2022-11-30 23:59 |  | 2022-12-01 23:59 | Roma WL | MRony2 | 2023-02-04 11:32 | SSabatini |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 13970.11 | 20 |  | L3 - Full RO |  | 58.3 | 66.7 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1033318 | O.1033318.02 | A.1033318.02.01 | SWPT_Oct22 | SANTOS LIMITED | CASTLE HILL 41, NORTH SCOTIA 1, SCOTIA 71, WOODROYD 4, NORTH SCOTIA 5, WOODROYD 6, AC23-73-1, CASTLE HILL 53, LINGA LONGA 9, LINGA LONGA 5, LINGA LONGA 10, LINGA LONGA 6, LINGA LONGA 7, KAIMANNA 63, KAIMANNA 64, DALDOWIE 20 | Rigless - Australia | J.22.110419 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2022-10-19 | 2022-10-19 |  | 2022-10-19 | 2022-10-25 23:59 |  | 2022-11-08 22:59 | Roma WL | JEsmeralda | 2023-02-04 11:33 | SSabatini |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5328.14 | 25 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1033318 | O.1033318.02 | A.1033318.02.03 | SWPT_Dec22 | SANTOS LIMITED |  | Rigless - Australia | J.22.110423 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-11-26 |  | 2022-11-27 | 2022-12-24 23:59 |  |  | Roma WL | JEsmeralda | 2022-11-06 13:34 | MRony2 |  | No |  |  |  |  | Jon Lawrie |  | 0 | 25 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1033318 | O.1033318.02 | A.1033318.02.02 | SWPT_Nov22 | SANTOS LIMITED |  | Rigless - Australia | J.22.110417 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-10-26 |  | 2022-10-27 | 2022-11-24 23:59 |  |  | Roma WL | JEsmeralda | 2022-10-28 16:35 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 25 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1033318 | O.1033318.01 | A.1033318.01.02 | SWPT_Aug | SANTOS LIMITED | CATTLE CREEK 10, CATTLE CREEK 13, CATTLE CREEK 14 | Rigless - Australia | J.22.110363 | RPI | PS-WL-Ops | Low | Operationally Complete | Execute - PSD |  | Design Completed | Not Required | In Progress | 2022-08-02 | 2022-07-01 |  | 2022-08-02 | 2022-08-04 23:59 |  | 2022-08-04 23:59 | Roma WL | MRony2 | 2023-12-04 12:42 | MSayed8 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 9649.12 | 28 |  | L3 - Full RO |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1033318 | O.1033318.01 | A.1033318.01.01 | SWPT_July | SANTOS LIMITED | FV12-114-1, FV12-115-1, FV12-116-1, FV12-117-1, BOTTLE TREE 4, BOTTLE TREE 6, BOTTLE TREE 9, BOTTLE TREE 7, BOTTLE TREE 11, BOTTLE TREE 12, COLLINGWOOD 18, COLLINGWOOD 20, COLLINGWOOD 22 | Rigless - Australia | J.22.110360 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2022-07-04 10:00 | 2022-07-03 10:00 |  | 2022-07-04 10:00 | 2022-07-28 09:59 |  | 2022-07-28 09:59 | Roma WL | MRony2 | 2023-02-04 11:37 | SSabatini |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 9649.12 | 28 |  | L3 - Full RO |  | 75 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1033318 | O.1033318.01 | A.1033318.01.03 | Aug_UPL | SANTOS LIMITED | Collingwood 19, Collingwood 25 | Rigless - Australia | J.22.111041 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-08-05 |  | 2022-08-05 16:00 | 2022-08-29 15:59 |  |  | Roma WL | MRony2 | 2022-10-19 14:05 | MRony2 |  | No |  |  |  |  | Jon Lawrie |  | 4467.19 | 28 |  |  |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1033318 | O.1033318.01 | A.1033318.01.04 | SWPT_Sep22 | SANTOS LIMITED | FV12-110-1, FV12-113-1, FV12-111-1, FV12-111-2, FV12-112-1, Linga Longa 6, Linga Longa 5, Linga Longa 8, Linga Longa 10, BOTTLE TREE 19, BOTTLE TREE 18, BOTTLE TREE 17, BOTTLE TREE 16, BOTTLE TREE 15, Bottle Tree 20, Bottle Tree 14, Bottle Tree 13, Bottle Tree 5, Bottle Tree 8, AC23-72-1, AC23-65-1, AC23-66-1 | Rigless - Australia | J.22.110408 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-09-08 |  | 2022-09-11 | 2022-10-07 23:59 |  |  | Roma WL | JEsmeralda | 2022-10-09 16:52 | SLie4 |  | No |  |  |  |  | Jon Lawrie |  | 9649.12 | 18 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1033294 | O.1033294.07 | A.1033294.07.01 | U418_H2-May24 | SANTOS LIMITED | GOORANIE 010, MOOMBA 335, MOOMBA 336, GOORANIE 19, MOOMBA 163, MOOMBA 169, TIRRAWARRA 17, FLY LAKE 30, FLY LAKE 31, MERCHANT 1, MERCHANT 1, MOOMBA 338 | Rigless - Australia | J.24.098166 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-05-18 17:00 | 2024-05-15 02:00 |  | 2024-05-18 17:00 | 2024-06-08 02:59 |  | 2024-11-23 04:59 | Moomba WL | ymoradi2 | 2024-10-14 19:44 | ymoradi2 |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 7 |  | L0 - No RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 1 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033294 | O.1033294.06 | A.1033294.06.01 | SWPT 418 Dec 2025 | SANTOS LIMITED | Well #15, Well #16, Well #17, Well #19, Well #20, Well #21, Well #18, Well #22, Well #23, Well #25, Well #24 | Rigless - Australia | J.25.001863 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-07-06 22:00 | 2025-08-15 13:00 | 2025-08-14 10:00 | 2025-08-16 22:00 | 2025-09-16 09:59 | 2025-09-15 21:00 | 2025-08-06 08:59 | Moomba WL | ymoradi2 | 2025-05-23 17:23 | CKok3 |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 20 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.05 | A.1033294.05.01 | U418_January-2024 | SANTOS LIMITED | GIDGEALPA 065, MOOMBA 300, MOOMBA 301, NEPHRITE SOUTH 14, NEPHRITE SOUTH 16, JACK LAKE 3, MOOMBA 330, MOOMBA 331, MOOMBA 332, TINDILPIE 19, TINDILPIE 20 | Rigless - Australia | J.24.034181 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-12-17 15:00 | 2023-12-17 14:00 |  | 2023-12-17 15:00 | 2024-01-31 00:59 |  | 2024-01-31 23:59 | Moomba WL | HEstrella | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 105076.65 | 22 |  | L0 - No RO |  | 83.3 | 66.7 | 100 | 100 | 85 |  | 1 |  |  |  | 0 |  |  |  | Mohammad Adel Mohammad Alhashemi | WL Production Services
P.1033294 | O.1033294.05 | A.1033294.05.03 | U418_Q1_2024_Rigless | SANTOS LIMITED | PSYCH 5, DURHAM DOWNS 11, DURHAM DOWNS NORTH 4, COCINERO 17, WACKETT EAST 1, BARYULAH 7ST1 | Rigless - Australia | J.24.041375 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2024-02-26 15:00 | 2024-02-22 14:00 |  | 2024-02-26 15:00 | 2024-02-27 00:59 |  | 2024-02-13 04:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 2 |  | L0 - No RO |  | 91.7 | 66.7 | 0 | 100 | 77.5 |  | 3 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.05 | A.1033294.05.04 | U418_Rigless_Mar-2024 | SANTOS LIMITED | PSYCH 5, DURHAM DOWNS 11, DURHAM DOWNS NORTH 4, COCINERO 17, WACKETT EAST 1, BARYULAH 7ST1, MOOMBA 43, WINNINIA SOUTH 1, ACRUS 1, DURHAM DOWNS NORTH 3, KARMONA 3, NHUGANHA NGAKALANGA 1, MERRIMELIA 17, MOOMBA 319, MOOMBA 320 | Rigless - Australia | J.24.067583 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2024-03-07 15:00 | 2024-03-03 14:00 |  | 2024-03-07 15:00 | 2024-03-31 00:59 |  | 2024-02-13 04:59 | Moomba WL | ymoradi2 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 2 |  | L0 - No RO |  | 100 | 100 | 0 | 100 | 90 |  | 2 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033294 | O.1033294.05 | A.1033294.05.06 | U418_H2-May24 | SANTOS LIMITED | MOOMBA 43, WINNINIA SOUTH 1, ACRUS 1, DURHAM DOWNS NORTH 3, KARMONA 3, NHUGANHA NGAKALANGA 1, MERRIMELIA 17, SWAN LAKE 016, MOOMBA 195, ANNA NORTH 1, MOORARI 20, WACKETT EAST 1, COLOY 2, BARROLKA 27, GOORANIE 18, GOORANIE 19, BIG LAKE 158, BIG LAKE 85 | Rigless - Australia | J.24.098158 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-05-15 15:00 | 2024-05-14 |  | 2024-05-15 15:00 | 2024-06-11 00:59 |  | 2024-11-26 04:59 | Moomba WL | ymoradi2 | 2024-07-16 16:02 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 7 |  | L0 - No RO |  | 66.7 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033294 | O.1033294.05 | A.1033294.05.05 | SWPT 418-APR 2024 | SANTOS LIMITED | MOOMBA 43, WINNINIA SOUTH 1, ACRUS 1, DURHAM DOWNS NORTH 3, KARMONA 3, NHUGANHA NGAKALANGA 1, MERRIMELIA 17, SWAN LAKE 016, MOOMBA 195, ANNA NORTH 1, MOORARI 20, WACKETT EAST 1, COLOY 2, BARROLKA 27, GOORANIE 18, GOORANIE 19, BIG LAKE 158, BIG LAKE 85 | Rigless - Australia | J.24.076192 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2024-04-02 15:00 | 2024-04-01 | 2024-03-26 12:00 | 2024-04-02 15:00 | 2024-04-30 00:59 | 2024-10-09 13:00 | 2024-10-15 03:59 | Moomba WL | ymoradi2 | 2024-05-24 07:54 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 7 |  | L0 - No RO |  | 100 | 100 | 0 | 100 | 90 |  | 1 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033294 | O.1033294.05 | A.1033294.05.02 | U418_Jan-2024_YM | SANTOS LIMITED | GIDGEALPA 065, MOOMBA 300, MOOMBA 301, NEPHRITE SOUTH 14, NEPHRITE SOUTH 16, JACK LAKE 3, MOOMBA 330, MOOMBA 331, MOOMBA 332 | Rigless - Australia | J.24.036763 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2024-01-11 15:00 | 2024-01-11 14:00 |  | 2024-01-11 15:00 | 2024-02-25 00:59 |  | 2024-02-25 02:59 | Moomba WL | ymoradi2 | 2024-02-06 14:23 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 20 |  | L0 - No RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033294 | O.1033294.04 | A.1033294.04.02 | SWPT 418 July | SANTOS LIMITED | BARINA 8, NAPOWIE 11, NAPOWIE 12, MERUPA 4, NAPOWIE 13, MERCHANT 001, TIRRAWARRA 101, TIRRAWARRA 103, TIRRAWARRA 25, MOOMBA 311, GIDGEALPA 27, MARABOOKA 5, MERANJI 30, MERANJI 31, MOOMBA 79 | Rigless - Australia | J.23.114408 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-07-17 | 2023-07-15 15:00 | 2023-07-15 10:00 | 2023-07-17 | 2023-09-30 11:59 | 2023-10-01 | 2023-09-30 11:59 | Moomba WL | eismail | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 96147.7 | 18 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.04 | A.1033294.04.04 | U418_Sep-2023 | SANTOS LIMITED | MARSILEA 002, BEARCAT 2, COLOY 1, ANNA NORTH 1, TARTULLA 9, KARMONA 3, WACKETT 6, BIG LAKE 44, STIMPEE 6, DILCHEE 005, NUNGEROO WEST 001, TIRRAWARRA 76, NANIMA 2, TIRRAWARRA 107, TIRRAWARRA 108, GOYDER 5, TIRRAWARRA 106, BIG LAKE 160, TIRRAWARRA 091, MOOMBA 307, MOOMBA 308, MOOMBA 304, BIG LAKE 70, MOOMBA 79, TALLALIA 2, TOOLACHEE 58 | Rigless - Australia | J.23.136923 | RPI | PS-WL-Ops | InComplete | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-09-16 | 2023-09-14 15:00 |  | 2023-09-16 | 2023-12-31 11:59 |  | 2023-12-31 13:59 | Moomba WL | ymoradi2 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 120007.13 | 20 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 1 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033294 | O.1033294.04 | A.1033294.04.10 | SWPT 418 Jun 2024 | SANTOS LIMITED | MARSILEA 002, BEARCAT 2, COLOY 1, ANNA NORTH 1, TARTULLA 9, KARMONA 3, WACKETT 6, BIG LAKE 44, STIMPEE 6, DILCHEE 005, NUNGEROO WEST 001 | Rigless - Australia | J.24.023003 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-06-01 | 2024-05-30 15:00 |  | 2024-06-01 | 2024-06-30 11:59 |  | 2024-06-30 10:59 | Moomba WL | KKeese | 2024-07-25 16:20 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 20 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.04 | A.1033294.04.08 | Test OA | SANTOS LIMITED | MARSILEA 002, BEARCAT 2, COLOY 1, ANNA NORTH 1, TARTULLA 9, KARMONA 3, WACKETT 6, BIG LAKE 44, STIMPEE 6, DILCHEE 005, NUNGEROO WEST 001 | Rigless - Australia | J.24.023001 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-04-01 | 2024-03-30 15:00 | 2024-03-30 11:00 | 2024-04-01 | 2024-04-30 11:59 | 2024-04-30 05:00 | 2024-04-30 09:59 | Moomba WL | KKeese | 2024-05-23 15:28 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 20 |  | L0 - No RO |  | 91.7 | 50 | 0 | 0 | 42.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.04 | A.1033294.04.09 | SWPT 418 May 2024 | SANTOS LIMITED | MARSILEA 002, BEARCAT 2, COLOY 1, ANNA NORTH 1, TARTULLA 9, KARMONA 3, WACKETT 6, BIG LAKE 44, STIMPEE 6, DILCHEE 005, NUNGEROO WEST 001 | Rigless - Australia | J.24.023002 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-05-01 | 2024-04-29 15:00 | 2024-04-29 10:00 | 2024-05-01 | 2024-05-31 11:59 | 2024-05-31 21:00 | 2024-05-31 10:59 | Moomba WL | KKeese | 2024-05-23 15:20 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 20 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.04 | A.1033294.04.16 | SWPT 418 Dec 2024 | SANTOS LIMITED | MARSILEA 002, BEARCAT 2, COLOY 1, ANNA NORTH 1, TARTULLA 9, KARMONA 3, WACKETT 6, BIG LAKE 44, STIMPEE 6, DILCHEE 005, NUNGEROO WEST 001 | Rigless - Australia | J.24.023009 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-12-01 | 2024-11-29 15:00 | 2024-11-29 11:00 | 2024-12-01 | 2024-12-31 11:59 | 2024-12-31 22:00 | 2024-12-31 10:59 | Moomba WL | KKeese | 2024-05-10 08:23 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 20 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.04 | A.1033294.04.15 | SWPT 418 Nov 2024 | SANTOS LIMITED | MARSILEA 002, BEARCAT 2, COLOY 1, ANNA NORTH 1, TARTULLA 9, KARMONA 3, WACKETT 6, BIG LAKE 44, STIMPEE 6, DILCHEE 005, NUNGEROO WEST 001 | Rigless - Australia | J.24.023008 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-11-01 | 2024-10-30 15:00 | 2024-10-30 11:00 | 2024-11-01 | 2024-11-30 11:59 | 2024-11-30 22:00 | 2024-11-30 10:59 | Moomba WL | KKeese | 2024-05-10 08:23 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 20 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.04 | A.1033294.04.14 | SWPT 418 Oct 2024 | SANTOS LIMITED | MARSILEA 002, BEARCAT 2, COLOY 1, ANNA NORTH 1, TARTULLA 9, KARMONA 3, WACKETT 6, BIG LAKE 44, STIMPEE 6, DILCHEE 005, NUNGEROO WEST 001 | Rigless - Australia | J.24.023007 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-10-01 | 2024-09-29 15:00 | 2024-09-29 10:00 | 2024-10-01 | 2024-10-31 11:59 | 2024-10-31 22:00 | 2024-10-31 11:59 | Moomba WL | KKeese | 2024-05-10 08:23 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 20 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.04 | A.1033294.04.13 | SWPT 418 Sep 2024 | SANTOS LIMITED | MARSILEA 002, BEARCAT 2, COLOY 1, ANNA NORTH 1, TARTULLA 9, KARMONA 3, WACKETT 6, BIG LAKE 44, STIMPEE 6, DILCHEE 005, NUNGEROO WEST 001 | Rigless - Australia | J.24.023006 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-09-01 | 2024-08-30 15:00 | 2024-08-30 10:00 | 2024-09-01 | 2024-10-01 11:59 | 2024-10-01 21:00 | 2024-10-01 10:59 | Moomba WL | KKeese | 2024-05-10 08:23 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 20 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.04 | A.1033294.04.12 | SWPT 418 Aug 2024 | SANTOS LIMITED | MARSILEA 002, BEARCAT 2, COLOY 1, ANNA NORTH 1, TARTULLA 9, KARMONA 3, WACKETT 6, BIG LAKE 44, STIMPEE 6, DILCHEE 005, NUNGEROO WEST 001 | Rigless - Australia | J.24.023005 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-08-01 | 2024-07-30 15:00 | 2024-07-30 10:00 | 2024-08-01 | 2024-08-31 11:59 | 2024-08-31 21:00 | 2024-08-31 10:59 | Moomba WL | KKeese | 2024-05-10 08:22 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 20 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.04 | A.1033294.04.11 | SWPT 418 Jul 2024 | SANTOS LIMITED | MARSILEA 002, BEARCAT 2, COLOY 1, ANNA NORTH 1, TARTULLA 9, KARMONA 3, WACKETT 6, BIG LAKE 44, STIMPEE 6, DILCHEE 005, NUNGEROO WEST 001 | Rigless - Australia | J.24.023004 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-07-01 | 2024-06-29 15:00 | 2024-06-29 10:00 | 2024-07-01 | 2024-07-31 11:59 | 2024-07-31 21:00 | 2024-07-31 10:59 | Moomba WL | KKeese | 2024-05-08 08:33 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 20 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.04 | A.1033294.04.07 | SWPT 418 _ Mar 2024 | SANTOS LIMITED | MARSILEA 002, BEARCAT 2, COLOY 1, ANNA NORTH 1, TARTULLA 9, KARMONA 3, WACKETT 6, BIG LAKE 44, STIMPEE 6, DILCHEE 005, NUNGEROO WEST 001 | Rigless - Australia | J.24.021434 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-03-01 | 2024-02-28 15:00 | 2024-02-28 11:00 | 2024-03-01 | 2024-03-31 11:59 | 2024-03-31 22:00 | 2024-03-31 10:59 | Moomba WL | KKeese | 2024-04-02 15:01 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 20 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.04 | A.1033294.04.17 | SWPT 418_ Q1-2024 | SANTOS LIMITED | MARSILEA 002, BEARCAT 2, COLOY 1, ANNA NORTH 1, TARTULLA 9, KARMONA 3, WACKETT 6, BIG LAKE 44, STIMPEE 6, DILCHEE 005, NUNGEROO WEST 001 | Rigless - Australia | J.24.055566 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-02-22 | 2024-02-20 15:00 | 2024-02-20 11:00 | 2024-02-22 | 2024-03-21 11:59 | 2024-03-22 | 2024-03-21 12:59 | Moomba WL | ymoradi2 | 2024-04-02 15:01 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 20 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Adel Mohammad Alhashemi | WL Production Services
P.1033294 | O.1033294.04 | A.1033294.04.06 | SWPT 418 _ Feb 2024 | SANTOS LIMITED | MARSILEA 002, BEARCAT 2, COLOY 1, ANNA NORTH 1, TARTULLA 9, KARMONA 3, WACKETT 6, BIG LAKE 44, STIMPEE 6, DILCHEE 005, NUNGEROO WEST 001 | Rigless - Australia | J.24.021433 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-02-01 | 2024-01-30 15:00 |  | 2024-02-01 | 2024-02-29 11:59 |  | 2024-02-29 12:59 | Moomba WL | KKeese | 2024-04-02 14:59 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 20 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.04 | A.1033294.04.05 | SWPT 418 _ Jan 2024 | SANTOS LIMITED | MARSILEA 002, BEARCAT 2, COLOY 1, ANNA NORTH 1, TARTULLA 9, KARMONA 3, WACKETT 6, BIG LAKE 44, STIMPEE 6, DILCHEE 005, NUNGEROO WEST 001 | Rigless - Australia | J.23.160231 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-01-01 | 2023-12-30 15:00 |  | 2024-01-01 | 2024-01-31 11:59 |  | 2024-01-31 12:59 | Moomba WL | KKeese | 2023-12-30 08:18 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 20 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.04 | A.1033294.04.01 | Rigless 418 Q2 June | SANTOS LIMITED |  | Rigless - Australia | J.23.114407 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-18 07:00 | 2023-09-17 06:00 | 2023-09-17 12:00 | 2023-09-18 07:00 | 2023-10-18 07:59 | 2023-10-18 | 2023-11-15 07:59 | Moomba WL | eismail | 2023-08-29 11:32 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.04 | A.1033294.04.03 | U418_Aug-2023 | SANTOS LIMITED | BARINA 8, NAPOWIE 11, NAPOWIE 12, MERUPA 4, NAPOWIE 13 | Rigless - Australia | J.23.121116 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-08-09 | 2023-08-07 15:00 | 2023-08-07 20:00 | 2023-08-09 | 2023-09-23 11:59 | 2023-09-23 06:00 | 2023-09-23 11:59 | Moomba WL | ymoradi2 | 2023-08-29 11:25 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 18 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Adel Mohammad Alhashemi | WL Production Services
P.1033294 | O.1033294.03 | A.1033294.03.04 | Rigless 418 Q3 August | SANTOS LIMITED | TIRRAWARRA 109, QUASAR 2, BIG LAKE 108, BIG LAKE 169, MOOMBA 297, MOOMBA 298, TINDILPIE 9, BIG LAKE 168 | Rigless - Australia | J.23.083626 | RPI | PS-WL-Ops | Low | Cancelled | Execute - PSD |  | In Progress | In Progress | In Progress | 2023-08-01 06:00 | 2023-08-01 05:00 |  | 2023-08-01 06:00 | 2023-08-31 05:59 |  | 2023-09-12 05:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 6 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.03 | A.1033294.03.05 | Rigless 418 Q3 September | SANTOS LIMITED | TIRRAWARRA 108, TIRRAWARRA 109, DULLINGARI 043 DW1, QUASAR 2, BIG LAKE 108, BIG LAKE 169, MOOMBA 297, MOOMBA 298, TINDILPIE 9, BIG LAKE 168, WACKETT 20, TIRRAWARRA 107, TIRRAWARRA 78, DORODILLO 5, DORODILLO 6 | Rigless - Australia | J.23.083627 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-01 06:00 | 2023-09-01 05:00 |  | 2023-09-01 06:00 | 2023-09-30 05:59 |  | 2023-09-30 07:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 6 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.03 | A.1033294.03.03 | Rigless 418 Q2 June | SANTOS LIMITED | TIRRAWARRA 108, TIRRAWARRA 109, DULLINGARI 043 DW1, QUASAR 2, BIG LAKE 108, BIG LAKE 169, TINDILPIE 9, BIG LAKE 168, TIRRAWARRA 107, DORODILLO 5, DORODILLO 6, MARSILEA 002, DORODILLO 7, DULLINGARI 33, DORODILLO 8, MOOMBA 299, MOOMBA 300, MOOMBA 306 | Rigless - Australia | J.23.083625 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-03 06:00 | 2023-06-02 05:00 |  | 2023-06-03 06:00 | 2023-07-03 05:59 |  | 2023-07-31 05:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.03 | A.1033294.03.06 | Rigless 418 Q3 October | SANTOS LIMITED | TIRRAWARRA 108, TIRRAWARRA 109, DULLINGARI 043 DW1, QUASAR 2, BIG LAKE 108, BIG LAKE 169, MOOMBA 297, MOOMBA 298, TINDILPIE 9, BIG LAKE 168, WACKETT 20, TIRRAWARRA 107, TIRRAWARRA 78, DORODILLO 5, DORODILLO 6 | Rigless - Australia | J.23.085750 | RPI | PS-WL-Ops | Low | Cancelled | Execute - PSD |  | In Progress | In Progress | In Progress | 2023-10-01 06:00 | 2023-10-01 05:00 | 2023-09-30 12:00 | 2023-10-01 06:00 | 2023-10-30 05:59 | 2023-10-30 02:00 | 2023-10-30 07:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 6 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.03 | A.1033294.03.11 | SWPT 418 September | SANTOS LIMITED |  | Rigless - Australia | J.23.088193 | RPI | PS-WL-NO | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2023-09-01 18:00 | 2023-08-30 15:00 | 2023-09-01 | 2023-09-01 18:00 | 2023-09-30 05:59 | 2023-09-30 01:00 | 2023-09-30 07:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 284195.63 | 17 |  | L0 - No RO |  | 66.7 | 33.3 | 100 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.03 | A.1033294.03.09 | PNX-Campaign_U_418-Jul | SANTOS LIMITED | WINDIGO 3, STRZELECKI 033, MARABOOKA 6, NANIMA 2, COOLAH 16, WANARA 1, STRZELECKI 10, MARABOOKA 5 | Rigless - Australia | J.23.088191 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Required | In Progress | 2023-08-10 18:00 | 2023-08-09 15:00 | 2023-08-10 | 2023-08-10 18:00 | 2023-08-31 05:59 | 2023-08-31 01:00 | 2023-10-01 05:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 16 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 50 | 65 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.03 | A.1033294.03.15 | Dullingari North 26 | SANTOS LIMITED | DULLINGARI NORTH 26, DULLINGARI NORTH 27, AMYEMA 002 | Rigless - Australia | J.23.112009 | RPI | PS-WL-NO | High | Operationally Complete | Close - PSD |  | Design Completed | Not Started | Design Completed | 2023-07-22 | 2023-07-17 | 2023-07-11 | 2023-07-22 | 2023-07-31 23:59 | 2023-08-01 | 2023-07-31 23:59 | Moomba WL | ssultan | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 50 | 100 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.03 | A.1033294.03.16 | PNX_Campaign_Aug-2023 | SANTOS LIMITED | WINDIGO 3, STRZELECKI 033, MARABOOKA 6, NANIMA 2, COOLAH 16, WANARA 1, STRZELECKI 10, MARABOOKA 5 | Rigless - Australia | J.23.121420 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-08-10 18:00 | 2023-08-09 15:00 | 2023-08-10 | 2023-08-10 18:00 | 2023-10-01 05:59 | 2023-10-01 | 2023-10-01 05:59 | Moomba WL | ymoradi2 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 16 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Adel Mohammad Alhashemi | WL Production Services
P.1033294 | O.1033294.03 | A.1033294.03.14 | SWPT 418 December | SANTOS LIMITED |  | Rigless - Australia | J.23.088203 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-12-01 18:00 | 2023-11-29 15:00 |  | 2023-12-01 18:00 | 2023-12-30 05:59 |  | 2023-12-30 05:59 | Moomba WL | KKeese | 2023-12-30 08:21 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 17 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.03 | A.1033294.03.02 | Rigless 418 Apr-May | SANTOS LIMITED | TIRRAWARRA 108, TIRRAWARRA 109, DULLINGARI 043 DW1, QUASAR 2, BIG LAKE 108, BIG LAKE 169, MOOMBA 297, MOOMBA 298, TINDILPIE 9, BIG LAKE 168, TIRRAWARRA 107, TIRRAWARRA 78 | Rigless - Australia | J.23.071847 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-19 06:00 | 2023-04-19 05:00 | 2023-04-18 02:00 | 2023-04-19 06:00 | 2023-06-06 05:59 | 2023-06-05 23:00 | 2023-06-06 05:59 | Moomba WL | KKeese | 2023-10-03 21:17 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 6 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.03 | A.1033294.03.10 | SWPT 418 August | SANTOS LIMITED |  | Rigless - Australia | J.23.088192 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-08-01 18:00 | 2023-07-30 15:00 | 2023-08-01 | 2023-08-01 18:00 | 2023-08-31 05:59 | 2023-08-31 | 2023-08-31 05:59 | Moomba WL | KKeese | 2023-08-29 11:25 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 17 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.03 | A.1033294.03.12 | SWPT 418 October | SANTOS LIMITED |  | Rigless - Australia | J.23.088194 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2023-10-01 18:00 | 2023-09-29 15:00 | 2023-10-01 | 2023-10-01 18:00 | 2023-10-31 05:59 | 2023-10-31 01:00 | 2023-10-31 05:59 | Moomba WL | KKeese | 2023-08-28 17:00 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 17 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.03 | A.1033294.03.13 | SWPT 418 November | SANTOS LIMITED |  | Rigless - Australia | J.23.088195 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2023-11-01 18:00 | 2023-10-30 15:00 | 2023-11-01 01:00 | 2023-11-01 18:00 | 2023-11-30 05:59 | 2023-11-30 01:00 | 2023-11-30 05:59 | Moomba WL | KKeese | 2023-08-28 16:59 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 17 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.03 | A.1033294.03.08 | Rigless 418 Q3 December | SANTOS LIMITED | TIRRAWARRA 108, TIRRAWARRA 109, DULLINGARI 043 DW1, QUASAR 2, BIG LAKE 108, BIG LAKE 169, MOOMBA 297, MOOMBA 298, TINDILPIE 9, BIG LAKE 168, WACKETT 20, TIRRAWARRA 107, TIRRAWARRA 78, DORODILLO 5, DORODILLO 6, POORAKA 002 | Rigless - Australia | J.23.085752 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-01 06:00 | 2023-12-01 05:00 |  | 2023-12-01 06:00 | 2023-12-30 05:59 |  | 2023-12-30 07:59 | Moomba WL | KKeese | 2023-05-22 21:23 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 6 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.03 | A.1033294.03.07 | Rigless 418 Q3 November | SANTOS LIMITED | TIRRAWARRA 108, TIRRAWARRA 109, DULLINGARI 043 DW1, QUASAR 2, BIG LAKE 108, BIG LAKE 169, MOOMBA 297, MOOMBA 298, TINDILPIE 9, BIG LAKE 168, WACKETT 20, TIRRAWARRA 107, TIRRAWARRA 78, DORODILLO 5, DORODILLO 6, POORAKA 002 | Rigless - Australia | J.23.085751 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-01 06:00 | 2023-11-01 05:00 |  | 2023-11-01 06:00 | 2023-11-30 05:59 |  | 2023-11-30 07:59 | Moomba WL | KKeese | 2023-05-22 21:22 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 6 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.03 | A.1033294.03.01 | Rigless_U418 | SANTOS LIMITED | TIRRAWARRA 108, TIRRAWARRA 109, BEARCAT 1, WINNINIA 1, WACKETT 20, DULLINGARI 043 DW1, JUNO 8 | Rigless - Australia | J.23.066750 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-02 06:00 | 2023-03-30 12:00 |  | 2023-04-02 06:00 | 2023-04-18 05:59 |  | 2023-04-30 05:59 | Moomba WL | PLima7 | 2023-05-09 07:40 | PLima7 |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 6 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.35 | Well 29 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041015 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-25 11:00 | 2023-06-24 12:00 |  | 2023-06-25 12:00 | 2023-06-27 23:59 |  | 2023-06-27 22:59 | Moomba WL | KKeese | 2023-06-13 09:29 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.34 | Well 28 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041014 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-22 11:00 | 2023-06-21 12:00 |  | 2023-06-22 12:00 | 2023-06-24 23:59 |  | 2023-06-24 22:59 | Moomba WL | KKeese | 2023-06-13 09:29 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.33 | Well 27 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041013 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-19 11:00 | 2023-06-18 12:00 |  | 2023-06-19 12:00 | 2023-06-21 23:59 |  | 2023-06-21 22:59 | Moomba WL | KKeese | 2023-06-13 09:29 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.32 | Well 26 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041012 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-16 11:00 | 2023-06-15 12:00 |  | 2023-06-16 12:00 | 2023-06-18 23:59 |  | 2023-06-18 22:59 | Moomba WL | KKeese | 2023-06-13 09:29 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.29 | Well 23 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.101150 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-07 11:00 | 2023-06-06 12:00 |  | 2023-06-07 12:00 | 2023-06-09 23:59 |  | 2023-06-09 22:59 | Moomba WL | KKeese | 2023-06-13 09:29 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.31 | Well 25 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041011 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-13 11:00 | 2023-06-12 12:00 |  | 2023-06-13 12:00 | 2023-06-15 23:59 |  | 2023-06-15 22:59 | Moomba WL | KKeese | 2023-06-13 09:29 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.30 | Well 24 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041010 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-10 11:00 | 2023-06-09 12:00 |  | 2023-06-10 12:00 | 2023-06-12 23:59 |  | 2023-06-12 22:59 | Moomba WL | KKeese | 2023-06-13 09:29 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.28 | Well 22 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041009 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-04 11:00 | 2023-06-03 12:00 |  | 2023-06-04 12:00 | 2023-06-06 23:59 |  | 2023-06-06 22:59 | Moomba WL | KKeese | 2023-06-13 09:29 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.27 | Well 21 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041008 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-01 11:00 | 2023-05-31 12:00 |  | 2023-06-01 12:00 | 2023-06-03 23:59 |  | 2023-06-03 22:59 | Moomba WL | KKeese | 2023-06-13 09:28 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.36 | Well 30 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041016 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-28 11:00 | 2023-06-27 12:00 |  | 2023-06-28 12:00 | 2023-06-30 23:59 |  | 2023-06-30 22:59 | Moomba WL | KKeese | 2023-05-29 10:37 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.26 | Well 20 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041007 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-05-28 11:00 | 2023-05-27 12:00 |  | 2023-05-28 12:00 | 2023-05-30 23:59 |  | 2023-05-30 22:59 | Moomba WL | KKeese | 2023-05-22 20:17 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.25 | Well 19 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041006 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-05-25 11:00 | 2023-05-24 12:00 |  | 2023-05-25 12:00 | 2023-05-27 23:59 |  | 2023-05-27 22:59 | Moomba WL | KKeese | 2023-05-22 20:17 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.24 | Well 18 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041005 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-05-22 11:00 | 2023-05-21 12:00 |  | 2023-05-22 12:00 | 2023-05-24 23:59 |  | 2023-05-24 22:59 | Moomba WL | KKeese | 2023-05-22 20:17 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.23 | Well 17 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041004 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-05-19 11:00 | 2023-05-18 12:00 |  | 2023-05-19 12:00 | 2023-05-21 23:59 |  | 2023-05-21 22:59 | Moomba WL | KKeese | 2023-05-22 20:17 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.22 | Well 16 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041003 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-05-16 11:00 | 2023-05-15 12:00 |  | 2023-05-16 12:00 | 2023-05-18 23:59 |  | 2023-05-18 22:59 | Moomba WL | KKeese | 2023-05-22 20:17 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.21 | Well 15 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041002 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-05-13 11:00 | 2023-05-12 12:00 |  | 2023-05-13 12:00 | 2023-05-15 23:59 |  | 2023-05-15 22:59 | Moomba WL | KKeese | 2023-05-22 20:17 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.20 | Well 14 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041001 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-05-10 11:00 | 2023-05-09 12:00 |  | 2023-05-10 12:00 | 2023-05-12 23:59 |  | 2023-05-12 22:59 | Moomba WL | KKeese | 2023-05-22 20:17 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.19 | Well 13 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.041000 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-05-07 11:00 | 2023-05-06 12:00 |  | 2023-05-07 12:00 | 2023-05-09 23:59 |  | 2023-05-09 22:59 | Moomba WL | KKeese | 2023-05-22 20:17 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.18 | Well 12 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040999 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-05-04 11:00 | 2023-05-03 12:00 |  | 2023-05-04 12:00 | 2023-05-06 23:59 |  | 2023-05-06 22:59 | Moomba WL | KKeese | 2023-05-22 20:16 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.17 | Well 11 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040998 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-05-01 11:00 | 2023-04-30 12:00 |  | 2023-05-01 12:00 | 2023-05-03 23:59 |  | 2023-05-03 22:59 | Moomba WL | KKeese | 2023-05-22 20:16 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.16 | Well 10 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040997 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-04-28 11:00 | 2023-04-27 12:00 |  | 2023-04-28 12:00 | 2023-04-30 23:59 |  | 2023-04-30 22:59 | Moomba WL | KKeese | 2023-05-22 20:16 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.15 | Well 9 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040996 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-04-25 11:00 | 2023-04-24 12:00 |  | 2023-04-25 12:00 | 2023-04-27 23:59 |  | 2023-04-27 22:59 | Moomba WL | KKeese | 2023-04-27 18:43 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.14 | Well 8 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040995 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-04-22 11:00 | 2023-04-21 12:00 |  | 2023-04-22 12:00 | 2023-04-24 23:59 |  | 2023-04-24 22:59 | Moomba WL | KKeese | 2023-04-27 18:43 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.13 | Well 7 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.053664 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-04-19 11:00 | 2023-04-18 12:00 |  | 2023-04-19 12:00 | 2023-04-21 23:59 |  | 2023-04-21 22:59 | Moomba WL | KKeese | 2023-04-27 18:43 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.12 | Well 6 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040994 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-04-16 11:00 | 2023-04-15 12:00 |  | 2023-04-16 12:00 | 2023-04-18 23:59 |  | 2023-04-18 22:59 | Moomba WL | KKeese | 2023-04-27 18:43 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.11 | Well 5 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040992 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-04-13 11:00 | 2023-04-12 12:00 |  | 2023-04-13 12:00 | 2023-04-15 23:59 |  | 2023-04-15 22:59 | Moomba WL | KKeese | 2023-04-27 18:42 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.10 | Well 4 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.053663 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-04-10 11:00 | 2023-04-09 12:00 |  | 2023-04-10 12:00 | 2023-04-12 23:59 |  | 2023-04-12 22:59 | Moomba WL | KKeese | 2023-04-27 18:42 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.09 | Well 3 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040991 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-04-07 11:00 | 2023-04-06 12:00 |  | 2023-04-07 12:00 | 2023-04-09 23:59 |  | 2023-04-09 22:59 | Moomba WL | KKeese | 2023-04-27 18:42 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.39 | April 4 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.053942 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-04-04 11:00 | 2023-04-03 12:00 |  | 2023-04-04 12:00 | 2023-04-06 23:59 |  | 2023-04-06 22:59 | Moomba WL | KKeese | 2023-04-17 09:00 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.38 | April 1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.053941 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-04-01 11:00 | 2023-03-31 12:00 |  | 2023-04-01 12:00 | 2023-04-03 22:59 |  | 2023-04-03 21:59 | Moomba WL | KKeese | 2023-04-17 09:00 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.07 | Well 1 Q2 2023 | SANTOS LIMITED | MERANJI 21, NAPOWIE 009, COOLAH 8, TOOLACHEE 27 | Rigless - Australia | J.23.040990 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-03-09 10:00 | 2023-02-05 11:00 |  | 2023-03-09 12:00 | 2023-03-11 23:59 |  | 2023-03-11 22:59 | Moomba WL | KKeese | 2023-04-04 15:42 | ymoradi2 |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 4 |  | L0 - No RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.06 | SWQ Campaign | SANTOS LIMITED | BARYULAH 11, COOLAH 8, DURHAM DOWNS NORTH 9, WACKETT SOUTH 1, KERNA 7, MERANJI 21, MERRIMELIA 39, NAPOWIE 009 | Rigless - Australia | J.23.040842 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-21 06:00 | 2023-02-18 12:00 |  | 2023-02-21 06:00 | 2023-03-11 05:59 |  | 2023-03-11 05:59 | Moomba WL | PLima7 | 2023-03-08 08:01 | PLima7 |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.08 | Well 2 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.053662 | RPI | PS-WL-Ops | Low | Cancelled | Execute - PSD |  | In Progress | Not Started | In Progress | 2023-04-04 11:00 | 2023-04-03 12:00 |  | 2023-04-04 12:00 | 2023-04-06 23:59 |  | 2023-04-06 22:59 | Moomba WL | KKeese | 2023-03-07 10:45 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.37 | April 2023 Unit 420 | SANTOS LIMITED |  | Rigless - Australia | J.23.053667 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2023-04-01 |  | 2023-04-01 | 2023-04-25 23:59 |  |  | Moomba WL | KKeese | 2023-03-07 10:34 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 0 |  | L0 - No RO |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.05 | Brolga Campaign | SANTOS LIMITED | TIRRAWARRA 47, BARINA 8, MOOMBA 261, BIG LAKE 161, QUARTPOT 2, BARROLKA 14, CHALLUM 13, DURHAM DOWNS NORTH 1, ZEUS 14, ZEUS 15, TENNAPERRA 11, MINOS 4, MOOMBA 290 | Rigless - Australia | J.22.133753 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2022-12-16 18:00 | 2022-12-14 |  | 2022-12-16 18:00 | 2023-01-03 17:59 |  | 2023-01-03 17:59 | Moomba WL | ADuong4 | 2023-01-31 06:42 | ssultan |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.04 | U 418 SA campaign | SANTOS LIMITED | TIRRAWARRA 47, TANTANNA 12, BROLGA 8, BROLGA 9, TANTANNA 2 | Rigless - Australia | J.22.131475 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-11 | 2022-12-10 |  | 2022-12-11 | 2022-12-13 23:59 |  | 2022-12-13 23:59 | Moomba WL | ymoradi2 | 2022-12-17 14:58 | eismail |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO | [7 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.03 | Coolah 3 -Perforation | SANTOS LIMITED | WACKETT SOUTH 1, YARROW 003, TIRRAWARRA 47, BOLAH 5, COOLAH 3, DUNADOO 1, BARYULAH 2 | Rigless - Australia | J.22.129749 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-28 | 2022-11-27 |  | 2022-11-28 | 2022-11-30 23:59 |  | 2022-11-30 23:59 | Moomba WL | ymoradi2 | 2022-12-15 18:46 | ymoradi2 |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO | [7 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.02 | Wackett South 1 | SANTOS LIMITED | WACKETT SOUTH 1, YARROW 003, TIRRAWARRA 47, BOLAH 5, COOLAH 3 | Rigless - Australia | J.22.125813 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-11 | 2022-11-10 |  | 2022-11-11 | 2022-11-13 23:59 |  | 2022-11-13 23:59 | Moomba WL | ADuong4 | 2022-12-01 18:21 | ymoradi2 |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  |  |  | 58.3 | 83.3 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.02 | A.1033294.02.01 | SWPT418 - Q4 2022 | SANTOS LIMITED | WOOLKINA 003, MOOMBA 280, TIRRAWARRA 47, MOOMBA 281, MOOMBA 282, BIG LAKE 119, TINDILPIE 12, TARWONGA 2, COOROO NORTH 1 | Rigless - Australia | J.22.119152 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-22 | 2022-10-21 |  | 2022-10-22 | 2022-11-09 23:59 |  | 2022-11-09 23:59 | Moomba WL | JMoraes2 | 2022-11-11 06:21 | ADuong4 |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.101 | Q1 2023 Well 30 | SANTOS LIMITED |  | Rigless - Australia | J.23.012149 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-30 11:00 | 2023-03-29 12:00 |  | 2023-03-30 12:00 | 2023-03-31 23:59 |  | 2023-03-31 22:59 | Moomba WL | eismail | 2023-04-02 09:54 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.100 | Q1 2023 Well 29 | SANTOS LIMITED |  | Rigless - Australia | J.23.012148 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-27 11:00 | 2023-03-26 12:00 |  | 2023-03-27 12:00 | 2023-03-29 23:59 |  | 2023-03-29 22:59 | Moomba WL | eismail | 2023-04-02 09:54 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.99 | Q1 2023 Well 28 | SANTOS LIMITED |  | Rigless - Australia | J.23.012147 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-24 11:00 | 2023-03-23 12:00 |  | 2023-03-24 12:00 | 2023-03-26 23:59 |  | 2023-03-26 22:59 | Moomba WL | eismail | 2023-04-02 09:53 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.98 | Q1 2023 Well 27 | SANTOS LIMITED |  | Rigless - Australia | J.23.012146 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-21 11:00 | 2023-03-20 12:00 |  | 2023-03-21 12:00 | 2023-03-23 23:59 |  | 2023-03-23 22:59 | Moomba WL | eismail | 2023-04-02 09:53 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.97 | Q1 2023 Well 26 | SANTOS LIMITED |  | Rigless - Australia | J.23.012145 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-18 11:00 | 2023-03-17 12:00 |  | 2023-03-18 12:00 | 2023-03-20 23:59 |  | 2023-03-20 22:59 | Moomba WL | eismail | 2023-04-02 09:53 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.96 | Q1 2023 Well 25 | SANTOS LIMITED |  | Rigless - Australia | J.23.012144 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-15 11:00 | 2023-03-14 12:00 |  | 2023-03-15 12:00 | 2023-03-17 23:59 |  | 2023-03-17 22:59 | Moomba WL | eismail | 2023-04-02 09:53 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.95 | Q1 2023 Well 24 | SANTOS LIMITED |  | Rigless - Australia | J.23.012143 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-12 11:00 | 2023-03-11 12:00 |  | 2023-03-12 12:00 | 2023-03-14 23:59 |  | 2023-03-14 22:59 | Moomba WL | eismail | 2023-04-02 09:53 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.94 | Q1 2023 Well 23 | SANTOS LIMITED |  | Rigless - Australia | J.23.012142 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-09 11:00 | 2023-03-08 12:00 |  | 2023-03-09 12:00 | 2023-03-11 23:59 |  | 2023-03-11 22:59 | Moomba WL | eismail | 2023-04-02 09:53 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.93 | Q1 2023 Well 22 | SANTOS LIMITED |  | Rigless - Australia | J.23.012141 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-06 11:00 | 2023-03-05 12:00 |  | 2023-03-06 12:00 | 2023-03-08 23:59 |  | 2023-03-08 22:59 | Moomba WL | eismail | 2023-03-22 08:07 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.92 | Q1 2023 Well 21 | SANTOS LIMITED |  | Rigless - Australia | J.23.012140 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-03 11:00 | 2023-03-02 12:00 |  | 2023-03-03 12:00 | 2023-03-05 23:59 |  | 2023-03-05 22:59 | Moomba WL | eismail | 2023-03-22 08:07 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.52 | Q4 2022 Well 13 | SANTOS LIMITED | Moomba 275, Moomba 276 | Rigless - Australia | J.22.110050 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-11-01 11:00 | 2022-10-31 12:00 |  | 2022-11-01 12:00 | 2022-11-03 23:59 |  | 2022-11-03 22:59 | Moomba WL | KKeese | 2023-03-07 18:39 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.53 | Q4 2022 Well 14 | SANTOS LIMITED | Moomba 275, Moomba 276 | Rigless - Australia | J.22.110051 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-11-04 11:00 | 2022-11-03 12:00 |  | 2022-11-04 12:00 | 2022-11-06 23:59 |  | 2022-11-06 22:59 | Moomba WL | KKeese | 2023-03-07 18:39 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.54 | Q4 2022 Well 15 | SANTOS LIMITED | Moomba 275, Moomba 276 | Rigless - Australia | J.22.110052 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-11-07 11:00 | 2022-11-06 12:00 |  | 2022-11-07 12:00 | 2022-11-09 23:59 |  | 2022-11-09 22:59 | Moomba WL | KKeese | 2023-03-07 18:39 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.55 | Q4 2022 Well 16 | SANTOS LIMITED | Moomba 275, Moomba 276 | Rigless - Australia | J.22.110053 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-11-10 11:00 | 2022-11-09 12:00 |  | 2022-11-10 12:00 | 2022-11-12 23:59 |  | 2022-11-12 22:59 | Moomba WL | KKeese | 2023-03-07 18:39 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.56 | Q4 2022 Well 17 | SANTOS LIMITED | Moomba 275, Moomba 276 | Rigless - Australia | J.22.110054 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-11-13 11:00 | 2022-11-12 12:00 |  | 2022-11-13 12:00 | 2022-11-15 23:59 |  | 2022-11-15 22:59 | Moomba WL | KKeese | 2023-03-07 18:39 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.57 | Q4 2022 Well 18 | SANTOS LIMITED | Moomba 275, Moomba 276 | Rigless - Australia | J.22.110055 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-11-16 11:00 | 2022-11-15 12:00 |  | 2022-11-16 12:00 | 2022-11-18 23:59 |  | 2022-11-18 22:59 | Moomba WL | KKeese | 2023-03-07 18:39 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.58 | Q4 2022 Well 19 | SANTOS LIMITED | Moomba 275, Moomba 276 | Rigless - Australia | J.22.110056 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-11-25 11:00 | 2022-11-24 12:00 |  | 2022-11-25 12:00 | 2022-11-27 23:59 |  | 2022-11-27 22:59 | Moomba WL | KKeese | 2023-03-07 18:39 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.59 | Q4 2022 Well 20 | SANTOS LIMITED | Moomba 275, Moomba 276 | Rigless - Australia | J.22.110057 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-11-28 11:00 | 2022-11-27 12:00 |  | 2022-11-28 12:00 | 2022-11-30 23:59 |  | 2022-11-30 22:59 | Moomba WL | KKeese | 2023-03-07 18:39 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.69 | Q4 2022 Well 30 | SANTOS LIMITED | Moomba 275, Moomba 276 | Rigless - Australia | J.22.110067 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-22 11:00 | 2022-12-21 12:00 |  | 2022-12-22 12:00 | 2022-12-24 23:59 |  | 2022-12-24 22:59 | Moomba WL | KKeese | 2023-03-07 18:32 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.68 | Q4 2022 Well 29 | SANTOS LIMITED | Moomba 275, Moomba 276 | Rigless - Australia | J.22.110066 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-19 11:00 | 2022-12-18 12:00 |  | 2022-12-19 12:00 | 2022-12-21 23:59 |  | 2022-12-21 22:59 | Moomba WL | KKeese | 2023-03-07 18:32 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.67 | Q4 2022 Well 28 | SANTOS LIMITED | Moomba 275, Moomba 276 | Rigless - Australia | J.22.110065 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-16 11:00 | 2022-12-15 12:00 |  | 2022-12-16 12:00 | 2022-12-18 23:59 |  | 2022-12-18 22:59 | Moomba WL | KKeese | 2023-03-07 18:31 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.66 | Q4 2022 Well 27 | SANTOS LIMITED | Moomba 275, Moomba 276 | Rigless - Australia | J.22.110064 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-13 11:00 | 2022-12-12 12:00 |  | 2022-12-13 12:00 | 2022-12-15 23:59 |  | 2022-12-15 22:59 | Moomba WL | KKeese | 2023-03-07 18:31 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.65 | Q4 2022 Well 26 | SANTOS LIMITED | Moomba 275, Moomba 276 | Rigless - Australia | J.22.110063 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-10 11:00 | 2022-12-09 12:00 |  | 2022-12-10 12:00 | 2022-12-12 23:59 |  | 2022-12-12 22:59 | Moomba WL | KKeese | 2023-03-07 18:31 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.64 | Q4 2022 Well 25 | SANTOS LIMITED | Moomba 275, Moomba 276 | Rigless - Australia | J.22.110062 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-07 11:00 | 2022-12-06 12:00 |  | 2022-12-07 12:00 | 2022-12-09 23:59 |  | 2022-12-10 00:59 | Moomba WL | KKeese | 2023-03-07 18:31 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.62 | Q4 2022 Well 23 | SANTOS LIMITED | Moomba 275, Moomba 276 | Rigless - Australia | J.22.110060 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-01 11:00 | 2022-11-30 12:00 |  | 2022-12-01 12:00 | 2022-12-03 23:59 |  | 2022-12-03 22:59 | Moomba WL | KKeese | 2023-03-07 18:31 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.63 | Q4 2022 Well 24 | SANTOS LIMITED | Moomba 275, Moomba 276 | Rigless - Australia | J.22.110061 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-04 11:00 | 2022-12-03 12:00 |  | 2022-12-04 12:00 | 2022-12-06 23:59 |  | 2022-12-06 22:59 | Moomba WL | KKeese | 2023-03-07 18:31 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.91 | Q1 2023 Well 20 | SANTOS LIMITED |  | Rigless - Australia | J.23.012139 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-02-28 11:00 | 2023-02-27 12:00 |  | 2023-02-28 12:00 | 2023-03-02 23:59 |  | 2023-03-02 22:59 | Moomba WL | eismail | 2023-03-07 18:27 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.90 | Q1 2023 Well 19 | SANTOS LIMITED |  | Rigless - Australia | J.23.012138 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-02-25 11:00 | 2023-02-24 12:00 |  | 2023-02-25 12:00 | 2023-02-27 23:59 |  | 2023-02-27 22:59 | Moomba WL | eismail | 2023-03-07 18:27 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.89 | Q1 2023 Well 18 | SANTOS LIMITED |  | Rigless - Australia | J.23.012137 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-02-22 11:00 | 2023-02-21 12:00 |  | 2023-02-22 12:00 | 2023-03-07 23:59 |  | 2023-03-07 22:59 | Moomba WL | eismail | 2023-03-07 18:27 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.88 | Q1 2023 Well 17 | SANTOS LIMITED |  | Rigless - Australia | J.23.012136 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-02-19 11:00 | 2023-02-18 12:00 |  | 2023-02-19 12:00 | 2023-02-21 23:59 |  | 2023-02-21 22:59 | Moomba WL | eismail | 2023-03-07 18:27 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.87 | Q1 2023 Well 16 | SANTOS LIMITED |  | Rigless - Australia | J.23.012135 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-02-16 11:00 | 2023-02-15 12:00 |  | 2023-02-16 12:00 | 2023-02-18 23:59 |  | 2023-02-18 22:59 | Moomba WL | eismail | 2023-03-07 18:27 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.86 | Q1 2023 Well 15 | SANTOS LIMITED |  | Rigless - Australia | J.23.012131 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-02-13 11:00 | 2023-02-12 12:00 |  | 2023-02-13 12:00 | 2023-02-15 23:59 |  | 2023-02-15 22:59 | Moomba WL | eismail | 2023-03-07 18:27 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.85 | Q1 2023 Well 14 | SANTOS LIMITED |  | Rigless - Australia | J.23.012130 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-02-10 11:00 | 2023-02-09 12:00 |  | 2023-02-10 12:00 | 2023-02-12 23:59 |  | 2023-02-12 22:59 | Moomba WL | eismail | 2023-03-07 18:27 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.84 | Q1 2023 Well 13 | SANTOS LIMITED |  | Rigless - Australia | J.23.012129 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-02-07 11:00 | 2023-02-06 12:00 |  | 2023-02-07 12:00 | 2023-02-09 23:59 |  | 2023-02-09 22:59 | Moomba WL | eismail | 2023-03-07 18:26 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.83 | Q1 2023 Well 12 | SANTOS LIMITED |  | Rigless - Australia | J.23.012128 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-02-04 11:00 | 2023-02-03 12:00 |  | 2023-02-04 12:00 | 2023-02-06 23:59 |  | 2023-02-06 22:59 | Moomba WL | eismail | 2023-03-07 18:26 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.82 | Q1 2023 Well 11 | SANTOS LIMITED |  | Rigless - Australia | J.23.012127 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-02-01 11:00 | 2023-01-31 12:00 |  | 2023-02-01 12:00 | 2023-02-03 23:59 |  | 2023-02-03 22:59 | Moomba WL | eismail | 2023-03-07 18:26 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.73 | Q1 2023 Well 02 | SANTOS LIMITED | Moomba 275, Moomba 276 | Rigless - Australia | J.23.012118 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-31 11:00 | 2022-12-31 12:00 |  | 2022-12-31 12:00 | 2023-01-02 23:59 |  | 2023-01-02 22:59 | Moomba WL | eismail | 2023-03-07 18:24 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.74 | Q1 2023 Well 03 | SANTOS LIMITED |  | Rigless - Australia | J.23.012119 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-01-03 11:00 | 2023-01-03 12:00 |  | 2023-01-03 12:00 | 2023-01-05 23:59 |  | 2023-01-05 22:59 | Moomba WL | eismail | 2023-03-07 18:23 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.75 | Q1 2023 Well 04 | SANTOS LIMITED |  | Rigless - Australia | J.23.012120 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-01-06 11:00 | 2023-01-05 12:00 |  | 2023-01-06 12:00 | 2023-01-08 23:59 |  | 2023-01-08 22:59 | Moomba WL | eismail | 2023-03-07 18:23 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.76 | Q1 2023 Well 05 | SANTOS LIMITED |  | Rigless - Australia | J.23.012121 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-01-09 11:00 | 2023-01-08 12:00 |  | 2023-01-09 12:00 | 2023-01-11 23:59 |  | 2023-01-11 22:59 | Moomba WL | eismail | 2023-03-07 18:23 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.78 | Q1 2023 Well 07 | SANTOS LIMITED |  | Rigless - Australia | J.23.012123 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-01-15 11:00 | 2023-01-14 12:00 |  | 2023-01-15 12:00 | 2023-01-17 23:59 |  | 2023-01-17 22:59 | Moomba WL | eismail | 2023-03-07 18:23 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.79 | Q1 2023 Well 08 | SANTOS LIMITED |  | Rigless - Australia | J.23.012124 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-01-18 11:00 | 2023-01-17 12:00 |  | 2023-01-18 12:00 | 2023-01-20 23:59 |  | 2023-01-20 22:59 | Moomba WL | eismail | 2023-03-07 18:23 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.80 | Q1 2023 Well 09 | SANTOS LIMITED |  | Rigless - Australia | J.23.012125 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-01-21 11:00 | 2023-01-20 12:00 |  | 2023-01-21 12:00 | 2023-01-23 23:59 |  | 2023-01-23 22:59 | Moomba WL | eismail | 2023-03-07 18:23 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.81 | Q1 2023 Well 10 | SANTOS LIMITED |  | Rigless - Australia | J.23.012126 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-01-24 11:00 | 2023-01-23 12:00 |  | 2023-01-24 12:00 | 2023-01-26 23:59 |  | 2023-01-26 22:59 | Moomba WL | eismail | 2023-03-07 18:23 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.102 | Q1 2023 Well 10 (2) | SANTOS LIMITED |  | Rigless - Australia | J.23.012150 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-01-27 11:00 | 2023-01-26 12:00 |  | 2023-01-27 12:00 | 2023-01-29 23:59 |  | 2023-01-29 22:59 | Moomba WL | eismail | 2023-03-07 18:23 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.77 | Q1 2023 Well 06 | SANTOS LIMITED |  | Rigless - Australia | J.23.012122 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-01-12 11:00 | 2023-01-11 12:00 |  | 2023-01-12 12:00 | 2023-01-14 23:59 |  | 2023-01-14 22:59 | Moomba WL | eismail | 2023-03-07 17:33 | OMosleh |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.60 | Q4 2022 Well 21 | SANTOS LIMITED | Moomba 275, Moomba 276 | Rigless - Australia | J.22.110058 | RPI | PS-WL-Ops | Low | Cancelled | Execute - PSD |  | In Progress | Not Started | In Progress | 2022-11-25 13:00 | 2022-11-24 12:00 |  | 2022-11-25 12:00 | 2022-11-27 23:59 |  | 2022-11-28 00:59 | Moomba WL | KKeese | 2022-11-19 11:10 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.61 | Q4 2022 Well 22 | SANTOS LIMITED | Moomba 275, Moomba 276 | Rigless - Australia | J.22.110059 | RPI | PS-WL-Ops | Low | Cancelled | Execute - PSD |  | In Progress | Not Started | In Progress | 2022-11-28 13:00 | 2022-11-27 12:00 |  | 2022-11-28 12:00 | 2022-11-30 23:59 |  | 2022-12-01 00:59 | Moomba WL | KKeese | 2022-11-19 11:10 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.02 | September DK | SANTOS LIMITED | BIG LAKE 119, BIG LAKE 97, COWRALLI 17, SWAN LAKE 019, SWAN LAKE 6, KUDRIEKE 004, MOOMBA 277, MOOMBA 278, MOOMBA 279, NARCOONOWIE 011, GIDGEALPA 067, GIDGEALPA 068, GIDGEALPA 066, BIG LAKE 158, BIG LAKE 159, BIG LAKE 160, JENA 029, ODONATA 003, RAGNO 2, RAGNO 3, RAGNO 4 | Rigless - Australia | J.22.109857 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-08-21 05:00 | 2022-09-14 |  | 2022-09-14 06:00 | 2022-09-17 05:59 |  | 2022-09-12 13:23 | Moomba WL | KKeese | 2022-11-02 17:10 | DKitney |  | No |  |  |  |  | Mazhar Iqbal |  | 25625.82 | 1 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.70 | Big Lake 77 | SANTOS LIMITED | Big Lake 77, Moomba 254, Merrimelia 10 | Rigless - Australia | J.22.110085 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-08-31 |  | 2022-09-01 | 2022-09-03 23:59 |  |  | Moomba WL | ADuong4 | 2022-11-02 16:59 | DKitney |  | No |  |  |  |  | Mazhar Iqbal |  | 5217.75 | 2 |  |  |  | 91.7 | 83.3 | 0 | 75 | 75 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.72 | Q1 2023 Well 01 | SANTOS LIMITED | Moomba 275, Moomba 276 | Rigless - Australia | J.23.012117 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-12-31 12:00 |  | 2022-12-31 12:00 | 2023-01-02 23:59 |  |  | Moomba WL | eismail | 2022-10-30 17:10 | eismail |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.71 | SWPT418-Q3 | SANTOS LIMITED | BIG LAKE 137, MOORARI 021, MERANJI 21 | Rigless - Australia | J.22.115633 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-12 07:04 | 2022-10-12 |  | 2022-10-12 | 2022-10-24 23:59 |  | 2022-11-30 23:59 | Moomba WL | JMoraes2 | 2022-10-23 15:56 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.40 | Gidgealpa Water Well | SANTOS LIMITED | MOOMBA 275, MOOMBA 276 | Rigless - Australia | J.22.110038 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-09-26 12:00 | 2022-09-25 12:00 |  | 2022-09-26 12:00 | 2022-09-28 23:59 |  | 2022-09-28 23:59 | Moomba WL | KKeese | 2022-10-15 09:58 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.01 | Pelican 10, Big Lake 7 | SANTOS LIMITED | PELICAN 10, AMYEMA 002, MOOMBA 187 | Rigless - Australia | J.22.109856 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2022-07-04 08:00 | 2022-07-04 08:00 |  | 2022-07-04 09:00 | 2022-07-07 08:59 |  | 2022-07-07 09:59 | Moomba WL | KKeese | 2022-10-14 11:10 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 19969.33 | 1 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.51 | Q4 2022 Well 12 | SANTOS LIMITED | MOOMBA 275, MOOMBA 276 | Rigless - Australia | J.22.110049 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-10-29 11:00 | 2022-10-28 12:00 |  | 2022-10-29 12:00 | 2022-10-31 23:59 |  | 2022-10-31 22:59 | Moomba WL | KKeese | 2022-10-03 12:35 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.50 | Q4 2022 Well 11 | SANTOS LIMITED | MOOMBA 275, MOOMBA 276 | Rigless - Australia | J.22.110048 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-10-26 11:00 | 2022-10-25 12:00 |  | 2022-10-26 12:00 | 2022-10-28 23:59 |  | 2022-10-28 22:59 | Moomba WL | KKeese | 2022-10-03 12:35 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.49 | Q4 2022 Well 10 | SANTOS LIMITED | MOOMBA 275, MOOMBA 276 | Rigless - Australia | J.22.110047 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-10-23 11:00 | 2022-10-22 12:00 |  | 2022-10-23 12:00 | 2022-10-25 23:59 |  | 2022-10-25 22:59 | Moomba WL | KKeese | 2022-10-03 12:35 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.48 | Q4 2022 Well 9 | SANTOS LIMITED | MOOMBA 275, MOOMBA 276 | Rigless - Australia | J.22.110046 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-10-20 11:00 | 2022-10-19 12:00 |  | 2022-10-20 12:00 | 2022-10-22 23:59 |  | 2022-10-23 00:59 | Moomba WL | KKeese | 2022-10-03 12:35 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.47 | Q4 2022 Well 8 | SANTOS LIMITED | MOOMBA 275, MOOMBA 276 | Rigless - Australia | J.22.110045 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-10-17 11:00 | 2022-10-16 12:00 |  | 2022-10-17 12:00 | 2022-10-19 23:59 |  | 2022-10-20 00:59 | Moomba WL | KKeese | 2022-10-03 12:35 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.46 | Q4 2022 Well 7 | SANTOS LIMITED | MOOMBA 275, MOOMBA 276 | Rigless - Australia | J.22.110044 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-10-14 11:00 | 2022-10-13 12:00 |  | 2022-10-14 12:00 | 2022-10-16 23:59 |  | 2022-10-17 00:59 | Moomba WL | KKeese | 2022-10-03 12:35 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.45 | Q4 2022 Well 6 | SANTOS LIMITED | MOOMBA 275, MOOMBA 276 | Rigless - Australia | J.22.110043 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-10-11 11:00 | 2022-10-10 12:00 |  | 2022-10-11 12:00 | 2022-10-13 23:59 |  | 2022-10-13 22:59 | Moomba WL | KKeese | 2022-10-03 12:35 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.44 | Q4 2022 Well 5 | SANTOS LIMITED | MOOMBA 275, MOOMBA 276 | Rigless - Australia | J.22.110042 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-10-08 11:00 | 2022-10-07 12:00 |  | 2022-10-08 12:00 | 2022-10-10 23:59 |  | 2022-10-10 22:59 | Moomba WL | KKeese | 2022-10-03 12:34 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.43 | Q4 2022 Well 4 | SANTOS LIMITED | MOOMBA 275, MOOMBA 276 | Rigless - Australia | J.22.110041 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-10-05 11:00 | 2022-10-04 12:00 |  | 2022-10-05 12:00 | 2022-10-07 23:59 |  | 2022-10-07 22:59 | Moomba WL | KKeese | 2022-10-03 12:34 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.42 | Q4 2022 Well 3 | SANTOS LIMITED | MOOMBA 275, MOOMBA 276 | Rigless - Australia | J.22.110040 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-10-01 12:00 | 2022-10-01 11:00 |  | 2022-10-02 12:00 | 2022-10-04 23:59 |  | 2022-10-03 23:59 | Moomba WL | KKeese | 2022-10-03 12:34 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.41 | Q4 2022 Well 2 | SANTOS LIMITED | MOOMBA 275, MOOMBA 276 | Rigless - Australia | J.22.110039 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-09-29 12:00 | 2022-09-28 12:00 |  | 2022-09-29 12:00 | 2022-10-01 23:59 |  | 2022-10-01 23:59 | Moomba WL | KKeese | 2022-10-03 12:34 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.39 | Moomba 275 / Moomba 276 | SANTOS LIMITED | MOOMBA 275, MOOMBA 276, GIDGEALPA 068, Raven-2, BIG LAKE 77, MOOMBA 254 | Rigless - Australia | J.22.110037 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2022-08-10 12:00 | 2022-08-09 12:00 |  | 2022-08-10 12:00 | 2022-08-12 23:59 |  | 2022-08-18 15:24 | Moomba WL | ADuong4 | 2022-10-03 12:34 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.38 | Well 25 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.110035 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-09-14 23:00 | 2022-10-09 |  | 2022-10-09 | 2022-10-11 23:59 |  | 2022-09-17 23:59 | Moomba WL | KKeese | 2022-10-03 12:34 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.37 | Well 24 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.110034 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-09-11 23:00 | 2022-10-06 |  | 2022-10-06 | 2022-10-08 23:59 |  | 2022-09-14 23:59 | Moomba WL | KKeese | 2022-10-03 12:34 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.36 | Well 23 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.110033 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-09-07 23:00 | 2022-10-02 |  | 2022-10-02 | 2022-10-05 00:59 |  | 2022-09-10 23:59 | Moomba WL | KKeese | 2022-10-03 12:34 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.35 | Well 21 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.110032 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-09-27 23:00 | 2022-10-23 |  | 2022-10-23 | 2022-10-25 23:59 |  | 2022-09-30 23:59 | Moomba WL | KKeese | 2022-10-03 12:33 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.34 | Well 21 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.110031 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-09-01 23:00 | 2022-09-26 |  | 2022-09-26 | 2022-09-28 23:59 |  | 2022-09-05 00:59 | Moomba WL | KKeese | 2022-10-03 12:33 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.33 | Unit 418_Jul-Aug-2022 | SANTOS LIMITED | Cooroo North West 7, Barrolka 26, Tirrawarra 76, Moomba 269, Moomba 270 | Rigless - Australia | J.22.109963 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-07-27 17:30 | 2022-07-25 23:30 |  | 2022-07-27 17:30 | 2022-07-30 17:29 |  | 2022-07-30 17:29 | Moomba WL | ymoradi2 | 2022-10-03 12:27 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 75 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.32 | Dullingari 68 | SANTOS LIMITED | Dullingari 68, Meranji 16 | Rigless - Australia | J.22.109958 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-07-20 | 2022-07-19 |  | 2022-07-20 | 2022-07-22 23:59 |  | 2022-07-22 23:59 | Moomba WL | ADuong4 | 2022-10-03 12:26 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.31 | cooba 5 | SANTOS LIMITED | Cooba 5 | Rigless - Australia | J.22.109955 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-07-15 | 2022-07-14 |  | 2022-07-15 | 2022-07-17 23:59 |  | 2022-07-17 23:59 | Moomba WL | ADuong4 | 2022-10-03 12:26 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 12735.54 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.30 | Well 30 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109886 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-09-25 23:00 | 2022-10-20 01:00 |  | 2022-10-20 01:00 | 2022-10-23 00:59 |  | 2022-09-28 23:59 | Moomba WL | KKeese | 2022-10-03 12:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.29 | Well 29 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109885 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-09-22 23:00 | 2022-10-17 01:00 |  | 2022-10-17 01:00 | 2022-10-20 00:59 |  | 2022-09-25 23:59 | Moomba WL | KKeese | 2022-10-03 12:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.28 | Well 28 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109884 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-09-19 23:00 | 2022-10-14 01:00 |  | 2022-10-14 01:00 | 2022-10-17 00:59 |  | 2022-09-22 23:59 | Moomba WL | KKeese | 2022-10-03 12:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.27 | Well 27 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109883 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-09-16 23:00 | 2022-10-11 01:00 |  | 2022-10-11 01:00 | 2022-10-14 00:59 |  | 2022-09-19 23:59 | Moomba WL | KKeese | 2022-10-03 12:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.26 | Well 26 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109882 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-09-13 23:00 | 2022-10-08 01:00 |  | 2022-10-08 01:00 | 2022-10-11 00:59 |  | 2022-09-16 23:59 | Moomba WL | KKeese | 2022-10-03 12:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.25 | Well 25 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109881 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-09-10 23:00 | 2022-10-05 01:00 |  | 2022-10-05 01:00 | 2022-10-08 00:59 |  | 2022-09-13 23:59 | Moomba WL | KKeese | 2022-10-03 12:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.24 | Well 24 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109880 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-09-07 23:00 | 2022-10-02 |  | 2022-10-02 | 2022-10-05 00:59 |  | 2022-09-10 23:59 | Moomba WL | KKeese | 2022-10-03 12:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.23 | Well 23 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109879 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-09-04 23:00 | 2022-09-29 |  | 2022-09-29 | 2022-10-01 23:59 |  | 2022-09-07 23:59 | Moomba WL | KKeese | 2022-10-03 12:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.22 | Well 22 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109878 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-09-01 23:00 | 2022-09-26 |  | 2022-09-26 | 2022-09-28 23:59 |  | 2022-09-04 23:59 | Moomba WL | KKeese | 2022-10-03 12:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.21 | Well 21 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109877 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-08-30 23:00 | 2022-09-24 |  | 2022-09-24 | 2022-09-26 23:59 |  | 2022-09-02 23:59 | Moomba WL | KKeese | 2022-10-03 12:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.20 | Well 20 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109876 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-08-26 23:00 | 2022-09-20 |  | 2022-09-20 | 2022-09-22 23:59 |  | 2022-08-30 00:59 | Moomba WL | KKeese | 2022-10-03 12:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.19 | Well 19 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109875 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-08-23 23:00 | 2022-09-17 |  | 2022-09-17 | 2022-09-19 23:59 |  | 2022-08-27 00:59 | Moomba WL | KKeese | 2022-10-03 12:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.18 | Well 18 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109874 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-08-20 23:00 | 2022-09-14 |  | 2022-09-14 | 2022-09-16 23:59 |  | 2022-08-24 00:59 | Moomba WL | KKeese | 2022-10-03 12:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.17 | Well 17 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109873 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-08-17 23:00 | 2022-09-11 |  | 2022-09-11 | 2022-09-13 23:59 |  | 2022-08-21 00:59 | Moomba WL | KKeese | 2022-10-03 12:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.16 | Well 16 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109872 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-08-14 23:00 | 2022-09-08 |  | 2022-09-08 | 2022-09-10 23:59 |  | 2022-08-18 00:59 | Moomba WL | KKeese | 2022-10-03 12:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.15 | Well 15 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109871 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-08-11 23:00 | 2022-09-05 |  | 2022-09-05 | 2022-09-07 23:59 |  | 2022-08-15 00:59 | Moomba WL | KKeese | 2022-10-03 12:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.14 | Well 14 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109870 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-08-08 23:00 | 2022-09-02 |  | 2022-09-02 | 2022-09-04 23:59 |  | 2022-08-12 00:59 | Moomba WL | KKeese | 2022-10-03 12:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.13 | Well 13 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109869 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-08-05 23:00 | 2022-08-30 |  | 2022-08-30 | 2022-09-01 23:59 |  | 2022-08-09 00:59 | Moomba WL | KKeese | 2022-10-03 12:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.12 | Well 12 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109868 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-08-02 23:00 | 2022-08-27 |  | 2022-08-27 | 2022-08-29 23:59 |  | 2022-08-06 00:59 | Moomba WL | KKeese | 2022-10-03 12:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.11 | Well 11 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109867 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-07-30 23:00 | 2022-08-24 |  | 2022-08-24 | 2022-08-26 23:59 |  | 2022-08-03 00:59 | Moomba WL | KKeese | 2022-10-03 12:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.10 | Well 10 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109866 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-07-27 23:00 | 2022-08-21 |  | 2022-08-21 | 2022-08-23 23:59 |  | 2022-07-31 00:59 | Moomba WL | KKeese | 2022-10-03 12:17 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.09 | Well 9 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109865 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-07-24 23:00 | 2022-08-18 |  | 2022-08-18 | 2022-08-20 23:59 |  | 2022-07-28 00:59 | Moomba WL | KKeese | 2022-10-03 12:17 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.08 | Well 8 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109864 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-07-21 23:00 | 2022-08-15 |  | 2022-08-15 | 2022-08-17 23:59 |  | 2022-07-25 00:59 | Moomba WL | KKeese | 2022-10-03 12:17 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.07 | Well 7 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109863 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-07-18 23:00 | 2022-08-12 |  | 2022-08-12 | 2022-08-14 23:59 |  | 2022-07-22 00:59 | Moomba WL | KKeese | 2022-10-03 12:17 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.06 | Well 6 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109862 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-07-15 23:00 | 2022-08-09 |  | 2022-08-09 | 2022-08-11 23:59 |  | 2022-07-19 00:59 | Moomba WL | KKeese | 2022-10-03 12:17 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.05 | Well 5 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109861 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-07-12 23:00 | 2022-08-06 |  | 2022-08-06 | 2022-08-08 23:59 |  | 2022-07-16 00:59 | Moomba WL | KKeese | 2022-10-03 12:17 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.04 | Well 4 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109859 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-07-09 23:00 | 2022-08-03 |  | 2022-08-03 | 2022-08-05 23:59 |  | 2022-07-13 00:59 | Moomba WL | KKeese | 2022-10-03 12:17 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033294 | O.1033294.01 | A.1033294.01.03 | Well 3 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109858 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-07-06 23:00 | 2022-07-31 |  | 2022-07-31 | 2022-08-02 23:59 |  | 2022-07-10 00:59 | Moomba WL | KKeese | 2022-10-03 12:17 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.11 | A.1033291.11.02 | Santos Cooper CH 2025 Well 2 | SANTOS LIMITED |  | RIGLESS - AUSTRALIA | J.25.102037 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-10-22 | 2025-10-21 | 2025-10-21 01:00 | 2025-10-22 | 2025-11-13 16:59 | 2025-11-28 02:00 | 2025-11-13 16:59 | Moomba WL | CKok3 | 2025-08-13 14:25 | CKok3 |  | No |  |  |  |  | Irwan Wongso |  | 0 | 4 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033291 | O.1033291.11 | A.1033291.11.01 | Santos Cooper CH 2025 | SANTOS LIMITED |  | RIGLESS - AUSTRALIA | J.25.102036 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-08-20 | 2025-08-19 | 2025-08-19 | 2025-08-20 | 2025-09-11 16:59 | 2025-09-26 01:00 | 2025-09-11 16:59 | Moomba WL | CKok3 | 2025-08-13 14:24 | CKok3 |  | No |  |  |  |  | Irwan Wongso |  | 0 | 4 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1033291 | O.1033291.10 | A.1033291.10.01 | Raffle-3 | SANTOS LIMITED | RAFFLE 3 | Rigless - Australia | J.24.191218 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | Not Started | 2024-12-13 | 2024-12-13 |  | 2024-12-13 | 2024-12-21 23:59 |  | 2024-12-21 23:59 | Moomba WL | CKok3 | 2024-12-12 13:51 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Cheryl Kok |  | 0 | 3 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1033291 | O.1033291.09 | A.1033291.09.01 | SWQ Campaign | SANTOS LIMITED | Well #34, Well #35, Well #37, Well #36, Well #32, Well #38, Well #26, Well #27, Well #39, Well #40 | Rigless - Australia | J.25.008008 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-08-11 13:00 | 2024-08-10 23:00 |  | 2024-08-11 12:00 | 2024-08-31 01:59 |  | 2024-08-31 02:59 | Moomba WL | FShallal | 2024-10-22 10:36 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 2 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033291 | O.1033291.08 | A.1033291.08.02 | Moomba Extension cased hole job September 2024 | SANTOS LIMITED | MOOMBA 237, MOOMBA 349, MOOMBA 350, MOOMBA 351, MOOMBA 352, BURKE 7, ULANDI 8, COOBA 1, NARCOONOWIE 14, BIG LAKE 9, MOOMBA 325, MOOMBA 326, TOOLACHEE 34, SWAN LAKE 2, BIG LAKE 63, GLOSS 1, BIG LAKE 120, MOOMBA 296, MOOMBA 279, DORODILLO 8, ZEUS 12, NAPOWIE 008, NAPOWIE 12, NAPOWIE 13, BECKLER 1, BECKLER 2, STRZELECKI 7, MOOMBA 121, MOORARI 021 | Rigless - Australia | J.24.152431 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2024-01-29 | 2024-09-05 | 2024-09-04 | 2024-09-05 | 2024-11-15 23:59 | 2024-10-26 | 2024-12-15 03:59 | Moomba WL | NAndilla | 2025-11-28 16:54 | ysaeedabadian |  | No |  |  |  |  | Irwan Wongso |  | 898310.59 | 12 |  | L0 - No RO |  | 91.7 | 66.7 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.08 | A.1033291.08.01 | SWQ Campaign | SANTOS LIMITED | MERANJI 33, MERANJI 34, MERANJI 35, MOOMBA 323, MOOMBA 324, JACKSON WATER WELL 1, FRIZZLE 1, TARTULLA 9, NARCOONOWIE 14, BIG LAKE 62, BIG LAKE 63, COOBA 1 | Rigless - Australia | J.25.008007 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-09-19 03:00 | 2024-08-08 16:00 |  | 2024-08-09 17:00 | 2024-09-09 06:59 |  | 2024-09-08 13:59 | Moomba WL | FShallal | 2024-09-05 15:02 | FShallal |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 7 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.07 | A.1033291.07.01 | U420 May 2024 | SANTOS LIMITED | GALEX 4 | Rigless - Australia | J.24.100783 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-05-20 09:00 | 2024-05-19 09:00 | 2024-05-19 | 2024-05-20 09:00 | 2024-06-12 01:59 | 2024-06-26 01:00 | 2024-06-12 01:59 | Moomba WL | AJaved15 | 2024-05-24 19:20 | AJaved15 |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 4 |  | L0 - No RO |  | 95.8 | 41.7 | 0 | 0 | 41.3 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.06 | A.1033291.06.06 | SWQ Campaign | SANTOS LIMITED | BEEREENLAH 1, MERANJI 33, MERANJI 34, MERANJI 35, DARALINGIE 27, STRZELECKI 033, MOOMBA 321, MOOMBA 322, BIG LAKE 63, STRZELECKI 37 | Rigless - Australia | J.24.126589 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-07-09 10:00 | 2024-07-08 21:00 |  | 2024-07-09 10:00 | 2024-08-07 23:59 |  | 2024-08-07 23:59 | Moomba WL | ADuong4 | 2024-08-27 17:27 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 14263.16 | 2 |  | L0 - No RO |  | 100 | 100 | 0 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033291 | O.1033291.06 | A.1033291.06.01 | Moomba 318 CBL | SANTOS LIMITED | NEPHRITE SOUTH 16, MOOMBA 317, MOOMBA 318, MOOMBA 330, MOOMBA 331, MOOMBA 332, GIDGEALPA 70, MOOMBA 287 | Rigless - Australia | J.24.041745 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2024-03-18 | 2024-01-20 15:00 |  | 2024-03-18 | 2024-04-10 11:59 |  | 2024-04-10 11:59 | Moomba WL | ADuong4 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 9 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033291 | O.1033291.06 | A.1033291.06.02 | Tindilpie Campaign | SANTOS LIMITED | TINDILPIE 19, TINDILPIE 20, MOOMBA 315, DORODILLO 6, TOOLACHEE 58 | Rigless - Australia | J.24.052239 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2024-02-12 10:00 | 2024-02-11 18:00 |  | 2024-02-12 10:00 | 2024-02-29 23:59 |  | 2024-02-29 23:59 | Moomba WL | ADuong4 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 10 |  | L0 - No RO |  | 91.7 | 50 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Adel Mohammad Alhashemi | WL Production Services
P.1033291 | O.1033291.06 | A.1033291.06.03 | Tirrawarra Campaign | SANTOS LIMITED | DORODILLO 6, GIDGEALPA 70 | Rigless - Australia | J.24.058729 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2024-02-28 | 2024-02-27 15:00 |  | 2024-02-28 | 2024-03-02 23:59 |  | 2024-03-02 23:59 | Moomba WL | ADuong4 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 3 |  | L0 - No RO |  | 91.7 | 100 | 0 | 50 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Adel Mohammad Alhashemi | WL Production Services
P.1033291 | O.1033291.06 | A.1033291.06.05 | SWQ Campaign April/May | SANTOS LIMITED | GALEX 4, MOOMBA 163, MOOMBA 169ST1, TIRRAWARRA 99, MOOMBA 321, MOOMBA 322, FLY LAKE 29, FLY LAKE 28, DARALINGIE 27, NEPHRITE SOUTH 7, TANTANNA 13, DORODILLO 6, SERPENTINE 1 | Rigless - Australia | J.24.089222 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-04-24 08:00 | 2024-04-24 08:00 |  | 2024-04-24 08:00 | 2024-07-15 23:59 |  | 2024-07-15 23:59 | Moomba WL | ADuong4 | 2024-08-13 16:24 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 14263.16 | 1 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033291 | O.1033291.06 | A.1033291.06.04 | Psyche Campaign | SANTOS LIMITED | BARYULAH 7ST1, PSYCHE 5, PSYCHE 8, GIDGEALPA 70, GIDGEALPA 71, GIDGEALPA 72, BARINA 1, MARABOOKA 14, BARINA 1 | Rigless - Australia | J.24.062142 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-03-03 | 2024-03-02 17:00 | 2024-03-02 13:00 | 2024-03-03 | 2024-04-06 23:59 | 2024-04-07 | 2024-04-06 23:59 | Moomba WL | AJaved15 | 2024-05-30 09:36 | ADuong4 |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 8 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.01 | SWPT 420 Q3 July | SANTOS LIMITED | WELLINGTON 4, CUISINIER 34, ACRUS 1, DAMPIERRE 1 | Rigless - Australia | J.24.008545 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-09 17:00 | 2023-07-05 14:00 | 2023-07-09 | 2023-07-09 17:00 | 2023-07-31 04:59 | 2023-07-31 | 2023-07-31 04:59 | Moomba WL | ymoradi2 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 17 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.11 | SWQ Campaign | SANTOS LIMITED | DURHAM DOWNS NORTH 3, DAMPIERRE 1, LEGHORN 1, PSYCHE 8, PSYCHE 9 | Rigless - Australia | J.23.113020 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-22 | 2023-07-21 | 2023-07-22 | 2023-07-22 | 2023-08-01 23:59 | 2023-08-01 | 2023-08-01 23:59 | Moomba WL | ADuong4 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.12 | SWPT U420 Rigless OPS | SANTOS LIMITED | WELLINGTON 4, WINNINIA NORTH 5, WINNINIA NORTH 6 | Rigless - Australia | J.23.127670 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-08-29 | 2023-08-28 | 2023-08-29 | 2023-08-29 | 2023-08-30 23:59 | 2023-08-31 | 2023-08-30 23:59 | Moomba WL | NAndilla | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 8 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.13 | Packer Campaign | SANTOS LIMITED | WINNINIA NORTH 6, PSYCHE 8, PSYCHE 9, WELLINGTON 4, MOOMBA 305, MOOMBA 306, MOOMBA 301, MOOMBA 309, MOOMBA 310, BIG LAKE 172, SWAN LAKE 5, MOOMBA 311, MOOMBA 312, MERANJI 29, MERANJI 30, MERANJI 32, MERANJI 31 | Rigless - Australia | J.23.129106 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-09-04 17:00 | 2023-08-31 | 2023-09-03 14:00 | 2023-09-04 17:00 | 2023-10-31 16:59 | 2023-10-31 | 2023-10-31 16:59 | Moomba WL | ADuong4 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 108179.52 | 3 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.14 | Tirrawarra Campaign | SANTOS LIMITED | TIRRAWARRA 100, TIRRAWARRA 103, DULLINGARI NORTH 26, MOON NORTH WEST 1, HECTOR 1, ANNA NORTH 1, WACKETT 6, WACKETT SOUTH 1, KARMONA 3, WHANTO 1, BANTAM 1, WHANTO 4, WHANTO SOUTH WEST 1, TARTULLA 9, TIRRAWARRA 106, HERA 2 | Rigless - Australia | J.23.152919 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-10-13 | 2023-10-12 |  | 2023-10-13 | 2023-11-30 23:59 |  | 2023-11-30 23:59 | Moomba WL | ADuong4 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 1 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.27 | Extension | SANTOS LIMITED | WINNINIA NORTH 6, PSYCHE 8, PSYCHE 9, WELLINGTON 4, MOOMBA 305, MOOMBA 306, MOOMBA 301, MOOMBA 309, MOOMBA 310, BIG LAKE 172, SWAN LAKE 5, MOOMBA 311, MOOMBA 312, MERANJI 29, MERANJI 30, MERANJI 32, MERANJI 31 | Rigless - Australia | J.24.104593 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-07-01 17:00 | 2024-06-27 |  | 2024-07-01 17:00 | 2024-07-30 16:59 |  | 2024-07-30 13:59 | Moomba WL | KKeese | 2024-07-24 07:41 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.20 | SWPT 420 Jun 2024 | SANTOS LIMITED | WINNINIA NORTH 6, PSYCHE 8, PSYCHE 9, WELLINGTON 4, MOOMBA 305, MOOMBA 306, MOOMBA 301, MOOMBA 309, MOOMBA 310, BIG LAKE 172, SWAN LAKE 5, MOOMBA 311, MOOMBA 312, MERANJI 29, MERANJI 30, MERANJI 32, MERANJI 31 | Rigless - Australia | J.24.022994 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-06-01 17:00 | 2024-05-28 |  | 2024-06-01 17:00 | 2024-06-30 16:59 |  | 2024-06-30 13:59 | Moomba WL | KKeese | 2024-06-26 14:56 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.19 | SWPT 420 May 2024 | SANTOS LIMITED | WINNINIA NORTH 6, PSYCHE 8, PSYCHE 9, WELLINGTON 4, MOOMBA 305, MOOMBA 306, MOOMBA 301, MOOMBA 309, MOOMBA 310, BIG LAKE 172, SWAN LAKE 5, MOOMBA 311, MOOMBA 312, MERANJI 29, MERANJI 30, MERANJI 32, MERANJI 31 | Rigless - Australia | J.24.022993 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-05-01 17:00 | 2024-04-27 | 2024-04-30 14:00 | 2024-05-01 17:00 | 2024-05-31 16:59 | 2024-05-30 21:00 | 2024-05-31 13:59 | Moomba WL | KKeese | 2024-05-23 15:20 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.26 | SWPT 420 Dec 2024 | SANTOS LIMITED | WINNINIA NORTH 6, PSYCHE 8, PSYCHE 9, WELLINGTON 4, MOOMBA 305, MOOMBA 306, MOOMBA 301, MOOMBA 309, MOOMBA 310, BIG LAKE 172, SWAN LAKE 5, MOOMBA 311, MOOMBA 312, MERANJI 29, MERANJI 30, MERANJI 32, MERANJI 31 | Rigless - Australia | J.24.023000 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-12-01 17:00 | 2024-11-27 | 2024-11-30 15:00 | 2024-12-01 17:00 | 2024-12-31 16:59 | 2024-12-30 22:00 | 2024-12-31 13:59 | Moomba WL | KKeese | 2024-05-10 08:23 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.25 | SWPT 420 Nov 2024 | SANTOS LIMITED | WINNINIA NORTH 6, PSYCHE 8, PSYCHE 9, WELLINGTON 4, MOOMBA 305, MOOMBA 306, MOOMBA 301, MOOMBA 309, MOOMBA 310, BIG LAKE 172, SWAN LAKE 5, MOOMBA 311, MOOMBA 312, MERANJI 29, MERANJI 30, MERANJI 32, MERANJI 31 | Rigless - Australia | J.24.022999 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-11-01 17:00 | 2024-10-28 | 2024-10-31 15:00 | 2024-11-01 17:00 | 2024-11-30 16:59 | 2024-11-29 22:00 | 2024-11-30 13:59 | Moomba WL | KKeese | 2024-05-10 08:23 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.24 | SWPT 420 Oct 2024 | SANTOS LIMITED | WINNINIA NORTH 6, PSYCHE 8, PSYCHE 9, WELLINGTON 4, MOOMBA 305, MOOMBA 306, MOOMBA 301, MOOMBA 309, MOOMBA 310, BIG LAKE 172, SWAN LAKE 5, MOOMBA 311, MOOMBA 312, MERANJI 29, MERANJI 30, MERANJI 32, MERANJI 31 | Rigless - Australia | J.24.022998 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-10-01 17:00 | 2024-09-27 | 2024-09-30 14:00 | 2024-10-01 17:00 | 2024-10-31 16:59 | 2024-10-30 22:00 | 2024-10-31 14:59 | Moomba WL | KKeese | 2024-05-10 08:23 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.23 | SWPT 420 Sep 2024 | SANTOS LIMITED | WINNINIA NORTH 6, PSYCHE 8, PSYCHE 9, WELLINGTON 4, MOOMBA 305, MOOMBA 306, MOOMBA 301, MOOMBA 309, MOOMBA 310, BIG LAKE 172, SWAN LAKE 5, MOOMBA 311, MOOMBA 312, MERANJI 29, MERANJI 30, MERANJI 32, MERANJI 31 | Rigless - Australia | J.24.022997 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-09-01 17:00 | 2024-08-28 | 2024-08-31 14:00 | 2024-09-01 17:00 | 2024-09-30 16:59 | 2024-09-29 21:00 | 2024-09-30 13:59 | Moomba WL | KKeese | 2024-05-10 08:23 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.22 | SWPT 420 Aug 2024 | SANTOS LIMITED | WINNINIA NORTH 6, PSYCHE 8, PSYCHE 9, WELLINGTON 4, MOOMBA 305, MOOMBA 306, MOOMBA 301, MOOMBA 309, MOOMBA 310, BIG LAKE 172, SWAN LAKE 5, MOOMBA 311, MOOMBA 312, MERANJI 29, MERANJI 30, MERANJI 32, MERANJI 31 | Rigless - Australia | J.24.022996 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-08-01 17:00 | 2024-07-28 | 2024-07-31 14:00 | 2024-08-01 17:00 | 2024-08-31 16:59 | 2024-08-30 21:00 | 2024-08-31 13:59 | Moomba WL | KKeese | 2024-05-10 08:22 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.21 | SWPT 420 Jul 2024 | SANTOS LIMITED | WINNINIA NORTH 6, PSYCHE 8, PSYCHE 9, WELLINGTON 4, MOOMBA 305, MOOMBA 306, MOOMBA 301, MOOMBA 309, MOOMBA 310, BIG LAKE 172, SWAN LAKE 5, MOOMBA 311, MOOMBA 312, MERANJI 29, MERANJI 30, MERANJI 32, MERANJI 31 | Rigless - Australia | J.24.022995 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-07-01 17:00 | 2024-06-27 | 2024-06-30 14:00 | 2024-07-01 17:00 | 2024-07-31 16:59 | 2024-07-30 21:00 | 2024-07-31 13:59 | Moomba WL | KKeese | 2024-05-08 08:33 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.18 | SWPT 420 Apr 2024 | SANTOS LIMITED | WINNINIA NORTH 6, PSYCHE 8, PSYCHE 9, WELLINGTON 4, MOOMBA 305, MOOMBA 306, MOOMBA 301, MOOMBA 309, MOOMBA 310, BIG LAKE 172, SWAN LAKE 5, MOOMBA 311, MOOMBA 312, MERANJI 29, MERANJI 30, MERANJI 32, MERANJI 31 | Rigless - Australia | J.24.022992 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-04-01 17:00 | 2024-03-28 | 2024-03-31 15:00 | 2024-04-01 17:00 | 2024-04-30 16:59 | 2024-04-29 21:00 | 2024-04-30 12:59 | Moomba WL | KKeese | 2024-04-23 14:05 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.17 | SWPT 420 Mar 2024 | SANTOS LIMITED | WINNINIA NORTH 6, PSYCHE 8, PSYCHE 9, WELLINGTON 4, MOOMBA 305, MOOMBA 306, MOOMBA 301, MOOMBA 309, MOOMBA 310, BIG LAKE 172, SWAN LAKE 5, MOOMBA 311, MOOMBA 312, MERANJI 29, MERANJI 30, MERANJI 32, MERANJI 31 | Rigless - Australia | J.24.021437 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-03-01 17:00 | 2024-02-26 | 2024-02-29 15:00 | 2024-03-01 17:00 | 2024-03-31 16:59 | 2024-03-30 22:00 | 2024-03-31 13:59 | Moomba WL | KKeese | 2024-04-02 15:01 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.16 | SWPT 420 Feb 2024 | SANTOS LIMITED | WINNINIA NORTH 6, PSYCHE 8, PSYCHE 9, WELLINGTON 4, MOOMBA 305, MOOMBA 306, MOOMBA 301, MOOMBA 309, MOOMBA 310, BIG LAKE 172, SWAN LAKE 5, MOOMBA 311, MOOMBA 312, MERANJI 29, MERANJI 30, MERANJI 32, MERANJI 31 | Rigless - Australia | J.24.021436 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-02-01 17:00 | 2024-01-28 |  | 2024-02-01 17:00 | 2024-02-29 16:59 |  | 2024-02-29 15:59 | Moomba WL | KKeese | 2024-04-02 14:58 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.15 | SWPT 420 Jan 2024 | SANTOS LIMITED | WINNINIA NORTH 6, PSYCHE 8, PSYCHE 9, WELLINGTON 4, MOOMBA 305, MOOMBA 306, MOOMBA 301, MOOMBA 309, MOOMBA 310, BIG LAKE 172, SWAN LAKE 5, MOOMBA 311, MOOMBA 312, MERANJI 29, MERANJI 30, MERANJI 32, MERANJI 31 | Rigless - Australia | J.24.021435 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-01-01 17:00 | 2023-12-28 |  | 2024-01-01 17:00 | 2024-01-31 16:59 |  | 2024-01-31 15:59 | Moomba WL | KKeese | 2023-12-30 08:18 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.10 | SWPT 420 Q3 December | SANTOS LIMITED | WHANTO 1, BANTAM 1, TIRRAWARRA 106, KARMONA 3, HERA 2, TARTULLA 9, WHANTO SOUTH WEST 1, WHANTO 4 | Rigless - Australia | J.24.008554 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-12-07 17:00 | 2024-12-05 14:00 |  | 2024-12-07 17:00 | 2025-01-06 04:59 |  | 2025-01-06 04:59 | Moomba WL | ymoradi2 | 2023-11-17 21:25 | SLie4 |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 17 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.08 | SWPT 420 Q3 October | SANTOS LIMITED | WHANTO 1, BANTAM 1, TIRRAWARRA 106, KARMONA 3, HERA 2, TARTULLA 9, WHANTO SOUTH WEST 1, WHANTO 4 | Rigless - Australia | J.24.008552 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-10-07 17:00 | 2024-10-05 14:00 |  | 2024-10-07 17:00 | 2024-11-06 04:59 |  | 2024-11-06 04:59 | Moomba WL | ymoradi2 | 2023-11-17 21:25 | SLie4 |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 17 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.09 | SWPT 420 Q3 November | SANTOS LIMITED | WHANTO 1, BANTAM 1, TIRRAWARRA 106, KARMONA 3, HERA 2, TARTULLA 9, WHANTO SOUTH WEST 1, WHANTO 4 | Rigless - Australia | J.24.008553 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-11-07 17:00 | 2024-11-05 14:00 |  | 2024-11-07 17:00 | 2024-12-06 04:59 |  | 2024-12-06 04:59 | Moomba WL | ymoradi2 | 2023-11-17 21:25 | SLie4 |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 17 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.07 | SWPT 420 Q3 September | SANTOS LIMITED | WHANTO 1, BANTAM 1, TIRRAWARRA 106, KARMONA 3, HERA 2, TARTULLA 9, WHANTO SOUTH WEST 1, WHANTO 4 | Rigless - Australia | J.24.008551 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-09-07 17:00 | 2024-09-05 14:00 |  | 2024-09-07 17:00 | 2024-10-06 05:59 |  | 2024-10-06 07:59 | Moomba WL | ymoradi2 | 2023-11-17 21:25 | SLie4 |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 17 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.06 | SWPT 420 Q3 December | SANTOS LIMITED | WHANTO 1, BANTAM 1, TIRRAWARRA 106, KARMONA 3, HERA 2, TARTULLA 9, WHANTO SOUTH WEST 1, WHANTO 4 | Rigless - Australia | J.24.008550 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-12-07 17:00 | 2024-12-05 14:00 |  | 2024-12-07 17:00 | 2025-01-05 04:59 |  | 2025-01-05 04:59 | Moomba WL | ymoradi2 | 2023-11-17 21:25 | SLie4 |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.05 | SWPT 420 Q3 November | SANTOS LIMITED | WHANTO 1, BANTAM 1, TIRRAWARRA 106, KARMONA 3, HERA 2, TARTULLA 9, WHANTO SOUTH WEST 1, WHANTO 4 | Rigless - Australia | J.24.008549 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-11-07 17:00 | 2024-11-05 14:00 |  | 2024-11-07 17:00 | 2024-12-06 04:59 |  | 2024-12-06 04:59 | Moomba WL | ymoradi2 | 2023-11-17 21:25 | SLie4 |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.03 | SWPT 420 Q3 September | SANTOS LIMITED | WHANTO 1, BANTAM 1, TIRRAWARRA 106, KARMONA 3, HERA 2, TARTULLA 9, WHANTO SOUTH WEST 1, WHANTO 4 | Rigless - Australia | J.24.008547 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-09-07 17:00 | 2024-09-05 14:00 |  | 2024-09-07 17:00 | 2024-10-06 05:59 |  | 2024-10-06 05:59 | Moomba WL | ymoradi2 | 2023-11-17 21:25 | SLie4 |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.04 | SWPT 420 Q3 October | SANTOS LIMITED | WHANTO 1, BANTAM 1, TIRRAWARRA 106, KARMONA 3, HERA 2, TARTULLA 9, WHANTO SOUTH WEST 1, WHANTO 4 | Rigless - Australia | J.24.008548 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-10-07 17:00 | 2024-10-05 14:00 |  | 2024-10-07 17:00 | 2024-11-05 04:59 |  | 2024-11-05 04:59 | Moomba WL | ymoradi2 | 2023-11-17 21:25 | SLie4 |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.05 | A.1033291.05.02 | SWPT 420 Q3 August | SANTOS LIMITED | WHANTO 1, BANTAM 1, TIRRAWARRA 106, KARMONA 3, HERA 2, TARTULLA 9, WHANTO SOUTH WEST 1, WHANTO 4 | Rigless - Australia | J.24.008546 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-08-07 17:00 | 2024-08-05 14:00 |  | 2024-08-07 17:00 | 2024-09-06 04:59 |  | 2024-09-06 04:59 | Moomba WL | ymoradi2 | 2023-11-17 21:25 | SLie4 |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 19 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.33 | SWQ Ops | SANTOS LIMITED | ACRUS 1, LEPARD 3, KAPPA 1, HECTOR 1, DURHAM DOWNS NORTH 6, TIRRAWARRA 108, COONATIE 5, CROWSNEST 2, EUROPA 1, MARSILEA 002, MOOMBA 313, MOOMBA 314, MERUPA 4, TARWONGA 8, TOOLACHEE 57, TOOLACHEE 59, TOOLACHEE 58 | Rigless - Australia | J.23.168403 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-11-17 | 2023-11-21 |  | 2023-12-27 | 2024-02-03 23:59 |  | 2023-12-25 23:59 | Moomba WL | ADuong4 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 1 |  | L0 - No RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 2 |  |  |  | 0 |  |  |  | Mohammad Adel Mohammad Alhashemi | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.29 | Well 28 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040986 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-06-20 22:00 | 2023-06-21 |  | 2023-06-21 | 2023-06-23 23:59 |  | 2023-06-23 23:59 | Moomba WL | KKeese | 2023-06-13 09:30 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.28 | Well 27 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.101151 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-06-17 22:00 | 2023-06-18 |  | 2023-06-18 | 2023-06-20 23:59 |  | 2023-06-20 23:59 | Moomba WL | KKeese | 2023-06-13 09:30 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.27 | Well 26 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040985 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-06-14 22:00 | 2023-06-15 |  | 2023-06-15 | 2023-06-17 23:59 |  | 2023-06-17 23:59 | Moomba WL | KKeese | 2023-06-13 09:30 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.26 | Well 25 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040976 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-06-11 22:00 | 2023-06-12 |  | 2023-06-12 | 2023-06-14 23:59 |  | 2023-06-14 23:59 | Moomba WL | KKeese | 2023-06-13 09:30 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.25 | Well 24 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040975 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-06-08 22:00 | 2023-06-09 |  | 2023-06-09 | 2023-06-11 23:59 |  | 2023-06-11 23:59 | Moomba WL | KKeese | 2023-06-13 09:30 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.24 | Well 23 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040974 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-06-05 22:00 | 2023-06-06 |  | 2023-06-06 | 2023-06-08 23:59 |  | 2023-06-08 23:59 | Moomba WL | KKeese | 2023-06-13 09:30 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.23 | Well 22 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040973 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-06-02 22:00 | 2023-06-03 |  | 2023-06-03 | 2023-06-05 23:59 |  | 2023-06-05 23:59 | Moomba WL | KKeese | 2023-06-13 09:29 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.22 | Well 21 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040972 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-05-30 22:00 | 2023-05-31 |  | 2023-05-31 | 2023-06-02 23:59 |  | 2023-06-02 23:59 | Moomba WL | KKeese | 2023-06-13 09:29 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.30 | Well 29 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040987 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-06-23 22:00 | 2023-06-24 |  | 2023-06-24 | 2023-06-26 23:59 |  | 2023-06-26 23:59 | Moomba WL | KKeese | 2023-05-29 10:37 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.31 | Well 30 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040988 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-06-26 22:00 | 2023-06-27 |  | 2023-06-27 | 2023-06-29 23:59 |  | 2023-06-29 23:59 | Moomba WL | KKeese | 2023-05-29 10:37 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.21 | Well 20 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040971 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-05-27 22:00 | 2023-05-28 |  | 2023-05-28 | 2023-05-30 23:59 |  | 2023-05-30 23:59 | Moomba WL | KKeese | 2023-05-22 20:19 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.20 | Well 18 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040970 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-05-24 22:00 | 2023-05-25 |  | 2023-05-25 | 2023-05-27 23:59 |  | 2023-05-27 23:59 | Moomba WL | KKeese | 2023-05-22 20:18 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.18 | Well 17 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.088168 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-05-18 22:00 | 2023-05-19 |  | 2023-05-19 | 2023-05-21 23:59 |  | 2023-05-21 23:59 | Moomba WL | KKeese | 2023-05-22 20:18 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.19 | Well 18 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040969 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-05-21 22:00 | 2023-05-22 |  | 2023-05-22 | 2023-05-24 23:59 |  | 2023-05-24 23:59 | Moomba WL | KKeese | 2023-05-22 20:18 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.17 | Well 16 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040968 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-05-15 22:00 | 2023-05-16 |  | 2023-05-16 | 2023-05-18 23:59 |  | 2023-05-18 23:59 | Moomba WL | KKeese | 2023-05-22 20:18 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.16 | Well 15 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040967 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-05-12 22:00 | 2023-05-13 |  | 2023-05-13 | 2023-05-15 23:59 |  | 2023-05-15 23:59 | Moomba WL | KKeese | 2023-05-22 20:18 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.15 | Well 14 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040966 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-05-09 22:00 | 2023-05-10 |  | 2023-05-10 | 2023-05-12 23:59 |  | 2023-05-12 23:59 | Moomba WL | KKeese | 2023-05-22 20:18 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.14 | Well 13 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040965 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-05-06 22:00 | 2023-05-07 |  | 2023-05-07 | 2023-05-09 23:59 |  | 2023-05-09 23:59 | Moomba WL | KKeese | 2023-05-22 20:18 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.13 | Well 12 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040964 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-05-03 22:00 | 2023-05-04 |  | 2023-05-04 | 2023-05-06 23:59 |  | 2023-05-06 23:59 | Moomba WL | KKeese | 2023-05-22 20:18 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.12 | Well 11 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040963 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-04-30 22:00 | 2023-05-01 |  | 2023-05-01 | 2023-05-03 23:59 |  | 2023-05-03 23:59 | Moomba WL | KKeese | 2023-05-22 20:18 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.11 | Well 10 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.088167 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-04-27 22:00 | 2023-04-28 |  | 2023-04-28 | 2023-04-30 23:59 |  | 2023-04-30 23:59 | Moomba WL | KKeese | 2023-05-22 20:16 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.09 | Well 8 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.075451 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-04-21 22:00 | 2023-04-22 |  | 2023-04-22 | 2023-04-24 23:59 |  | 2023-04-24 23:59 | Moomba WL | KKeese | 2023-04-27 18:44 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.10 | Well 9 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040961 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-04-24 22:00 | 2023-04-25 |  | 2023-04-25 | 2023-04-27 23:59 |  | 2023-04-27 23:59 | Moomba WL | KKeese | 2023-04-27 18:44 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.08 | Well 7 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040960 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-04-18 22:00 | 2023-04-19 |  | 2023-04-19 | 2023-04-21 23:59 |  | 2023-04-21 23:59 | Moomba WL | KKeese | 2023-04-27 18:44 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.07 | Well 6 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040959 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-04-15 22:00 | 2023-04-16 |  | 2023-04-16 | 2023-04-18 23:59 |  | 2023-04-18 23:59 | Moomba WL | KKeese | 2023-04-27 18:43 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.06 | Well 5 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040958 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-04-12 22:00 | 2023-04-13 |  | 2023-04-13 | 2023-04-15 23:59 |  | 2023-04-15 23:59 | Moomba WL | KKeese | 2023-04-27 18:43 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.05 | Well 4 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040957 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-04-09 22:00 | 2023-04-10 |  | 2023-04-10 | 2023-04-12 23:59 |  | 2023-04-12 23:59 | Moomba WL | KKeese | 2023-04-27 18:43 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.04 | Well 3 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040956 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2023-04-06 22:00 | 2023-04-07 |  | 2023-04-07 | 2023-04-09 23:59 |  | 2023-04-09 23:59 | Moomba WL | KKeese | 2023-04-27 18:43 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.03 | Well 2 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040955 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-04-03 22:00 | 2023-04-04 |  | 2023-04-04 | 2023-04-06 23:59 |  | 2023-04-06 23:59 | Moomba WL | KKeese | 2023-04-27 18:43 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.02 | Well 1 Q2 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.040954 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-03-31 22:00 | 2023-04-01 |  | 2023-04-01 | 2023-04-03 22:59 |  | 2023-04-03 22:59 | Moomba WL | KKeese | 2023-04-27 18:43 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.32 | U420 | SANTOS LIMITED | BIG LAKE 160, AMYEMA 002, MOOMBA 287, MOOMBA 288, MOOMBA 289, MOOMBA 290, TIRRAWARRA 101, TIRRAWARRA 102, TIRRAWARRA 103, BIG LAKE 154 | Rigless - Australia | J.23.041489 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-02-21 | 2023-02-20 |  | 2023-02-21 | 2023-03-15 23:59 |  | 2023-03-24 | Moomba WL | ADuong4 | 2023-03-12 09:04 | FShallal |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 4 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.04 | A.1033291.04.01 | Tirrawarra campaign | SANTOS LIMITED | TIRRAWARRA 99, TIRRAWARRA 100, QUARTPOT 2, BIG LAKE 161, BIG LAKE 162, BIG LAKE 160 | Rigless - Australia | J.23.035694 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-02-07 | 2023-02-06 |  | 2023-02-07 | 2023-02-13 23:59 |  | 2023-02-13 23:59 | Moomba WL | ADuong4 | 2023-02-17 10:10 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 9 |  | L0 - No RO |  | 91.7 | 66.7 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033291 | O.1033291.03 | A.1033291.03.13 | Dorodillo 5 | SANTOS LIMITED | DORODILLO 5, QUASAR 2, AMYEMA 002, MARSILEA 002, DULLINGARI NORTH 26, DULLINGARI NORTH 27, BARYULAH 8, CUISINIER 34 | Rigless - Australia | J.23.098716 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-07 12:00 | 2023-06-06 12:00 | 2023-06-06 14:00 | 2023-06-07 12:00 | 2023-07-23 23:59 | 2023-07-24 | 2023-07-23 23:59 | Moomba WL | ADuong4 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033291 | O.1033291.03 | A.1033291.03.12 | SWPT 420 Q3 December | SANTOS LIMITED | MOOMBA 293, MOOMBA 294, YARROW 003, TIRRAWARRA 105, TIRRAWARRA 108, TIRRAWARRA 109, NAPOWIE 009, KUDRIEKE 003 | Rigless - Australia | J.23.088184 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-12-01 18:00 | 2023-11-29 15:00 |  | 2023-12-01 18:00 | 2023-12-31 05:59 |  | 2023-12-31 05:59 | Moomba WL | KKeese | 2023-12-30 08:21 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 17 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.03 | A.1033291.03.02 | Moomba 294 | SANTOS LIMITED | MOOMBA 293, MOOMBA 294, YARROW 003, TIRRAWARRA 105, TIRRAWARRA 108, TIRRAWARRA 109, NAPOWIE 009, KUDRIEKE 003, TIRRAWARRA 107, BIG LAKE 169, BIG LAKE 168, MOOMBA 298, MOOMBA 297, DORODILLO 7, DORODILLO 5, BIG LAKE 170, BIG LAKE 171 | Rigless - Australia | J.23.074385 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-27 18:00 | 2023-04-25 15:00 | 2023-04-26 04:00 | 2023-04-27 18:00 | 2023-06-07 05:59 | 2023-06-07 | 2023-06-07 05:59 | Moomba WL | ADuong4 | 2023-10-03 21:16 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033291 | O.1033291.03 | A.1033291.03.09 | SWPT 420 Q3 September | SANTOS LIMITED | MOOMBA 293, MOOMBA 294, YARROW 003, TIRRAWARRA 105, TIRRAWARRA 108, TIRRAWARRA 109, NAPOWIE 009, KUDRIEKE 003 | Rigless - Australia | J.23.088181 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-01 18:00 | 2023-08-30 15:00 | 2023-09-01 | 2023-09-01 18:00 | 2023-09-30 05:59 | 2023-09-30 01:00 | 2023-09-30 07:59 | Moomba WL | KKeese | 2023-09-26 09:23 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 17 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.03 | A.1033291.03.11 | SWPT 420 Q3 November | SANTOS LIMITED | MOOMBA 293, MOOMBA 294, YARROW 003, TIRRAWARRA 105, TIRRAWARRA 108, TIRRAWARRA 109, NAPOWIE 009, KUDRIEKE 003 | Rigless - Australia | J.23.088183 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2023-11-01 18:00 | 2023-10-30 15:00 | 2023-11-01 01:00 | 2023-11-01 18:00 | 2023-11-30 05:59 | 2023-11-30 01:00 | 2023-11-30 05:59 | Moomba WL | KKeese | 2023-09-07 10:52 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 17 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.03 | A.1033291.03.10 | SWPT 420 Q3 October | SANTOS LIMITED | MOOMBA 293, MOOMBA 294, YARROW 003, TIRRAWARRA 105, TIRRAWARRA 108, TIRRAWARRA 109, NAPOWIE 009, KUDRIEKE 003 | Rigless - Australia | J.23.088182 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2023-10-01 18:00 | 2023-09-29 15:00 | 2023-10-01 | 2023-10-01 18:00 | 2023-10-31 05:59 | 2023-10-31 01:00 | 2023-10-31 05:59 | Moomba WL | KKeese | 2023-09-07 10:51 | KKeese |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 17 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.03 | A.1033291.03.04 | SWPT 420 Q3 August | SANTOS LIMITED | MOOMBA 293, MOOMBA 294, YARROW 003, TIRRAWARRA 105, TIRRAWARRA 108, TIRRAWARRA 109, NAPOWIE 009, KUDRIEKE 003 | Rigless - Australia | J.23.083629 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-08-01 18:00 | 2023-07-30 15:00 | 2023-08-01 | 2023-08-01 18:00 | 2023-08-31 05:59 | 2023-08-31 | 2023-08-31 05:59 | Moomba WL | KKeese | 2023-08-29 11:24 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 19 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.03 | A.1033291.03.03 | SWPT 420 Q3 July | SANTOS LIMITED | MOOMBA 293, MOOMBA 294, YARROW 003, TIRRAWARRA 105, TIRRAWARRA 108, TIRRAWARRA 109, NAPOWIE 009, KUDRIEKE 003 | Rigless - Australia | J.23.083628 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-07-01 18:00 | 2023-06-29 15:00 | 2023-07-01 | 2023-07-01 18:00 | 2023-07-31 05:59 | 2023-07-31 | 2023-07-31 05:59 | Moomba WL | KKeese | 2023-07-31 08:10 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 17 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.03 | A.1033291.03.08 | SWPT 420 Q3 December | SANTOS LIMITED | MOOMBA 293, MOOMBA 294, YARROW 003, TIRRAWARRA 105, TIRRAWARRA 108, TIRRAWARRA 109, NAPOWIE 009, KUDRIEKE 003 | Rigless - Australia | J.23.085749 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-12-01 18:00 | 2023-11-29 15:00 |  | 2023-12-01 18:00 | 2023-12-30 05:59 |  | 2023-12-30 05:59 | Moomba WL | KKeese | 2023-05-22 21:10 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.03 | A.1033291.03.07 | SWPT 420 Q3 November | SANTOS LIMITED | MOOMBA 293, MOOMBA 294, YARROW 003, TIRRAWARRA 105, TIRRAWARRA 108, TIRRAWARRA 109, NAPOWIE 009, KUDRIEKE 003 | Rigless - Australia | J.23.085748 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-11-01 18:00 | 2023-10-30 15:00 |  | 2023-11-01 18:00 | 2023-11-30 05:59 |  | 2023-11-30 05:59 | Moomba WL | KKeese | 2023-05-22 21:09 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.03 | A.1033291.03.06 | SWPT 420 Q3 October | SANTOS LIMITED | MOOMBA 293, MOOMBA 294, YARROW 003, TIRRAWARRA 105, TIRRAWARRA 108, TIRRAWARRA 109, NAPOWIE 009, KUDRIEKE 003 | Rigless - Australia | J.23.085747 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-01 18:00 | 2023-09-29 15:00 |  | 2023-10-01 18:00 | 2023-10-30 05:59 |  | 2023-10-30 05:59 | Moomba WL | KKeese | 2023-05-22 21:09 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.03 | A.1033291.03.05 | SWPT 420 Q3 September | SANTOS LIMITED | MOOMBA 293, MOOMBA 294, YARROW 003, TIRRAWARRA 105, TIRRAWARRA 108, TIRRAWARRA 109, NAPOWIE 009, KUDRIEKE 003 | Rigless - Australia | J.23.083630 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-01 18:00 | 2023-08-30 15:00 |  | 2023-09-01 18:00 | 2023-09-30 05:59 |  | 2023-09-30 05:59 | Moomba WL | KKeese | 2023-05-22 21:08 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.03 | A.1033291.03.01 | Big Lake 167 | SANTOS LIMITED | BIG LAKE 167, TIRRAWARRA 103, SWAN LAKE 017, MERRIMELIA 39, BIG LAKE 163, BIG LAKE 164, TOOLACHEE 27, TINDILPIE 9, BIG LAKE 165, BIG LAKE 166, EUROPA 1, FORTANNA 2, BOBS WELL 4, MOOMBA 291, MOOMBA 292, MOOMBA 293, MOOMBA 294, TIRRAWARRA 101, TIRRAWARRA 105 | Rigless - Australia | J.23.057381 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-03-16 15:00 | 2023-03-15 15:00 |  | 2023-03-16 15:00 | 2023-04-30 23:59 |  | 2023-04-30 23:59 | Moomba WL | ADuong4 | 2023-04-23 10:31 | ssultan |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.02 | A.1033291.02.01 | Oct-Nov DK | SANTOS LIMITED | BIG LAKE 137, BIG LAKE 146, MOOLION SOUTH 001, BIG LAKE 119, BIG LAKE 97, MOOMBA 241, BIG LAKE 160, SWAN LAKE 017, MOOMBA 296, BROLGA 10, RAGNO 3, WALLACE 2, SECCANTE 9, MOOMBA 280, MOOMBA 281, MOOMBA 282, MOOMBA 295, KUDRIEKE 004, ISOPTERA 5, ISOPTERA 4, ISOPTERA 7, BUGITO 4, BIG LAKE 149, ULANDI 17, ISOPTERA 6, PIRA 6, PIRA 5, DILCHEE 6, DULLINGARI NORTH 010 | Rigless - Australia | J.22.120217 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-23 06:00 | 2022-10-23 |  | 2022-10-23 06:00 | 2022-12-20 08:00 |  | 2022-12-20 08:00 | Moomba WL | DKitney | 2023-05-27 15:31 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 20809.1 | 1 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.02 | A.1033291.02.03 | U420_Feb-2023 | SANTOS LIMITED | ISOPTERA 6, DULLINGARI NORTH 010, DILCHEE 6, PIRA 5, PIRA 6, MOOMBA 302, MOOMBA 303, BROLGA 8, BROLGA 9, MOOMBA 283, BIG LAKE 159, MOOMBA 284, MOOMBA 285, MOOMBA 286 | Rigless - Australia | J.23.030713 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-02-04 06:00 | 2023-02-04 |  | 2023-02-04 06:00 | 2023-03-31 07:00 |  | 2023-03-31 06:00 | Moomba WL | ymoradi2 | 2023-03-07 18:26 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 10404.55 | 3 |  | L0 - No RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033291 | O.1033291.02 | A.1033291.02.02 | U420-DEC22-JAN23 | SANTOS LIMITED | ISOPTERA 6, DULLINGARI NORTH 010, DILCHEE 6, PIRA 5, PIRA 6, MOOMBA 302, MOOMBA 303, BROLGA 8, BROLGA 9, MOOMBA 283, BIG LAKE 159, MOOMBA 284, MOOMBA 285, MOOMBA 286, TIRRAWARRA 100, TIRRAWARRA 99 | Rigless - Australia | J.22.136237 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-27 06:00 | 2022-12-27 |  | 2022-12-27 06:00 | 2023-02-23 08:00 |  | 2023-02-23 08:00 | Moomba WL | ymoradi2 | 2023-02-26 11:45 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 10404.55 | 3 |  | L0 - No RO |  | 75 | 33.3 | 0 | 100 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.25 | Well 25 Q3 2022 | SANTOS LIMITED | NARCOONOWIE 011 | Rigless - Australia | J.22.109850 | RPI | PS-WL-Ops | Medium | Confirmed | Prepare - Mob |  | Design Completed | Design Completed | In Progress | 2022-09-14 12:00 | 2022-09-11 | 2022-09-13 13:00 | 2022-09-14 13:00 | 2022-09-17 12:59 | 2022-09-16 13:00 | 2022-09-17 13:59 | Moomba WL | KKeese | 2023-09-26 10:34 | MAlhashemi |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 0 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.95 | Well 30 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012044 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-03-28 22:00 | 2023-03-29 |  | 2023-03-29 | 2023-03-31 23:59 |  | 2023-03-31 23:59 | Moomba WL | eismail | 2023-04-02 09:53 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.94 | Well 29 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012043 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-03-25 22:00 | 2023-03-26 |  | 2023-03-26 | 2023-03-28 23:59 |  | 2023-03-28 23:59 | Moomba WL | eismail | 2023-04-02 09:53 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.93 | Well 28 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012042 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-03-22 22:00 | 2023-03-23 |  | 2023-03-23 | 2023-03-25 23:59 |  | 2023-03-25 23:59 | Moomba WL | eismail | 2023-04-02 09:53 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.92 | Well 27 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012041 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-03-19 22:00 | 2023-03-20 |  | 2023-03-20 | 2023-03-22 23:59 |  | 2023-03-22 23:59 | Moomba WL | eismail | 2023-04-02 09:53 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.91 | Well 26 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012040 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-03-16 22:00 | 2023-03-17 |  | 2023-03-17 | 2023-03-19 23:59 |  | 2023-03-19 23:59 | Moomba WL | eismail | 2023-04-02 09:53 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.90 | Well 25 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012038 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-03-13 22:00 | 2023-03-14 |  | 2023-03-14 | 2023-03-16 23:59 |  | 2023-03-16 23:59 | Moomba WL | eismail | 2023-04-02 09:53 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.89 | Well 24 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012037 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-03-10 22:00 | 2023-03-11 |  | 2023-03-11 | 2023-03-13 23:59 |  | 2023-03-13 23:59 | Moomba WL | eismail | 2023-04-02 09:53 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.88 | Well 23 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012036 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-03-07 22:00 | 2023-03-08 |  | 2023-03-08 | 2023-03-10 23:59 |  | 2023-03-10 23:59 | Moomba WL | eismail | 2023-04-02 09:53 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.87 | Well 22 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012035 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-03-04 22:00 | 2023-03-05 |  | 2023-03-05 | 2023-03-07 23:59 |  | 2023-03-07 23:59 | Moomba WL | eismail | 2023-04-02 09:52 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.43 | Well 42 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109981 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-11-01 22:00 | 2022-11-02 |  | 2022-11-02 | 2022-11-04 23:59 |  | 2022-11-04 23:59 | Moomba WL | KKeese | 2023-03-07 18:40 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.44 | Well 43 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109982 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-11-04 22:00 | 2022-11-05 |  | 2022-11-05 | 2022-11-07 23:59 |  | 2022-11-07 23:59 | Moomba WL | KKeese | 2023-03-07 18:40 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.45 | Well 44 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109983 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-11-07 22:00 | 2022-11-08 |  | 2022-11-08 | 2022-11-10 23:59 |  | 2022-11-10 23:59 | Moomba WL | KKeese | 2023-03-07 18:40 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.46 | Well 45 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109984 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-11-10 22:00 | 2022-11-11 |  | 2022-11-11 | 2022-11-13 23:59 |  | 2022-11-13 23:59 | Moomba WL | KKeese | 2023-03-07 18:40 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.47 | Well 46 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109985 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-11-13 22:00 | 2022-11-14 |  | 2022-11-14 | 2022-11-16 23:59 |  | 2022-11-16 23:59 | Moomba WL | KKeese | 2023-03-07 18:40 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.48 | Well 47 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109986 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-11-16 22:00 | 2022-11-17 |  | 2022-11-17 | 2022-11-19 23:59 |  | 2022-11-19 23:59 | Moomba WL | KKeese | 2023-03-07 18:40 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.49 | Well 48 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109987 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-11-19 22:00 | 2022-11-20 |  | 2022-11-20 | 2022-11-22 23:59 |  | 2022-11-22 23:59 | Moomba WL | KKeese | 2023-03-07 18:39 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.50 | Well 49 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109988 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-11-22 22:00 | 2022-11-23 |  | 2022-11-23 | 2022-11-25 23:59 |  | 2022-11-25 23:59 | Moomba WL | KKeese | 2023-03-07 18:39 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.51 | Well 50 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109989 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-11-25 22:00 | 2022-11-26 |  | 2022-11-26 | 2022-11-28 23:59 |  | 2022-11-28 23:59 | Moomba WL | KKeese | 2023-03-07 18:39 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.60 | Well 59 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109998 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-12-22 22:00 | 2022-12-23 |  | 2022-12-23 | 2022-12-25 23:59 |  | 2022-12-25 23:59 | Moomba WL | KKeese | 2023-03-07 18:35 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.59 | Well 58 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109997 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-12-19 22:00 | 2022-12-20 |  | 2022-12-20 | 2022-12-22 23:59 |  | 2022-12-22 23:59 | Moomba WL | KKeese | 2023-03-07 18:35 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.58 | Well 57 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109996 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-12-16 22:00 | 2022-12-17 |  | 2022-12-17 | 2022-12-19 23:59 |  | 2022-12-19 23:59 | Moomba WL | KKeese | 2023-03-07 18:35 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.57 | Well 56 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109995 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-12-13 22:00 | 2022-12-14 |  | 2022-12-14 | 2022-12-16 23:59 |  | 2022-12-16 23:59 | Moomba WL | KKeese | 2023-03-07 18:35 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.56 | Well 55 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109994 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-12-10 22:00 | 2022-12-11 |  | 2022-12-11 | 2022-12-13 23:59 |  | 2022-12-13 23:59 | Moomba WL | KKeese | 2023-03-07 18:34 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.55 | Well 54 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109993 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-12-07 22:00 | 2022-12-08 |  | 2022-12-08 | 2022-12-10 23:59 |  | 2022-12-10 23:59 | Moomba WL | KKeese | 2023-03-07 18:34 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.54 | Well 53 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109992 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-12-04 22:00 | 2022-12-05 |  | 2022-12-05 | 2022-12-07 23:59 |  | 2022-12-07 23:59 | Moomba WL | KKeese | 2023-03-07 18:34 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.53 | Well 52 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109991 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-12-01 22:00 | 2022-12-02 |  | 2022-12-02 | 2022-12-04 23:59 |  | 2022-12-04 23:59 | Moomba WL | KKeese | 2023-03-07 18:34 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.52 | Well 51 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109990 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-11-28 22:00 | 2022-11-29 |  | 2022-11-29 | 2022-12-01 23:59 |  | 2022-12-01 23:59 | Moomba WL | KKeese | 2023-03-07 18:34 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.86 | Well 21 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012033 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-03-01 22:00 | 2023-03-02 |  | 2023-03-02 | 2023-03-04 23:59 |  | 2023-03-04 23:59 | Moomba WL | eismail | 2023-03-07 18:29 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.85 | Well 20 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012032 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-02-26 22:00 | 2023-02-27 |  | 2023-02-27 | 2023-03-01 23:59 |  | 2023-03-01 23:59 | Moomba WL | eismail | 2023-03-07 18:28 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.84 | Well 19 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012031 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-02-23 22:00 | 2023-02-24 |  | 2023-02-24 | 2023-02-26 23:59 |  | 2023-02-26 23:59 | Moomba WL | eismail | 2023-03-07 18:28 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.83 | Well 18 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012030 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-02-20 22:00 | 2023-02-21 |  | 2023-02-21 | 2023-02-23 23:59 |  | 2023-02-23 23:59 | Moomba WL | eismail | 2023-03-07 18:28 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.82 | Well 17 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012029 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-02-17 22:00 | 2023-02-18 |  | 2023-02-18 | 2023-02-20 23:59 |  | 2023-02-20 23:59 | Moomba WL | eismail | 2023-03-07 18:28 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.81 | Well 16 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012028 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-02-14 22:00 | 2023-02-15 |  | 2023-02-15 | 2023-02-17 23:59 |  | 2023-02-17 23:59 | Moomba WL | eismail | 2023-03-07 18:28 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.80 | Well 15 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012027 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-02-11 22:00 | 2023-02-12 |  | 2023-02-12 | 2023-02-14 23:59 |  | 2023-02-14 23:59 | Moomba WL | eismail | 2023-03-07 18:28 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.79 | Well 14 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012026 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-02-08 22:00 | 2023-02-09 |  | 2023-02-09 | 2023-02-11 23:59 |  | 2023-02-11 23:59 | Moomba WL | eismail | 2023-03-07 18:28 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.78 | Well 13 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012025 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-02-05 22:00 | 2023-02-06 |  | 2023-02-06 | 2023-02-08 23:59 |  | 2023-02-08 23:59 | Moomba WL | eismail | 2023-03-07 18:28 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.77 | Well 12 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012024 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-02-02 22:00 | 2023-02-03 |  | 2023-02-03 | 2023-02-05 23:59 |  | 2023-02-05 23:59 | Moomba WL | eismail | 2023-03-07 18:28 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.76 | Well 11 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012023 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-01-30 22:00 | 2023-01-31 |  | 2023-01-31 | 2023-02-02 23:59 |  | 2023-02-02 23:59 | Moomba WL | eismail | 2023-03-07 18:27 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.75 | Well 10 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012022 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-01-27 22:00 | 2023-01-28 |  | 2023-01-28 | 2023-01-30 23:59 |  | 2023-01-30 23:59 | Moomba WL | eismail | 2023-03-07 18:25 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.74 | Well 09 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012021 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-01-24 22:00 | 2023-01-25 |  | 2023-01-25 | 2023-01-27 23:59 |  | 2023-01-27 23:59 | Moomba WL | eismail | 2023-03-07 18:24 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.73 | Well 08 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012020 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-01-21 22:00 | 2023-01-22 |  | 2023-01-22 | 2023-01-24 23:59 |  | 2023-01-24 23:59 | Moomba WL | eismail | 2023-03-07 18:24 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.72 | Well 07 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012019 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-01-18 22:00 | 2023-01-19 |  | 2023-01-19 | 2023-01-21 23:59 |  | 2023-01-21 23:59 | Moomba WL | eismail | 2023-03-07 18:24 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.71 | Well 06 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012018 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-01-15 22:00 | 2023-01-16 |  | 2023-01-16 | 2023-01-18 23:59 |  | 2023-01-18 23:59 | Moomba WL | eismail | 2023-03-07 18:24 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.70 | Well 05 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012017 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-01-12 22:00 | 2023-01-13 |  | 2023-01-13 | 2023-01-15 23:59 |  | 2023-01-15 23:59 | Moomba WL | eismail | 2023-03-07 18:24 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.69 | Well 04 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012016 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-01-09 22:00 | 2023-01-10 |  | 2023-01-10 | 2023-01-12 23:59 |  | 2023-01-12 23:59 | Moomba WL | eismail | 2023-03-07 18:24 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.68 | Well 03 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012015 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-01-06 22:00 | 2023-01-07 |  | 2023-01-07 | 2023-01-09 23:59 |  | 2023-01-09 23:59 | Moomba WL | eismail | 2023-03-07 18:24 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.66 | Well 01 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.22.122103 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-12-31 22:00 | 2023-01-01 |  | 2023-01-01 | 2023-01-03 23:59 |  | 2023-01-03 23:59 | Moomba WL | eismail | 2023-03-07 18:24 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.61 | Well 60 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109999 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-12-25 22:00 | 2022-12-26 |  | 2022-12-26 | 2022-12-28 23:59 |  | 2022-12-28 23:59 | Moomba WL | KKeese | 2023-03-07 17:34 | OMosleh |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.67 | Well 02 Q1 2023 | SANTOS LIMITED |  | Rigless - Australia | J.23.012013 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-01-03 22:00 | 2023-01-04 |  | 2023-01-04 | 2023-01-06 23:59 |  | 2023-01-06 23:59 | Moomba WL | eismail | 2023-03-07 17:33 | OMosleh |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.64 | Moomba/Big Lake Campaign | SANTOS LIMITED | Moomba 226 (Dev B), Moomba 273, Moomba 274, MOOMBA 227, MOOMBA 295, BIG LAKE 158, BIG LAKE 160 | Rigless - Australia | J.22.111712 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-10-11 11:00 |  | 2022-10-11 11:00 | 2022-10-24 10:59 |  |  | Moomba WL | ADuong4 | 2022-11-06 10:53 | DKitney |  | No |  |  |  |  | Mazhar Iqbal |  | 11755.8 | 1 |  |  |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.40 | Well 39 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109978 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-10-23 22:00 | 2022-10-24 |  | 2022-10-24 | 2022-10-26 23:59 |  | 2022-10-26 23:59 | Moomba WL | KKeese | 2022-10-23 16:24 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.04 | Oct_Nov-DK | SANTOS LIMITED | MOOMBA 274 | Rigless - Australia | J.22.109829 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-10-20 11:00 | 2022-10-20 10:00 |  | 2022-10-20 12:00 | 2022-10-23 11:59 |  | 2022-10-23 12:59 | Moomba WL | KKeese | 2022-10-19 08:47 | DKitney |  | No |  |  |  |  | Mazhar Iqbal |  | 60268.11 | 3 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 0 | 50 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.65 | Woolkina-3_ Perforation | SANTOS LIMITED |  | Rigless - Australia | J.22.117168 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | Not Required | Not Started | In Progress |  | 2022-10-18 |  | 2022-10-19 | 2022-10-21 23:59 |  |  | Moomba WL | NAndilla | 2022-10-17 07:38 | NAndilla |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 6 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.63 | Swan Lake Campaign | SANTOS LIMITED | SWAN LAKE 018, SWAN LAKE 019, MOOMBA 277, MOOMBA 278, MOOMBA 279 | Rigless - Australia | J.22.110096 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-28 | 2022-09-28 |  | 2022-09-28 | 2022-10-01 23:59 |  | 2022-10-01 23:59 | Moomba WL | ADuong4 | 2022-10-05 10:46 | ADuong4 |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 6 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.62 | U420-Moomba Campaign | SANTOS LIMITED | Barrolka 26, Moomba 266, Moomba 265, Toolachee 36, Moomba 226 (Dev B), RAVEN-1, Hector South East 2, Toolachee, Moomba 95, Moomba 267, Moomba 268, Moomba 269, Moomba 270 | Rigless - Australia | J.22.110086 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-08-20 15:00 | 2022-08-20 14:00 |  | 2022-08-20 16:00 | 2022-09-20 15:59 |  | 2022-08-23 15:59 | Moomba WL | KKeese | 2022-10-03 12:39 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 47592.72 | 4 |  |  |  | 66.7 | 66.7 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.42 | Well 41 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109980 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-10-29 22:00 | 2022-10-30 |  | 2022-10-30 | 2022-11-01 23:59 |  | 2022-11-01 23:59 | Moomba WL | KKeese | 2022-10-03 12:28 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.41 | Well 40 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109979 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-10-26 22:00 | 2022-10-27 |  | 2022-10-27 | 2022-10-29 23:59 |  | 2022-10-29 23:59 | Moomba WL | KKeese | 2022-10-03 12:28 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.39 | Well 38 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109977 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-10-20 22:00 | 2022-10-21 |  | 2022-10-21 | 2022-10-23 23:59 |  | 2022-10-23 23:59 | Moomba WL | KKeese | 2022-10-03 12:28 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.38 | Well 37 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109976 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-10-17 22:00 | 2022-10-18 |  | 2022-10-18 | 2022-10-20 23:59 |  | 2022-10-20 23:59 | Moomba WL | KKeese | 2022-10-03 12:28 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.37 | Well 36 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109975 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-10-14 22:00 | 2022-10-15 |  | 2022-10-15 | 2022-10-17 23:59 |  | 2022-10-17 23:59 | Moomba WL | KKeese | 2022-10-03 12:28 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.36 | Well 35 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109974 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-10-11 22:00 | 2022-10-12 |  | 2022-10-12 | 2022-10-14 23:59 |  | 2022-10-14 23:59 | Moomba WL | KKeese | 2022-10-03 12:28 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.35 | Well 34 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109973 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-10-08 22:00 | 2022-10-09 |  | 2022-10-09 | 2022-10-11 23:59 |  | 2022-10-11 23:59 | Moomba WL | KKeese | 2022-10-03 12:28 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.34 | Well 33 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109972 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-10-05 22:00 | 2022-10-06 |  | 2022-10-06 | 2022-10-08 23:59 |  | 2022-10-08 23:59 | Moomba WL | KKeese | 2022-10-03 12:28 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.33 | Well 32 Q4 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109971 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-10-01 23:00 | 2022-10-03 |  | 2022-10-03 | 2022-10-05 23:59 |  | 2022-10-05 00:59 | Moomba WL | KKeese | 2022-10-03 12:27 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.32 | Well 31 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109970 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-09-29 23:00 | 2022-09-30 |  | 2022-09-30 | 2022-10-03 00:59 |  | 2022-10-03 01:59 | Moomba WL | KKeese | 2022-10-03 12:27 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.31 | U420 - August Campaign | SANTOS LIMITED | Barrolka 26, Moomba 266, Moomba 265, Toolachee 36, Moomba 226 (Dev B), RAVEN-1, Hector South East 2, Toolachee, Moomba 95, Moomba 267, Moomba 268, DELLA #23 | Rigless - Australia | J.22.109960 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-08-01 15:00 | 2022-08-01 14:00 |  | 2022-08-01 16:00 | 2022-09-01 15:59 |  | 2022-08-04 15:59 | Moomba WL | JMoraes2 | 2022-10-03 12:26 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 95185.44 | 4 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.30 | Well 30 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109855 | RPI | PS-WL-Ops | Medium | Confirmed | Prepare - Mob |  | Design Completed | Design Completed | In Progress | 2022-09-25 23:00 | 2022-09-26 |  | 2022-09-27 | 2022-09-29 23:59 |  | 2022-09-29 00:59 | Moomba WL | KKeese | 2022-10-03 12:16 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 79.2 | 41.7 | 0 | 0 | 36.3 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.29 | Well 29 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109854 | RPI | PS-WL-Ops | Medium | Confirmed | Prepare - Mob |  | Design Completed | Design Completed | In Progress | 2022-09-23 23:00 | 2022-09-24 |  | 2022-09-24 | 2022-09-26 23:59 |  | 2022-09-27 00:59 | Moomba WL | KKeese | 2022-10-03 12:16 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 79.2 | 41.7 | 0 | 0 | 36.3 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.28 | Well 28 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109853 | RPI | PS-WL-Ops | Medium | Confirmed | Prepare - Mob |  | Design Completed | Design Completed | In Progress | 2022-09-20 23:00 | 2022-09-21 |  | 2022-09-21 | 2022-09-23 23:59 |  | 2022-09-24 00:59 | Moomba WL | KKeese | 2022-10-03 12:16 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 79.2 | 41.7 | 0 | 0 | 36.3 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.27 | Well 27 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109852 | RPI | PS-WL-Ops | Medium | Confirmed | Prepare - TLM/OP |  | Design Completed | Design Completed | In Progress | 2022-09-17 23:00 | 2022-09-18 |  | 2022-09-18 | 2022-09-20 23:59 |  | 2022-09-21 00:59 | Moomba WL | KKeese | 2022-10-03 12:16 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 79.2 | 41.7 | 0 | 0 | 36.3 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.26 | Well 26 Q3 2022 | SANTOS LIMITED | NARCOONOWIE 012 | Rigless - Australia | J.22.109851 | RPI | PS-WL-Ops | Medium | Confirmed | Prepare - Mob |  | Design Completed | Design Completed | In Progress | 2022-09-14 23:00 | 2022-09-15 |  | 2022-09-15 | 2022-09-17 23:59 |  | 2022-09-18 00:59 | Moomba WL | KKeese | 2022-10-03 12:16 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 0 | 50 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.24 | Well 24 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109849 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-09-07 23:00 | 2022-09-08 |  | 2022-09-08 | 2022-09-10 23:59 |  | 2022-09-11 00:59 | Moomba WL | KKeese | 2022-10-03 12:16 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.23 | Well 23 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109848 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-09-04 23:00 | 2022-09-05 |  | 2022-09-05 | 2022-09-07 23:59 |  | 2022-09-08 00:59 | Moomba WL | KKeese | 2022-10-03 12:16 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.22 | Karmona 6-CPST,Casing Patch | SANTOS LIMITED | Karmona 6 | Rigless - Australia | J.22.109847 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-06 07:00 | 2022-09-06 |  | 2022-09-06 08:00 | 2022-09-09 07:59 |  | 2022-09-09 07:59 | Moomba WL | KKeese | 2022-10-03 12:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  |  |  | 66.7 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.21 | Moomba 275-276_Competition-replacement | SANTOS LIMITED | Moomba 275, Moomba 276 | Rigless - Australia | J.22.109846 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-08-29 23:00 | 2022-08-30 |  | 2022-08-30 | 2022-09-01 23:59 |  | 2022-09-01 23:59 | Moomba WL | KKeese | 2022-10-03 12:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.20 | Swan Lake 16-Perfo Link | SANTOS LIMITED | Swan Lake 16 | Rigless - Australia | J.22.109845 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-03 14:00 | 2022-09-03 13:00 |  | 2022-09-03 15:00 | 2022-09-06 14:59 |  | 2022-09-06 14:59 | Moomba WL | KKeese | 2022-10-03 12:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.19 | Napowie 9- Perf | SANTOS LIMITED | NAPOWIE 009 | Rigless - Australia | J.22.109844 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-08-25 07:00 | 2022-08-25 |  | 2022-08-25 08:00 | 2022-08-28 07:59 |  | 2022-08-28 07:59 | Moomba WL | KKeese | 2022-10-03 12:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  |  |  | 75 | 16.7 | 0 | 75 | 50 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.18 | Well 18 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109843 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-08-20 23:00 | 2022-08-21 |  | 2022-08-21 | 2022-08-23 23:59 |  | 2022-08-24 00:59 | Moomba WL | KKeese | 2022-10-03 12:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.17 | Well 17 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109842 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-08-17 23:00 | 2022-08-18 |  | 2022-08-18 | 2022-08-20 23:59 |  | 2022-08-21 00:59 | Moomba WL | KKeese | 2022-10-03 12:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.16 | Well 16 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109841 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-08-14 23:00 | 2022-08-15 |  | 2022-08-15 | 2022-08-17 23:59 |  | 2022-08-18 00:59 | Moomba WL | KKeese | 2022-10-03 12:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.15 | Well 15 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109840 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-08-11 23:00 | 2022-08-12 |  | 2022-08-12 | 2022-08-14 23:59 |  | 2022-08-15 00:59 | Moomba WL | KKeese | 2022-10-03 12:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.14 | Well 14 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109839 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-08-08 23:00 | 2022-08-09 |  | 2022-08-09 | 2022-08-11 23:59 |  | 2022-08-12 00:59 | Moomba WL | KKeese | 2022-10-03 12:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.13 | Well 13 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109838 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-08-05 23:00 | 2022-08-06 |  | 2022-08-06 | 2022-08-08 23:59 |  | 2022-08-09 00:59 | Moomba WL | KKeese | 2022-10-03 12:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.12 | Well 12 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109837 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-08-02 23:00 | 2022-08-03 |  | 2022-08-03 | 2022-08-05 23:59 |  | 2022-08-06 00:59 | Moomba WL | KKeese | 2022-10-03 12:14 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.11 | Well 11 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109836 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-07-30 23:00 | 2022-07-31 |  | 2022-07-31 | 2022-08-02 23:59 |  | 2022-08-03 00:59 | Moomba WL | KKeese | 2022-10-03 12:14 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.10 | Well 10 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109835 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-07-27 23:00 | 2022-07-28 |  | 2022-07-28 | 2022-07-30 23:59 |  | 2022-07-31 00:59 | Moomba WL | KKeese | 2022-10-03 12:14 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.09 | Well 9 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109834 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-07-24 23:00 | 2022-07-25 |  | 2022-07-25 | 2022-07-27 23:59 |  | 2022-07-28 00:59 | Moomba WL | KKeese | 2022-10-03 12:14 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.08 | Well 8 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109833 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-07-21 23:00 | 2022-07-22 |  | 2022-07-22 | 2022-07-24 23:59 |  | 2022-07-25 00:59 | Moomba WL | KKeese | 2022-10-03 12:14 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.07 | Well 7 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109832 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-07-18 23:00 | 2022-07-19 |  | 2022-07-19 | 2022-07-21 23:59 |  | 2022-07-22 00:59 | Moomba WL | KKeese | 2022-10-03 12:14 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.06 | Well 6 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109831 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-07-15 23:00 | 2022-07-16 |  | 2022-07-16 | 2022-07-18 23:59 |  | 2022-07-19 00:59 | Moomba WL | KKeese | 2022-10-03 12:14 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.05 | Well 5 Q3 2022 | SANTOS LIMITED |  | Rigless - Australia | J.22.109830 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-07-12 23:00 | 2022-07-13 |  | 2022-07-13 | 2022-07-15 23:59 |  | 2022-07-16 00:59 | Moomba WL | KKeese | 2022-10-03 12:14 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.03 | U420 - September Campaign | SANTOS LIMITED | Narcoonowie 011, Narcoonowie 012, Nungeroo West 001 | Rigless - Australia | J.22.109828 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-22 09:00 | 2022-09-22 08:00 |  | 2022-09-22 10:00 | 2022-09-25 09:59 |  | 2022-09-25 09:59 | Moomba WL | KKeese | 2022-10-03 12:14 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 64798.44 | 4 |  |  |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.02 | Lyra 1 - PNX | SANTOS LIMITED | Lyra 1 | Rigless - Australia | J.22.109827 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-07-19 07:00 | 2022-07-19 06:00 |  | 2022-07-19 08:00 | 2022-07-22 07:59 |  | 2022-07-22 06:59 | Moomba WL | KKeese | 2022-10-03 12:13 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 42639.38 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033291 | O.1033291.01 | A.1033291.01.01 | U420 - July Campaign | SANTOS LIMITED | BARROLKA 26, BOLAH 10, KERNA 7, MOOMBA 271, MOOMBA 273, MOOMBA 274, MOOMBA 268, BIG LAKE 97, MOOMBA 266, MOOMBA 265, TOOLACHEE 36, MOOMBA 226, RAVEN-1, STREZLECKI 17 | Rigless - Australia | J.22.109826 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-07-06 21:54 | 2022-07-04 14:00 |  | 2022-07-04 16:00 | 2022-07-07 15:59 |  | 2022-07-07 15:59 | Moomba WL | KKeese | 2022-10-03 12:13 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 47592.72 | 4 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1033164 | O.1033164.01 | A.1033164.01.01 | CT Well#1 | BURU ENERGY LIMITED |  |  | J.23.008654 | RPI | CT-CIRC | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-01 | 2023-10-01 |  | 2023-10-01 | 2023-11-26 23:59 |  | 2023-11-27 00:59 | AUS East Coast WS | SKanaan | 2022-12-05 13:48 | OMosleh |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1033163 | O.1033163.01 | A.1033163.01.03 | Well-2 ORIGIN NT | ORIGIN ENERGY B2 PTY LIMITED |  |  | J.23.008672 | RPS | FRAC-PROP,FRAC-COMB,FRAC-SLICK, STM-RECHARGE | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-04-01 | 2025-04-01 |  | 2025-04-01 | 2025-05-01 23:59 |  | 2025-05-02 00:59 | AUS East Coast WS | radinegara | 2024-05-15 10:53 | CNevarez2 |  | Yes |  |  |  |  | Aidan Flynn Kohr |  | 0 | 15 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1033163 | O.1033163.01 | A.1033163.01.04 | CT-Well#2 | ORIGIN ENERGY B2 PTY LIMITED |  |  | J.23.008685 | RPI | CT-CIRC | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-04-15 | 2023-04-15 |  | 2023-04-15 | 2023-05-15 23:59 |  | 2023-05-15 23:59 | AUS East Coast WS | radinegara | 2023-02-28 15:24 | HFerdjallah |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 1 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1033163 | O.1033163.01 | A.1033163.01.02 | CT Well#1 | ORIGIN ENERGY B2 PTY LIMITED |  |  | J.23.008655 | RPI | CT-CIRC | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-14 | 2023-03-14 |  | 2023-03-14 | 2023-04-15 23:59 |  | 2023-04-15 22:59 | AUS East Coast WS | SKanaan | 2022-10-30 17:51 | HFerdjallah |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1033163 | O.1033163.01 | A.1033163.01.01 | Well#1 | ORIGIN ENERGY B2 PTY LIMITED |  |  | J.23.008659 | RPS | FRAC-PROP | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-03-14 | 2023-03-14 |  | 2023-03-14 | 2023-04-11 23:59 |  | 2023-04-11 22:59 | AUS East Coast WS | SKanaan | 2022-10-30 17:51 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 15 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1032910 | O.1032910.03 | A.1032910.03.01 | B1 P&A 2024 | EXXONMOBIL PNG LIMITED | ANGORE B1 | Esso PNG LNG Nabors 702 | J.24.070773 | RPE | ES-CH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-07-01 02:00 | 2024-06-24 |  | 2024-07-01 | 2024-07-15 23:59 |  | 2024-07-16 01:59 | Port Moresby WL | CKok3 | 2024-06-27 08:49 | CKok3 | M.1000131.08.53 | No |  |  |  |  | Peter Roche |  | 0 | 3 |  | L0 - No RO |  | 66.7 | 0 | 0 | 0 | 20 |  | 3 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1032910 | O.1032910.02 | A.1032910.02.07 | Hides F2 Perforation | EXXONMOBIL PNG LIMITED | HIDES F2 | Esso PNG LNG Nabors 702 | J.25.008149 | RPE | ES-CH-Ops | Medium | Unconfirmed - 90% | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2025-03-17 | 2025-03-01 | 2025-03-16 | 2025-04-01 | 2025-05-22 23:59 | 2025-05-07 | 2025-05-01 23:59 | Port Moresby WL | CKok3 | 2025-05-29 13:08 | CKok3 | M.1000131.09.53 | No |  |  |  |  | Peter Roche |  | 0 | 2 |  | L0 - No RO |  | 66.7 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1032910 | O.1032910.02 | A.1032910.02.06 | Hides F2 SLK+ Gyro and F1 Contingency SLK AFH Plug | EXXONMOBIL PNG LIMITED | HIDES F2 | Esso PNG LNG Nabors 702 | J.24.118546 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-08-25 | 2024-08-18 | 2024-08-25 | 2024-08-25 | 2024-09-10 23:59 | 2024-09-11 | 2024-09-10 23:59 | Port Moresby WL | CKok3 | 2025-05-21 11:58 | CKok3 | M.1000131.09.60 | No |  |  |  |  | Peter Roche |  | 0 | 1 |  | L0 - No RO |  | 75 | 50 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1032910 | O.1032910.02 | A.1032910.02.08 | Hides F2 SLK Completion | EXXONMOBIL PNG LIMITED | HIDES F2 | Esso PNG LNG Nabors 702 | J.25.011419 | RPI | PS-SLK-Rental-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-03-15 | 2025-03-08 | 2025-03-14 14:00 | 2025-03-15 | 2025-04-19 23:59 | 2025-04-20 | 2025-04-19 23:59 | Port Moresby WL | CKok3 | 2025-05-15 13:36 | CKok3 | M.1000131.09.55 | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 1 |  | L0 - No RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | Wireline Slickline
P.1032910 | O.1032910.02 | A.1032910.02.04 | F2 8.5" x 12.25" Logging | EXXONMOBIL PNG LIMITED | HIDES F2 | Esso PNG LNG Nabors 702 | J.24.070760 | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-02-08 | 2025-01-11 |  | 2025-02-08 | 2025-03-14 23:59 |  | 2025-03-14 23:59 | Port Moresby WL | CKok3 | 2025-03-15 18:47 | RRanjan3 | M.1000131.09.53 | No |  |  |  |  | Shameer Mumtaz Ali |  | 14500 | 4 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1032910 | O.1032910.02 | A.1032910.02.05 | F2 8.5" Logging | EXXONMOBIL PNG LIMITED | HIDES F2 | Esso PNG LNG Nabors 702 | J.24.070769 | RPE | ES-OH-Ops | High | Cancelled | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-03-01 | 2025-02-22 |  | 2025-03-01 | 2025-03-08 23:59 |  | 2025-03-08 23:59 | Port Moresby WL | CKok3 | 2025-02-26 13:01 | CKok3 | M.1000131.09.53 | No |  |  |  |  | Peter Roche |  | 0 | 7 |  | L0 - No RO |  | 66.7 | 0 | 0 | 0 | 20 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1032910 | O.1032910.02 | A.1032910.02.03 | F2 12.25" x 14.25" Logging | EXXONMOBIL PNG LIMITED | HIDES F2 | Esso PNG LNG Nabors 702 | J.24.070759 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-12-18 | 2024-11-10 |  | 2024-12-18 | 2025-01-05 23:59 |  | 2025-01-05 23:59 | Port Moresby WL | CKok3 | 2025-01-05 13:02 | RRanjan3 | M.1000131.09.53 | No |  |  |  |  | Shameer Mumtaz Ali |  | 126814 | 3 |  | L0 - No RO |  | 100 | 100 | 100 | 75 | 92.5 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1032910 | O.1032910.02 | A.1032910.02.02 | F2 15.5" x 17.5" Logging | EXXONMOBIL PNG LIMITED | HIDES F2 | Esso PNG LNG Nabors 702 | J.24.070750 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-11-13 | 2024-10-27 |  | 2024-11-13 | 2024-11-20 23:59 |  | 2024-11-20 23:59 | Port Moresby WL | CKok3 | 2024-11-25 01:48 | RRanjan3 | M.1000131.09.53 | No |  |  |  |  | Shameer Mumtaz Ali |  | 172901 | 3 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1032910 | O.1032910.02 | A.1032910.02.01 | F2 18-3/8" x 20" Logging | EXXONMOBIL PNG LIMITED | HIDES F2 | Esso PNG LNG Nabors 702 | J.24.070746 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-07-15 | 2024-10-20 |  | 2024-10-25 | 2024-11-01 23:59 |  | 2024-11-01 23:59 | Port Moresby WL | CKok3 | 2024-10-24 15:29 | RRanjan3 | M.1000131.09.53 | No |  |  |  |  | Peter Roche |  | 172901 | 3 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1032910 | O.1032910.02 | A.1032910.02.09 | F2 IBC in 20" Casing | EXXONMOBIL PNG LIMITED | HIDES F2 | Esso PNG LNG Nabors 702 | J.24.155840 | RPE | ES-CH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-09-16 | 2024-09-10 |  | 2024-09-16 | 2024-09-18 23:59 |  | 2024-09-18 23:59 | Port Moresby WL | CKok3 | 2024-10-02 13:01 | CKok3 | M.1000131.09.53 | No |  |  |  |  | Shameer Mumtaz Ali |  | 75084 | 1 |  | L0 - No RO |  | 75 | 83.3 | 100 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1032910 | O.1032910.01 | A.1032910.01.19 | Angore C1/C2 SLK Retrieve Gauge | EXXONMOBIL PNG LIMITED | ANGORE C1-BP2 | Esso PNG LNG Nabors 702 | J.24.118543 | RPI | PS-SLK-Rental-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-28 23:59 | 2025-05-29 | 2025-05-28 23:59 | Port Moresby WL | CKok3 | 2025-05-21 11:59 | CKok3 | M.1000131.07.60 | No |  |  |  |  | Peter Roche |  | 0 | 1 |  | L0 - No RO |  | 75 | 50 | 0 | 0 | 37.5 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | Wireline Slickline
P.1032910 | O.1032910.01 | A.1032910.01.21 | Angore C1/C2 WL Set Gauge | EXXONMOBIL PNG LIMITED | ANGORE C1-BP2 | Esso PNG LNG Nabors 702 | J.24.136254 | RPE | ES-CH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-09-26 | 2024-09-19 |  | 2024-09-26 | 2024-10-04 00:59 |  | 2024-10-04 00:59 | Port Moresby WL | CKok3 | 2025-02-02 11:06 | RRanjan3 | M.1000131.07.60 | No |  |  |  |  | Peter Roche |  | 0 | 1 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1032910 | O.1032910.01 | A.1032910.01.13 | Angore_C2 BP1_14.75in X 17in | EXXONMOBIL PNG LIMITED | ANGORE C2 BP-1 | Esso PNG LNG Nabors 702 | J.23.124520 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-09-01 | 2023-08-24 |  | 2023-09-01 | 2023-09-09 23:59 |  | 2023-09-09 23:59 | Port Moresby WL | MElsanousi | 2024-12-20 15:14 | CKok3 | M.1000131.05.53 | No |  |  |  |  | Peter Roche |  | 43141 | 3 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1032910 | O.1032910.01 | A.1032910.01.01 | Pipe Recovery Surface Drilling | EXXONMOBIL PNG LIMITED | ANGORE C1 | Esso PNG LNG Nabors 702 | J.22.110459 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-21 23:59 | 2022-10-15 |  | 2022-11-01 | 2023-07-17 23:59 |  | 2023-07-27 23:59 | Port Moresby WL | PZuliani | 2024-08-21 15:52 | FDPSystemUser | M.1000131.03.53 | No |  |  |  |  | Rob Twigg |  | 572406.47 | 3 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1032910 | O.1032910.01 | A.1032910.01.02 | Angore C1_17in OH Logging | EXXONMOBIL PNG LIMITED | ANGORE C1 | Esso PNG LNG Nabors 702 | J.23.008597 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-06-24 | 2023-06-19 |  | 2023-06-24 | 2023-07-18 23:59 |  | 2023-07-18 23:59 | Port Moresby WL | PZuliani | 2024-08-21 15:52 | FDPSystemUser | M.1000131.03.53 | No |  |  |  |  | Peter Roche |  | 109444.6 | 2 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1032910 | O.1032910.01 | A.1032910.01.03 | Angore_C2_17in OH Logging, | EXXONMOBIL PNG LIMITED | ANGORE C2 | Esso PNG LNG Nabors 702 | J.23.008600 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-08-02 | 2023-07-28 |  | 2023-08-02 | 2023-08-30 23:59 |  | 2023-08-30 23:59 | Port Moresby WL | MElsanousi | 2024-08-21 15:52 | FDPSystemUser | M.1000131.02.53 | No |  |  |  |  | Rob Twigg |  | 106808 | 3 |  | L0 - No RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1032910 | O.1032910.01 | A.1032910.01.04 | Angore_C2 BP1_Nabor_12 1/4 OH X 14 3/4in OH | EXXONMOBIL PNG LIMITED | ANGORE C2 BP-1 | Esso PNG LNG Nabors 702 | J.23.008598 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-09-27 | 2023-09-11 |  | 2023-10-01 | 2023-11-27 23:59 |  | 2023-11-23 23:59 | Port Moresby WL | MElsanousi | 2024-08-21 15:52 | FDPSystemUser | M.1000131.05.53 | Yes |  |  |  | ROE WL Mumbai | Rob Twigg |  | 513204 | 9 |  | L1 - Support RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1032910 | O.1032910.01 | A.1032910.01.05 | Angore_C1 BP2_Nabor_ 14 3/4in x 17 1/2in OH | EXXONMOBIL PNG LIMITED | ANGORE C1-BP2 | Esso PNG LNG Nabors 702 | J.23.008599 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-01-31 | 2024-01-25 |  | 2024-01-31 | 2024-02-01 23:59 |  | 2024-02-23 23:59 | Port Moresby WL | MElsanousi | 2024-08-21 15:52 | FDPSystemUser | M.1000131.07.53 | No |  |  |  |  | Peter Roche |  | 104308 | 2 |  | L0 - No RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1032910 | O.1032910.01 | A.1032910.01.08 | Angore_C2 BP2_8.5in OH Section | EXXONMOBIL PNG LIMITED | ANGORE C2 BP-2 | Esso PNG LNG Nabors 702 | J.23.062653 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2024-01-09 | 2024-01-04 |  | 2024-01-09 | 2024-01-30 23:59 |  | 2024-02-10 23:59 | Port Moresby WL | MElsanousi | 2024-08-21 15:52 | FDPSystemUser | M.1000131.02.53 | No |  |  |  |  | Peter Roche |  | 309312 | 4 |  | L0 - No RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 2 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1032910 | O.1032910.01 | A.1032910.01.11 | Angore_C1 BP2_Nabor_ 10-5/8 x 12-1/4 Logging | EXXONMOBIL PNG LIMITED | ANGORE C1-BP2 | Esso PNG LNG Nabors 702 | J.23.097915 | RPE | ES-CH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-03-12 | 2024-03-09 |  | 2024-03-12 | 2024-03-24 23:59 |  | 2024-03-24 23:59 | Port Moresby WL | MElsanousi | 2024-08-21 15:52 | FDPSystemUser | M.1000131.07.53 | No |  |  |  |  | Peter Roche |  | 167011 | 2 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1032910 | O.1032910.01 | A.1032910.01.12 | Angore C1-BP1_17in X 14.75in OH_Nabor 702 | EXXONMOBIL PNG LIMITED | ANGORE C1-BP1 | Esso PNG LNG Nabors 702 | J.23.107868 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-10 | 2023-07-05 |  | 2023-07-10 | 2023-08-03 23:59 |  | 2023-08-03 23:59 | Port Moresby WL | MElsanousi | 2024-08-21 15:52 | FDPSystemUser | M.1000131.04.53 | No |  |  |  |  | Peter Roche |  | 106808 | 2 |  | L0 - No RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1032910 | O.1032910.01 | A.1032910.01.14 | Exxon_Nabors 702_14in X 13 5/8in CSG | EXXONMOBIL PNG LIMITED | ANGORE C2 BP-1 | Esso PNG LNG Nabors 702 | J.23.133204 | RPE | ES-CH-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Not Started | Design Completed | 2023-09-20 | 2023-09-18 |  | 2023-09-20 | 2023-09-23 23:59 |  | 2023-09-23 23:59 | Port Moresby WL | MElsanousi | 2024-08-21 15:52 | FDPSystemUser | M.1000131.05.53 | No |  |  |  |  | Peter Roche |  | 0 | 2 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1032910 | O.1032910.01 | A.1032910.01.15 | Exxon_Angore C2 BP1_14.75in X 17.5in_Nabor 702 | EXXONMOBIL PNG LIMITED | ANGORE C2 BP-1 | Esso PNG LNG Nabors 702 | J.23.134017 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-09-07 | 2023-08-30 |  | 2023-09-07 | 2023-09-15 23:59 |  | 2023-09-15 23:59 | Port Moresby WL | MElsanousi | 2024-08-21 15:52 | FDPSystemUser | M.1000131.05.53 | No |  |  |  |  | Peter Roche |  | 43141 | 2 |  | L0 - No RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1032910 | O.1032910.01 | A.1032910.01.16 | Angore_C1 BP2_Nabors 702_12.25in X 14.75in OH | EXXONMOBIL PNG LIMITED | ANGORE C1-BP2 | Esso PNG LNG Nabors 702 | J.23.155719 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-02-20 | 2024-02-08 |  | 2024-02-24 | 2024-02-27 23:59 |  | 2024-03-18 23:59 | Port Moresby WL | MElsanousi | 2024-08-21 15:52 | FDPSystemUser | M.1000131.07.53 | No |  |  |  |  | Peter Roche |  | 0 | 2 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1032910 | O.1032910.01 | A.1032910.01.17 | Exxon_Angore C2 BP1_Pipe Recovery | EXXONMOBIL PNG LIMITED | ANGORE C2 BP-1 | Esso PNG LNG Nabors 702 | J.23.165079 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-11-12 | 2023-11-10 |  | 2023-11-12 | 2023-11-30 23:59 |  | 2023-11-30 23:59 | Port Moresby WL | MElsanousi | 2024-08-21 15:52 | FDPSystemUser | M.1000131.05.53 | No |  |  |  |  | Peter Roche |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 66.7 | 0 | 12.5 | 48.8 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1032910 | O.1032910.01 | A.1032910.01.18 | Exxon_Angore C2 BP 2_11 7/8 Liner X 14in | EXXONMOBIL PNG LIMITED | ANGORE C2 BP-2 | Esso PNG LNG Nabors 702 | J.23.172088 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-12-05 | 2023-12-03 |  | 2023-12-05 | 2023-12-23 23:59 |  | 2023-12-23 23:59 | Port Moresby WL | MElsanousi | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Peter Roche |  | 22494 | 2 |  | L0 - No RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1032910 | O.1032910.01 | A.1032910.01.07 | Angore_C1-BP2_8.5in OH Section | EXXONMOBIL PNG LIMITED | ANGORE C1-BP2 | Esso PNG LNG Nabors 702 | J.23.062547 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2024-03-28 | 2024-03-24 |  | 2024-03-28 | 2024-04-02 23:59 |  | 2024-04-03 23:59 | Port Moresby WL | MElsanousi | 2024-08-06 22:51 | RRanjan3 | M.1000131.07.53 | No |  |  |  |  | Peter Roche |  | 118445 | 3 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 5 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1032910 | O.1032910.01 | A.1032910.01.10 | Angore_C1/C2 Completion and Perf | EXXONMOBIL PNG LIMITED | ANGORE C1-BP2 | Esso PNG LNG Nabors 702 | J.23.070157 | RPE | ES-CH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-05-29 | 2024-04-24 |  | 2024-06-13 | 2024-08-03 23:59 |  | 2024-07-13 23:59 | Port Moresby WL | MElsanousi | 2024-07-04 11:19 | CKok3 | M.1000131.07.53 | No |  |  |  |  | Peter Roche |  | 1000357.5 | 2 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 5 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1032910 | O.1032910.01 | A.1032910.01.20 | Angore C2 Completion and Perf | EXXONMOBIL PNG LIMITED | ANGORE C2 BP-2 | Esso PNG LNG Nabors 702 | J.24.119009 | RPE | ES-CH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-06-05 | 2024-04-28 |  | 2024-06-20 | 2024-08-10 23:59 |  | 2024-07-20 23:59 | Port Moresby WL | CKok3 | 2024-06-26 16:50 | RRanjan3 | M.1000131.06.53 | No |  |  |  |  | Peter Roche |  | 1065977.5 | 2 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1032910 | O.1032910.01 | A.1032910.01.09 | Angore_C2_20in USIT | EXXONMOBIL PNG LIMITED | ANGORE C2 | Esso PNG LNG Nabors 702 | J.23.070121 | RPE | ES-CH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-21 | 2023-05-19 |  | 2023-05-21 | 2023-06-02 23:59 |  | 2023-06-02 23:59 | Port Moresby WL | MElsanousi | 2023-05-31 20:41 | PZuliani | M.1000131.02.53 | No |  |  |  |  | Peter Roche |  | 66103 | 1 |  | L0 - No RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1032910 | O.1032910.01 | A.1032910.01.06 | Angore_Surface Conductor | EXXONMOBIL PNG LIMITED | ANGORE C1 | Esso PNG LNG Nabors 702 | J.22.117561 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed |  | 2022-10-18 |  | 2022-10-20 | 2022-10-23 23:59 |  |  | Port Moresby WL | MElsanousi | 2022-10-28 08:55 | MElsanousi | M.1000131.03.60 | No |  |  |  |  | Rob Twigg |  | 47593 | 1 |  |  |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1032767 | O.1032767.01 | A.1032767.01.02 | CBL-VDL | SWEETPEA PETROLEUM PTY LTD | MAVERICK 1, MAVERICK T463 A1 | ENSIGN 970 | J.22.119779 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-10-27 |  | 2022-10-31 06:00 | 2022-11-05 05:59 |  |  | Roma WL | MRony2 | 2022-11-03 22:49 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 20077.97 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1032767 | O.1032767.01 | A.1032767.01.01 | Maverick T463 A1 8.75in Section | SWEETPEA PETROLEUM PTY LTD | MAVERICK-1, MAVERICK T463 A1 | ENSIGN 970 | J.22.111040 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2022-10-08 06:00 | 2022-10-06 |  | 2022-10-08 06:00 | 2022-10-13 05:59 |  | 2022-10-13 06:59 | Roma WL | MRony2 | 2022-10-23 14:08 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 73751.79 | 5 |  | L2 - Shift RO |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1032673 | O.1032673.01 | A.1032673.01.04 | Jadestone Well Integrity logging | JADESTONE ENERGY (AUSTRALIA) PTY LTD | STAG 48H | STAG SNUBBING UNIT 1 | J.23.032775 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-17 | 2023-05-14 | 2023-05-21 | 2023-05-17 | 2023-05-27 23:59 | 2023-06-01 | 2023-05-27 23:59 | New Burn WL | JDukas | 2023-08-21 14:21 | VOliveira5 |  | No |  |  |  |  | Peter Roche |  | 282955 | 1 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1032673 | O.1032673.01 | A.1032673.01.03 | STAG Well integrity | JADESTONE ENERGY (AUSTRALIA) PTY LTD |  | STAG SNUBBING UNIT 1 | J.22.125776 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-12 | 2022-12-09 |  | 2022-12-12 | 2022-12-22 23:59 |  | 2022-12-22 23:59 | New Burn WL | JDukas | 2022-12-07 14:07 | JDukas |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1032673 | O.1032673.01 | A.1032673.01.02 | Stag 44H | JADESTONE ENERGY (AUSTRALIA) PTY LTD | 44-H | STAG SNUBBING UNIT 1 | J.22.110167 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-07-04 |  | 2022-07-07 | 2022-07-17 23:59 |  |  | New Burn WL | VOliveira5 | 2022-10-03 10:02 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 133500 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1032673 | O.1032673.01 | A.1032673.01.01 | Stag-38H | JADESTONE ENERGY (AUSTRALIA) PTY LTD | 38-H | STAG SNUBBING UNIT 1 | J.22.110164 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-05-18 |  | 2022-05-21 | 2022-05-31 23:59 |  |  | New Burn WL | JCade | 2022-10-03 10:01 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 383441 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1032592 | O.1032592.01 | A.1032592.01.01 | Sapphire 5V | BLUE ENERGY | Sapphire 5V | Silver City 23 | J.22.111039 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-07-01 |  | 2022-07-05 | 2022-07-21 23:59 |  |  | Roma WL | MRony2 | 2022-10-19 13:20 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 52826.51 | 2 |  |  |  | 75 | 66.7 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1032592 | O.1032592.01 | A.1032592.01.02 | Well 2 | BLUE ENERGY | SAPPHIRE 6V | Silver City 23 | J.22.110351 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2022-07-20 | 2022-07-20 |  | 2022-07-20 | 2022-07-28 23:59 |  | 2022-07-28 23:59 | Roma WL | MRony2 | 2022-10-19 12:47 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 41598.44 | 2 |  | L3 - Full RO |  | 66.7 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1031960 | O.1031960.01 | A.1031960.01.03 | Well 3 | WESTSIDE CORPORATION LTD |  | Rigless - Australia | J.22.111038 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-06-23 10:00 |  | 2022-06-25 10:00 | 2022-06-26 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:38 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1031960 | O.1031960.01 | A.1031960.01.01 | 1st well | WESTSIDE CORPORATION LTD |  | Rigless - Australia | J.22.110362 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-10-15 10:00 |  | 2022-10-20 10:00 | 2022-10-24 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1031960 | O.1031960.01 | A.1031960.01.02 | well 2 | WESTSIDE CORPORATION LTD |  | Rigless - Australia | J.22.110350 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-06-18 10:00 |  | 2022-06-20 10:00 | 2022-06-21 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:16 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1031255 | O.1031255.01 | A.1031255.01.03 | 3rd Well | GALILEE ENERGY LIMITED | GLENARAS 27 | Silver City 23 | J.22.110336 | RPE | ES-OH-Ops | Low | Operationally Complete | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2022-05-20 06:00 | 2022-05-19 | 2022-05-19 | 2022-05-20 06:00 | 2022-05-30 23:59 | 2022-05-31 | 2022-05-30 23:59 | Roma WL | MRony2 | 2023-08-18 12:59 | MEketone |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 33868.45 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1031255 | O.1031255.01 | A.1031255.01.01 | 1st well | GALILEE ENERGY LIMITED | Glenaras 24 | Silver City 23 | J.22.110353 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-04-22 |  | 2022-04-24 16:00 | 2022-04-28 09:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:16 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 26088.37 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1031255 | O.1031255.01 | A.1031255.01.05 | 5th Well | GALILEE ENERGY LIMITED | GLENARAS 26, GLENARAS 29 | Silver City 23 | J.22.110345 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2022-06-13 06:00 | 2022-06-13 |  | 2022-06-13 06:00 | 2022-06-23 23:59 |  | 2022-06-23 23:59 | Roma WL | MRony2 | 2022-10-03 14:16 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 12900.26 | 1 |  | L3 - Full RO |  | 75 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1031255 | O.1031255.01 | A.1031255.01.04 | 4th Well | GALILEE ENERGY LIMITED | GLENARAS 25 | Silver City 23 | J.22.110340 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2022-06-01 06:00 | 2022-05-31 |  | 2022-06-01 06:00 | 2022-06-10 23:59 |  | 2022-06-10 23:59 | Roma WL | MRony2 | 2022-10-03 14:16 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 25659.49 | 1 |  | L3 - Full RO |  | 75 | 33.3 | 0 | 100 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1031255 | O.1031255.01 | A.1031255.01.02 | 2nd Well | GALILEE ENERGY LIMITED | Glenaras 28 | Silver City 23 | J.22.110335 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-05-10 |  | 2022-05-11 06:00 | 2022-05-18 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 56613.23 | 1 |  |  |  | 75 | 83.3 | 0 | 50 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1030724 | O.1030724.02 | A.1030724.02.01 | Ocean Apex Reimbursable and Explosives | BHP PETROLEUM PTY LTD |  | Ocean Apex | J.22.114342 | RPI | PS-WL-NO | Medium | Confirmed | Design - PSD |  | Not Started | Not Started | In Progress |  | 2022-10-07 |  | 2023-03-07 | 2023-04-12 23:59 |  |  | New Burn WL | JDukas | 2023-03-31 16:15 | VOliveira5 |  | No |  |  |  |  | Jarrod Sedmak |  | 49407.41 | 0 |  | L0 - No RO |  | 50 | 33.3 | 100 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1030724 | O.1030724.01 | A.1030724.01.06 | Stickle New Well completions | BHP PETROLEUM PTY LTD | STICKLE 4 H1 | Ocean Apex | J.23.027240 | RPI | PS-SLK-Rental-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-03-16 | 2023-02-04 |  | 2023-03-16 | 2023-03-26 23:59 |  | 2023-03-26 23:59 | New Burn WL | JDukas | 2023-03-27 17:03 | VOliveira5 |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 50 | 0 | 25 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1030724 | O.1030724.01 | A.1030724.01.04 | Crosby-3H1 P&A Slickline | BHP PETROLEUM PTY LTD | CRO-3H1 | Ocean Apex | J.22.110175 | RPI | PS-SLK-Rental-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-10-04 | 2022-09-26 |  | 2022-10-31 | 2022-12-03 23:59 |  | 2022-12-03 23:59 | New Burn WL | VOliveira5 | 2023-01-10 15:43 | VOliveira5 |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  | L0 - No RO |  | 58.3 | 83.3 | 0 | 12.5 | 46.3 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1030724 | O.1030724.01 | A.1030724.01.05 | Stickle P&A - SLICKLINE | BHP PETROLEUM PTY LTD | STI-4H1 | Ocean Apex | J.22.110176 | RPI | PS-SLK-Rental-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-01 | 2022-11-29 |  | 2022-12-11 | 2023-01-19 23:59 |  | 2023-01-19 23:59 | New Burn WL | VOliveira5 | 2023-01-04 14:38 | VOliveira5 |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  | L0 - No RO | [7 empty] | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1030724 | O.1030724.01 | A.1030724.01.02 | Stickle P&A | BHP PETROLEUM PTY LTD | STI-4H1 | Ocean Apex | J.22.110161 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-12-03 | 2022-11-29 |  | 2022-12-13 | 2022-12-23 23:59 |  | 2023-01-21 23:59 | New Burn WL | JDukas | 2022-12-26 18:41 | EBrobbey |  | No |  |  |  |  | Justin Dukas |  | 234366.08 | 5 |  | L0 - No RO |  | 91.7 | 100 | 0 | 75 | 80 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1030724 | O.1030724.01 | A.1030724.01.01 | Crosby -3H1 P&A | BHP PETROLEUM PTY LTD | CRO-3H1 | Ocean Apex | J.22.110160 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-04 | 2022-10-22 |  | 2022-11-04 | 2022-12-03 23:59 |  | 2022-12-17 | New Burn WL | JDukas | 2022-12-07 05:13 | APutri |  | No |  |  |  |  | Justin Dukas |  | 41942.82 | 3 |  |  |  | 83.3 | 100 | 0 | 100 | 85 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1030724 | O.1030724.01 | A.1030724.01.03 | BHP Crosby SIT | BHP PETROLEUM PTY LTD | CRO-3H1 | Ocean Apex | J.22.110170 | RPI | PS-WL-NO | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-07-21 |  | 2022-07-23 | 2022-08-10 23:59 |  |  | New Burn WL | JDukas | 2022-10-26 22:06 | APutri |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1030214 | O.1030214.01 | A.1030214.01.02 | TCP Run#1 | EXXONMOBIL PNG LIMITED | HIDES D1 | RIGLESS - AUSTRALIA | J.22.109467 | RPI | TCP-PERM-JOB | High | Confirmed | Execute - PSD |  | Not Started | Design Completed | In Progress |  | 2022-04-20 |  | 2022-09-26 | 2022-10-12 23:59 |  |  | APG TS | MSwara | 2022-10-24 10:14 | RWallis |  | No |  |  |  |  | Yudha Swara |  | 0 | 1 |  |  |  | 41.7 | 25 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TCP - Tubing-Conveyed Perforation
P.1030214 | O.1030214.01 | A.1030214.01.04 | TCP Run#3 | EXXONMOBIL PNG LIMITED | Hides D1 | RIGLESS - AUSTRALIA | J.22.109469 | RPI | TCP-PERM-JOB | High | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2022-09-21 |  | 2022-09-21 | 2022-10-01 23:59 |  |  | APG TS | MSwara | 2022-10-03 06:31 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TCP - Tubing-Conveyed Perforation
P.1030214 | O.1030214.01 | A.1030214.01.03 | TCP Run#2 | EXXONMOBIL PNG LIMITED | Hides D1 | RIGLESS - AUSTRALIA | J.22.109468 | RPI | TCP-PERM-JOB | High | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2022-09-10 |  | 2022-09-10 | 2022-09-20 23:59 |  |  | APG TS | MSwara | 2022-10-03 06:30 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TCP - Tubing-Conveyed Perforation
P.1030214 | O.1030214.01 | A.1030214.01.01 | Job Design | EXXONMOBIL PNG LIMITED | HIDES D1 | RIGLESS - AUSTRALIA | J.22.109466 | RPI | TCP-DSGN | High | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2022-03-12 |  | 2022-03-12 | 2022-09-30 23:59 |  |  | APG TS | MSwara | 2022-10-03 06:30 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 0 | 4 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TCP - Tubing-Conveyed Perforation
P.1030127 | O.1030127.02 | A.1030127.02.01 | V107 Reimbursable and Explosives | ENI AUSTRALIA B.V. |  | Valaris 107 | J.22.114346 | RPI | PS-WL-NO | Low | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-10-06 |  | 2022-10-07 | 2023-07-01 23:59 |  |  | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 0 |  | L0 - No RO |  | 33.3 | 33.3 | 100 | 50 | 45 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1030127 | O.1030127.01 | A.1030127.01.04 | Blacktip P1 intervention with V107 | ENI AUSTRALIA B.V. | BLACKTIP P1 | Valaris 107 | J.22.110183 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-21 | 2022-11-14 | 2022-12-02 | 2022-12-03 | 2022-12-16 23:59 | 2022-12-17 | 2023-01-02 23:59 | New Burn WL | JDukas | 2023-07-20 10:26 | VOliveira5 |  | No |  |  |  |  | Justin Dukas |  | 516213.48 | 7 |  | L0 - No RO |  | 83.3 | 100 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1030127 | O.1030127.01 | A.1030127.01.09 | Blacktip Intervention Campaign | ENI AUSTRALIA B.V. |  | Valaris 107 | J.23.103904 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-17 | 2023-09-16 | 2023-09-30 08:00 | 2023-10-01 | 2023-11-25 23:59 | 2023-11-26 | 2023-11-25 23:59 | New Burn WL | APutri | 2023-06-29 10:06 | APutri |  | No |  |  |  |  | Justin Dukas |  | 0 | 5 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1030127 | O.1030127.01 | A.1030127.01.08 | ENI ADRM iX | ENI AUSTRALIA B.V. | BLACKTIP P3 | Valaris 107 | J.23.055805 | RPI | PS-WL-NO | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | Design Completed | 2023-04-01 | 2023-03-24 |  | 2023-05-17 | 2023-06-15 23:59 |  | 2023-06-15 23:59 | New Burn WL | JDukas | 2023-06-07 15:04 | PZuliani |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 55000 | 3 |  | L2 - Shift RO |  | 75 | 33.3 | 100 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1030127 | O.1030127.01 | A.1030127.01.02 | BT_P3 PLT and slickline | ENI AUSTRALIA B.V. | BLACKTIP P3, BLACKTIP P1 | Valaris 107 | J.22.110168 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-02-17 | 2023-02-13 |  | 2023-04-01 | 2023-05-31 23:59 |  | 2023-05-31 23:59 | New Burn WL | JDukas | 2023-05-29 09:25 | APutra7 |  | No |  |  |  | ROE WL Mumbai | Jarrod Sedmak |  | 52304.92 | 5 |  | L2 - Shift RO |  | 100 | 83.3 | 0 | 100 | 85 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1030127 | O.1030127.01 | A.1030127.01.07 | Blacktip P1 workover operations | ENI AUSTRALIA B.V. | BLACKTIP P1, BLACKTIP P3 | Valaris 107 | J.23.026136 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-12 | 2023-03-11 |  | 2023-03-26 | 2023-05-20 23:59 |  | 2023-05-20 23:59 | New Burn WL | JDukas | 2023-05-18 11:56 | VOliveira5 |  | No |  |  |  |  | Justin Dukas |  | 403051.77 | 5 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1030127 | O.1030127.01 | A.1030127.01.03 | BT_P3 SLK ops | ENI AUSTRALIA B.V. | BLACKTIP P3 | Valaris 107 | J.22.110177 | RPI | PS-SLK-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-02-17 | 2023-02-16 |  | 2023-02-17 | 2023-03-24 23:59 |  | 2023-03-24 23:59 | New Burn WL | JDukas | 2023-04-28 11:23 | VOliveira5 |  | No |  |  |  |  | Justin Dukas |  | 670211.22 | 1 |  | L0 - No RO |  | 83.3 | 100 | 0 | 50 | 70 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1030127 | O.1030127.01 | A.1030127.01.06 | BT_P3 IBC-CBL and TCP correlation | ENI AUSTRALIA B.V. | BLACKTIP P3 | Valaris 107 | J.23.019899 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-01-02 | 2023-01-01 |  | 2023-01-24 | 2023-02-14 23:59 |  | 2023-02-14 23:59 | New Burn WL | JDukas | 2023-02-15 11:01 | APutra7 |  | No |  |  |  |  | Justin Dukas |  | 63600 | 2 |  | L0 - No RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1030127 | O.1030127.01 | A.1030127.01.01 | BT_P3 exploration | ENI AUSTRALIA B.V. | BLACKTIP P3 | Valaris 107 | J.22.110159 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2022-10-27 | 2022-12-18 |  | 2023-01-09 | 2023-01-24 23:59 |  | 2023-02-09 23:59 | New Burn WL | JDukas | 2023-01-27 16:09 | VOliveira5 |  | No |  |  |  |  | James Cade |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 33.3 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1030127 | O.1030127.01 | A.1030127.01.05 | SLK - Blacktip P1 intervention with V107 | ENI AUSTRALIA B.V. | BLACKTIP P1 | Valaris 107 | J.22.110184 | RPI | PS-SLK-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-13 | 2022-11-13 |  | 2022-12-01 | 2022-12-14 23:59 |  | 2022-12-31 23:59 | New Burn WL | JDukas | 2023-01-13 11:27 | AHermawan |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1030064 | O.1030064.01 | A.1030064.01.02 | Stickle-4H1 - 9 5/8in casing | BHP PETROLEUM PTY LTD | STI-4H1 | Ocean Apex | J.22.111037 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | Not Required | Design Completed | In Progress |  | 2022-08-15 |  | 2022-11-18 | 2022-11-25 23:59 |  |  | AUS West Coast WS | NKhoa | 2022-10-03 12:38 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1030064 | O.1030064.01 | A.1030064.01.01 | Stickle-4H1 - Cased hole PnA | BHP PETROLEUM PTY LTD | STI-4H1 | Ocean Apex | J.22.110829 | WCF | REM-PA | Medium | Cancelled | Close - PSD |  | Not Required | Design Completed | In Progress |  | 2022-08-15 |  | 2022-11-10 | 2022-11-17 23:59 |  |  | AUS West Coast WS | NKhoa | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1030063 | O.1030063.04 | A.1030063.04.03 | Inflow test - 9 5/8in packer | WOODSIDE ENERGY LTD | BAL-5H-ST2 | Ocean Apex | J.22.110843 | WCF | CMT-TOOLS | High | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-10-15 | 2022-08-26 |  | 2022-10-15 | 2022-10-16 23:59 |  | 2022-10-17 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1030063 | O.1030063.04 | A.1030063.04.01 | PnA 1 - Deep | WOODSIDE ENERGY LTD | BAL-5H-ST2 | Ocean Apex | J.22.110813 | WCF | REM-PA | Medium | Cancelled | Close - PSD |  | Not Required | Design Completed | In Progress |  | 2022-06-15 |  | 2022-10-17 | 2022-10-18 23:59 |  |  | AUS West Coast WS | NKhoa | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1030063 | O.1030063.04 | A.1030063.04.02 | PnA 2 - Shallow | WOODSIDE ENERGY LTD | BAL-5H-ST2 | Ocean Apex | J.22.110810 | WCF | REM-PA | Medium | Cancelled | Close - PSD |  | Not Required | Design Completed | In Progress |  | 2022-06-15 |  | 2022-10-19 | 2022-10-20 23:59 |  |  | AUS West Coast WS | NKhoa | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1030063 | O.1030063.03 | A.1030063.03.02 | PnA 2 - Shallow | WOODSIDE ENERGY LTD | BALNAVES-8GI | Ocean Apex | J.22.111036 | WCF | REM-PA | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-06-15 |  | 2022-09-11 | 2022-09-17 23:59 |  |  | AUS West Coast WS | NKhoa | 2022-10-03 12:38 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1030063 | O.1030063.03 | A.1030063.03.03 | Inflow test - 9 5/8in packer | WOODSIDE ENERGY LTD | BALNAVES-8GI | Ocean Apex | J.22.110837 | WCF | CMT-TOOLS | High | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-09-04 | 2022-08-12 |  | 2022-09-04 | 2022-09-06 23:59 |  | 2022-09-06 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1030063 | O.1030063.03 | A.1030063.03.01 | PnA 1 - Deep | WOODSIDE ENERGY LTD | BALNAVES-8GI | Ocean Apex | J.22.110821 | WCF | REM-PA | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-06-15 |  | 2022-09-07 | 2022-09-10 23:59 |  |  | AUS West Coast WS | NKhoa | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1030063 | O.1030063.02 | A.1030063.02.03 | Inflow test - 9 5/8in | WOODSIDE ENERGY LTD | BAL-6H | Ocean Apex | J.22.110840 | WCF | CMT-TOOLS | High | Cancelled | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-08-21 | 2022-07-29 |  | 2022-08-21 | 2022-08-23 23:59 |  | 2022-08-23 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1030063 | O.1030063.02 | A.1030063.02.02 | PnA 2 - Shallow | WOODSIDE ENERGY LTD | BAL-6H | Ocean Apex | J.22.110825 | WCF | REM-PA | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-06-15 |  | 2022-08-28 | 2022-09-03 23:59 |  |  | AUS West Coast WS | NKhoa | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1030063 | O.1030063.02 | A.1030063.02.01 | PnA 1 - Deep | WOODSIDE ENERGY LTD | BAL-6H | Ocean Apex | J.22.110824 | WCF | REM-PA | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-06-15 |  | 2022-08-24 | 2022-08-27 23:59 |  |  | AUS West Coast WS | NKhoa | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1030063 | O.1030063.01 | A.1030063.01.01 | PnA 1 - Deep | WOODSIDE ENERGY LTD | BAL 7WI | Ocean Apex | J.22.110808 | WCF | REM-PA | High | Confirmed | Design - CEC |  | Design Completed | Design Completed | Design Completed | 2022-08-14 | 2022-07-23 |  | 2022-08-14 | 2022-08-15 23:59 |  | 2022-08-20 23:59 | AUS West Coast WS | NKhoa | 2022-10-12 13:34 | RKale4 |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1030063 | O.1030063.01 | A.1030063.01.03 | Inflow test - 9 5/8in | WOODSIDE ENERGY LTD | BAL 7WI | Ocean Apex | J.22.110832 | WCF | CMT-TOOLS | High | Confirmed | Design - CEC |  | Design Completed | Not Required | Design Completed | 2022-08-12 | 2022-07-29 |  | 2022-08-12 | 2022-08-13 23:59 |  | 2022-08-14 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1030063 | O.1030063.01 | A.1030063.01.02 | PnA 2 - Shallow | WOODSIDE ENERGY LTD | BAL 7WI | Ocean Apex | J.22.110805 | WCF | REM-PA | High | Confirmed | Design - CEC |  | Design Completed | Design Completed | Design Completed |  | 2022-06-15 |  | 2022-08-16 | 2022-08-17 23:59 |  |  | AUS West Coast WS | NKhoa | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1029909 | O.1029909.01 | A.1029909.01.01 | MPF Operation | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Well #1 |  | J.22.111034 | RPI | CT-CIRC | Low | Unconfirmed - 50% | Design - CEC |  | Design Completed | Not Required | In Progress | 2022-03-14 | 2022-03-14 |  | 2022-03-14 | 2022-03-14 23:59 |  | 2022-03-14 23:59 | AUS East Coast WS | JMeyer9 | 2022-10-03 15:38 | FDPSystemUser |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1029651 | O.1029651.02 | A.1029651.02.02 | Barrolka 27 | SANTOS LIMITED | BARROLKA 27 | SAVANNA 188 | J.24.077270 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-03-23 | 2024-03-23 |  | 2024-03-23 | 2024-03-24 22:59 |  | 2024-03-28 23:59 | Moomba WL | HChapman3 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Jakarta | Shameer Mumtaz Ali |  | 45701.3 | 2 |  | L2 - Shift RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.02 | A.1029651.02.03 | Barrolka 28 | SANTOS LIMITED | BARROLKA 28 | SAVANNA 188 | J.24.087893 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-04-15 | 2024-04-15 |  | 2024-04-15 | 2024-04-20 23:59 |  | 2024-04-20 23:59 | Moomba WL | JDagdag | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L2 - Shift RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.02 | A.1029651.02.04 | Frizzle 1 | SANTOS LIMITED | FRIZZLE 1 | SAVANNA 188 | J.24.088573 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-04-29 12:00 | 2024-04-26 |  | 2024-04-29 12:00 | 2024-05-05 11:59 |  | 2024-05-05 11:59 | Moomba WL | AKavooris | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Jakarta | Shameer Mumtaz Ali |  | 0 | 2 |  | L2 - Shift RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.02 | A.1029651.02.01 | Beeree 4 | SANTOS LIMITED | BEEREE 4 | SAVANNA 188 | J.24.062921 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-05-20 | 2024-05-20 |  | 2024-05-20 | 2024-07-20 22:59 |  | 2024-05-25 23:59 | Moomba WL | AKavooris | 2024-08-13 16:26 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 45701.3 | 2 |  | L1 - Support RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.02 | A.1029651.02.07 | Bugito 5 | SANTOS LIMITED | BUGUITO 5 | SAVANNA 188 | J.24.120525 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-06-25 23:00 | 2024-06-21 |  | 2024-06-25 23:00 | 2024-07-01 22:59 |  | 2024-07-01 22:59 | Moomba WL | SMccauley | 2024-06-29 11:25 | SMccauley |  | No |  |  |  | ROE WL Mumbai | Elsamawal Mohamedelhassan Awadalla Ismail |  | 0 | 2 |  | L3 - Full RO |  | 91.7 | 83.3 | 100 | 100 | 92.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.02 | A.1029651.02.06 | Serpentine 1 | SANTOS LIMITED | SERPENTINE 1 | SAVANNA 188 | J.24.105182 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-01-25 08:00 | 2024-05-24 | 2024-05-25 | 2024-05-25 | 2024-06-01 23:59 | 2024-06-02 | 2024-06-01 23:59 | Moomba WL | YPouryan | 2024-05-29 20:58 | YPouryan |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.02 | A.1029651.02.05 | Beereenlah 1 | SANTOS LIMITED | BEEREENLAH 1 | SAVANNA 188 | J.24.098191 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-01-25 08:00 | 2024-05-14 | 2024-05-15 | 2024-05-15 | 2024-05-22 23:59 | 2024-05-23 | 2024-05-22 23:59 | Moomba WL | YPouryan | 2024-05-19 17:19 | YPouryan |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L2 - Shift RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.46 | Winninia North 6 | SANTOS LIMITED | WINNINIA NORTH 6 | Saxon Rig 188 | J.23.054843 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-06 23:00 | 2023-07-07 |  | 2023-07-07 | 2023-07-12 23:59 |  | 2023-07-12 22:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Jakarta | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Adel Mohammad Alhashemi | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.50 | Watkins North 2 | SANTOS LIMITED | WATKINS NORTH 2 | Saxon Rig 188 | J.23.083620 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-08-21 19:00 | 2023-08-21 16:00 |  | 2023-08-21 20:00 | 2023-08-27 19:59 |  | 2023-08-27 18:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 64.98 | 2 |  | L3 - Full RO |  | 100 | 100 | 0 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.51 | Walter 1 | SANTOS LIMITED | WALTER 1 | Saxon Rig 188 | J.23.083621 | RPE | ES-OH-NO | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | Design Completed | 2023-08-31 23:00 | 2023-09-01 |  | 2023-09-01 | 2023-09-06 23:59 |  | 2023-09-06 22:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 83.3 | 66.7 | 100 | 75 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.47 | Psyche 8 | SANTOS LIMITED | PSYCHE 8 | Saxon Rig 188 | J.23.083617 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-16 21:00 | 2023-07-15 10:00 |  | 2023-07-16 22:00 | 2023-07-22 21:59 |  | 2023-07-22 20:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.52 | Nhuganha Ngakalanga | SANTOS LIMITED | NHUGANHA NGAKALANGA 1 | Saxon Rig 188 | J.23.083622 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-09-13 09:00 | 2023-09-12 |  | 2023-09-13 10:00 | 2023-09-19 09:59 |  | 2023-09-19 08:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 100 | 100 | 0 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.49 | Watkins North 1 | SANTOS LIMITED | WATKINS NORTH 1 | Saxon Rig 188 | J.23.083619 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-08-14 02:00 | 2023-08-14 |  | 2023-08-14 03:00 | 2023-08-20 02:59 |  | 2023-08-20 01:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Jakarta | Mazhar Iqbal |  | 26545.33 | 2 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.48 | Psyche 9 | SANTOS LIMITED | PSYCHE 9 | Saxon Rig 188 | J.23.083618 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-26 21:00 | 2023-07-25 |  | 2023-07-26 22:00 | 2023-08-01 21:59 |  | 2023-08-01 20:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.56 | Toolachee 59 | SANTOS LIMITED | TOOLACHEE 59 | Saxon Rig 188 | J.23.085667 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-12-12 01:00 | 2023-12-11 10:00 |  | 2023-12-12 02:00 | 2023-12-18 01:59 |  | 2023-12-18 00:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Jakarta | Shameer Mumtaz Ali |  | 0 | 3 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.55 | Tarwonga 8 | SANTOS LIMITED | TARWONGA 8 | Saxon Rig 188 | J.23.085666 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-11-05 16:00 | 2023-11-01 12:00 | 2023-11-03 | 2023-11-05 17:00 | 2023-11-11 16:59 | 2023-11-09 | 2023-11-11 15:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Jakarta | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.60 | Toolachee 57 (GAS DEV A) DXCF | SANTOS LIMITED | TOOLACHEE 57 | Saxon Rig 188 | J.23.124231 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-11-19 23:00 | 2023-11-19 20:00 | 2023-11-19 | 2023-11-19 23:00 | 2023-11-25 22:59 | 2023-11-26 | 2023-11-25 22:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 48607.93 | 1 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.58 | Kappa 3_QC-MDT-MSCT | SANTOS LIMITED | KAPPA 3 | Saxon Rig 188 | J.23.122622 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-09-30 15:00 | 2023-09-29 11:00 | 2023-09-30 | 2023-09-30 16:00 | 2023-10-06 15:59 | 2023-10-07 | 2023-10-06 15:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Jakarta | Shameer Mumtaz Ali |  | 33640.12 | 2 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.59 | Kappa 4 (DEV B GAS) DCXF | SANTOS LIMITED | KAPPA 4 | Saxon Rig 188 | J.23.122623 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-10-19 15:00 | 2023-10-17 | 2023-10-19 | 2023-10-19 16:00 | 2023-10-25 15:59 | 2023-10-26 | 2023-10-25 14:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 33640.12 | 2 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.61 | Toolachee 58 (GAS DEV B) DXCF | SANTOS LIMITED | TOOLACHEE 58 | Saxon Rig 188 | J.23.122624 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2023-11-26 23:00 | 2023-11-20 | 2023-11-27 | 2023-11-27 | 2023-12-02 23:59 | 2023-12-03 01:00 | 2023-12-02 22:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 62.5 | 41.7 | 100 | 50 | 56.3 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.64 | Cocinero 14 | SANTOS LIMITED | COCINERO 14 | Saxon Rig 188 | J.23.160232 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-12-24 23:00 | 2023-12-24 |  | 2023-12-25 | 2023-12-30 23:59 |  | 2023-12-30 22:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.66 | Cocinero 17 (DEV T Oil) DXCF | SANTOS LIMITED | COCINERO 17 | Saxon Rig 188 | J.24.021444 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-01-27 23:00 | 2024-01-22 |  | 2024-01-28 | 2024-02-02 23:59 |  | 2024-02-02 23:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L2 - Shift RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.65 | Cocinero 16 | SANTOS LIMITED | COCINERO 16 | Saxon Rig 188 | J.24.021443 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-01-18 13:00 | 2024-01-17 |  | 2024-01-18 14:00 | 2024-01-20 13:59 |  | 2024-01-20 12:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Jakarta | Shameer Mumtaz Ali |  | 0 | 3 |  | L2 - Shift RO |  | 100 | 100 | 0 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.70 | Cocinero 15 | SANTOS LIMITED | COCINERO 15 | Saxon Rig 188 | J.23.178413 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-01-03 23:00 | 2024-01-03 |  | 2024-01-04 | 2024-01-09 23:59 |  | 2024-01-09 23:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L2 - Shift RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.75 | SLR 188 /5 | SANTOS LIMITED |  | Saxon Rig 188 | J.24.050665 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-05-28 23:00 | 2024-05-29 |  | 2024-05-29 | 2024-06-03 23:59 |  | 2024-05-31 22:59 | Moomba WL | KKeese | 2024-06-12 08:11 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.68 | Barrolka 27 (M GAS DEV H) DXCF | SANTOS LIMITED |  | Saxon Rig 188 | J.24.021446 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-02-21 23:00 | 2024-02-22 | 2024-02-22 01:00 | 2024-02-22 | 2024-02-27 23:59 | 2024-02-28 01:00 | 2024-02-27 22:59 | Moomba WL | KKeese | 2024-05-24 08:26 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.74 | SLR 188 /4 | SANTOS LIMITED |  | Saxon Rig 188 | J.24.050664 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-05-13 23:00 | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2024-05-19 23:59 | 2024-05-17 | 2024-05-16 22:59 | Moomba WL | KKeese | 2024-05-23 15:21 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L2 - Shift RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.76 | SLR 188 /6 | SANTOS LIMITED |  | Saxon Rig 188 | J.24.050666 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-06-17 23:00 | 2024-06-18 | 2024-06-18 | 2024-06-18 | 2024-06-23 23:59 | 2024-06-21 | 2024-06-20 22:59 | Moomba WL | KKeese | 2024-05-08 08:23 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.73 | SLR 188 /3 | SANTOS LIMITED |  | Saxon Rig 188 | J.24.050663 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-04-30 23:00 | 2024-05-01 | 2024-05-01 | 2024-05-01 | 2024-05-06 23:59 | 2024-05-04 | 2024-05-03 22:59 | Moomba WL | KKeese | 2024-05-08 08:17 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.72 | SLR 188 /2 | SANTOS LIMITED |  | Saxon Rig 188 | J.24.088592 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-04-14 23:00 | 2024-04-15 | 2024-04-15 | 2024-04-15 | 2024-04-20 23:59 | 2024-04-18 | 2024-04-17 22:59 | Moomba WL | KKeese | 2024-04-23 14:09 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.71 | SLR 188 /1 | SANTOS LIMITED |  | Saxon Rig 188 | J.24.050662 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-03-31 23:00 | 2024-04-01 | 2024-04-01 01:00 | 2024-04-01 | 2024-04-06 23:59 | 2024-04-04 01:00 | 2024-04-03 22:59 | Moomba WL | KKeese | 2024-04-23 14:08 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.69 | Barrolka 28 (M GAS DEV J) DXCF | SANTOS LIMITED |  | Saxon Rig 188 | J.24.021447 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-03-07 23:00 | 2024-03-08 | 2024-03-08 01:00 | 2024-03-08 | 2024-03-13 23:59 | 2024-03-11 01:00 | 2024-03-10 22:59 | Moomba WL | KKeese | 2024-04-02 15:02 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.67 | Beeree 4 (GAS APP A) DXCF | SANTOS LIMITED |  | Saxon Rig 188 | J.24.021445 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-02-04 23:00 | 2024-02-05 |  | 2024-02-05 | 2024-02-10 23:59 |  | 2024-02-10 22:59 | Moomba WL | KKeese | 2024-02-28 09:41 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.42 | Dullingari North 27 | SANTOS LIMITED | DULLINGARI NORTH 27 | Saxon Rig 188 | J.23.041202 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-07 | 2023-06-07 | 2023-06-06 | 2023-06-07 | 2023-06-12 23:59 | 2023-06-13 | 2023-06-12 23:59 | Moomba WL | KKeese | 2023-10-03 21:19 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 3 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.45 | Winninia North 5 | SANTOS LIMITED | WINNINIA NORTH 5 | Saxon Rig 188 | J.23.054842 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-06-21 23:00 | 2023-06-22 | 2023-06-21 14:00 | 2023-06-22 | 2023-06-28 23:59 | 2023-06-29 | 2023-06-28 22:59 | Moomba WL | KKeese | 2023-10-03 21:12 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.53 | Kappa 4 | SANTOS LIMITED |  | Saxon Rig 188 | J.23.085664 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2023-11-10 23:00 | 2023-11-11 | 2023-11-11 01:00 | 2023-11-11 | 2023-11-16 23:59 | 2023-11-17 01:00 | 2023-11-16 22:59 | Moomba WL | KKeese | 2023-09-07 10:53 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.62 | Toolachee 59 (GAS DEV E) DXCF | SANTOS LIMITED |  | Saxon Rig 188 | J.23.122625 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-11-24 23:00 | 2023-11-25 | 2023-11-25 01:00 | 2023-11-25 | 2023-11-30 23:59 | 2023-12-01 01:00 | 2023-11-30 22:59 | Moomba WL | KKeese | 2023-08-17 17:30 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.54 | Kappa 5 | SANTOS LIMITED |  | Saxon Rig 188 | J.23.085665 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-11-24 23:00 | 2023-11-25 | 2023-11-25 01:00 | 2023-11-25 | 2023-11-30 23:59 | 2023-12-01 01:00 | 2023-11-30 22:59 | Moomba WL | KKeese | 2023-08-17 17:29 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.57 | Kappa 3 | SANTOS LIMITED |  | Saxon Rig 188 | J.23.087857 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-31 23:00 | 2023-11-01 | 2023-11-01 01:00 | 2023-11-01 | 2023-11-06 23:59 | 2023-11-07 01:00 | 2023-11-06 22:59 | Moomba WL | KKeese | 2023-08-17 17:28 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.63 | Tarwonga 8 (GAS DEV A) DXCF | SANTOS LIMITED |  | Saxon Rig 188 | J.23.122626 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-12-14 23:00 | 2023-12-15 | 2023-12-15 01:00 | 2023-12-15 | 2023-12-20 23:59 | 2023-12-21 01:00 | 2023-12-20 22:59 | Moomba WL | KKeese | 2023-08-11 17:09 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.38 | Dorodillo 8 | SANTOS LIMITED | DORODILLO 8 | Saxon Rig 188 | J.23.021786 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Not Required | Design Completed | 2023-04-14 | 2023-04-13 | 2023-04-14 | 2023-04-14 | 2023-04-19 23:59 | 2023-04-20 | 2023-04-19 23:59 | Moomba WL | KKeese | 2023-08-06 13:38 | JDagdag |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L2 - Shift RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.36 | Dorodillo 6 | SANTOS LIMITED | DORODILLO 6 | Saxon Rig 188 | J.23.021785 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-03-22 11:00 | 2023-03-22 10:00 | 2023-03-22 | 2023-03-22 12:00 | 2023-03-28 11:59 | 2023-03-29 | 2023-03-28 11:59 | Moomba WL | KKeese | 2023-08-06 13:38 | JDagdag |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 44787.27 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.34 | Bobs Well 4 | SANTOS LIMITED | BOBS WELL 4 | Saxon Rig 188 | J.23.012010 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-03-06 23:00 | 2023-03-07 |  | 2023-03-07 | 2023-03-12 23:59 |  | 2023-03-12 23:59 | Moomba WL | eismail | 2023-06-13 11:06 | DYanagawa |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 59996.3 | 2 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.41 | Dullingari North 26 | SANTOS LIMITED | DULLINGARI NORTH 26 | Saxon Rig 188 | J.23.041201 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-05-16 | 2023-05-15 |  | 2023-05-16 | 2023-05-23 23:59 |  | 2023-05-23 23:59 | Moomba WL | KKeese | 2023-05-24 09:23 | YPouryan |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.43 | Watkins North 1 | SANTOS LIMITED |  | Saxon Rig 188 | J.23.041203 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-10 | 2023-06-10 |  | 2023-06-10 | 2023-06-15 23:59 |  | 2023-06-15 23:59 | Moomba WL | KKeese | 2023-05-09 07:10 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.39 | Arrakis 2 | SANTOS LIMITED | ARRAKIS 2 | Saxon Rig 188 | J.23.021787 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-05-08 | 2023-05-08 |  | 2023-05-08 | 2023-05-13 23:59 |  | 2023-05-13 23:59 | Moomba WL | KKeese | 2023-05-08 16:31 | ASamokhin |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 44787.27 | 2 |  | L3 - Full RO |  | 75 | 33.3 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.40 | Dorodillo 5 | SANTOS LIMITED | DORODILLO 5 | Saxon Rig 188 | J.23.041200 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-28 21:00 | 2023-04-27 |  | 2023-04-28 21:00 | 2023-05-04 20:59 |  | 2023-05-04 20:59 | Moomba WL | KKeese | 2023-04-30 15:57 | ASamokhin |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.44 | Watkins North 1 | SANTOS LIMITED |  | Saxon Rig 188 | J.23.054841 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-17 23:00 | 2023-06-18 |  | 2023-06-18 | 2023-06-23 23:59 |  | 2023-06-23 22:59 | Moomba WL | KKeese | 2023-04-15 13:03 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.37 | Dorodillo 7 | SANTOS LIMITED | DORODILLO 7 | Saxon Rig 188 | J.23.061994 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2023-03-30 01:00 | 2023-04-06 |  | 2023-04-06 02:00 | 2023-04-12 01:59 |  | 2023-04-12 01:59 | Moomba WL | KKeese | 2023-04-09 08:38 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.33 | Fortanna 2 | SANTOS LIMITED | FORTANNA 2 | Saxon Rig 188 | J.23.012009 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-02-22 23:00 | 2023-02-22 |  | 2023-02-23 | 2023-02-28 23:59 |  | 2023-02-28 22:59 | Moomba WL | eismail | 2023-03-23 08:42 | eismail |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 59996.3 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.31 | Europa 1 | SANTOS LIMITED | EUROPA 1 | Saxon Rig 188 | J.23.012007 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-02-07 07:00 | 2023-02-01 |  | 2023-02-07 08:00 | 2023-02-13 07:59 |  | 2023-02-13 06:59 | Moomba WL | eismail | 2023-02-16 08:08 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 45701.3 | 4 |  | L3 - Full RO |  | 91.7 | 50 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.35 | Indigo 1 | SANTOS LIMITED |  | Saxon Rig 188 | J.23.012011 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-16 23:00 | 2023-03-17 |  | 2023-03-17 | 2023-03-22 23:59 |  | 2023-03-22 22:59 | Moomba WL | eismail | 2023-02-13 21:30 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.21 | Dilchee 6 | SANTOS LIMITED | DILCHEE 6 | Saxon Rig 188 | J.22.110007 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-15 21:00 | 2022-11-14 |  | 2022-11-15 22:00 | 2022-11-21 21:59 |  | 2022-11-21 22:59 | Moomba WL | KKeese | 2023-02-07 16:39 | asulaimanov |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 53955.74 | 2 |  | L3 - Full RO |  | 75 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.25 | Strzelecki 34 | SANTOS LIMITED | STRZELECKI 34 | Saxon Rig 188 | J.23.011733 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-01-18 09:00 | 2023-01-17 |  | 2023-01-18 10:00 | 2023-01-24 09:59 |  | 2023-01-24 10:59 | Moomba WL | KKeese | 2023-01-24 14:17 | YPouryan |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 53955.74 | 3 |  | L3 - Full RO |  | 75 | 83.3 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.32 | Wackett South 2 | SANTOS LIMITED |  | Saxon Rig 188 | J.23.012008 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-02-05 01:00 | 2023-02-05 |  | 2023-02-05 | 2023-02-10 23:59 |  | 2023-02-11 00:59 | Moomba WL | eismail | 2023-01-08 11:05 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.22 | Marabooka 19-QC-XPT-FMI | SANTOS LIMITED | MARABOOKA 19 | Saxon Rig 188 | J.22.110008 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-12-02 01:00 | 2022-11-27 |  | 2022-11-30 | 2022-12-08 23:59 |  | 2022-12-11 00:59 | Moomba WL | KKeese | 2022-12-03 08:54 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 55727.5 | 3 |  |  |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.24 | Strzelecki 34 | SANTOS LIMITED |  | Saxon Rig 188 | J.22.121234 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-12 01:00 | 2022-12-12 |  | 2022-12-12 | 2022-12-17 23:59 |  | 2022-12-18 00:59 | Moomba WL | KKeese | 2022-12-01 11:40 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.20 | Pira 6 QC-XPT | SANTOS LIMITED | PIRA 6 | Saxon Rig 188 | J.22.110006 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-10-30 |  | 2022-10-31 09:00 | 2022-11-03 08:59 |  |  | Moomba WL | KKeese | 2022-11-05 00:52 | eismail |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 55727.5 | 4 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.17 | Quasar 2 | SANTOS LIMITED | QUASAR 2 | Saxon Rig 188 | J.22.110003 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-10-12 |  | 2022-11-01 | 2022-11-06 23:59 |  |  | Moomba WL | KKeese | 2022-11-05 00:39 | eismail |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 47474.51 | 2 |  |  |  | 75 | 83.3 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.26 | Coloy 1 | SANTOS LIMITED |  | Saxon Rig 188 | J.23.011734 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2023-02-01 |  | 2023-02-01 | 2023-02-06 23:59 |  |  | Moomba WL | KKeese | 2022-10-29 22:59 | eismail |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.27 | Wackett South 2 | SANTOS LIMITED |  | Saxon Rig 188 | J.23.011735 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2023-02-13 |  | 2023-02-13 | 2023-02-18 23:59 |  |  | Moomba WL | KKeese | 2022-10-29 22:58 | eismail |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.28 | Dampierre 1 | SANTOS LIMITED |  | Saxon Rig 188 | J.23.011736 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2023-02-27 |  | 2023-02-27 | 2023-03-04 23:59 |  |  | Moomba WL | KKeese | 2022-10-29 22:57 | eismail |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.29 | Maya 2 | SANTOS LIMITED |  | Saxon Rig 188 | J.23.011737 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2023-03-13 |  | 2023-03-13 | 2023-03-18 23:59 |  |  | Moomba WL | KKeese | 2022-10-29 22:57 | eismail |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.30 | Indigo 1 | SANTOS LIMITED |  | Saxon Rig 188 | J.23.011738 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2023-03-27 |  | 2023-03-27 | 2023-04-01 23:59 |  |  | Moomba WL | KKeese | 2022-10-29 22:56 | eismail |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.18 | PIRA DEV B | SANTOS LIMITED | PIRA 5 | Saxon Rig 188 | J.22.110004 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-10-19 |  | 2022-10-21 05:00 | 2022-10-23 04:59 |  |  | Moomba WL | KKeese | 2022-10-23 16:39 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 55727.5 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.19 | PIRA DEV C | SANTOS LIMITED |  | Saxon Rig 188 | J.22.110005 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-10-23 |  | 2022-10-23 | 2022-10-28 23:59 |  |  | Moomba WL | KKeese | 2022-10-23 12:47 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.23 | OH Swan Lake 18 QC | SANTOS LIMITED | Swan Lake 18 | Saxon Rig 188 | J.22.110093 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-08-27 | 2022-08-26 |  | 2022-08-27 | 2022-09-03 23:59 |  | 2022-09-03 23:59 | Moomba WL | YPouryan | 2022-10-03 12:39 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.16 | Gidgealpa 66 QC, Press Test | SANTOS LIMITED | Gidgealpa 66 | Saxon Rig 188 | J.22.109961 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-07-27 21:30 | 2022-07-23 |  | 2022-07-27 21:30 | 2022-08-04 21:29 |  | 2022-08-04 21:29 | Moomba WL | YPouryan | 2022-10-03 12:27 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.15 | Gidgealpa 68 | SANTOS LIMITED | Gidgealpa 68 | Saxon Rig 188 | J.22.109953 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-07-11 | 2022-07-11 |  | 2022-07-11 | 2022-07-14 23:59 |  | 2022-07-14 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 12:26 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.14 | OH Logging Well # 1 | SANTOS LIMITED | Gidgealpa 67 | Saxon Rig 188 | J.22.109948 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-06-27 | 2022-06-26 |  | 2022-06-27 | 2022-07-04 23:59 |  | 2022-07-04 23:59 | Moomba WL | YPouryan | 2022-10-03 12:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 26770.63 | 2 |  |  |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.13 | Marsilea 2 | SANTOS LIMITED | Marsilea 002 | Saxon Rig 188 | J.22.109896 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-09-16 | 2022-09-14 |  | 2022-09-16 | 2022-09-25 23:59 |  | 2022-09-25 23:59 | Moomba WL | KKeese | 2022-10-03 12:20 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.12 | QC/XPT Q3 Well 7 | SANTOS LIMITED |  | Saxon Rig 188 | J.22.109895 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-08-29 | 2022-08-29 |  | 2022-08-29 | 2022-09-03 23:59 |  | 2022-09-03 23:59 | Moomba WL | KKeese | 2022-10-03 12:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.11 | QC/XPT Q3 Well 6 | SANTOS LIMITED |  | Saxon Rig 188 | J.22.109894 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | Design Completed | Not Started | In Progress | 2022-08-18 | 2022-08-18 |  | 2022-08-18 | 2022-08-23 23:59 |  | 2022-08-23 23:59 | Moomba WL | KKeese | 2022-10-03 12:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 50 | 16.7 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.10 | QC/XPT Q3 Well 5 | SANTOS LIMITED |  | Saxon Rig 188 | J.22.109893 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-08-06 | 2022-08-06 |  | 2022-08-06 | 2022-08-11 23:59 |  | 2022-08-11 23:59 | Moomba WL | KKeese | 2022-10-03 12:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.09 | QC/XPT Q3 Well 4 | SANTOS LIMITED |  | Saxon Rig 188 | J.22.109892 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-07-28 | 2022-07-28 |  | 2022-07-28 | 2022-08-02 23:59 |  | 2022-08-02 23:59 | Moomba WL | KKeese | 2022-10-03 12:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.08 | QC/XPT Q3 Well 3 | SANTOS LIMITED |  | Saxon Rig 188 | J.22.109891 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-07-18 | 2022-07-18 |  | 2022-07-18 | 2022-07-23 23:59 |  | 2022-07-23 23:59 | Moomba WL | KKeese | 2022-10-03 12:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.07 | QC/XPT Q3 Well 2 | SANTOS LIMITED |  | Saxon Rig 188 | J.22.109890 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-07-05 | 2022-07-05 |  | 2022-07-05 | 2022-07-10 23:59 |  | 2022-07-10 23:59 | Moomba WL | KKeese | 2022-10-03 12:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.06 | QC/XPT Q3 Well 1 | SANTOS LIMITED |  | Saxon Rig 188 | J.22.109889 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-06-23 | 2022-06-23 |  | 2022-06-23 | 2022-06-28 23:59 |  | 2022-06-28 23:59 | Moomba WL | KKeese | 2022-10-03 12:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.05 | OH Logging Dampierre | SANTOS LIMITED |  | Saxon Rig 188 | J.22.109768 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-09-25 01:00 | 2022-09-25 |  | 2022-09-25 | 2022-09-30 23:59 |  | 2022-10-01 00:59 | Moomba WL | KKeese | 2022-10-03 12:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.04 | OH Logging Well #4 | SANTOS LIMITED |  | Saxon Rig 188 | J.22.109752 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-06-14 | 2022-06-14 |  | 2022-06-14 | 2022-06-19 23:59 |  | 2022-06-19 23:59 | Moomba WL | KKeese | 2022-10-03 12:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.03 | OH Logging Well #3 | SANTOS LIMITED |  | Saxon Rig 188 | J.22.109751 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-06-01 | 2022-06-01 |  | 2022-06-01 | 2022-06-06 23:59 |  | 2022-06-06 23:59 | Moomba WL | KKeese | 2022-10-03 12:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.02 | OH Logging Well # 2 | SANTOS LIMITED |  | Saxon Rig 188 | J.22.109750 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-05-21 | 2022-05-21 |  | 2022-05-21 | 2022-05-26 23:59 |  | 2022-05-26 23:59 | Moomba WL | KKeese | 2022-10-03 12:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029651 | O.1029651.01 | A.1029651.01.01 | OH Logging Swan Lake 17 QC-XPT | SANTOS LIMITED | Swan Lake 17 | Saxon Rig 188 | J.22.109749 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-08-14 | 2022-08-14 |  | 2022-08-14 | 2022-08-19 23:59 |  | 2022-08-19 23:59 | Moomba WL | KKeese | 2022-10-03 12:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 15789.47 | 2 |  |  |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1029574 | O.1029574.01 | A.1029574.01.09 | CBL-VDL | CENTRAL PETROLEUM SERVICES PTY LTD | PALM VALLEY 12 | ENSIGN 963 | J.22.111033 | RPE | ES-CH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2022-09-15 10:00 | 2022-09-14 |  | 2022-09-15 10:00 | 2022-09-24 08:59 |  | 2022-09-24 08:59 | Roma WL | MRony2 | 2022-10-19 21:12 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 54977.26 | 1 |  | L1 - Support RO |  | 83.3 | 50 | 0 | 50 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1029574 | O.1029574.01 | A.1029574.01.08 | CBL/Plug | CENTRAL PETROLEUM SERVICES PTY LTD | Palm Valley 12 | ENSIGN 963 | J.22.111032 | RPE | ES-CH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-08-24 |  | 2022-08-29 10:00 | 2022-09-02 09:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:37 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 79597.14 | 3 |  |  |  | 75 | 83.3 | 0 | 50 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1029574 | O.1029574.01 | A.1029574.01.06 | 9 5/8 CBL | CENTRAL PETROLEUM SERVICES PTY LTD | Palm Valley 12 | ENSIGN 963 | J.22.111031 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-08-15 |  | 2022-08-18 | 2022-08-26 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:37 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1029574 | O.1029574.01 | A.1029574.01.04 | Palm Valley 12A | CENTRAL PETROLEUM SERVICES PTY LTD |  | ENSIGN 963 | J.22.111030 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-07-22 |  | 2022-07-23 | 2022-07-27 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:37 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 5 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1029574 | O.1029574.01 | A.1029574.01.07 | CBL+OH | CENTRAL PETROLEUM SERVICES PTY LTD |  | ENSIGN 963 | J.22.110383 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-08-30 |  | 2022-09-04 | 2022-09-07 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 4 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1029574 | O.1029574.01 | A.1029574.01.05 | 13 3/8 CBL | CENTRAL PETROLEUM SERVICES PTY LTD | Palm Valley 12 | ENSIGN 963 | J.22.110376 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-07-29 |  | 2022-08-01 | 2022-08-09 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1029574 | O.1029574.01 | A.1029574.01.02 | Logging 8.5 | CENTRAL PETROLEUM SERVICES PTY LTD | Palm Valley 12 | ENSIGN 963 | J.22.110349 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-06-16 |  | 2022-06-16 10:00 | 2022-06-20 09:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:16 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 66601.69 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1029574 | O.1029574.01 | A.1029574.01.03 | 6in Section | CENTRAL PETROLEUM SERVICES PTY LTD |  | ENSIGN 963 | J.22.110333 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-07-21 |  | 2022-07-24 | 2022-07-25 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 4 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1029574 | O.1029574.01 | A.1029574.01.01 | Logging for 12.25 | CENTRAL PETROLEUM SERVICES PTY LTD | Palm Valley 12 | ENSIGN 963 | J.22.110328 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-05-15 |  | 2022-05-18 | 2022-05-26 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 59129.3 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1029257 | O.1029257.02 | A.1029257.02.01 | NTP Reimbursable and Explosives | SANTOS LIMITED |  | NOBLE TOM PROSSER | J.22.114347 | RPI | PS-WL-NO | Low | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2022-10-06 |  | 2022-10-07 | 2023-02-04 23:59 |  |  | New Burn WL | JDukas | 2023-03-02 11:37 | VOliveira5 |  | No |  |  |  |  | Justin Dukas |  | 0 | 0 |  | L0 - No RO |  | 41.7 | 33.3 | 100 | 50 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1029257 | O.1029257.01 | A.1029257.01.02 | Spartan-2 SLK ops | SANTOS LIMITED | Spartan-2 | NOBLE TOM PROSSER | J.22.110178 | RPI | PS-SLK-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-11 | 2022-11-07 |  | 2022-11-09 | 2023-01-17 23:59 |  | 2023-01-24 23:59 | New Burn WL | JDukas | 2023-01-17 18:12 | OAzarenko |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  | L0 - No RO |  | 66.7 | 66.7 | 0 | 50 | 55 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1029257 | O.1029257.01 | A.1029257.01.01 | Spartan-2 Well | SANTOS LIMITED | Spartan-2 | NOBLE TOM PROSSER | J.22.110157 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-10 | 2022-11-08 |  | 2022-11-09 | 2023-01-17 23:59 |  | 2023-01-18 23:59 | New Burn WL | JDukas | 2023-01-17 18:03 | OAzarenko |  | No |  |  |  |  | Justin Dukas |  | 81738 | 11 |  | L0 - No RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1029132 | O.1029132.03 | A.1029132.03.02 | Mylor 2 and Mylor 3 CH | LOCHARD ENERGY (IONA OPERATIONS) TRUST | MYLOR 2, MYLOR 3 | Ensign 973 | J.25.098499 | RPE | ES-CH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-06-16 | 2025-06-01 | 2025-06-11 | 2025-06-11 | 2025-06-30 23:59 | 2025-07-01 | 2025-06-30 23:59 | Roma WL | CKok3 | 2025-08-05 16:17 | PMishra18 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1029132 | O.1029132.03 | A.1029132.03.01 | Mylor 2 and Mylor 3 OH | LOCHARD ENERGY (IONA OPERATIONS) TRUST | MYLOR 2, MYLOR 3 | Ensign 973 | J.25.025147 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2025-04-19 01:00 | 2025-04-20 | 2025-04-30 15:00 | 2025-05-01 | 2025-06-17 23:59 | 2025-07-01 | 2025-06-24 00:59 | Roma WL | JEsmeralda | 2025-06-26 23:16 | SNiang |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 4 |  | L2 - Shift RO |  | 100 | 100 | 100 | 100 | 100 |  | 3 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1029132 | O.1029132.02 | A.1029132.02.01 | CBL-VDL | LOCHARD ENERGY (IONA OPERATIONS) TRUST | Seamer 2 | Ensign 973 | J.22.111029 | RPE | ES-CH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed |  | 2022-06-10 |  | 2022-06-11 | 2022-06-26 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:37 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 113190.38 | 1 |  |  |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1028952 | O.1028952.02 | A.1028952.02.02 | DST Run | ENI JPDA 11-106 B.V. |  | Valaris 107 | J.22.109471 | RPE | DST-CH-JOB | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-11-23 | 2022-11-04 |  | 2022-11-15 | 2022-12-30 23:59 |  | 2022-12-23 23:59 | APG TS | MSwara | 2024-11-19 20:24 | FDPSystemUser |  | No |  | [AUJN-DST] - AU - Jandakot TST |  |  | Yudha Swara |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Downhole Reservoir Testing
P.1028952 | O.1028952.02 | A.1028952.02.01 | TCP Run | ENI JPDA 11-106 B.V. |  | Valaris 107 | J.22.109470 | RPI | TCP-TEMP-JOB | Medium | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2022-08-03 |  | 2022-09-01 | 2022-12-15 23:59 |  |  | APG TS | MSwara | 2024-11-19 20:07 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 0 | 4 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TCP - Tubing-Conveyed Perforation
P.1028952 | O.1028952.01 | A.1028952.01.02 | Blacktip Flowback Operations | ENI JPDA 11-106 B.V. | P3 | Valaris 107 | J.22.109461 | RPI | TSWT-SEPONLY-JOB | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-02-21 | 2022-11-01 |  | 2022-11-01 | 2023-02-15 23:59 |  | 2023-03-07 23:59 | APG TS | RWallis | 2024-11-19 20:14 | FDPSystemUser |  | No |  | [AUNB-TSWT] - Perth- New Burn STT |  |  | Yudha Swara |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1028952 | O.1028952.01 | A.1028952.01.01 | Blacktip Flowback Design | ENI JPDA 11-106 B.V. |  | Valaris 107 | J.22.109460 | RPI | TSWT-DSGN | Medium | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-04-21 |  | 2022-04-21 | 2022-11-20 23:59 |  |  | APG TS | RWallis | 2022-10-03 06:30 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 1600 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1028940 | O.1028940.01 | A.1028940.01.07 | Ocean Apex - Apr Service | SAPURAOMV UPSTREAM (WESTERN AUSTRALIA) PTY LTD | KANGA 1 | Ocean Apex | J.22.111028 | WCF | CMT-EQPRNT,CMT-PERS | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2022-03-21 | 2022-03-21 |  | 2022-03-21 | 2022-04-20 23:59 |  | 2022-04-20 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 12:37 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1028940 | O.1028940.01 | A.1028940.01.01 | 36in conductor | SAPURAOMV UPSTREAM (WESTERN AUSTRALIA) PTY LTD | KANGA-1 | Ocean Apex | J.22.111027 | WCF | PRI-COND | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-05-07 | 2022-04-01 |  | 2022-05-07 | 2022-05-09 23:59 |  | 2022-05-09 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 12:37 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1028940 | O.1028940.01 | A.1028940.01.06 | Ocean Apex - Mar service | SAPURAOMV UPSTREAM (WESTERN AUSTRALIA) PTY LTD | KANGA 1 | Ocean Apex | J.22.110812 | WCF | CMT-EQPRNT,CMT-PERS | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2022-02-21 | 2022-02-21 |  | 2022-02-21 | 2022-03-20 23:59 |  | 2022-03-20 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1028940 | O.1028940.01 | A.1028940.01.02 | 13 3/8in surface casing | SAPURAOMV UPSTREAM (WESTERN AUSTRALIA) PTY LTD | KANGA-1 | Ocean Apex | J.22.110811 | WCF | PRI-SURF | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-05-14 | 2022-04-01 |  | 2022-05-14 | 2022-05-16 23:59 |  | 2022-05-21 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1028940 | O.1028940.01 | A.1028940.01.08 | Ocean Apex - May Service | SAPURAOMV UPSTREAM (WESTERN AUSTRALIA) PTY LTD | KANGA 1 | Ocean Apex | J.22.110809 | WCF | CMT-EQPRNT,CMT-PERS,CMT-MPUMP | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | Design Completed | 2022-04-21 | 2022-04-21 |  | 2022-04-21 | 2022-05-20 23:59 |  | 2022-05-20 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 175082.32 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1028940 | O.1028940.01 | A.1028940.01.03 | 9 5/8in liner | SAPURAOMV UPSTREAM (WESTERN AUSTRALIA) PTY LTD | KANGA 1 | Ocean Apex | J.22.110803 | WCF | PRI-LIN | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-05-24 | 2022-04-01 |  | 2022-05-24 | 2022-05-31 23:59 |  | 2022-05-31 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 171961.54 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1028940 | O.1028940.01 | A.1028940.01.09 | Ocean Apex - Jun service | SAPURAOMV UPSTREAM (WESTERN AUSTRALIA) PTY LTD | KANGA 1 | Ocean Apex | J.22.110801 | WCF | CMT-EQPRNT,CMT-PERS | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | Design Completed | 2022-05-21 | 2022-05-21 |  | 2022-05-21 | 2022-06-20 23:59 |  | 2022-06-20 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 140007.35 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1028940 | O.1028940.01 | A.1028940.01.10 | SapuraOMV - DHT and DSEH rental | SAPURAOMV UPSTREAM (WESTERN AUSTRALIA) PTY LTD | KANGA 1 | Ocean Apex | J.22.110799 | WCF | CMT-EQPRNT | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2022-04-01 | 2022-04-01 |  | 2022-04-01 | 2022-06-30 23:59 |  | 2022-06-30 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1028940 | O.1028940.01 | A.1028940.01.04 | PnA OH | SAPURAOMV UPSTREAM (WESTERN AUSTRALIA) PTY LTD | KANGA 1 | Ocean Apex | J.22.110797 | WCF | REM-PA | High | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-05-31 | 2022-04-01 |  | 2022-05-31 | 2022-06-01 23:59 |  | 2022-06-07 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 249867.26 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1028940 | O.1028940.01 | A.1028940.01.05 | PnA Casing | SAPURAOMV UPSTREAM (WESTERN AUSTRALIA) PTY LTD | KANGA 1 | Ocean Apex | J.22.110795 | WCF | REM-PA | High | Confirmed | Design - CEC |  | Design Completed | Design Completed | Design Completed | 2022-06-02 | 2022-04-01 |  | 2022-06-02 | 2022-06-03 23:59 |  | 2022-06-09 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 |  |  |  | 50 | 66.7 | 0 | 0 | 40 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1028860 | O.1028860.01 | A.1028860.01.01 | Sasanof-1 exploration well | WESTERN GAS (519 P) PTY LTD | SASONOF-1 | ENSCO MS-1 | J.22.110151 | RPE | ES-OH-NO | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-05-02 |  | 2022-05-04 | 2022-06-15 23:59 |  |  | New Burn WL | JDukas | 2022-10-03 10:00 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 256490 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1028859 | O.1028859.01 | A.1028859.01.01 | Sapura Kanga 1 exploration well | SAPURA AUSTRALIA PTY LTD |  | Ocean Apex | J.22.110150 | RPE | ES-OH-NO | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-04-29 |  | 2022-05-04 13:24 | 2022-05-28 23:59 |  |  | New Burn WL | JDukas | 2022-10-03 10:00 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 5 |  |  |  | 66.7 | 100 | 100 | 50 | 75 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1028707 | O.1028707.03 | A.1028707.03.02 | Spartan Flowback - Q4 | SANTOS LIMITED | SPARTAN-2 | NOBLE TOM PROSSER | J.22.109464 | RPI | TSWT-SEPONLY-JOB | High | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2022-10-01 | 2022-08-15 |  | 2022-10-01 | 2023-03-31 23:59 |  | 2023-03-31 23:59 | APG TS | PFlores15 | 2024-11-19 20:14 | FDPSystemUser |  | No |  |  |  |  | Evgeniy Kondratiev |  | 2248740.35 | 1 |  | L0 - No RO |  | 75 | 100 | 100 | 100 | 92.5 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1028707 | O.1028707.03 | A.1028707.03.01 | Spartan Flowback - Q3 | SANTOS LIMITED | Spartan-2 | NOBLE TOM PROSSER | J.22.109463 | RPI | TSWT-SEPONLY-JOB | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-08-15 | 2022-08-01 |  | 2022-08-23 | 2022-09-30 23:59 |  | 2022-11-23 23:59 | APG TS | PFlores15 | 2024-11-19 20:14 | FDPSystemUser |  | No |  | [AUNB-TSWT] - Perth- New Burn STT |  |  | Pablo Andres Caceres Flores |  | 397118.65 | 1 |  |  |  | 83.3 | 83.3 | 100 | 75 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1028707 | O.1028707.03 | A.1028707.03.03 | Spartan Flowback - Q1 | SANTOS LIMITED | Spartan-2 | NOBLE TOM PROSSER | J.22.137291 | RPI | TSWT-SEPONLY-JOB | Medium | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-12-29 |  | 2023-01-01 | 2023-03-31 23:59 |  |  | APG TS | EKondratiev | 2024-11-19 20:14 | FDPSystemUser |  | No |  |  |  |  | Evgeniy Kondratiev |  | 0 | 1 |  | L0 - No RO |  | 25 | 0 | 0 | 25 | 15 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1028707 | O.1028707.02 | A.1028707.02.02 | HJV Campaign - SWT Bleed-Off Q3 | SANTOS LIMITED | GD-02 | NOBLE TOM PROSSER | J.22.109462 | RPI | TSWT-NOSEPNOVX-JOB | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-07-01 | 2022-07-01 |  | 2022-07-01 | 2022-08-01 23:59 |  | 2022-07-01 23:59 | APG TS | PFlores15 | 2022-10-03 06:30 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Pablo Andres Caceres Flores |  | 393826.93 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1028707 | O.1028707.02 | A.1028707.02.01 | HJV Campaign - SWT Bleed Off | SANTOS LIMITED | HA-05, GD-02, HA-01, HA-11, NA-02, HA-08 | NOBLE TOM PROSSER | J.22.109459 | RPI | TSWT-NOSEPNOVX-JOB | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-04-01 | 2022-04-01 |  | 2022-04-01 | 2022-06-24 23:59 |  | 2022-06-24 23:59 | APG TS | PFlores15 | 2022-10-03 06:30 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Pablo Andres Caceres Flores |  | 116258 | 1 |  |  |  | 50 | 50 | 0 | 75 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1028707 | O.1028707.01 | A.1028707.01.01 | HJV Bleed Off and Spartan Flowback Design | SANTOS LIMITED |  | NOBLE TOM PROSSER | J.22.109458 | RPI | TSWT-RENTAL | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress | 2022-06-17 | 2022-04-01 |  | 2022-06-17 | 2022-06-30 23:59 |  | 2022-06-30 23:59 | APG TS | PFlores15 | 2023-02-13 09:56 | RWallis |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Pablo Andres Caceres Flores |  | 76000 | 1 |  |  |  | 50 | 41.7 | 0 | 50 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1028660 | O.1028660.01 | A.1028660.01.05 | ENI_BP_Intervention_SIMPL2 | ENI AUSTRALIA LIMITED | BLACKTIP P2, BLACKTIP P1, BLACKTIP P3 | RIGLESS - AUSTRALIA | J.23.166402 | RPI | PS-SLK-Ops | High | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2024-06-26 | 2024-06-01 |  | 2024-07-05 | 2024-08-26 23:59 |  | 2024-08-26 23:59 | New Burn WL | VOliveira5 | 2025-02-27 09:53 | AHermawan |  | Yes |  |  |  | ROE WL Abu Dhabi | Olesia Azarenko |  | 0 | 11 |  | L1 - Support RO |  | 83.3 | 83.3 | 100 | 75 | 82.5 |  | 6 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1028660 | O.1028660.01 | A.1028660.01.04 | Blacktip P3 Intervention - Commercial | ENI AUSTRALIA LIMITED |  | RIGLESS - AUSTRALIA | J.23.104231 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | In Progress | Not Started |  | 2024-01-17 |  | 2024-02-01 | 2024-03-27 23:59 |  |  | New Burn WL | JSedmak | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 0 |  | L0 - No RO |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1028660 | O.1028660.01 | A.1028660.01.06 | ENI_BTP_Intervention SLK | ENI AUSTRALIA LIMITED | BLACKTIP P2, BLACKTIP P1, BLACKTIP P3 | RIGLESS - AUSTRALIA | J.24.102735 | RPI | PS-SLK-Ops | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | Design Completed | 2024-07-06 | 2024-06-01 |  | 2024-06-10 | 2024-07-22 23:59 |  | 2024-07-22 23:59 | New Burn WL | MElsanousi | 2024-07-06 10:21 | MElsanousi |  | No |  |  |  | ROE WL Abu Dhabi | Jarrod Sedmak |  | 0 | 0 |  | L1 - Support RO |  | 75 | 83.3 | 0 | 0 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1028660 | O.1028660.01 | A.1028660.01.03 | Blacktip SLK | ENI AUSTRALIA LIMITED | Blacktip P1, Blacktip P2 | RIGLESS - AUSTRALIA | J.22.110182 | RPI | PS-SLK-Ops | High | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-10-28 |  | 2022-11-01 | 2022-11-28 23:59 |  |  | New Burn WL | JDukas | 2022-10-03 10:04 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1028660 | O.1028660.01 | A.1028660.01.02 | Blacktip Rigless October | ENI AUSTRALIA LIMITED | Blacktip P1, Blacktip P2 | RIGLESS - AUSTRALIA | J.22.110181 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-10-28 |  | 2022-11-01 | 2022-11-28 23:59 |  |  | New Burn WL | JDukas | 2022-10-03 10:04 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 5 |  |  |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1028660 | O.1028660.01 | A.1028660.01.01 | Blacktip Intervention | ENI AUSTRALIA LIMITED | Blacktip P1, Blacktip P2 | RIGLESS - AUSTRALIA | J.22.110147 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed |  | 2022-05-13 |  | 2022-05-17 | 2022-06-13 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 10:00 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 190378.17 | 5 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1028649 | O.1028649.01 | A.1028649.01.01 | Wastia-5 Flowback | AWE PERTH PTY LTD | Waitsia 5 |  | J.22.109453 | RPI | TSWT-VXONLY-JOB | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-05-15 | 2022-04-15 |  | 2022-06-01 | 2022-06-30 23:59 |  | 2022-05-31 23:59 | APG TS | RWallis | 2024-11-19 20:21 | FDPSystemUser |  | No |  |  |  |  | George Frankpitt |  | 0 | 1 |  |  |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1028649 | O.1028649.01 | A.1028649.01.02 | Watsia-6 Flowback | AWE PERTH PTY LTD | WAITSIA 6 |  | J.22.109454 | RPI | TSWT-VXONLY-JOB | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-04-15 | 2022-04-30 |  | 2022-06-01 | 2022-06-24 23:59 |  | 2022-06-24 23:59 | APG TS | RWallis | 2024-11-19 20:21 | FDPSystemUser |  | No |  |  |  |  | George Frankpitt |  | 0 | 1 |  |  |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1028649 | O.1028649.01 | A.1028649.01.03 | Watsia-8 | AWE PERTH PTY LTD | Waitsia 8 |  | J.22.109455 | RPI | TSWT-VXONLY-JOB | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-06-16 | 2022-07-02 |  | 2022-07-02 | 2022-08-01 23:59 |  | 2022-07-02 23:59 | APG TS | RWallis | 2024-11-19 20:21 | FDPSystemUser |  | No |  |  |  |  | George Frankpitt |  | 0 | 1 |  |  |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1028649 | O.1028649.01 | A.1028649.01.04 | Watsia-7 Flowback | AWE PERTH PTY LTD | Waitsia 7 |  | J.22.109456 | RPI | TSWT-VXONLY-JOB | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-08-10 | 2022-08-02 |  | 2022-08-26 | 2022-09-25 23:59 |  | 2022-08-26 23:59 | APG TS | RWallis | 2024-11-19 20:21 | FDPSystemUser |  | No |  |  |  |  | Qasim Malik |  | 0 | 1 |  |  |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1028649 | O.1028649.01 | A.1028649.01.05 | Watsia-9 Flowback | AWE PERTH PTY LTD |  |  | J.22.109457 | RPI | TSWT-VXONLY-JOB | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2022-09-14 | 2022-09-30 |  | 2022-09-30 | 2022-10-30 23:59 |  | 2022-10-30 23:59 | APG TS | RWallis | 2024-11-19 20:21 | FDPSystemUser |  | No |  |  |  |  | Qasim Malik |  | 0 | 2 |  |  |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1028649 | O.1028649.01 | A.1028649.01.06 | Waitsia-10 Flowback | AWE PERTH PTY LTD | Waitsia 10 |  | J.22.109473 | RPI | TSWT-VXONLY-JOB | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2022-10-10 | 2022-11-10 |  | 2022-11-10 | 2022-12-10 23:59 |  | 2022-11-10 23:59 | APG TS | RWallis | 2024-11-19 20:21 | FDPSystemUser |  | No |  |  |  |  | Qasim Malik |  | 0 | 1 |  |  |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1028649 | O.1028649.01 | A.1028649.01.07 | Watsia 09 Flowback* | AWE PERTH PTY LTD | Waitsia 9 |  | J.22.109484 | RPI | TSWT-VXONLY-JOB | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-09-26 | 2022-09-26 |  | 2022-09-26 | 2022-10-25 23:59 |  | 2022-10-25 23:59 | APG TS | QMalik2 | 2024-11-19 20:21 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Qasim Malik |  | 0 | 1 |  |  |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1028314 | O.1028314.02 | A.1028314.02.04 | MANGAHEWA 39 HFM | TODD ENERGY LIMITED | MANGAHEWA 40, MANGAHEWA 38 | Big Ben | J.25.101945 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2023-09-22 | 2025-09-14 | 2025-09-14 01:00 | 2025-09-14 | 2025-10-10 23:59 | 2025-10-11 | 2024-04-06 23:59 | New Plymouth WL | CKok3 | 2025-11-08 11:55 | LKenzhegulova |  | No |  |  |  |  | Cheryl Kok |  | 361485.7 | 1 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1028314 | O.1028314.02 | A.1028314.02.03 | MANGAHEWA 40 | TODD ENERGY LIMITED | MANGAHEWA 40 | Big Ben | J.25.030270 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-09-22 | 2025-05-20 | 2025-05-26 12:00 | 2025-05-27 | 2025-06-13 23:59 | 2025-06-26 | 2025-06-14 00:59 | New Plymouth WL | CKok3 | 2025-06-21 18:07 | ysaeedabadian |  | No |  |  |  | ROE WL Mumbai | Cheryl Kok |  | 0 | 2 |  | L2 - Shift RO |  | 100 | 100 | 100 | 100 | 100 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1028314 | O.1028314.02 | A.1028314.02.01 | MANGAHEWA 37 | TODD ENERGY LIMITED | MANGAHEWA 37 | Big Ben | J.25.030268 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-09-12 16:00 | 2025-04-29 | 2025-05-04 | 2025-05-04 16:00 | 2025-05-12 15:59 | 2025-05-29 | 2025-05-12 16:59 | New Plymouth WL | CKok3 | 2025-05-21 14:00 | CKok3 |  | No |  |  |  |  | Cheryl Kok |  | 324502 | 2 |  | L0 - No RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 2 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1028314 | O.1028314.02 | A.1028314.02.02 | MANGAHEWA 38 | TODD ENERGY LIMITED | MANGAHEWA 38 | Big Ben | J.25.030269 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-10-03 | 2025-03-10 | 2025-03-28 | 2025-03-28 | 2025-04-04 23:59 | 2025-04-05 | 2025-04-04 23:59 | New Plymouth WL | CKok3 | 2025-04-08 17:17 | LKenzhegulova |  | No |  |  |  |  | Cheryl Kok |  | 327110 | 3 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 2 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1028314 | O.1028314.01 | A.1028314.01.08 | MHW-35 | TODD ENERGY LIMITED | MANGAHEWA-35 | Big Ben | J.22.110446 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2022-12-08 02:00 | 2022-12-02 |  | 2022-12-08 | 2022-12-12 23:59 |  | 2022-12-13 01:59 | New Plymouth WL | CLorenzo | 2022-12-07 16:21 | CKok3 |  | No |  |  |  |  | Omar Mosleh |  | 341696.46 | 4 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Claudio Sanabria | WL Evaluation Services
P.1028314 | O.1028314.01 | A.1028314.01.07 | MHW-36 | TODD ENERGY LIMITED | MANGAHEWA-36 | Big Ben | J.22.111026 | RPE | ES-OH-Ops | Medium | Confirmed | Design - PSD |  | Design Completed | Not Required | In Progress | 2022-10-23 22:00 | 2022-11-02 |  | 2022-11-02 | 2022-11-06 23:59 |  | 2022-11-19 14:42 | New Plymouth WL | CLorenzo | 2022-11-18 15:24 | YLee25 |  | No |  |  |  |  | Omar Mosleh |  | 341696.46 | 4 |  | L0 - No RO |  | 75 | 33.3 | 0 | 100 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Claudio Sanabria | WL Evaluation Services
P.1028314 | O.1028314.01 | A.1028314.01.06 | MHW-34 | TODD ENERGY LIMITED | MANGAHEWA-34 | Big Ben | J.22.110445 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-09-15 |  | 2022-09-25 | 2022-09-30 00:59 |  |  | New Plymouth WL | CLorenzo | 2022-10-24 11:38 | CLorenzo |  | No |  |  |  |  | Paulo Zuliani |  | 341696.46 | 4 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Claudio Sanabria | WL Evaluation Services
P.1028314 | O.1028314.01 | A.1028314.01.01 | MHW-33 | TODD ENERGY LIMITED | Mangahewa-33 | Big Ben | J.22.110449 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed |  | 2022-08-15 |  | 2022-08-21 | 2022-08-29 23:59 |  |  | New Plymouth WL | MRony2 | 2022-10-24 11:37 | CLorenzo |  | No |  |  |  |  | Omar Mosleh |  | 0 | 4 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Claudio Sanabria | WL Evaluation Services
P.1028314 | O.1028314.01 | A.1028314.01.02 | MHW-34 | TODD ENERGY LIMITED |  | Big Ben | J.22.111025 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-08-31 |  | 2022-09-02 | 2022-09-06 23:59 |  |  | New Plymouth WL | MRony2 | 2022-10-03 17:37 | FDPSystemUser |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 3 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Ansar-Ud-Din Muhammad | WL Evaluation Services
P.1028314 | O.1028314.01 | A.1028314.01.03 | MHW-36 | TODD ENERGY LIMITED |  | Big Ben | J.22.110453 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-10-05 |  | 2022-10-07 | 2022-10-11 23:59 |  |  | New Plymouth WL | MRony2 | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 3 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ansar-Ud-Din Muhammad | WL Evaluation Services
P.1028314 | O.1028314.01 | A.1028314.01.05 | MHW-34 | TODD ENERGY LIMITED |  | Big Ben | J.22.110447 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-09-15 |  | 2022-09-25 | 2022-09-30 00:59 |  |  | New Plymouth WL | CLorenzo | 2022-10-03 16:19 | FDPSystemUser |  | Yes |  |  |  |  | Paulo Zuliani |  | 0 | 4 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Claudio Sanabria | WL Evaluation Services
P.1028314 | O.1028314.01 | A.1028314.01.04 | MHW-33 | TODD ENERGY LIMITED |  | Big Ben | J.22.110442 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-11-03 |  | 2022-11-05 | 2022-11-09 23:59 |  |  | New Plymouth WL | MRony2 | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 3 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Ansar-Ud-Din Muhammad | WL Evaluation Services
P.1028276 | O.1028276.01 | A.1028276.01.01 | Vali-2_Frac support | VINTAGE ENERGY LTD | VALI 2 | Rigless Australia - 1 | J.22.110319 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-05-05 23:00 | 2022-05-03 |  | 2022-05-06 | 2022-06-03 23:59 |  | 2022-06-03 22:59 | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 223326.01 | 9 |  | L0 - No RO |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1028276 | O.1028276.01 | A.1028276.01.02 | Vali-2_Frac | VINTAGE ENERGY LTD | VALI-2, VALI-3 | Rigless Australia - 1 | J.22.110309 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2022-04-02 23:00 |  | 2022-04-02 23:00 | 2022-04-17 22:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 187690.19 | 10 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1028109 | O.1028109.01 | A.1028109.01.01 | CL-VDL | ARROW ENERGY LTD | Tipton 200 |  | J.22.110313 | RPI | PS-WL-Ops | InComplete | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-02-15 15:00 |  | 2022-02-16 10:00 | 2022-02-16 16:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1028053 | O.1028053.01 | A.1028053.01.01 | HJV RIg P&A Campaign | SANTOS LIMITED | GD-02, HA-01, HARRIET A3 (HA 03), HA-05, HA-08, HA-11, NA-02, HARRIET A9 (HA 09) | NOBLE TOM PROSSER | J.22.110156 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-04-28 |  | 2022-04-29 | 2022-09-11 23:59 |  |  | New Burn WL | JDukas | 2022-10-03 10:01 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 91895 | 7 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1027604 | O.1027604.01 | A.1027604.01.06 | Arroew_Sep | ARROW ENERGY LTD | Stratheden 168 | SAVANNA DRILLING #407 | J.22.111024 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-09-07 |  | 2022-09-09 08:00 | 2022-09-11 20:59 |  |  | Roma WL | MRony2 | 2022-10-19 15:43 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1027604 | O.1027604.01 | A.1027604.01.01 | Tipton 285 | ARROW ENERGY LTD | Tipton 285 | SAVANNA DRILLING #407 | J.22.111023 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-01-20 |  | 2022-01-20 20:00 | 2022-01-21 08:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:37 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 8999.35 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1027604 | O.1027604.01 | A.1027604.01.04 | Stratheden 168 | ARROW ENERGY LTD | Stratheden 168 | SAVANNA DRILLING #407 | J.22.110306 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-02-15 |  | 2022-02-17 08:00 | 2022-02-19 20:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 8999.35 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1027604 | O.1027604.01 | A.1027604.01.05 | Longswamp 401 | ARROW ENERGY LTD |  | SAVANNA DRILLING #407 | J.22.110305 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-04-14 |  | 2022-04-15 20:00 | 2022-04-16 08:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1027604 | O.1027604.01 | A.1027604.01.02 | Stratheden 166 | ARROW ENERGY LTD | Tipton 285, Stratheden 166 | SAVANNA DRILLING #407 | J.22.110303 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-02-03 |  | 2022-02-03 20:00 | 2022-02-04 08:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 8999.35 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1027604 | O.1027604.01 | A.1027604.01.03 | Stratheden 167 | ARROW ENERGY LTD | Stratheden 167 | SAVANNA DRILLING #407 | J.22.110302 | RPE | ES-OH-NO | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-02-21 |  | 2022-02-22 20:00 | 2022-03-22 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 47205.98 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1027419 | O.1027419.01 | A.1027419.01.01 | USIT_Plug | AGL ENERGY LIMITED | LINK-1 |  | J.22.111022 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-17 06:00 | 2022-01-16 |  | 2022-01-17 06:00 | 2022-01-20 23:59 |  | 2022-01-20 23:59 | Roma WL | MRony2 | 2022-10-03 15:36 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 36419.75 | 3 |  | L0 - No RO |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1026787 | O.1026787.02 | A.1026787.02.01 | XNA-03 OHGP | WOODSIDE BURRUP PTY. LTD | Well #1 | OCEAN APEX | J.25.099741 | RPS | SMS-OHGP-APS | High | Confirmed | Design - CEC |  | Not Started | Design Completed | Not Started |  | 2026-02-16 |  | 2026-02-16 | 2026-03-01 23:59 |  |  | AUS West Coast WS | radinegara | 2025-10-31 23:02 | radinegara |  | No |  |  |  |  | Ramadhani Adi Negara |  | 0 | 0 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 10 |  | 1 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Production Services
P.1026787 | O.1026787.01 | A.1026787.01.03 | 13 3/8in casing | WOODSIDE BURRUP PTY. LTD | XNA 02 | Ocean Apex | J.22.111021 | WCF | PRI-INTER | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-06-25 | 2022-05-11 |  | 2022-06-25 | 2022-07-02 23:59 |  | 2022-07-02 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 12:36 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 |  |  |  | 68.8 | 66.7 | 0 | 0 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1026787 | O.1026787.01 | A.1026787.01.01 | 36in Conductor | WOODSIDE BURRUP PTY. LTD | XNA 02 | Ocean Apex | J.22.111020 | WCF | PRI-COND | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | Design Completed | 2022-06-10 | 2022-06-02 |  | 2022-06-10 | 2022-06-12 23:59 |  | 2022-06-12 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 12:36 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 |  |  |  | 75 | 66.7 | 0 | 0 | 50 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1026787 | O.1026787.01 | A.1026787.01.08 | Woodside - DHT rental | WOODSIDE BURRUP PTY. LTD |  | Ocean Apex | J.22.110852 | WCF | CMT-EQPRNT | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2022-06-04 | 2022-06-04 |  | 2022-06-04 | 2022-07-31 23:59 |  | 2022-09-02 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 |  |  |  | 75 | 66.7 | 100 | 25 | 65 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1026787 | O.1026787.01 | A.1026787.01.06 | Ocean Apex - July Service | WOODSIDE BURRUP PTY. LTD | XNA02 | Ocean Apex | J.22.110847 | WCF | CMT-EQPRNT,CMT-MATSAL,CMT-PERS | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-07-05 | 2022-06-21 |  | 2022-06-21 | 2022-07-20 23:59 |  | 2022-07-20 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 185239.98 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1026787 | O.1026787.01 | A.1026787.01.07 | Ocean Apex - Aug service | WOODSIDE BURRUP PTY. LTD | XNA 02 | Ocean Apex | J.22.110831 | WCF | CMT-EQPRNT,CMT-MATSAL,CMT-PERS,CMT-MPUMP | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | Design Completed | 2022-08-29 | 2022-07-21 |  | 2022-07-21 | 2022-08-20 23:59 |  | 2022-08-30 21:27 | AUS West Coast WS | NKhoa | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 46194.09 | 1 |  |  |  | 93.8 | 50 | 100 | 75 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1026787 | O.1026787.01 | A.1026787.01.05 | Ocean Apex - Jun service | WOODSIDE BURRUP PTY. LTD | XNA 02 | Ocean Apex | J.22.110827 | WCF | CMT-EQPRNT,CMT-MATSAL,CMT-PERS | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | Design Completed | 2022-06-20 | 2022-06-01 |  | 2022-06-01 | 2022-06-20 23:59 |  | 2022-06-20 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 100763.9 | 0 |  |  |  | 93.8 | 50 | 100 | 50 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1026787 | O.1026787.01 | A.1026787.01.04 | 9 5/8in liner | WOODSIDE BURRUP PTY. LTD | XNA 02 | Ocean Apex | J.22.110816 | WCF | PRI-LIN | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-07-08 | 2022-05-19 |  | 2022-07-08 | 2022-07-15 23:59 |  | 2022-07-15 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 483287.8 | 1 |  |  |  | 81.3 | 66.7 | 0 | 50 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1026787 | O.1026787.01 | A.1026787.01.02 | 20in Casing | WOODSIDE BURRUP PTY. LTD | XNA 02 | Ocean Apex | J.22.110814 | WCF | PRI-SURF | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-06-13 | 2022-05-11 |  | 2022-06-13 | 2022-06-15 23:59 |  | 2022-06-15 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 149867 | 1 |  |  |  | 81.3 | 66.7 | 0 | 50 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1026432 | O.1026432.01 | A.1026432.01.04 | Yoorn-1 | SANTOS LIMITED | YOORN-1 | NOBLE TOM PROSSER | J.22.110142 | RPE | ES-OH-Ops | Medium | Cancelled | Execute - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-12-14 |  | 2024-01-01 13:24 | 2024-01-25 23:59 |  |  | New Burn WL | BAhmad | 2024-08-21 13:52 | FDPSystemUser |  | Yes |  |  |  |  | Justin Dukas |  | 0 | 5 |  |  |  | 58.3 | 16.7 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1026432 | O.1026432.01 | A.1026432.01.03 | Apus 1 | SANTOS LIMITED | APUS-1 | NOBLE TOM PROSSER | J.22.110141 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-04-16 |  | 2022-04-19 13:24 | 2022-05-13 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:59 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 1164398 | 5 |  |  |  | 83.3 | 100 | 0 | 100 | 85 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1026432 | O.1026432.01 | A.1026432.01.02 | Pavo | SANTOS LIMITED | PAVO-1 | NOBLE TOM PROSSER | J.22.110140 | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-02-22 |  | 2022-03-10 | 2022-04-01 |  |  | New Burn WL | BAhmad | 2022-10-03 09:59 | FDPSystemUser |  | No |  |  |  |  | James Cade |  | 1036626 | 6 |  |  |  | 91.7 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1026432 | O.1026432.01 | A.1026432.01.01 | Dancer-1 | SANTOS LIMITED | DANCER-1 | NOBLE TOM PROSSER | J.22.110139 | RPE | ES-OH-NO | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-01-07 |  | 2022-01-13 13:24 | 2022-02-01 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:59 | FDPSystemUser |  | Yes |  |  |  | ROE WL Mumbai | James Cade |  | 841932 | 5 |  |  |  | 75 | 50 | 100 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1026302 | O.1026302.01 | A.1026302.01.03 | Harriet Alpha April ops | SANTOS LIMITED |  |  | J.22.110137 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-04-14 |  | 2022-04-15 | 2022-05-09 23:59 |  |  | New Burn WL | JDukas | 2022-10-03 09:59 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 9 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1026302 | O.1026302.01 | A.1026302.01.02 | Harriet Alpha March-April ops | SANTOS LIMITED | HA-11, HARRIET A3 (HA 03), HA-08, HA-01, HA-05, HARRIET A9 (HA 09), NA-02, GD-02 |  | J.22.110136 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-02-25 23:00 |  | 2022-02-26 | 2022-04-28 23:59 |  |  | New Burn WL | JDukas | 2022-10-03 09:58 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 4 |  |  |  | 91.7 | 50 | 0 | 50 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1026302 | O.1026302.01 | A.1026302.01.01 | Harriet Alpha Feb ops | SANTOS LIMITED | NA-02, HA-01, HA-08, HA-05 |  | J.22.110135 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-02-02 |  | 2022-02-06 | 2022-03-02 23:59 |  |  | New Burn WL | JDukas | 2022-10-03 09:58 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 322600 | 9 |  |  |  | 91.7 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1026261 | O.1026261.01 | A.1026261.01.01 | Preparation | SANTOS LIMITED | DURHAM DOWNS 9 | RIGLESS - AUSTRALIA | J.22.109451 | RPI | TCP-PERM-JOB | High | Confirmed | Execute - PSD |  | Not Required | Design Completed | In Progress |  | 2022-08-01 |  | 2022-08-09 | 2022-09-02 23:59 |  |  | APG TS | MSwara | 2022-10-03 06:29 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 89507.79 | 1 |  |  |  | 66.7 | 50 | 100 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TCP - Tubing-Conveyed Perforation
P.1025644 | O.1025644.01 | A.1025644.01.06 | Quotation For 9000T Of Grout Blend | LIHIR GOLD LTD | TIRRAWARRA 47 |  | J.23.096546 | WCF | CMT-DSL | Low | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2023-06-02 |  | 2023-09-01 | 2023-12-31 23:59 |  |  | AUS East Coast WS | MAlsaman | 2023-08-17 10:50 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 0 |  |  |  | 56.3 | 33.3 | 100 | 25 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025644 | O.1025644.01 | A.1025644.01.05 | Product Direct Sale For May | LIHIR GOLD LTD | TIRRAWARRA 47 |  | J.23.094877 | WCF | CMT-DSL | Low | Operationally Complete | Execute - PSD |  | Not Started | Not Started | Not Started |  | 2023-05-31 |  | 2023-05-31 | 2023-05-31 23:59 |  |  | AUS East Coast WS | MAlsaman | 2023-06-15 15:39 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 51765.5 | 0 |  |  |  | 56.3 | 33.3 | 100 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025644 | O.1025644.01 | A.1025644.01.02 | Jan 2023 Direct Sale | LIHIR GOLD LTD | TIRRAWARRA 47 |  | J.23.029193 | WCF | CMT-DSL | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2023-01-24 |  | 2023-01-25 | 2023-01-25 23:59 |  |  | AUS East Coast WS | MAlsaman | 2023-05-27 15:31 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 409370 | 0 |  |  |  | 62.5 | 33.3 | 100 | 50 | 55 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025644 | O.1025644.01 | A.1025644.01.04 | Mar 2023 Direct Sale | LIHIR GOLD LTD | TIRRAWARRA 47 |  | J.23.059502 | WCF | CMT-DSL | Low | Operationally Complete | Close - PSD |  | Not Started | Not Started | Not Started |  | 2023-03-25 |  | 2023-03-25 | 2023-03-25 23:59 |  |  | AUS East Coast WS | MAlsaman | 2023-03-24 15:17 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 157525 | 0 |  |  |  | 56.3 | 33.3 | 100 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025644 | O.1025644.01 | A.1025644.01.03 | Feb Direct Sale | LIHIR GOLD LTD | TIRRAWARRA 47 |  | J.23.042538 | WCF | CMT-DSL | Low | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2023-02-22 |  | 2023-02-25 | 2023-02-25 23:59 |  |  | AUS East Coast WS | MAlsaman | 2023-02-27 00:50 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 307906 | 0 |  |  |  | 62.5 | 33.3 | 100 | 25 | 50 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025644 | O.1025644.01 | A.1025644.01.01 | Product Sales Oct 2022 | LIHIR GOLD LTD | TIRRAWARRA 47 |  | J.22.119110 | WCF | CMT-DSL,CMT-MATSAL | Low | Confirmed | Design - CEC |  | Not Required | Design Completed | Not Required |  | 2022-10-21 |  | 2022-10-25 | 2022-10-25 23:59 |  |  | AUS East Coast WS | MAlsaman | 2022-10-24 18:36 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 131339 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025249 | O.1025249.01 | A.1025249.01.01 | Santos Bottles and Sampling Analysis | SANTOS LIMITED |  | NOBLE TOM PROSSER | J.21.108348 | RPE | FSA-RECHARGE | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2021-11-12 |  | 2021-11-18 | 2021-11-25 23:59 |  |  | APG TS | RWallis | 2022-10-03 06:29 | FDPSystemUser |  | No |  |  |  |  | Wayne Wallis |  | 51000 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Downhole Reservoir Testing
P.1025208 | O.1025208.02 | A.1025208.02.08 | Services - Personnel & Equipment - September 2022 | AWE PERTH PTY LTD | Waitsia 9 | Easternwell 106 | J.22.110841 | WCF | CMT-EQPRNT,CMT-PERS | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-08-21 |  | 2022-08-21 | 2022-09-20 23:59 |  |  | AUS West Coast WS | HNarainasamy | 2023-01-25 13:26 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 136632.54 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.02 | A.1025208.02.10 | Services - Personnel & Equipment - November 2022 | AWE PERTH PTY LTD | Waitsia 10 | Easternwell 106 | J.22.111019 | WCF | CMT-EQPRNT,CMT-PERS | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-10-21 |  | 2022-10-21 | 2022-10-30 23:59 |  |  | AUS West Coast WS | HNarainasamy | 2022-11-11 11:29 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 47902.25 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.02 | A.1025208.02.09 | Services - Personnel & Equipment - October 2022 | AWE PERTH PTY LTD | Waitsia 10 | Easternwell 106 | J.22.110851 | WCF | CMT-EQPRNT,CMT-PERS | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-09-21 |  | 2022-09-21 | 2022-10-20 23:59 |  |  | AUS West Coast WS | HNarainasamy | 2022-10-26 15:58 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 141718.96 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.02 | A.1025208.02.05 | Services - Personnel & Equipment - July 2022 - Waitsia-08 | AWE PERTH PTY LTD | Waitsia 8 | Easternwell 106 | J.22.111018 | WCF | CMT-EQPRNT,CMT-PERS | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | Design Completed |  | 2022-06-21 |  | 2022-06-21 | 2022-07-09 23:59 |  |  | AUS West Coast WS | HNarainasamy | 2022-10-03 12:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 78268.07 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.02 | A.1025208.02.01 | Services - Personnel & Equipment - April 2022 | AWE PERTH PTY LTD | Waitsia 5 | Easternwell 106 | J.22.111017 | WCF | CMT-EQPRNT,CMT-PERS | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-03-23 |  | 2022-03-23 | 2022-04-24 23:59 |  |  | AUS West Coast WS | HNarainasamy | 2022-10-03 12:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 183858.34 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.02 | A.1025208.02.04 | Services - Personnel & Equipment - June 2022 - Waitsia 08 | AWE PERTH PTY LTD | Waitsia 8 | Easternwell 106 | J.22.110844 | WCF | CMT-EQPRNT,CMT-PERS | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | Design Completed |  | 2022-06-05 |  | 2022-06-05 | 2022-06-20 23:59 |  |  | AUS West Coast WS | HNarainasamy | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 58270.08 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.02 | A.1025208.02.06 | Services - Personnel & Equipment - July 2022 - Waitsia-07 | AWE PERTH PTY LTD | Waitsia 7 | Easternwell 106 | J.22.110833 | WCF | CMT-EQPRNT,CMT-PERS | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-07-10 |  | 2022-07-10 | 2022-07-20 23:59 |  |  | AUS West Coast WS | HNarainasamy | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 45491.93 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.02 | A.1025208.02.07 | Services - Personnel & Equipment - August 2022 | AWE PERTH PTY LTD | Waitsia 7 | Easternwell 106 | J.22.110823 | WCF | CMT-EQPRNT,CMT-PERS | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-07-21 |  | 2022-07-21 | 2022-08-20 23:59 |  |  | AUS West Coast WS | HNarainasamy | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 128477.9 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.02 | A.1025208.02.03 | Services - Personnel & Equipment - June 2022 | AWE PERTH PTY LTD | Waitsia 6 | Easternwell 106 | J.22.110820 | WCF | CMT-EQPRNT,CMT-PERS | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | Design Completed |  | 2022-05-21 |  | 2022-05-21 | 2022-06-04 23:59 |  |  | AUS West Coast WS | HNarainasamy | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 46179.15 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.02 | A.1025208.02.02 | Services - Personnel & Equipment - May 2022 | AWE PERTH PTY LTD | Waitsia 6 | Easternwell 106 | J.22.110819 | WCF | CMT-EQPRNT,CMT-PERS | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-04-25 |  | 2022-04-25 | 2022-05-20 23:59 |  |  | AUS West Coast WS | HNarainasamy | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 128060.74 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.01 | A.1025208.01.11 | 13-3/8" Casing Cementing | AWE PERTH PTY LTD | WAITSIA 10 | Easternwell 106 | J.22.110779 | WCF | PRI-SURF, CMT-MATSAL | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2022-09-07 19:00 | 2022-10-08 12:00 |  | 2022-10-09 07:00 | 2022-10-10 06:59 |  | 2022-09-08 18:59 | AUS West Coast WS | HNarainasamy | 2022-11-29 10:02 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 55317.84 | 0 |  |  |  | 87.5 | 66.7 | 0 | 50 | 65 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.01 | A.1025208.01.16 | Waitsia 10 -Plugback - #4 | AWE PERTH PTY LTD | Waitsia 10 | Easternwell 106 | J.22.120257 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-27 14:00 | 2022-10-29 06:00 |  | 2022-10-29 20:00 | 2022-10-30 19:59 |  | 2022-11-01 13:59 | AUS West Coast WS | HNarainasamy | 2022-11-04 15:51 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 5819.43 | 1 |  |  |  | 81.3 | 50 | 0 | 50 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.01 | A.1025208.01.14 | Waitsia 10 - Plugback for Suspension #1-#2 | AWE PERTH PTY LTD | Waitsia 10 | Easternwell 106 | J.22.118741 | WCF | REM-PA, CMT-MATSAL | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-24 12:00 | 2022-10-26 06:00 |  | 2022-10-26 18:00 | 2022-10-27 17:59 |  | 2022-10-29 11:59 | AUS West Coast WS | HNarainasamy | 2022-11-04 15:45 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 54292.28 | 1 |  |  |  | 81.3 | 50 | 0 | 50 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.01 | A.1025208.01.15 | Waitsia 10 - Plugback #3 | AWE PERTH PTY LTD | WAITSIA 10 | Easternwell 106 | J.22.120255 | WCF | REM-PA | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-10-24 17:00 | 2022-10-26 06:00 |  | 2022-10-26 23:00 | 2022-10-27 06:00 |  | 2022-10-29 | AUS West Coast WS | HNarainasamy | 2022-10-26 12:35 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 68.8 | 50 | 0 | 0 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.01 | A.1025208.01.12 | 9-5/8" Casing Cementing | AWE PERTH PTY LTD | Waitsia 10 | Easternwell 106 | J.22.110777 | WCF | PRI-INTER, CMT-DSL | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-09-20 06:00 | 2022-10-18 12:00 |  | 2022-10-19 06:00 | 2022-10-20 05:59 |  | 2022-09-21 05:59 | AUS West Coast WS | HNarainasamy | 2022-10-21 12:19 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 46507.02 | 1 |  |  |  | 87.5 | 66.7 | 0 | 50 | 65 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.01 | A.1025208.01.13 | Waitsia 07 - Suspension Plug | AWE PERTH PTY LTD | Waitsia 7 | Easternwell 106 | J.22.110850 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-09 21:00 | 2022-08-11 18:00 |  | 2022-08-12 03:00 | 2022-08-14 02:59 |  | 2022-08-15 20:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 9999.91 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.01 | A.1025208.01.10 | 9-5/8" Casing Cementing | AWE PERTH PTY LTD | Waitsia 9 | Easternwell 106 | J.22.110790 | WCF | PRI-INTER, CMT-DSL | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-12 | 2022-09-09 12:00 |  | 2022-09-10 | 2022-09-10 23:59 |  | 2022-08-12 23:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 15804.57 | 1 |  |  |  | 87.5 | 33.3 | 0 | 50 | 55 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.01 | A.1025208.01.08 | 9-5/8" Casing Cementing | AWE PERTH PTY LTD | Waitsia 7 | Easternwell 106 | J.22.110789 | WCF | PRI-INTER, CMT-DSL | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-02 17:00 | 2022-08-01 12:00 |  | 2022-08-03 17:00 | 2022-08-05 16:59 |  | 2022-08-06 16:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 18152.68 | 1 |  |  |  | 87.5 | 83.3 | 0 | 50 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.01 | A.1025208.01.05 | 13-3/8" Casing Cementing | AWE PERTH PTY LTD | Waitsia 8 | Easternwell 106 | J.22.110787 | WCF | PRI-SURF, CMT-MATSAL | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-06-11 04:00 | 2022-06-11 12:00 |  | 2022-06-14 12:00 | 2022-06-16 11:59 |  | 2022-06-18 03:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 8268.1 | 0 |  |  |  | 87.5 | 50 | 0 | 50 | 60 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.01 | A.1025208.01.04 | 9-5/8" Casing Cementing | AWE PERTH PTY LTD | Waitsia 6 | Easternwell 106 | J.22.110784 | WCF | PRI-INTER, CMT-DSL | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-05-18 10:00 | 2022-05-15 06:00 |  | 2022-05-19 16:00 | 2022-05-20 06:00 |  | 2022-05-22 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 16073.24 | 1 |  |  |  | 87.5 | 50 | 0 | 50 | 60 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.01 | A.1025208.01.09 | 13-3/8" Casing Cementing | AWE PERTH PTY LTD | Waitsia 9 | Easternwell 106 | J.22.110781 | WCF | PRI-SURF, CMT-MATSAL | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-02 02:00 | 2022-08-30 |  | 2022-08-31 02:00 | 2022-09-02 01:59 |  | 2022-08-04 01:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 8930.47 | 0 |  |  |  | 87.5 | 33.3 | 0 | 25 | 50 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.01 | A.1025208.01.02 | 9-5/8" Casing Cementing | AWE PERTH PTY LTD | Waitsia 5 | Easternwell 106 | J.22.110776 | WCF | PRI-INTER, CMT-DSL | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-08 10:00 | 2022-04-07 16:00 |  | 2022-04-10 10:00 | 2022-04-11 09:59 |  | 2022-04-12 09:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 15897.24 | 1 |  |  |  | 81.3 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.01 | A.1025208.01.06 | 9-5/8" Casing Cementing | AWE PERTH PTY LTD | Waitsia 8 | Easternwell 106 | J.22.110775 | WCF | PRI-INTER, CMT-DSL | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-06-22 22:00 | 2022-06-22 12:00 |  | 2022-06-25 | 2022-06-26 23:59 |  | 2022-06-28 09:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 15491.15 | 1 |  |  |  | 87.5 | 33.3 | 0 | 50 | 55 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.01 | A.1025208.01.07 | 13-3/8" Casing Cementing | AWE PERTH PTY LTD | Waitsia 7 | Easternwell 106 | J.22.110774 | WCF | PRI-SURF, CMT-MATSAL | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-07-20 13:00 | 2022-07-21 12:00 |  | 2022-07-22 01:00 | 2022-07-23 00:59 |  | 2022-07-24 12:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 9222.97 | 0 |  |  |  | 87.5 | 50 | 0 | 50 | 60 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.01 | A.1025208.01.01 | 13-3/8" Casing Cementing | AWE PERTH PTY LTD | Waitsia 5 | Easternwell 106 | J.22.110770 | WCF | PRI-SURF, CMT-MATSAL | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2022-03-18 03:00 | 2022-03-25 |  | 2022-03-29 03:00 | 2022-03-29 19:00 |  | 2022-03-31 19:00 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 8560.59 | 0 |  |  |  | 75 | 33.3 | 0 | 50 | 50 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025208 | O.1025208.01 | A.1025208.01.03 | 13-3/8" Casing Cementing | AWE PERTH PTY LTD | Waitsia 6 | Easternwell 106 | J.22.110769 | WCF | PRI-SURF, CMT-MATSAL | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-05-06 | 2022-05-04 |  | 2022-05-06 02:00 | 2022-05-08 01:59 |  | 2022-05-09 23:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 8370.7 | 0 |  |  |  | 87.5 | 33.3 | 0 | 50 | 55 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1025016 | O.1025016.01 | A.1025016.01.01 | EOG - 2023 - DST | SANTOS LIMITED | Well #1 | WDI-826 | J.23.008518 | RPE | DST-CH-JOB | Medium | Cancelled | Close - PSD |  | In Progress | Not Required | In Progress | 2023-04-01 | 2022-12-01 |  | 2023-05-01 | 2023-05-31 23:59 |  | 2023-05-31 23:59 | APG TS | GRoxo | 2024-11-19 20:24 | FDPSystemUser |  | No |  | [AUJN-DST] - AU - Jandakot TST |  |  | Yudha Swara |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Downhole Reservoir Testing
P.1025016 | O.1025016.01 | A.1025016.01.02 | EOG - 2023 - SWT | SANTOS LIMITED | Well #1 | WDI-826 | J.23.008519 | RPI | TSWT-SEPONLY-JOB | Medium | Cancelled | Close - PSD |  | In Progress | Not Required | In Progress | 2023-04-01 | 2022-12-01 |  | 2023-04-01 | 2023-05-31 23:59 |  | 2023-05-31 23:59 | APG TS | GRoxo | 2024-11-19 20:14 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1024999 | O.1024999.01 | A.1024999.01.01 | 2022-006; Kappa-1 | SANTOS LIMITED | Kappa 1 | RIGLESS - AUSTRALIA | J.22.109449 | RPI | TCP-TEMP-JOB | Medium | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-02-27 |  | 2022-02-27 | 2022-03-23 23:59 |  |  | APG TS | GRoxo | 2024-11-19 20:07 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 0 | 1 |  |  |  | 75 | 33.3 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TCP - Tubing-Conveyed Perforation
P.1024999 | O.1024999.01 | A.1024999.01.02 | Moomba TCP 2022 Well 02 | SANTOS LIMITED | Well #2 | RIGLESS - AUSTRALIA | J.22.109450 | RPI | TCP-TEMP-JOB | Medium | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-04-23 |  | 2022-04-29 | 2022-05-23 23:59 |  |  | APG TS | GRoxo | 2024-11-19 20:07 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 0 | 1 |  |  |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TCP - Tubing-Conveyed Perforation
P.1024984 | O.1024984.03 | A.1024984.03.02 | Mitsui Hovea-14 Intercept Pump down | MEPAU PERTH BASIN PTY LTD | HOVEA 14 | VENTIA 106 | J.24.102683 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2024-07-01 | 2024-06-28 |  | 2024-07-01 | 2024-07-22 09:55 |  | 2024-07-22 09:55 | New Burn WL | MElsanousi | 2024-07-31 17:55 | MAlhashemi |  | No |  |  |  |  | Peter Roche |  | 22092.27 | 21 |  | L0 - No RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1024984 | O.1024984.03 | A.1024984.03.01 | Mitsui Hovea-14 Intercept P&A | MEPAU PERTH BASIN PTY LTD | HOVEA 14 | VENTIA 106 | J.24.076799 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2024-05-20 | 2024-05-17 |  | 2024-05-20 | 2024-06-23 09:55 |  | 2024-06-23 09:55 | New Burn WL | APutri | 2024-07-30 09:30 | MAlhashemi |  | No |  |  |  |  | Ade Kusuma Putri |  | 62610 | 1 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1024984 | O.1024984.02 | A.1024984.02.01 | Mitsui OH Logging Jul | MEPAU PERTH BASIN PTY LTD |  | VENTIA 106 | J.23.008578 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2023-01-26 |  | 2023-01-30 | 2023-02-18 23:59 |  |  | New Burn WL | APutri | 2022-10-03 10:02 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1024984 | O.1024984.01 | A.1024984.01.04 | Mitsui SLK CO2 | MEPAU PERTH BASIN PTY LTD |  | VENTIA 106 | J.23.008572 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2024-02-15 | 2024-02-14 |  | 2024-02-15 | 2024-03-05 23:59 |  | 2024-03-05 23:59 | New Burn WL | BAhmad | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Peter Roche |  | 0 | 1 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 1 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1024984 | O.1024984.01 | A.1024984.01.02 | Mitsui OH Logging Jul | MEPAU PERTH BASIN PTY LTD |  | VENTIA 106 | J.23.008570 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-11-23 | 2023-11-10 |  | 2023-11-23 | 2023-12-12 23:59 |  | 2023-12-12 23:59 | New Burn WL | BAhmad | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1024984 | O.1024984.01 | A.1024984.01.03 | Mitsui OH Logging Sep | MEPAU PERTH BASIN PTY LTD |  | VENTIA 106 | J.23.008571 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-12-14 | 2023-12-09 |  | 2023-12-14 | 2024-01-02 23:59 |  | 2024-01-02 23:59 | New Burn WL | BAhmad | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1024984 | O.1024984.01 | A.1024984.01.05 | Mitsui HSD Perforation | MEPAU PERTH BASIN PTY LTD |  | VENTIA 106 | J.22.110172 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-08-25 |  | 2022-08-31 | 2022-09-20 23:59 |  |  | New Burn WL | APutri | 2022-10-03 10:02 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 4 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1024984 | O.1024984.01 | A.1024984.01.01 | Mitsui OH Logging May | MEPAU PERTH BASIN PTY LTD |  | VENTIA 106 | J.22.110133 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-05-01 |  | 2022-05-05 | 2022-05-24 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:58 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1024966 | O.1024966.01 | A.1024966.01.04 | OH Logging Nov | STRIKE ENERGY LIMITED |  | Ensign 962 | J.23.008569 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-15 | 2023-03-13 |  | 2023-03-15 | 2023-04-05 23:59 |  | 2023-04-05 23:59 | New Burn WL | BAhmad | 2023-02-28 09:54 | PZuliani |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1024966 | O.1024966.01 | A.1024966.01.03 | OH Logging Aug | STRIKE ENERGY LIMITED |  | Ensign 962 | J.22.110132 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2023-01-30 |  | 2023-02-01 | 2023-02-22 23:59 |  |  | New Burn WL | BAhmad | 2022-11-10 14:03 | JDukas |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1024966 | O.1024966.01 | A.1024966.01.02 | OH Logging May | STRIKE ENERGY LIMITED |  | Ensign 962 | J.22.110131 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-05-01 |  | 2022-05-03 | 2022-05-24 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:57 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1024966 | O.1024966.01 | A.1024966.01.01 | OH Logging Feb | STRIKE ENERGY LIMITED |  | Ensign 962 | J.22.110130 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-02-01 |  | 2022-02-03 | 2022-02-24 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:57 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 2 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1024963 | O.1024963.01 | A.1024963.01.04 | CH logging contingency - Jul | VERMILION OIL & GAS AUSTRALIA PTY LTD |  | Valaris 107 | J.22.110129 | RPE | ES-OH-NO | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-07-31 |  | 2022-08-15 | 2022-08-22 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:57 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 0 |  |  |  | 50 | 33.3 | 100 | 50 | 50 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1024963 | O.1024963.01 | A.1024963.01.03 | CH logging contingency - Jun | VERMILION OIL & GAS AUSTRALIA PTY LTD |  | Valaris 107 | J.22.110128 | RPE | ES-OH-NO | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-07-26 |  | 2022-07-29 | 2022-08-07 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:57 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 0 |  |  |  | 50 | 33.3 | 100 | 50 | 50 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1024963 | O.1024963.01 | A.1024963.01.02 | CH logging contingency - May | VERMILION OIL & GAS AUSTRALIA PTY LTD |  | Valaris 107 | J.22.110127 | RPE | ES-OH-NO | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-07-14 |  | 2022-07-21 | 2022-07-29 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:57 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 0 |  |  |  | 50 | 33.3 | 100 | 50 | 50 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1024963 | O.1024963.01 | A.1024963.01.01 | CH logging contingency - April | VERMILION OIL & GAS AUSTRALIA PTY LTD |  | Valaris 107 | J.22.110126 | RPE | ES-CH-NO | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-06-01 |  | 2022-06-29 | 2022-07-19 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:57 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 0 |  |  |  | 58.3 | 33.3 | 100 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1024961 | O.1024961.01 | A.1024961.01.01 | Exploration Well | WOODSIDE ENERGY LTD |  | Ocean Apex | J.22.110125 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-09-04 |  | 2022-09-08 | 2022-09-27 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:57 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 3 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1024957 | O.1024957.02 | A.1024957.02.33 | Q4-2025_SLK Barossa | SANTOS LIMITED | BR S1 1 (BS16), BR S2 2, BR N11 (BS03) | VALARIS MS-1 | J.25.156274 | RPI | PS-SLK-Rental-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-10-14 | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-12-29 23:59 | 2025-12-30 | 2025-12-29 23:59 | New Burn WL | MElsanousi | 2025-11-18 12:07 | VQuoc |  | No |  |  |  |  | Edmund Brobbey |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 100 | 100 | 75 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1024957 | O.1024957.02 | A.1024957.02.34 | Q4-2025_WL Barossa | SANTOS LIMITED | BR N11 (BS03) | VALARIS MS-1 | J.25.160820 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2025-10-08 13:00 | 2025-08-22 | 2025-10-02 | 2025-10-08 13:00 | 2026-01-05 23:59 | 2026-01-01 | 2026-01-06 12:59 | New Burn WL | MElsanousi | 2025-10-31 12:57 | INasir |  | No |  |  |  | ROE WL Mumbai | Jarrod Sedmak |  | 0 | 4 |  | L2 - Shift RO |  | 100 | 100 | 0 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1024957 | O.1024957.02 | A.1024957.02.31 | Q3-2025_WL_Barossa | SANTOS LIMITED | BR N11 (BS03) | VALARIS MS-1 | J.25.084597 | RPI | PS-WL-Ops | High | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2025-07-15 13:00 | 2025-06-01 | 2025-07-15 | 2025-07-15 13:00 | 2025-10-13 12:59 | 2025-10-14 | 2025-10-13 12:59 | New Burn WL | ymoradi2 | 2025-10-02 14:04 | MElsanousi |  | No |  |  |  | ROE WL Mumbai | Yasser Moradi |  | 0 | 4 |  | L2 - Shift RO |  | 100 | 100 | 100 | 50 | 85 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1024957 | O.1024957.02 | A.1024957.02.32 | Q3-2025_SLK_Barossa | SANTOS LIMITED | BR S1 1 (BS16), BR S2 2, BR N11 (BS03) | VALARIS MS-1 | J.25.084601 | RPI | PS-SLK-Rental-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-07-13 | 2025-06-29 | 2025-06-30 | 2025-06-30 | 2025-09-27 23:59 | 2025-09-28 | 2025-09-27 23:59 | New Burn WL | ymoradi2 | 2025-09-22 19:04 | VQuoc |  | No |  |  |  |  | Yasser Moradi |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 100 | 100 | 75 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1024957 | O.1024957.02 | A.1024957.02.30 | Q2-2025-WL_Barossa-April-May-June | SANTOS LIMITED | BR N11 (BS03) | VALARIS MS-1 | J.25.079858 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2025-04-01 13:00 | 2025-04-01 | 2025-04-01 | 2025-04-01 13:00 | 2025-06-30 12:59 | 2025-07-01 | 2025-06-30 12:59 | New Burn WL | SKhan109 | 2025-07-29 12:43 | WMaung |  | No |  |  |  | ROE WL Mumbai | Yasser Moradi |  | 17000 | 4 |  | L3 - Full RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1024957 | O.1024957.02 | A.1024957.02.26 | Q1-25_SLK | SANTOS LIMITED |  | VALARIS MS-1 | J.24.172557 | RPE | ES-CH-Ops | Medium | Unconfirmed - 10% | Design - CEC |  | Not Required | Not Required | Design Completed |  | 2024-12-31 | 2025-01-01 | 2025-01-01 | 2025-04-01 23:59 | 2025-04-02 |  | New Burn WL | ymoradi2 | 2025-07-08 09:49 | MElsanousi |  | No |  |  |  |  | Yasser Moradi |  | 0 | 0 |  | L0 - No RO |  | 66.7 | 33.3 | 0 | 25 | 37.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1024957 | O.1024957.02 | A.1024957.02.23 | Barossa_H2Q4_WL | SANTOS LIMITED | BR S2 1 | VALARIS MS-1 | J.24.149352 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Not Required | Design Completed | 2024-11-24 | 2024-10-31 | 2024-11-24 | 2024-11-24 | 2025-01-23 23:59 | 2025-01-24 | 2025-01-23 23:59 | New Burn WL | ymoradi2 | 2025-07-08 09:47 | MElsanousi |  | No |  |  |  | ROE WL Mumbai | Yasser Moradi |  | 0 | 1 |  | L3 - Full RO |  | 66.7 | 16.7 | 0 | 0 | 25 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1024957 | O.1024957.02 | A.1024957.02.28 | Q2-2025_SLK_Barossa_ | SANTOS LIMITED | BR N11 (BS03), BR N12 (BS09) | VALARIS MS-1 | J.25.059683 | RPI | PS-SLK-Rental-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-04-14 | 2025-03-31 | 2025-04-01 | 2025-04-01 | 2025-06-30 23:59 | 2025-07-01 | 2025-06-30 23:59 | New Burn WL | ymoradi2 | 2025-06-27 11:34 | MElsanousi |  | No |  |  |  |  | Yasser Moradi |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 100 | 100 | 75 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1024957 | O.1024957.02 | A.1024957.02.27 | Q1-25_WL_Barossa | SANTOS LIMITED | BR N12 (BS09), BR N11 (BS03) | VALARIS MS-1 | J.24.172561 | RPI | PS-WL-Ops | High | Confirmed | Execute - PSD |  | Design Completed | Not Required | Not Started | 2025-04-14 | 2024-12-31 | 2025-01-04 | 2025-04-10 | 2025-07-08 23:59 | 2025-04-06 | 2025-07-08 23:59 | New Burn WL | ymoradi2 | 2025-04-14 16:53 | SKhan109 |  | No |  |  |  | ROE WL Mumbai | Yasser Moradi |  | 17000 | 1 |  | L1 - Support RO |  | 83.3 | 100 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1024957 | O.1024957.02 | A.1024957.02.29 | Q2-2025_WL_Barossa | SANTOS LIMITED | BR N12 (BS09) | VALARIS MS-1 | J.25.059684 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-03-31 | 2025-03-30 | 2025-03-31 | 2025-03-31 | 2025-06-28 23:59 | 2025-06-29 | 2025-06-28 23:59 | New Burn WL | ymoradi2 | 2025-04-07 09:42 | ymoradi2 |  | No |  |  |  | ROE WL Mumbai | Yasser Moradi |  | 0 | 4 |  | L1 - Support RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1024957 | O.1024957.02 | A.1024957.02.25 | Barossa_H2Q4-SLK | SANTOS LIMITED | BR S2 1, BR S2 2, S-21, S-22 | VALARIS MS-1 | J.24.149355 | RPI | PS-SLK-Rental-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-11-24 | 2024-10-31 |  | 2024-11-15 | 2024-12-31 23:59 |  | 2024-12-31 23:59 | New Burn WL | ymoradi2 | 2024-12-13 23:45 | VQuoc |  | No |  |  |  |  | Yasser Moradi |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 100 | 100 | 75 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1024957 | O.1024957.02 | A.1024957.02.06 | Barossa Well N-12 | SANTOS LIMITED | N-12 | VALARIS MS-1 | J.23.008577 | RPI | PS-WL-Ops | High | Unconfirmed - 50% | Execute - PSD |  | In Progress | In Progress | In Progress | 2024-09-10 | 2024-08-01 |  | 2024-10-22 | 2024-10-28 23:59 |  | 2025-03-22 23:59 | New Burn WL | JDukas | 2024-10-22 10:54 | ymoradi2 |  | No |  |  |  |  | Justin Dukas |  | 0 | 6 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 6 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1024957 | O.1024957.02 | A.1024957.02.22 | Barossa+H2_Oct | SANTOS LIMITED | BR S1 1 (BS16) | VALARIS MS-1 | J.24.149351 | RPI | PS-WL-Ops | High | Confirmed | Design - CEC |  | Design Completed | Not Required | Design Completed | 2024-10-14 | 2024-10-13 |  | 2024-10-14 | 2024-10-31 23:59 |  | 2024-10-31 23:59 | New Burn WL | ymoradi2 | 2024-10-21 09:53 | AHermawan |  | No |  |  |  |  | Yasser Moradi |  | 0 | 1 |  | L0 - No RO |  | 87.5 | 33.3 | 0 | 0 | 36.3 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1024957 | O.1024957.02 | A.1024957.02.02 | Barossa Campaign | SANTOS LIMITED | S-21, BR S1 2 (BS17) | VALARIS MS-1 | J.23.008573 | RPI | PS-WL-Ops | High | Confirmed | Prepare - Mob |  | Design Completed | Design Completed | Design Completed | 2024-08-14 08:00 | 2024-07-12 |  | 2024-08-15 08:00 | 2024-08-30 07:59 |  | 2024-08-31 07:59 | New Burn WL | JDukas | 2024-10-03 11:11 | APutra7 |  | No |  |  |  | ROE WL Jakarta | Mohammad Adel Mohammad Alhashemi |  | 0 | 1 |  | L1 - Support RO |  | 75 | 41.7 | 0 | 0 | 35 |  | 15 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1024957 | O.1024957.02 | A.1024957.02.08 | Barossa PR and USIT-CBL contingency | SANTOS LIMITED | BR S2 2 | VALARIS MS-1 | J.22.110173 | RPI | PS-WL-NO | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-08-28 |  | 2022-09-01 | 2022-09-22 23:59 |  |  | New Burn WL | JDukas | 2024-10-02 10:13 | APutra7 |  | No |  |  |  |  | Justin Dukas |  | 0 | 0 |  | L0 - No RO |  | 58.3 | 33.3 | 100 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1024957 | O.1024957.02 | A.1024957.02.21 | BR-S-22 XT SLK ops | SANTOS LIMITED | S-21, BR S2 2 | VALARIS MS-1 | J.24.088565 | RPI | PS-SLK-Ops | Medium | Operationally Complete | Execute - PSD |  | Design Completed | Not Required | In Progress | 2024-05-04 12:00 | 2024-04-28 |  | 2024-05-04 12:00 | 2024-05-23 11:59 |  | 2024-05-23 11:59 | New Burn WL | JDukas | 2024-09-03 23:50 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  | L0 - No RO |  | 66.7 | 66.7 | 0 | 75 | 62.5 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1024957 | O.1024957.02 | A.1024957.02.16 | Barossa S-22 CH SLK ops | SANTOS LIMITED | BR S2 2 | VALARIS MS-1 | J.24.039037 | RPI | PS-SLK-Rental-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2024-02-01 | 2024-01-16 |  | 2024-02-01 | 2024-03-01 23:59 |  | 2024-03-01 23:59 | New Burn WL | JDukas | 2024-09-03 23:50 | FDPSystemUser |  | Yes |  |  |  |  | Justin Dukas |  | 0 | 0 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1024957 | O.1024957.02 | A.1024957.02.24 | Barossa_SLK_H2-Oct | SANTOS LIMITED |  | VALARIS MS-1 | J.24.149353 | RPI | PS-SLK-Rental-Ops | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2024-10-14 |  | 2024-10-15 | 2024-10-31 23:59 |  |  | New Burn WL | ymoradi2 | 2024-08-30 12:35 | FDPSystemUser |  | No |  |  |  |  | Mohammad Adel Mohammad Alhashemi |  | 0 | 0 |  | L0 - No RO |  | 8.3 | 0 | 0 | 0 | 2.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1024957 | O.1024957.02 | A.1024957.02.20 | Barossa S-21 well SLK ops | SANTOS LIMITED | BR S1 2 (BS17) | VALARIS MS-1 | J.24.079153 | RPI | PS-SLK-Rental-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2024-08-14 | 2024-08-08 |  | 2024-08-14 | 2024-08-27 23:59 |  | 2024-08-27 23:59 | New Burn WL | JDukas | 2024-08-29 14:38 | ymoradi2 |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 100 | 0 | 62.5 | 73.8 |  | 3 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1024957 | O.1024957.02 | A.1024957.02.05 | Barossa Well N-11 | SANTOS LIMITED | N-11 | VALARIS MS-1 | J.23.008576 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-09-10 | 2024-10-19 |  | 2024-10-22 | 2025-01-09 23:59 |  | 2025-01-09 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 6 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 1 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1024957 | O.1024957.02 | A.1024957.02.03 | Barossa Well S-12 | SANTOS LIMITED | S-12 | VALARIS MS-1 | J.23.008574 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-03-31 | 2024-05-09 |  | 2024-05-12 | 2024-07-30 23:59 |  | 2024-07-30 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 6 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 1 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1024957 | O.1024957.02 | A.1024957.02.04 | Barossa Well S-11 | SANTOS LIMITED | S-11 | VALARIS MS-1 | J.23.008575 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-06-21 | 2024-07-30 |  | 2024-08-02 | 2024-10-20 23:59 |  | 2024-10-20 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 6 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 1 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1024957 | O.1024957.02 | A.1024957.02.01 | Barossa S-22 CH well Completions Phase | SANTOS LIMITED | BR S2 2 | VALARIS MS-1 | J.22.110144 | RPI | PS-WL-Ops | High | Confirmed | Prepare - TLM/OP |  | Design Completed | Design Completed | Design Completed | 2024-01-26 | 2024-01-10 |  | 2024-01-26 | 2024-02-29 23:59 |  | 2024-02-29 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | Yes |  |  |  | ROE WL Mumbai | Justin Dukas |  | 0 | 9 |  | L1 - Support RO |  | 87.5 | 16.7 | 0 | 0 | 31.3 |  | 3 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1024957 | O.1024957.02 | A.1024957.02.10 | Barossa S-22 SLK ops | SANTOS LIMITED | BR S2 2 | VALARIS MS-1 | J.22.110179 | RPI | PS-SLK-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2023-08-26 | 2023-08-09 |  | 2023-08-26 | 2023-10-13 23:59 |  | 2023-10-13 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 0 | 1 |  | L1 - Support RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1024957 | O.1024957.02 | A.1024957.02.18 | BR-S1 2 Resolve ix | SANTOS LIMITED | BR S1 1 (BS16), BR S2 2, BR S2 1 | VALARIS MS-1 | J.24.053120 | RPI | PS-SLK-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2024-05-12 12:00 | 2024-05-01 |  | 2024-05-12 12:00 | 2024-06-03 11:59 |  | 2024-06-03 11:59 | New Burn WL | JDukas | 2024-08-12 14:41 | MElsanousi |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 48800 | 1 |  | L2 - Shift RO |  | 100 | 100 | 100 | 83.3 | 95 |  | 5 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1024957 | O.1024957.02 | A.1024957.02.19 | BR-S1 2 USIT-CBL-TTiX contingency | SANTOS LIMITED | BR S1 2 (BS17) | VALARIS MS-1 | J.24.053122 | RPI | PS-WL-Ops | High | Unconfirmed - 50% | Design - CEC |  | Design Completed | Not Required | Design Completed | 2024-05-21 | 2024-06-14 | 2024-06-15 16:00 | 2024-06-17 | 2024-07-06 23:59 | 2024-07-13 | 2024-07-06 23:59 | New Burn WL | JDukas | 2024-06-04 15:10 | PZuliani |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  | L0 - No RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 7 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1024957 | O.1024957.02 | A.1024957.02.17 | BR-S2 1A IBC-CBL Contingency | SANTOS LIMITED | BR S2 1 | VALARIS MS-1 | J.24.053065 | RPI | PS-WL-Ops | High | Unconfirmed - 50% | Design - CEC |  | Design Completed | In Progress | In Progress | 2024-01-18 | 2024-02-26 | 2024-02-27 08:00 | 2024-02-29 | 2024-05-02 23:59 | 2024-05-02 | 2024-05-02 23:59 | New Burn WL | JDukas | 2024-05-03 14:05 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 3 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1024957 | O.1024957.02 | A.1024957.02.14 | Barossa SK well 5 | SANTOS LIMITED |  | VALARIS MS-1 | J.23.008582 | RPI | PS-SLK-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-10-02 | 2024-08-31 |  | 2024-10-02 | 2024-11-19 23:59 |  | 2024-11-19 23:59 | New Burn WL | JDukas | 2023-11-02 14:36 | VOliveira5 |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 0 | 1 |  | L1 - Support RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 1 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1024957 | O.1024957.02 | A.1024957.02.15 | Barossa Well 6 | SANTOS LIMITED |  | VALARIS MS-1 | J.23.008583 | RPI | PS-SLK-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-11-26 | 2024-10-25 |  | 2024-11-26 | 2025-01-13 23:59 |  | 2025-01-13 23:59 | New Burn WL | JDukas | 2023-11-02 14:33 | VOliveira5 |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 0 | 1 |  | L1 - Support RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 1 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1024957 | O.1024957.02 | A.1024957.02.13 | Barossa SLK well 4 | SANTOS LIMITED |  | VALARIS MS-1 | J.23.008581 | RPI | PS-SLK-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-04-09 | 2024-03-08 |  | 2024-04-09 | 2024-05-27 23:59 |  | 2024-05-27 23:59 | New Burn WL | JDukas | 2023-05-17 17:12 | VOliveira5 |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 0 | 1 |  | L1 - Support RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1024957 | O.1024957.02 | A.1024957.02.12 | Barossa SLK well 3 | SANTOS LIMITED |  | VALARIS MS-1 | J.23.008580 | RPI | PS-SLK-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-01-10 | 2023-12-09 |  | 2024-01-10 | 2024-02-27 23:59 |  | 2024-02-27 23:59 | New Burn WL | JDukas | 2023-05-17 17:12 | VOliveira5 |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 0 | 1 |  | L1 - Support RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1024957 | O.1024957.02 | A.1024957.02.11 | Barossa SLK well2 | SANTOS LIMITED |  | VALARIS MS-1 | J.23.008579 | RPI | PS-SLK-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-11-14 | 2023-10-13 |  | 2023-11-14 | 2024-01-01 23:59 |  | 2024-01-01 23:59 | New Burn WL | JDukas | 2023-05-17 17:12 | VOliveira5 |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 0 | 1 |  | L1 - Support RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1024957 | O.1024957.02 | A.1024957.02.09 | Barrosa Reimbursables - Rentals | SANTOS LIMITED |  | VALARIS MS-1 | J.22.110174 | RPI | PS-WL-NO | Medium | Confirmed | Design - PSD |  | Not Started | Not Started | In Progress |  | 2022-09-01 |  | 2022-09-01 | 2023-03-31 23:59 |  |  | New Burn WL | VOliveira5 | 2023-03-28 12:10 | JDukas |  | No |  |  |  |  | Justin Dukas |  | 0 | 0 |  | L0 - No RO |  | 33.3 | 33.3 | 100 | 50 | 45 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1024957 | O.1024957.02 | A.1024957.02.07 | Barossa S-22 PR | SANTOS LIMITED | BR-S2 2 (BS25) | VALARIS MS-1 | J.22.110169 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2022-07-18 |  | 2022-07-22 | 2022-08-30 23:59 |  |  | New Burn WL | JDukas | 2022-10-03 10:02 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 2138 | 0 |  |  |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1024957 | O.1024957.01 | A.1024957.01.02 | Barossa | SANTOS LIMITED |  | VALARIS MS-1 | J.22.110119 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-08-29 |  | 2022-09-01 | 2022-09-22 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:56 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 2 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1024957 | O.1024957.01 | A.1024957.01.01 | Barossa | SANTOS LIMITED |  | VALARIS MS-1 | J.22.110118 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-06-02 |  | 2022-06-03 | 2022-06-24 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:56 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1024869 | O.1024869.02 | A.1024869.02.03 | Tri-Star | TRI-STAR OPCO LLC | FAIRFIELDS 1X | SWS-2 | J.24.142242 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2025-02-08 | 2025-02-07 |  | 2025-02-08 | 2025-02-12 23:59 |  | 2025-03-03 23:59 | Roma WL | KKeese | 2024-11-25 10:42 | JEsmeralda |  | No |  |  |  |  | Irwan Wongso |  | 0 | 5 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 4 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1024869 | O.1024869.02 | A.1024869.02.02 | Tri-Star | TRI-STAR OPCO LLC | FAIRFIELDS 1X | SWS-2 | J.24.096882 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-11-01 | 2024-10-31 |  | 2024-11-01 | 2024-12-01 23:59 |  | 2024-12-01 23:59 | Roma WL | KKeese | 2024-08-16 15:23 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 5 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1024869 | O.1024869.02 | A.1024869.02.01 | Fairfields 1X PNA | TRI-STAR OPCO LLC | FAIRFIELDS 1X | SWS-2 | J.24.087497 | RPI | PS-WL-Ops | InComplete | Confirmed | Prepare - Mob |  | Design Completed | Design Completed | In Progress | 2024-04-25 | 2024-04-24 |  | 2024-04-25 | 2024-04-26 23:59 |  | 2024-05-25 23:59 | Roma WL | JEsmeralda | 2024-08-08 13:52 | SNiang |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 5 |  | L2 - Shift RO |  | 66.7 | 66.7 | 0 | 25 | 47.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1024869 | O.1024869.01 | A.1024869.01.02 | Post Frac | TRI-STAR OPCO LLC | FAIRFIELDS 2 | Rigless Australia - 1 | J.22.110326 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-04-16 23:00 |  | 2022-04-17 23:00 | 2022-05-01 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 44346.98 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1024869 | O.1024869.01 | A.1024869.01.01 | Rigless_Sonic | TRI-STAR OPCO LLC | FAIRFIELDS 2 | Rigless Australia - 1 | J.22.110297 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-03-21 |  | 2022-03-24 12:00 | 2022-03-27 11:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 49155.3 | 2 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1024845 | O.1024845.02 | A.1024845.02.05 | Santos CH PNA May-Jun 2025 | SANTOS LIMITED | FAIRVIEW 61, FAIRVIEW 83 OB3, TARRAWONGA 3, FV11-02-21, FV08-36-3 | WILD DESERT RIG 20 | J.25.087855 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2025-03-14 01:00 | 2025-04-25 | 2025-04-29 16:00 | 2025-05-01 | 2025-06-30 23:59 | 2025-07-01 | 2025-07-01 00:59 | Roma WL | JEsmeralda | 2025-07-02 15:23 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 25352.18 | 4 |  | L2 - Shift RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1024845 | O.1024845.02 | A.1024845.02.04 | Santos CH PNA Mar-Apr 2025 | SANTOS LIMITED | FAIRVIEW 61, FAIRVIEW 29, FAIRVIEW 80 | WILD DESERT RIG 20 | J.25.008274 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-03-05 | 2025-04-22 | 2025-04-21 13:00 | 2025-04-22 | 2025-05-01 | 2025-05-20 | 2025-05-19 23:59 | Roma WL | KKeese | 2025-05-02 14:13 | SAli112 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 25352.18 | 3 |  | L2 - Shift RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1024845 | O.1024845.02 | A.1024845.02.03 | Santos CH Dedicated Feb 2025 | SANTOS LIMITED | SCOTIA 37, MOUNT KINGSLEY 48 | WILD DESERT RIG 20 | J.25.008273 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2025-02-02 | 2025-02-01 |  | 2025-02-01 | 2025-02-28 23:59 |  | 2025-02-28 23:59 | Roma WL | KKeese | 2025-02-27 18:10 | AJaved15 |  | No |  |  |  |  | Irwan Wongso |  | 0 | 1 |  | L0 - No RO |  | 100 | 100 | 0 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1024845 | O.1024845.02 | A.1024845.02.02 | Santos CH Dedicated Jan 2025 | SANTOS LIMITED | OKSGWBA 01, OKSGWP 07, DALDOWIE 22 | WILD DESERT RIG 20 | J.24.141757 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2025-01-22 | 2025-01-01 |  | 2025-01-01 | 2025-01-31 23:59 |  | 2025-01-31 23:59 | Roma WL | KKeese | 2025-02-03 00:11 | SAli112 |  | No |  |  |  |  | Irwan Wongso |  | 0 | 1 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1024845 | O.1024845.02 | A.1024845.02.01 | Jun CH Dedicated Santos | SANTOS LIMITED |  | WILD DESERT RIG 20 | J.27.000026 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2027-06-01 | 2027-05-30 |  | 2027-06-01 | 2027-06-25 22:59 |  | 2027-07-01 22:59 | Roma WL | KKeese | 2024-08-15 13:13 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 10 |  | L0 - No RO |  | 41.7 | 33.3 | 0 | 25 | 30 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.35 | Santos Dedicated CH Dec 24 | SANTOS LIMITED | FV18-84-1, GLEN EVIS 14, HARDENLEY 32, HARDENLEY 31, OKSGWBA 01, FV18-84-3, GLEN EVIS 12, OKSGWP01, GLEN EVIS 10 | SAVANNA 68 | J.24.096868 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | Design Completed | In Progress | In Progress | 2024-12-01 | 2024-11-29 |  | 2024-12-01 | 2024-12-25 22:59 |  | 2024-12-31 22:59 | Roma WL | KKeese | 2024-12-10 19:33 | AJaved15 |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 2 |  | L0 - No RO |  | 62.5 | 25 | 0 | 50 | 41.3 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.34 | Nov CH Dedicated | SANTOS LIMITED |  | SAVANNA 68 | J.24.096867 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-11-01 | 2024-10-30 |  | 2024-11-01 | 2024-11-25 22:59 |  | 2024-12-01 22:59 | Roma WL | KKeese | 2024-11-09 11:07 | JEsmeralda |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 10 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.32 | Sep CH Dedicated | SANTOS LIMITED |  | SAVANNA 68 | J.24.096865 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-09-01 | 2024-08-30 |  | 2024-09-01 | 2024-09-25 22:59 |  | 2024-10-01 22:59 | Roma WL | KKeese | 2024-10-22 10:36 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 10 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.29 | Jun CH Dedicated Santos | SANTOS LIMITED |  | SAVANNA 68 | J.24.050649 | RPI | PS-WL-NO | Low | Operationally Complete | Execute - PSD |  | In Progress | In Progress | In Progress | 2024-06-01 | 2024-05-30 |  | 2024-06-01 | 2024-06-25 22:59 |  | 2024-07-01 22:59 | Roma WL | KKeese | 2024-08-16 09:58 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 149447.69 | 10 |  | L0 - No RO |  | 66.7 | 33.3 | 100 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.31 | Aug CH Dedicated Santos | SANTOS LIMITED |  | SAVANNA 68 | J.24.050651 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-08-01 | 2024-07-30 |  | 2024-08-01 | 2024-08-25 22:59 |  | 2024-08-31 22:59 | Roma WL | KKeese | 2024-07-24 16:32 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 10 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.30 | Jul CH Dedicated Santos | SANTOS LIMITED |  | SAVANNA 68 | J.24.050650 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-07-01 | 2024-06-29 |  | 2024-07-01 | 2024-07-25 22:59 |  | 2024-07-31 22:59 | Roma WL | KKeese | 2024-07-24 07:41 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 10 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.33 | Oct CH Dedicated | SANTOS LIMITED |  | SAVANNA 68 | J.24.096866 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2024-10-01 | 2024-09-29 | 2024-09-30 | 2024-10-01 | 2024-10-25 22:59 | 2024-10-29 | 2024-10-31 23:59 | Roma WL | KKeese | 2024-05-10 08:58 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 10 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.28 | May CH Dedicated Santos | SANTOS LIMITED |  | SAVANNA 68 | J.24.050648 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2024-05-01 | 2024-04-29 | 2024-04-30 | 2024-05-01 | 2024-05-25 22:59 | 2024-05-28 23:00 | 2024-05-31 22:59 | Roma WL | KKeese | 2024-04-24 09:50 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 149447.69 | 10 |  | L0 - No RO |  | 50 | 0 | 0 | 25 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.25 | CH Dedicated Feb 2024 | SANTOS LIMITED |  | SAVANNA 68 | J.24.021429 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-02-01 | 2024-01-30 |  | 2024-02-01 | 2024-02-25 22:59 |  | 2024-03-02 22:59 | Roma WL | KKeese | 2024-04-02 14:59 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 10 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.27 | April CH Dedicated Santos | SANTOS LIMITED |  | SAVANNA 68 | J.24.050647 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2024-04-01 | 2024-03-30 |  | 2024-04-01 | 2024-04-25 22:59 |  | 2024-05-01 21:59 | Roma WL | KKeese | 2024-02-14 17:42 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 129954.52 | 10 |  | L0 - No RO |  | 50 | 0 | 0 | 25 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.24 | CH Dedicated Jan 2024 | SANTOS LIMITED |  | SAVANNA 68 | J.23.160228 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2024-01-01 | 2023-12-30 |  | 2024-01-01 | 2024-01-31 22:59 |  | 2024-01-31 22:59 | Roma WL | KKeese | 2023-12-30 08:16 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 144626.8 | 10 |  | L0 - No RO |  | 50 | 0 | 0 | 25 | 22.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.23 | Dedicated December | SANTOS LIMITED |  | SAVANNA 68 | J.23.176719 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2023-12-01 | 2023-11-29 |  | 2023-12-01 | 2023-12-25 22:59 |  | 2023-12-31 22:59 | Roma WL | KKeese | 2023-12-22 11:33 | FDPSystemUser |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 10 |  | L0 - No RO |  | 50 | 0 | 0 | 25 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.26 | CH Dedicated Mar 2024 | SANTOS LIMITED |  | SAVANNA 68 | J.24.021430 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2024-03-01 | 2024-02-28 | 2024-02-29 01:00 | 2024-03-01 | 2024-03-25 22:59 | 2024-03-29 | 2024-03-31 22:59 | Roma WL | KKeese | 2023-10-29 14:29 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 149447.69 | 10 |  | L0 - No RO |  | 50 | 0 | 0 | 25 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.21 | Dedicated October | SANTOS LIMITED |  | SAVANNA 68 | J.23.085716 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2023-10-01 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2023-10-25 22:59 | 2023-10-29 | 2023-10-31 23:59 | Roma WL | KKeese | 2023-09-26 12:14 | KKeese |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 149447.69 | 10 |  | L0 - No RO |  | 50 | 0 | 0 | 25 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.18 | Dedicated July | SANTOS LIMITED |  | SAVANNA 68 | J.23.084125 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2023-07-01 | 2023-06-29 | 2023-06-30 | 2023-07-01 | 2023-07-25 22:59 | 2023-07-28 23:00 | 2023-07-31 22:59 | Roma WL | KKeese | 2023-06-30 16:59 | KKeese |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 10 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.17 | Dedicated June | SANTOS LIMITED |  | SAVANNA 68 | J.23.041616 | RPI | PS-WL-NO | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2023-06-01 | 2023-05-30 |  | 2023-06-01 | 2023-06-25 22:59 |  | 2023-07-01 22:59 | Roma WL | MRony2 | 2023-06-25 15:19 | KKeese |  | No |  |  |  |  | Jon Lawrie |  | 149447.69 | 10 |  | L0 - No RO |  | 66.7 | 33.3 | 100 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.16 | Dedicated CH May | SANTOS LIMITED |  | SAVANNA 68 | J.23.041615 | RPI | PS-WL-NO | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2023-05-01 | 2023-04-29 |  | 2023-05-01 | 2023-05-25 22:59 |  | 2023-05-31 22:59 | Roma WL | MRony2 | 2023-05-24 15:15 | KKeese |  | No |  |  |  |  | Jon Lawrie |  | 149447.69 | 10 |  | L0 - No RO |  | 66.7 | 33.3 | 100 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.19 | Dedicated August | SANTOS LIMITED |  | SAVANNA 68 | J.23.084126 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2023-08-01 | 2023-07-30 |  | 2023-08-01 | 2023-08-25 22:59 |  | 2023-08-31 22:59 | Roma WL | KKeese | 2023-05-18 12:54 | KKeese |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 149447.69 | 10 |  | L0 - No RO |  | 50 | 0 | 0 | 25 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.20 | Dedicated September | SANTOS LIMITED |  | SAVANNA 68 | J.23.084127 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2023-09-01 | 2023-08-30 |  | 2023-09-01 | 2023-09-25 22:59 |  | 2023-10-01 23:59 | Roma WL | KKeese | 2023-05-18 12:51 | KKeese |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 149447.69 | 10 |  | L0 - No RO |  | 50 | 0 | 0 | 25 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.22 | Dedicated November | SANTOS LIMITED |  | SAVANNA 68 | J.23.085717 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2023-11-01 | 2023-10-30 |  | 2023-11-01 | 2023-11-25 22:59 |  | 2023-12-01 22:59 | Roma WL | KKeese | 2023-05-18 11:52 | KKeese |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 149447.69 | 10 |  | L0 - No RO |  | 50 | 0 | 0 | 25 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.14 | Dedicated March | SANTOS LIMITED |  | SAVANNA 68 | J.23.011904 | RPI | PS-WL-NO | Low | Confirmed | Design - CEC |  | Design Completed | In Progress | In Progress | 2023-03-01 | 2023-02-27 |  | 2023-03-01 | 2023-03-25 22:59 |  | 2023-03-31 22:59 | Roma WL | MRony2 | 2023-04-04 16:35 | MRony2 |  | No |  |  |  |  | Jon Lawrie |  | 172695.32 | 10 |  | L0 - No RO |  | 75 | 50 | 100 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.15 | CH Dedicated # 1 | SANTOS LIMITED |  | SAVANNA 68 | J.23.041614 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2023-04-01 | 2023-03-30 |  | 2023-04-01 | 2023-04-25 22:59 |  | 2023-05-01 21:59 | Roma WL | MRony2 | 2023-02-26 22:08 | MRony2 |  | No |  |  |  |  | Jon Lawrie |  | 172695.32 | 10 |  | L0 - No RO |  | 50 | 0 | 0 | 25 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.13 | Dedicated Feb | SANTOS LIMITED |  | SAVANNA 68 | J.23.011903 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2023-02-01 | 2023-01-30 |  | 2023-02-01 | 2023-02-25 22:59 |  | 2023-03-03 22:59 | Roma WL | MRony2 | 2023-02-16 16:55 | MRony2 |  | No |  |  |  |  | Jon Lawrie |  | 149447.69 | 10 |  | L0 - No RO |  | 50 | 0 | 0 | 25 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.12 | Dedicated Jan | SANTOS LIMITED |  | SAVANNA 68 | J.22.121721 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2023-01-01 | 2022-12-30 |  | 2023-01-01 | 2023-01-28 22:59 |  | 2023-02-03 22:59 | Roma WL | MRony2 | 2023-01-04 23:38 | MRony2 |  | No |  |  |  |  | Jon Lawrie |  | 178078.84 | 10 |  | L0 - No RO |  | 50 | 0 | 0 | 25 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.11 | Dedicated truck Dec | SANTOS LIMITED |  | SAVANNA 68 | J.22.110356 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-12-01 | 2022-11-29 |  | 2022-12-01 | 2022-12-25 22:59 |  | 2022-12-31 23:59 | Roma WL | MRony2 | 2022-12-30 09:38 | MRony2 |  | No |  |  |  |  | Jon Lawrie |  | 0 | 10 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.10 | Dedicated Truck Nov | SANTOS LIMITED |  | SAVANNA 68 | J.22.110372 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-11-01 | 2022-10-30 |  | 2022-11-01 | 2022-11-25 22:59 |  | 2022-12-01 23:59 | Roma WL | MRony2 | 2022-11-23 21:49 | MRony2 |  | No |  |  |  |  | Jon Lawrie |  | 0 | 10 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.09 | Dedicated truck Oct | SANTOS LIMITED |  | SAVANNA 68 | J.22.110352 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-09-29 |  | 2022-10-01 | 2022-10-25 22:59 |  |  | Roma WL | MRony2 | 2022-10-19 15:53 | MRony2 |  | No |  |  |  |  | Jon Lawrie |  | 0 | 10 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.08 | Dedicated truck _ Sep | SANTOS LIMITED |  | SAVANNA 68 | J.22.110354 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-08-30 |  | 2022-09-01 | 2022-09-25 22:59 |  |  | Roma WL | MRony2 | 2022-10-18 14:42 | MRony2 |  | No |  |  |  |  | Jon Lawrie |  | 0 | 10 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.07 | Rental Aug | SANTOS LIMITED |  | SAVANNA 68 | J.22.110358 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-07-30 |  | 2022-08-01 | 2022-08-25 22:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 10 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.06 | Dedicated truck July | SANTOS LIMITED |  | SAVANNA 68 | J.22.110355 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-06-29 |  | 2022-07-01 | 2022-07-25 22:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 10 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.04 | Rental May | SANTOS LIMITED |  | SAVANNA 68 | J.22.110344 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress |  | 2022-04-24 |  | 2022-05-05 | 2022-05-25 22:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:16 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 10 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.05 | Rental June | SANTOS LIMITED |  | SAVANNA 68 | J.22.110324 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress |  | 2022-05-24 |  | 2022-05-26 | 2022-06-22 22:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 10 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.02 | Stand by _ Feb | SANTOS LIMITED |  | SAVANNA 68 | J.22.110296 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-02-24 |  | 2022-03-16 | 2022-03-25 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 10 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.03 | Rental April | SANTOS LIMITED |  | SAVANNA 68 | J.22.110292 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress |  | 2022-04-01 |  | 2022-04-05 | 2022-04-25 22:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 10 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1024845 | O.1024845.01 | A.1024845.01.01 | Unit and crew rental | SANTOS LIMITED |  | SAVANNA 68 | J.22.110291 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-02-10 |  | 2022-02-15 | 2022-02-25 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 10 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1024839 | O.1024839.17 | A.1024839.17.03 | Santos OH Dedicated Dec 2026 | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.26.022234 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-10-31 23:00 | 2026-11-25 | 2026-11-26 01:00 | 2026-11-26 | 2026-12-25 23:59 | 2026-12-26 01:00 | 2026-12-26 23:59 | Roma WL | CKok3 | 2025-11-26 16:35 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.17 | A.1024839.17.02 | Santos OH Dedicated Nov 2026 | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.26.022233 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-09-30 22:00 | 2026-10-25 | 2026-10-26 01:00 | 2026-10-26 | 2026-11-24 23:59 | 2026-11-25 01:00 | 2026-11-25 23:59 | Roma WL | CKok3 | 2025-11-26 16:34 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.17 | A.1024839.17.01 | Santos OH Dedicated Oct 2026 | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.26.022232 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-08-31 23:00 | 2026-09-25 | 2026-09-26 | 2026-09-26 | 2026-10-25 23:59 | 2026-10-26 01:00 | 2026-10-27 00:59 | Roma WL | CKok3 | 2025-11-26 16:34 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.16 | A.1024839.16.03 | Santos OH Dedicated Sep 2026 | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.26.022231 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-07-31 23:00 | 2026-08-25 | 2026-08-26 | 2026-08-26 | 2026-09-24 23:59 | 2026-09-25 | 2026-09-25 23:59 | Roma WL | CKok3 | 2025-11-26 16:33 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.16 | A.1024839.16.02 | Santos OH Dedicated Aug 2026 | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.26.022230 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-06-30 23:00 | 2026-07-25 | 2026-07-26 | 2026-07-26 | 2026-08-24 23:59 | 2026-08-25 | 2026-08-25 23:59 | Roma WL | CKok3 | 2025-11-26 16:33 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.16 | A.1024839.16.01 | Santos OH Dedicated Jul 2026 | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.26.022229 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-05-31 23:00 | 2026-06-25 | 2026-06-26 | 2026-06-26 | 2026-07-25 23:59 | 2026-07-26 | 2026-07-26 23:59 | Roma WL | CKok3 | 2025-11-26 16:32 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.15 | A.1024839.15.03 | Santos OH Dedicated June 2026 | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.26.022228 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-04-30 23:00 | 2026-05-25 | 2026-05-26 | 2026-05-26 | 2026-06-24 23:59 | 2026-06-25 | 2026-06-25 23:59 | Roma WL | CKok3 | 2025-11-26 16:32 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.15 | A.1024839.15.02 | Santos OH Dedicated May 2026 | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.26.022227 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-04-01 | 2026-04-25 | 2026-04-26 | 2026-04-26 | 2026-05-25 23:59 | 2026-05-26 | 2026-05-26 23:59 | Roma WL | CKok3 | 2025-11-26 16:31 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.15 | A.1024839.15.01 | Santos OH Dedicated Apr 2026 | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.26.022226 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-02-28 23:00 | 2026-03-25 | 2026-03-26 01:00 | 2026-03-26 | 2026-04-24 23:59 | 2026-04-25 | 2026-04-25 22:59 | Roma WL | CKok3 | 2025-11-26 16:30 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.14 | A.1024839.14.03 | Santos OH Dedicated Mar 2026 | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.26.022225 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-01-31 23:00 | 2026-02-25 | 2026-02-26 01:00 | 2026-02-26 | 2026-03-27 23:59 | 2026-03-28 01:00 | 2026-03-28 23:59 | Roma WL | CKok3 | 2025-11-26 16:30 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.14 | A.1024839.14.02 | Santos OH Dedicated Feb 2026 | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.26.022224 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2025-12-31 23:00 | 2026-01-25 | 2026-01-26 01:00 | 2026-01-26 | 2026-02-24 23:59 | 2026-02-25 01:00 | 2026-02-25 23:59 | Roma WL | CKok3 | 2025-11-26 16:29 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.14 | A.1024839.14.01 | Santos OH Dedicated Jan 2026 | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.25.181386 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2025-11-30 23:00 | 2025-12-25 | 2025-12-26 01:00 | 2025-12-26 | 2026-01-24 23:59 | 2026-01-25 01:00 | 2026-01-25 23:59 | Roma WL | CKok3 | 2025-11-26 16:28 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.13 | A.1024839.13.02 | Santos OH Dedicated Nov 2025 | SANTOS LIMITED | RM27-29-1, RM27-35-1, RM27-25-1, RM27-22-1, RM23-57-1, RM23-64-1, FV08-31-1, FV08-31-2, RM23-48-1, RM23-53-1, RM22-62-1, RM22-66-1 | SAVANNA 186 | J.25.101991 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2025-09-30 22:00 | 2025-10-25 | 2025-10-26 | 2025-10-26 | 2025-11-30 23:59 | 2025-12-01 01:00 | 2025-12-01 23:59 | Roma WL | CKok3 | 2025-11-28 12:43 | ysaeedabadian |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L3 - Full RO |  | 91.7 | 66.7 | 100 | 83.3 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.13 | A.1024839.13.03 | Santos OH Dedicated Dec 2025 | SANTOS LIMITED |  | SAVANNA 186 | J.25.101992 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | Design Completed | 2025-10-31 23:00 | 2025-11-25 | 2025-11-26 01:00 | 2025-11-26 | 2025-12-25 23:59 | 2025-12-26 01:00 | 2025-12-26 23:59 | Roma WL | CKok3 | 2025-11-28 09:46 | CClark9 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 25 | 60 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.13 | A.1024839.13.01 | Santos OH Dedicated Oct 2025 | SANTOS LIMITED | RM22-48-1, RM22-56-1, FV08-30-1, RM23-65-1, RM23-22-1, RM27-35-1, RM23-58-1, RM27-29-1, RM27-25-1, FV18-178-1 | SAVANNA 186 | J.25.101990 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2025-08-31 23:00 | 2025-09-25 | 2025-09-26 | 2025-09-26 | 2025-10-30 23:59 | 2025-11-05 | 2025-11-01 00:59 | Roma WL | CKok3 | 2025-10-30 11:36 | ysaeedabadian |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 4 |  | L3 - Full RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.12 | A.1024839.12.03 | Santos OH Dedicated Sep 2025 | SANTOS LIMITED | RM22-65-1, RM22-103-1, RM22-68-1, RM23-55-1, RM23-59-1, RM14-62-1, FV13-113-1, RM23-63-1, RM23-68-1, RM23-61-1, RM23-67-1, FV17-92-1, RM23-69-1, RM22-48-1 | SAVANNA DRILLING #408 | J.25.101989 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2025-07-28 23:00 | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-09-30 23:59 | 2025-10-01 | 2025-10-01 23:59 | Roma WL | CKok3 | 2025-10-02 00:12 | NT2 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 4 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.12 | A.1024839.12.02 | Santos OH Dedicated Aug 2025 | SANTOS LIMITED | RM13-106-1, RM13-103-1, RM13-107-1, FV12-128-1, RM13-102-1, FV12-127-1, RM27-39-1, FV11-112-1 | SAVANNA DRILLING #408 | J.25.101988 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-04-01 | 2025-07-25 | 2025-07-26 | 2025-07-26 | 2025-08-24 23:59 | 2025-08-25 | 2025-08-25 23:59 | Roma WL | CKok3 | 2025-08-22 12:22 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 4 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.12 | A.1024839.12.01 | Santos OH Dedicated July 2025 | SANTOS LIMITED | RM22-40-1, RM22-80-1, RM22-70-1, RM22-41-1, RM13-101-1, RM22-42-1, RM22-71-1, RM13-105-1, RM13-109-1, RM13-104-1, RM17-46-1, RM17-49-1, RM13-106-1 | SAVANNA DRILLING #408 | J.25.101987 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2025-06-02 23:00 | 2025-06-25 | 2025-06-28 | 2025-06-28 | 2025-07-27 23:59 | 2025-07-28 | 2025-07-28 23:59 | Roma WL | CKok3 | 2025-07-31 02:28 | handoko |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L3 - Full RO |  | 91.7 | 83.3 | 100 | 83.3 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.11 | A.1024839.11.01 | Santos Dedicated OH Jun 2025 | SANTOS LIMITED | RM13-108-1, RM27-18-1, RM22-69-1, RM21-31-1, RM21-22-1, RM22-76-1, FV13-108-1, FV08-35-2, FV10-06-21, RM22-40-1, RM22-44-1, RM22-38-1 | SAVANNA DRILLING #408 | J.25.088815 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2024-08-22 05:00 | 2025-05-28 | 2025-05-27 19:00 | 2025-05-28 06:00 | 2025-06-30 06:00 | 2025-07-06 | 2025-07-03 05:59 | Roma WL | JEsmeralda | 2025-06-28 11:39 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.10 | A.1024839.10.07 | Santos Dedicated OH May 2025 | SANTOS LIMITED | RM07-129-1, RM08-106-1, RM01-53-1, RM09-86-1, FV13-96-1, RM68-139-1, RM23-30-1, RM27-43-1 | SAVANNA DRILLING #408 | J.25.058961 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2025-04-03 | 2025-04-27 | 2025-04-28 | 2025-04-28 | 2025-05-27 23:59 | 2025-05-28 | 2025-05-28 23:59 | Roma WL | JEsmeralda | 2025-06-09 15:17 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 100 | 87.5 | 86.3 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.10 | A.1024839.10.06 | Santos Dedicated OH Apr 2025 | SANTOS LIMITED | RM09-85-1, RM09-84-1, RM90-60-1, RM96-60-1, RM96-71-1, RM96-70-1 | SAVANNA DRILLING #408 | J.25.058960 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-04-01 | 2025-04-01 | 2025-04-01 | 2025-04-01 | 2025-04-30 23:59 | 2025-05-01 | 2025-04-30 23:59 | Roma WL | JEsmeralda | 2025-04-28 08:51 | NSchwenke |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.10 | A.1024839.10.08 | Santos Dedicated OH Jun 2025 | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.25.058963 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | Not Started | 2025-06-01 | 2025-06-01 |  | 2025-06-01 | 2025-06-30 23:59 |  | 2025-07-01 23:59 | Roma WL | JEsmeralda | 2025-04-26 09:22 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 16.7 | 33.3 | 0 | 25 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.10 | A.1024839.10.04 | Santos Dedicated OH Mar 2025 | SANTOS LIMITED | RM40-65-1, RM40-54-1, FV10-47-21, FV13-95-2, RM40-44-1, RM40-43-1, RM40-42-1, RM50-160-1, RM49-174-1, FV 08-24-1 | SAVANNA DRILLING #408 | J.25.008277 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-02-28 23:00 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-31 23:59 | 2025-04-01 | 2025-03-31 23:59 | Roma WL | KKeese | 2025-04-15 13:25 | ajain13 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 11077.32 | 2 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.10 | A.1024839.10.02 | Santos Dedicated OH Jan 2025 | SANTOS LIMITED | KELSALL 39, THE ROCK 52, HARDENLEY 36 | SAVANNA DRILLING #408 | J.24.141758 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-01-01 | 2025-01-01 |  | 2025-01-01 | 2025-01-31 23:59 |  | 2025-01-31 23:59 | Roma WL | KKeese | 2025-03-12 00:11 | ysaeedabadian |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 11077.32 | 1 |  | L3 - Full RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.10 | A.1024839.10.03 | Santos Dedicated OH Feb 2025 | SANTOS LIMITED | BRUMBY WEST 1, FV11-109-21, RM40-75-1, RM40-55-1, FV08-23-1 | SAVANNA DRILLING #408 | J.25.008276 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2025-02-01 | 2025-02-01 |  | 2025-02-01 | 2025-03-01 23:59 |  | 2025-03-01 23:59 | Roma WL | KKeese | 2025-03-05 11:14 | NSchwenke |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 18096.82 | 1 |  | L3 - Full RO |  | 83.3 | 100 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.10 | A.1024839.10.05 | Santos Dedicated OH QC Dec 24 | SANTOS LIMITED | RM40-63-1, RM40-64-1, RM40-66-1, RM40-74-1, HARDENLEY 42, HARDENLEY 29 | SAVANNA DRILLING #408 | J.24.171850 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-11-13 | 2024-11-01 |  | 2024-11-27 | 2025-01-01 23:59 |  | 2024-11-26 00:59 | Roma WL | CKok3 | 2024-12-26 15:26 | BLima7 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 83.3 | 77.5 |  | 2 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.10 | A.1024839.10.01 | Jun OH Dedicated Santos | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.25.008275 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-10-12 23:00 | 2025-09-12 23:00 |  | 2025-09-12 23:00 | 2025-10-10 10:00 |  | 2025-10-11 23:00 | Roma WL | KKeese | 2024-11-16 13:17 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 33.3 | 0 | 25 | 30 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.09 | A.1024839.09.03 | Dedicated 408_QC_Aug24 | SANTOS LIMITED | RM40-90-1, RM40-101-1, RM40-103-1, RM40-94-1, RM40-105-1, RM40-85-1, RM40-84-1, RM40-61-1, RM40-71-1, RM40-23-1, RM40-24-1, RM40-26-1, RM40-37-1, RM40-36-1, RM40-47-1, RM40-48-1, RM40-59-1, RM40-50-1, RM40-51-1, RM40-38-1, RM40-25-1, RM40-62-1, RM40-52-1, RM40-82-1, RM40-93-1, RM40-106-1, RM40-124-1, RM40-115-1, RM40-76-1 | SAVANNA DRILLING #408 | J.24.131348 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-03-28 23:00 | 2024-07-24 |  | 2024-07-25 | 2024-08-25 23:59 |  | 2024-08-25 23:59 | Roma WL | JEsmeralda | 2024-12-12 17:15 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 100 | 0 | 87.5 | 81.3 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.09 | A.1024839.09.06 | Dedicated 408_QC_Nov24 | SANTOS LIMITED | HARDENLEY-13, HARDENLEY 33, HARDENLEY 40, HARDENLEY 44, GLEN EVIS 13, RM40-73-1 | SAVANNA DRILLING #408 | J.24.171678 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-11-13 | 2024-10-25 |  | 2024-10-25 | 2024-11-26 00:59 |  | 2024-11-26 00:59 | Roma WL | JEsmeralda | 2024-12-07 09:56 | JCampos31 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L3 - Full RO |  | 100 | 83.3 | 100 | 58.3 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.09 | A.1024839.09.05 | Dedicated 408_QC_Oct24 | SANTOS LIMITED | HARDENLEY-13, HARDENLEY 33, HARDENLEY 40, HARDENLEY 44, GLEN EVIS 13 | SAVANNA DRILLING #408 | J.24.159632 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2024-09-30 | 2024-09-25 |  | 2024-09-25 | 2024-10-27 00:59 |  | 2024-10-27 00:59 | Roma WL | JEsmeralda | 2024-10-31 14:40 | NSchwenke |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 100 | 100 | 0 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.09 | A.1024839.09.04 | Dedicated 408_QC_Sep24 | SANTOS LIMITED | RM40-90-1, RM40-101-1, RM40-103-1, RM40-94-1, RM40-105-1, RM40-85-1, RM40-84-1, RM40-61-1, RM40-71-1, RM40-23-1, RM40-24-1, RM40-26-1, RM40-37-1, RM40-36-1, RM40-47-1, RM40-48-1, RM40-59-1, RM40-50-1, RM40-51-1, RM40-38-1, RM40-25-1, RM40-62-1, RM40-52-1, RM40-82-1, RM40-93-1, RM40-106-1, RM40-124-1, RM40-115-1, RM40-76-1, HARDENLEY 4 | SAVANNA DRILLING #408 | J.24.143477 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-05-04 10:00 | 2024-08-23 |  | 2024-08-23 | 2024-09-23 23:59 |  | 2024-09-23 23:59 | Roma WL | JEsmeralda | 2024-09-22 13:51 | AKavooris |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 91.7 | 83.3 | 100 | 100 | 92.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.09 | A.1024839.09.02 | Dedicated 408_QC_Jul24 | SANTOS LIMITED | RM40-90-1, RM40-101-1, RM40-103-1, RM40-94-1, RM40-105-1, RM40-85-1, RM40-84-1, RM40-61-1, RM40-71-1, RM40-23-1, RM40-24-1, RM40-26-1, RM40-37-1, RM40-47-1, RM40-48-1, RM40-35-1, RM40-51-1, RM40-50-1, RM40-59-1, RM40-36-1 | SAVANNA DRILLING #408 | J.24.119041 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-02-28 23:00 | 2024-06-26 |  | 2024-06-27 | 2024-07-28 23:59 |  | 2024-07-28 23:59 | Roma WL | JEsmeralda | 2024-08-08 01:31 | SNiang |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 8 |  | L1 - Support RO |  | 100 | 83.3 | 0 | 100 | 85 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.09 | A.1024839.09.01 | Dedicated 408_QC_Jun24 | SANTOS LIMITED | RM40-90-1, RM40-101-1, RM40-103-1, RM40-94-1, RM40-105-1, RM40-85-1, RM40-96-1, RM40-86-1, RM40-83-1 | SAVANNA DRILLING #408 | J.24.105197 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-02-28 23:00 | 2024-05-24 |  | 2024-05-25 | 2024-06-25 23:59 |  | 2023-12-12 23:59 | Roma WL | JEsmeralda | 2024-07-29 15:49 | SNiang |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.08 | A.1024839.08.02 | Dedicated 408_QC_Feb24 | SANTOS LIMITED | RM90-87-1, RM90-100-1, RM90-99-1, RM90-123-1, RM90-132-1, RM90-98-1, RM90-109-1, RM90-122-1, RM09-22-1, RM09-13-1, RM09-68-1, RM09-19-1, RM09-17-1, RM90-139-1, RM90-150-1, RM90-149-1, RM90-160-1, RM90-161-1, MEDML01 | SAVANNA DRILLING #408 | J.24.043681 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2023-11-17 | 2024-11-16 |  | 2024-11-16 | 2024-12-10 23:59 |  | 2024-01-21 23:59 | Roma WL | JEsmeralda | 2024-11-29 18:29 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.08 | A.1024839.08.01 | Santos OH 408 Dedicated Jan | SANTOS LIMITED | RM90-87-1, RM90-100-1, RM90-99-1, RM90-123-1, RM90-132-1, RM90-98-1, RM90-109-1, RM90-122-1, RM09-22-1, RM09-13-1, RM09-83-1, RM09-68-1, RM09-19-1 | SAVANNA DRILLING #408 | J.23.176197 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-11-18 | 2024-11-16 |  | 2024-11-17 | 2024-11-17 23:59 |  | 2023-12-30 23:59 | Roma WL | JEsmeralda | 2024-11-16 13:52 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 2 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.08 | A.1024839.08.03 | Dedicated 408_QC_Mar24 | SANTOS LIMITED | RM40-69-1, RM40-49-1, RM40-60-1, RM40-72-1, RM40-58-1, RM40-46-1 | SAVANNA DRILLING #408 | J.24.060081 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-03-02 | 2024-02-29 |  | 2024-03-01 | 2024-04-13 23:59 |  | 2023-04-13 22:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.08 | A.1024839.08.05 | Dedicated 408_QC_May24 | SANTOS LIMITED | RM40-69-1, RM40-49-1, RM40-60-1, RM40-72-1, RM40-58-1, RM40-46-1, RM23-46-1, RM23-42-1, RM23-43-1, RM23-41-1, DULACCA WEST-1, RM40-109-1, RM90-157-1, RM40-119-1, RM40-120-1 | SAVANNA DRILLING #408 | J.24.087492 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-26 | 2024-04-24 |  | 2024-04-25 | 2024-05-26 23:59 |  | 2024-05-26 23:59 | Roma WL | JEsmeralda | 2024-06-05 11:50 | NSchwenke |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.08 | A.1024839.08.04 | Dedicated 408_QC_Apr24 | SANTOS LIMITED | RM40-69-1, RM40-49-1, RM40-60-1, RM40-72-1, RM40-58-1, RM40-46-1, RM23-46-1, RM23-42-1, RM23-43-1, RM23-41-1 | SAVANNA DRILLING #408 | J.24.073532 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-03-26 | 2024-03-24 | 2024-03-25 | 2024-03-25 | 2024-04-25 23:59 | 2024-05-08 | 2023-05-07 22:59 | Roma WL | JEsmeralda | 2024-05-06 08:16 | BLima7 |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.07 | A.1024839.07.10 | Jun OH Dedicated Santos | SANTOS LIMITED | RM90-105-1, RM90-95-1, RM90-84-1, RM90-74-1, RM90-77-1, RM90-66-1, RM90-78-1, RM90-67-1, FV13-86-1 | SAVANNA DRILLING #408 | J.24.050654 | RPE | ES-OH-NO | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress | 2024-06-30 23:00 | 2024-06-01 |  | 2024-06-01 | 2024-06-28 10:00 |  | 2024-06-29 23:00 | Roma WL | KKeese | 2024-12-12 17:02 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 137751.79 | 1 |  | L3 - Full RO |  | 66.7 | 33.3 | 100 | 75 | 62.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.07 | A.1024839.07.16 | Dec OH Dedicated Santos | SANTOS LIMITED | RM90-105-1, RM90-95-1, RM90-84-1, RM90-74-1, RM90-77-1, RM90-66-1, RM90-78-1, RM90-67-1, FV13-86-1 | SAVANNA DRILLING #408 | J.24.096872 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-12-30 23:00 | 2024-12-01 |  | 2024-12-01 | 2024-12-31 10:00 |  | 2025-01-01 23:00 | Roma WL | KKeese | 2024-10-29 11:41 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.07 | A.1024839.07.15 | Nov OH Dedicated Santos | SANTOS LIMITED | RM90-105-1, RM90-95-1, RM90-84-1, RM90-74-1, RM90-77-1, RM90-66-1, RM90-78-1, RM90-67-1, FV13-86-1 | SAVANNA DRILLING #408 | J.24.096871 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-11-30 23:00 | 2024-11-01 |  | 2024-11-01 | 2024-11-30 10:00 |  | 2024-12-01 23:00 | Roma WL | KKeese | 2024-10-29 11:38 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1024839 | O.1024839.07 | A.1024839.07.13 | Sep OH Dedicated Santos | SANTOS LIMITED | RM90-105-1, RM90-95-1, RM90-84-1, RM90-74-1, RM90-77-1, RM90-66-1, RM90-78-1, RM90-67-1, FV13-86-1 | SAVANNA DRILLING #408 | J.24.096869 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-09-30 23:00 | 2024-09-01 |  | 2024-09-01 | 2024-09-30 10:00 |  | 2024-10-01 23:00 | Roma WL | KKeese | 2024-10-22 10:36 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.07 | A.1024839.07.01 | Quad Combo_Aug1 | SANTOS LIMITED | RM27-49-1, RM27-50-1, RM90-71-1, RM90-70-1, RM90-82-1, RM90-92-1 | SAVANNA DRILLING #408 | J.24.010388 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-08-18 | 2023-09-25 | 2023-09-25 12:00 | 2023-09-26 | 2023-10-12 10:00 | 2023-10-13 01:00 | 2023-09-11 10:00 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 14 |  | L3 - Full RO |  | 83.3 | 83.3 | 100 | 100 | 90 |  | 1 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.07 | A.1024839.07.02 | Dedicated Unit September | SANTOS LIMITED | RM27-49-1, RM27-50-1, RM90-71-1, RM90-70-1, RM90-82-1, RM90-92-1, RM90-81-1, RM90-80-1, RM90-69-1, RM90-91-1, RM90-102-1, RM90-103-1, RM90-125, RM90-104-1, RM90-93-1 | SAVANNA DRILLING #408 | J.23.130613 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-09-02 | 2023-10-03 | 2023-09-24 14:00 | 2023-10-03 | 2023-10-14 10:00 | 2023-10-15 | 2023-09-05 10:00 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.07 | A.1024839.07.03 | Quad Combo_Dedicated Oct23 | SANTOS LIMITED | RM90-105-1, RM90-95-1, RM90-84-1, RM90-74-1, RM90-77-1, RM90-66-1 | SAVANNA DRILLING #408 | J.23.139932 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-10-20 | 2023-09-20 |  | 2023-09-20 | 2023-10-20 10:00 |  | 2023-10-22 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.07 | A.1024839.07.04 | Quad Combo_Dedicated Nov23 | SANTOS LIMITED | RM90-105-1, RM90-95-1, RM90-84-1, RM90-74-1, RM90-77-1, RM90-66-1, RM90-78-1, RM90-67-1, FV13-86-1, RM90-60-1, RM90-48-1, RM90-59-1, FV18-135-1, RM90-58-1, RM90-68-1, RM90-36-1, RM90-37-1 | SAVANNA DRILLING #408 | J.23.157221 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-11-20 23:00 | 2023-10-22 |  | 2023-10-22 | 2023-11-21 10:00 |  | 2023-11-22 23:00 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.07 | A.1024839.07.05 | Quad Combo_Dedicated Dec23 | SANTOS LIMITED | RM90-47-1, RM14-29-1, RM14-18-1, RM14-60-1, RM14-90-1, RM14-08-1, RM90-86-1, RM14-19-1 | SAVANNA DRILLING #408 | J.23.160229 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-12-24 23:00 | 2023-11-23 |  | 2023-11-25 | 2023-12-25 10:00 |  | 2023-12-26 23:00 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.07 | A.1024839.07.12 | Aug OH Dedicated Santos | SANTOS LIMITED | RM90-105-1, RM90-95-1, RM90-84-1, RM90-74-1, RM90-77-1, RM90-66-1, RM90-78-1, RM90-67-1, FV13-86-1 | SAVANNA DRILLING #408 | J.24.050656 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-08-30 23:00 | 2024-08-01 |  | 2024-08-01 | 2024-08-31 10:00 |  | 2024-09-01 23:00 | Roma WL | KKeese | 2024-07-24 16:32 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.07 | A.1024839.07.11 | Jul OH Dedicated Santos | SANTOS LIMITED | RM90-105-1, RM90-95-1, RM90-84-1, RM90-74-1, RM90-77-1, RM90-66-1, RM90-78-1, RM90-67-1, FV13-86-1 | SAVANNA DRILLING #408 | J.24.050655 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-07-30 23:00 | 2024-07-01 |  | 2024-07-01 | 2024-07-31 10:00 |  | 2024-08-01 23:00 | Roma WL | KKeese | 2024-07-24 07:41 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.07 | A.1024839.07.09 | May OH Dedicated Santos | SANTOS LIMITED | RM90-105-1, RM90-95-1, RM90-84-1, RM90-74-1, RM90-77-1, RM90-66-1, RM90-78-1, RM90-67-1, FV13-86-1 | SAVANNA DRILLING #408 | J.24.050653 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-05-30 23:00 | 2024-05-01 | 2024-04-30 23:00 | 2024-05-01 | 2024-05-31 10:00 | 2024-06-13 23:00 | 2024-06-01 23:00 | Roma WL | KKeese | 2024-05-23 15:20 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.07 | A.1024839.07.14 | Oct OH Dedicated Santos | SANTOS LIMITED | RM90-105-1, RM90-95-1, RM90-84-1, RM90-74-1, RM90-77-1, RM90-66-1, RM90-78-1, RM90-67-1, FV13-86-1 | SAVANNA DRILLING #408 | J.24.096870 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2024-10-31 | 2024-10-01 | 2024-09-30 23:00 | 2024-10-01 | 2024-10-31 10:00 | 2024-11-14 | 2024-11-02 | Roma WL | KKeese | 2024-05-10 09:02 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.07 | A.1024839.07.06 | OH Dedicated Feb 2024 | SANTOS LIMITED | RM90-105-1, RM90-95-1, RM90-84-1, RM90-74-1, RM90-77-1, RM90-66-1, RM90-78-1, RM90-67-1, FV13-86-1 | SAVANNA DRILLING #408 | J.24.021431 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-03-01 23:00 | 2024-02-01 | 2024-02-01 | 2024-02-01 | 2024-02-29 10:00 | 2024-03-14 | 2024-03-01 23:00 | Roma WL | KKeese | 2024-04-02 14:59 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.07 | A.1024839.07.08 | Apr OH Dedicated Santos | SANTOS LIMITED | RM90-105-1, RM90-95-1, RM90-84-1, RM90-74-1, RM90-77-1, RM90-66-1, RM90-78-1, RM90-67-1, FV13-86-1 | SAVANNA DRILLING #408 | J.24.050652 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2024-04-30 22:00 | 2024-04-01 |  | 2024-04-01 | 2024-04-29 10:00 |  | 2024-04-30 22:00 | Roma WL | KKeese | 2024-02-15 13:51 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 137751.79 | 1 |  | L3 - Full RO |  | 50 | 0 | 0 | 25 | 22.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.07 | A.1024839.07.07 | OH Dedicated Mar 2024 | SANTOS LIMITED | RM90-105-1, RM90-95-1, RM90-84-1, RM90-74-1, RM90-77-1, RM90-66-1, RM90-78-1, RM90-67-1, FV13-86-1 | SAVANNA DRILLING #408 | J.24.021432 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2024-03-30 23:00 | 2024-03-01 |  | 2024-03-01 | 2024-03-31 10:00 |  | 2024-04-01 23:00 | Roma WL | KKeese | 2023-10-29 14:31 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 137751.79 | 1 |  | L3 - Full RO |  | 50 | 0 | 0 | 25 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.06 | A.1024839.06.03 | Quad Combo May 16-31 | SANTOS LIMITED | RM13-30-1, RM08-42-1, RM08-43-1, RM16-26-1 | SAVANNA DRILLING #408 | J.23.081900 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-16 | 2023-05-16 |  | 2023-05-16 | 2023-06-04 23:59 |  | 2023-06-04 23:59 | Roma WL | RDell | 2023-06-08 12:42 | RDell |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7719.3 | 6 |  | L3 - Full RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.06 | A.1024839.06.02 | Quad Combo_May1-15 | SANTOS LIMITED | RM13-34-1, RM13-35-1, RM13-40-1, RM12-68-1, RM17-13-1, RM13-29-1 | SAVANNA DRILLING #408 | J.23.076121 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-01 09:00 | 2023-04-30 23:00 |  | 2023-05-01 09:00 | 2023-05-15 08:59 |  | 2023-05-15 08:59 | Roma WL | SAli63 | 2023-05-14 22:14 | RDell |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 14 |  | L3 - Full RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.06 | A.1024839.06.01 | Quad Combo | SANTOS LIMITED | RM17-08-1, RM12-63-1, RM17-11-1, RM17-23-1, RM17-36-1, RM13-39-1 | SAVANNA DRILLING #408 | J.23.071479 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-16 09:00 | 2023-04-15 23:00 |  | 2023-04-16 09:00 | 2023-04-30 08:59 |  | 2023-04-30 08:59 | Roma WL | SAli63 | 2023-04-29 16:16 | NMoore2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 14 |  | L3 - Full RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.05 | A.1024839.05.16 | Quad Combo_Aug1 | SANTOS LIMITED | RM27-46-1, RM27-48-1 | SAVANNA DRILLING #408 | J.23.117754 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-08-01 01:00 | 2023-08-01 |  | 2023-08-01 01:00 | 2023-08-25 12:00 |  | 2023-08-25 12:00 | Roma WL | SAli63 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 14 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.05 | A.1024839.05.15 | Quad Combo_Jul2 | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.23.084121 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | Design Completed | 2023-07-15 01:00 | 2023-07-15 |  | 2023-07-15 01:00 | 2023-07-29 12:00 |  | 2023-07-29 12:00 | Roma WL | SAli63 | 2023-05-15 17:19 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 14 |  | L3 - Full RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.05 | A.1024839.05.14 | Quad Combo_Jul1 | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.23.084120 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | Design Completed | 2023-07-01 01:00 | 2023-07-01 |  | 2023-07-01 01:00 | 2023-07-15 12:00 |  | 2023-07-15 12:00 | Roma WL | SAli63 | 2023-05-15 17:19 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 14 |  | L3 - Full RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.05 | A.1024839.05.08 | Quad Combo APR_1 | SANTOS LIMITED | RM17-20-1, RM17-10-1, RM17-22-1, RM17-21-1, RM17-09-1 | SAVANNA DRILLING #408 | J.23.050156 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-01 06:00 | 2023-04-01 |  | 2023-04-01 06:00 | 2023-04-15 23:59 |  | 2023-04-15 23:59 | Roma WL | SAli63 | 2023-04-18 02:17 | NSchwenke |  | No |  |  |  |  | Jon Lawrie |  | 0 | 14 |  | L3 - Full RO |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.05 | A.1024839.05.09 | Quad Combo_Apr2 | SANTOS LIMITED | RM17-08-1 | SAVANNA DRILLING #408 | J.23.050149 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-04-16 01:00 | 2023-04-16 |  | 2023-04-16 01:00 | 2023-04-30 12:00 |  | 2023-04-30 12:00 | Roma WL | SAli63 | 2023-04-15 14:26 | SAli63 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 14 |  | L3 - Full RO |  | 79.2 | 8.3 | 0 | 0 | 26.3 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.05 | A.1024839.05.11 | Quad Combo_May2 | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.23.071478 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | Design Completed | 2023-05-16 01:00 | 2023-05-16 |  | 2023-05-16 01:00 | 2023-05-30 12:00 |  | 2023-05-30 12:00 | Roma WL | SAli63 | 2023-04-15 14:05 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 14 |  | L3 - Full RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.05 | A.1024839.05.10 | Quad Combo_May1 | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.23.071477 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | Design Completed | 2023-05-01 23:00 | 2023-05-01 |  | 2023-05-01 23:00 | 2023-05-15 15:00 |  | 2023-05-15 15:00 | Roma WL | SAli63 | 2023-04-15 14:04 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 14 |  | L3 - Full RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.05 | A.1024839.05.06 | Quad Combo | SANTOS LIMITED | RM17-05-1, RM12-49-1, RM12-50-1, RM12-61-1, RM12-62-1, RM17-17-1, RM17-16-1, RM17-19-1 | SAVANNA DRILLING #408 | J.23.016510 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-03-15 09:00 | 2023-03-14 23:00 |  | 2023-03-15 09:00 | 2023-04-01 08:59 |  | 2023-04-03 08:59 | Roma WL | MRony2 | 2023-04-02 00:11 | NMoore2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 14 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.05 | A.1024839.05.05 | Quad Combo | SANTOS LIMITED | RM12-59-1, RM12-42-1, RM17-7-1, RM17-18-1, RM17-06-1 | SAVANNA DRILLING #408 | J.23.016509 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-03-01 09:00 | 2023-02-28 18:00 |  | 2023-03-01 10:00 | 2023-03-15 09:59 |  | 2023-03-17 08:59 | Roma WL | MRony2 | 2023-03-14 13:38 | NSchwenke |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 14 |  | L3 - Full RO |  | 91.7 | 66.7 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.05 | A.1024839.05.13 | Quad Combo_June2 | SANTOS LIMITED |  | SAVANNA DRILLING #408 |  | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | Design Completed | Not Started | Design Completed | 2023-06-15 01:00 | 2023-06-15 |  | 2023-06-15 01:00 | 2023-06-29 12:00 |  | 2023-06-29 12:00 | Roma WL | SAli63 | 2023-03-05 15:19 | SAli63 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 14 |  | L3 - Full RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.05 | A.1024839.05.12 | Quad Combo_June1 | SANTOS LIMITED |  | SAVANNA DRILLING #408 |  | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | Design Completed | Not Started | Design Completed | 2023-06-01 01:00 | 2023-06-01 |  | 2023-06-01 01:00 | 2023-06-15 12:00 |  | 2023-06-15 12:00 | Roma WL | SAli63 | 2023-03-05 15:18 | SAli63 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 14 |  | L3 - Full RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.05 | A.1024839.05.07 | Quad Combo | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.23.016511 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Not Required | Not Started | In Progress | 2023-03-25 10:00 | 2023-03-25 23:00 |  | 2023-03-26 09:00 | 2023-04-02 08:59 |  | 2023-04-03 08:59 | Roma WL | MRony2 | 2023-03-03 18:36 | SAli63 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.05 | A.1024839.05.04 | Quad Combo | SANTOS LIMITED | RM12-41-1, RM12-58-1, RM12-47-1, RM12-51-1, RM12-52-1 | SAVANNA DRILLING #408 | J.23.016508 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-02-19 08:00 | 2023-02-18 23:00 |  | 2023-02-19 09:00 | 2023-02-28 08:59 |  | 2023-03-02 07:59 | Roma WL | MRony2 | 2023-02-28 16:50 | RDell |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  | L3 - Full RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.05 | A.1024839.05.03 | Quad Combo | SANTOS LIMITED | RM11-08-1, RM12-37-1, RM11-06-1, RM12-36-1, RM12-41-1 | SAVANNA DRILLING #408 | J.23.016507 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-02-09 18:00 | 2023-02-09 23:00 |  | 2023-02-11 03:00 | 2023-02-18 02:59 |  | 2023-02-28 18:00 | Roma WL | MRony2 | 2023-02-17 12:40 | NSchwenke |  | No |  |  |  |  | Jon Lawrie |  | 0 | 2 |  | L3 - Full RO |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.05 | A.1024839.05.02 | Quad Combo | SANTOS LIMITED | RM08-70-1, RM11-05-1, RM11-07-1, RM12-33-1, RM12-32-1 | SAVANNA DRILLING #408 | J.23.016506 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-02-01 08:00 | 2023-02-01 |  | 2023-02-01 09:00 | 2023-02-08 08:59 |  | 2023-02-10 07:59 | Roma WL | MRony2 | 2023-02-11 04:44 | NMoore2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  | L3 - Full RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.05 | A.1024839.05.01 | Quad combo | SANTOS LIMITED | RM08-59-1, RM08-73-1, RM08-64-1, RM08-57-1, RM08-61-1 | SAVANNA DRILLING #408 | J.23.016505 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-01-17 08:00 | 2023-01-16 23:00 |  | 2023-01-17 09:00 | 2023-01-24 08:59 |  | 2023-01-26 07:59 | Roma WL | MRony2 | 2023-01-30 15:06 | RDell |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 3 |  | L3 - Full RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.04 | A.1024839.04.09 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.23.008588 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-01-12 09:00 | 2023-01-11 01:00 |  | 2023-01-17 11:00 | 2023-01-30 10:59 |  | 2023-01-27 08:59 | Roma WL | MRony2 | 2023-02-04 11:53 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.04 | A.1024839.04.10 | Quad combo | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.23.008589 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-01-22 09:00 | 2023-01-21 01:00 |  | 2023-01-22 11:00 | 2023-01-29 10:59 |  | 2023-01-31 08:59 | Roma WL | MRony2 | 2023-02-04 11:52 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.04 | A.1024839.04.08 | QC | SANTOS LIMITED | RM06-53-1, RM08-71-1, RM08-72-1, RM08-58-1, RM08-65-1 | SAVANNA DRILLING #408 | J.22.110373 | RPE | ES-OH-Ops | Low | Operationally Complete | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-01-04 11:00 | 2023-01-04 01:00 |  | 2023-01-04 11:00 | 2023-01-25 10:59 |  | 2023-01-27 10:59 | Roma WL | MRony2 | 2023-01-17 20:31 | NMoore2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 3 |  | L3 - Full RO |  | 75 | 66.7 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.04 | A.1024839.04.05 | Quad combo | SANTOS LIMITED | RM08-69-1, RM08-53-1, RM08-76-1, RM08-66-1, RM08-56-1, RM08-63-1, RM06-52-1, RM08-51-1 | SAVANNA DRILLING #408 | J.22.111015 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-12-14 11:00 | 2022-12-08 01:00 |  | 2022-12-14 11:00 | 2022-12-31 10:59 |  | 2023-01-02 10:59 | Roma WL | MRony2 | 2023-01-05 09:51 | NSchwenke |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 3 |  | L3 - Full RO |  | 75 | 33.3 | 0 | 50 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.04 | A.1024839.04.06 | Quad combo | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.22.110385 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-14 11:00 | 2022-12-13 01:00 |  | 2022-12-14 11:00 | 2022-12-21 10:59 |  | 2022-12-23 10:59 | Roma WL | MRony2 | 2023-01-02 23:33 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.04 | A.1024839.04.07 | Quad Combo | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.22.110379 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-25 11:00 | 2022-12-24 01:00 |  | 2022-12-25 11:00 | 2023-01-01 10:59 |  | 2023-01-03 10:59 | Roma WL | MRony2 | 2022-12-29 03:49 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.04 | A.1024839.04.04 | Quad combo | SANTOS LIMITED | RM68-122-1, RM68-124-1, RM68-121-1, RM08-52-1, RM08-60-1 | SAVANNA DRILLING #408 | J.22.111014 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-30 11:00 | 2022-11-29 01:00 |  | 2022-11-30 11:00 | 2022-12-16 10:59 |  | 2022-12-18 10:59 | Roma WL | MRony2 | 2022-12-14 23:28 | NMoore2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 3 |  | L3 - Full RO | [7 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.04 | A.1024839.04.03 | Quad combo | SANTOS LIMITED | RM68-111-1, RM68-110-1, RM68-14 1, RM68-123-1 | SAVANNA DRILLING #408 | J.22.110368 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-16 11:00 | 2022-11-15 01:00 |  | 2022-11-16 11:00 | 2022-12-03 10:59 |  | 2022-12-05 10:59 | Roma WL | MRony2 | 2022-12-01 17:25 | NMoore2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.04 | A.1024839.04.02 | Quad combo | SANTOS LIMITED | RM12-77-1, RM08-81-1, RM68-100-1, RM68-101-1 | SAVANNA DRILLING #408 | J.22.110370 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-09 11:00 | 2022-11-08 02:00 |  | 2022-11-09 12:00 | 2022-11-18 10:59 |  | 2022-11-20 10:59 | Roma WL | MRony2 | 2022-11-22 13:27 | RDell |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.04 | A.1024839.04.13 | A.1024839.04.02 | SANTOS LIMITED | RM08-62-1, RM08-47-1, RM08-55-1, RM08-54-1, RM08-77-1 | SAVANNA DRILLING #408 | J.22.117006 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-10-24 01:00 |  | 2022-10-25 11:00 | 2022-11-08 10:59 |  |  | Roma WL | NSchwenke | 2022-11-09 23:00 | NMoore2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.04 | A.1024839.04.12 | Omeo 2 | SANTOS LIMITED | OMEO 2 | SAVANNA DRILLING #408 | J.22.110400 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-10-06 08:00 |  | 2022-10-07 18:00 | 2022-10-09 16:59 |  |  | Roma WL | MRony2 | 2022-11-03 18:33 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 74116.31 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.04 | A.1024839.04.01 | Quad Combo | SANTOS LIMITED | RM12-31-1, RM08-79-1, RM08-80-1 | SAVANNA DRILLING #408 | J.22.110381 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-10-19 |  | 2022-10-19 | 2022-10-20 10:59 |  |  | Roma WL | MRony2 | 2022-10-25 10:00 | RDell |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.04 | A.1024839.04.11 | Brumby 34 | SANTOS LIMITED | BRUMBY 34 | SAVANNA DRILLING #408 | J.22.111016 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-09-27 01:00 |  | 2022-09-28 11:00 | 2022-10-01 10:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:36 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 73531.51 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.03 | A.1024839.03.12 | QC and MDT RM40-81-1 | SANTOS LIMITED | RM40-81-1 | SAVANNA DRILLING #408 | J.23.041213 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-07-21 14:00 | 2023-07-20 |  | 2023-07-21 14:00 | 2023-07-22 14:00 |  | 2023-07-22 14:00 | Roma WL | SAli63 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  | L2 - Shift RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.03 | A.1024839.03.11 | QC and MDT on RM40-53-1 | SANTOS LIMITED | RM40-53-1 | SAVANNA DRILLING #408 | J.23.041212 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-07 10:00 | 2023-06-30 |  | 2023-07-07 10:00 | 2023-07-17 10:00 |  | 2023-07-17 10:00 | Roma WL | SAli63 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 21156.6 | 3 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.03 | A.1024839.03.15 | MDT September | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.23.084149 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-12 10:00 | 2023-09-11 | 2023-09-12 | 2023-09-12 10:00 | 2023-09-13 10:00 | 2023-09-14 | 2023-09-13 10:00 | Roma WL | KKeese | 2023-09-26 09:20 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 3 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1024839 | O.1024839.03 | A.1024839.03.14 | QC and MDT on Warrinilla 12 | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.23.041217 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-11-26 10:00 | 2023-11-25 | 2023-11-26 01:00 | 2023-11-26 10:00 | 2023-11-27 10:00 | 2023-11-28 01:00 | 2023-11-27 10:00 | Roma WL | SAli63 | 2023-08-29 11:33 | KKeese |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.03 | A.1024839.03.13 | QC and MDT on Warrinilla 7 | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.23.041216 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-11-12 10:00 | 2023-11-11 | 2023-11-12 01:00 | 2023-11-12 10:00 | 2023-11-13 10:00 | 2023-11-14 01:00 | 2023-11-13 10:00 | Roma WL | SAli63 | 2023-08-29 11:33 | KKeese |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.03 | A.1024839.03.10 | QC and MDT RM90-79-1 | SANTOS LIMITED | RM90-79-1 | SAVANNA DRILLING #408 | J.23.041211 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-28 | 2023-06-26 | 2023-06-27 04:00 | 2023-06-28 | 2023-06-30 | 2023-06-30 14:00 | 2023-06-30 | Roma WL | SAli63 | 2023-07-28 19:35 | ysaeedabadian |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 9720.6 | 3 |  | L2 - Shift RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.03 | A.1024839.03.09 | QC and MDT RM90-51-1 | SANTOS LIMITED | RM90-51-1 | SAVANNA DRILLING #408 | J.23.041210 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-24 14:00 | 2023-06-23 |  | 2023-06-24 14:00 | 2023-06-25 14:00 |  | 2023-06-25 14:00 | Roma WL | SAli63 | 2023-06-26 17:50 | RDell |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 19441.2 | 3 |  | L2 - Shift RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.03 | A.1024839.03.08 | QC and MDT RM90-94-1 | SANTOS LIMITED | RM90-94-1 | SAVANNA DRILLING #408 | J.23.041209 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-20 | 2023-06-20 |  | 2023-06-20 | 2023-06-21 |  | 2023-06-21 | Roma WL | SAli63 | 2023-06-22 19:21 | RDell |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 14580.9 | 3 |  | L2 - Shift RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.03 | A.1024839.03.06 | QC and MDT Well 3 | SANTOS LIMITED | RM90-76-1 | SAVANNA DRILLING #408 | J.23.041207 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-14 10:00 | 2023-06-14 |  | 2023-06-14 10:00 | 2023-06-15 10:00 |  | 2023-06-15 10:00 | Roma WL | SAli63 | 2023-06-19 14:00 | ysaeedabadian |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.03 | A.1024839.03.07 | QC and MDT Well 2 | SANTOS LIMITED | RM90-131-1 | SAVANNA DRILLING #408 | J.23.041208 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-11 10:00 | 2023-06-11 |  | 2023-06-11 10:00 | 2023-06-12 10:00 |  | 2023-06-12 10:00 | Roma WL | SAli63 | 2023-06-17 11:40 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 54320.99 | 3 |  | L2 - Shift RO |  | 83.3 | 83.3 | 0 | 75 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.03 | A.1024839.03.05 | QC & MDT | SANTOS LIMITED | RM16-26-1, RM90-131-1, RM90-76-1 | SAVANNA DRILLING #408 | J.23.041206 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-08 10:00 | 2023-06-07 |  | 2023-06-08 10:00 | 2023-06-15 10:00 |  | 2023-06-15 10:00 | Roma WL | SAli63 | 2023-06-16 01:09 | RDell |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 69792.07 | 3 |  | L2 - Shift RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.03 | A.1024839.03.04 | MDT | SANTOS LIMITED | RM16-26-1 | SAVANNA DRILLING #408 | J.23.040028 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Not Required | In Progress | 2023-06-01 10:00 | 2023-05-31 |  | 2023-06-01 10:00 | 2023-06-02 10:00 |  | 2023-06-02 10:00 | Roma WL | MRony2 | 2023-06-08 12:52 | RDell |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  | L2 - Shift RO |  | 70.8 | 0 | 0 | 0 | 21.3 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.03 | A.1024839.03.01 | BRUMBY 34 | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.22.111013 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-06-13 |  | 2022-06-14 | 2022-06-16 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:36 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.03 | A.1024839.03.02 | Omeo 2 | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.22.110347 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-06-23 |  | 2022-06-24 | 2022-06-26 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:16 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.03 | A.1024839.03.03 | Mundalya 1 ATP2052 Corehole | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.22.110343 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-07-08 |  | 2022-07-09 | 2022-07-11 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:16 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.02 | A.1024839.02.04 | Quad Combo | SANTOS LIMITED | RM13-69-1, RM13-100-1, RM12-45-1 | SAVANNA DRILLING #408 | J.22.110337 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2022-07-11 02:00 | 2022-07-09 03:00 |  | 2022-07-11 03:00 | 2022-07-23 02:59 |  | 2022-07-25 01:59 | Roma WL | MRony2 | 2023-02-04 11:37 | SSabatini |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 3 |  | L3 - Full RO |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.02 | A.1024839.02.06 | Quad Combo | SANTOS LIMITED | RM96-01-1, RM96-02-1, RM23-21-1, RM15-131-1, RM23-19-1, RM23-20-1 | SAVANNA DRILLING #408 | J.22.111011 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2022-08-25 09:00 | 2022-08-25 |  | 2022-08-25 10:00 | 2022-09-13 09:59 |  | 2022-09-15 08:59 | Roma WL | MRony2 | 2023-02-04 11:35 | SSabatini |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 3 |  | L3 - Full RO |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.02 | A.1024839.02.13 | Mundelya-1 | SANTOS LIMITED | Mundalya 1 | SAVANNA DRILLING #408 | J.22.110396 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed |  | 2022-08-13 |  | 2022-08-14 10:00 | 2022-08-31 09:59 |  |  | Roma WL | MRony2 | 2022-10-19 13:55 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 19210.53 | 1 |  |  |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.02 | A.1024839.02.05 | Quad Combo | SANTOS LIMITED | RM96-05-1, RM96-03-1 | SAVANNA DRILLING #408 | J.22.110322 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-07-28 |  | 2022-07-28 10:00 | 2022-08-04 09:59 |  |  | Roma WL | MRony2 | 2022-10-19 13:51 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.02 | A.1024839.02.03 | Quad Combo | SANTOS LIMITED | RM07-107-1, RM02-67-1, RM07-07-1 | SAVANNA DRILLING #408 | J.22.110320 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-06-23 |  | 2022-06-23 10:00 | 2022-07-01 09:59 |  |  | Roma WL | MRony2 | 2022-10-19 13:24 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 3 |  |  |  | 66.7 | 83.3 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.02 | A.1024839.02.07 | Quad Combo | SANTOS LIMITED | RM23-20-1 | SAVANNA DRILLING #408 | J.22.111012 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-09-17 |  | 2022-09-17 17:00 | 2022-09-24 16:59 |  |  | Roma WL | MRony2 | 2022-10-18 15:11 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 3 |  |  |  | 70.8 | 8.3 | 0 | 0 | 23.8 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.02 | A.1024839.02.01 | Quad Combo | SANTOS LIMITED | RM15-133, RM15-37-1A, RM12-79-1, RM12-75-1 | SAVANNA DRILLING #408 | J.22.111010 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed |  | 2022-05-23 |  | 2022-05-24 10:00 | 2022-06-13 09:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:35 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 13450.29 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.02 | A.1024839.02.12 | Quad combo | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.22.110374 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-10-07 01:00 |  | 2022-10-07 11:00 | 2022-10-14 10:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.02 | A.1024839.02.11 | Quad combo | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.22.110369 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-09-27 |  | 2022-09-27 10:00 | 2022-10-06 10:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.02 | A.1024839.02.10 | Kaimanna 2: Quadcombo + MDT | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.22.110330 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-06-02 |  | 2022-06-02 10:00 | 2022-06-04 09:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.02 | A.1024839.02.09 | Kaimanna 21 | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.22.110331 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-06-22 |  | 2022-06-22 10:00 | 2022-06-24 09:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 1 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.02 | A.1024839.02.08 | Quad Combo | SANTOS LIMITED |  | SAVANNA DRILLING #408 | J.22.110321 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-09-18 |  | 2022-09-18 10:00 | 2022-09-25 09:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.02 | A.1024839.02.02 | Quad Combo | SANTOS LIMITED | RM13-05-1, RM09-82-1, RM03-101-1 | SAVANNA DRILLING #408 | J.22.110317 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-06-13 |  | 2022-06-13 10:00 | 2022-06-20 09:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 3 |  |  |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.01 | A.1024839.01.08 | Quad Combo | SANTOS LIMITED | RM15-126-1, RM15-133, RM15-37-1A | SAVANNA DRILLING #408 | J.22.111009 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-05-09 |  | 2022-05-09 23:00 | 2022-05-22 22:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:35 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  |  |  | 75 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.01 | A.1024839.01.06 | Quad Combo | SANTOS LIMITED | RM13-96-1, RM13-90-1, RM13-95-1, RM15-119-1, RM15-129-1 | SAVANNA DRILLING #408 | J.22.111008 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-04-17 |  | 2022-04-17 16:00 | 2022-04-21 15:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:35 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | 3 |  |  |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.01 | A.1024839.01.05 | Quad Combo | SANTOS LIMITED | RM13-98-1, RM13-97-1, RM13-79-1, RM13-91-1, RM22-19-1 | SAVANNA DRILLING #408 | J.22.111007 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-03-27 |  | 2022-03-30 | 2022-04-15 22:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:35 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | 3 |  |  |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.01 | A.1024839.01.01 | Quad Combo | SANTOS LIMITED | RM42-07-1, RM42-11-1, RM42-10-1, RM42-14-1 | SAVANNA DRILLING #408 | J.22.111006 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-02-03 |  | 2022-02-03 | 2022-02-09 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:35 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | 3 |  |  |  | 91.7 | 50 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.01 | A.1024839.01.03 | Quad Combo | SANTOS LIMITED | RM15-65-1 | SAVANNA DRILLING #408 | J.22.110290 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-03-07 |  | 2022-03-08 | 2022-03-15 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | 3 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.01 | A.1024839.01.07 | Quad Combo | SANTOS LIMITED | RM15-119-1, RM15-129-1, RM15-125-1 | SAVANNA DRILLING #408 | J.22.110288 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-04-27 16:00 |  | 2022-04-28 16:00 | 2022-05-06 15:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 3 |  |  |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.01 | A.1024839.01.04 | Quad Combo | SANTOS LIMITED | RM15-66-1, RM15-76-1, RM13-74-1, RM13-79-1, RM13-88-1 | SAVANNA DRILLING #408 | J.22.110284 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-03-14 |  | 2022-03-17 | 2022-03-30 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 5360.62 | 3 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024839 | O.1024839.01 | A.1024839.01.02 | Quad Combo | SANTOS LIMITED | RM42-14-1, RM42-12-1 | SAVANNA DRILLING #408 | J.22.110283 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-02-20 |  | 2022-02-20 | 2022-03-08 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 18458.09 | 3 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1024808 | O.1024808.01 | A.1024808.01.01 | CT Milling Well 1 | WOODSIDE ENERGY LTD | Well #1 |  | J.23.008729 | RPI | CT-MILLSLB,CT-MILLNOSLB | Low | Cancelled | Close - PSD |  | Not Required | Not Started | In Progress |  | 2023-02-02 |  | 2023-02-02 | 2023-02-11 23:59 |  |  | AUS West Coast WS | JMeyer9 | 2023-02-02 07:47 | HFerdjallah |  | No |  |  |  |  | Samer Kanaan |  | 0 | 3 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1024807 | O.1024807.02 | A.1024807.02.04 | Test - Crew Archetype | IMPERIAL OIL AND GAS PTY LTD | CARPENTARIA-3H |  | J.23.105160 | RPI | CT-LIFT | Low | Cancelled | Close - PSD |  | In Progress | Not Required | In Progress | 2023-08-01 | 2023-08-01 |  | 2023-08-01 | 2023-09-12 |  | 2023-09-17 | AUS East Coast WS | HFerdjallah | 2023-06-30 20:07 | HFerdjallah |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 1 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1024807 | O.1024807.02 | A.1024807.02.02 | Carpentaria-3H | IMPERIAL OIL AND GAS PTY LTD | CARPENTARIA-3H |  | J.22.111005 | RPI | CT-CIRC | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-13 | 2022-12-13 |  | 2022-12-13 | 2023-01-24 |  | 2023-01-29 | AUS East Coast WS | SKanaan | 2023-02-02 18:00 | radinegara |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 5 |  |  |  | 43.8 | 66.7 | 100 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1024807 | O.1024807.02 | A.1024807.02.03 | Carp-2H MPLT | IMPERIAL OIL AND GAS PTY LTD | Carpentaria 2 |  | J.22.124613 | RPI | CT-CIRC | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-30 | 2022-11-30 |  | 2022-12-04 | 2022-12-12 23:59 |  | 2023-01-13 23:59 | AUS East Coast WS | JMeyer9 | 2022-12-29 12:59 | HFerdjallah |  | No |  |  |  |  | Jacob Patrick Meyer |  | 233226.45 | 2 |  |  |  | 81.3 | 50 | 100 | 75 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1024807 | O.1024807.02 | A.1024807.02.01 | Carpentaria-2 | IMPERIAL OIL AND GAS PTY LTD | Carpentaria 2 |  | J.22.110519 | RPI | CT-WBCLEAN, CT-MILLSLB,CT-FISHING | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-07-01 | 2022-07-01 |  | 2022-07-01 | 2022-08-12 23:59 |  | 2022-08-12 23:59 | AUS East Coast WS | JMeyer9 | 2022-10-12 17:10 | HFerdjallah |  | No |  |  |  |  | Samer Kanaan |  | 0 | 11 |  |  |  | 68.8 | 66.7 | 0 | 37.5 | 55 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1024805 | O.1024805.01 | A.1024805.01.05 | Q2 Well 5 | SANTOS LIMITED |  |  | J.23.008641 | RPI | CT-WBCLEAN-N2 | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2025-04-23 01:00 | 2025-04-23 01:00 | 2025-04-23 12:00 | 2025-04-23 01:00 | 2025-04-29 00:59 | 2025-04-29 12:00 | 2025-04-29 00:59 | AUS East Coast WS | JMeyer9 | 2024-05-15 10:55 | CNevarez2 |  | No |  |  |  |  | Samer Kanaan |  | 0 | 2 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 1 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1024805 | O.1024805.01 | A.1024805.01.04 | Q2 Well 4 | SANTOS LIMITED |  |  | J.23.008644 | RPI | CT-WBCLEAN-N2 | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-04-17 01:00 | 2025-04-17 01:00 | 2025-04-17 02:00 | 2025-04-17 01:00 | 2025-04-23 00:59 | 2025-04-23 12:00 | 2025-04-23 00:59 | AUS East Coast WS | JMeyer9 | 2024-05-15 10:54 | CNevarez2 |  | No |  |  |  |  | Samer Kanaan |  | 0 | 2 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 1 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1024805 | O.1024805.01 | A.1024805.01.02 | Q2 Well 2 | SANTOS LIMITED |  |  | J.23.008645 | RPI | CT-WBCLEAN-N2 | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-04-05 01:00 | 2025-04-05 01:00 | 2025-04-05 02:00 | 2025-04-05 01:00 | 2025-04-11 00:59 | 2025-04-11 12:00 | 2025-04-11 00:59 | AUS East Coast WS | JMeyer9 | 2024-05-15 10:54 | CNevarez2 |  | No |  |  |  |  | Samer Kanaan |  | 0 | 2 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 1 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1024805 | O.1024805.01 | A.1024805.01.03 | Q2 Well 3 | SANTOS LIMITED |  |  | J.23.008637 | RPI | CT-WBCLEAN-N2 | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-04-11 01:00 | 2025-04-11 01:00 | 2025-04-11 02:00 | 2025-04-11 01:00 | 2025-04-17 00:59 | 2025-04-17 12:00 | 2025-04-17 00:59 | AUS East Coast WS | JMeyer9 | 2024-05-15 10:54 | CNevarez2 |  | No |  |  |  |  | Samer Kanaan |  | 0 | 2 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 1 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1024805 | O.1024805.01 | A.1024805.01.01 | Q2 Well 1 | SANTOS LIMITED |  |  | J.23.008648 | RPI | CT-WBCLEAN-N2 | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2025-04-01 01:00 | 2025-04-01 | 2025-04-01 03:00 | 2025-04-01 | 2025-04-06 23:59 | 2025-04-07 13:00 | 2025-04-07 01:59 | AUS East Coast WS | JMeyer9 | 2024-05-15 10:53 | CNevarez2 |  | No |  |  |  |  | Samer Kanaan |  | 0 | 2 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 1 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1024745 | O.1024745.01 | A.1024745.01.05 | Reindeer Perfo PLT Resolve | SANTOS LIMITED | REINDEER 2, REINDEER 3 | REINDEER PLATFORM | J.23.032777 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-12-16 | 2023-12-16 |  | 2023-12-16 | 2024-01-08 23:59 |  | 2024-01-08 23:59 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 5 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1024745 | O.1024745.01 | A.1024745.01.02 | Reindeer Q4 2022 | SANTOS LIMITED | REINDEER 2, REINDEER 3, REINDEER 4 | REINDEER PLATFORM | J.22.110185 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-10 | 2022-11-10 |  | 2022-11-10 | 2023-01-07 23:59 |  | 2023-01-07 23:59 | New Burn WL | JDukas | 2023-12-05 08:42 | AMuhammad9 |  | No |  |  |  |  | Justin Dukas |  | 550750.5 | 5 |  | L0 - No RO |  | 91.7 | 83.3 | 100 | 100 | 92.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1024745 | O.1024745.01 | A.1024745.01.04 | Reindeer Q1 | SANTOS LIMITED | REINDEER 2, REINDEER 3 | REINDEER PLATFORM | J.23.020646 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-01-16 | 2023-01-16 | 2023-01-15 08:00 | 2023-01-16 | 2023-02-08 23:59 | 2023-02-09 | 2023-02-08 23:59 | New Burn WL | JDukas | 2023-08-03 17:47 | VOliveira5 |  | No |  |  |  |  | Justin Dukas |  | 205640 | 4 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 87.5 | 78.8 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1024745 | O.1024745.01 | A.1024745.01.03 | Reindeer Jan Activity | SANTOS LIMITED | Reindeer-2, Reindeer-3, Reindeer-4 | REINDEER PLATFORM | J.23.019251 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2023-01-21 | 2023-01-21 |  | 2023-01-21 | 2023-02-25 23:59 |  | 2023-02-25 23:59 | New Burn WL | JDukas | 2022-12-05 08:50 | JDukas |  | No |  |  |  |  | Justin Dukas |  | 0 | 5 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1024745 | O.1024745.01 | A.1024745.01.01 | Reindeer April Ops | SANTOS LIMITED | Reindeer-2, Reindeer-3, Reindeer-4 | REINDEER PLATFORM | J.22.110162 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed |  | 2022-03-30 |  | 2022-04-01 | 2022-05-06 23:59 |  |  | New Burn WL | APutra7 | 2022-10-03 10:01 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 609898 | 4 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1024088 | O.1024088.01 | A.1024088.01.19 | MB-01 | OMV NEW ZEALAND LTD | MB 01 | Rowan Gorilla VII | J.22.131658 | RPI | PS-WL-Ops | High | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-22 | 2023-01-17 |  | 2023-01-22 | 2023-02-17 |  | 2023-02-16 02:00 | New Plymouth WL | CLorenzo | 2023-05-04 16:55 | CKok3 |  | No |  |  |  |  | Ayssar Alsayed |  | 233445.3 | 8 |  | L0 - No RO |  | 91.7 | 91.7 | 0 | 100 | 85 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1024088 | O.1024088.01 | A.1024088.01.20 | MB-05C | OMV NEW ZEALAND LTD | MB 05 | Rowan Gorilla VII | J.23.021146 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress | 2023-04-01 | 2023-03-29 |  | 2023-04-01 | 2023-04-11 23:59 |  | 2023-04-11 23:59 | New Plymouth WL | CKok3 | 2023-01-30 14:55 | CKok3 |  | No |  |  |  |  | Ayssar Alsayed |  | 0 | 4 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1024088 | O.1024088.01 | A.1024088.01.17 | MB08 | OMV NEW ZEALAND LTD | MB 08 | Rowan Gorilla VII | J.23.010999 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-05 02:00 | 2022-10-25 |  | 2022-10-25 | 2022-11-01 |  | 2022-10-11 02:59 | New Plymouth WL | CLorenzo | 2022-11-25 16:16 | CLorenzo |  | No |  |  |  |  | Omar Mosleh |  | 175822.5 | 13 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Claudio Sanabria | WL Production Services
P.1024088 | O.1024088.01 | A.1024088.01.18 | MB01 | OMV NEW ZEALAND LTD | MB 01 | Rowan Gorilla VII | J.23.011000 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2023-01-09 |  | 2023-01-09 | 2023-01-16 |  |  | New Plymouth WL | CLorenzo | 2022-11-09 13:32 | CLorenzo |  | No |  |  |  |  | Omar Mosleh |  | 0 | 13 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Claudio Sanabria | WL Production Services
P.1024088 | O.1024088.01 | A.1024088.01.14 | CANCELLED | OMV NEW ZEALAND LTD |  | Rowan Gorilla VII | J.22.110456 | RPI | PS-WL-Ops | Low | Unconfirmed - 10% | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-07-24 04:00 | 2022-11-01 |  | 2022-11-01 04:00 | 2022-11-10 03:59 |  | 2022-09-13 02:59 | New Plymouth WL | CLorenzo | 2022-11-02 19:37 | CLorenzo |  | No |  |  |  | ROE WL Abu Dhabi | Omar Mosleh |  | 0 | 10 |  | L3 - Full RO |  | 66.7 | 16.7 | 0 | 0 | 25 |  | 0 |  |  |  | 0 |  |  |  | Claudio Sanabria | WL Production Services
P.1024088 | O.1024088.01 | A.1024088.01.16 | MB05C & MB06F | OMV NEW ZEALAND LTD | MB 05, MB 06 | Rowan Gorilla VII | J.22.110454 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-09-29 |  | 2022-10-03 | 2022-10-24 23:59 |  |  | New Plymouth WL | YLee25 | 2022-11-02 19:09 | CLorenzo |  | No |  |  |  | ROE WL Abu Dhabi | Omar Mosleh |  | 161322.5 | 10 |  |  |  | 83.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Claudio Sanabria | WL Production Services
P.1024088 | O.1024088.01 | A.1024088.01.13 | MB05 | OMV NEW ZEALAND LTD | MB 01, MB 05 | Rowan Gorilla VII | J.22.110452 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed |  | 2022-09-26 |  | 2022-09-26 | 2022-10-03 |  |  | New Plymouth WL | CLorenzo | 2022-10-24 11:51 | CLorenzo |  | No |  |  |  |  | Omar Mosleh |  | 295448.1 | 13 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Claudio Sanabria | WL Production Services
P.1024088 | O.1024088.01 | A.1024088.01.15 | MB-06 FSI | OMV NEW ZEALAND LTD | MB 06 | Rowan Gorilla VII | J.22.111004 | RPI | PS-WL-Ops | High | Unconfirmed - 10% | Design - PSD |  | Design Completed | In Progress | In Progress | 2022-09-02 04:00 | 2022-08-25 |  | 2022-09-02 04:00 | 2022-09-20 04:59 |  | 2022-09-20 04:59 | New Plymouth WL | CLorenzo | 2022-10-24 11:45 | CLorenzo |  | No |  |  |  | ROE WL Abu Dhabi | Omar Mosleh |  | 0 | 1 |  | L2 - Shift RO |  | 66.7 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Claudio Sanabria | WL Production Services
P.1024088 | O.1024088.01 | A.1024088.01.04 | MB-06 | OMV NEW ZEALAND LTD | MB 06 | Rowan Gorilla VII | J.22.110435 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed |  | 2022-05-17 |  | 2022-06-06 04:00 | 2022-07-01 03:59 |  |  | New Plymouth WL | CLorenzo | 2022-10-24 09:30 | CLorenzo |  | Yes |  |  |  | ROE WL Abu Dhabi | Paulo Zuliani |  | 145185.75 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Claudio Sanabria | WL Production Services
P.1024088 | O.1024088.01 | A.1024088.01.05 | July, 2022 | OMV NEW ZEALAND LTD | Maui-B6 | Rowan Gorilla VII | J.22.111003 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-06-16 |  | 2022-06-30 04:00 | 2022-07-25 03:59 |  |  | New Plymouth WL | MRony2 | 2022-10-03 17:35 | FDPSystemUser |  | Yes |  |  |  | ROE WL Abu Dhabi | Mohammad Rashed Al Rony |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ansar-Ud-Din Muhammad | WL Production Services
P.1024088 | O.1024088.01 | A.1024088.01.02 | MB-01 | OMV NEW ZEALAND LTD | Maui-B6, Maui-B1, Maui-B5 | Rowan Gorilla VII | J.22.111002 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-04-10 |  | 2022-04-15 | 2022-06-13 23:59 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 17:35 | FDPSystemUser |  | No |  |  |  |  | Paulo Zuliani |  | 0 | 10 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1024088 | O.1024088.01 | A.1024088.01.11 | MB06F FSI | OMV NEW ZEALAND LTD | Maui-B6 | Rowan Gorilla VII | J.22.110455 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-07-24 |  | 2022-07-25 | 2022-07-30 23:59 |  |  | New Plymouth WL | YLee25 | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  | ROE WL Abu Dhabi | Omar Mosleh |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Claudio Sanabria | WL Production Services
P.1024088 | O.1024088.01 | A.1024088.01.12 | MB04 (SCMT / CIS / ReSOLVE / HSD) | OMV NEW ZEALAND LTD | Maui-B4 | Rowan Gorilla VII | J.22.110450 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-09-10 |  | 2022-09-30 04:00 | 2022-10-25 03:59 |  |  | New Plymouth WL | CLorenzo | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  | ROE WL Abu Dhabi | Omar Mosleh |  | 0 | 10 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Claudio Sanabria | WL Production Services
P.1024088 | O.1024088.01 | A.1024088.01.10 | MB04 | OMV NEW ZEALAND LTD | Maui-B4 | Rowan Gorilla VII | J.22.110448 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed |  | 2022-06-17 |  | 2022-06-20 | 2022-07-04 23:59 |  |  | New Plymouth WL | YLee25 | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Omar Mosleh |  | 390959.8 | 9 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Omar Mosleh | WL Production Services
P.1024088 | O.1024088.01 | A.1024088.01.08 | Sep,22 | OMV NEW ZEALAND LTD | Maui-B6 | Rowan Gorilla VII | J.22.110443 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-08-17 |  | 2022-08-31 04:00 | 2022-09-25 03:59 |  |  | New Plymouth WL | MRony2 | 2022-10-03 16:19 | FDPSystemUser |  | Yes |  |  |  | ROE WL Abu Dhabi | Mohammad Rashed Al Rony |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ansar-Ud-Din Muhammad | WL Production Services
P.1024088 | O.1024088.01 | A.1024088.01.09 | SCMT, CIS, Resolve, Perforation | OMV NEW ZEALAND LTD | Maui-B6 | Rowan Gorilla VII | J.22.110441 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-05-18 |  | 2022-06-07 04:00 | 2022-07-02 03:59 |  |  | New Plymouth WL | ymoradi2 | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  | ROE WL Abu Dhabi | Paulo Zuliani |  | 164183.9 | 10 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Omar Mosleh | WL Production Services
P.1024088 | O.1024088.01 | A.1024088.01.06 | Aug-22 | OMV NEW ZEALAND LTD | Maui-B6 | Rowan Gorilla VII | J.22.110440 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-07-17 |  | 2022-07-31 04:00 | 2022-08-25 03:59 |  |  | New Plymouth WL | MRony2 | 2022-10-03 16:19 | FDPSystemUser |  | Yes |  |  |  | ROE WL Abu Dhabi | Mohammad Rashed Al Rony |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ansar-Ud-Din Muhammad | WL Production Services
P.1024088 | O.1024088.01 | A.1024088.01.07 | Aug,22 | OMV NEW ZEALAND LTD | Maui-B6 | Rowan Gorilla VII | J.22.110438 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-07-17 |  | 2022-07-31 04:00 | 2022-08-25 03:59 |  |  | New Plymouth WL | MRony2 | 2022-10-03 16:19 | FDPSystemUser |  | Yes |  |  |  | ROE WL Abu Dhabi | Mohammad Rashed Al Rony |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ansar-Ud-Din Muhammad | WL Production Services
P.1024088 | O.1024088.01 | A.1024088.01.03 | MB-05 | OMV NEW ZEALAND LTD | Maui-B6 | Rowan Gorilla VII | J.22.110436 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-07-10 |  | 2022-07-15 | 2022-09-12 23:59 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  |  | Paulo Zuliani |  | 0 | 10 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1024088 | O.1024088.01 | A.1024088.01.01 | Maui-B6 | OMV NEW ZEALAND LTD | MB 06 | Rowan Gorilla VII | J.22.110433 | RPI | PS-WL-Ops | High | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-22 | 2022-01-16 |  | 2022-03-22 | 2022-05-27 22:59 |  | 2022-07-20 22:59 | New Plymouth WL | VOliveira5 | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  | ROE WL Abu Dhabi | Paulo Zuliani |  | 1152662.34 | 10 |  | L1 - Support RO |  | 83.3 | 83.3 | 0 | 87.5 | 76.3 |  | 0 |  |  |  | 0 |  |  |  | Claudio Sanabria | WL Production Services
P.1023577 | O.1023577.01 | A.1023577.01.01 | Nano sealant Squeeze Job TGS4A | AGI TUBRIDGI PTY LIMITED | TGS 4A |  | J.23.031531 | WCF | REM-SQ | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-04 | 2023-02-04 |  | 2023-02-04 | 2023-02-10 23:59 |  | 2023-03-05 23:59 | AUS West Coast WS | GSingh54 | 2023-03-22 09:39 | NKhoa |  | Yes |  |  |  |  | Gaurav Kumar Singh |  | 0 | 1 |  |  |  | 81.3 | 50 | 0 | 25 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1022464 | O.1022464.01 | A.1022464.01.01 | Fairview | TRI-STAR OPCO PTY LTD |  |  | J.22.110484 | RPS | FRAC-PROP | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-04-06 | 2022-04-06 |  | 2022-04-06 | 2022-04-20 23:59 |  | 2022-04-20 23:59 | AUS East Coast WS | SKanaan | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1021969 | O.1021969.01 | A.1021969.01.07 | TCP Inventory Sale | ENI AUSTRALIA LIMITED |  | Valaris MS-1 | J.21.108349 | RPI | TCP-SALE | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2021-11-25 |  | 2021-11-25 | 2021-12-25 23:59 |  |  | APG TS | GRoxo | 2022-10-03 06:29 | FDPSystemUser |  | No |  |  |  |  | Ferly Komul |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TCP - Tubing-Conveyed Perforation
P.1021969 | O.1021969.01 | A.1021969.01.04 | ENI WBT Well 4 | ENI AUSTRALIA LIMITED | Woollybutt | Valaris MS-1 |  | RPI | TSWT-NOSEPNOVX-JOB | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-03-01 | 2022-02-26 |  | 2022-03-01 | 2022-03-25 23:59 |  | 2022-03-23 23:59 | APG TS | GRoxo | 2022-09-03 05:59 | walfaro |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Ferly Komul |  | 0 | 1 |  | L0 - No RO | [7 empty] | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1021969 | O.1021969.01 | A.1021969.01.03 | ENI WBT Well 3 | ENI AUSTRALIA LIMITED | Woollybutt | Valaris MS-1 |  | RPI | TSWT-NOSEPNOVX-JOB | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-02-01 | 2022-01-26 |  | 2022-02-01 | 2022-02-25 23:59 |  | 2022-02-23 23:59 | APG TS | GRoxo | 2022-09-03 05:59 | walfaro |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Ferly Komul |  | 0 | 1 |  | L0 - No RO | [7 empty] | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1021969 | O.1021969.01 | A.1021969.01.05 | ENI WBT Well 5 | ENI AUSTRALIA LIMITED | Woollybutt | Valaris MS-1 |  | RPI | TSWT-NOSEPNOVX-JOB | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-04-28 |  | 2022-05-01 | 2022-05-25 23:59 |  |  | APG TS | GRoxo | 2022-09-03 05:59 | walfaro |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Ferly Komul |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1021969 | O.1021969.01 | A.1021969.01.02 | ENI WBT Well 2 | ENI AUSTRALIA LIMITED | Woollybutt | Valaris MS-1 |  | RPI | TSWT-NOSEPNOVX-JOB | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-01-01 | 2021-12-14 |  | 2022-01-01 | 2022-01-25 23:59 |  | 2022-01-23 23:59 | APG TS | GRoxo | 2022-09-03 05:59 | walfaro |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Ferly Komul |  | 57577.54 | 1 |  | L0 - No RO | [7 empty] | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1021969 | O.1021969.01 | A.1021969.01.06 | ENI WBT Well 6 | ENI AUSTRALIA LIMITED | Woollybutt | Valaris MS-1 |  | RPI | TSWT-NOSEPNOVX-JOB | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-05-29 |  | 2022-06-01 | 2022-06-25 23:59 |  |  | APG TS | GRoxo | 2022-09-03 05:59 | walfaro |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Ferly Komul |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1021969 | O.1021969.01 | A.1021969.01.01 | Design and Tickets Correction | ENI AUSTRALIA LIMITED | Woollybutt | Valaris MS-1 |  | RPI | TSWT-NOSEPNOVX-JOB | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-11-21 | 2021-10-15 |  | 2021-11-24 | 2022-02-26 23:59 |  | 2022-02-23 23:59 | APG TS | GRoxo | 2022-03-02 13:33 | fkomul |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Ferly Komul |  | 32000 | 1 |  | L0 - No RO | [7 empty] | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1021539 | O.1021539.01 | A.1021539.01.02 | Santos Barossa TCP Operation Contingency | SANTOS NA BAROSSA PTY LTD | BR S2 1 | Valaris MS-1 | J.22.109465 | RPI | TCP-PERM-JOB | High | Confirmed | Prepare - Mob |  | Not Required | Design Completed | Design Completed |  | 2022-04-01 | 2024-09-28 08:00 | 2024-09-29 | 2025-09-06 23:59 | 2025-09-07 |  | APG TS | RWallis | 2025-08-30 11:06 | ZGao2 |  | No |  |  |  |  | Yudha Swara |  | 20400 | 1 |  |  |  | 87.5 | 25 | 0 | 25 | 41.3 |  | 3 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP - Tubing-Conveyed Perforation
P.1021539 | O.1021539.01 | A.1021539.01.01 | TCP Job Design | SANTOS NA BAROSSA PTY LTD | BR-S2 1 (BS19) | Valaris MS-1 | J.22.109447 | RPI | TCP-RENTAL | Medium | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-02-28 |  | 2022-07-12 | 2022-09-15 23:59 |  |  | APG TS | GRoxo | 2023-02-13 09:52 | RWallis |  | No |  |  |  |  | Yudha Swara |  | 595686 | 1 |  |  |  | 50 | 33.3 | 100 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TCP - Tubing-Conveyed Perforation
P.1021296 | O.1021296.01 | A.1021296.01.01 | NEWCREST_Thru Bit Logging | NEWCREST MINING LTD |  |  | J.21.108873 | RPE | ES-CH-Ops | Low | Unconfirmed - 10% | Design - CEC |  | Not Started | Not Started | In Progress |  | 2021-11-01 |  | 2021-11-03 | 2021-11-25 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:54 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | James Cade |  | 0 | 0 |  | L1 - Support RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1021161 | O.1021161.01 | A.1021161.01.08 | WBT-1 Operation | ENI AUSTRALIA LIMITED | WBT-1ST2 | ENSCO MS-1 | J.22.110134 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-02-05 |  | 2022-02-05 | 2022-03-02 23:59 |  |  | New Burn WL | JDukas | 2022-10-03 09:58 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 305814 | 10 |  |  |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1021161 | O.1021161.01 | A.1021161.01.07 | ENI BLK Tip_Aug | ENI AUSTRALIA LIMITED |  | ENSCO MS-1 | J.22.110115 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-08-20 |  | 2022-08-24 | 2022-10-09 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:55 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 4 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1021161 | O.1021161.01 | A.1021161.01.06 | WBT 4 P&A | ENI AUSTRALIA LIMITED |  | ENSCO MS-1 | J.21.108884 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2021-12-23 |  | 2021-12-25 | 2022-01-12 23:59 |  |  | New Burn WL | JDukas | 2022-10-03 09:55 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 11 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1021161 | O.1021161.01 | A.1021161.01.05 | Scalybutt 1 P&A | ENI AUSTRALIA LIMITED |  | ENSCO MS-1 | J.22.110114 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-03-04 |  | 2022-03-06 | 2022-03-24 23:59 |  |  | New Burn WL | JDukas | 2022-10-03 09:55 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 11 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1021161 | O.1021161.01 | A.1021161.01.04 | WBT-4H, WBT1 and SBT-1 operation | ENI AUSTRALIA LIMITED | WBT-4ST1, WBT-2A ST2ST3, WBT-1ST2, SBT-1 | ENSCO MS-1 | J.21.108883 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-12-19 18:00 |  | 2021-12-22 | 2022-02-28 23:59 |  |  | New Burn WL | JDukas | 2022-10-03 09:55 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 305814 | 10 |  |  |  | 83.3 | 66.7 | 0 | 50 | 60 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1021161 | O.1021161.01 | A.1021161.01.03 | Cancelled ops 2 | ENI AUSTRALIA LIMITED |  | ENSCO MS-1 | J.21.108879 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-11-12 |  | 2021-11-12 | 2021-12-05 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:54 | FDPSystemUser |  | No |  |  |  |  | James Cade |  | 0 | 0 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1021161 | O.1021161.01 | A.1021161.01.02 | Cancelled OPS | ENI AUSTRALIA LIMITED |  | ENSCO MS-1 | J.21.108878 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-10-13 |  | 2021-10-13 | 2021-11-05 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:54 | FDPSystemUser |  | No |  |  |  |  | James Cade |  | 0 | 5 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1021161 | O.1021161.01 | A.1021161.01.01 | WBT WBT-2 well | ENI AUSTRALIA LIMITED | WBT-2A ST2ST3 | ENSCO MS-1 | J.21.108870 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-10-15 |  | 2021-11-10 | 2021-12-10 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:53 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 305814 | 12 |  |  |  | 91.7 | 50 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1021126 | O.1021126.02 | A.1021126.02.01 | Vali-2 | VINTAGE ENERGY LTD | VALI-2 | RIGLESS - AUSTRALIA | J.22.110582 | RPI | CT-LIFT,CT-WBCLEAN, CT-MILLSLB,CT-FISHING | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-31 23:00 | 2022-04-01 |  | 2022-04-01 | 2022-04-14 23:59 |  | 2022-04-14 21:59 | AUS East Coast WS | YHou5 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1021126 | O.1021126.02 | A.1021126.02.02 | Vali-3 | VINTAGE ENERGY LTD | VALI-3 | RIGLESS - AUSTRALIA | J.22.110577 | RPI | CT-LIFT,CT-WBCLEAN, CT-MILLSLB,CT-FISHING | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-09 23:00 | 2022-04-09 23:00 |  | 2022-04-09 23:00 | 2022-04-17 22:59 |  | 2022-04-17 22:59 | AUS East Coast WS | YHou5 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1021126 | O.1021126.01 | A.1021126.01.04 | Vali-3 | VINTAGE ENERGY LTD | VALI-3 | RIGLESS - AUSTRALIA | J.22.110553 | RPS | FRAC-PROP | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-16 | 2022-04-15 23:00 |  | 2022-04-15 23:00 | 2022-04-28 21:59 |  | 2022-05-09 23:59 | AUS East Coast WS | radinegara | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Ramadhani Adi Negara |  | 0 | 6 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1021126 | O.1021126.01 | A.1021126.01.01 | Vali-2 | VINTAGE ENERGY LTD | VALI-2 | RIGLESS - AUSTRALIA | J.22.110487 | RPS | FRAC-PROP | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-02 | 2022-04-01 |  | 2022-04-01 | 2022-06-01 22:59 |  | 2022-04-17 22:59 | AUS East Coast WS | YHou5 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Ramadhani Adi Negara |  | 77685.28 | 7 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1021126 | O.1021126.01 | A.1021126.01.03 | Well #2 | VINTAGE ENERGY LTD |  | RIGLESS - AUSTRALIA | J.22.110485 | RPS | FRAC-PROP | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-01-29 | 2022-01-29 |  | 2022-01-29 | 2022-02-05 23:59 |  | 2022-02-05 23:59 | AUS East Coast WS | YHou5 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 7 |  |  |  | 40.6 | 8.3 | 0 | 0 | 18.8 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1021126 | O.1021126.01 | A.1021126.01.02 | Well #1 | VINTAGE ENERGY LTD |  | RIGLESS - AUSTRALIA | J.22.110482 | RPS | FRAC-PROP | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-01-20 | 2022-01-20 |  | 2022-01-20 | 2022-01-27 23:59 |  | 2022-01-27 23:59 | AUS East Coast WS | YHou5 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 7 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1021122 | O.1021122.01 | A.1021122.01.11 | Well#1 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Well #1 | RIGLESS - AUSTRALIA | J.23.008649 | RPI | CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-08-18 23:00 | 2025-08-27 23:00 |  | 2025-08-27 23:00 | 2025-08-31 22:59 |  | 2025-08-22 22:59 | AUS East Coast WS | JMeyer9 | 2024-10-25 15:04 | CNevarez2 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 2 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1021122 | O.1021122.01 | A.1021122.01.12 | Well#2 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.008656 | RPI | CT-CIRC | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-08-21 | 2025-08-30 | 2025-08-10 | 2025-08-30 | 2025-09-02 23:59 | 2025-08-14 | 2025-08-24 23:59 | AUS East Coast WS | SKanaan | 2024-05-15 10:56 | CNevarez2 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 2 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1021122 | O.1021122.01 | A.1021122.01.07 | Q2 Well 2 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA NORTH 248 | RIGLESS - AUSTRALIA | J.23.008630 | RPI | CT-WBCLEAN-N2 | Medium | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress | 2023-04-13 | 2025-09-08 23:00 | 2025-08-18 23:00 | 2025-09-08 23:00 | 2025-09-13 22:59 | 2025-08-24 23:00 | 2025-09-04 23:59 | AUS East Coast WS | JMeyer9 | 2024-05-15 10:56 | CNevarez2 |  | No |  |  |  |  | Samer Kanaan |  | 0 | 5 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 2 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1021122 | O.1021122.01 | A.1021122.01.06 | Q2 Well 1 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA NORTH 248 | RIGLESS - AUSTRALIA | J.23.008640 | RPI | CT-WBCLEAN-N2 | Medium | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2023-04-07 | 2025-09-02 23:00 | 2025-08-12 23:00 | 2025-09-02 23:00 | 2025-09-07 22:00 | 2025-08-18 23:00 | 2025-08-29 23:59 | AUS East Coast WS | JMeyer9 | 2024-05-15 10:56 | CNevarez2 |  | No |  |  |  |  | Samer Kanaan |  | 0 | 5 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 2 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1021122 | O.1021122.01 | A.1021122.01.09 | CMN83 - Frac | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Combabula North 83 | RIGLESS - AUSTRALIA | J.21.109611 | RPS | FRAC-MATSAL | Low | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-12-16 |  | 2021-12-16 | 2021-12-22 23:59 |  |  | AUS East Coast WS | SKanaan | 2022-10-03 15:34 | FDPSystemUser |  | No |  |  |  |  | Jacob Patrick Meyer |  | 23685.47 | 1 |  |  |  | 62.5 | 33.3 | 100 | 50 | 55 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1021122 | O.1021122.01 | A.1021122.01.04 | CFE055 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CLIFFORD EAST 55 | RIGLESS - AUSTRALIA | J.22.111001 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-22 23:00 | 2021-11-27 23:00 |  | 2022-01-22 23:00 | 2022-01-26 22:59 |  | 2022-01-26 22:59 | AUS East Coast WS | YHou5 | 2022-10-03 15:34 | FDPSystemUser |  | No |  |  |  |  | Yuxiao Hou |  | 23684.79 | 2 |  |  |  | 81.3 | 50 | 0 | 62.5 | 60 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1021122 | O.1021122.01 | A.1021122.01.10 | CMN140 Frac | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA NORTH 140 | RIGLESS - AUSTRALIA | J.22.110558 | RPS | FRAC-MATSAL | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2022-01-15 |  | 2022-01-15 | 2022-01-21 23:59 |  |  | AUS East Coast WS | SKanaan | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 1 |  |  |  | 56.3 | 33.3 | 100 | 25 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1021122 | O.1021122.01 | A.1021122.01.08 | CMN248 - Frac | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Combabula North 248 | RIGLESS - AUSTRALIA | J.21.109315 | RPS | FRAC-MATSAL | Low | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-12-11 |  | 2021-12-11 | 2021-12-12 23:59 |  |  | AUS East Coast WS | SKanaan | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Jacob Patrick Meyer |  | 25008.33 | 0 |  |  |  | 62.5 | 33.3 | 100 | 50 | 55 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1021122 | O.1021122.01 | A.1021122.01.01 | CMN248 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Combabula North 248 | RIGLESS - AUSTRALIA | J.21.109288 | RPI | CT-WBCLEAN-N2 | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-08 23:00 | 2021-11-20 23:00 |  | 2021-11-20 23:00 | 2021-12-12 22:59 |  | 2021-09-24 22:59 | AUS East Coast WS | YHou5 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Yuxiao Hou |  | 30849.96 | 2 |  |  |  | 81.3 | 50 | 0 | 50 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1021122 | O.1021122.01 | A.1021122.01.05 | Well #5 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.21.109280 | RPI | CT-WBCLEAN | Low | Cancelled | Close - PSD |  | Not Started | Design Completed | In Progress |  | 2021-12-26 23:00 |  | 2021-12-26 23:00 | 2021-12-30 22:59 |  |  | AUS East Coast WS | YHou5 | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 2 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1021122 | O.1021122.01 | A.1021122.01.03 | CMN140 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Combabula North 140 | RIGLESS - AUSTRALIA | J.22.110479 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-16 23:00 | 2021-11-28 23:00 |  | 2022-01-17 | 2022-01-22 23:59 |  | 2022-01-22 22:59 | AUS East Coast WS | YHou5 | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Yuxiao Hou |  | 23684.79 | 2 |  |  |  | 81.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1021122 | O.1021122.01 | A.1021122.01.02 | CMN83 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Combabula North 83 | RIGLESS - AUSTRALIA | J.21.109271 | RPI | CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-16 23:00 | 2021-11-25 23:00 |  | 2021-12-16 23:00 | 2021-12-23 22:59 |  | 2021-12-23 22:59 | AUS East Coast WS | YHou5 | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 2 |  |  |  | 68.8 | 50 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1021059 | O.1021059.01 | A.1021059.01.01 | Skua 10 | JADESTONE ENERGY (EAGLE) PTY LTD | Montara Project | Valaris 107 |  | RPI | TSWT-FLOWBACK-JOB | High | Confirmed | Prepare - Mob |  | Design Completed | Not Required | In Progress | 2021-09-23 10:11 | 2021-08-20 |  | 2021-11-04 | 2021-12-02 23:59 |  | 2021-11-11 23:59 | APG TS | GRoxo | 2022-09-03 05:59 | walfaro |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Gabriela Soter Roxo Teckemeier |  | 337434.15 | 1 |  | L0 - No RO | [7 empty] | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1021059 | O.1021059.01 | A.1021059.01.02 | Skua 11 | JADESTONE ENERGY (EAGLE) PTY LTD | Montara Project | Valaris 107 |  | RPI | TSWT-FLOWBACK-JOB | High | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2021-09-17 10:11 | 2021-09-23 |  | 2021-09-28 | 2021-10-02 23:59 |  | 2021-10-26 23:59 | APG TS | GRoxo | 2022-09-03 05:59 | walfaro |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Gabriela Soter Roxo Teckemeier |  | 0 | 1 |  | L0 - No RO | [7 empty] | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1020894 | O.1020894.07 | A.1020894.07.04 | Spartan-2_7in Liner Cementing | SANTOS LIMITED | Spartan-2 | Noble Tom Prosser | J.22.110836 | WCF | PRI-LIN, CMT-MATSAL | Low | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress | 2022-11-18 | 2022-11-17 23:00 |  | 2022-11-18 | 2022-11-19 |  | 2022-11-19 | AUS West Coast WS | HNarainasamy | 2022-10-31 13:16 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.07 | A.1020894.07.02 | Spartan-2_13-3/8" Surface Casing | SANTOS LIMITED | Spartan-2 | Noble Tom Prosser | J.22.110817 | WCF | PRI-SURF, CMT-MATSAL | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-11-01 | 2022-11-07 |  | 2022-11-08 12:00 | 2022-11-09 11:59 |  | 2022-11-30 23:59 | AUS West Coast WS | HNarainasamy | 2022-10-31 13:12 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.07 | A.1020894.07.01 | Spartan-2_30" Conductor | SANTOS LIMITED | Spartan-2 | Noble Tom Prosser | J.22.110995 | WCF | PRI-COND, CMT-MATSAL | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-11-02 | 2022-11-02 20:00 |  | 2022-11-03 20:00 | 2022-11-04 20:00 |  | 2022-12-01 23:59 | AUS West Coast WS | HNarainasamy | 2022-10-31 13:10 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.07 | A.1020894.07.03 | Spartan-2_9-5/8in Liner Cementing | SANTOS LIMITED | Spartan-2 | Noble Tom Prosser | J.22.110830 | WCF | PRI-LONG, CMT-MATSAL | High | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-30 | 2022-11-09 12:00 |  | 2022-11-10 08:00 | 2022-11-11 07:59 |  | 2022-11-28 23:59 | AUS West Coast WS | HNarainasamy | 2022-10-26 12:57 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.06 | A.1020894.06.10 | Services - Personnel & Equipment - Sept 2022 | SANTOS LIMITED | HARRIET A1 (HA 01) | Noble Tom Prosser | J.22.110796 | WCF | CMT-PERS,CMT-EQPRNT | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-08-21 |  | 2022-08-21 | 2022-09-17 18:00 |  |  | AUS West Coast WS | HNarainasamy | 2022-11-13 12:21 | JAhmed8 |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 235647.25 | 1 |  |  |  | 87.5 | 66.7 | 100 | 50 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.06 | A.1020894.06.13 | Services - Personnel and Equipment - Dec 2022 | SANTOS LIMITED | Spartan-2 | Noble Tom Prosser | J.22.117576 | WCF | CMT-PERS,CMT-EQPRNT | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-11-21 |  | 2022-11-21 | 2022-12-21 23:59 |  |  | AUS West Coast WS | HNarainasamy | 2022-10-26 13:34 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.06 | A.1020894.06.12 | Services - Personnel & Equipment - Nov 2022 | SANTOS LIMITED | Spartan-2 | Noble Tom Prosser | J.22.110804 | WCF | CMT-PERS,CMT-EQPRNT | Low | Cancelled | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-10-21 |  | 2022-10-21 | 2022-11-20 23:59 |  |  | AUS West Coast WS | HNarainasamy | 2022-10-26 13:33 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.06 | A.1020894.06.11 | Services - Personnel & Equipment - Oct 2022 | SANTOS LIMITED | Spartan-2 | Noble Tom Prosser | J.22.110783 | WCF | CMT-PERS,CMT-EQPRNT | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-09-17 18:01 |  | 2022-09-17 18:01 | 2022-10-20 23:59 |  |  | AUS West Coast WS | HNarainasamy | 2022-10-21 16:22 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 206213.74 | 1 |  |  |  | 87.5 | 66.7 | 100 | 50 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.06 | A.1020894.06.08 | Services - Personnel & Equipment - July 2022 | SANTOS LIMITED | NORTH ALKIMOS 2H (NA02) | Noble Tom Prosser | J.22.110990 | WCF | CMT-PERS,CMT-EQPRNT | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-06-21 |  | 2022-06-21 | 2022-07-20 23:59 |  |  | AUS West Coast WS | HNarainasamy | 2022-10-03 12:33 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 193585.4 | 1 |  |  |  | 87.5 | 50 | 100 | 50 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.06 | A.1020894.06.05 | Services - Personnel & Equipment - April 2022 | SANTOS LIMITED | PAVO-1, APUS-1 | Noble Tom Prosser | J.22.110989 | WCF | CMT-PERS, PRI-COND | Medium | Operationally Complete | Close - PSD |  | Not Required | Not Required | Design Completed |  | 2022-03-21 |  | 2022-03-21 | 2022-04-20 23:59 |  |  | AUS West Coast WS | HNarainasamy | 2022-10-03 12:33 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 171536.59 | 1 |  |  |  | 68.8 | 16.7 | 0 | 50 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.06 | A.1020894.06.04 | Services - Personnel & Equipment - March 2022 - Pavo-1 | SANTOS LIMITED | PAVO-1 | Noble Tom Prosser | J.22.110988 | WCF | CMT-PERS,CMT-EQPRNT, PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-02-21 |  | 2022-02-21 | 2022-03-20 23:59 |  |  | AUS West Coast WS | HNarainasamy | 2022-10-03 12:33 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 171298.04 | 1 |  |  |  | 62.5 | 16.7 | 0 | 50 | 40 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.06 | A.1020894.06.02 | Services - Personnel & Equipment - January 2022 | SANTOS LIMITED | DANCER-1 | Noble Tom Prosser | J.21.109610 | WCF | CMT-PERS,CMT-EQPRNT | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2021-12-21 |  | 2021-12-21 | 2022-01-20 23:59 |  |  | AUS West Coast WS | HNarainasamy | 2022-10-03 12:33 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 165492.58 | 1 |  |  |  | 87.5 | 66.7 | 100 | 50 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.06 | A.1020894.06.07 | Services - Personnel & Equipment - June 2022 | SANTOS LIMITED | HARRIET A11 (HA 11), Harriet Alpha-8H1 (HA08), HARRIET A1 (HA 01), NORTH ALKIMOS 2H (NA02), GUDRUN 2 (GD02) | Noble Tom Prosser | J.22.110794 | WCF | CMT-PERS,CMT-EQPRNT | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-05-21 |  | 2022-05-21 | 2022-06-20 23:59 |  |  | AUS West Coast WS | HNarainasamy | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 190366.58 | 1 |  |  |  | 87.5 | 66.7 | 100 | 50 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.06 | A.1020894.06.01 | Services - Personnel and Equipment - December 2021 | SANTOS LIMITED | DANCER-1 | Noble Tom Prosser | J.21.109401 | WCF | CMT-PERS,CMT-EQPRNT | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2021-12-02 |  | 2021-12-02 | 2021-12-20 23:59 |  |  | AUS West Coast WS | HNarainasamy | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 86569.98 | 1 |  |  |  | 87.5 | 66.7 | 100 | 50 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.06 | A.1020894.06.09 | Services - Personnel & Equipment - August 2022 | SANTOS LIMITED | Harriet Alpha-8H1 (HA08) | Noble Tom Prosser | J.22.110786 | WCF | CMT-PERS,CMT-EQPRNT | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-07-21 |  | 2022-07-21 | 2022-08-20 23:59 |  |  | AUS West Coast WS | HNarainasamy | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 193249.58 | 1 |  |  |  | 87.5 | 66.7 | 100 | 50 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.06 | A.1020894.06.03 | Services - Personnel & Equipment - February 2022 | SANTOS LIMITED | DANCER-1 | Noble Tom Prosser | J.22.110785 | WCF | CMT-PERS,CMT-EQPRNT | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-01-21 |  | 2022-01-21 | 2022-02-20 23:59 |  |  | AUS West Coast WS | HNarainasamy | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 178391.33 | 1 |  |  |  | 87.5 | 66.7 | 100 | 50 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.06 | A.1020894.06.06 | Services - Personnel & Equipment - May 2022 | SANTOS LIMITED | Harriet Alpha-3 (HA03) | Noble Tom Prosser |  | WCF | CMT-PERS,CMT-EQPRNT | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-04-21 |  | 2022-04-21 | 2022-05-20 23:59 |  |  | AUS West Coast WS | HNarainasamy | 2022-05-24 14:11 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 180616.4 | 1 |  |  |  | 87.5 | 50 | 100 | 75 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.32 | HA01 - 13-3/8" Bridge Plug | SANTOS LIMITED | HARRIET A1 (HA 01) | Noble Tom Prosser | J.22.111000 | WCF | CMT-TOOLS | Medium | Confirmed | Design - CEC |  | Design Completed | Not Required | Design Completed | 2022-09-03 17:00 | 2022-09-03 |  | 2022-09-03 17:00 | 2022-09-03 22:00 |  | 2022-09-03 22:00 | AUS West Coast WS | HNarainasamy | 2022-10-03 12:34 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.27 | HA11_13-3/8in Bridge Plug | SANTOS LIMITED | HARRIET A11 (HA 11) | Noble Tom Prosser | J.22.110999 | WCF | CMT-TOOLS | Medium | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2022-08-19 02:00 | 2022-08-18 10:00 |  | 2022-08-19 02:00 | 2022-08-19 07:00 |  | 2022-08-19 07:00 | AUS West Coast WS | HNarainasamy | 2022-10-03 12:34 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.24 | HA08-9-5/8" DLT Packer for Pressure Test | SANTOS LIMITED | HARRIET A8H1 (HA 08H1) | Noble Tom Prosser | J.22.110998 | WCF | CMT-TOOLS | Medium | Confirmed | Design - CEC |  | Design Completed | Not Required | Design Completed | 2022-08-25 23:00 | 2022-08-25 18:00 |  | 2022-08-25 23:00 | 2022-08-26 04:00 |  | 2022-08-26 04:00 | AUS West Coast WS | HNarainasamy | 2022-10-03 12:34 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.22 | BM03 - Plug #1-2-3 | SANTOS LIMITED | Bambra-3 | Noble Tom Prosser | J.22.110997 | WCF | REM-PA, CMT-MATSAL | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-25 | 2022-09-07 |  | 2022-09-08 | 2022-09-08 12:00 |  | 2022-08-25 12:00 | AUS West Coast WS | HNarainasamy | 2022-10-03 12:34 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.20 | GD02 - Plug #3 | SANTOS LIMITED | GUDRUN 2 (GD02) | Noble Tom Prosser | J.22.110996 | WCF | REM-PA, CMT-MATSAL | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | Design Completed | 2022-08-16 20:00 | 2022-08-30 12:00 |  | 2022-08-30 20:00 | 2022-08-31 08:00 |  | 2022-08-17 08:00 | AUS West Coast WS | HNarainasamy | 2022-10-03 12:34 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.14 | HA-08_DLT_Casing Leak Isolation | SANTOS LIMITED | HARRIET A8H1 (HA 08H1) | Noble Tom Prosser | J.22.110994 | WCF | CMT-TOOLS | Medium | Unconfirmed - 50% | Design - CEC |  | Design Completed | Not Required | In Progress | 2022-08-23 03:00 | 2022-08-23 12:00 |  | 2022-08-23 19:00 | 2022-08-24 18:59 |  | 2022-08-24 02:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 12:34 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.05 | HA-01_Plug #1 - Plan A | SANTOS LIMITED | HARRIET A1 (HA 01) | Noble Tom Prosser | J.22.110992 | WCF | REM-PA, CMT-MATSAL | Medium | Confirmed | Design - PSD |  | Design Completed | Design Completed | Design Completed | 2022-06-18 03:00 | 2022-06-18 12:00 |  | 2022-06-19 06:00 | 2022-06-19 18:00 |  | 2022-06-20 02:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 12:33 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.02 | HA-05_Plug #1-2 | SANTOS LIMITED | HARRIET A5 ST1 (HA 05 ST1) | Noble Tom Prosser | J.22.110991 | WCF | REM-PA, CMT-MATSAL | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-05-07 21:00 | 2022-05-20 |  | 2022-05-21 21:00 | 2022-05-22 09:00 |  | 2022-05-08 09:00 | AUS West Coast WS | HNarainasamy | 2022-10-03 12:33 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.28 | HA08_9-5/8" Bridge Plug | SANTOS LIMITED | NORTH ALKIMOS 2H (NA02) | Noble Tom Prosser | J.22.110857 | WCF | CMT-TOOLS | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2022-08-24 20:00 | 2022-08-24 04:00 |  | 2022-08-24 20:00 | 2022-08-25 01:00 |  | 2022-08-25 01:00 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:39 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.33 | HA01_13-3/8" DLT Packer | SANTOS LIMITED | HARRIET A1 (HA 01) | Noble Tom Prosser | J.22.110854 | WCF | CMT-TOOLS | Medium | Unconfirmed - 50% | Design - CEC |  | Design Completed | Not Required | Design Completed | 2022-09-02 08:00 | 2022-09-02 21:00 |  | 2022-09-03 10:00 | 2022-09-03 16:00 |  | 2022-09-02 14:00 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.30 | HA-11_13-3/8in DLT Packer for Pressure Test | SANTOS LIMITED | HARRIET A11 (HA 11) | Noble Tom Prosser | J.22.110853 | WCF | CMT-TOOLS | Medium | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2022-08-19 18:00 | 2022-08-19 12:00 |  | 2022-08-20 10:00 | 2022-08-20 16:00 |  | 2022-08-20 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.31 | GD02_13-38in DLT Packer | SANTOS LIMITED | GUDRUN 2 (GD02) | Noble Tom Prosser | J.22.110848 | WCF | CMT-TOOLS | Medium | Unconfirmed - 50% | Design - CEC |  | Design Completed | Not Required | In Progress | 2022-08-31 11:00 | 2022-09-01 |  | 2022-09-01 13:00 | 2022-09-01 19:00 |  | 2022-08-31 17:00 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.23 | HA08 - Plug 2 | SANTOS LIMITED | HARRIET A8H1 (HA 08H1) | Noble Tom Prosser | J.22.110845 | WCF | REM-PA, CMT-MATSAL | Medium | Confirmed | Design - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-24 | 2022-08-24 |  | 2022-08-24 15:00 | 2022-08-24 22:00 |  | 2022-08-24 22:00 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.29 | GD-02_13-3/8" Bridge Plug | SANTOS LIMITED | GUDRUN 2 (GD02) | Noble Tom Prosser | J.22.110846 | WCF | CMT-TOOLS | Medium | Confirmed | Design - CEC |  | Design Completed | Not Required | Design Completed | 2022-08-30 16:00 | 2022-08-30 08:00 |  | 2022-08-30 16:00 | 2022-08-30 21:00 |  | 2022-08-30 21:00 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.18 | HA01 - Plug #3 | SANTOS LIMITED | HARRIET A1 (HA 01) | Noble Tom Prosser | J.22.110839 | WCF | REM-PA, CMT-MATSAL | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | Design Completed | 2022-08-19 17:00 | 2022-09-02 |  | 2022-09-02 17:00 | 2022-09-03 05:00 |  | 2022-08-20 05:00 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.25 | NA02 - 9-5/8" Bridge Plug | SANTOS LIMITED | NORTH ALKIMOS 2H (NA02) | Noble Tom Prosser | J.22.110838 | WCF | CMT-TOOLS | Medium | Cancelled | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-06-23 16:00 | 2022-06-23 |  | 2022-06-23 16:00 | 2022-06-24 |  | 2022-06-24 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.26 | NA02_Plug #1B_Section Mill | SANTOS LIMITED | NORTH ALKIMOS 2H (NA02) | Noble Tom Prosser | J.22.110835 | WCF | REM-PA, CMT-MATSAL | Medium | Confirmed | Design - PSD |  | Design Completed | Design Completed | In Progress | 2022-07-04 12:00 | 2022-07-04 12:00 |  | 2022-07-05 22:00 | 2022-07-06 10:00 |  | 2022-07-07 11:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.17 | HA05 - Plug #3 | SANTOS LIMITED | HARRIET A5 ST1 (HA 05 ST1) | Noble Tom Prosser | J.22.110834 | WCF | REM-PA, CMT-MATSAL | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | Design Completed | 2022-08-15 15:00 | 2022-08-15 18:00 |  | 2022-08-16 15:00 | 2022-08-17 03:00 |  | 2022-08-18 14:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.16 | HA11 - Plug #3 | SANTOS LIMITED | HARRIET A11 (HA 11) | Noble Tom Prosser | J.22.110828 | WCF | REM-PA, CMT-MATSAL | Medium | Confirmed | Design - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-18 | 2022-08-19 10:00 |  | 2022-08-19 12:00 | 2022-08-19 18:00 |  | 2022-08-20 17:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.19 | NA02 - Plug #3 | SANTOS LIMITED | NORTH ALKIMOS 2H (NA02) | Noble Tom Prosser | J.22.110822 | WCF | REM-PA, CMT-MATSAL | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | Design Completed | 2022-08-11 08:00 | 2022-08-11 12:00 |  | 2022-08-12 16:00 | 2022-08-13 04:00 |  | 2022-08-14 07:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.15 | HA08 - Plug #3 | SANTOS LIMITED | HARRIET A8H1 (HA 08H1) | Noble Tom Prosser | J.22.110815 | WCF | REM-PA, CMT-MATSAL | Medium | Confirmed | Design - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-26 12:00 | 2022-08-26 |  | 2022-08-27 12:00 | 2022-08-28 |  | 2022-08-29 11:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.08 | NA-02_Plug #1 - PWC Cementing with Hydrawell | SANTOS LIMITED | NORTH ALKIMOS 2H (NA02) | Noble Tom Prosser | J.22.110807 | WCF | REM-SQ, CMT-MATSAL | Medium | Confirmed | Design - PSD |  | Design Completed | Design Completed | Design Completed | 2022-06-25 06:00 | 2022-06-24 12:00 |  | 2022-06-25 20:00 | 2022-06-26 08:00 |  | 2022-06-28 05:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.10 | GD-02_Plug #1 - PWC | SANTOS LIMITED | GUDRUN 2 (GD02) | Noble Tom Prosser | J.22.110806 | WCF | REM-SQ, CMT-MATSAL | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-07-15 12:00 | 2022-07-15 12:00 |  | 2022-07-16 12:00 | 2022-07-17 |  | 2022-07-18 11:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.03 | HA-11_Plug #1-2 | SANTOS LIMITED | HARRIET A11 (HA 11) | Noble Tom Prosser | J.22.110802 | WCF | REM-PA, CMT-MATSAL | Medium | Confirmed | Design - PSD |  | Design Completed | Design Completed | Design Completed | 2022-05-25 12:00 | 2022-05-25 12:00 |  | 2022-05-26 03:00 | 2022-05-26 15:00 |  | 2022-05-26 15:00 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.11 | GD-02_Plug #2 | SANTOS LIMITED | GUDRUN 2 (GD02) | Noble Tom Prosser | J.22.110798 | WCF | REM-PA | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | Design Completed | 2022-07-23 09:00 | 2022-07-23 08:00 |  | 2022-07-24 09:00 | 2022-07-24 21:00 |  | 2022-07-26 08:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.06 | HA-01_PWC Cement Plug #1 | SANTOS LIMITED | HARRIET A1 (HA 01) | Noble Tom Prosser | J.22.110793 | WCF | REM-SQ, CMT-MATSAL | Medium | Confirmed | Design - PSD |  | Design Completed | Design Completed | Design Completed | 2022-06-18 04:00 | 2022-06-17 |  | 2022-06-19 04:00 | 2022-06-19 16:00 |  | 2022-06-21 03:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.09 | NA-02_Plug #1B | SANTOS LIMITED | NORTH ALKIMOS 2H (NA02) | Noble Tom Prosser | J.22.110791 | WCF | REM-PA, CMT-MATSAL | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-06-27 10:00 | 2022-06-27 08:00 |  | 2022-06-28 20:00 | 2022-06-29 08:00 |  | 2022-06-30 09:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.07 | Surface Plugs - Harriet Alpha Platform | SANTOS LIMITED | Harriet Alpha Platform | Noble Tom Prosser | J.22.110792 | WCF | REM-PA, CMT-MATSAL | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | Design Completed | 2022-09-03 20:00 | 2022-09-03 |  | 2022-09-03 20:00 | 2022-09-12 08:00 |  | 2022-09-13 19:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 8 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.04 | HA08_Reservoir Abandonment | SANTOS LIMITED | HARRIET A8H1 (HA 08H1) | Noble Tom Prosser | J.22.110788 | WCF | REM-SQ, CMT-MATSAL | Medium | Confirmed | Design - PSD |  | Design Completed | Design Completed | Design Completed | 2022-06-10 05:00 | 2022-06-10 12:00 |  | 2022-06-11 17:00 | 2022-06-12 05:00 |  | 2022-06-14 04:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.12 | HA-03_Plug #3 | SANTOS LIMITED | Harriet Alpha-3 (HA03) | Noble Tom Prosser |  | WCF | REM-PA, CMT-MATSAL | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | Design Completed | 2022-08-06 20:00 | 2022-08-06 12:00 |  | 2022-08-07 20:00 | 2022-08-08 08:00 |  | 2022-08-09 19:59 | AUS West Coast WS | HNarainasamy | 2022-08-05 12:16 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.21 | HA09 - Plug #3 | SANTOS LIMITED | Harriet Alpha-9 (HA09) | Noble Tom Prosser |  | WCF | REM-PA, CMT-MATSAL | Medium | Confirmed | Design - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-02 03:00 | 2022-08-02 06:00 |  | 2022-08-03 20:00 | 2022-08-04 08:00 |  | 2022-08-06 02:59 | AUS West Coast WS | HNarainasamy | 2022-08-03 15:17 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.13 | HA03_DLT_Csg Leak Isolation | SANTOS LIMITED | Harriet Alpha-3 (HA03) | Noble Tom Prosser |  | WCF | CMT-TOOLS | Medium | Cancelled | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-05-17 16:00 | 2022-05-14 |  | 2022-05-17 16:00 | 2022-05-18 15:59 |  | 2022-05-18 15:59 | AUS West Coast WS | HNarainasamy | 2022-05-19 11:29 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.05 | A.1020894.05.01 | HA-03_Plug #1 & #2 | SANTOS LIMITED | Harriet Alpha-3 (HA03) | Noble Tom Prosser |  | WCF | REM-PA, CMT-MATSAL | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | Design Completed | 2022-05-13 18:00 | 2022-05-14 |  | 2022-05-15 06:00 | 2022-05-15 18:00 |  | 2022-05-17 17:59 | AUS West Coast WS | HNarainasamy | 2022-05-12 22:28 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.04 | A.1020894.04.08 | Yoorn-1_Plug and Abandon_Plug #3 | SANTOS LIMITED |  | Noble Tom Prosser | J.22.110773 | WCF | REM-PA, CMT-MATSAL | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-01 | 2022-11-06 |  | 2022-12-02 | 2022-12-02 23:59 |  | 2022-12-02 23:59 | AUS West Coast WS | HNarainasamy | 2022-10-12 14:51 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.04 | A.1020894.04.07 | Yoorn-1_Plug and Abandon_Plug #2 | SANTOS LIMITED | Yoorn 1 | Noble Tom Prosser | J.22.110771 | WCF | REM-PA, CMT-MATSAL | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-29 | 2022-11-06 |  | 2022-11-30 | 2022-11-30 23:59 |  | 2022-11-30 23:59 | AUS West Coast WS | HNarainasamy | 2022-10-12 14:51 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.04 | A.1020894.04.06 | Yoorn-1_Plug and Abandon_Plug #1 | SANTOS LIMITED | Yoorn 1 | Noble Tom Prosser | J.22.110764 | WCF | REM-PA, CMT-MATSAL | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-27 | 2022-11-06 |  | 2022-11-28 | 2022-11-28 23:59 |  | 2022-11-28 23:59 | AUS West Coast WS | HNarainasamy | 2022-10-12 14:50 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.04 | A.1020894.04.05 | Yoorn-1_9-5/8in Liner Cementing | SANTOS LIMITED | Yoorn 1 | Noble Tom Prosser | J.22.110761 | WCF | PRI-LIN, CMT-MATSAL | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-20 | 2022-11-06 |  | 2022-11-21 | 2022-11-22 23:59 |  | 2022-11-22 23:59 | AUS West Coast WS | HNarainasamy | 2022-10-12 14:50 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.04 | A.1020894.04.04 | Yoorn-1_11-3/4in Liner Cementing | SANTOS LIMITED | Yoorn 1 | Noble Tom Prosser | J.22.110768 | WCF | PRI-LIN, CMT-MATSAL | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-17 | 2022-11-06 |  | 2022-11-18 | 2022-11-19 23:59 |  | 2022-11-19 23:59 | AUS West Coast WS | HNarainasamy | 2022-10-12 14:49 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.04 | A.1020894.04.03 | Yoorn-1_13-3/8in Intermediate Casing Cementing | SANTOS LIMITED | Yoorn 1 | Noble Tom Prosser | J.22.110765 | WCF | PRI-SURF, CMT-MATSAL | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-13 | 2022-11-06 |  | 2022-11-14 | 2022-11-15 23:59 |  | 2022-11-15 23:59 | AUS West Coast WS | HNarainasamy | 2022-10-12 14:49 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.04 | A.1020894.04.02 | Yoorn-1_20" Surface Casing Cementing | SANTOS LIMITED | Yoorn 1 | Noble Tom Prosser | J.22.110767 | WCF | PRI-SURF, CMT-MATSAL | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-10 | 2022-11-06 |  | 2022-11-11 | 2022-11-12 23:59 |  | 2022-11-12 23:59 | AUS West Coast WS | HNarainasamy | 2022-10-12 14:48 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.04 | A.1020894.04.01 | Yoorn-1_30" Conductor Casing Cementing | SANTOS LIMITED | Yoorn 1 | Noble Tom Prosser | J.22.110766 | WCF | PRI-COND, CMT-MATSAL | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-06 | 2022-11-06 |  | 2022-11-07 | 2022-11-08 23:59 |  | 2022-11-08 23:59 | AUS West Coast WS | HNarainasamy | 2022-10-12 14:47 | HNarainasamy |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.03 | A.1020894.03.04 | Apus-1_Plug and Abandon_Plug #1A-1B-2 | SANTOS LIMITED | APUS 1 | Noble Tom Prosser | J.22.110763 | WCF | REM-PA, CMT-MATSAL | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-04-06 16:00 | 2022-04-21 16:00 |  | 2022-04-22 16:00 | 2022-04-23 15:59 |  | 2022-04-09 15:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 68.8 | 33.3 | 0 | 0 | 37.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.03 | A.1020894.03.05 | Apus-1_Plug and Abandon_Plug #4 | SANTOS LIMITED | APUS 1 | Noble Tom Prosser | J.22.110762 | WCF | REM-PA, CMT-MATSAL | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-04-09 16:00 | 2022-04-23 17:00 |  | 2022-04-25 16:00 | 2022-04-26 15:59 |  | 2022-04-12 15:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 68.8 | 33.3 | 0 | 0 | 37.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.03 | A.1020894.03.06 | Apus-1_Plug and Abandon_Plug #3 | SANTOS LIMITED | APUS-1 | Noble Tom Prosser | J.22.110760 | WCF | REM-PA, CMT-MATSAL | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-11 | 2022-04-25 |  | 2022-04-26 | 2022-04-26 23:59 |  | 2022-04-12 23:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.03 | A.1020894.03.01 | Apus-1_30in Conductor Casing Cementing | SANTOS LIMITED | APUS 1 | Noble Tom Prosser | J.22.110757 | WCF | PRI-COND, CMT-MATSAL | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-05-17 21:00 | 2022-04-06 12:00 |  | 2022-05-20 | 2022-05-21 |  | 2022-05-20 20:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 68.8 | 50 | 0 | 0 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.03 | A.1020894.03.03 | Apus-1_9-5/8in Liner Cementing | SANTOS LIMITED | APUS 1 | Noble Tom Prosser | J.22.110753 | WCF | PRI-LIN, CMT-MATSAL | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-03-30 | 2022-04-15 12:00 |  | 2022-04-16 12:00 | 2022-04-17 12:00 |  | 2022-04-01 23:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 68.8 | 33.3 | 0 | 0 | 37.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.03 | A.1020894.03.02 | Apus-1_13-3/8in Surface Casing Cementing | SANTOS LIMITED | APUS 1 | Noble Tom Prosser | J.22.110752 | WCF | PRI-SURF, CMT-MATSAL | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-04-02 | 2022-04-09 21:00 |  | 2022-04-10 21:00 | 2022-04-11 21:00 |  | 2022-04-30 23:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 68.8 | 50 | 0 | 0 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.02 | A.1020894.02.08 | Pavo-1_DHT_Cyclone Suspension_13-3/8" DLT | SANTOS LIMITED | PAVO 1 | Noble Tom Prosser | J.22.110818 | WCF | CMT-TOOLS | Medium | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2022-02-26 20:00 | 2022-02-26 |  | 2022-02-26 20:00 | 2022-02-27 19:59 |  | 2022-02-27 19:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.02 | A.1020894.02.06 | Pavo-1_Plug and Abandon_Plug #4 | SANTOS LIMITED | PAVO-1 | Noble Tom Prosser | J.22.110759 | WCF | REM-PA, CMT-MATSAL | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-29 | 2022-03-29 |  | 2022-03-30 22:00 | 2022-03-31 21:59 |  | 2022-04-01 23:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.02 | A.1020894.02.07 | Pavo-1_DHT_Cyclone Suspension_9-5/8in DLT + SV | SANTOS LIMITED | PAVO 1 | Noble Tom Prosser | J.22.110758 | WCF | CMT-TOOLS | Medium | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2022-02-26 18:00 | 2022-02-26 |  | 2022-02-26 18:00 | 2022-02-27 17:59 |  | 2022-02-27 17:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 68.8 | 33.3 | 0 | 0 | 37.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.02 | A.1020894.02.05 | Pavo-1_Plug and Abandon_Plug #3 | SANTOS LIMITED | PAVO 1 | Noble Tom Prosser | J.22.110755 | WCF | REM-PA, CMT-MATSAL | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-03-27 | 2022-03-28 |  | 2022-03-28 12:00 | 2022-03-29 11:59 |  | 2022-03-30 23:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 68.8 | 33.3 | 0 | 0 | 37.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.02 | A.1020894.02.02 | Pavo-1_13-3/8in Surface Casing Cementing | SANTOS LIMITED | PAVO 1 | Noble Tom Prosser | J.22.110754 | WCF | PRI-SURF, CMT-MATSAL | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-02-12 16:00 | 2022-02-12 |  | 2022-02-13 16:00 | 2022-02-15 15:59 |  | 2022-02-15 15:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 68.8 | 33.3 | 0 | 0 | 37.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.02 | A.1020894.02.04 | Pavo-1_Plug and Abandon_Plug #1-2 | SANTOS LIMITED | PAVO-1 | Noble Tom Prosser | J.22.110751 | WCF | REM-PA, CMT-MATSAL | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-26 14:00 | 2022-03-27 |  | 2022-03-27 14:00 | 2022-03-28 13:59 |  | 2022-03-28 13:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 68.8 | 33.3 | 0 | 25 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.02 | A.1020894.02.03 | Pavo-1_9-5/8in Liner Cementing | SANTOS LIMITED | PAVO 1 | Noble Tom Prosser | J.22.110748 | WCF | PRI-LIN, CMT-MATSAL | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-02-21 06:00 | 2022-02-21 |  | 2022-02-22 06:00 | 2022-02-24 05:59 |  | 2022-02-24 05:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 68.8 | 50 | 0 | 0 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.02 | A.1020894.02.01 | Pavo-1_30in Conductor Casing | SANTOS LIMITED | PAVO 1 | Noble Tom Prosser | J.22.110747 | WCF | PRI-COND, CMT-MATSAL | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-02-08 23:00 | 2022-02-08 |  | 2022-02-09 23:00 | 2022-02-11 22:59 |  | 2022-02-11 22:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 68.8 | 33.3 | 0 | 0 | 37.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.01 | A.1020894.01.08 | Dancer-1_7in Liner Cementing | SANTOS LIMITED | DANCER 1 | Noble Tom Prosser | J.22.110993 | WCF | PRI-LIN, CMT-MATSAL | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-01-21 01:00 | 2022-01-19 |  | 2022-01-21 01:00 | 2022-01-22 01:00 |  | 2022-01-22 01:00 | AUS West Coast WS | HNarainasamy | 2022-10-03 12:34 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.01 | A.1020894.01.03 | Dancer-1_9-5/8" Liner Cementing | SANTOS LIMITED | DANCER 1 | Noble Tom Prosser | J.22.110987 | WCF | PRI-LIN, CMT-MATSAL | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-01-14 03:00 | 2022-01-05 |  | 2022-01-14 03:00 | 2022-01-16 02:59 |  | 2022-01-16 02:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 12:33 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 68.8 | 50 | 0 | 0 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.01 | A.1020894.01.07 | Pavo-1_30in Conductor Casing | SANTOS LIMITED |  | Noble Tom Prosser | J.21.109393 | WCF | PRI-COND, CMT-MATSAL | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-12-15 | 2021-12-01 |  | 2021-12-15 | 2021-12-16 23:59 |  | 2021-12-16 23:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.01 | A.1020894.01.02 | Dancer-1_13-3/8" Surface Casing Cementing | SANTOS LIMITED | DANCER 1 | Noble Tom Prosser | J.22.110749 | WCF | PRI-SURF, CMT-MATSAL | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-01-05 12:00 | 2022-01-01 |  | 2022-01-06 12:00 | 2022-01-08 11:59 |  | 2022-01-08 11:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 68.8 | 33.3 | 0 | 0 | 37.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.01 | A.1020894.01.06 | Dancer-1_Plug and Abandon_Plug #3 | SANTOS LIMITED | DANCER-1 | Noble Tom Prosser | J.22.110750 | WCF | REM-PA, CMT-MATSAL | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-31 | 2022-01-31 |  | 2022-02-01 | 2022-02-01 23:59 |  | 2022-02-01 23:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.01 | A.1020894.01.01 | Dancer-1_30" Conductor Casing Cementing | SANTOS LIMITED | DANCER 1 | Noble Tom Prosser | J.21.109390 | WCF | PRI-COND, CMT-MATSAL | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-12-04 06:00 | 2021-12-11 |  | 2021-12-14 06:00 | 2021-12-16 05:59 |  | 2021-12-16 05:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 68.8 | 33.3 | 0 | 0 | 37.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.01 | A.1020894.01.05 | Dancer-1_Plug and Abandon_Plug #3 | SANTOS LIMITED | DANCER 1 | Noble Tom Prosser | J.22.110746 | WCF | REM-PA, CMT-MATSAL | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-01-26 18:00 | 2022-01-27 12:00 |  | 2022-01-27 18:00 | 2022-01-28 17:59 |  | 2022-01-28 17:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 68.8 | 33.3 | 0 | 0 | 37.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020894 | O.1020894.01 | A.1020894.01.04 | Dancer-1_Plug and Abandon_Plug #1 & Plug #2 | SANTOS LIMITED | DANCER 1 | Noble Tom Prosser | J.22.110745 | WCF | REM-PA, CMT-MATSAL | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-01-25 16:00 | 2022-01-26 |  | 2022-01-26 16:00 | 2022-01-27 15:59 |  | 2022-01-27 15:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 68.8 | 33.3 | 0 | 0 | 37.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020740 | O.1020740.01 | A.1020740.01.03 | Frac Well#3 | TODD ENERGY LIMITED |  |  | J.23.008733 | RPS | FRAC-PROP | Low | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2023-04-02 22:00 |  | 2023-04-02 22:00 | 2023-04-23 21:59 |  |  | New Plymouth WS | THuynh | 2022-10-03 16:39 | FDPSystemUser |  | No |  |  |  |  | Tony Huynh |  | 0 | 5 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Omar Mosleh | WS Production Services
P.1020740 | O.1020740.01 | A.1020740.01.01 | Frac Well#1 | TODD ENERGY LIMITED |  |  | J.22.110862 | RPS | FRAC-PROP | Low | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2022-12-01 |  | 2022-12-01 | 2022-12-14 23:59 |  |  | New Plymouth WS | THuynh | 2022-10-03 16:39 | FDPSystemUser |  | No |  |  |  |  | Tony Huynh |  | 0 | 6 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Omar Mosleh | WS Production Services
P.1020740 | O.1020740.01 | A.1020740.01.02 | Frac Well #2 | TODD ENERGY LIMITED |  |  | J.23.008730 | RPS | FRAC-PROP | Low | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2023-02-01 |  | 2023-02-01 | 2023-02-21 23:59 |  |  | New Plymouth WS | THuynh | 2022-10-03 16:39 | FDPSystemUser |  | No |  |  |  |  | Tony Huynh |  | 0 | 5 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Omar Mosleh | WS Production Services
P.1020562 | O.1020562.01 | A.1020562.01.01 | Q2 Enfield P&A Preparation and 6 wells | WOODSIDE ENERGY LTD | Enfield | ENSCO DPS-1 |  | RPI | TSWT-SEPONLY-JOB | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-03-01 | 2021-12-01 |  | 2022-04-01 | 2022-06-30 23:59 |  | 2022-06-30 23:59 | APG TS | RWallis | 2024-11-19 20:14 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Wayne Wallis |  | 21572.25 | 2 |  |  |  | 75 | 66.7 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1020562 | O.1020562.01 | A.1020562.01.02 | Q3 Enfield P&A - 6 Wells | WOODSIDE ENERGY LTD | Well #1, Well #3, Well #2, Well #4, Well #5 | ENSCO DPS-1 | J.22.115700 | RPI | TSWT-SEPONLY-JOB | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-02-25 | 2022-06-26 |  | 2022-06-26 | 2022-10-01 23:59 |  | 2022-06-30 | APG TS | GRoxo | 2024-11-19 20:14 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Wayne Wallis |  | 0 | 6 |  |  |  | 75 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1020562 | O.1020562.01 | A.1020562.01.03 | Q4 Enfield P&A - 6 wells | WOODSIDE ENERGY LTD | Enfield, Well #1, Well #3, Well #2, Well #4, Well #5 | ENSCO DPS-1 |  | RPI | TSWT-SEPONLY-JOB | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-05-28 | 2022-09-26 |  | 2022-09-26 | 2022-12-26 23:59 |  | 2022-11-26 | APG TS | GRoxo | 2024-11-19 20:14 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Wayne Wallis |  | 0 | 6 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1020483 | O.1020483.04 | A.1020483.04.05 | 4 1/2" Production | IMPERIAL OIL AND GAS PTY LTD |  | RIGLESS - AUSTRALIA | J.23.011913 | WCF | PRI-LONG | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2023-12-10 22:00 |  | 2024-01-03 21:00 | 2024-01-09 20:59 |  |  | AUS East Coast WS | ALyons | 2024-07-11 16:01 | MMendoza26 |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020483 | O.1020483.04 | A.1020483.04.06 | Remote Ops - Chemicals & Equipment | IMPERIAL OIL AND GAS PTY LTD |  | RIGLESS - AUSTRALIA | J.23.011914 | WCF | CMT-MATSAL | Low | Unconfirmed - 50% | Design - CEC |  | In Progress | Design Completed | In Progress | 2023-01-02 | 2023-12-10 21:00 |  | 2023-12-10 23:00 | 2024-01-09 22:59 |  | 2023-01-31 23:59 | AUS East Coast WS | ALyons | 2023-05-20 09:02 | HFerdjallah |  | No |  |  |  |  | Ariel Lyons |  | 0 | 0 |  |  |  | 68.8 | 33.3 | 100 | 25 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020483 | O.1020483.04 | A.1020483.04.04 | 7" Intermediate | IMPERIAL OIL AND GAS PTY LTD |  | RIGLESS - AUSTRALIA | J.23.011912 | WCF | PRI-INTER | Low | Unconfirmed - 50% | Design - CEC |  | Not Started | Not Started | In Progress |  | 2023-12-10 22:00 |  | 2023-12-24 21:00 | 2023-12-30 20:59 |  |  | AUS East Coast WS | ALyons | 2023-05-20 08:51 | HFerdjallah |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020483 | O.1020483.04 | A.1020483.04.03 | PlugBack & KickOff | IMPERIAL OIL AND GAS PTY LTD |  | RIGLESS - AUSTRALIA | J.23.011911 | WCF | REM-PA,REM-KOP | Low | Unconfirmed - 50% | Design - CEC |  | Not Started | Not Started | In Progress |  | 2023-12-15 22:00 |  | 2023-12-24 21:00 | 2023-12-30 20:59 |  |  | AUS East Coast WS | ALyons | 2023-05-20 08:51 | HFerdjallah |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020483 | O.1020483.04 | A.1020483.04.02 | 9 5/8" surface | IMPERIAL OIL AND GAS PTY LTD |  | RIGLESS - AUSTRALIA | J.23.011910 | WCF | PRI-SURF | Low | Unconfirmed - 50% | Design - CEC |  | Not Started | Not Started | In Progress |  | 2023-12-10 22:00 |  | 2023-12-14 21:00 | 2023-12-20 20:59 |  |  | AUS East Coast WS | ALyons | 2023-05-20 08:51 | HFerdjallah |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020483 | O.1020483.04 | A.1020483.04.01 | 13 3/8" Conductor | IMPERIAL OIL AND GAS PTY LTD | Well #AH | RIGLESS - AUSTRALIA | J.23.011909 | WCF | PRI-COND | Low | Unconfirmed - 50% | Design - CEC |  | Not Required | Not Required | In Progress |  | 2023-12-10 21:00 |  | 2023-12-10 23:00 | 2023-12-15 22:59 |  |  | AUS East Coast WS | ALyons | 2023-05-20 08:51 | HFerdjallah |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020483 | O.1020483.03 | A.1020483.03.05 | Remote Ops - Chemicals & Equipment | IMPERIAL OIL AND GAS PTY LTD |  | RIGLESS - AUSTRALIA | J.22.121743 | WCF | CMT-MATSAL | Low | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress | 2022-10-01 | 2022-10-01 |  | 2022-10-01 | 2022-10-30 23:59 |  | 2022-10-31 00:59 | AUS East Coast WS | ALyons | 2022-10-28 17:43 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020483 | O.1020483.03 | A.1020483.03.04 | 4 1/2" Production | IMPERIAL OIL AND GAS PTY LTD |  | RIGLESS - AUSTRALIA | J.22.121742 | WCF | PRI-LONG | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-10-01 |  | 2022-10-25 | 2022-10-30 23:59 |  |  | AUS East Coast WS | ALyons | 2022-10-28 17:43 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020483 | O.1020483.03 | A.1020483.03.03 | 7" Intermediate | IMPERIAL OIL AND GAS PTY LTD |  | RIGLESS - AUSTRALIA | J.22.121741 | WCF | PRI-INTER | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-10-01 |  | 2022-10-15 | 2022-10-20 23:59 |  |  | AUS East Coast WS | ALyons | 2022-10-28 17:43 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020483 | O.1020483.03 | A.1020483.03.02 | PlugBack & KickOff | IMPERIAL OIL AND GAS PTY LTD | Well #4H | RIGLESS - AUSTRALIA | J.22.121740 | WCF | REM-PA,REM-KOP | Low | Cancelled | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-10-01 |  | 2022-10-10 | 2022-10-15 23:59 |  |  | AUS East Coast WS | ALyons | 2022-10-28 17:43 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020483 | O.1020483.03 | A.1020483.03.01 | 9 5/8" surface | IMPERIAL OIL AND GAS PTY LTD |  | RIGLESS - AUSTRALIA | J.22.121739 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-10-01 |  | 2022-10-05 | 2022-10-10 23:59 |  |  | AUS East Coast WS | ALyons | 2022-10-28 17:43 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020483 | O.1020483.02 | A.1020483.02.04 | Remote Ops - Chemicals & Equipment | IMPERIAL OIL AND GAS PTY LTD | Well #3H | RIGLESS - AUSTRALIA | J.23.011908 | WCF | CMT-MATSAL | Low | Unconfirmed - 50% | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-11-02 | 2023-11-11 01:00 |  | 2023-11-11 01:00 | 2023-12-11 00:59 |  | 2022-12-01 23:59 | AUS East Coast WS | ALyons | 2023-05-20 09:02 | HFerdjallah |  | No |  |  |  |  | Ariel Lyons |  | 0 | 0 |  |  |  | 75 | 33.3 | 100 | 25 | 55 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020483 | O.1020483.02 | A.1020483.02.03 | 4 1/2" Production | IMPERIAL OIL AND GAS PTY LTD | Well #3H | RIGLESS - AUSTRALIA | J.23.011907 | WCF | PRI-LONG | Low | Unconfirmed - 50% | Design - CEC |  | Not Required | Not Required | In Progress |  | 2023-11-11 01:00 |  | 2023-12-05 01:00 | 2023-12-11 00:59 |  |  | AUS East Coast WS | ALyons | 2023-05-20 08:51 | HFerdjallah |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020483 | O.1020483.02 | A.1020483.02.02 | 7" Intermediate | IMPERIAL OIL AND GAS PTY LTD | Well #3H | RIGLESS - AUSTRALIA | J.23.011906 | WCF | PRI-INTER | Low | Unconfirmed - 50% | Design - CEC |  | Not Required | Not Required | In Progress |  | 2023-11-11 01:00 |  | 2023-11-25 01:00 | 2023-12-01 00:59 |  |  | AUS East Coast WS | ALyons | 2023-05-20 08:51 | HFerdjallah |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020483 | O.1020483.02 | A.1020483.02.01 | 9 5/8" Surface | IMPERIAL OIL AND GAS PTY LTD | Well #3H | RIGLESS - AUSTRALIA | J.23.011905 | WCF | PRI-SURF | Low | Unconfirmed - 50% | Design - CEC |  | Not Required | Not Required | In Progress |  | 2023-11-11 01:00 |  | 2023-11-15 01:00 | 2023-11-21 00:59 |  |  | AUS East Coast WS | ALyons | 2023-05-20 08:51 | HFerdjallah |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020483 | O.1020483.01 | A.1020483.01.04 | Production 4 1/2" | IMPERIAL OIL AND GAS PTY LTD |  | Silver City 40 | J.21.111623 | WCF | PRI-LONG, CMT-MATSAL | Low | Unconfirmed - 50% | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-12-04 23:00 | 2021-12-05 |  | 2021-12-16 | 2021-12-16 23:59 |  | 2021-12-05 22:59 | AUS East Coast WS | ALyons | 2022-10-28 17:42 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 0 |  |  |  | 68.8 | 33.3 | 100 | 0 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020483 | O.1020483.01 | A.1020483.01.03 | Plug Back and Kick Off | IMPERIAL OIL AND GAS PTY LTD |  | Silver City 40 | J.21.111622 | WCF | REM-PA,REM-KOP, CMT-MATSAL | Low | Unconfirmed - 50% | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-11-14 23:00 | 2021-11-14 23:00 |  | 2021-12-07 23:00 | 2021-12-08 22:59 |  | 2021-11-15 22:59 | AUS East Coast WS | ALyons | 2022-10-28 17:42 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 2 |  |  |  | 68.8 | 33.3 | 0 | 0 | 37.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020483 | O.1020483.01 | A.1020483.01.02 | Intermediate 7 | IMPERIAL OIL AND GAS PTY LTD | CARPENTARIA 2 | Silver City 40 | J.21.111621 | WCF | PRI-INTER, CMT-MATSAL | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-10-22 | 2021-10-22 |  | 2021-11-22 23:00 | 2021-11-23 22:59 |  | 2021-10-22 23:59 | AUS East Coast WS | ALyons | 2022-10-28 17:42 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 |  |  |  | 53.1 | 25 | 0 | 0 | 28.7 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020483 | O.1020483.01 | A.1020483.01.01 | Surface 9 5/8 | IMPERIAL OIL AND GAS PTY LTD | CARPENTARIA 2 | Silver City 40 | J.21.111620 | WCF | PRI-SURF, CMT-MATSAL | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-11-08 | 2021-11-08 |  | 2021-11-10 | 2021-11-10 23:59 |  | 2021-11-10 23:59 | AUS East Coast WS | ALyons | 2022-10-28 17:42 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 0 |  |  |  | 68.8 | 16.7 | 0 | 0 | 32.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1020221 | O.1020221.01 | A.1020221.01.01 | IBC-ChealB7 | TAMARIND NZ ONSHORE LIMITED | Cheal-B7 | Ensign 6 (WO) | J.21.109100 | RPE | ES-CH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-07-24 |  | 2021-07-25 | 2021-07-27 23:59 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  |  | Paulo Zuliani |  | 0 | 1 |  |  |  | 50 | 50 | 0 | 0 | 30 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1020110 | O.1020110.01 | A.1020110.01.03 | Carnavon ¦ Buffalo-10 ¦ Valaris-107 ¦ Open Hole Evaluation | CARNARVON PETROLEUM TIMOR | Buffalo-10 | Valaris 107 | J.22.110111 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-01-14 14:00 |  | 2022-01-17 | 2022-01-24 |  |  | New Burn WL | BAhmad | 2022-10-03 09:54 | FDPSystemUser |  | No |  |  |  |  | James Cade |  | 878738 | 4 |  |  |  | 91.7 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1020110 | O.1020110.01 | A.1020110.01.02 | Buffalo-10 Exploration Nov-21 Activity | CARNARVON PETROLEUM TIMOR |  | Valaris 107 | J.21.108869 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-11-01 |  | 2021-11-01 | 2021-11-24 23:59 |  |  | New Burn WL | MMclean3 | 2022-10-03 09:53 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1020110 | O.1020110.01 | A.1020110.01.01 | Buffalo-10 Exploration Nov-21 Activity | CARNARVON PETROLEUM TIMOR |  | Valaris 107 | J.21.108868 | RPE | ES-OH-NO | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-10-18 |  | 2021-11-01 | 2021-12-15 23:59 |  |  | New Burn WL | MMclean3 | 2022-10-03 09:53 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 0 |  |  |  | 33.3 | 33.3 | 100 | 50 | 45 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1020099 | O.1020099.01 | A.1020099.01.03 | Personnel Aug | GREYMOUTH PETROLEUM | Well #3 |  | J.22.110861 | RPS | FRAC-MATSAL | Low | Confirmed | Design - CEC |  | Not Required | Not Required | In Progress |  | 2022-07-26 |  | 2022-07-26 | 2022-08-25 23:59 |  |  | New Plymouth WS | THuynh | 2024-07-22 21:19 | DR4 |  | No |  |  |  |  | Tony Huynh |  | 0 | 1 |  |  |  | 81.3 | 50 | 100 | 25 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Omar Mosleh | WS Production Services
P.1020099 | O.1020099.01 | A.1020099.01.10 | PM Sell up | GREYMOUTH PETROLEUM |  |  | J.23.133887 | RPS | FRAC-MATSAL | Low | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2023-10-01 |  | 2023-10-01 | 2023-10-30 23:59 |  |  | New Plymouth WS | HFerdjallah | 2023-09-06 10:37 | HFerdjallah |  | No |  |  |  |  | Ramadhani Adi Negara |  | 0 | 0 |  |  |  | 50 | 33.3 | 100 | 25 | 45 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1020099 | O.1020099.01 | A.1020099.01.09 | Material Sales May 2023 | GREYMOUTH PETROLEUM |  |  | J.23.085282 | RPS | FRAC-MATSAL | Low | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2023-05-13 |  | 2023-05-13 | 2023-05-19 23:59 |  |  | New Plymouth WS | radinegara | 2023-05-17 20:21 | radinegara |  | No |  |  |  |  | Feras Manja |  | 0 | 1 |  |  |  | 50 | 33.3 | 100 | 25 | 45 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1020099 | O.1020099.01 | A.1020099.01.08 | Feb Material sales | GREYMOUTH PETROLEUM | Well #3 |  |  | RPS | FRAC-MATSAL | Low | Confirmed | Design - CEC |  | Not Started | Design Completed | In Progress |  | 2023-02-22 |  | 2023-02-22 | 2023-03-24 23:59 |  |  | New Plymouth WS | THuynh | 2023-02-28 14:51 | OMosleh |  | No |  |  |  |  | Tony Huynh |  | 0 | 1 |  |  |  | 62.5 | 33.3 | 100 | 25 | 50 |  | 0 |  |  |  | 0 |  |  |  | Omar Mosleh | WS Production Services
P.1020099 | O.1020099.01 | A.1020099.01.04 | Services | GREYMOUTH PETROLEUM |  |  | J.22.110867 | RPS | FRAC-MATSAL | Low | Confirmed | Design - CEC |  | Not Required | Not Required | In Progress |  | 2022-05-26 |  | 2022-05-26 | 2022-06-25 23:59 |  |  | New Plymouth WS | THuynh | 2022-10-03 16:39 | FDPSystemUser |  | No |  |  |  |  | Tony Huynh |  | 0 | 0 |  |  |  | 81.3 | 66.7 | 100 | 25 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Omar Mosleh | WS Production Services
P.1020099 | O.1020099.01 | A.1020099.01.07 | July Material Sales | GREYMOUTH PETROLEUM | Well #3 |  | J.22.110865 | RPS | FRAC-MATSAL | Low | Confirmed | Design - CEC |  | Not Required | Not Required | In Progress |  | 2022-06-25 |  | 2022-06-25 | 2022-07-25 23:59 |  |  | New Plymouth WS | THuynh | 2022-10-03 16:39 | FDPSystemUser |  | No |  |  |  |  | Tony Huynh |  | 0 | 1 |  |  |  | 75 | 33.3 | 100 | 25 | 55 |  | 0 |  |  |  | 0 |  |  |  | Omar Mosleh | WS Production Services
P.1020099 | O.1020099.01 | A.1020099.01.02 | Material Sales Well 3 | GREYMOUTH PETROLEUM | Well #3 |  | J.22.110864 | RPS | FRAC-MATSAL | Low | Confirmed | Design - CEC |  | Not Required | Design Completed | In Progress |  | 2022-05-25 |  | 2022-05-25 | 2022-06-24 23:59 |  |  | New Plymouth WS | THuynh | 2022-10-03 16:39 | FDPSystemUser |  | No |  |  |  |  | Tony Huynh |  | 0 | 0 |  |  |  | 75 | 33.3 | 100 | 25 | 55 |  | 0 |  |  |  | 0 |  |  |  | Omar Mosleh | WS Production Services
P.1020099 | O.1020099.01 | A.1020099.01.06 | Personnel - Sep | GREYMOUTH PETROLEUM | Well #3 |  | J.22.110863 | RPS | FRAC-MATSAL | Low | Confirmed | Design - CEC |  | Not Required | Not Required | In Progress |  | 2022-07-26 |  | 2022-08-25 | 2022-09-24 23:59 |  |  | New Plymouth WS | THuynh | 2022-10-03 16:39 | FDPSystemUser |  | No |  |  |  |  | Tony Huynh |  | 0 | 1 |  |  |  | 81.3 | 66.7 | 100 | 25 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Omar Mosleh | WS Production Services
P.1020099 | O.1020099.01 | A.1020099.01.05 | Personnel - July | GREYMOUTH PETROLEUM | Well #3 |  | J.22.110856 | RPS | FRAC-MATSAL | Low | Confirmed | Design - CEC |  | Not Required | Not Required | In Progress |  | 2022-05-26 |  | 2022-06-25 | 2022-07-25 23:59 |  |  | New Plymouth WS | THuynh | 2022-10-03 16:39 | FDPSystemUser |  | No |  |  |  |  | Tony Huynh |  | 0 | 1 |  |  |  | 81.3 | 66.7 | 100 | 25 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Omar Mosleh | WS Production Services
P.1020099 | O.1020099.01 | A.1020099.01.01 | Frac | GREYMOUTH PETROLEUM | Well #1 |  | J.21.109407 | RPS | FRAC-MATSAL | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-12-01 | 2021-12-01 |  | 2021-12-01 | 2022-03-31 22:59 |  | 2022-03-31 22:59 | New Plymouth WS | THuynh | 2022-10-03 16:39 | FDPSystemUser |  | No |  |  |  |  | Tony Huynh |  | 0 | 0 |  |  |  | 68.8 | 33.3 | 100 | 25 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Omar Mosleh | WS Production Services
P.1020036 | O.1020036.02 | A.1020036.02.05 | PNX (Oct) | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.110391 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-10-12 |  | 2022-10-13 10:00 | 2022-10-14 00:59 |  |  | Roma WL | MRony2 | 2022-10-13 19:04 | MRony2 |  | No |  |  |  |  | Jon Lawrie |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1020036 | O.1020036.02 | A.1020036.02.04 | SCMT-SLDT Woodroyd 7 | SANTOS LIMITED | Woodroyd 7 | Rigless Australia - 1 | J.22.110986 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-08-22 |  | 2022-08-24 10:00 | 2022-08-25 00:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:32 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 12102.01 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1020036 | O.1020036.02 | A.1020036.02.01 | PNX-Rigless | SANTOS LIMITED | RM02-64 1 | Rigless Australia - 1 | J.21.109607 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2021-11-20 10:00 | 2021-11-20 |  | 2021-11-20 10:00 | 2021-11-22 23:59 |  | 2021-11-27 23:59 | Roma WL | MRony2 | 2022-10-03 15:32 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 56920.08 | 1 |  | L0 - No RO |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1020036 | O.1020036.02 | A.1020036.02.06 | PNX pre-frac | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.110418 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-09-30 |  | 2022-10-01 10:00 | 2022-10-02 00:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:18 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1020036 | O.1020036.02 | A.1020036.02.02 | PNX_Pre FoamX | SANTOS LIMITED | RM02-64-01 | Rigless Australia - 1 | J.21.109081 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-12-04 |  | 2021-12-09 10:00 | 2021-12-11 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 30409.36 | 1 |  |  |  | 75 | 33.3 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1020036 | O.1020036.02 | A.1020036.02.03 | PNX-Frac Jan22 | SANTOS LIMITED | RM15-102-1, RM15-104-1, RM15-83-1 | Rigless Australia - 1 | J.22.110299 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-01-05 |  | 2022-01-08 10:00 | 2022-01-14 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 35899.93 | 3 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1020036 | O.1020036.01 | A.1020036.01.07 | PNX-Perfo | SANTOS LIMITED | RM49-168-1 | WILD DESERT RIG 4 | J.21.109606 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2021-10-04 08:00 |  | 2021-10-04 12:00 | 2021-10-11 11:59 |  |  | Roma WL | ysaeedabadian | 2022-10-03 15:32 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 5 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1020036 | O.1020036.01 | A.1020036.01.06 | PNX 6th | SANTOS LIMITED |  | WILD DESERT RIG 4 | J.21.109013 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-09-05 |  | 2021-09-05 14:00 | 2021-09-08 13:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1020036 | O.1020036.01 | A.1020036.01.05 | PNX 5th well | SANTOS LIMITED | RM49-170-1 | WILD DESERT RIG 4 | J.21.109010 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-09-02 |  | 2021-09-03 18:00 | 2021-09-06 17:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 2 |  |  |  | 70.8 | 33.3 | 0 | 0 | 31.3 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1020036 | O.1020036.01 | A.1020036.01.04 | PNX 4thwell | SANTOS LIMITED | RM49-171-1, RM49-170-1, RM49-169-1 | WILD DESERT RIG 4 | J.21.109007 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-08-31 08:00 |  | 2021-09-01 12:00 | 2021-09-08 11:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 14 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1020036 | O.1020036.01 | A.1020036.01.03 | PNX 3rd Well | SANTOS LIMITED |  | WILD DESERT RIG 4 | J.22.110261 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-01-19 |  | 2022-01-21 | 2022-01-23 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1020036 | O.1020036.01 | A.1020036.01.02 | PNX Well 2 | SANTOS LIMITED | RM15-102-1 | WILD DESERT RIG 4 | J.22.110259 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-05-30 |  | 2022-06-04 | 2022-06-07 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 13027.94 | 1 |  |  |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1020036 | O.1020036.01 | A.1020036.01.01 | Pre frac PNX job | SANTOS LIMITED | RM49-169-1, RM49-168-1, RM49-170-1 | WILD DESERT RIG 4 | J.21.109003 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-07-28 |  | 2021-07-28 22:00 | 2021-08-02 21:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1020008 | O.1020008.01 | A.1020008.01.04 | Ungani-8H Logging_Dec | BURU ENERGY LIMITED |  | ENSIGN 963 | J.21.108874 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-12-01 |  | 2021-12-01 | 2022-02-28 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:54 | FDPSystemUser |  | No |  |  |  |  | James Cade |  | 0 | 1 |  |  |  | 41.7 | 16.7 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1020008 | O.1020008.01 | A.1020008.01.03 | Ungani-8H Logging | BURU ENERGY LIMITED |  | ENSIGN 963 | J.21.108872 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2021-11-15 | 2021-11-11 |  | 2021-11-15 | 2021-11-24 23:59 |  | 2021-11-28 23:59 | New Burn WL | BAhmad | 2022-10-03 09:53 | FDPSystemUser |  | No |  |  |  |  | James Cade |  | 0 | 3 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1020008 | O.1020008.01 | A.1020008.01.02 | Rafael-1 Logging | BURU ENERGY LIMITED |  | ENSIGN 963 | J.21.108871 | RPE | ES-OH-NO | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-09-16 |  | 2021-09-20 | 2021-09-23 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:53 | FDPSystemUser |  | No |  |  |  |  | James Cade |  | 0 | 3 |  |  |  | 50 | 33.3 | 100 | 50 | 50 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1020008 | O.1020008.01 | A.1020008.01.01 | Buru Open hole | BURU ENERGY LIMITED | Currajong 1 | ENSIGN 963 | J.21.108867 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-07-14 |  | 2021-07-18 | 2021-07-25 23:59 |  |  | New Burn WL | frosa2 | 2022-10-03 09:53 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 228322.81 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1019890 | O.1019890.01 | A.1019890.01.01 | Greymouth Frac #1 | GREYMOUTH PETROLEUM | Well #1 |  | J.21.109273 | RPS | FRAC-PROP | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-09-02 | 2021-09-01 |  | 2021-09-02 | 2021-09-09 23:59 |  | 2021-09-09 23:59 | AUS East Coast WS | THuynh | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Tony Huynh |  | 0 | 6 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Omar Mosleh | WS Production Services
P.1019660 | O.1019660.02 | A.1019660.02.10 | Hides_D1 P&A Feb PCE Rental | EXXONMOBIL PNG LIMITED | HIDES D1 | Superior Energy Rig 32 | J.23.031105 | RPI | PS-WL-NO | Low | Cancelled | Close - PSD |  | Not Required | Not Started | In Progress |  | 2023-01-24 |  | 2023-01-26 | 2023-02-25 23:59 |  |  | Port Moresby WL | MElsanousi | 2023-02-08 11:06 | MElsanousi |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 0 |  | L0 - No RO |  | 58.3 | 33.3 | 100 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1019660 | O.1019660.02 | A.1019660.02.09 | Hides_D1 P&A Jan PCE Rental | EXXONMOBIL PNG LIMITED | HIDES D1 | Superior Energy Rig 32 | J.23.026016 | RPI | PS-WL-NO | Low | Confirmed | Design - CEC |  | Not Required | Not Required | Not Required |  | 2023-01-10 |  | 2023-01-12 | 2023-01-25 23:59 |  |  | Port Moresby WL | MElsanousi | 2023-01-14 08:33 | MElsanousi |  | No |  |  |  |  | Mazhar Iqbal |  | 21086.4 | 0 |  | L0 - No RO |  | 100 | 33.3 | 100 | 75 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1019660 | O.1019660.02 | A.1019660.02.08 | Hides_D1 P&A Dec Rentals | EXXONMOBIL PNG LIMITED | HIDES D1 | Superior Energy Rig 32 | J.22.130683 | RPI | PS-WL-NO | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | Design Completed |  | 2022-11-26 |  | 2022-11-30 | 2022-12-25 23:59 |  |  | Port Moresby WL | MElsanousi | 2023-01-08 14:46 | MElsanousi |  | No |  |  |  |  | Mazhar Iqbal |  | 21086.4 | 0 |  | L0 - No RO |  | 100 | 66.7 | 100 | 75 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1019660 | O.1019660.02 | A.1019660.02.02 | 9-7/8" Cement Evaluation | EXXONMOBIL PNG LIMITED | HIDES D1 | Superior Energy Rig 32 | J.22.110461 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-05-26 | 2022-05-28 14:33 |  | 2022-05-31 | 2022-06-09 23:59 |  | 2022-06-10 23:59 | Port Moresby WL | PZuliani | 2023-01-08 14:42 | MElsanousi |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 139279.29 | 2 |  |  |  | 75 | 83.3 | 0 | 50 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1019660 | O.1019660.02 | A.1019660.02.07 | Hides_D1 Nov_Rentals | EXXONMOBIL PNG LIMITED | HIDES D1 | Superior Energy Rig 32 | J.22.123430 | RPI | PS-WL-NO | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-11-04 | 2022-11-01 |  | 2022-11-04 | 2022-11-26 23:59 |  | 2022-11-26 23:59 | Port Moresby WL | MElsanousi | 2022-11-30 16:41 | MElsanousi |  | No |  |  |  |  | Mazhar Iqbal |  | 97034.64 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1019660 | O.1019660.02 | A.1019660.02.01 | D1 P&A | EXXONMOBIL PNG LIMITED | HIDES D1 | Superior Energy Rig 32 | J.22.110462 | RPI | PS-WL-Ops | Medium | Operationally Complete | Execute - PSD |  | Design Completed | Not Required | In Progress |  | 2022-05-21 |  | 2022-05-24 | 2022-06-27 23:59 |  |  | Port Moresby WL | JDukas | 2022-10-29 21:10 | MElsanousi |  | No |  |  |  |  | Rob Twigg |  | 61500 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1019660 | O.1019660.02 | A.1019660.02.06 | Hides_D1_30-Sep-2022 | EXXONMOBIL PNG LIMITED | HIDES D1 | Superior Energy Rig 32 | J.22.110458 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-09-29 |  | 2022-10-02 23:00 | 2022-10-27 22:59 |  |  | Port Moresby WL | MElsanousi | 2022-10-29 20:58 | MElsanousi |  | No |  |  |  |  | Rob Twigg |  | 351513.92 | 3 |  |  |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1019660 | O.1019660.02 | A.1019660.02.04 | 13-3/8" Temperature Log | EXXONMOBIL PNG LIMITED | Hides D1 | Superior Energy Rig 32 | J.22.110463 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-08-28 14:00 |  | 2022-08-29 08:00 | 2022-08-31 08:00 |  |  | Port Moresby WL | AIbrahim3 | 2022-10-03 13:20 | FDPSystemUser |  | No |  |  |  |  | Paulo Zuliani |  | 156900 | 2 |  |  |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1019660 | O.1019660.02 | A.1019660.02.05 | Hides_D1_13 3/8 CSG. | EXXONMOBIL PNG LIMITED | HIDES D1 | Superior Energy Rig 32 | J.22.110460 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-09-06 |  | 2022-09-09 11:00 | 2022-09-23 10:59 |  |  | Port Moresby WL | AIbrahim3 | 2022-10-03 13:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 47000 | 1 |  |  |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1019660 | O.1019660.02 | A.1019660.02.03 | 13-3/8" Casing Logging | EXXONMOBIL PNG LIMITED | Hides D1 | Superior Energy Rig 32 | J.22.110457 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed |  | 2022-06-11 |  | 2022-08-15 20:00 | 2022-10-29 19:59 |  |  | Port Moresby WL | PZuliani | 2022-10-03 13:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 132040.47 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1019660 | O.1019660.01 | A.1019660.01.01 | Sept Pressure Temp & PLT | EXXONMOBIL PNG LIMITED | HIDES D1 | SUPERIOR ENERGY RIG 32 | J.21.109104 | RPI | PS-WL-NO | Low | Confirmed | Design - CEC |  | Design Completed | Not Started | In Progress | 2021-09-11 | 2021-09-09 |  | 2021-09-11 | 2021-09-21 23:59 |  | 2021-09-21 23:59 | Port Moresby WL | frosa2 | 2022-10-03 13:20 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 1 |  | L0 - No RO |  | 58.3 | 50 | 100 | 50 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1019660 | O.1019660.01 | A.1019660.01.02 | Oct_PNG Activity | EXXONMOBIL PNG LIMITED |  | SUPERIOR ENERGY RIG 32 | J.21.109103 | RPI | PS-WL-NO | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2021-10-02 | 2021-10-02 |  | 2021-10-02 | 2021-12-06 23:59 |  | 2021-12-14 23:59 | Port Moresby WL | BAhmad | 2022-10-03 13:20 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 33.3 | 100 | 50 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1019660 | O.1019660.01 | A.1019660.01.03 | Nov_PNG Activity | EXXONMOBIL PNG LIMITED |  | SUPERIOR ENERGY RIG 32 | J.21.109102 | RPI | PS-WL-NO | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2021-11-02 | 2021-11-02 |  | 2021-11-02 | 2021-12-06 23:59 |  | 2021-12-14 23:59 | Port Moresby WL | BAhmad | 2022-10-03 13:20 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 33.3 | 100 | 50 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1019657 | O.1019657.01 | A.1019657.01.01 | Spartan TCP | SANTOS WESTERN AUSTRALIA |  | Noble Tom Prosser | J.22.109442 | RPI | TCP-PERM-JOB | High | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-07-31 |  | 2022-08-01 | 2023-01-31 23:59 |  |  | APG TS | RWallis | 2022-10-03 06:27 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TCP - Tubing-Conveyed Perforation
P.1019628 | O.1019628.01 | A.1019628.01.01 | PNG ops September | EXXONMOBIL PNG LIMITED |  |  | J.21.108865 | RPI | PS-WL-NO | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-09-01 |  | 2021-09-01 | 2021-09-30 23:59 |  |  | New Burn WL | frosa2 | 2022-10-03 09:52 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 0 |  |  |  | 33.3 | 33.3 | 100 | 50 | 45 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1019607 | O.1019607.02 | A.1019607.02.02 | USIT-CBL | ARROW ENERGY LTD | TIPTON 149 | MPC 001 | J.22.110985 | RPE | ES-CH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2022-08-22 05:00 | 2022-08-21 10:00 |  | 2022-08-22 06:00 | 2022-08-26 23:59 |  | 2022-08-27 00:59 | Roma WL | MRony2 | 2022-10-03 15:32 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 27826.51 | 1 |  | L3 - Full RO |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1019607 | O.1019607.02 | A.1019607.02.07 | USIT-Density | ARROW ENERGY LTD | Tipton 149 | MPC 001 | J.22.110392 | RPE | ES-CH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-09-18 10:00 |  | 2022-09-19 06:00 | 2022-09-20 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1019607 | O.1019607.02 | A.1019607.02.04 | Well-3 | ARROW ENERGY LTD | Tipton 149 | MPC 001 | J.22.110388 | RPE | ES-CH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-09-11 10:00 |  | 2022-09-12 06:00 | 2022-09-13 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1019607 | O.1019607.02 | A.1019607.02.05 | Well 4 | ARROW ENERGY LTD | Tipton 149 | MPC 001 | J.22.110382 | RPE | ES-CH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-09-14 10:00 |  | 2022-09-15 06:00 | 2022-09-16 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1019607 | O.1019607.02 | A.1019607.02.06 | Well 5 | ARROW ENERGY LTD | Tipton 149 | MPC 001 | J.22.110380 | RPE | ES-CH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-09-21 10:00 |  | 2022-09-22 06:00 | 2022-09-23 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1019607 | O.1019607.02 | A.1019607.02.08 | PEX-HRLA_SS-CMR (Well-2) | ARROW ENERGY LTD | Tipton 149 | MPC 001 | J.22.110378 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-09-07 10:00 |  | 2022-09-08 06:00 | 2022-09-09 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1019607 | O.1019607.02 | A.1019607.02.03 | Well-2 | ARROW ENERGY LTD | Tipton 149 | MPC 001 | J.22.110377 | RPE | ES-CH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-09-06 10:00 |  | 2022-09-07 06:00 | 2022-09-08 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1019607 | O.1019607.02 | A.1019607.02.01 | USIT-CBL | ARROW ENERGY LTD | Tipton 149 | MPC 001 | J.21.109082 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-12-24 10:00 |  | 2021-12-25 06:00 | 2021-12-26 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 19539.96 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1019607 | O.1019607.01 | A.1019607.01.01 | USIT-Tractor | ARROW ENERGY LTD | Daandine 205 | Wild Desert Rig 4 | J.21.109001 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-09-05 |  | 2021-09-06 10:00 | 2021-09-14 09:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 183235.87 | 3 |  |  |  | 58.3 | 33.3 | 0 | 75 | 50 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1019461 | O.1019461.01 | A.1019461.01.04 | WBT-3 | ENI JPDA 11-106 B.V. | WBT-1 | Valaris MS-1 | J.21.108347 | RPI | TSWT-NOSEPNOVX-JOB | High | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2021-11-26 | 2021-11-26 |  | 2021-11-26 | 2021-12-25 23:59 |  | 2022-01-13 23:59 | APG TS | GRoxo | 2022-10-03 06:28 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Gabriela Soter Roxo Teckemeier |  | 0 | 1 |  | L0 - No RO | [7 empty] | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1019461 | O.1019461.01 | A.1019461.01.03 | TCP Execution | ENI JPDA 11-106 B.V. |  | Valaris MS-1 | J.21.108346 | RPI | TCP-RENTAL | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2021-10-27 | 2021-10-16 |  | 2021-10-27 | 2022-02-21 23:59 |  | 2022-02-21 23:59 | APG TS | GRoxo | 2022-10-03 06:28 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 0 | 5 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TCP - Tubing-Conveyed Perforation
P.1019461 | O.1019461.01 | A.1019461.01.02 | WBT-4 Bleed Off | ENI JPDA 11-106 B.V. | WBT-1 | Valaris MS-1 | J.21.108345 | RPI | TSWT-NOSEPNOVX-JOB | High | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2021-10-27 | 2021-09-28 |  | 2021-11-13 08:00 | 2021-11-24 07:59 |  | 2021-11-06 23:59 | APG TS | GRoxo | 2022-10-03 06:27 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Ferly Komul |  | 0 | 1 |  | L0 - No RO | [7 empty] | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1019461 | O.1019461.01 | A.1019461.01.01 | Job Design | ENI JPDA 11-106 B.V. |  | Valaris MS-1 | J.21.108341 | RPI | TCP-SALE | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2021-08-27 |  | 2021-08-27 | 2021-12-22 23:59 |  |  | APG TS | MSwara | 2022-10-03 06:27 | FDPSystemUser |  | No |  |  |  |  | Ferly Komul |  | 0 | 4 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TCP - Tubing-Conveyed Perforation
P.1018746 | O.1018746.04 | A.1018746.04.01 | Beach Well 23 | BEACH ENERGY LTD | Well #25 | SAVANNA 184 | J.26.000180 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2026-08-02 20:00 | 2026-08-01 22:00 | 2026-07-30 22:00 | 2026-08-02 21:00 | 2026-08-05 06:00 | 2026-08-05 22:00 | 2026-08-05 06:00 | Moomba WL | AKavooris | 2025-11-26 16:00 | CKok3 |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 4 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.04 | A.1018746.04.02 | Martlet 10 | BEACH ENERGY LTD | MARTLET 10 | SAVANNA 184 | J.24.039860 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2024-01-12 22:00 | 2024-01-12 |  | 2024-01-12 23:00 | 2024-01-15 08:00 |  | 2024-01-15 08:00 | Moomba WL | AKavooris | 2024-08-02 08:33 | KKeese |  | No |  |  |  | ROE WL Jakarta | Shameer Mumtaz Ali |  | 0 | 1 |  | L2 - Shift RO |  | 100 | 83.3 | 0 | 100 | 85 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.03 | A.1018746.03.01 | Magic Beach 2 | BEACH ENERGY LTD | MAGIC BEACH 2 | SAVANNA 184 | J.26.000178 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-12-21 04:00 | 2023-12-19 19:00 |  | 2023-12-21 05:00 | 2023-12-23 14:00 |  | 2023-12-23 14:00 | Moomba WL | HChapman3 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Jakarta | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.03 | A.1018746.03.02 | Green Bay 1 | BEACH ENERGY LTD | GREEN BAY 1 | SAVANNA 184 | J.23.178422 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-01-01 05:00 | 2023-12-30 20:00 |  | 2024-01-01 06:00 | 2024-01-04 15:00 |  | 2024-01-04 15:00 | Moomba WL | ASamokhin | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Jakarta | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.67 | Marion _1_QC-MDT | BEACH ENERGY LTD | MARION 1 | Saxon Rig 184 | J.23.027689 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-09-27 23:00 | 2023-09-27 |  | 2023-09-27 23:00 | 2023-09-30 07:00 |  | 2023-09-30 09:00 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 4 |  | L3 - Full RO |  | 100 | 100 | 0 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.62 | Skyrocket 1_QC-FMI_MDT | BEACH ENERGY LTD | SKYROCKET 1 | Saxon Rig 184 | J.23.027684 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-08-19 23:00 | 2023-08-19 |  | 2023-08-19 23:00 | 2023-08-22 07:00 |  | 2023-08-22 09:00 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 30477.78 | 3 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.64 | Growler 22 | BEACH ENERGY LTD | GROWLER 22 | Saxon Rig 184 | J.23.027686 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2023-09-08 03:00 | 2023-09-07 11:00 |  | 2023-09-08 03:00 | 2023-09-10 11:00 |  | 2023-09-10 13:00 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 4 |  | L3 - Full RO |  | 100 | 100 | 0 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.61 | Mustang 4 QC-MDT | BEACH ENERGY LTD | MUSTANG 4 | Saxon Rig 184 | J.23.027683 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-08-10 18:00 | 2023-08-10 16:00 |  | 2023-08-10 18:00 | 2023-08-13 02:00 |  | 2023-08-13 04:00 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Jakarta | Mazhar Iqbal |  | 29629.63 | 6 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.66 | Bangalee South 1 | BEACH ENERGY LTD | BANGALEE SOUTH 1 | Saxon Rig 184 | J.23.027688 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-10-08 19:00 | 2023-10-07 12:00 |  | 2023-10-08 20:00 | 2023-10-11 04:00 |  | 2023-10-11 05:00 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Jakarta | Shameer Mumtaz Ali |  | 0 | 4 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.69 | Wooley Rock 1 | BEACH ENERGY LTD | WOOLEY ROCK 1 | Saxon Rig 184 | J.23.027691 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-10-28 15:00 | 2023-10-25 |  | 2023-10-28 16:00 | 2023-10-31 01:00 |  | 2023-10-31 01:00 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.65 | Kangaroo 4_QC-MDT | BEACH ENERGY LTD | KANGAROO 4 | Saxon Rig 184 | J.23.027687 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-09-18 02:00 | 2023-09-17 16:00 |  | 2023-09-18 02:00 | 2023-09-20 10:00 |  | 2023-09-20 12:00 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 4 |  | L3 - Full RO |  | 100 | 100 | 0 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.68 | Windmill West 1 | BEACH ENERGY LTD | WINDMILL WEST 1 | Saxon Rig 184 | J.23.027690 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-10-17 21:00 | 2023-10-16 13:00 |  | 2023-10-17 22:00 | 2023-10-20 06:00 |  | 2023-10-20 07:00 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Jakarta | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 100 | 83.3 | 0 | 100 | 85 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.58 | Callawonga North 1 | BEACH ENERGY LTD | CALLAWONGA NORTH 1 | Saxon Rig 184 | J.23.027680 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-12-04 22:00 | 2023-12-04 |  | 2023-12-04 23:00 | 2023-12-07 07:00 |  | 2023-12-07 08:00 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 3 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.70 | Tractor 1 | BEACH ENERGY LTD | MARTLET 009, TRACTOR 1 | Saxon Rig 184 | J.23.087846 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-11-02 22:00 | 2023-11-02 | 2023-10-30 12:00 | 2023-11-02 23:00 | 2023-11-10 08:00 | 2023-11-10 23:00 | 2023-11-10 08:00 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 4 |  | L3 - Full RO |  | 91.7 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.72 | Coorong 2 | BEACH ENERGY LTD | COORONG 2 | Saxon Rig 184 | J.23.087852 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2023-11-15 22:00 | 2023-11-14 | 2023-11-12 | 2023-11-15 23:00 | 2023-11-18 08:00 | 2023-11-19 | 2023-11-18 08:00 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 1 |  | L1 - Support RO |  | 100 | 83.3 | 0 | 100 | 85 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.74 | Chadinga 1 | BEACH ENERGY LTD | CHADINGA 1 | Saxon Rig 184 | J.23.172721 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-12-09 22:00 | 2023-12-08 | 2023-12-06 | 2023-12-09 23:00 | 2023-12-12 08:00 | 2023-12-13 | 2023-12-12 08:00 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 3 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.75 | Magic Beach 2 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.23.087854 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-12-21 22:00 | 2023-12-21 | 2023-12-18 23:00 | 2023-12-21 23:00 | 2023-12-24 08:00 | 2023-12-24 23:00 | 2023-12-24 08:00 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 3 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.76 | Saro 1 | BEACH ENERGY LTD | SARO 1 | Saxon Rig 184 | J.23.127287 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-08-28 23:00 | 2023-08-28 | 2023-08-28 | 2023-08-28 23:00 | 2023-08-31 07:00 | 2023-09-01 | 2023-08-31 09:00 | Moomba WL | AKavooris | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 30477.78 | 4 |  | L3 - Full RO |  | 100 | 50 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.77 | QC_MDT | BEACH ENERGY LTD | GROWLER 22 | Saxon Rig 184 | J.23.132631 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-08-31 23:00 | 2023-08-31 |  | 2023-08-31 23:00 | 2023-09-03 07:00 |  | 2023-09-03 09:00 | Moomba WL | AKavooris | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 4 |  | L1 - Support RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.79 | Beach Well 21 | BEACH ENERGY LTD | MARTLET 009 | Saxon Rig 184 | J.24.022169 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-01-15 22:00 | 2024-01-15 |  | 2024-01-15 23:00 | 2024-01-18 08:00 |  | 2024-01-18 08:00 | Moomba WL | KKeese | 2024-01-15 08:51 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 4 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.86 | Beach Well 28 | BEACH ENERGY LTD | MARTLET 009 | Saxon Rig 184 | J.24.022176 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-03-24 22:00 | 2024-03-24 |  | 2024-03-24 23:00 | 2024-03-27 08:00 |  | 2024-03-27 08:00 | Moomba WL | KKeese | 2024-01-10 16:28 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 4 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.85 | Beach Well 27 | BEACH ENERGY LTD | MARTLET 009 | Saxon Rig 184 | J.24.022175 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-03-10 22:00 | 2024-03-10 |  | 2024-03-10 23:00 | 2024-03-13 08:00 |  | 2024-03-13 08:00 | Moomba WL | KKeese | 2024-01-10 16:28 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 4 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.84 | Beach Well 26 | BEACH ENERGY LTD | MARTLET 009 | Saxon Rig 184 | J.24.022174 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-03-01 22:00 | 2024-03-01 |  | 2024-03-01 23:00 | 2024-03-04 08:00 |  | 2024-03-04 08:00 | Moomba WL | KKeese | 2024-01-10 16:18 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 4 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.83 | Beach Well 25 | BEACH ENERGY LTD | MARTLET 009 | Saxon Rig 184 | J.24.022173 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-02-25 22:00 | 2024-02-25 |  | 2024-02-25 23:00 | 2024-02-28 08:00 |  | 2024-02-28 08:00 | Moomba WL | KKeese | 2024-01-10 16:17 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 4 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.82 | Beach Well 24 | BEACH ENERGY LTD | MARTLET 009 | Saxon Rig 184 | J.24.022172 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-02-18 22:00 | 2024-02-18 |  | 2024-02-18 23:00 | 2024-02-21 08:00 |  | 2024-02-21 08:00 | Moomba WL | KKeese | 2024-01-10 16:17 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 4 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.81 | Beach Well 23 | BEACH ENERGY LTD | MARTLET 009 | Saxon Rig 184 | J.24.022171 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-02-05 22:00 | 2024-02-05 |  | 2024-02-05 23:00 | 2024-02-08 08:00 |  | 2024-02-08 08:00 | Moomba WL | KKeese | 2024-01-10 16:17 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 4 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.78 | Beach Well 20 | BEACH ENERGY LTD | MARTLET 009 | Saxon Rig 184 | J.24.022168 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-01-01 22:00 | 2024-01-01 |  | 2024-01-01 23:00 | 2024-01-04 08:00 |  | 2024-01-04 08:00 | Moomba WL | KKeese | 2023-12-30 07:50 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 4 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.80 | Beach Well 22 | BEACH ENERGY LTD | MARTLET 009 | Saxon Rig 184 | J.24.022170 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-01-28 22:00 | 2024-01-28 |  | 2024-01-28 23:00 | 2024-01-31 08:00 |  | 2024-01-31 08:00 | Moomba WL | KKeese | 2023-12-30 07:50 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 4 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.63 | Beach Well 7 | BEACH ENERGY LTD | MARTLET 009 | Saxon Rig 184 | J.23.027685 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-08-27 23:00 | 2023-08-27 | 2023-08-25 | 2023-08-27 23:00 | 2023-08-30 07:00 | 2023-08-30 23:00 | 2023-08-30 09:00 | Moomba WL | KKeese | 2023-08-29 11:26 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 4 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.71 | Beach Well 15 | BEACH ENERGY LTD | MARTLET 009 | Saxon Rig 184 | J.23.087848 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2023-11-12 22:00 | 2023-11-12 | 2023-11-09 23:00 | 2023-11-12 23:00 | 2023-11-15 08:00 | 2023-11-15 23:00 | 2023-11-15 08:00 | Moomba WL | KKeese | 2023-08-28 16:58 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 4 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.73 | Beach Well 17 | BEACH ENERGY LTD | MARTLET 009 | Saxon Rig 184 | J.23.087853 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-12-01 22:00 | 2023-12-01 | 2023-11-28 23:00 | 2023-12-01 23:00 | 2023-12-04 08:00 | 2023-12-04 23:00 | 2023-12-04 08:00 | Moomba WL | KKeese | 2023-08-28 16:55 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 4 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.59 | Beach Well 3 | BEACH ENERGY LTD | MARTLET 009 | Saxon Rig 184 | J.23.027681 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-12-13 22:00 | 2023-12-13 | 2023-12-10 23:00 | 2023-12-13 23:00 | 2023-12-16 07:00 | 2023-12-16 22:00 | 2023-12-16 08:00 | Moomba WL | KKeese | 2023-08-28 16:55 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 4 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.60 | Beach Well 4 | BEACH ENERGY LTD | MARTLET 009 | Saxon Rig 184 | J.23.027682 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-07-26 23:00 | 2023-07-26 | 2023-07-24 | 2023-07-26 23:00 | 2023-08-01 07:00 | 2023-08-01 23:00 | 2023-08-01 09:00 | Moomba WL | KKeese | 2023-07-31 08:10 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 4 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.56 | Chiton South East 1 | BEACH ENERGY LTD | CHITON SOUTHEAST 1 | Saxon Rig 184 | J.23.021956 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-05-12 23:00 | 2023-05-12 |  | 2023-05-12 23:00 | 2023-05-15 07:00 |  | 2023-05-15 09:00 | Moomba WL | KKeese | 2023-05-30 11:33 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 37616.71 | 3 |  | L2 - Shift RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.55 | Bauer North 4 | BEACH ENERGY LTD | BAUER NORTH 4 | Saxon Rig 184 | J.23.021955 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-05-05 23:00 | 2023-05-01 |  | 2023-05-05 23:00 | 2023-05-08 07:00 |  | 2023-05-08 08:00 | Moomba WL | KKeese | 2023-05-30 11:24 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 62612.22 | 1 |  | L1 - Support RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.57 | Beach Well 1 | BEACH ENERGY LTD | MARTLET 009 | Saxon Rig 184 | J.23.027679 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-07-01 23:00 | 2023-07-01 |  | 2023-07-01 23:00 | 2023-07-04 07:00 |  | 2023-07-04 09:00 | Moomba WL | KKeese | 2023-05-10 07:17 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 4 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.53 | QC-MDT_Martlet-8 | BEACH ENERGY LTD | MARTLET 008 | Saxon Rig 184 | J.22.110098 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-09-30 |  | 2022-10-01 23:00 | 2022-10-04 08:00 |  |  | Moomba WL | ysaeedabadian | 2022-11-05 00:28 | eismail |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.54 | Martlet 9 | BEACH ENERGY LTD | MARTLET 009 | Saxon Rig 184 | J.22.113715 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-10-12 |  | 2022-10-12 23:00 | 2022-10-15 07:00 |  |  | Moomba WL | KKeese | 2022-10-13 09:35 | OAzarenko |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 3 |  |  |  | 75 | 0 | 0 | 100 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.52 | Martlet 6 | BEACH ENERGY LTD | Martlet 6 | Saxon Rig 184 | J.22.110036 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-08-11 | 2022-08-11 |  | 2022-08-11 | 2022-08-15 23:59 |  | 2022-08-15 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 12:34 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.51 | Beach OH | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109966 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-08-03 | 2022-08-04 |  | 2022-08-04 | 2022-08-08 23:59 |  | 2022-08-08 23:59 | Moomba WL | eismail | 2022-10-03 12:27 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.50 | Rocky 1 | BEACH ENERGY LTD | Rocky 1 | Saxon Rig 184 | J.22.109965 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-08-03 | 2022-08-04 |  | 2022-08-04 | 2022-08-08 23:59 |  | 2022-08-08 23:59 | Moomba WL | eismail | 2022-10-03 12:27 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.49 | Knapmans 1 | BEACH ENERGY LTD | Knapmans 1 | Saxon Rig 184 | J.22.109962 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-07-27 | 2022-07-28 |  | 2022-07-28 | 2022-08-01 23:59 |  | 2022-08-01 23:59 | Moomba WL | KKeese | 2022-10-03 12:27 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  |  |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.48 | McLaren 1 | BEACH ENERGY LTD | McLaren 1 | Saxon Rig 184 | J.22.109940 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-06-14 16:30 | 2022-06-13 22:30 |  | 2022-06-14 16:30 | 2022-06-19 16:29 |  | 2022-06-19 16:29 | Moomba WL | eismail | 2022-10-03 12:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 60654.65 | 2 |  |  |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.47 | Beach OH Logging #23 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109935 | RPE | ES-OH-Ops | High | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-06-12 08:00 | 2022-06-11 17:00 |  | 2022-06-12 08:00 | 2022-06-14 07:59 |  | 2022-08-05 07:59 | Moomba WL | YPouryan | 2022-10-03 12:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 101389.7 | 2 |  |  |  | 79.2 | 41.7 | 0 | 0 | 36.3 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.46 | Coorong 1 | BEACH ENERGY LTD | Coorong 1 | Saxon Rig 184 | J.22.109819 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-05-23 | 2022-05-23 |  | 2022-05-23 | 2022-05-26 23:59 |  | 2022-05-27 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 12:13 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  |  |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.45 | Kiandra 1 | BEACH ENERGY LTD | Kiandra 1 | Saxon Rig 184 | J.22.109814 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-05-14 | 2022-05-15 |  | 2022-05-15 | 2022-05-19 23:59 |  | 2022-05-19 23:59 | Moomba WL | eismail | 2022-10-03 12:12 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.44 | Beach OH Logging #35 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109795 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-09-04 | 2022-09-05 |  | 2022-09-05 | 2022-09-09 23:59 |  | 2022-09-12 12:50 | Moomba WL | KKeese | 2022-10-03 12:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | 2 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.43 | Beach OH Logging #34 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109794 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-08-26 | 2022-08-27 |  | 2022-08-27 | 2022-08-31 23:59 |  | 2022-08-31 23:59 | Moomba WL | KKeese | 2022-10-03 12:10 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.42 | Beach OH Logging #33 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109793 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-08-17 | 2022-08-18 |  | 2022-08-18 | 2022-08-22 23:59 |  | 2022-08-22 23:59 | Moomba WL | KKeese | 2022-10-03 12:10 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.41 | Beach OH Logging #32 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109792 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-08-07 | 2022-08-08 |  | 2022-08-08 | 2022-08-12 23:59 |  | 2022-08-12 23:59 | Moomba WL | KKeese | 2022-10-03 12:10 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.40 | Beach OH Logging #38 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109784 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-08-25 | 2022-08-26 |  | 2022-08-26 | 2022-08-30 23:59 |  | 2022-09-02 12:50 | Moomba WL | KKeese | 2022-10-03 12:09 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.39 | Beach OH Logging #37 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109783 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-08-17 | 2022-08-18 |  | 2022-08-18 | 2022-08-22 23:59 |  | 2022-08-25 12:50 | Moomba WL | KKeese | 2022-10-03 12:09 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.38 | Beach OH Logging #36 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109782 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-08-09 | 2022-08-10 |  | 2022-08-10 | 2022-08-14 23:59 |  | 2022-08-17 12:50 | Moomba WL | KKeese | 2022-10-03 12:09 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.37 | Beach OH Logging #35 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109781 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-08-01 | 2022-08-02 |  | 2022-08-02 | 2022-08-06 23:59 |  | 2022-08-09 12:50 | Moomba WL | KKeese | 2022-10-03 12:09 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.36 | Beach OH Logging #34 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109780 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-07-22 | 2022-07-23 |  | 2022-07-23 | 2022-07-27 23:59 |  | 2022-07-30 12:50 | Moomba WL | KKeese | 2022-10-03 12:09 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.35 | Beach OH Logging #33 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109779 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-07-14 | 2022-07-15 |  | 2022-07-15 | 2022-07-19 23:59 |  | 2022-07-22 12:50 | Moomba WL | KKeese | 2022-10-03 12:09 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.34 | Beach OH Logging #32 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109778 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-07-06 | 2022-07-07 |  | 2022-07-07 | 2022-07-11 23:59 |  | 2022-07-11 23:59 | Moomba WL | KKeese | 2022-10-03 12:09 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.33 | Beach OH Logging #31 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109777 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-07-27 | 2022-07-28 |  | 2022-07-28 | 2022-08-01 23:59 |  | 2022-08-01 23:59 | Moomba WL | KKeese | 2022-10-03 12:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.32 | Magic Beach 1 | BEACH ENERGY LTD | Magic Beach 1 | Saxon Rig 184 | J.22.109765 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-03-30 12:00 | 2022-03-30 08:00 |  | 2022-03-30 12:00 | 2022-04-05 10:59 |  | 2022-04-05 10:59 | Moomba WL | SYalamanchi2 | 2022-10-03 12:07 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.31 | Ganarabba 1 | BEACH ENERGY LTD | Ganarabba 1 | Saxon Rig 184 | J.22.109753 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-03-07 | 2022-03-06 |  | 2022-03-07 | 2022-03-10 23:59 |  | 2022-03-10 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 12:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.30 | Beach OH Logging #30 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109643 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | Design Completed | Not Started | In Progress | 2022-06-12 22:00 | 2022-06-12 |  | 2022-06-13 22:00 | 2022-06-18 21:59 |  | 2022-06-21 10:50 | Moomba WL | KKeese | 2022-10-03 11:56 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.29 | Snug 1 | BEACH ENERGY LTD | Snug 1 | Saxon Rig 184 | J.22.109642 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-05-30 | 2022-05-31 |  | 2022-05-31 | 2022-06-04 23:59 |  | 2022-06-04 23:59 | Moomba WL | KKeese | 2022-10-03 11:56 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 60654.65 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.28 | Beach OH Logging #20 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109641 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-06-18 | 2022-06-19 |  | 2022-06-19 | 2022-06-23 23:59 |  | 2022-06-23 23:59 | Moomba WL | KKeese | 2022-10-03 11:56 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.27 | Beach OH Logging #19 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109640 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-05-21 | 2022-05-22 |  | 2022-05-22 | 2022-05-26 23:59 |  | 2022-05-29 12:50 | Moomba WL | KKeese | 2022-10-03 11:56 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.26 | Beach OH Logging #17 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109639 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-05-02 | 2022-05-03 |  | 2022-05-03 | 2022-05-07 23:59 |  | 2022-05-10 12:50 | Moomba WL | KKeese | 2022-10-03 11:56 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.25 | Hummocky 1_Quad Combo | BEACH ENERGY LTD | Hummocky 1 | Saxon Rig 184 | J.22.109638 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-05-08 | 2022-05-09 |  | 2022-05-09 | 2022-05-13 23:59 |  | 2022-05-13 23:59 | Moomba WL | KKeese | 2022-10-03 11:55 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.24 | Beach OH Logging # 16 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109637 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-04-23 | 2022-04-24 |  | 2022-04-24 | 2022-04-28 23:59 |  | 2022-05-01 12:50 | Moomba WL | KKeese | 2022-10-03 11:55 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.23 | Beach OH Logging # 18 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109636 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-05-01 | 2022-06-26 |  | 2022-06-29 | 2022-07-01 23:59 |  | 2022-05-06 23:59 | Moomba WL | KKeese | 2022-10-03 11:55 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.22 | Beach OH Logging # 15 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109635 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-05-12 | 2022-05-13 |  | 2022-05-13 | 2022-05-17 23:59 |  | 2022-05-20 12:50 | Moomba WL | KKeese | 2022-10-03 11:55 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.21 | Bangalee 1 | BEACH ENERGY LTD | Bangalee 1 | Saxon Rig 184 | J.22.109634 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-04-21 18:00 | 2022-04-21 18:00 |  | 2022-04-22 18:00 | 2022-04-29 17:59 |  | 2022-04-29 17:59 | Moomba WL | KKeese | 2022-10-03 11:55 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 62473.2 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.20 | Morialta 1_QC | BEACH ENERGY LTD | Morialta 1 | Saxon Rig 184 | J.22.109633 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-04-12 | 2022-04-13 |  | 2022-04-13 | 2022-04-17 23:59 |  | 2022-04-17 23:59 | Moomba WL | KKeese | 2022-10-03 11:55 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 58.3 | 83.3 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.19 | Beach OH Logging # 11 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109632 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-03-24 01:00 | 2022-03-24 |  | 2022-03-25 | 2022-03-29 23:59 |  | 2022-04-01 12:50 | Moomba WL | KKeese | 2022-10-03 11:55 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.18 | Martlet 5 | BEACH ENERGY LTD | Marlet 5 | Saxon Rig 184 | J.22.109629 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-02-14 | 2022-02-13 |  | 2022-02-14 | 2022-02-18 23:59 |  | 2022-02-18 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 11:55 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.17 | Beach OH Logging #10 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109614 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-03-16 01:00 | 2022-03-17 |  | 2022-03-17 | 2022-03-21 23:59 |  | 2022-03-24 11:50 | Moomba WL | IWahbi | 2022-10-03 11:51 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.16 | Beach OH Logging #9 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109613 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-03-11 01:00 | 2022-03-12 |  | 2022-03-12 | 2022-03-16 23:59 |  | 2022-03-19 11:49 | Moomba WL | IWahbi | 2022-10-03 11:50 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.15 | Beach OH Logging #8 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109612 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-03-06 01:00 | 2022-03-07 |  | 2022-03-07 | 2022-03-11 23:59 |  | 2022-03-14 11:50 | Moomba WL | IWahbi | 2022-10-03 11:50 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.14 | Beach OH Logging #7 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109611 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-03-01 01:00 | 2022-03-02 |  | 2022-03-02 | 2022-03-06 23:59 |  | 2022-03-09 11:49 | Moomba WL | IWahbi | 2022-10-03 11:50 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.13 | Stirling 1 | BEACH ENERGY LTD | Stirling 1 | Saxon Rig 184 | J.22.109610 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-02-24 16:00 | 2022-02-23 12:00 |  | 2022-02-24 15:00 | 2022-02-26 14:59 |  | 2022-02-26 16:00 | Moomba WL | IWahbi | 2022-10-03 11:50 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.12 | Beach OH Logging #5 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109609 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-02-16 23:00 | 2022-02-17 |  | 2022-02-17 | 2022-02-21 23:59 |  | 2022-02-24 11:49 | Moomba WL | IWahbi | 2022-10-03 11:50 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.11 | Beach OH Logging #4 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.22.109608 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-02-07 23:00 | 2022-02-08 |  | 2022-02-08 | 2022-02-12 23:59 |  | 2022-02-15 11:50 | Moomba WL | IWahbi | 2022-10-03 11:50 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.10 | Martlet 7 QC-MDT | BEACH ENERGY LTD | Martlet 007 | Saxon Rig 184 | J.22.109607 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-09-23 13:00 | 2022-09-24 10:00 |  | 2022-09-24 12:00 | 2022-09-25 23:59 |  | 2022-09-29 12:59 | Moomba WL | IWahbi | 2022-10-03 11:50 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 31327.97 | 2 |  |  |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.09 | Martlet 3 | BEACH ENERGY LTD | Martlet 3 | Saxon Rig 184 | J.22.109606 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-01-21 17:30 | 2022-01-20 |  | 2022-01-21 | 2022-01-25 23:59 |  | 2022-01-25 10:00 | Moomba WL | IWahbi | 2022-10-03 11:50 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 31678.85 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.08 | Martlet 4 | BEACH ENERGY LTD | Martlet 4 | Saxon Rig 184 | J.22.109605 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-01-10 01:00 | 2022-01-10 |  | 2022-01-11 | 2022-01-15 23:59 |  | 2022-01-16 00:59 | Moomba WL | IWahbi | 2022-10-03 11:50 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 28888.89 | 1 |  |  |  | 91.7 | 50 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.07 | Lowry Southwest1 DW1 | BEACH ENERGY LTD | LOWRY SOUTHWEST 1 | Saxon Rig 184 | J.21.108760 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-10-11 01:00 | 2021-10-11 | 2021-10-12 | 2021-10-11 | 2021-10-15 23:59 | 2021-10-20 | 2021-10-16 00:59 | Moomba WL | eismail | 2022-10-03 11:39 | FDPSystemUser |  | No |  |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail |  | 101389.7 | 2 |  |  |  | 83.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.06 | Wittelbee 1 DW 1 | BEACH ENERGY LTD | Wittelbee 1 DW1 | Saxon Rig 184 | J.21.108743 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress | 2021-09-17 | 2021-09-17 | 2021-09-17 | 2021-09-17 | 2021-09-24 23:59 | 2021-09-25 | 2021-09-24 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 66.7 | 33.3 | 0 | 75 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.05 | Lowry Southwest 1 | BEACH ENERGY LTD | LOWRY SOUTHWEST 1 | Saxon Rig 184 | J.21.108561 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-10-02 | 2021-10-02 | 2021-10-03 | 2021-10-02 | 2021-10-07 00:59 | 2021-10-11 | 2021-10-07 00:59 | Moomba WL | IWahbi | 2022-10-03 11:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 101389.7 | 1 |  |  |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.04 | Wittelbee 1 | BEACH ENERGY LTD | WITTLEBEE 1 | Saxon Rig 184 | J.21.108560 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-09-08 | 2021-09-08 | 2021-09-07 14:00 | 2021-09-08 | 2021-09-15 23:59 | 2021-09-19 | 2021-09-15 23:59 | Moomba WL | IWahbi | 2022-10-03 11:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 101389.7 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.03 | Lowry South 1 | BEACH ENERGY LTD | LOWRY SOUTH 1 | Saxon Rig 184 | J.21.108559 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-08-25 | 2021-08-25 | 2021-08-23 | 2021-08-25 | 2021-08-29 23:59 | 2021-08-29 | 2021-08-29 23:59 | Moomba WL | IWahbi | 2022-10-03 11:17 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 101389.7 | 2 |  |  |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.02 | Rosebay 1 | BEACH ENERGY LTD | ROSEBAY 1 | Saxon Rig 184 | J.21.108558 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-08-10 | 2021-08-11 | 2021-08-11 | 2021-08-11 | 2021-08-15 23:59 | 2021-08-16 | 2021-08-15 23:59 | Moomba WL | IWahbi | 2022-10-03 11:17 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 101389.7 | 4 |  |  |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1018746 | O.1018746.01 | A.1018746.01.01 | Kangaroo 2 | BEACH ENERGY LTD | Kangaroo 2 | Saxon Rig 184 | J.21.108557 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-07-30 07:00 | 2021-07-27 06:00 | 2021-07-28 | 2021-07-30 07:00 | 2021-08-04 06:59 | 2021-08-02 | 2021-08-04 06:59 | Moomba WL | IWahbi | 2022-10-03 11:17 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 87458.58 | 4 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1018744 | O.1018744.02 | A.1018744.02.01 | Kyalla 117 Intervention | ORIGIN ENERGY B2 PTY LIMITED | KYALLA 117 N2-1 |  | J.21.109605 | RPI | CT-WBCLEAN | Medium | Confirmed | Prepare - Mob |  | Design Completed | Design Completed | In Progress | 2021-09-13 | 2021-09-06 |  | 2021-09-13 | 2021-09-24 23:59 |  | 2021-09-24 23:59 | AUS East Coast WS | JMeyer9 | 2022-10-03 15:32 | FDPSystemUser |  | No |  |  |  |  | Ben Drew |  | 197677.55 | 1 |  |  |  | 78.1 | 25 | 0 | 50 | 48.8 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1018744 | O.1018744.01 | A.1018744.01.01 | CMLTP run | ORIGIN ENERGY B2 PTY LIMITED | Amungee NW-1H |  | J.21.109604 | RPI | CT-TOOLCON | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-08-17 | 2021-08-16 |  | 2021-08-17 | 2021-09-01 23:59 |  | 2021-09-01 23:59 | AUS East Coast WS | SKanaan | 2022-10-03 15:32 | FDPSystemUser |  | No |  |  |  |  | Ben Drew |  | 387887.56 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1018743 | O.1018743.02 | A.1018743.02.15 | Central March | CENTRAL PETROLEUM SERVICES PTY LTD | RANGE 9 | Silver City 23 | J.25.008351 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-02-26 | 2025-02-27 12:00 |  | 2025-02-27 12:00 | 2025-03-03 16:59 |  | 2025-03-31 23:59 | Roma WL | KKeese | 2024-11-16 16:42 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018743 | O.1018743.02 | A.1018743.02.10 | Central Feb | CENTRAL PETROLEUM SERVICES PTY LTD | RANGE 9 | Silver City 23 | J.24.022196 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2023-03-15 03:00 | 2025-01-12 12:00 |  | 2025-01-12 12:00 | 2025-01-16 16:59 |  | 2023-03-18 02:59 | Roma WL | KKeese | 2024-10-29 11:43 | KKeese |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 2 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018743 | O.1018743.02 | A.1018743.02.14 | ELIXIR PLACEHOLDER 3 | CENTRAL PETROLEUM SERVICES PTY LTD | Range 9 | Silver City 23 | J.24.022200 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-03-10 12:00 | 2024-03-09 12:00 |  | 2024-03-10 12:00 | 2024-03-14 16:59 |  | 2024-03-14 16:59 | Roma WL | KKeese | 2024-02-29 12:55 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 3 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018743 | O.1018743.02 | A.1018743.02.11 | Central Mar | CENTRAL PETROLEUM SERVICES PTY LTD | Range 9 | Silver City 23 | J.24.022197 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-03-01 12:00 | 2024-02-29 12:00 |  | 2024-03-01 12:00 | 2024-03-05 16:59 |  | 2024-03-05 16:59 | Roma WL | KKeese | 2024-02-29 12:55 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 3 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018743 | O.1018743.02 | A.1018743.02.13 | ELIXIR PLACEHOLDER 2 | CENTRAL PETROLEUM SERVICES PTY LTD | Range 9 | Silver City 23 | J.24.022199 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-02-10 12:00 | 2024-02-09 12:00 |  | 2024-02-10 12:00 | 2024-02-14 16:59 |  | 2024-02-14 16:59 | Roma WL | KKeese | 2024-01-10 16:18 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 3 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018743 | O.1018743.02 | A.1018743.02.09 | Central Jan | CENTRAL PETROLEUM SERVICES PTY LTD | Range 9 | Silver City 23 | J.24.022195 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-01-01 12:00 | 2023-12-31 12:00 |  | 2024-01-01 12:00 | 2024-01-05 16:59 |  | 2024-01-05 16:59 | Roma WL | KKeese | 2023-12-30 07:52 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 3 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018743 | O.1018743.02 | A.1018743.02.12 | ELIXIR PLACEHOLDER 1 | CENTRAL PETROLEUM SERVICES PTY LTD | Range 9 | Silver City 23 | J.24.022198 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-01-10 12:00 | 2024-01-09 12:00 |  | 2024-01-10 12:00 | 2024-01-14 16:59 |  | 2024-01-14 16:59 | Roma WL | KKeese | 2023-12-30 07:52 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 3 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018743 | O.1018743.02 | A.1018743.02.08 | Central TD December | CENTRAL PETROLEUM SERVICES PTY LTD | Range 9 | Silver City 23 | J.23.087899 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-12-11 12:00 | 2023-12-10 12:00 | 2023-12-13 18:00 | 2023-12-11 12:00 | 2023-12-15 16:59 | 2023-12-18 18:00 | 2023-12-15 16:59 | Roma WL | KKeese | 2023-08-29 11:34 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 3 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018743 | O.1018743.02 | A.1018743.02.07 | Central Intermediate November | CENTRAL PETROLEUM SERVICES PTY LTD | Range 9 | Silver City 23 | J.23.087898 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-11-13 12:00 | 2023-11-12 12:00 | 2023-11-15 18:00 | 2023-11-13 12:00 | 2023-11-17 16:59 | 2023-11-20 18:00 | 2023-11-17 16:59 | Roma WL | KKeese | 2023-08-29 11:22 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 2 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018743 | O.1018743.02 | A.1018743.02.06 | Central TD October | CENTRAL PETROLEUM SERVICES PTY LTD | Range 9 | Silver City 23 | J.23.087897 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-23 12:00 | 2023-10-22 12:00 | 2023-10-25 18:00 | 2023-10-23 12:00 | 2023-10-27 16:59 | 2023-10-30 18:00 | 2023-10-27 16:59 | Roma WL | KKeese | 2023-08-01 15:51 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 2 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018743 | O.1018743.02 | A.1018743.02.05 | Central Intermediate October | CENTRAL PETROLEUM SERVICES PTY LTD | Range 9 | Silver City 23 | J.23.087896 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2023-10-08 12:00 | 2023-10-11 18:00 | 2023-10-09 12:00 | 2023-10-13 16:59 | 2023-10-16 18:00 |  | Roma WL | KKeese | 2023-08-01 15:51 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018743 | O.1018743.02 | A.1018743.02.04 | Central August | CENTRAL PETROLEUM SERVICES PTY LTD | Range 9 | Silver City 23 | J.23.087870 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2023-08-06 12:00 |  | 2023-08-07 12:00 | 2023-08-11 16:59 |  |  | Roma WL | KKeese | 2023-06-15 16:28 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018743 | O.1018743.02 | A.1018743.02.03 | Central July | CENTRAL PETROLEUM SERVICES PTY LTD | Range 9 | Silver City 23 | J.23.087868 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-07-17 12:00 | 2023-07-16 12:00 |  | 2023-07-17 12:00 | 2023-07-21 16:59 |  | 2023-07-21 16:59 | Roma WL | KKeese | 2023-06-09 10:35 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018743 | O.1018743.02 | A.1018743.02.02 | Range-9 | CENTRAL PETROLEUM SERVICES PTY LTD | Range 9 | Silver City 23 | J.22.110984 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-02-18 12:00 |  | 2022-02-19 12:00 | 2022-02-19 16:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:32 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 9096.82 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1018743 | O.1018743.02 | A.1018743.02.01 | Range-10 | CENTRAL PETROLEUM SERVICES PTY LTD | Range-10 | Silver City 23 | J.22.110983 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-02-08 |  | 2022-02-08 20:00 | 2022-02-09 00:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:32 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1018743 | O.1018743.01 | A.1018743.01.04 | West Mereenie 30 | CENTRAL PETROLEUM SERVICES PTY LTD | WEST MEREENIE 30 | EASTERNWELL 29 | J.24.180195 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2025-01-28 | 2025-01-01 | 2025-01-11 | 2025-01-11 | 2025-02-26 23:59 | 2025-02-26 | 2025-02-26 23:59 | Roma WL | JEsmeralda | 2025-08-19 14:46 | SNiang |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 201124.11 | 3 |  | L3 - Full RO |  | 91.7 | 83.3 | 100 | 100 | 92.5 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1018743 | O.1018743.01 | A.1018743.01.05 | test | CENTRAL PETROLEUM SERVICES PTY LTD |  | EASTERNWELL 29 | J.25.122326 | RPE | ES-CH-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2025-07-03 | 2025-07-04 | 2025-07-04 | 2025-07-05 23:59 | 2025-07-06 |  | Roma WL | ESchmidtke | 2025-07-02 16:53 | ESchmidtke |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 0 |  | L3 - Full RO |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1018743 | O.1018743.01 | A.1018743.01.03 | West Mereenie 29 | CENTRAL PETROLEUM SERVICES PTY LTD | WEST MEREENIE 30, WEST MEREENIE 29 | EASTERNWELL 29 | J.24.180178 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-01-22 | 2024-12-01 |  | 2024-12-11 | 2025-01-24 |  | 2025-01-24 | Roma WL | JEsmeralda | 2025-02-01 20:48 | CKok3 |  | No |  |  |  |  | Irwan Wongso |  | 195331.38 | 6 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1018743 | O.1018743.01 | A.1018743.01.01 | WM-27 | CENTRAL PETROLEUM SERVICES PTY LTD | WEST MEREENIE 27 | EASTERNWELL 29 | J.21.109603 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-06-15 |  | 2021-06-25 | 2021-07-16 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:32 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 100847.84 | 2 |  |  |  | 58.3 | 83.3 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1018743 | O.1018743.01 | A.1018743.01.02 | WM-28 | CENTRAL PETROLEUM SERVICES PTY LTD | Mereenie 28, WEST MEREENIE 27 | EASTERNWELL 29 | J.21.108992 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-08-05 |  | 2021-08-05 10:00 | 2021-09-02 09:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 393469.79 | 2 |  |  |  | 58.3 | 83.3 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.32 | Gloss 1 | SANTOS LIMITED | GLOSS 1 | SLR RIG 183 | J.24.122469 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2024-06-27 | 2024-06-27 |  | 2024-06-27 | 2024-07-04 23:59 |  | 2024-07-04 23:59 | Moomba WL | YPouryan | 2024-08-13 16:27 | KKeese |  | No |  |  |  | ROE WL Mumbai | Elsamawal Mohamedelhassan Awadalla Ismail |  | 1575116.06 | 3 |  | L3 - Full RO |  | 79.2 | 25 | 0 | 0 | 31.3 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.26 | Big Lake 172 | SANTOS LIMITED | BIG LAKE 172 | SLR RIG 183 | J.23.027883 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-05-20 14:00 | 2023-05-19 | 2023-05-19 | 2023-05-20 14:00 | 2023-06-09 13:59 | 2023-06-07 | 2023-06-05 15:59 | Moomba WL | KKeese | 2023-07-29 07:56 | eismail |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 1629273.41 | 2 |  | L2 - Shift RO |  | 91.7 | 83.3 | 0 | 75 | 75 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.31 | Moomba 312 | SANTOS LIMITED | BIG LAKE 163 | SLR RIG 183 | J.23.083616 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-07-16 14:00 | 2023-07-13 |  | 2023-07-16 14:00 | 2023-07-24 13:59 |  | 2023-07-24 13:59 | Moomba WL | KKeese | 2023-06-13 09:28 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 1 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.30 | Moomba 311 | SANTOS LIMITED | BIG LAKE 163 | SLR RIG 183 | J.23.083615 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-07-03 14:00 | 2023-06-30 |  | 2023-07-03 14:00 | 2023-07-11 13:59 |  | 2023-07-11 15:59 | Moomba WL | KKeese | 2023-06-13 09:28 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.28 | Moomba 309 | SANTOS LIMITED | BIG LAKE 163 | SLR RIG 183 | J.23.071475 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-15 14:00 | 2023-06-12 |  | 2023-06-15 14:00 | 2023-06-23 13:59 |  | 2023-06-23 15:59 | Moomba WL | KKeese | 2023-06-09 15:51 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.29 | Moomba 310 | SANTOS LIMITED | BIG LAKE 163 | SLR RIG 183 | J.23.071476 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-20 14:00 | 2023-06-17 |  | 2023-06-20 14:00 | 2023-06-28 13:59 |  | 2023-06-28 15:59 | Moomba WL | KKeese | 2023-05-29 08:10 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.27 | Big Lake 170 | SANTOS LIMITED | BIG LAKE 170 | SLR RIG 183 | J.23.061996 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2023-04-22 14:00 | 2023-04-19 |  | 2023-04-22 14:00 | 2023-04-30 13:59 |  | 2023-04-30 13:59 | Moomba WL | KKeese | 2023-04-25 17:25 | ASamokhin |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 28369.69 | 1 |  | L2 - Shift RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.25 | Big Lake 170 | SANTOS LIMITED | BIG LAKE 163 | SLR RIG 183 | J.23.027882 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-04-14 14:00 | 2023-04-11 |  | 2023-04-14 14:00 | 2023-04-22 13:59 |  | 2023-04-22 13:59 | Moomba WL | KKeese | 2023-03-22 11:09 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 1 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.24 | Big Lake 163 | SANTOS LIMITED | BIG LAKE 163 | SLR RIG 183 | J.23.011739 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-01-13 15:00 | 2023-01-10 |  | 2023-01-13 14:00 | 2023-01-21 13:59 |  | 2023-01-21 14:59 | Moomba WL | KKeese | 2023-01-23 18:03 | YPouryan |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 28369.69 | 2 |  | L2 - Shift RO |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.23 | Moomba 302 | SANTOS LIMITED | MOOMBA 302 | SLR RIG 183 | J.22.119534 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-11-08 |  | 2022-11-10 22:00 | 2022-11-14 21:59 |  |  | Moomba WL | KKeese | 2022-11-17 08:48 | KKeese |  | No |  |  |  | ROE WL Abu Dhabi | Mazhar Iqbal |  | 28369.69 | 5 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.17 | Moomba 295 | SANTOS LIMITED | MOOMBA 295 | SLR RIG 183 | J.22.110000 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-10-05 |  | 2022-10-05 | 2022-10-10 23:59 |  |  | Moomba WL | KKeese | 2022-11-02 18:56 | OAzarenko |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 28369.69 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.20 | BIG LAKE (NE) DEV A | SANTOS LIMITED |  | SLR RIG 183 | J.22.110030 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-12-15 |  | 2022-12-15 | 2022-12-20 23:59 |  |  | Moomba WL | KKeese | 2022-10-27 10:36 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  |  |  | 66.7 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.19 | BIG LAKE CENT DEV R | SANTOS LIMITED |  | SLR RIG 183 | J.22.110029 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-11-30 |  | 2022-11-30 | 2022-12-05 23:59 |  |  | Moomba WL | KKeese | 2022-10-27 10:36 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.18 | Moomba 296 | SANTOS LIMITED | MOOMBA 296 | SLR RIG 183 | J.22.110001 | RPE | ES-OH-Ops | Medium | Operationally Complete | Execute - PSD |  | Design Completed | Not Required | In Progress |  | 2022-10-17 |  | 2022-10-19 | 2022-10-25 06:00 |  |  | Moomba WL | KKeese | 2022-10-27 08:31 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 28369.69 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.22 | Quadcombo_MDT | SANTOS LIMITED |  | SLR RIG 183 | J.22.114776 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | Design Completed | Not Started | In Progress | 2022-10-20 | 2022-10-20 |  | 2022-10-20 | 2022-10-21 23:59 |  | 2022-10-21 23:59 | Moomba WL | PLima7 | 2022-10-09 11:09 | PLima7 |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.21 | Big Lake 158 | SANTOS LIMITED | Big Lake 158 | SLR RIG 183 | J.22.110088 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-08-19 | 2022-08-19 |  | 2022-08-19 | 2022-08-21 23:59 |  | 2022-08-21 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 12:39 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.16 | Moomba 276 | SANTOS LIMITED | Moomba 276 | SLR RIG 183 | J.22.109964 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-08-06 | 2022-08-06 |  | 2022-08-06 | 2022-08-09 23:59 |  | 2022-08-09 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 12:27 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.15 | QC/MDT Moomba 270 | SANTOS LIMITED | Moomba 270 | SLR RIG 183 | J.22.109957 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-07-20 22:00 | 2022-07-18 |  | 2022-07-20 22:00 | 2022-07-28 21:59 |  | 2022-07-28 21:59 | Moomba WL | YPouryan | 2022-10-03 12:26 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  |  |  | 58.3 | 50 | 0 | 100 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.14 | Moomba 269_QC HT,MDT-Press | SANTOS LIMITED | Moomba 269 | SLR RIG 183 | J.22.109952 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-07-07 | 2022-07-07 |  | 2022-07-07 | 2022-07-16 23:59 |  | 2022-07-16 23:59 | Moomba WL | YPouryan | 2022-10-03 12:26 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.13 | QC/XPT | SANTOS LIMITED |  | SLR RIG 183 | J.22.109899 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-09-10 | 2022-09-10 |  | 2022-09-10 | 2022-09-15 23:59 |  | 2022-09-15 23:59 | Moomba WL | KKeese | 2022-10-03 12:21 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.12 | Big Lake 159 | SANTOS LIMITED | Big Lake 159 | SLR RIG 183 | J.22.109898 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-08-31 | 2022-08-30 |  | 2022-08-31 | 2022-09-05 23:59 |  | 2022-09-05 23:59 | Moomba WL | KKeese | 2022-10-03 12:21 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 26770.63 | 2 |  |  |  | 50 | 83.3 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.11 | QC(XY & X-Dipole) / XPT | SANTOS LIMITED |  | SLR RIG 183 | J.22.109897 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-08-17 | 2022-08-17 |  | 2022-08-17 | 2022-08-22 23:59 |  | 2022-08-22 23:59 | Moomba WL | KKeese | 2022-10-03 12:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.10 | QC/MDT Santos OH Logging #5 | SANTOS LIMITED |  | SLR RIG 183 | J.22.109888 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-07-18 23:00 | 2022-07-19 |  | 2022-07-19 | 2022-07-26 23:59 |  | 2022-07-27 00:59 | Moomba WL | KKeese | 2022-10-03 12:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.09 | QC/MDT Santos OH Logging #4 | SANTOS LIMITED |  | SLR RIG 183 | J.22.109887 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-07-05 23:00 | 2022-07-06 |  | 2022-07-06 | 2022-07-13 23:59 |  | 2022-07-14 00:59 | Moomba WL | KKeese | 2022-10-03 12:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.08 | Moolion South 1 | SANTOS LIMITED | Moolion South 1 | SLR RIG 183 | J.22.109815 | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-05-18 | 2022-05-17 |  | 2022-05-18 | 2022-05-22 23:59 |  | 2022-05-22 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 12:12 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | 2 |  |  |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.07 | Meranji 27 | SANTOS LIMITED | Meranji 27 | SLR RIG 183 | J.22.109747 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-03-04 | 2022-03-04 |  | 2022-03-04 | 2022-03-09 23:59 |  | 2022-03-09 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 12:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.06 | Tirrawarra 97 | SANTOS LIMITED | Tirrawarra 97 | SLR RIG 183 | J.22.109729 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-04-02 | 2022-04-02 |  | 2022-04-02 | 2022-04-09 22:59 |  | 2022-04-09 22:59 | Moomba WL | KKeese | 2022-10-03 12:04 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 46868.17 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.05 | Moomba 266_QC-HT, MDT-Press | SANTOS LIMITED | Moomba 266 | SLR RIG 183 | J.22.109659 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-06-19 23:00 | 2022-06-20 |  | 2022-06-20 | 2022-06-27 23:59 |  | 2022-06-27 22:59 | Moomba WL | KKeese | 2022-10-03 11:57 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.04 | Moomba 265 QCombo-MDT | SANTOS LIMITED | Moomba 265 | SLR RIG 183 | J.22.109658 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-06-04 23:00 | 2022-06-04 |  | 2022-06-05 | 2022-06-12 23:59 |  | 2022-06-12 22:59 | Moomba WL | KKeese | 2022-10-03 11:57 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 37090.36 | 2 |  |  |  | 66.7 | 83.3 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.03 | Kudrieke 4_Triple Combo, MDT, FMI-SS | SANTOS LIMITED | Kudrieke 4 | SLR RIG 183 | J.22.109657 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-05-01 23:00 | 2022-05-02 |  | 2022-05-02 | 2022-05-09 23:59 |  | 2022-05-09 22:59 | Moomba WL | KKeese | 2022-10-03 11:57 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.02 | Kudrieke 3 | SANTOS LIMITED | Kudrieke 3 | SLR RIG 183 | J.22.109623 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-01-22 | 2022-01-21 |  | 2022-01-22 | 2022-01-29 23:59 |  | 2022-01-29 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 11:54 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1018740 | O.1018740.02 | A.1018740.02.01 | Moorari 22 | SANTOS LIMITED | MOOMBA 266 | SLR RIG 183 | J.22.109622 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-07-06 22:00 | 2022-07-05 22:00 |  | 2022-07-06 22:00 | 2022-07-09 21:59 |  | 2022-07-11 21:59 | Moomba WL | KKeese | 2022-10-03 11:54 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 28369.69 | 1 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1018740 | O.1018740.01 | A.1018740.01.02 | Moorari 22 | SANTOS LIMITED | Moorari 22 | SLR RIG 183 | J.21.108796 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-12-04 01:00 | 2021-12-03 |  | 2021-12-04 | 2021-12-06 23:59 |  | 2021-12-07 00:59 | Moomba WL | eismail | 2022-10-03 11:51 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 91.7 | 33.3 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1018740 | O.1018740.01 | A.1018740.01.01 | Gidgealpa 65 | SANTOS LIMITED | Gidgealpa 65 | SLR RIG 183 | J.21.108556 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-07-10 | 2021-07-10 | 2021-07-16 | 2021-07-10 | 2021-07-14 23:59 | 2021-07-20 | 2021-07-14 23:59 | Moomba WL | IWahbi | 2022-10-03 11:17 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 27809.33 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1018739 | O.1018739.01 | A.1018739.01.09 | Armour Well 3 | ARMOUR ENERGY (SURAT BASIN) PTY LTD |  |  | J.23.088029 | RPS | FRAC-PROP | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-11-14 23:00 | 2025-11-15 |  | 2025-11-15 | 2025-11-19 23:59 |  | 2025-11-22 22:59 | AUS East Coast WS | HFerdjallah | 2024-10-25 15:05 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 1 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1018739 | O.1018739.01 | A.1018739.01.08 | Armour Well 2 | ARMOUR ENERGY (SURAT BASIN) PTY LTD |  |  | J.23.088028 | RPS | FRAC-PROP | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-04-09 23:00 | 2025-04-10 | 2025-04-09 23:00 | 2025-04-10 | 2025-04-17 23:59 | 2025-04-17 23:00 | 2025-04-17 22:59 | AUS East Coast WS | HFerdjallah | 2024-05-15 10:52 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 2 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1018739 | O.1018739.01 | A.1018739.01.05 | Myall-Creek 2 | ARMOUR ENERGY (SURAT BASIN) PTY LTD |  |  | J.23.008601 | RPS | FRAC-PROP | Low | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2025-03-31 23:00 | 2025-04-01 | 2025-03-31 23:00 | 2025-04-01 | 2025-04-08 23:59 | 2025-04-08 23:00 | 2025-04-08 22:59 | AUS East Coast WS | YHou5 | 2024-05-15 10:52 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 2 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1018739 | O.1018739.01 | A.1018739.01.10 | Armour well 2 | ARMOUR ENERGY (SURAT BASIN) PTY LTD |  |  | J.23.088030 | RPS | FRAC-PROP | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-23 | 2023-08-23 |  | 2023-08-23 | 2023-08-26 23:59 |  | 2023-08-30 23:59 | AUS East Coast WS | radinegara | 2023-05-22 13:21 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 2 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1018739 | O.1018739.01 | A.1018739.01.11 | Armour well 3 | ARMOUR ENERGY (SURAT BASIN) PTY LTD |  |  | J.23.088031 | RPS | FRAC-PROP | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-10-01 | 2024-10-01 |  | 2024-10-01 | 2024-10-04 23:59 |  | 2024-10-08 23:59 | AUS East Coast WS | radinegara | 2023-05-22 08:30 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1018739 | O.1018739.01 | A.1018739.01.07 | Well #3 | ARMOUR ENERGY (SURAT BASIN) PTY LTD |  |  | J.22.110477 | RPS | FRAC-PROP | Low | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2022-03-25 |  | 2022-03-25 | 2022-04-01 23:59 |  |  | AUS East Coast WS | YHou5 | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 2 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1018739 | O.1018739.01 | A.1018739.01.06 | Well #3 Armour | ARMOUR ENERGY (SURAT BASIN) PTY LTD |  |  | J.22.110476 | RPS | FRAC-PROP | Low | Cancelled | Close - PSD |  | Not Required | In Progress | In Progress |  | 2022-12-01 |  | 2022-12-05 | 2022-12-12 23:59 |  |  | AUS East Coast WS | YHou5 | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 2 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1018739 | O.1018739.01 | A.1018739.01.02 | Horse Creek 20 | ARMOUR ENERGY (SURAT BASIN) PTY LTD | Horse Creek 20 |  | J.22.110475 | RPS | FRAC-PROP | Low | Cancelled | Close - PSD |  | Not Required | Design Completed | In Progress |  | 2022-03-15 |  | 2022-03-15 | 2022-03-22 23:59 |  |  | AUS East Coast WS | SKanaan | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 3 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1018739 | O.1018739.01 | A.1018739.01.03 | Horse Shoe 4 | ARMOUR ENERGY (SURAT BASIN) PTY LTD | Horse Shoe 4 |  | J.22.110474 | RPS | FRAC-PROP | Low | Cancelled | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-02-12 |  | 2022-02-12 | 2022-02-19 23:59 |  |  | AUS East Coast WS | SKanaan | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 0 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1018739 | O.1018739.01 | A.1018739.01.04 | Greymouth | ARMOUR ENERGY (SURAT BASIN) PTY LTD |  |  | J.21.109238 | RPS | STM-DSL | InComplete | Cancelled | Close - PSD |  | Not Required | Design Completed | In Progress |  | 2021-10-17 |  | 2021-10-17 | 2021-10-24 23:59 |  |  | AUS East Coast WS | SKanaan | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 0 |  |  |  | 75 | 33.3 | 100 | 25 | 55 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1018739 | O.1018739.01 | A.1018739.01.01 | Warroon 1 | ARMOUR ENERGY (SURAT BASIN) PTY LTD | Warroon 1 |  | J.22.110472 | RPS | FRAC-PROP | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-08 | 2022-01-06 |  | 2022-01-08 | 2022-01-14 23:59 |  | 2022-01-17 23:59 | AUS East Coast WS | SKanaan | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Yuxiao Hou |  | 65952.35 | 1 |  |  |  | 87.5 | 33.3 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1018651 | O.1018651.01 | A.1018651.01.08 | KA-28 E19 | TODD ENERGY LIMITED | KA-28 | Big Ben | J.23.017720 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-07-07 | 2023-07-03 01:00 |  | 2023-07-07 | 2023-07-11 23:59 |  | 2023-07-18 23:59 | New Plymouth WL | OMosleh | 2024-08-21 17:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Ayssar Alsayed |  | 0 | 3 |  | L2 - Shift RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1018651 | O.1018651.01 | A.1018651.01.09 | KA-26 E15 | TODD ENERGY LIMITED | KA-26 | Big Ben | J.23.019182 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-09-01 | 2023-08-27 01:00 |  | 2023-09-01 | 2023-09-05 23:59 |  | 2023-09-05 23:59 | New Plymouth WL | CLorenzo | 2024-08-21 17:52 | FDPSystemUser |  | No |  |  |  |  | Ayssar Alsayed |  | 0 | 4 |  | L0 - No RO |  | 66.7 | 33.3 | 0 | 0 | 30 |  | 0 |  |  |  | 0 |  |  |  | Claudio Sanabria | WL Evaluation Services
P.1018651 | O.1018651.01 | A.1018651.01.10 | KA-27 G13 | TODD ENERGY LIMITED | KA-27 | Big Ben | J.23.019183 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-29 | 2023-07-28 01:00 |  | 2023-07-29 | 2023-08-16 23:59 |  | 2023-08-16 23:59 | New Plymouth WL | CLorenzo | 2024-08-21 17:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Ayssar Alsayed |  | 30000.17 | 5 |  | L2 - Shift RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1018651 | O.1018651.01 | A.1018651.01.07 | KA-25_G12 | TODD ENERGY LIMITED | KA-25 | Big Ben | J.23.017719 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-06-02 | 2023-06-01 01:00 | 2023-06-03 | 2023-06-02 | 2023-06-06 23:59 | 2023-06-05 | 2023-06-07 00:59 | New Plymouth WL | OMosleh | 2023-06-27 16:37 | CKok3 |  | No |  |  |  |  | Ayssar Alsayed |  | 0 | 1 |  | L0 - No RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1018651 | O.1018651.01 | A.1018651.01.05 | KA-23 CH RST / VSI | TODD ENERGY LIMITED | Kapuni-23 | Big Ben | J.22.110982 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-02-07 01:00 |  | 2022-02-10 | 2022-02-20 23:59 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 17:32 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Paulo Zuliani |  | 0 | 11 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1018651 | O.1018651.01 | A.1018651.01.02 | Kapuni 22 | TODD ENERGY LIMITED | Kapuni-22 | Big Ben | J.21.109101 | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-10-28 01:00 |  | 2021-10-31 | 2021-11-10 23:59 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 249103.13 | 9 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1018651 | O.1018651.01 | A.1018651.01.06 | KA23- CH VSI8 RST | TODD ENERGY LIMITED | Kapuni-23 | Big Ben | J.22.110437 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-02-28 |  | 2022-02-28 | 2022-03-04 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Paulo Zuliani |  | 112690 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1018651 | O.1018651.01 | A.1018651.01.03 | Kapuni 23 | TODD ENERGY LIMITED | Kapuni-23 | Big Ben | J.22.110434 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-01-04 01:00 |  | 2022-01-07 | 2022-01-17 23:59 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 1328768.23 | 5 |  |  |  | 83.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1018651 | O.1018651.01 | A.1018651.01.01 | Kapuni 21 | TODD ENERGY LIMITED | Kapuni-21 | Big Ben | J.21.109095 | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-10-22 |  | 2021-10-22 | 2021-10-26 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Paulo Zuliani |  | 661449.78 | 10 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1018651 | O.1018651.01 | A.1018651.01.04 | Kapuni 24 | TODD ENERGY LIMITED | Kapuni-24 | Big Ben | J.22.110432 | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-01-20 01:00 |  | 2022-01-24 | 2022-02-03 23:59 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 568680.21 | 11 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1018250 | O.1018250.01 | A.1018250.01.01 | Fishing Rental | TODD ENERGY LIMITED | MANGAHEWA 31 | Big Ben | J.21.109096 | RPI | PS-SLK-Ops | Low | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-05-21 |  | 2021-05-21 | 2021-06-10 23:59 |  |  | New Plymouth WL | PZuliani | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  |  | Paulo Zuliani |  | 54250 | 0 |  |  |  | 33.3 | 0 | 0 | 25 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1018113 | O.1018113.01 | A.1018113.01.02 | vsi16 | NEW ZEALAND ENERGY CORPORATION | Tariki D1 | Rigless NZ Land | J.21.109099 | RPE | ES-CH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-06-25 |  | 2021-06-27 | 2021-07-15 23:59 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 229173.7 | 1 |  |  |  | 66.7 | 33.3 | 0 | 75 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1018113 | O.1018113.01 | A.1018113.01.01 | HDVS_3DSurvey | NEW ZEALAND ENERGY CORPORATION |  | Rigless NZ Land | J.21.109092 | RPE | ES-CH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-06-25 |  | 2021-06-27 | 2021-07-15 23:59 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 0 | 1 |  |  |  | 41.7 | 33.3 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1017822 | O.1017822.01 | A.1017822.01.01 | PWW1 | OMV NEW ZEALAND LTD | PWW 1 | Rigless NZ Land | J.21.109602 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-05-22 |  | 2021-05-23 | 2021-06-01 23:59 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 17:31 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 45095 | 1 |  |  |  | 83.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Paulo Zuliani | WL Production Services
P.1017643 | O.1017643.01 | A.1017643.01.01 | USIT-CBL | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | PEAT 21 | MPC 001 | J.21.109052 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-05-01 |  | 2021-05-01 18:00 | 2021-05-03 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 0 |  |  |  | 58.3 | 50 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1017360 | O.1017360.04 | A.1017360.04.01 | Personnel | SANTOS NA (19-12) PTY LTD |  | Noble Tom Prosser | J.21.109601 | WCF | CMT-PERS | Low | Confirmed | Design - CEC |  | Not Required | Not Required | In Progress |  | 2021-10-14 |  | 2021-10-14 | 2021-12-02 |  |  | AUS West Coast WS | JAhmed8 | 2022-10-03 12:31 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 0 |  |  |  | 75 | 66.7 | 100 | 50 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1017360 | O.1017360.03 | A.1017360.03.01 | BU-DS06 - 36" Conductor Csg | SANTOS NA (19-12) PTY LTD | BU- DS06 | Noble Tom Prosser | J.21.109599 | WCF | PRI-COND | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-10-02 23:00 | 2021-09-27 |  | 2021-10-02 23:00 | 2021-10-03 22:59 |  | 2021-10-04 22:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 12:31 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1017360 | O.1017360.03 | A.1017360.03.04 | Plug and Abandon | SANTOS NA (19-12) PTY LTD | BU- DS06 | Noble Tom Prosser | J.21.109399 | WCF | REM-PA | Medium | Unconfirmed - 10% | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-11-07 20:00 | 2021-10-11 |  | 2021-11-07 12:00 | 2021-11-09 11:59 |  | 2021-11-11 19:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1017360 | O.1017360.03 | A.1017360.03.03 | BU-DS06_9-5/8" Intermediate Casing | SANTOS NA (19-12) PTY LTD | BU- DS06 | Noble Tom Prosser | J.21.109383 | WCF | PRI-INTER | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-10-30 10:00 | 2021-10-12 |  | 2021-10-31 12:00 | 2021-11-01 12:00 |  | 2021-11-10 09:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1017360 | O.1017360.03 | A.1017360.03.02 | BU-DS06_13-3/8" Surface Casing | SANTOS NA (19-12) PTY LTD | BU- DS06 | Noble Tom Prosser | J.21.109378 | WCF | PRI-SURF | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-10-12 03:00 | 2021-10-05 |  | 2021-10-13 03:00 | 2021-10-14 19:00 |  | 2021-10-19 02:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1017360 | O.1017360.02 | A.1017360.02.05 | BUW10_7in Liner cementing | SANTOS NA (19-12) PTY LTD | BU- W10 | Noble Tom Prosser | J.21.109598 | WCF | PRI-LIN | InComplete | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-08-31 | 2021-07-02 |  | 2021-08-31 | 2021-09-01 23:59 |  | 2021-09-12 07:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 12:31 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1017360 | O.1017360.02 | A.1017360.02.02 | BUW10_20inch casing | SANTOS NA (19-12) PTY LTD | BU- W10 | Noble Tom Prosser | J.21.109597 | WCF | PRI-SURF | InComplete | Confirmed | Design - CEC |  | Design Completed | In Progress | In Progress | 2021-07-01 00:44 | 2021-06-18 01:17 |  | 2021-07-20 18:00 | 2021-07-23 16:43 |  | 2021-07-24 00:43 | AUS West Coast WS | FDPSystemUser | 2022-10-03 12:31 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1017360 | O.1017360.02 | A.1017360.02.09 | Personnel | SANTOS NA (19-12) PTY LTD | BU-W10 | Noble Tom Prosser | J.21.109398 | WCF | CMT-BONUS | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2021-09-05 |  | 2021-09-05 | 2021-09-11 23:59 |  |  | AUS West Coast WS | JAhmed8 | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 0 |  |  |  | 75 | 66.7 | 100 | 50 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1017360 | O.1017360.02 | A.1017360.02.08 | BU-W10_PnA_Plug #a | SANTOS NA (19-12) PTY LTD | BU-W10 | Noble Tom Prosser | J.21.109396 | WCF | REM-PA | Medium | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-09-05 23:00 | 2021-08-29 |  | 2021-09-05 15:00 | 2021-09-07 14:59 |  | 2021-09-09 22:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1017360 | O.1017360.02 | A.1017360.02.07 | 9-5/8in DLT Packer | SANTOS NA (19-12) PTY LTD | BU- W10 | Noble Tom Prosser | J.21.109394 | WCF | CMT-TOOLS | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2021-08-23 17:00 | 2021-08-23 04:00 |  | 2021-08-23 17:00 | 2021-08-24 17:00 |  | 2021-08-24 17:00 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 0 |  |  |  | 50 | 16.7 | 0 | 0 | 25 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1017360 | O.1017360.02 | A.1017360.02.06 | 13-3/8in DLT Packer Run | SANTOS NA (19-12) PTY LTD | BU- W10 | Noble Tom Prosser | J.21.109391 | WCF | CMT-TOOLS | InComplete | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2021-08-02 08:00 | 2021-08-02 |  | 2021-08-02 08:00 | 2021-08-03 08:00 |  | 2021-08-03 08:00 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 0 |  |  |  | 50 | 16.7 | 0 | 0 | 25 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1017360 | O.1017360.02 | A.1017360.02.03 | BUW10_1338 inch casing | SANTOS NA (19-12) PTY LTD | BU- W10 | Noble Tom Prosser | J.21.109380 | WCF | PRI-INTER | InComplete | Confirmed | Design - CEC |  | Design Completed | In Progress | In Progress | 2021-08-02 07:00 | 2021-06-18 |  | 2021-08-01 23:00 | 2021-08-04 22:59 |  | 2021-08-13 06:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1017360 | O.1017360.02 | A.1017360.02.04 | BU-W10_9 58 inch Liner | SANTOS NA (19-12) PTY LTD | BU- W10 | Noble Tom Prosser | J.21.109376 | WCF | PRI-LIN | InComplete | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-08-20 12:00 | 2021-07-02 |  | 2021-08-20 04:00 | 2021-08-21 03:59 |  | 2021-09-02 11:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1017360 | O.1017360.02 | A.1017360.02.01 | BUW10_30inch casing | SANTOS NA (19-12) PTY LTD | BU- W10 | Noble Tom Prosser | J.21.109373 | WCF | PRI-COND | InComplete | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-07-16 08:00 | 2021-06-18 |  | 2021-07-16 | 2021-07-17 23:59 |  | 2021-07-21 07:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1017360 | O.1017360.01 | A.1017360.01.11 | PnA - Plug 1 - 3665m to 3365m | SANTOS NA (19-12) PTY LTD | BU-W13 ST2 | Noble Tom Prosser | J.21.109600 | WCF | REM-PA | Medium | Unconfirmed - 50% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-07-15 08:00 | 2021-06-22 |  | 2021-07-15 | 2021-07-15 08:00 |  | 2021-07-19 07:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 12:31 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1017360 | O.1017360.01 | A.1017360.01.06 | W13-ST1 - PnA_C - 3690mMD to 3470mMD | SANTOS NA (19-12) PTY LTD | BU-W13ST1 | Noble Tom Prosser | J.21.109596 | WCF | REM-PA | InComplete | Confirmed | Design - CEC |  | In Progress | Design Completed | In Progress | 2021-06-06 01:00 | 2021-05-24 |  | 2021-06-05 17:00 | 2021-06-07 04:59 |  | 2021-06-07 12:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 12:31 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1017360 | O.1017360.01 | A.1017360.01.05 | PnA 1B - 3700mMD - 4000mMD | SANTOS NA (19-12) PTY LTD | BU-W13ST1 | Noble Tom Prosser | J.21.109595 | WCF | REM-PA | InComplete | Confirmed | Design - CEC |  | In Progress | Design Completed | In Progress | 2021-05-31 08:00 | 2021-05-24 |  | 2021-05-31 | 2021-05-31 12:00 |  | 2021-05-31 20:00 | AUS West Coast WS | FDPSystemUser | 2022-10-03 12:31 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1017360 | O.1017360.01 | A.1017360.01.03 | Service - Personnel and Equipment Rental | SANTOS NA (19-12) PTY LTD | BU-W13ST1 | Noble Tom Prosser | J.21.109594 | WCF | CMT-EQPRNT,CMT-PERS | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2021-04-19 08:00 | 2021-04-19 |  | 2021-04-22 | 2021-05-31 23:59 |  | 2021-06-01 07:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 12:31 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1017360 | O.1017360.01 | A.1017360.01.12 | PnA - Plug 2 - 3365m to 3065m | SANTOS NA (19-12) PTY LTD | BU-W13 ST2 | Noble Tom Prosser | J.21.109392 | WCF | REM-PA | Medium | Unconfirmed - 50% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-07-16 16:00 | 2021-06-22 12:00 |  | 2021-07-16 08:00 | 2021-07-17 |  | 2021-07-20 15:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1017360 | O.1017360.01 | A.1017360.01.10 | BUW13ST1-PlugC2_3296m to 3596m | SANTOS NA (19-12) PTY LTD | BU-W13ST1 | Noble Tom Prosser | J.21.109388 | WCF | REM-PA | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-06-08 02:00 | 2021-05-26 |  | 2021-06-07 18:00 | 2021-06-09 05:59 |  | 2021-06-09 13:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 40.6 | 8.3 | 0 | 0 | 18.8 |  | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1017360 | O.1017360.01 | A.1017360.01.13 | PnA - Plug 3 - 3065m to 2765m | SANTOS NA (19-12) PTY LTD | BU-W13 ST2 | Noble Tom Prosser | J.21.109387 | WCF | REM-PA | Medium | Unconfirmed - 50% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-07-17 10:00 | 2021-06-23 02:00 |  | 2021-07-17 02:00 | 2021-07-17 12:00 |  | 2021-07-21 09:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1017360 | O.1017360.01 | A.1017360.01.14 | Personnel-June | SANTOS NA (19-12) PTY LTD | BU-W13ST1 | Noble Tom Prosser | J.21.109386 | WCF | CMT-PERS | Low | Unconfirmed - 50% | Design - CEC |  | Not Required | Not Required | In Progress |  | 2021-07-01 |  | 2021-07-01 | 2021-07-30 23:59 |  |  | AUS West Coast WS | VWedhaswari | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 81.3 | 66.7 | 100 | 50 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1017360 | O.1017360.01 | A.1017360.01.09 | Personnel-May | SANTOS NA (19-12) PTY LTD | BU-W13ST1 | Noble Tom Prosser | J.21.109382 | WCF | CMT-PERS | Low | Unconfirmed - 50% | Design - CEC |  | Not Required | Not Required | In Progress |  | 2021-06-01 |  | 2021-06-01 | 2021-06-30 23:59 |  |  | AUS West Coast WS | VWedhaswari | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 |  |  |  | 81.3 | 66.7 | 100 | 50 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1017360 | O.1017360.01 | A.1017360.01.08 | W13-ST1 - PnA_D - 2460mMD to 2260mMD | SANTOS NA (19-12) PTY LTD | BU-W13ST1 | Noble Tom Prosser | J.21.109381 | WCF | REM-PA | InComplete | Confirmed | Design - CEC |  | In Progress | Design Completed | In Progress | 2021-06-08 22:00 | 2021-05-25 |  | 2021-06-08 14:00 | 2021-06-10 01:59 |  | 2021-06-10 09:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 62.5 | 16.7 | 0 | 0 | 30 |  | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1017360 | O.1017360.01 | A.1017360.01.07 | W13-ST1 - Plug E_KOP - 755mMD to 915mMD | SANTOS NA (19-12) PTY LTD | BU-W13ST1 | Noble Tom Prosser | J.21.109375 | WCF | REM-KOP | InComplete | Confirmed | Design - CEC |  | In Progress | Design Completed | In Progress | 2021-06-11 | 2021-05-24 |  | 2021-06-10 16:00 | 2021-06-12 15:59 |  | 2021-06-12 23:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1017360 | O.1017360.01 | A.1017360.01.01 | BU-W13_13 3/8inch casing | SANTOS NA (19-12) PTY LTD | BU-W13 ST2 | Noble Tom Prosser | J.21.109374 | WCF | PRI-SURF | InComplete | Confirmed | Design - CEC |  | In Progress | Design Completed | In Progress | 2021-06-17 20:00 | 2021-05-24 |  | 2021-06-17 12:00 | 2021-06-24 11:59 |  | 2021-06-24 19:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1017360 | O.1017360.01 | A.1017360.01.04 | PnA 1A - 4000mMD - 4300mMD | SANTOS NA (19-12) PTY LTD | BU-W13ST1 | Noble Tom Prosser | J.21.109369 | WCF | REM-PA | InComplete | Confirmed | Design - CEC |  | In Progress | Design Completed | In Progress | 2021-05-29 08:00 | 2021-05-24 |  | 2021-05-29 | 2021-05-30 23:59 |  | 2021-06-02 07:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1017360 | O.1017360.01 | A.1017360.01.02 | BU-W13-ST2_9 5/8inch cementing | SANTOS NA (19-12) PTY LTD | BU-W13 ST2 | Noble Tom Prosser | J.21.109366 | WCF | PRI-LONG | InComplete | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-06-24 16:00 | 2021-05-24 |  | 2021-06-24 08:00 | 2021-07-03 07:59 |  | 2021-07-03 15:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1017359 | O.1017359.01 | A.1017359.01.01 | SS-Plug | DENISON GAS | SARDINE CREEK 1 | SWS-2 | J.21.109040 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-27 22:00 | 2021-04-27 18:00 |  | 2021-04-27 22:00 | 2021-05-02 21:59 |  | 2021-05-02 21:59 | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 27192.98 | 0 |  | L1 - Support RO |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1017357 | O.1017357.02 | A.1017357.02.01 | DFIR | ORIGIN ENERGY B2 PTY LIMITED |  | Rigless Australia - 1 | J.22.110266 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-01-14 |  | 2022-01-19 | 2022-01-24 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1017357 | O.1017357.01 | A.1017357.01.01 | Memory PLT | ORIGIN ENERGY B2 PTY LIMITED | Amungee NW-1H | Rigless Australia - 1 | J.21.109049 | RPI | PS-SLK-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2021-08-26 |  | 2021-08-26 | 2021-09-02 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | Wireline Slickline
P.1017311 | O.1017311.01 | A.1017311.01.02 | 2021-003-Jadestone-107-Bleef Off - Design | JADESTONE ENERGY (AUSTRALIA) PTY LTD | Montara H1 ST1 | Valaris 107 | J.21.108340 | RPI | TSWT-FLOWBACK-JOB | High | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-03-03 |  | 2021-05-01 | 2021-05-27 23:59 |  |  | APG TS | GFrankpitt | 2022-10-03 06:27 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | George Frankpitt |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1017311 | O.1017311.01 | A.1017311.01.01 | 2021-003-Jadestone-107- Bleed off - Design Phase | JADESTONE ENERGY (AUSTRALIA) PTY LTD | Montara H1 ST1 | Valaris 107 | J.21.108339 | RPI | TSWT-FLOWBACK-JOB | High | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-07-11 |  | 2021-08-18 | 2021-08-27 23:59 |  |  | APG TS | GFrankpitt | 2022-10-03 06:26 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | George Frankpitt |  | 75000 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1016918 | O.1016918.01 | A.1016918.01.01 | ENI Blacktip | ENI AUSTRALIA B.V. | Blacktip P1, Blacktip P2 |  | J.21.108852 | RPI | PS-WL-Ops | Medium | Operationally Complete | Execute - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-08-14 |  | 2021-08-26 23:00 | 2021-09-11 22:59 |  |  | New Burn WL | frosa2 | 2022-10-03 09:51 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 279209.1 | 4 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1016821 | O.1016821.01 | A.1016821.01.01 | USIT-CBL | SANTOS LIMITED | FV11-107-1 | Ensign 966 | J.21.109593 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-04-06 19:00 |  | 2021-04-06 20:00 | 2021-04-07 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:31 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 21741.39 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1015738 | O.1015738.01 | A.1015738.01.01 | Well #1 - Potential | SANTOS LIMITED | Tarwonga 7 | Wild Desert Rig 6 | J.21.108337 | RPI | TCP-TEMP-JOB | Medium | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress |  | 2021-05-07 |  | 2021-05-08 | 2021-05-21 23:59 |  |  | APG TS | GRoxo | 2024-11-19 20:07 | FDPSystemUser |  | No |  |  |  |  | Wayne Wallis |  | 25050.68 | 2 |  |  |  | 58.3 | 50 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TCP - Tubing-Conveyed Perforation
P.1015738 | O.1015738.01 | A.1015738.01.02 | Well # 2 - Potential | SANTOS LIMITED | TARWONGA 007 | Wild Desert Rig 6 | J.21.108338 | RPI | TSWT-FLOWBACK-JOB | High | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress |  | 2021-06-26 |  | 2021-06-26 | 2021-07-26 23:59 |  |  | APG TS | GRoxo | 2022-10-03 06:26 | FDPSystemUser |  | No |  |  |  |  | Wayne Wallis |  | 0 | 1 |  | L0 - No RO | [7 empty] | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1015629 | O.1015629.01 | A.1015629.01.06 | Vintage Jun Ops | VINTAGE ENERGY LTD | VALI-3 | Saxon Rig 184 | J.24.053489 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | Design Completed | 2024-06-16 | 2024-06-16 |  | 2024-06-16 | 2024-06-18 23:59 |  | 2024-06-18 23:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 1 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1015629 | O.1015629.01 | A.1015629.01.08 | BRIDGEPORT PLACEHOLDER | VINTAGE ENERGY LTD | VALI-3 | Saxon Rig 184 | J.24.096857 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-07-15 | 2024-07-15 |  | 2024-07-15 | 2024-09-27 23:59 |  | 2024-09-27 23:59 | Moomba WL | KKeese | 2024-07-24 07:42 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1015629 | O.1015629.01 | A.1015629.01.05 | Odin 2 | VINTAGE ENERGY LTD | ODIN 2 | Saxon Rig 184 | J.24.053488 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-11-15 22:00 | 2024-05-28 |  | 2024-05-28 | 2024-06-02 23:59 |  | 2024-06-02 23:59 | Moomba WL | KKeese | 2024-06-18 17:42 | AKavooris |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 70402.86 | 2 |  | L2 - Shift RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 2 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1015629 | O.1015629.01 | A.1015629.01.07 | Vintage Well 3 | VINTAGE ENERGY LTD | VALI-3 | Saxon Rig 184 | J.24.096856 | RPE | ES-OH-Ops | Low | Cancelled | Execute - PSD |  | In Progress | Not Started | In Progress | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-03 23:59 | 2024-07-04 | 2024-07-03 23:59 | Moomba WL | KKeese | 2024-05-30 15:47 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1015629 | O.1015629.01 | A.1015629.01.04 | Vali-3 | VINTAGE ENERGY LTD | VALI-3 | Saxon Rig 184 | J.21.108634 | RPE | ES-CH-Ops | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2021-06-18 |  | 2021-06-18 | 2021-06-20 23:59 |  |  | Moomba WL | KKeese | 2022-10-03 11:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1015629 | O.1015629.01 | A.1015629.01.03 | Vali 3 | VINTAGE ENERGY LTD | VALI-3 | Saxon Rig 184 | J.21.108546 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2021-06-19 12:00 | 2021-06-28 12:00 | 2021-06-28 | 2021-06-28 12:00 | 2021-07-07 11:59 | 2021-07-08 | 2021-07-07 23:59 | Moomba WL | IWahbi | 2022-10-03 11:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | 3 |  | L1 - Support RO |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1015629 | O.1015629.01 | A.1015629.01.02 | Odin 1 | VINTAGE ENERGY LTD | Odin 1 | Saxon Rig 184 | J.21.108431 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-05-24 | 2021-05-24 12:00 | 2021-05-24 | 2021-05-24 12:00 | 2021-06-01 11:59 | 2021-06-02 | 2021-05-31 12:00 | Moomba WL | IWahbi | 2022-10-03 11:04 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1015629 | O.1015629.01 | A.1015629.01.01 | Vali 2 | VINTAGE ENERGY LTD | VALI-2 | Saxon Rig 184 | J.21.108430 | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-05-04 | 2021-05-04 | 2021-05-04 | 2021-05-04 | 2021-05-08 23:59 | 2021-05-09 | 2021-05-06 | Moomba WL | IWahbi | 2022-10-03 11:04 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1015489 | O.1015489.01 | A.1015489.01.03 | Carp-3 | IMPERIAL OIL AND GAS PTY LTD | CARPENTARIA-3H | Rigless Australia - 1 | J.22.110409 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-04 01:00 | 2022-11-23 06:00 |  | 2022-12-04 | 2023-01-11 23:59 |  | 2023-02-10 00:59 | Roma WL | MRony2 | 2023-01-15 21:50 | ysaeedabadian |  | Yes |  |  |  |  | Jon Lawrie |  | 1212348.5 | 41 |  | L0 - No RO |  | 83.3 | 58.3 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1015489 | O.1015489.01 | A.1015489.01.02 | Perfo | IMPERIAL OIL AND GAS PTY LTD | Carpentaria 2 | Rigless Australia - 1 | J.22.110334 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-07-02 06:00 |  | 2022-07-06 06:00 | 2022-08-24 05:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 546988.42 | 27 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1015489 | O.1015489.01 | A.1015489.01.01 | Frac-Perfo | IMPERIAL OIL AND GAS PTY LTD | Carpentaria 1 | Rigless Australia - 1 | J.21.108995 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-05-28 01:00 |  | 2021-06-01 01:00 | 2021-06-13 00:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 131331.71 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1015414 | O.1015414.01 | A.1015414.01.07 | Carp 4H | IMPERIAL OIL AND GAS PTY LTD | CARPENTARIA-3H | Rigless Australia - 1 | J.23.100808 | RPS | FRAC-PROP | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-26 | 2024-01-01 | 2023-12-26 | 2024-01-01 | 2024-01-31 23:59 | 2024-02-18 | 2024-02-15 23:59 | AUS East Coast WS | radinegara | 2023-08-28 10:05 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 40 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1015414 | O.1015414.01 | A.1015414.01.10 | Carp 7H | IMPERIAL OIL AND GAS PTY LTD | CARPENTARIA-3H | Rigless Australia - 1 | J.24.007705 | RPS | FRAC-PROP | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-03-26 | 2024-04-01 | 2024-03-26 | 2024-04-01 | 2024-05-01 23:59 | 2024-05-18 23:00 | 2024-05-16 22:59 | AUS East Coast WS | radinegara | 2023-08-28 09:58 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 40 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1015414 | O.1015414.01 | A.1015414.01.08 | Carp 5H | IMPERIAL OIL AND GAS PTY LTD | CARPENTARIA-3H | Rigless Australia - 1 | J.24.007703 | RPS | FRAC-PROP | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-01-26 | 2024-02-01 | 2024-01-26 | 2024-02-01 | 2024-03-02 23:59 | 2024-03-20 | 2024-03-17 23:59 | AUS East Coast WS | radinegara | 2023-08-28 09:58 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 40 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1015414 | O.1015414.01 | A.1015414.01.09 | Carp 6H | IMPERIAL OIL AND GAS PTY LTD | CARPENTARIA-3H | Rigless Australia - 1 | J.24.007704 | RPS | FRAC-PROP | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-02-24 | 2024-03-01 | 2024-02-24 | 2024-03-01 | 2024-03-31 23:59 | 2024-04-17 23:00 | 2024-04-15 22:59 | AUS East Coast WS | radinegara | 2023-08-28 09:58 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 40 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1015414 | O.1015414.01 | A.1015414.01.06 | Post Carp-3H Reimbursable | IMPERIAL OIL AND GAS PTY LTD |  | Rigless Australia - 1 | J.23.045907 | RPS | STM-RECHARGE | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2023-03-01 |  | 2023-03-01 | 2023-03-23 23:59 |  |  | AUS East Coast WS | HFerdjallah | 2023-04-16 12:08 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 0 |  |  |  | 56.3 | 33.3 | 100 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1015414 | O.1015414.01 | A.1015414.01.04 | Carpenteria 3H - FRAC | IMPERIAL OIL AND GAS PTY LTD | CARPENTARIA-3H | Rigless Australia - 1 | J.22.125810 | RPS | FRAC-PROP | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-01 | 2022-12-01 |  | 2022-12-07 | 2023-01-17 23:59 |  | 2023-01-21 23:59 | AUS East Coast WS | SKanaan | 2023-03-26 11:54 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 3905573.03 | 40 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1015414 | O.1015414.01 | A.1015414.01.03 | Prop Frac | IMPERIAL OIL AND GAS PTY LTD | Carpentaria 2 | Rigless Australia - 1 | J.22.125809 | RPS | FRAC-SLICK,FRAC-PROP,FRAC-COMB | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-07-09 | 2022-06-30 |  | 2022-07-01 | 2022-08-17 22:59 |  | 2022-08-18 22:59 | AUS East Coast WS | YHou5 | 2022-11-23 18:45 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 198806.74 | 25 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1015414 | O.1015414.01 | A.1015414.01.05 | Imperial Carp 3 Material Sales | IMPERIAL OIL AND GAS PTY LTD | CARPENTARIA-3H | Rigless Australia - 1 | J.22.125811 | RPS | FRAC-MATSAL | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2022-10-13 |  | 2022-10-13 | 2022-10-15 23:59 |  |  | AUS East Coast WS | radinegara | 2022-11-10 18:39 | FDPSystemUser |  | No |  |  |  |  | Aidan Flynn Kohr |  | 7312.52 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1015414 | O.1015414.01 | A.1015414.01.02 | Coil | IMPERIAL OIL AND GAS PTY LTD | Carpentaria 1 | Rigless Australia - 1 | J.21.111694 | RPI | CT-CIRC,CT-WBCLEAN-N2 | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-10 10:00 | 2021-06-02 |  | 2021-06-10 | 2021-07-10 23:59 |  | 2021-07-11 09:59 | AUS East Coast WS | ATanha | 2022-11-10 18:39 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 45966.54 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1015414 | O.1015414.01 | A.1015414.01.01 | Frac | IMPERIAL OIL AND GAS PTY LTD | Carpentaria 1 | Rigless Australia - 1 | J.21.111693 | RPS | FRAC-SLICK,FRAC-PROP,FRAC-COMB | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-02 10:00 | 2021-06-02 |  | 2021-06-02 | 2021-07-02 23:59 |  | 2021-07-03 09:59 | AUS East Coast WS | ATanha | 2022-11-10 18:38 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 198087.1 | 4 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1015406 | O.1015406.01 | A.1015406.01.27 | PBG 12 | DENISON GAS | PUNCHBOWL GULLY 12 | EASTERNWELL 27 | J.23.104662 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-06 21:00 | 2023-07-05 11:00 | 2023-06-30 | 2023-07-06 21:00 | 2023-07-09 20:59 | 2023-07-10 | 2023-07-12 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 3 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.25 | Punchbowl Gully 12_SS-HRLA-PEX_CMR | DENISON GAS | PUNCHBOWL GULLY 12 | EASTERNWELL 27 | J.23.030075 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-21 21:00 | 2023-05-20 11:00 |  | 2023-05-21 21:00 | 2023-05-24 20:59 |  | 2023-05-27 | Roma WL | MRony2 | 2023-05-25 18:29 | ysaeedabadian |  | No |  |  |  |  | Jon Lawrie |  | 21760.43 | 4 |  | L0 - No RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.24 | Punchbowl Gully 11_PEX-SS-GR_CMR | DENISON GAS | PUNCHBOWL GULLY 11 | EASTERNWELL 27 | J.23.030074 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-03-19 01:00 | 2023-03-17 17:00 |  | 2023-03-19 03:00 | 2023-03-22 02:59 |  | 2023-03-22 00:59 | Roma WL | MRony2 | 2023-03-21 16:10 | handoko |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 28979.86 | 3 |  | L2 - Shift RO |  | 83.3 | 83.3 | 0 | 75 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.26 | 3rd well | DENISON GAS |  | EASTERNWELL 27 | J.23.035730 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-20 20:00 | 2023-04-06 11:00 |  | 2023-04-08 21:00 | 2023-04-11 20:59 |  | 2023-04-14 20:59 | Roma WL | MRony2 | 2023-02-24 11:00 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  | L2 - Shift RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.19 | PEX-HRLA-SS | DENISON GAS | PUNCHBOWL GULLY 7 | EASTERNWELL 27 | J.22.110980 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-10-31 11:00 |  | 2022-10-31 21:00 | 2022-11-03 20:59 |  |  | Roma WL | MRony2 | 2022-11-04 13:59 | OAzarenko |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 64912.28 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.17 | PEX-HRLA-SS-CMR | DENISON GAS | PUNCHBOWL GULLY 10 | EASTERNWELL 27 | J.22.110393 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-10-04 16:00 |  | 2022-10-05 19:00 | 2022-10-08 18:59 |  |  | Roma WL | MRony2 | 2022-11-03 18:33 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 58577 | 3 |  |  |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.18 | PEX-HRLA-SS-CMR | DENISON GAS | PUNCHBOWL GULLY 8 | EASTERNWELL 27 | J.22.110397 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-10-19 10:00 |  | 2022-10-20 20:00 | 2022-10-23 19:59 |  |  | Roma WL | MRony2 | 2022-10-21 14:56 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 28979.86 | 3 |  |  |  | 66.7 | 33.3 | 0 | 100 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.16 | PEX-HRLA-SS-CMR | DENISON GAS | Punchbowl Gully 9 | EASTERNWELL 27 | J.22.110979 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-09-16 10:00 |  | 2022-09-17 20:00 | 2022-09-20 19:59 |  |  | Roma WL | MRony2 | 2022-10-05 16:08 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 58577 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.22 | PEX-HRLA-SS_MDT | DENISON GAS | Punchbowl Gully 6 | EASTERNWELL 27 | J.22.110981 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-11-27 11:00 |  | 2022-11-29 20:00 | 2022-12-02 19:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:30 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.15 | Denison OH | DENISON GAS | Punchbowl Gully 6 | EASTERNWELL 27 | J.22.110978 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-03-10 10:00 |  | 2022-03-11 20:00 | 2022-03-15 19:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:30 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 51364.52 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.14 | 5th well intermediate | DENISON GAS | Turkey Creek 7 | EASTERNWELL 27 | J.21.109590 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-10-26 |  | 2021-10-26 | 2021-10-28 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:30 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 20792.72 | 0 |  |  |  | 83.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.08 | TD Section - Rolleston 20 | DENISON GAS | Rolleston 20 | EASTERNWELL 27 | J.21.109589 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-08-15 12:00 |  | 2021-08-16 02:00 | 2021-08-18 01:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:30 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.06 | Arcturus 8_PNX-AIT-Plug-CBL | DENISON GAS | Arcturus 8 | EASTERNWELL 27 | J.21.109588 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-06-10 |  | 2021-06-10 20:00 | 2021-06-16 19:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:30 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 67868.75 | 4 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.23 | PEX-HRLA_SS-MDT | DENISON GAS | Punchbowl Gully 6 | EASTERNWELL 27 | J.22.110401 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-12-12 11:00 |  | 2022-12-14 20:00 | 2022-12-17 19:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:18 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.20 | PEX-HRLS_SS_FMI-MDT | DENISON GAS | Punchbowl Gully 6 | EASTERNWELL 27 | J.22.110398 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-10-10 11:00 |  | 2022-10-11 21:00 | 2022-10-14 20:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.21 | PEX_HRLS_SS_FMI-MDT | DENISON GAS | Punchbowl Gully 6 | EASTERNWELL 27 | J.22.110387 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-10-22 11:00 |  | 2022-10-24 20:00 | 2022-10-27 19:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.07 | TD Section_Arcturus 9 | DENISON GAS | ARCTURUS 9 | EASTERNWELL 27 | J.21.109059 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-08-28 |  | 2021-08-28 | 2021-08-31 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 67868.75 | 4 |  |  |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.05 | Arcturus 9 QC | DENISON GAS | ARCTURUS 9 | EASTERNWELL 27 | J.21.109056 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-08-25 20:00 |  | 2021-08-26 10:00 | 2021-08-28 09:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 0 |  |  |  | 75 | 33.3 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.03 | Rollestone 20 _QC-SS-FMI+MDT | DENISON GAS | Rolleston 20 | EASTERNWELL 27 | J.21.109054 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-08-10 |  | 2021-08-10 | 2021-08-13 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 2 |  |  |  | 58.3 | 50 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.04 | Yellowbank 8 QC_MDT | DENISON GAS | Yellowbank 8 | EASTERNWELL 27 | J.21.109048 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-05-25 |  | 2021-05-26 04:00 | 2021-05-28 03:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 165319.69 | 0 |  |  |  | 58.3 | 50 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.02 | Arcturus QC | DENISON GAS | Arcturus 8 | EASTERNWELL 27 | J.21.109045 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-06-05 |  | 2021-06-06 | 2021-06-08 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 22417.15 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.13 | TD_Turkey Creek 7 | DENISON GAS | Turkey Creek 7 | EASTERNWELL 27 | J.21.109025 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-10-27 01:00 |  | 2021-10-30 | 2021-10-31 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 2 |  |  |  | 75 | 33.3 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.12 | 4th well _Project 2 | DENISON GAS |  | EASTERNWELL 27 | J.21.109022 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-09-07 |  | 2021-09-08 | 2021-09-09 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 0 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.11 | TD Logging | DENISON GAS |  | EASTERNWELL 27 | J.21.109019 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-10-17 |  | 2021-10-18 | 2021-10-19 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.10 | TD logging _ PBG 5 | DENISON GAS | Punchbowl Gully 5 | EASTERNWELL 27 | J.21.109016 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-10-14 |  | 2021-10-15 | 2021-10-16 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 1 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.09 | Punchbowl Gully 4_Intermediate logging | DENISON GAS | Punchbowl Gully 4 | EASTERNWELL 27 | J.21.109015 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-09-15 |  | 2021-09-16 | 2021-09-19 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  |  |  | 66.7 | 33.3 | 0 | 75 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1015406 | O.1015406.01 | A.1015406.01.01 | Punch Gully -3 Logging | DENISON GAS | PUNCHBOWL GULLY 3 | EASTERNWELL 27 | J.21.108971 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2021-05-08 23:00 | 2021-05-07 |  | 2021-05-09 | 2021-05-12 23:59 |  | 2021-05-15 12:13 | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 165319.69 | 0 |  | L2 - Shift RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1014757 | O.1014757.01 | A.1014757.01.02 | Echo Yodel Prep & Flow | WOODSIDE ENERGY LTD | Echo Yodel 3, Echo Yodel 4 | Ocean Apex | J.21.108333 | RPI | TSWT-SEPONLY-JOB | High | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-04-06 |  | 2021-06-07 23:00 | 2021-06-28 23:59 |  |  | APG TS | GRoxo | 2024-11-19 20:14 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | George Frankpitt |  | 1881632.1 | 1 |  |  |  | 50 | 16.7 | 0 | 75 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1014757 | O.1014757.01 | A.1014757.01.05 | GWF3 GDA04 Well Unload | WOODSIDE ENERGY LTD | GDA-04 | Ocean Apex |  | RPI | TSWT-SEPONLY-JOB | High | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-09-09 |  | 2021-09-14 10:00 | 2021-10-01 09:59 |  |  | APG TS | AFrancis4 | 2024-11-19 20:14 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 0 | 1 |  |  |  | 58.3 | 33.3 | 0 | 75 | 50 |  | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1014757 | O.1014757.01 | A.1014757.01.06 | Lambert Deep | WOODSIDE ENERGY LTD | GDA-05 | Ocean Apex |  | RPI | TSWT-SEPONLY-JOB | High | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2021-10-09 | 2021-09-26 |  | 2021-12-27 | 2022-03-31 23:59 |  | 2021-12-04 23:59 | APG TS | GRoxo | 2024-11-19 20:14 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 0 | 1 |  | L0 - No RO |  | 75 | 33.3 | 0 | 25 | 40 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1014757 | O.1014757.01 | A.1014757.01.08 | GDA05 | WOODSIDE ENERGY LTD | GDA-05, GDA-04, GDA-03 | Ocean Apex |  | RPI | TSWT-SEPONLY-JOB | High | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2021-12-01 | 2021-10-22 |  | 2021-11-06 | 2022-03-15 23:59 |  | 2021-12-17 23:59 | APG TS | GRoxo | 2024-11-19 20:14 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 0 | 1 |  | L0 - No RO |  | 50 | 25 | 0 | 25 | 30 |  | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1014757 | O.1014757.01 | A.1014757.01.07 | GDA03 Unload | WOODSIDE ENERGY LTD | GDA-03, GDA-04, GDA-05 | Ocean Apex |  | RPI | TSWT-SEPONLY-JOB | High | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2021-10-31 | 2021-09-21 |  | 2021-11-01 | 2021-11-17 23:59 |  | 2021-11-16 23:59 | APG TS | GRoxo | 2024-11-19 20:14 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 0 | 1 |  | L0 - No RO |  | 75 | 33.3 | 0 | 62.5 | 51.2 |  | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1014757 | O.1014757.01 | A.1014757.01.04 | Echo Yodel Radio Rental | WOODSIDE ENERGY LTD | Echo Yodel 3 | Ocean Apex | J.21.108334 | RPI | TSWT-RENTAL | High | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-06-20 |  | 2021-06-22 | 2021-11-25 23:59 |  |  | APG TS | GRoxo | 2022-10-03 06:26 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | George Frankpitt |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1014757 | O.1014757.01 | A.1014757.01.01 | Echo Yodel Prep. | WOODSIDE ENERGY LTD | Echo Yodel 3, Echo Yodel 4 | Ocean Apex | J.21.108330 | RPI | TSWT-RENTAL | High | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-03-03 |  | 2021-03-03 | 2021-03-25 23:59 |  |  | APG TS | AFrancis4 | 2022-10-03 06:25 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Allwyn Francis |  | 1881632.1 | 1 |  |  |  | 58.3 | 33.3 | 0 | 50 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1014757 | O.1014757.01 | A.1014757.01.03 | GWF Equipment Prep | WOODSIDE ENERGY LTD | GDA-03 | Ocean Apex |  | RPI | TSWT-SEPONLY-STB | High | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2021-08-15 | 2021-07-15 |  | 2021-08-15 | 2022-01-31 23:59 |  | 2021-09-17 23:59 | APG TS | GRoxo | 2022-09-03 05:59 | walfaro |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | George Frankpitt |  | 83040 | 1 |  |  |  | 66.7 | 33.3 | 100 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1014547 | O.1014547.03 | A.1014547.03.05 | 5 1/2" HZ Production | ORIGIN ENERGY B2 PTY LIMITED | AMUNGEE NW-2H | Silver City 40 | J.22.118926 | WCF | PRI-LONG, CMT-MATSAL | Medium | Unconfirmed - 50% | Design - PSD |  | Not Required | Design Completed | In Progress |  | 2022-10-23 02:00 |  | 2022-12-21 01:00 | 2022-12-26 00:59 |  |  | AUS East Coast WS | ALyons | 2022-12-20 20:43 | ALyons |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014547 | O.1014547.03 | A.1014547.03.01 | 18 5/8 Conductor | ORIGIN ENERGY B2 PTY LIMITED | AMUNGEE NW-2H | Silver City 40 | J.22.118921 | WCF | PRI-COND | Low | Unconfirmed - 50% | Design - PSD |  | Not Required | Design Completed | In Progress |  | 2022-10-16 01:00 |  | 2022-11-13 | 2022-11-17 23:59 |  |  | AUS East Coast WS | FDPSystemUser | 2022-11-29 11:05 | DVickers |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014547 | O.1014547.03 | A.1014547.03.03 | 9 5/8" Intermediate | ORIGIN ENERGY B2 PTY LIMITED | AMUNGEE NW-2H | Silver City 40 | J.22.118924 | WCF | PRI-INTER, CMT-MATSAL | Low | Unconfirmed - 50% | Design - PSD |  | Not Required | Design Completed | In Progress |  | 2022-11-05 02:00 |  | 2022-11-29 | 2022-12-04 23:59 |  |  | AUS East Coast WS | ALyons | 2022-11-28 19:00 | ALyons |  | Yes |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014547 | O.1014547.03 | A.1014547.03.02 | 13 3/8" surface | ORIGIN ENERGY B2 PTY LIMITED | AMUNGEE NW-2H | Silver City 40 | J.22.118922 | WCF | PRI-SURF, CMT-MATSAL | Low | Unconfirmed - 50% | Execute - PSD |  | Not Required | Design Completed | In Progress |  | 2022-11-04 02:00 |  | 2022-11-18 01:00 | 2022-11-23 00:59 |  |  | AUS East Coast WS | FDPSystemUser | 2022-11-16 19:35 | ALyons |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014547 | O.1014547.03 | A.1014547.03.06 | Remote Package - Chemicals & Equipment | ORIGIN ENERGY B2 PTY LIMITED | AMUNGEE NW-2H | Silver City 40 | J.22.118927 | WCF | CMT-MATSAL,CMT-EQPRNT, CMT-TOOLS | Low | Unconfirmed - 50% | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-10-16 | 2022-10-16 01:00 |  | 2022-10-16 01:00 | 2022-12-15 23:59 |  | 2022-12-15 23:59 | AUS East Coast WS | ALyons | 2022-10-21 01:44 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014547 | O.1014547.03 | A.1014547.03.04 | PlugBack & KickOff | ORIGIN ENERGY B2 PTY LIMITED |  | Silver City 40 | J.22.118925 | WCF | REM-PA | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-11-18 02:00 |  | 2023-01-01 01:00 | 2023-01-06 00:59 |  |  | AUS East Coast WS | ALyons | 2022-10-21 01:44 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014547 | O.1014547.02 | A.1014547.02.06 | Remote Package - Chemicals & Equipment | ORIGIN ENERGY B2 PTY LIMITED | Amungee NW2-1.1H | Silver City 40 | J.22.118923 | WCF | CMT-MATSAL,CMT-EQPRNT, CMT-TOOLS | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2023-04-14 23:00 | 2023-04-15 21:00 |  | 2023-04-15 21:00 | 2023-06-15 21:59 |  | 2023-06-15 22:59 | AUS East Coast WS | ALyons | 2022-12-07 19:11 | ALyons |  | No |  |  |  |  | Ariel Lyons |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014547 | O.1014547.02 | A.1014547.02.01 | 18 5/8 Conductor | ORIGIN ENERGY B2 PTY LIMITED | Amungee NW2-1.1H | Silver City 40 | J.22.118919 | WCF | PRI-COND, CMT-MATSAL | Low | Unconfirmed - 50% | Design - CEC |  | Not Required | Design Completed | In Progress |  | 2023-04-11 |  | 2023-04-15 | 2023-04-19 23:59 |  |  | AUS East Coast WS | FDPSystemUser | 2022-12-07 19:11 | ALyons |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014547 | O.1014547.02 | A.1014547.02.05 | 5 1/2" HZ Production | ORIGIN ENERGY B2 PTY LIMITED | Amungee NW2-1.1H | Silver City 40 | J.23.010787 | WCF | PRI-LONG, CMT-MATSAL | Medium | Unconfirmed - 50% | Design - CEC |  | Not Required | Design Completed | In Progress |  | 2023-04-11 01:00 |  | 2023-06-13 | 2023-06-17 22:59 |  |  | AUS East Coast WS | ALyons | 2022-12-07 19:11 | ALyons |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014547 | O.1014547.02 | A.1014547.02.04 | PlugBack & KickOff | ORIGIN ENERGY B2 PTY LIMITED | Amungee NW2-1.1H | Silver City 40 | J.23.010786 | WCF | REM-PA | Low | Unconfirmed - 50% | Design - CEC |  | Not Required | Design Completed | In Progress |  | 2023-04-11 |  | 2023-05-16 | 2023-05-20 23:59 |  |  | AUS East Coast WS | ALyons | 2022-12-07 19:11 | ALyons |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014547 | O.1014547.02 | A.1014547.02.03 | 9 5/8" Intermediate | ORIGIN ENERGY B2 PTY LIMITED | Amungee NW2-1.1H | Silver City 40 | J.23.010785 | WCF | PRI-INTER, CMT-MATSAL | Low | Unconfirmed - 50% | Design - CEC |  | Not Required | Design Completed | In Progress |  | 2023-04-15 |  | 2023-05-30 23:00 | 2023-06-05 22:59 |  |  | AUS East Coast WS | ALyons | 2022-12-07 19:11 | ALyons |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014547 | O.1014547.02 | A.1014547.02.02 | 13 3/8" surface | ORIGIN ENERGY B2 PTY LIMITED | Amungee NW2-1.1H | Silver City 40 | J.22.118920 | WCF | PRI-SURF | Low | Unconfirmed - 50% | Execute - PSD |  | Not Required | Design Completed | In Progress |  | 2023-04-15 |  | 2023-04-26 | 2023-04-30 23:59 |  |  | AUS East Coast WS | FDPSystemUser | 2022-12-07 19:11 | ALyons |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014547 | O.1014547.01 | A.1014547.01.05 | 9 8/8" Intermediate | ORIGIN ENERGY B2 PTY LIMITED | VELKERRI 76 S2-1H | Silver City 40 | J.21.111582 | WCF | PRI-INTER, CMT-MATSAL | Low | Unconfirmed - 90% | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-08-14 09:00 | 2021-08-23 01:00 |  | 2021-09-16 | 2021-09-17 23:59 |  | 2021-10-04 09:59 | AUS East Coast WS | ALyons | 2022-10-21 01:43 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014547 | O.1014547.01 | A.1014547.01.03 | Plug Back | ORIGIN ENERGY B2 PTY LIMITED | Velkerri 76 S2-1 | Silver City 40 | J.21.111581 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress | 2021-04-15 10:00 | 2021-05-15 01:00 |  | 2021-05-31 01:00 | 2021-06-05 00:59 |  | 2021-07-17 09:59 | AUS East Coast WS | ALyons | 2022-10-21 01:42 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014547 | O.1014547.01 | A.1014547.01.02 | 13 3/8" surface | ORIGIN ENERGY B2 PTY LIMITED | VELKERRI 76 S2-1 | Silver City 40 | J.21.111580 | WCF | PRI-SURF, CMT-MATSAL | Low | Unconfirmed - 90% | Design - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-07 10:00 | 2021-08-13 01:00 |  | 2021-08-29 01:00 | 2021-08-30 00:59 |  | 2021-09-27 09:59 | AUS East Coast WS | ALyons | 2022-10-21 01:42 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014547 | O.1014547.01 | A.1014547.01.06 | 5 1/2" HZ Production | ORIGIN ENERGY B2 PTY LIMITED | VELKERRI 76 S2-1H | Silver City 40 | J.21.111579 | WCF | PRI-LONG, CMT-MATSAL | Medium | Unconfirmed - 50% | Design - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-09 10:00 | 2021-09-26 01:00 |  | 2021-10-13 01:00 | 2021-10-18 00:59 |  | 2021-10-28 10:59 | AUS East Coast WS | ALyons | 2022-10-21 01:42 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014547 | O.1014547.01 | A.1014547.01.04 | Kick Off Plug | ORIGIN ENERGY B2 PTY LIMITED | Velkerri 76 S2-1H | Silver City 40 | J.21.111578 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress | 2021-05-01 10:00 | 2021-05-15 01:00 |  | 2021-06-04 01:00 | 2021-06-09 00:59 |  | 2021-07-16 09:59 | AUS East Coast WS | ALyons | 2022-10-21 01:42 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014547 | O.1014547.01 | A.1014547.01.01 | 18 5/8 Conductor | ORIGIN ENERGY B2 PTY LIMITED | VELKERRI 76 S2-1 | Silver City 40 | J.21.111577 | WCF | PRI-COND, CMT-MATSAL, REM-PA, LC-CMTP | Low | Unconfirmed - 90% | Design - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-06 23:00 | 2021-08-16 |  | 2021-08-17 | 2021-08-17 23:59 |  | 2021-09-20 22:59 | AUS East Coast WS | FDPSystemUser | 2022-10-21 01:42 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 7 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014449 | O.1014449.01 | A.1014449.01.01 | Cooper Energy _ SIT (Dummy Job) | COOPER ENERGY LIMITED | BASKER 1 | RIGLESS - AUSTRALIA | J.21.109372 | WCF | REM-PA | Low | Confirmed | Design - CEC |  | Design Completed | In Progress | In Progress | 2021-03-08 08:00 | 2021-03-08 |  | 2021-03-08 | 2021-03-13 23:59 |  | 2021-03-14 07:59 | AUS West Coast WS | MAlsaman | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1014281 | O.1014281.01 | A.1014281.01.01 | Geothermal-1 | CONTACT ENERGY LTD. |  | Webster Nova 1 | J.21.109098 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-07-04 |  | 2021-07-05 | 2021-07-08 23:59 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Paulo Zuliani | WL Evaluation Services
P.1014280 | O.1014280.01 | A.1014280.01.01 | MR6 | OMV NEW ZEALAND LTD |  | ISS Rig 18 Maari OMV | J.21.109586 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-05-02 14:24 |  | 2021-05-10 14:24 | 2021-05-18 14:25 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 17:29 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Paulo Zuliani | WL Production Services
P.1014279 | O.1014279.01 | A.1014279.01.03 | MB-PnA3 | OMV NEW ZEALAND LTD |  | Maui B Platform | J.21.109585 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-06-30 |  | 2021-07-03 | 2021-07-05 23:59 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 17:29 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Paulo Zuliani | WL Production Services
P.1014279 | O.1014279.01 | A.1014279.01.05 | MB-PnA5 | OMV NEW ZEALAND LTD |  | Maui B Platform | J.21.109584 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-07-11 |  | 2021-07-14 | 2021-07-16 23:59 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 17:29 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Paulo Zuliani | WL Production Services
P.1014279 | O.1014279.01 | A.1014279.01.01 | MauiB IRF3 P&A Campaign | OMV NEW ZEALAND LTD | MB-04B, MB-02A, MB-05B | Maui B Platform | J.21.109583 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-06-30 12:00 |  | 2021-07-04 12:00 | 2021-07-17 11:59 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 17:29 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 207234.15 | 4 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Paulo Zuliani | WL Production Services
P.1014279 | O.1014279.01 | A.1014279.01.02 | MB-PnA2 | OMV NEW ZEALAND LTD |  | Maui B Platform | J.21.109094 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-06-24 |  | 2021-06-27 | 2021-06-29 23:59 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Paulo Zuliani | WL Production Services
P.1014279 | O.1014279.01 | A.1014279.01.06 | MB-PnA6 | OMV NEW ZEALAND LTD |  | Maui B Platform | J.21.109093 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-07-17 |  | 2021-07-20 | 2021-07-22 23:59 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Paulo Zuliani | WL Production Services
P.1014279 | O.1014279.01 | A.1014279.01.04 | MB-PnA4 | OMV NEW ZEALAND LTD |  | Maui B Platform | J.21.109090 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-07-06 |  | 2021-07-08 | 2021-07-10 23:59 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Paulo Zuliani | WL Production Services
P.1014279 | O.1014279.01 | A.1014279.01.07 | Double entry | OMV NEW ZEALAND LTD | Maui- Field | Maui B Platform |  | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-06-27 |  | 2021-06-30 | 2021-07-01 23:59 |  |  | New Plymouth WL | VOliveira5 | 2022-09-03 09:59 | walfaro |  | No |  |  |  |  | Victor Oliveira |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1014279 | O.1014279.01 | A.1014279.01.08 | Double entry | OMV NEW ZEALAND LTD | Maui- Field | Maui B Platform |  | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-07-06 |  | 2021-07-07 | 2021-07-09 23:59 |  |  | New Plymouth WL | VOliveira5 | 2022-09-03 09:59 | walfaro |  | No |  |  |  |  | Victor Oliveira |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1014088 | O.1014088.08 | A.1014088.08.02 | Equipment & Personnel Monthly Charges For Mar | BEACH ENERGY LTD | THYLACINE WEST 1 | Ocean Onyx | J.22.110605 | WCF | CMT-PERS,CMT-EQPRNT | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2022-03-10 | 2022-02-25 |  | 2022-02-26 | 2022-03-25 23:59 |  | 2022-03-25 23:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 14371.9 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.08 | A.1014088.08.01 | Personnel & Equipment | BEACH ENERGY LTD | THYLACINE NORTH 2 | Ocean Onyx | J.21.109307 | WCF | CMT-EQPRNT,CMT-PERS | Low | Confirmed | Execute - PSD |  | Not Required | Not Required | In Progress |  | 2021-12-01 |  | 2021-12-01 | 2022-07-31 23:59 |  |  | AUS East Coast WS | JAhmed8 | 2022-10-03 14:28 | FDPSystemUser | M.1000057.08.34 | No |  |  |  |  | Tareq AlSaman |  | 843327.84 | 0 |  |  |  | 87.5 | 66.7 | 100 | 50 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.07 | A.1014088.07.03 | 9-5/8in Intermediate Casing | BEACH ENERGY LTD | THYLACINE NORTH-2 | Ocean Onyx | J.22.110492 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-05-06 09:00 | 2022-04-05 |  | 2022-05-24 10:00 | 2022-05-25 09:59 |  | 2022-06-30 09:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:26 | FDPSystemUser | M.1000057.08.34 | No |  |  |  |  | Tareq AlSaman |  | 90742.95 | 1 |  |  |  | 81.3 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.07 | A.1014088.07.01 | 36in Conductor | BEACH ENERGY LTD | THYLACINE NORTH-2 | Ocean Onyx | J.22.110488 | WCF | PRI-COND | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-27 23:00 | 2022-03-25 |  | 2022-05-01 | 2022-05-01 23:59 |  | 2022-06-21 23:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 129724.79 | 1 |  |  |  | 81.3 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.07 | A.1014088.07.02 | 13-3/8in Surface Casing | BEACH ENERGY LTD | THYLACINE NORTH-2 | Ocean Onyx | J.22.110480 | WCF | PRI-SURF | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-29 22:00 | 2022-03-25 |  | 2022-05-05 23:00 | 2022-05-06 22:59 |  | 2022-06-23 22:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 44536.71 | 1 |  |  |  | 81.3 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.06 | A.1014088.06.04 | Product Dispatch | BEACH ENERGY LTD | THYLACINE WEST 2 | Ocean Onyx | J.21.109314 | WCF | CMT-MATSAL | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2022-01-01 |  | 2022-01-01 | 2022-01-02 23:59 |  |  | AUS East Coast WS | JAhmed8 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 0 |  |  |  | 50 | 33.3 | 100 | 25 | 45 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.06 | A.1014088.06.03 | 9-5/8in Intermediate Casing | BEACH ENERGY LTD | THYLACINE WEST-2 | Ocean Onyx | J.22.110486 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-02-19 | 2022-02-15 |  | 2022-03-13 | 2022-03-13 23:59 |  | 2022-04-15 22:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 85533.69 | 1 |  |  |  | 81.3 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.06 | A.1014088.06.02 | 13-3/8in Casing Cement Job | BEACH ENERGY LTD | THYLACINE WEST-2 | Ocean Onyx | J.22.110483 | WCF | PRI-SURF | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-11 | 2022-01-04 |  | 2022-01-22 | 2022-01-22 23:59 |  | 2022-03-07 23:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 21825.05 | 1 |  |  |  | 81.3 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.06 | A.1014088.06.01 | 36in Conductor Casing | BEACH ENERGY LTD | THYLACINE WEST-2 | Ocean Onyx | J.22.110473 | WCF | PRI-COND | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-29 02:00 | 2022-01-02 |  | 2022-01-18 15:00 | 2022-01-19 14:59 |  | 2022-03-07 14:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 102626.7 | 1 |  |  |  | 81.3 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.05 | A.1014088.05.04 | Thylacine West-1 _ 7in Liner | BEACH ENERGY LTD | THYLACINE WEST-1 | Ocean Onyx | J.22.110467 | WCF | PRI-LIN | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-19 | 2022-01-01 |  | 2022-02-11 | 2022-02-11 23:59 |  | 2022-03-05 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 66049.95 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.05 | A.1014088.05.01 | Thylacine West-1 _ 36in Conductor Casing | BEACH ENERGY LTD | THYLACINE WEST-1 | Ocean Onyx | J.22.110466 | WCF | PRI-COND | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-19 14:00 | 2022-01-06 |  | 2022-01-24 14:00 | 2022-01-25 13:59 |  | 2022-03-06 13:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 127965.2 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.05 | A.1014088.05.03 | Thylacine West-1 _ 9-5/8in Intermediate Casing | BEACH ENERGY LTD | THYLACINE WEST 1 | Ocean Onyx | J.22.110465 | WCF | PRI-INTER | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-01-19 | 2022-01-01 |  | 2022-02-07 | 2022-02-07 23:59 |  | 2022-03-05 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 84414.25 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.05 | A.1014088.05.02 | Thylacine West-1 _ 13-3/8in Surface Casing | BEACH ENERGY LTD | THYLACINE WEST-1 | Ocean Onyx | J.22.110464 | WCF | PRI-SURF | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-18 | 2022-01-09 |  | 2022-01-26 | 2022-01-26 23:59 |  | 2022-03-04 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 21217.85 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.04 | A.1014088.04.04 | Thylacine-1 _ 7in Liner | BEACH ENERGY LTD | Thylacine | Ocean Onyx |  | WCF | PRI-LIN | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-31 03:00 | 2021-11-17 |  | 2021-12-08 02:00 | 2021-12-09 01:59 |  | 2021-12-19 02:59 | AUS East Coast WS | MAlsaman | 2021-12-27 09:48 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 69016.85 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.04 | A.1014088.04.03 | Thylacine-1 _ 9-5/8in Intermediate Casing | BEACH ENERGY LTD | Thylacine | Ocean Onyx |  | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-02 | 2021-11-17 |  | 2021-12-02 23:00 | 2021-12-03 22:59 |  | 2021-12-20 23:59 | AUS East Coast WS | MAlsaman | 2021-12-27 09:43 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 83820.7 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.04 | A.1014088.04.02 | Thylacine-1 _ 13-3/8in Surface Casing | BEACH ENERGY LTD | Thylacine | Ocean Onyx |  | WCF | PRI-SURF | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-02 19:00 | 2021-11-14 |  | 2021-11-22 18:00 | 2021-11-23 17:59 |  | 2021-12-21 18:59 | AUS East Coast WS | MAlsaman | 2021-11-23 17:46 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 20451.43 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.04 | A.1014088.04.01 | Thylacine-1 _ 36in Conductor Casing | BEACH ENERGY LTD | Thylacine | Ocean Onyx |  | WCF | PRI-COND | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-02 01:00 | 2021-11-14 |  | 2021-11-20 | 2021-11-20 23:59 |  | 2021-12-21 00:59 | AUS East Coast WS | MAlsaman | 2021-11-23 17:41 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 129341.58 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.03 | A.1014088.03.08 | Personnel For May | BEACH ENERGY LTD | GEOGRAPHE 4 | Ocean Onyx | J.21.109582 | WCF | CMT-PERS | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2021-05-31 |  | 2021-05-31 | 2021-06-01 23:59 |  |  | AUS East Coast WS | MAlsaman | 2022-10-03 15:29 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 0 |  |  |  | 56.3 | 33.3 | 100 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.03 | A.1014088.03.05 | Geographe-4 _ 7in Liner | BEACH ENERGY LTD | Geographe-4 | Ocean Onyx | J.21.109580 | WCF | PRI-LIN | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-31 02:00 | 2021-04-25 |  | 2021-05-30 16:00 | 2021-06-08 15:59 |  | 2021-06-09 01:59 | AUS East Coast WS | MAlsaman | 2022-10-03 15:28 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 118255.65 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.03 | A.1014088.03.03 | Geographe-4 _ 13-3/8in Intermediate Casing | BEACH ENERGY LTD | Geographe-4 | Ocean Onyx | J.21.109578 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-29 11:00 | 2021-04-03 |  | 2021-04-29 | 2021-05-10 00:59 |  | 2021-05-10 10:59 | AUS East Coast WS | MAlsaman | 2022-10-03 15:28 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 143917.95 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.03 | A.1014088.03.01 | Geographe-4 _ 36in Conductor Casing | BEACH ENERGY LTD | Geographe-4 | Ocean Onyx | J.21.109577 | WCF | PRI-COND | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-07 11:00 | 2021-03-26 |  | 2021-04-07 | 2021-04-10 23:59 |  | 2021-04-11 10:59 | AUS East Coast WS | MAlsaman | 2022-10-03 15:28 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 166521.7 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.03 | A.1014088.03.07 | Equipment & Personnel Monthly Activity | BEACH ENERGY LTD | GEOGRAPHE 4 | Ocean Onyx | J.21.109226 | WCF | CMT-EQPRNT,CMT-PERS | Low | Confirmed | Design - CEC |  | Design Completed | Not Started | In Progress | 2021-06-01 10:00 | 2021-06-01 |  | 2021-06-01 | 2021-06-30 23:59 |  | 2021-07-01 09:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 0 |  |  |  | 62.5 | 33.3 | 100 | 25 | 50 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.03 | A.1014088.03.06 | Personnel in April | BEACH ENERGY LTD | GEOGRAPHE 4 | Ocean Onyx | J.21.109223 | WCF | CMT-PERS | Low | Unconfirmed - 50% | Design - CEC |  | Not Required | Not Required | In Progress |  | 2021-04-04 23:00 |  | 2021-05-01 | 2021-06-01 00:59 |  |  | AUS East Coast WS | VWedhaswari | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 0 |  |  |  | 81.3 | 66.7 | 100 | 50 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1014088 | O.1014088.03 | A.1014088.03.02 | Geographe-4 _ 20in Surface Casing | BEACH ENERGY LTD | Geographe-4 | Ocean Onyx | J.21.109203 | WCF | PRI-SURF | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-10 11:00 | 2021-03-30 |  | 2021-04-10 | 2021-04-13 23:59 |  | 2021-04-14 10:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 220363.65 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.03 | A.1014088.03.04 | Geographe-4 _ 9-5/8in Liner | BEACH ENERGY LTD | Geographe-4 | Ocean Onyx | J.21.109183 | WCF | PRI-LIN | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-20 10:00 | 2021-04-14 |  | 2021-05-20 | 2021-05-30 23:59 |  | 2021-05-31 09:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 91262.3 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.02 | A.1014088.02.02 | Geographe-5 _ 36in Conductor Casing | BEACH ENERGY LTD | GEOGRAPHE-5 | Ocean Onyx | J.21.109200 | WCF | PRI-COND | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-02 10:00 | 2021-03-27 23:00 |  | 2021-04-01 23:00 | 2021-04-04 20:59 |  | 2021-04-13 08:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 89196.3 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.02 | A.1014088.02.01 | Geographe-5 _ 13-3/8in Surface Casing | BEACH ENERGY LTD | GEOGRAPHE-5 | Ocean Onyx | J.21.109193 | WCF | PRI-SURF | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-03 10:00 | 2021-03-30 23:00 |  | 2021-04-02 23:00 | 2021-04-05 21:59 |  | 2021-04-06 08:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 100296.9 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.02 | A.1014088.02.03 | Geographe-5 _ 9-5/8in Intermediate Casing | BEACH ENERGY LTD | GEOGRAPHE-5 | Ocean Onyx | J.21.109192 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-30 10:00 | 2021-06-13 |  | 2021-07-02 | 2021-07-31 23:59 |  | 2021-07-30 09:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 198204.05 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.01 | A.1014088.01.04 | Artisan-1 _ 7in Liner | BEACH ENERGY LTD | ARTISAN-1 | Ocean Onyx | J.21.109581 | WCF | PRI-LIN | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-20 11:00 | 2021-03-10 |  | 2021-03-20 | 2021-03-30 23:59 |  | 2021-03-31 10:59 | AUS East Coast WS | MAlsaman | 2022-10-03 15:29 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 123986.85 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1014088 | O.1014088.01 | A.1014088.01.02 | Artisan-1 _ 13-3/8in Surface Casing | BEACH ENERGY LTD | ARTISAN-1 | Ocean Onyx | J.21.109579 | WCF | PRI-SURF | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-01 04:00 | 2021-02-24 |  | 2021-02-28 17:00 | 2021-03-03 16:59 |  | 2021-03-04 03:59 | AUS East Coast WS | MAlsaman | 2022-10-03 15:28 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 100296.9 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1014088 | O.1014088.01 | A.1014088.01.01 | Artisan-1 _ 36in Conductor Casing | BEACH ENERGY LTD | ARTISAN-1 | Ocean Onyx | J.21.109196 | WCF | PRI-COND | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-02-21 11:00 | 2021-02-12 |  | 2021-02-21 | 2021-03-26 23:59 |  | 2021-03-27 10:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 260314.64 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1014088 | O.1014088.01 | A.1014088.01.05 | Artisan-1 _ P&A | BEACH ENERGY LTD | ARTISAN-1 | Ocean Onyx | J.21.109195 | WCF | REM-PA | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-11 11:00 | 2021-03-11 |  | 2021-03-11 | 2021-03-26 23:59 |  | 2021-03-27 10:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 253093.6 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014088 | O.1014088.01 | A.1014088.01.03 | Artisan-1 _ 9-5/8in Intermediate Casing | BEACH ENERGY LTD | ARTISAN-1 | Ocean Onyx | J.21.109190 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-27 11:00 | 2021-02-27 |  | 2021-02-27 | 2021-03-09 23:59 |  | 2021-03-10 10:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 251664.11 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1014022 | O.1014022.03 | A.1014022.03.03 | BUWD10_1338 inch casing | SANTOS LIMITED | BU-W10 | Noble Tom Prosser | J.21.109573 | WCF | PRI-INTER | InComplete | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-28 08:00 | 2021-06-21 |  | 2021-06-28 | 2021-07-08 23:59 |  | 2021-07-09 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 12:28 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1014022 | O.1014022.03 | A.1014022.03.04 | BU-W10_9 58 inch casing | SANTOS LIMITED | BU-W10 | Noble Tom Prosser | J.21.109570 | WCF | PRI-LONG | InComplete | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-12 08:00 | 2021-06-28 |  | 2021-07-12 | 2021-07-24 23:59 |  | 2021-07-25 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 12:27 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1014022 | O.1014022.03 | A.1014022.03.06 | BU-W10_PnA_Plug #A | SANTOS LIMITED |  | Noble Tom Prosser | J.21.109395 | WCF | REM-PA | Medium | Unconfirmed - 50% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-09-03 08:00 | 2021-08-29 |  | 2021-09-03 | 2021-09-04 23:59 |  | 2021-09-07 07:59 | AUS West Coast WS | HNarainasamy | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1014022 | O.1014022.03 | A.1014022.03.05 | BUWD10_7in Liner cementing | SANTOS LIMITED | BU-W10 | Noble Tom Prosser | J.21.109370 | WCF | PRI-LIN | InComplete | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-28 08:00 | 2021-07-12 |  | 2021-07-28 | 2021-08-08 23:59 |  | 2021-08-09 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1014022 | O.1014022.03 | A.1014022.03.01 | BUWD10_30inch casing | SANTOS LIMITED | BU-W10 | Noble Tom Prosser | J.21.109364 | WCF | PRI-COND | InComplete | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-10 08:00 | 2021-06-07 |  | 2021-06-10 | 2021-06-14 23:59 |  | 2021-06-15 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1014022 | O.1014022.03 | A.1014022.03.02 | BUWD10_20inch casing | SANTOS LIMITED | BU-W10 | Noble Tom Prosser | J.21.109358 | WCF | PRI-SURF | InComplete | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-20 08:00 | 2021-06-14 01:17 |  | 2021-06-20 01:16 | 2021-06-22 23:59 |  | 2021-06-23 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1014022 | O.1014022.02 | A.1014022.02.03 | BU-DS06_9 5/8 casing | SANTOS LIMITED | BU-DS06 | Noble Tom Prosser | J.21.109572 | WCF | PRI-INTER | InComplete | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-09 08:00 | 2021-08-23 |  | 2021-09-09 | 2021-09-19 23:59 |  | 2021-09-20 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 12:28 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1014022 | O.1014022.02 | A.1014022.02.02 | BUDS6_13 3/8inch casing | SANTOS LIMITED | BU-DS06 | Noble Tom Prosser | J.21.109367 | WCF | PRI-SURF | InComplete | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-23 08:00 | 2021-08-16 |  | 2021-08-23 | 2021-08-27 23:59 |  | 2021-08-28 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1014022 | O.1014022.02 | A.1014022.02.01 | BU-DS06 - 30inch casing | SANTOS LIMITED | BU-DS06 | Noble Tom Prosser | J.21.109365 | WCF | PRI-COND | InComplete | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-15 08:00 | 2021-08-09 |  | 2021-08-15 | 2021-08-22 23:59 |  | 2021-08-23 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1014022 | O.1014022.01 | A.1014022.01.06 | W13-ST1 - PnA1C - 2360mMD to 2460mMD | SANTOS LIMITED | BU-W13 | Noble Tom Prosser | J.21.109576 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress | 2021-05-05 20:00 | 2021-04-12 12:00 |  | 2021-05-05 12:00 | 2021-05-06 23:59 |  | 2021-05-07 07:59 | AUS West Coast WS | NKhoa | 2022-10-03 12:28 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1014022 | O.1014022.01 | A.1014022.01.05 | PnA 1B - 3700mMD - 4000mMD | SANTOS LIMITED | BU-W13 | Noble Tom Prosser | J.21.109575 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress | 2021-05-05 08:00 | 2021-04-12 |  | 2021-05-05 | 2021-05-05 12:00 |  | 2021-05-05 20:00 | AUS West Coast WS | NKhoa | 2022-10-03 12:28 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1014022 | O.1014022.01 | A.1014022.01.04 | PnA 1A - 4000mMD - 4300mMD | SANTOS LIMITED | BU-W13 | Noble Tom Prosser | J.21.109574 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-01 08:00 | 2021-04-13 |  | 2021-05-01 | 2021-05-04 23:59 |  | 2021-05-05 07:59 | AUS West Coast WS | NKhoa | 2022-10-03 12:28 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1014022 | O.1014022.01 | A.1014022.01.01 | BU-W13_13 3/8inch casing | SANTOS LIMITED | BU-W13 ST2 | Noble Tom Prosser | J.21.109571 | WCF | PRI-SURF | InComplete | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress | 2021-05-09 08:00 | 2021-04-12 |  | 2021-05-09 | 2021-05-15 23:59 |  | 2021-05-16 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 12:28 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1014022 | O.1014022.01 | A.1014022.01.08 | SL4 activity in April | SANTOS LIMITED | BU-W13 ST2 | Noble Tom Prosser | J.21.109379 | WCF | CMT-EQPRNT,CMT-PERS | Low | Unconfirmed - 50% | Design - CEC |  | In Progress | Not Started | In Progress | 2021-04-28 08:00 | 2021-04-28 |  | 2021-05-01 | 2021-06-09 23:59 |  | 2021-06-10 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 |  |  |  | 62.5 | 66.7 | 100 | 25 | 60 |  | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1014022 | O.1014022.01 | A.1014022.01.07 | W13-ST1 - KOP - 780mMD to 930mMD | SANTOS LIMITED | BU-W13 | Noble Tom Prosser | J.21.109377 | WCF | REM-KOP | InComplete | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress | 2021-05-07 08:00 | 2021-04-12 |  | 2021-05-07 | 2021-05-08 23:59 |  | 2021-05-09 07:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1014022 | O.1014022.01 | A.1014022.01.03 | Service - Personnel and Equipment Rental | SANTOS LIMITED | BU-W13 ST2 | Noble Tom Prosser | J.21.109371 | WCF | CMT-EQPRNT,CMT-PERS | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-04-19 08:00 | 2021-04-19 |  | 2021-04-22 | 2021-05-31 23:59 |  | 2021-06-01 07:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1014022 | O.1014022.01 | A.1014022.01.02 | BU-W13-ST2_9 5/8inch cementing | SANTOS LIMITED |  | Noble Tom Prosser | J.21.109363 | WCF | PRI-LONG | InComplete | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress | 2021-05-16 08:00 | 2021-04-12 |  | 2021-05-16 | 2021-05-24 23:59 |  | 2021-05-25 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1013717 | O.1013717.01 | A.1013717.01.04 | Jadestone¦ Workover Ops | JADESTONE ENERGY (EAGLE) PTY LTD |  | VALARIS 107 | J.22.110117 | RPI | PS-WL-NO | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-08-17 | 2022-08-17 |  | 2022-09-24 12:00 | 2022-11-21 11:59 |  | 2022-11-30 23:59 | New Burn WL | BAhmad | 2022-11-23 11:07 | VOliveira5 |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 5 |  |  |  | 83.3 | 33.3 | 100 | 50 | 60 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1013717 | O.1013717.01 | A.1013717.01.05 | Jadestone¦ Workover Activity | JADESTONE ENERGY (EAGLE) PTY LTD |  | VALARIS 107 | J.23.008560 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2023-02-06 |  | 2023-02-06 12:00 | 2023-02-26 11:59 |  |  | New Burn WL | BAhmad | 2022-10-13 10:49 | JDukas |  | No |  |  |  |  | Justin Dukas |  | 0 | 3 |  |  |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1013717 | O.1013717.01 | A.1013717.01.06 | SKUA-10 ST2 New Completion | JADESTONE ENERGY (EAGLE) PTY LTD | Skua 10 | VALARIS 107 | J.21.108886 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-11-24 |  | 2021-11-27 21:00 | 2021-12-19 20:59 |  |  | New Burn WL | AHermawan | 2022-10-03 09:58 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 4 |  |  |  | 91.7 | 50 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1013717 | O.1013717.01 | A.1013717.01.03 | SKUA-11/10 | JADESTONE ENERGY (EAGLE) PTY LTD | Skua 10, Skua 11 | VALARIS 107 | J.21.108863 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-10-22 |  | 2021-10-30 12:00 | 2021-11-19 11:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:52 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 4 |  |  |  | 91.7 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1013717 | O.1013717.01 | A.1013717.01.02 | SKUA 11 | JADESTONE ENERGY (EAGLE) PTY LTD | Skua 11 | VALARIS 107 | J.21.108862 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-09-24 |  | 2021-09-27 12:00 | 2021-10-17 11:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:52 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 743366 | 15 |  |  |  | 75 | 66.7 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1013717 | O.1013717.01 | A.1013717.01.01 | Sep Jadestone E107 Ops Activity | JADESTONE ENERGY (EAGLE) PTY LTD | Montara H2, Montara H6 | VALARIS 107 | J.21.108843 | RPI | PS-SLK-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-09-01 |  | 2021-09-11 | 2021-09-23 23:59 |  |  | New Burn WL | frosa2 | 2022-10-03 09:50 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | Wireline Slickline
P.1013282 | O.1013282.01 | A.1013282.01.02 | Horseshoe #2 | ARMOUR ENERGY (SURAT BASIN) PTY LTD | HORSESHOE #2 | Rigless Australia - 1 | J.21.109569 | RPS | STM-MPUMP | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-03 11:00 | 2021-01-31 |  | 2021-02-03 | 2021-02-14 23:59 |  | 2021-02-15 10:59 | AUS East Coast WS | ATanha | 2022-10-03 15:27 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 1629.63 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1013282 | O.1013282.01 | A.1013282.01.03 | Horseshoe #4 | ARMOUR ENERGY (SURAT BASIN) PTY LTD | HORSESHOE 4 | Rigless Australia - 1 | J.21.109568 | RPS | STM-MPUMP | InComplete | Confirmed | Execute - PSD |  | Design Completed | In Progress | In Progress | 2021-02-04 11:00 | 2021-01-31 |  | 2021-02-04 | 2021-02-11 23:59 |  | 2021-02-16 10:59 | AUS East Coast WS | ATanha | 2022-10-03 15:27 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1013282 | O.1013282.01 | A.1013282.01.04 | Forecast | ARMOUR ENERGY (SURAT BASIN) PTY LTD | Horse Shoe 4 | Rigless Australia - 1 | J.21.109212 | RPS | STM-MPUMP | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-09-14 11:00 | 2021-09-14 |  | 2021-09-14 | 2021-09-21 23:59 |  | 2021-09-26 10:59 | AUS East Coast WS | THuynh | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1013282 | O.1013282.01 | A.1013282.01.01 | Warroon 1 | ARMOUR ENERGY (SURAT BASIN) PTY LTD | Warroon 1 | Rigless Australia - 1 | J.21.109177 | RPS | STM-MPUMP | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-31 11:00 | 2021-01-31 |  | 2021-01-31 | 2021-02-11 23:59 |  | 2021-02-12 10:59 | AUS East Coast WS | TGunadi | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Trianto Adiputro Gunadi |  | 17906.43 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1013208 | O.1013208.02 | A.1013208.02.02 | Cased hole density | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri South 085 | Nitschke Rod Rig | J.21.109073 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-09-20 |  | 2021-09-21 | 2021-09-21 10:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1013208 | O.1013208.02 | A.1013208.02.01 | Cased hole density | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri South 085, Condabri South 214 | Nitschke Rod Rig | J.21.109068 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-09-16 |  | 2021-09-17 | 2021-09-21 10:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 12670.57 | 1 |  |  |  | 58.3 | 50 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1013208 | O.1013208.01 | A.1013208.01.02 | CH Density | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI SOUTH 213 | SAVANNA DRILLING #72 | J.21.109070 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-09-11 |  | 2021-09-11 18:00 | 2021-09-12 03:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 12670.57 | 1 |  |  |  | 58.3 | 50 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1013208 | O.1013208.01 | A.1013208.01.01 | USI | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Talinga 18 | SAVANNA DRILLING #72 | J.21.108968 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-01-18 |  | 2021-01-19 | 2021-01-19 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 9567.9 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1013019 | O.1013019.01 | A.1013019.01.03 | 5 1/2" | RCMA AUSTRALIA PTY LTD |  | RIGLESS - AUSTRALIA | J.22.122974 | WCF | PRI-LONG | Low | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress | 2022-06-15 10:00 | 2022-06-22 |  | 2022-07-13 | 2022-07-17 23:59 |  | 2022-08-06 09:59 | AUS East Coast WS | FDPSystemUser | 2022-11-07 19:56 | ALyons |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1013019 | O.1013019.01 | A.1013019.01.02 | 9 5/8" | RCMA AUSTRALIA PTY LTD |  | RIGLESS - AUSTRALIA | J.22.122973 | WCF | PRI-INTER | Low | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress | 2021-08-16 10:00 | 2021-08-16 |  | 2022-07-01 | 2022-07-05 23:59 |  | 2022-08-06 09:59 | AUS East Coast WS | FDPSystemUser | 2022-11-07 19:55 | ALyons |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1013019 | O.1013019.01 | A.1013019.01.01 | 13 3/8 | RCMA AUSTRALIA PTY LTD |  | RIGLESS - AUSTRALIA | J.21.111658 | WCF | PRI-SURF | InComplete | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress | 2021-06-24 10:00 | 2021-06-24 |  | 2021-07-01 | 2021-07-05 23:59 |  | 2021-08-15 09:59 | AUS East Coast WS | FDPSystemUser | 2022-11-01 15:53 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012967 | O.1012967.05 | A.1012967.05.02 | OA Service - Jan 2022 | WOODSIDE ENERGY LTD | LDA01 | Ocean Apex | J.21.109402 | WCF | CMT-EQPRNT,CMT-PERS,CMT-MATSAL,CMT-MPUMP,CMT-RECHARGE | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-01 | 2022-01-01 |  | 2022-01-01 | 2022-01-31 23:59 |  | 2022-01-31 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 83644.5 | 0 |  |  |  | 87.5 | 50 | 100 | 75 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012967 | O.1012967.05 | A.1012967.05.01 | OA Service - Dec 2021 | WOODSIDE ENERGY LTD | LDA 01 | Ocean Apex | J.21.109400 | WCF | CMT-EQPRNT,CMT-PERS,CMT-MATSAL,CMT-MPUMP,CMT-RECHARGE | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2021-12-06 | 2021-12-02 |  | 2021-12-02 | 2021-12-31 23:59 |  | 2021-12-31 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 171240 | 0 |  |  |  | 87.5 | 50 | 100 | 75 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012967 | O.1012967.04 | A.1012967.04.01 | 36in Conductor CMT | WOODSIDE ENERGY LTD | GDA05 | Ocean Apex | J.21.109562 | WCF | PRI-COND | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-11 | 2021-10-11 |  | 2021-10-11 | 2021-10-12 23:59 |  | 2021-10-12 23:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 12:27 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 219447 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012967 | O.1012967.04 | A.1012967.04.04 | 9 5/8in Liner CMT | WOODSIDE ENERGY LTD | GDA05 | Ocean Apex | J.21.109559 | WCF | PRI-LIN | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-26 | 2021-10-23 |  | 2021-10-26 | 2021-11-02 23:59 |  | 2021-11-04 23:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 12:26 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 115047.1 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012967 | O.1012967.04 | A.1012967.04.02 | 20in Surface Casing CMT | WOODSIDE ENERGY LTD | GDA 05 | Ocean Apex | J.21.109359 | WCF | PRI-SURF | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-10-13 | 2021-10-13 |  | 2021-10-13 | 2021-10-14 23:59 |  | 2021-10-14 23:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012967 | O.1012967.04 | A.1012967.04.03 | 13 5/8in Intermediate Casing CMT | WOODSIDE ENERGY LTD | GDA 05 | Ocean Apex | J.21.109356 | WCF | PRI-INTER | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-10-17 | 2021-10-15 |  | 2021-10-17 | 2021-10-22 23:59 |  | 2021-10-24 23:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012967 | O.1012967.03 | A.1012967.03.04 | LTA-01 - 10 3/4in Liner CMT | WOODSIDE ENERGY LTD | LDA 01 | Ocean Apex | J.21.109563 | WCF | PRI-LIN | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-12-13 | 2021-12-13 |  | 2021-12-13 | 2021-12-14 23:59 |  | 2021-12-14 23:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 12:27 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012967 | O.1012967.03 | A.1012967.03.02 | LDA-01 - 20in Surface Casing CMT | WOODSIDE ENERGY LTD | LDA 01 | Ocean Apex | J.21.109560 | WCF | PRI-SURF | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-11-22 | 2021-11-22 |  | 2021-11-22 | 2021-11-24 23:59 |  | 2021-11-24 23:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 12:26 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012967 | O.1012967.03 | A.1012967.03.03 | LDA-01 - 13 5/8in Intermediate Casing CMT | WOODSIDE ENERGY LTD | LDA 01 | Ocean Apex | J.21.109558 | WCF | PRI-INTER | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-11-25 | 2021-11-25 |  | 2021-11-25 | 2021-12-01 23:59 |  | 2021-12-01 23:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 12:26 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 250796.7 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012967 | O.1012967.03 | A.1012967.03.01 | LDA-01 - 36in Conductor CMT | WOODSIDE ENERGY LTD | LDA01 | Ocean Apex | J.21.109357 | WCF | PRI-COND | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-19 | 2021-11-19 |  | 2021-11-19 | 2021-11-21 23:59 |  | 2021-11-21 23:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 196274 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012967 | O.1012967.02 | A.1012967.02.03 | 13 5/8in Intermediate Casing CMT | WOODSIDE ENERGY LTD | GDA 04 | Ocean Apex | J.21.109564 | WCF | PRI-INTER | InComplete | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-07-16 02:00 | 2021-07-25 |  | 2021-08-14 18:00 | 2021-08-16 17:59 |  | 2021-07-30 01:59 | AUS West Coast WS | NKhoa | 2022-10-03 12:27 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012967 | O.1012967.02 | A.1012967.02.04 | 10 3/4in Liner CMT | WOODSIDE ENERGY LTD | GDA 04 | Ocean Apex | J.21.109362 | WCF | PRI-LIN | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-04 02:00 | 2021-07-25 |  | 2021-08-22 18:00 | 2021-09-30 |  | 2021-09-08 01:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 111969.6 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012967 | O.1012967.02 | A.1012967.02.02 | 20in Surface Casing CMT | WOODSIDE ENERGY LTD | GDA 04 | Ocean Apex | J.21.109354 | WCF | PRI-SURF | InComplete | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-07-08 | 2021-07-20 |  | 2021-08-06 16:00 | 2021-08-08 15:59 |  | 2021-07-12 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012967 | O.1012967.02 | A.1012967.02.01 | 36in Conductor CMT | WOODSIDE ENERGY LTD | GDA 04 | Ocean Apex | J.21.109350 | WCF | PRI-COND | InComplete | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-07-05 08:00 | 2021-07-20 |  | 2021-08-04 | 2021-08-04 23:59 |  | 2021-07-08 07:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 208104.5 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012967 | O.1012967.01 | A.1012967.01.07 | Personnel | WOODSIDE ENERGY LTD | GDA03 | Ocean Apex | J.21.109567 | WCF | CMT-MPUMP,CMT-PERS | Low | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2021-08-05 |  | 2021-08-09 | 2021-08-31 23:59 |  |  | AUS West Coast WS | VWedhaswari | 2022-10-03 12:27 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 |  |  |  | 81.3 | 50 | 100 | 25 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012967 | O.1012967.01 | A.1012967.01.06 | 9 5/8in liner leak hunting | WOODSIDE ENERGY LTD | GDA 03 | Ocean Apex | J.21.109566 | WCF | CMT-TOOLS | InComplete | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2021-07-21 18:00 | 2021-07-15 |  | 2021-07-21 18:00 | 2021-07-22 23:59 |  | 2021-07-22 23:59 | AUS West Coast WS | NKhoa | 2022-10-03 12:27 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 |  |  |  | 68.8 | 16.7 | 0 | 12.5 | 35 |  | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1012967 | O.1012967.01 | A.1012967.01.05 | P&A | WOODSIDE ENERGY LTD | GDA 03 | Ocean Apex | J.21.109565 | WCF | REM-PA | Medium | Unconfirmed - 50% | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-07-20 08:00 | 2021-06-28 |  | 2021-07-20 | 2021-08-01 23:59 |  | 2021-08-02 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 12:27 | FDPSystemUser |  | No |  |  |  |  | Victoria Rasmi Wedhaswari |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1012967 | O.1012967.01 | A.1012967.01.04 | 9 5/8in Liner CMT | WOODSIDE ENERGY LTD | GDA 03 | Ocean Apex | J.21.109561 | WCF | PRI-LIN | InComplete | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-06-19 08:00 | 2021-06-28 |  | 2021-07-19 | 2021-07-24 23:59 |  | 2021-07-04 07:59 | AUS West Coast WS | NKhoa | 2022-10-03 12:27 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1012967 | O.1012967.01 | A.1012967.01.02 | 20in Surface Casing CMT | WOODSIDE ENERGY LTD | GDA 03 | Ocean Apex | J.21.109557 | WCF | PRI-SURF | InComplete | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-06-04 08:00 | 2021-06-18 |  | 2021-07-04 | 2021-07-08 23:59 |  | 2021-06-09 07:59 | AUS West Coast WS | NKhoa | 2022-10-03 12:26 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1012967 | O.1012967.01 | A.1012967.01.03 | 13 5/8in Intermediate Casing CMT | WOODSIDE ENERGY LTD | GDA 03 | Ocean Apex | J.21.109355 | WCF | PRI-INTER | InComplete | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-06-11 20:00 | 2021-07-06 |  | 2021-07-11 12:00 | 2021-07-16 11:59 |  | 2021-06-25 19:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1012967 | O.1012967.01 | A.1012967.01.01 | 36in Conductor CMT | WOODSIDE ENERGY LTD | GDA03 | Ocean Apex | J.21.109345 | WCF | PRI-COND | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-02 08:00 | 2021-06-18 |  | 2021-07-02 | 2021-07-04 23:59 |  | 2021-06-05 07:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 318971.1 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1012966 | O.1012966.03 | A.1012966.03.01 | PnA-1 - 250m | WOODSIDE ENERGY LTD | YODEL 4 | Ocean Apex | J.21.109554 | WCF | REM-PA | InComplete | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-06-28 11:00 | 2021-06-10 |  | 2021-06-28 03:00 | 2021-07-13 02:59 |  | 2021-07-13 10:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 12:26 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 7167.5 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1012966 | O.1012966.03 | A.1012966.03.02 | Perf and Wash CMT | WOODSIDE ENERGY LTD | Echo Yodel 4 | Ocean Apex | J.21.109349 | WCF | REM-SQ | InComplete | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-25 08:00 | 2021-06-25 |  | 2021-06-25 | 2021-06-29 23:59 |  | 2021-07-10 07:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1012966 | O.1012966.02 | A.1012966.02.03 | Personnel | WOODSIDE ENERGY LTD | YODEL 3 | Ocean Apex | J.21.109384 | WCF | CMT-PERS | Low | Confirmed | Design - CEC |  | Not Required | Not Required | In Progress |  | 2021-06-01 |  | 2021-06-01 | 2021-06-30 23:59 |  |  | AUS West Coast WS | VWedhaswari | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 |  |  |  | 87.5 | 66.7 | 100 | 50 | 75 |  | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1012966 | O.1012966.02 | A.1012966.02.01 | PnA-1 - 250m | WOODSIDE ENERGY LTD | Echo Yodel 3 | Ocean Apex | J.21.109353 | WCF | REM-PA | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-14 08:00 | 2021-05-21 |  | 2021-06-14 | 2021-06-18 23:59 |  | 2021-06-29 07:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 27755 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1012966 | O.1012966.02 | A.1012966.02.02 | Perf and Wash CMT | WOODSIDE ENERGY LTD | Echo Yodel 3 | Ocean Apex | J.21.109352 | WCF | REM-SQ | InComplete | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-05 08:00 | 2021-06-05 |  | 2021-06-05 | 2021-06-09 23:59 |  | 2021-06-20 07:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1012966 | O.1012966.01 | A.1012966.01.05 | SL4 activity-April | WOODSIDE ENERGY LTD | CAPELLA 1 | Ocean Apex | J.21.109556 | WCF | CMT-EQPRNT,CMT-PERS | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Required | In Progress | 2021-05-01 08:00 | 2021-04-17 |  | 2021-05-01 | 2021-06-05 23:59 |  | 2021-06-06 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 12:26 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 |  |  |  | 75 | 66.7 | 100 | 25 | 65 |  | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1012966 | O.1012966.01 | A.1012966.01.04 | SL4 Activity | WOODSIDE ENERGY LTD | CAPELLA 1 | Ocean Apex | J.21.109555 | WCF | CMT-EQPRNT,CMT-PERS | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-04-15 08:00 | 2021-04-01 |  | 2021-04-15 | 2021-05-20 23:59 |  | 2021-05-21 07:59 | AUS West Coast WS | NKhoa | 2022-10-03 12:26 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1012966 | O.1012966.01 | A.1012966.01.01 | PnA-1 - 250m | WOODSIDE ENERGY LTD | Capella-1 | Ocean Apex | J.21.109553 | WCF | REM-PA | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-10 08:00 | 2021-04-10 |  | 2021-05-10 | 2021-05-24 23:59 |  | 2021-05-25 07:59 | AUS West Coast WS | NKhoa | 2022-10-03 12:26 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 55219.3 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1012966 | O.1012966.01 | A.1012966.01.06 | 7in casing Inflow test | WOODSIDE ENERGY LTD | Capella-1 | Ocean Apex | J.21.109385 | WCF | CMT-TOOLS | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-05-10 08:00 | 2021-05-04 |  | 2021-05-10 | 2021-05-31 12:24 |  | 2021-05-31 20:24 | AUS West Coast WS | NKhoa | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 |  |  |  | 68.8 | 33.3 | 0 | 0 | 37.5 |  | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1012966 | O.1012966.01 | A.1012966.01.03 | Service - Equipment and Personnel | WOODSIDE ENERGY LTD | CAPELLA 1 | Ocean Apex | J.21.109361 | WCF | CMT-PERS,CMT-EQPRNT | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2021-04-19 08:00 | 2021-03-15 |  | 2021-04-15 | 2021-06-30 12:21 |  | 2021-06-30 20:21 | AUS West Coast WS | NKhoa | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1012966 | O.1012966.01 | A.1012966.01.02 | Perf and Wash CMT | WOODSIDE ENERGY LTD | CAPELLA 1 | Ocean Apex | J.21.109360 | WCF | REM-SQ | InComplete | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-16 08:00 | 2021-05-16 |  | 2021-05-16 | 2021-05-20 23:59 |  | 2021-05-31 07:59 | AUS West Coast WS | NKhoa | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Khoa Nguyen Thuong |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1012874 | O.1012874.06 | A.1012874.06.03 | Contingency Squeeze | OMV NEW ZEALAND LTD | MA-14 | Archer Emerald | J.21.109344 | WCF | REM-SQ | InComplete | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-09-15 08:00 | 2021-09-13 |  | 2021-09-15 | 2021-09-17 23:59 |  | 2021-09-18 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Victoria Rasmi Wedhaswari |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012874 | O.1012874.06 | A.1012874.06.02 | 5in Liner | OMV NEW ZEALAND LTD | MA-14 | Archer Emerald | J.21.109339 | WCF | PRI-LIN | InComplete | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-08-31 08:00 | 2021-08-29 |  | 2021-08-31 | 2021-09-02 23:59 |  | 2021-09-03 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Victoria Rasmi Wedhaswari |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012874 | O.1012874.06 | A.1012874.06.01 | 7in Casing | OMV NEW ZEALAND LTD | MA-14 | Archer Emerald | J.21.109335 | WCF | PRI-INTER | InComplete | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-08-16 08:00 | 2021-08-02 |  | 2021-08-16 | 2021-08-18 23:59 |  | 2021-08-19 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Victoria Rasmi Wedhaswari |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012874 | O.1012874.05 | A.1012874.05.02 | P&A | OMV NEW ZEALAND LTD |  | Archer Emerald | J.21.109548 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-07-08 08:00 | 2021-07-05 |  | 2021-07-08 | 2021-07-10 23:59 |  | 2021-07-11 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 12:25 | FDPSystemUser |  | No |  |  |  |  | Victoria Rasmi Wedhaswari |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012874 | O.1012874.05 | A.1012874.05.01 | 5in Liner Cementing | OMV NEW ZEALAND LTD |  | Archer Emerald | J.21.109337 | WCF | PRI-LIN | InComplete | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-06-30 08:00 | 2021-06-15 |  | 2021-06-30 | 2021-07-05 23:59 |  | 2021-07-06 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Victoria Rasmi Wedhaswari |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012874 | O.1012874.04 | A.1012874.04.01 | Contingency Squeeze | OMV NEW ZEALAND LTD | MA-13 | Archer Emerald | J.21.109550 | WCF | REM-SQ | InComplete | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-05-15 08:00 | 2021-05-03 |  | 2021-05-15 | 2021-05-20 23:59 |  | 2021-05-21 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 12:26 | FDPSystemUser |  | No |  |  |  |  | Victoria Rasmi Wedhaswari |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012874 | O.1012874.03 | A.1012874.03.02 | Contingency squeeze | OMV NEW ZEALAND LTD | MA-01A | Archer Emerald | J.21.109351 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-04-26 08:00 | 2021-04-22 |  | 2021-04-26 | 2021-04-28 23:59 |  | 2021-04-29 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Victoria Rasmi Wedhaswari |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012874 | O.1012874.03 | A.1012874.03.01 | 7inch casing | OMV NEW ZEALAND LTD | MA-01A | Archer Emerald | J.21.109348 | WCF | PRI-INTER | InComplete | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-04-15 08:00 | 2021-03-18 |  | 2021-04-15 | 2021-04-20 23:59 |  | 2021-06-10 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Victoria Rasmi Wedhaswari |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012874 | O.1012874.02 | A.1012874.02.03 | Compressor charge MA-11 | OMV NEW ZEALAND LTD | MA-11A | Archer Emerald | J.21.109552 | WCF | CMT-RECHARGE | InComplete | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-01-27 08:00 | 2021-01-25 |  | 2021-01-26 | 2021-02-25 23:59 |  | 2021-02-26 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 12:26 | FDPSystemUser |  | No |  |  |  |  | Victoria Rasmi Wedhaswari |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012874 | O.1012874.02 | A.1012874.02.02 | Monthly Rental Feb | OMV NEW ZEALAND LTD | MA-11A | Archer Emerald | J.21.109551 | WCF | CMT-EQPRNT | InComplete | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-01-27 08:00 | 2021-01-25 |  | 2021-01-26 | 2021-02-25 23:59 |  | 2021-02-26 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 12:26 | FDPSystemUser |  | No |  |  |  |  | Victoria Rasmi Wedhaswari |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012874 | O.1012874.02 | A.1012874.02.04 | Contingency Squeeze | OMV NEW ZEALAND LTD | MA-11A | Archer Emerald | J.21.109342 | WCF | REM-SQ | InComplete | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-08 08:00 | 2021-03-05 |  | 2021-03-08 | 2021-03-10 23:59 |  | 2021-03-11 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Victoria Rasmi Wedhaswari |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012874 | O.1012874.02 | A.1012874.02.01 | 7inch Casing | OMV NEW ZEALAND LTD | MA-11A | Archer Emerald | J.21.109332 | WCF | PRI-INTER | InComplete | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-20 08:00 | 2021-02-10 |  | 2021-02-20 | 2021-02-23 23:59 |  | 2021-02-24 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Victoria Rasmi Wedhaswari |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012874 | O.1012874.01 | A.1012874.01.03 | P&A Through BHA | OMV NEW ZEALAND LTD | MA-03A | Archer Emerald | J.21.109549 | WCF | REM-PA | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-16 16:00 | 2021-01-16 |  | 2021-01-16 08:00 | 2021-01-18 07:59 |  | 2021-01-18 15:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 12:25 | FDPSystemUser |  | No |  |  |  |  | Victoria Rasmi Wedhaswari |  | 39076.3 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012874 | O.1012874.01 | A.1012874.01.01 | Leaking Casing Squeeze | OMV NEW ZEALAND LTD | MA 03A | Archer Emerald | J.21.109347 | WCF | REM-SQ | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-01-09 08:00 | 2021-01-08 20:00 |  | 2021-01-09 | 2021-01-10 23:59 |  | 2021-01-11 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Victoria Rasmi Wedhaswari |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012874 | O.1012874.01 | A.1012874.01.02 | 7inch Casing | OMV NEW ZEALAND LTD | MA-03A | Archer Emerald | J.21.109346 | WCF | PRI-INTER | InComplete | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-27 08:00 | 2021-01-20 |  | 2021-01-27 | 2021-01-29 23:59 |  | 2021-01-30 07:59 | AUS West Coast WS | VWedhaswari | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Victoria Rasmi Wedhaswari |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012820 | O.1012820.02 | A.1012820.02.06 | Timor Sea Well Dec | SANTOS NA (19-12) PTY LTD |  | Noble Tom Prosser | J.22.110124 | RPE | ES-OH-Ops | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-12-01 |  | 2022-12-05 | 2022-12-24 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:57 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1012820 | O.1012820.02 | A.1012820.02.05 | Timor Sea Well Sep | SANTOS NA (19-12) PTY LTD |  | Noble Tom Prosser | J.22.110123 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-09-01 |  | 2022-09-05 | 2022-09-24 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:57 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1012820 | O.1012820.02 | A.1012820.02.04 | Exploration Well 4 | SANTOS NA (19-12) PTY LTD |  | Noble Tom Prosser | J.22.110110 | RPE | ES-OH-Ops | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-07-01 |  | 2022-07-05 | 2022-07-24 23:59 |  |  | New Burn WL | MMclean3 | 2022-10-03 09:53 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1012820 | O.1012820.02 | A.1012820.02.03 | Exploration Well 3 | SANTOS NA (19-12) PTY LTD |  | Noble Tom Prosser | J.22.110109 | RPE | ES-OH-Ops | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-05-01 |  | 2022-05-10 | 2022-06-20 23:59 |  |  | New Burn WL | MMclean3 | 2022-10-03 09:53 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1012820 | O.1012820.02 | A.1012820.02.02 | Exploration Well 2 | SANTOS NA (19-12) PTY LTD |  | Noble Tom Prosser | J.22.110108 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-01-10 |  | 2022-01-15 | 2022-03-17 23:59 |  |  | New Burn WL | MMclean3 | 2022-10-03 09:53 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1012820 | O.1012820.02 | A.1012820.02.01 | Decmeber Activity | SANTOS NA (19-12) PTY LTD | DANCER-1 | Noble Tom Prosser | J.21.108864 | RPE | ES-OH-NO | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-12-17 |  | 2021-12-23 | 2022-01-31 23:59 |  |  | New Burn WL | frosa2 | 2022-10-03 09:52 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 1 |  |  |  | 41.7 | 33.3 | 100 | 50 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1012820 | O.1012820.01 | A.1012820.01.07 | NTP_October_BU-DS06 | SANTOS NA (19-12) PTY LTD | BU-DS06 | Noble Tom Prosser | J.21.108880 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-10-15 |  | 2021-11-17 | 2021-12-04 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:55 | FDPSystemUser |  | No |  |  |  |  | James Cade |  | 0 | 1 |  |  |  | 66.7 | 50 | 0 | 25 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1012820 | O.1012820.01 | A.1012820.01.06 | July SLK activity | SANTOS NA (19-12) PTY LTD | BU-W13 ST2 | Noble Tom Prosser | J.21.108866 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-06-25 |  | 2021-07-10 | 2021-07-25 23:59 |  |  | New Burn WL | frosa2 | 2022-10-03 09:53 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 1 |  |  |  | 50 | 50 | 0 | 50 | 45 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1012820 | O.1012820.01 | A.1012820.01.05 | Santos ¦ BU-W10 ¦ Noble Tom Prosser ¦ Intervention & Slickline | SANTOS NA (19-12) PTY LTD | BU-W10 | Noble Tom Prosser | J.21.108861 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-09-08 |  | 2021-09-15 | 2021-09-22 23:59 |  |  | New Burn WL | frosa2 | 2022-10-03 09:52 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 2032 | 0 |  |  |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1012820 | O.1012820.01 | A.1012820.01.04 | Aug Activity NTP | SANTOS NA (19-12) PTY LTD |  | Noble Tom Prosser | J.21.108860 | RPI | PS-WL-NO | High | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2021-08-01 | 2021-08-01 |  | 2021-08-01 | 2021-08-14 23:59 |  | 2021-08-14 23:59 | New Burn WL | frosa2 | 2022-10-03 09:52 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 0 |  | L0 - No RO |  | 66.7 | 66.7 | 100 | 50 | 65 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1012820 | O.1012820.01 | A.1012820.01.03 | July Activity NTP | SANTOS NA (19-12) PTY LTD |  | Noble Tom Prosser | J.21.108850 | RPI | PS-WL-NO | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2021-07-01 | 2021-07-01 |  | 2021-07-01 | 2021-07-14 23:59 |  | 2021-07-14 23:59 | New Burn WL | frosa2 | 2022-10-03 09:51 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 0 |  | L0 - No RO |  | 41.7 | 33.3 | 100 | 50 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1012820 | O.1012820.01 | A.1012820.01.02 | May Activity NTP | SANTOS NA (19-12) PTY LTD | BU-W13ST1 | Noble Tom Prosser | J.21.108849 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-04-15 |  | 2021-05-08 | 2021-06-07 23:59 |  |  | New Burn WL | frosa2 | 2022-10-03 09:51 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 288603 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1012820 | O.1012820.01 | A.1012820.01.01 | Bayu Undan Phase 3C Infill | SANTOS NA (19-12) PTY LTD |  | Noble Tom Prosser | J.21.108842 | RPI | PS-WL-NO | Medium | Unconfirmed - 50% | Design - CEC |  | Design Completed | Not Started | In Progress | 2021-05-10 | 2021-04-15 |  | 2021-05-10 | 2021-10-31 23:59 |  | 2021-10-31 23:59 | New Burn WL | BAhmad | 2022-10-03 09:50 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 0 |  | L0 - No RO |  | 50 | 50 | 100 | 50 | 55 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1012748 | O.1012748.01 | A.1012748.01.02 | Santos¦ MS-1 | SANTOS WESTERN AUSTRALIA |  | ENSCO MS-1 | J.23.008561 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2023-09-21 |  | 2023-09-21 | 2023-10-14 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:56 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 0 |  |  |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1012748 | O.1012748.01 | A.1012748.01.01 | Van Gogh Phase 2 | SANTOS WESTERN AUSTRALIA |  | ENSCO MS-1 | J.22.110105 | RPI | PS-WL-NO | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-06-01 |  | 2022-06-21 | 2022-12-02 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:50 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1012690 | O.1012690.01 | A.1012690.01.07 | Kumbili-1 8.5in OH | TIMOR RESOURCES | Kumbili-1 | EASTERN DRILLING RIG # 1 | J.22.110146 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2022-02-01 |  | 2022-02-18 01:29 | 2022-03-17 23:59 |  |  | New Burn WL | CChairil | 2022-10-03 10:00 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 7650 | 7 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1012690 | O.1012690.01 | A.1012690.01.06 | Timor Resources Kumbili-1 12.25in | TIMOR RESOURCES | Kumbili-1 | EASTERN DRILLING RIG # 1 | J.22.110113 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-01-24 |  | 2022-01-30 | 2022-02-18 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:54 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 48240 | 5 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1012690 | O.1012690.01 | A.1012690.01.05 | Timor Resources Karau-1 6in | TIMOR RESOURCES | Karau 1 | EASTERN DRILLING RIG # 1 | J.21.108877 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-12-01 |  | 2021-12-07 | 2021-12-26 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:54 | FDPSystemUser |  | No |  |  |  |  | James Cade |  | 0 | 4 |  |  |  | 91.7 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1012690 | O.1012690.01 | A.1012690.01.04 | Sep-Timor Resources | TIMOR RESOURCES |  | EASTERN DRILLING RIG # 1 | J.21.108858 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-08-25 |  | 2021-08-25 | 2021-09-13 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:52 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 4 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1012690 | O.1012690.01 | A.1012690.01.03 | Sept Activity Timor Resources | TIMOR RESOURCES |  | EASTERN DRILLING RIG # 1 | J.21.108851 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-09-01 |  | 2021-09-01 | 2021-09-25 23:59 |  |  | New Burn WL | frosa2 | 2022-10-03 09:51 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1012690 | O.1012690.01 | A.1012690.01.01 | Timor Resources project non Operational | TIMOR RESOURCES |  | EASTERN DRILLING RIG # 1 | J.22.110104 | RPE | ES-OH-NO | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-01-24 |  | 2022-01-24 | 2022-03-31 23:59 |  |  | New Burn WL | frosa2 | 2022-10-03 09:50 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1012690 | O.1012690.01 | A.1012690.01.02 | Timor Resources Karau-1 8.5in | TIMOR RESOURCES | Karau 1 | EASTERN DRILLING RIG # 1 | J.21.108841 | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-10-01 |  | 2021-11-22 13:00 | 2021-12-11 12:59 |  |  | New Burn WL | frosa2 | 2022-10-03 09:50 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 0 | 6 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1012679 | O.1012679.01 | A.1012679.01.04 | 5-1/2in Casing - Squeeze Cementing | ENERGY RESOURCES LIMITED | LOCKYER DEEP 1 | RIGLESS - AUSTRALIA | J.21.109283 | WCF | PRI-LONG, CMT-MATSAL, REM-SQ | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-10-21 | 2021-10-21 22:00 |  | 2021-10-22 12:00 | 2021-10-24 11:59 |  | 2021-10-27 23:59 | AUS East Coast WS | HNarainasamy | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 |  |  |  | 68.8 | 16.7 | 0 | 0 | 32.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012679 | O.1012679.01 | A.1012679.01.03 | 5 1/2" Lockyer Deep 1 | ENERGY RESOURCES LIMITED | LOCKYER DEEP 1 | RIGLESS - AUSTRALIA | J.21.109191 | WCF | PRI-LONG, CMT-MATSAL | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-08-14 03:00 | 2021-09-18 |  | 2021-09-22 18:00 | 2021-09-24 17:59 |  | 2021-10-29 17:59 | AUS East Coast WS | ALyons | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012679 | O.1012679.01 | A.1012679.01.01 | 13 3/8 Lockyer Deep | ENERGY RESOURCES LIMITED | LOCKYER DEEP 1 | RIGLESS - AUSTRALIA | J.21.109185 | WCF | PRI-SURF, CMT-MATSAL | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-07-15 12:00 | 2021-07-15 12:00 |  | 2021-07-22 08:00 | 2021-07-24 07:59 |  | 2021-09-30 23:59 | AUS East Coast WS | ALyons | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012679 | O.1012679.01 | A.1012679.01.02 | 9 5/8" Lockyer Deep 1 | ENERGY RESOURCES LIMITED | LOCKYER DEEP 1 | RIGLESS - AUSTRALIA | J.21.109173 | WCF | PRI-INTER, CMT-MATSAL | InComplete | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-08-11 21:00 | 2021-07-15 12:00 |  | 2021-08-25 12:00 | 2021-08-27 11:59 |  | 2021-10-22 00:59 | AUS East Coast WS | ALyons | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Heimanath Naidu Narainasamy |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1012060 | O.1012060.06 | A.1012060.06.20 | 2024 Archetype Test | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Well #1 | RIGLESS - AUSTRALIA | J.24.010444 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2021-01-10 11:00 | 2024-02-01 | 2024-02-01 | 2024-02-01 | 2024-02-02 23:59 | 2024-02-03 | 2023-02-22 10:59 | AUS East Coast WS | AKohr | 2023-08-28 10:07 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.06 | A.1012060.06.19 | Well 85 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.088036 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-28 | 2023-12-28 | 2023-12-27 01:00 | 2023-12-28 | 2023-12-30 23:59 | 2023-12-30 01:00 | 2023-12-30 23:59 | AUS East Coast WS | HFerdjallah | 2023-08-28 10:03 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.06 | A.1012060.06.18 | WELL 84 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.085430 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-19 | 2023-12-19 | 2023-12-18 01:00 | 2023-12-19 | 2023-12-21 23:59 | 2023-12-21 01:00 | 2023-12-21 23:59 | AUS East Coast WS | radinegara | 2023-08-28 10:02 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.06 | A.1012060.06.17 | WELL 83 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.085429 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-16 | 2023-12-16 | 2023-12-15 01:00 | 2023-12-16 | 2023-12-18 23:59 | 2023-12-18 01:00 | 2023-12-18 23:59 | AUS East Coast WS | radinegara | 2023-08-28 10:01 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.06 | A.1012060.06.01 | WELL 67 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Well #1 | RIGLESS - AUSTRALIA | J.23.085396 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-10-21 | 2023-10-21 |  | 2023-10-21 | 2023-10-23 23:59 |  | 2023-10-24 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:13 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.06 | A.1012060.06.02 | WELL 68 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Well #1 | RIGLESS - AUSTRALIA | J.23.085404 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-10-24 | 2023-10-24 |  | 2023-10-24 | 2023-10-26 23:59 |  | 2023-10-26 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:13 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.06 | A.1012060.06.03 | WELL 69 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Well #1 | RIGLESS - AUSTRALIA | J.23.085405 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-10-27 | 2023-10-27 |  | 2023-10-27 | 2023-10-31 23:59 |  | 2023-10-31 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:13 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.06 | A.1012060.06.04 | WELL 70 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Well #1 | RIGLESS - AUSTRALIA | J.23.085406 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-01 | 2023-11-01 |  | 2023-11-01 | 2023-11-03 23:59 |  | 2023-11-03 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:13 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.06 | A.1012060.06.05 | WELL 71 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Well #1 | RIGLESS - AUSTRALIA | J.23.085407 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-04 | 2023-11-04 |  | 2023-11-04 | 2023-11-06 23:59 |  | 2023-11-06 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:13 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.06 | A.1012060.06.06 | WELL 72 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Well #1 | RIGLESS - AUSTRALIA | J.23.085812 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-07 | 2023-11-07 |  | 2023-11-07 | 2023-11-09 23:59 |  | 2023-11-09 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:13 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.06 | A.1012060.06.07 | WELL 73 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Well #1 | RIGLESS - AUSTRALIA | J.23.085409 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-10 | 2023-11-10 |  | 2023-11-10 | 2023-11-12 23:59 |  | 2023-11-12 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:13 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.06 | A.1012060.06.08 | WELL 74 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Well #1 | RIGLESS - AUSTRALIA | J.23.085412 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-13 | 2023-11-13 |  | 2023-11-13 | 2023-11-15 23:59 |  | 2023-11-15 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:13 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.06 | A.1012060.06.09 | WELL 75 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Well #1 | RIGLESS - AUSTRALIA | J.23.085413 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-16 | 2023-11-16 |  | 2023-11-16 | 2023-11-18 23:59 |  | 2023-11-18 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:13 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.06 | A.1012060.06.10 | WELL 76 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Well #1 | RIGLESS - AUSTRALIA | J.23.085416 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-19 | 2023-11-19 |  | 2023-11-19 | 2023-11-21 23:59 |  | 2023-11-21 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:12 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.06 | A.1012060.06.11 | WELL 77 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Well #1 | RIGLESS - AUSTRALIA | J.23.085415 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-22 | 2023-11-22 |  | 2023-11-22 | 2023-11-24 23:59 |  | 2023-11-24 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:12 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.06 | A.1012060.06.12 | WELL 78 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Well #1 | RIGLESS - AUSTRALIA | J.23.085420 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-01 | 2023-12-01 |  | 2023-12-01 | 2023-12-03 23:59 |  | 2023-12-03 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:12 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.06 | A.1012060.06.13 | WELL 79 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Well #1 | RIGLESS - AUSTRALIA | J.23.085421 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-04 | 2023-12-04 |  | 2023-12-04 | 2023-12-06 23:59 |  | 2023-12-06 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:12 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.06 | A.1012060.06.15 | WELL 81 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Well #1 | RIGLESS - AUSTRALIA | J.23.085423 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-10 | 2023-12-10 |  | 2023-12-10 | 2023-12-12 23:59 |  | 2023-12-12 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:12 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.06 | A.1012060.06.14 | WELL 80 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Well #1 | RIGLESS - AUSTRALIA | J.23.085422 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-07 | 2023-12-07 |  | 2023-12-07 | 2023-12-09 23:59 |  | 2023-12-09 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:12 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.06 | A.1012060.06.16 | WELL 82 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Well #1 | RIGLESS - AUSTRALIA | J.23.085424 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-13 | 2023-12-13 |  | 2023-12-13 | 2023-12-15 23:59 |  | 2023-12-15 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:12 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.39 | Sample well for Archetype | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.24.006839 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-03-01 | 2025-03-01 | 2025-02-26 | 2025-03-01 | 2025-03-03 23:59 | 2025-03-01 | 2025-03-03 23:59 | AUS East Coast WS | radinegara | 2024-05-15 14:17 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.25 | RCK 132 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 132 | RIGLESS - AUSTRALIA | J.23.085381 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-08-04 | 2023-08-04 |  | 2023-08-04 | 2023-08-05 23:59 |  | 2023-08-05 23:59 | AUS East Coast WS | radinegara | 2023-11-12 13:28 | JMeyer9 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 779.7 | 7 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.24 | RCK 100 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 100 | RIGLESS - AUSTRALIA | J.23.085377 | RPS | FRAC-PROP | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-28 | 2023-07-28 |  | 2023-07-28 | 2023-08-03 23:59 |  | 2023-08-03 23:59 | AUS East Coast WS | radinegara | 2023-11-12 12:23 | JMeyer9 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 3063.02 | 7 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.13 | COM 377 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 377 | RIGLESS - AUSTRALIA | J.23.085365 | RPS | FRAC-PROP | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-22 | 2023-06-22 |  | 2023-06-22 | 2023-06-23 23:59 |  | 2023-06-23 23:59 | AUS East Coast WS | radinegara | 2023-11-03 19:35 | JMeyer9 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 3388.17 | 7 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.26 | RCK 161 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 161 | RIGLESS - AUSTRALIA | J.23.085382 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-08-06 | 2023-08-06 | 2023-08-06 | 2023-08-06 | 2023-08-08 23:59 | 2023-08-08 | 2023-08-07 23:59 | AUS East Coast WS | radinegara | 2023-09-04 15:47 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 259.9 | 7 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.40 | Origin CoilFRAC Retainer Charges | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.129186 | RPS | STM-RECHARGE | Low | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2023-10-01 |  | 2023-10-01 | 2023-12-31 23:59 |  |  | AUS East Coast WS | HFerdjallah | 2023-08-30 14:18 | HFerdjallah |  | No |  |  |  |  | Ramadhani Adi Negara |  | 0 | 0 |  |  |  | 43.8 | 33.3 | 100 | 50 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.18 | COM 422 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 422 | RIGLESS - AUSTRALIA | J.23.085369 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-15 | 2023-07-15 | 2023-07-15 | 2023-07-15 | 2023-07-16 23:59 | 2023-07-17 | 2023-07-16 23:59 | AUS East Coast WS | radinegara | 2023-08-12 08:58 | TZin |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.17 | COM 421 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 421 | RIGLESS - AUSTRALIA | J.23.085368 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-12 | 2023-07-12 | 2023-07-12 | 2023-07-12 | 2023-07-14 23:59 | 2023-07-15 | 2023-07-14 23:59 | AUS East Coast WS | radinegara | 2023-08-12 08:54 | TZin |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.23 | RCK 102 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 102 | RIGLESS - AUSTRALIA | J.23.085792 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-26 | 2023-07-26 | 2023-07-26 | 2023-07-26 | 2023-07-27 23:59 | 2023-07-28 | 2023-07-27 23:59 | AUS East Coast WS | radinegara | 2023-08-04 10:54 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.22 | RCK 071 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 71 | RIGLESS - AUSTRALIA | J.23.085376 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-23 | 2023-07-23 | 2023-07-23 | 2023-07-23 | 2023-07-25 23:59 | 2023-07-26 | 2023-07-25 23:59 | AUS East Coast WS | radinegara | 2023-08-04 10:52 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.21 | RCK 286 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 286 | RIGLESS - AUSTRALIA | J.23.085375 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-21 | 2023-07-21 | 2023-07-21 | 2023-07-21 | 2023-07-22 23:59 | 2023-07-23 | 2023-07-22 23:59 | AUS East Coast WS | radinegara | 2023-07-23 21:27 | TZin |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.20 | RCK 072 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 72 | RIGLESS - AUSTRALIA | J.23.085374 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-19 | 2023-07-19 | 2023-07-19 | 2023-07-19 | 2023-07-20 23:59 | 2023-07-21 | 2023-07-20 23:59 | AUS East Coast WS | radinegara | 2023-07-23 21:19 | TZin |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.19 | RCK 070 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 70 | RIGLESS - AUSTRALIA | J.23.085370 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-17 | 2023-07-17 | 2023-07-17 | 2023-07-17 | 2023-07-18 23:59 | 2023-07-19 | 2023-07-18 23:59 | AUS East Coast WS | radinegara | 2023-07-23 21:05 | TZin |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.16 | COM 420 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 420 | RIGLESS - AUSTRALIA | J.23.085367 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-07-11 23:59 | 2023-07-12 | 2023-07-11 23:59 | AUS East Coast WS | radinegara | 2023-07-14 16:36 | radinegara |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.15 | COM 375 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 375 | RIGLESS - AUSTRALIA | J.23.085366 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-26 | 2023-06-26 | 2023-06-26 | 2023-06-26 | 2023-07-09 23:59 | 2023-07-10 | 2023-07-09 23:59 | AUS East Coast WS | radinegara | 2023-07-09 20:07 | TZin |  | No |  |  |  |  | Aidan Flynn Kohr |  | 259.9 | 7 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.27 | WELL 55 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 105 | RIGLESS - AUSTRALIA | J.23.085384 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-07-26 | 2023-07-26 | 2023-07-26 | 2023-07-26 | 2023-07-27 23:59 | 2023-07-28 | 2023-07-27 23:59 | AUS East Coast WS | radinegara | 2023-06-30 20:08 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.14 | COM 376 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 376 | RIGLESS - AUSTRALIA | J.23.085791 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-24 | 2023-06-24 |  | 2023-06-24 | 2023-06-25 23:59 |  | 2023-06-25 23:59 | AUS East Coast WS | radinegara | 2023-06-25 15:05 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.32 | WELL 60 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 105 | RIGLESS - AUSTRALIA | J.23.085795 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-17 | 2023-09-17 |  | 2023-09-17 | 2023-09-19 23:59 |  | 2023-09-19 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:16 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.33 | WELL 61 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 105 | RIGLESS - AUSTRALIA | J.23.085387 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-20 | 2023-09-20 |  | 2023-09-20 | 2023-09-23 23:59 |  | 2023-09-23 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:16 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.34 | WELL 62 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 105 | RIGLESS - AUSTRALIA | J.23.085794 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-24 | 2023-09-24 |  | 2023-09-24 | 2023-09-26 23:59 |  | 2023-09-26 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:16 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.35 | WELL 63 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 105 | RIGLESS - AUSTRALIA | J.23.085388 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-27 | 2023-09-27 |  | 2023-09-27 | 2023-09-29 23:59 |  | 2023-09-29 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:16 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.36 | WELL 64 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 105 | RIGLESS - AUSTRALIA | J.23.085389 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-30 | 2023-09-30 |  | 2023-09-30 | 2023-10-02 23:59 |  | 2023-10-02 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:16 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.37 | WELL 65 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 105 | RIGLESS - AUSTRALIA | J.23.085390 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-10-03 | 2023-10-03 |  | 2023-10-03 | 2023-10-05 23:59 |  | 2023-10-05 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:16 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.38 | WELL 66 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 105 | RIGLESS - AUSTRALIA | J.23.085391 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-10-06 | 2023-10-06 |  | 2023-10-06 | 2023-10-08 23:59 |  | 2023-10-08 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:16 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.31 | WELL 59 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 105 | RIGLESS - AUSTRALIA | J.23.085386 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-14 | 2023-09-14 |  | 2023-09-14 | 2023-09-16 23:59 |  | 2023-09-16 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:10 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.30 | WELL 58 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 105 | RIGLESS - AUSTRALIA | J.23.085385 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-11 | 2023-09-11 |  | 2023-09-11 | 2023-09-13 23:59 |  | 2023-09-13 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:10 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.29 | WELL 57 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 105 | RIGLESS - AUSTRALIA | J.23.085383 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-08 | 2023-09-08 |  | 2023-09-08 | 2023-09-10 23:59 |  | 2023-09-10 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:10 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.28 | WELL 56 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 105 | RIGLESS - AUSTRALIA | J.23.085793 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-05 | 2023-09-05 |  | 2023-09-05 | 2023-09-07 23:59 |  | 2023-09-07 23:59 | AUS East Coast WS | radinegara | 2023-06-23 21:09 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.12 | COM 379 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 379 | RIGLESS - AUSTRALIA | J.23.085364 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-20 | 2023-06-20 |  | 2023-06-20 | 2023-06-21 23:59 |  | 2023-06-21 23:59 | AUS East Coast WS | radinegara | 2023-06-21 17:18 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.07 | COM 492 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 492 | RIGLESS - AUSTRALIA | J.23.085354 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-09 | 2023-06-09 |  | 2023-06-09 | 2023-06-11 23:59 |  | 2023-06-11 23:59 | AUS East Coast WS | radinegara | 2023-06-20 10:49 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.11 | COM 378 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 378 | RIGLESS - AUSTRALIA | J.23.085363 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-18 | 2023-06-18 |  | 2023-06-18 | 2023-06-19 23:59 |  | 2023-06-19 23:59 | AUS East Coast WS | radinegara | 2023-06-19 16:56 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.10 | COM 493 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 493 | RIGLESS - AUSTRALIA | J.23.085362 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-16 | 2023-06-16 |  | 2023-06-16 | 2023-06-17 23:59 |  | 2023-06-17 23:59 | AUS East Coast WS | radinegara | 2023-06-17 21:59 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.09 | COM 399 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 399 | RIGLESS - AUSTRALIA | J.23.085356 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-14 | 2023-06-14 |  | 2023-06-14 | 2023-06-15 23:59 |  | 2023-06-15 23:59 | AUS East Coast WS | radinegara | 2023-06-15 21:29 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.08 | RCK 284 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 284 | RIGLESS - AUSTRALIA | J.23.085355 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-06-12 | 2023-06-12 |  | 2023-06-12 | 2023-06-13 23:59 |  | 2023-06-13 23:59 | AUS East Coast WS | radinegara | 2023-06-13 20:59 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.06 | COM 494 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 494 | RIGLESS - AUSTRALIA | J.23.085357 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-07 | 2023-06-07 |  | 2023-06-07 | 2023-06-08 23:59 |  | 2023-06-08 23:59 | AUS East Coast WS | radinegara | 2023-06-08 22:56 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 87.5 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.05 | COM 401 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085353 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-29 | 2023-05-29 |  | 2023-05-29 | 2023-05-30 23:59 |  | 2023-05-30 23:59 | AUS East Coast WS | radinegara | 2023-06-04 15:11 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.01 | RCK 105 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 105 | RIGLESS - AUSTRALIA | J.23.084469 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-21 | 2023-05-21 |  | 2023-05-21 | 2023-05-23 23:59 |  | 2023-05-23 23:59 | AUS East Coast WS | radinegara | 2023-06-03 06:27 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.03 | COM 380 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 380 | RIGLESS - AUSTRALIA | J.23.084811 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-26 | 2023-05-26 |  | 2023-05-26 | 2023-05-28 23:59 |  | 2023-05-28 23:59 | AUS East Coast WS | radinegara | 2023-05-30 09:26 | HFerdjallah |  | No |  |  |  |  | Thaw Htet Zin |  | 129.95 | 7 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.04 | COM402 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 402 | RIGLESS - AUSTRALIA | J.23.084812 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-27 | 2023-05-29 |  | 2023-05-27 | 2023-05-28 23:59 |  | 2023-05-28 23:59 | AUS East Coast WS | radinegara | 2023-05-30 09:25 | HFerdjallah |  | No |  |  |  |  | Thaw Htet Zin |  | 129.95 | 7 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.04 | A.1012060.04.02 | RCK 075 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 75 | RIGLESS - AUSTRALIA | J.23.084487 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-24 | 2023-05-24 |  | 2023-05-24 | 2023-05-26 23:59 |  | 2023-05-26 23:59 | AUS East Coast WS | radinegara | 2023-05-24 17:57 | TZin |  | No |  |  |  |  | Thaw Htet Zin |  | 129.95 | 7 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.03 | A.1012060.03.11 | COM375 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.087572 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-26 01:00 | 2023-06-26 01:00 | 2023-06-25 | 2023-06-26 01:00 | 2023-07-10 00:59 | 2023-07-11 | 2023-07-10 00:59 | AUS East Coast WS | JMeyer9 | 2023-09-01 08:48 | HFerdjallah |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.22 | RCK161 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085889 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-08-06 01:00 | 2023-08-06 01:00 | 2023-08-06 | 2023-08-06 01:00 | 2023-08-09 00:59 | 2023-08-09 | 2023-08-09 00:59 | AUS East Coast WS | JMeyer9 | 2023-08-09 20:30 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.21 | RCK132 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085886 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-08-04 01:00 | 2023-08-04 01:00 | 2023-08-04 | 2023-08-04 01:00 | 2023-08-06 00:59 | 2023-08-06 | 2023-08-06 00:59 | AUS East Coast WS | JMeyer9 | 2023-08-07 19:26 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 75 | 66.7 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.19 | RCK102 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085884 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-07-26 01:00 | 2023-07-26 01:00 | 2023-07-26 | 2023-07-26 01:00 | 2023-07-28 00:59 | 2023-07-28 | 2023-07-28 00:59 | AUS East Coast WS | JMeyer9 | 2023-08-04 10:42 | HFerdjallah |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 75 | 66.7 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.20 | RCK100 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085885 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-28 01:00 | 2023-07-28 01:00 | 2023-07-28 | 2023-07-28 01:00 | 2023-08-04 00:59 | 2023-08-04 | 2023-08-04 00:59 | AUS East Coast WS | JMeyer9 | 2023-08-03 13:33 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.18 | RCK071 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085883 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-07-23 01:00 | 2023-07-23 01:00 | 2023-07-23 | 2023-07-23 01:00 | 2023-07-26 00:59 | 2023-07-26 | 2023-07-26 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-25 18:27 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 75 | 66.7 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.17 | RCK286 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085875 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-07-21 01:00 | 2023-07-21 01:00 | 2023-07-21 | 2023-07-21 01:00 | 2023-07-23 00:59 | 2023-07-23 | 2023-07-23 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-22 17:26 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 75 | 66.7 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.16 | RCK072 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085876 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-07-19 01:00 | 2023-07-19 01:00 | 2023-07-19 | 2023-07-19 01:00 | 2023-07-21 00:59 | 2023-07-21 | 2023-07-21 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-20 14:50 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 75 | 66.7 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.15 | RCK070 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085874 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-07-17 01:00 | 2023-07-17 01:00 | 2023-07-17 | 2023-07-17 01:00 | 2023-07-19 00:59 | 2023-07-19 | 2023-07-19 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-19 07:57 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 75 | 66.7 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.14 | COM422 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085877 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-15 01:00 | 2023-07-15 01:00 | 2023-07-15 | 2023-07-15 01:00 | 2023-07-17 00:59 | 2023-07-17 | 2023-07-17 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-17 13:35 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.13 | COM421 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085878 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-07-12 01:00 | 2023-07-12 01:00 | 2023-07-12 | 2023-07-12 01:00 | 2023-07-15 00:59 | 2023-07-15 | 2023-07-15 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-15 15:18 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 75 | 66.7 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.12 | COM420 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.087573 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-10 01:00 | 2023-07-10 01:00 | 2023-07-09 | 2023-07-10 01:00 | 2023-07-12 00:59 | 2023-07-12 | 2023-07-13 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-14 06:51 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.48 | Q4 WELL 19 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085915 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-12-09 01:00 | 2023-12-08 01:00 | 2023-12-07 01:00 | 2023-12-08 01:00 | 2023-12-11 00:59 | 2023-12-10 01:00 | 2023-12-12 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-05 07:33 | AKohr |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.10 | COM376 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085865 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-24 01:00 | 2023-06-24 01:00 | 2023-06-23 | 2023-06-24 01:00 | 2023-06-26 00:59 | 2023-06-26 | 2023-06-26 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-02 16:22 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.09 | COM377 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085864 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-22 01:00 | 2023-06-22 01:00 | 2023-06-22 | 2023-06-22 01:00 | 2023-06-24 00:59 | 2023-06-24 | 2023-06-24 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-02 16:17 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.08 | COM379 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085863 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-20 01:00 | 2023-06-20 01:00 | 2023-06-20 | 2023-06-20 01:00 | 2023-06-22 00:59 | 2023-06-22 | 2023-06-22 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-02 16:11 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.07 | COM378 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085854 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-06-18 01:00 | 2023-06-18 01:00 | 2023-06-18 | 2023-06-18 01:00 | 2023-06-20 00:59 | 2023-06-20 | 2023-06-19 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-02 15:53 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 75 | 66.7 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.06 | COM493 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085856 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-16 01:00 | 2023-06-16 01:00 | 2023-06-16 | 2023-06-16 01:00 | 2023-06-18 00:59 | 2023-06-19 | 2023-06-18 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-02 15:40 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.05 | COM399 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085853 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-14 01:00 | 2023-06-14 01:00 | 2023-06-13 | 2023-06-14 01:00 | 2023-06-16 00:59 | 2023-06-16 | 2023-06-16 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-02 15:32 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.04 | RCK284 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085852 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-06-13 01:00 | 2023-06-13 01:00 | 2023-06-13 | 2023-06-13 01:00 | 2023-06-14 00:59 | 2023-06-16 | 2023-06-16 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-02 15:22 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 75 | 66.7 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.03 | COM492 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085851 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-10 01:00 | 2023-06-10 01:00 | 2023-06-10 | 2023-06-10 01:00 | 2023-06-13 00:59 | 2023-06-15 | 2023-06-13 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-02 14:34 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.24 | Q3 WELL 3 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085891 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-02 01:00 | 2023-09-02 01:00 | 2023-09-01 | 2023-09-02 01:00 | 2023-09-05 00:59 | 2023-09-04 | 2023-09-05 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:29 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.25 | Q3 WELL 4 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085892 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-05 01:00 | 2023-09-05 01:00 | 2023-09-04 | 2023-09-05 01:00 | 2023-09-08 00:59 | 2023-09-07 | 2023-09-08 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:29 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.26 | Q3 WELL 5 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085893 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-08 01:00 | 2023-09-08 01:00 | 2023-09-07 | 2023-09-08 01:00 | 2023-09-11 00:59 | 2023-09-10 | 2023-09-11 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:13 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.27 | Q3 WELL 6 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085894 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-11 01:00 | 2023-09-11 01:00 | 2023-09-10 | 2023-09-11 01:00 | 2023-09-14 00:59 | 2023-09-13 | 2023-09-14 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:12 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.28 | Q3 WELL 7 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085901 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-15 01:00 | 2023-09-14 01:00 | 2023-09-13 | 2023-09-14 01:00 | 2023-09-17 00:59 | 2023-09-16 | 2023-09-18 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:12 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.29 | Q3 WELL 8 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085898 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-18 01:00 | 2023-09-17 01:00 | 2023-09-16 | 2023-09-17 01:00 | 2023-09-20 00:59 | 2023-09-19 | 2023-09-21 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:11 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.30 | Q4 WELL 1 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085899 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-27 01:00 | 2023-09-26 01:00 | 2023-09-25 | 2023-09-26 01:00 | 2023-09-29 00:59 | 2023-09-28 01:00 | 2023-09-30 01:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:11 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.31 | Q4 WELL 2 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085900 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-30 01:00 | 2023-09-29 01:00 | 2023-09-28 01:00 | 2023-09-29 01:00 | 2023-10-02 00:59 | 2023-10-01 01:00 | 2023-10-03 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:11 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.32 | Q4 WELL 3 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.087575 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-03 01:00 | 2023-10-02 01:00 | 2023-10-01 01:00 | 2023-10-02 01:00 | 2023-10-05 00:59 | 2023-10-04 01:00 | 2023-10-06 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:10 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.33 | Q4 WELL 4 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085902 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-06 01:00 | 2023-10-05 01:00 | 2023-10-04 01:00 | 2023-10-05 01:00 | 2023-10-08 00:59 | 2023-10-07 01:00 | 2023-10-09 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:10 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.34 | Q4 WELL 5 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085903 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-09 01:00 | 2023-10-08 01:00 | 2023-10-07 01:00 | 2023-10-08 01:00 | 2023-10-11 00:59 | 2023-10-10 01:00 | 2023-10-12 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:10 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.35 | Q4 WELL 6 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085904 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-12 01:00 | 2023-10-11 01:00 | 2023-10-10 01:00 | 2023-10-11 01:00 | 2023-10-14 00:59 | 2023-10-13 01:00 | 2023-10-15 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:09 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.36 | Q4 WELL 7 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.087576 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-15 01:00 | 2023-10-14 01:00 | 2023-10-13 01:00 | 2023-10-14 01:00 | 2023-10-17 00:59 | 2023-10-16 01:00 | 2023-10-18 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:09 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.37 | Q4 WELL 8 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085905 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-18 01:00 | 2023-10-17 01:00 | 2023-10-16 01:00 | 2023-10-17 01:00 | 2023-10-20 00:59 | 2023-10-19 01:00 | 2023-10-21 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:09 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.38 | Q4 WELL 9 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.087577 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-28 01:00 | 2023-10-27 01:00 | 2023-10-26 01:00 | 2023-10-27 01:00 | 2023-10-30 00:59 | 2023-10-29 01:00 | 2023-10-31 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:08 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.39 | Q4 WELL 10 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.087578 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-31 01:00 | 2023-10-30 01:00 | 2023-10-29 01:00 | 2023-10-30 01:00 | 2023-11-02 00:59 | 2023-11-01 01:00 | 2023-11-03 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:07 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.40 | Q4 WELL 11 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085906 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-11-03 01:00 | 2023-11-02 01:00 | 2023-11-01 01:00 | 2023-11-02 01:00 | 2023-11-05 00:59 | 2023-11-04 01:00 | 2023-11-06 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:05 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.41 | Q4 WELL 12 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085907 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-11-06 01:00 | 2023-11-05 01:00 | 2023-11-04 01:00 | 2023-11-05 01:00 | 2023-11-08 00:59 | 2023-11-07 01:00 | 2023-11-09 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:05 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.42 | Q4 WELL 13 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085908 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-11-09 01:00 | 2023-11-08 01:00 | 2023-11-07 01:00 | 2023-11-08 01:00 | 2023-11-11 00:59 | 2023-11-10 01:00 | 2023-11-12 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:04 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.43 | Q4 WELL 14 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085909 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-11-12 01:00 | 2023-11-11 01:00 | 2023-11-10 01:00 | 2023-11-11 01:00 | 2023-11-14 00:59 | 2023-11-13 01:00 | 2023-11-15 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:03 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.44 | Q4 WELL 15 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085912 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-11-15 01:00 | 2023-11-14 01:00 | 2023-11-13 01:00 | 2023-11-14 01:00 | 2023-11-17 00:59 | 2023-11-16 01:00 | 2023-11-18 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:03 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.45 | Q4 WELL 16 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085910 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-11-18 01:00 | 2023-11-17 01:00 | 2023-11-16 01:00 | 2023-11-17 01:00 | 2023-11-20 00:59 | 2023-11-19 01:00 | 2023-11-21 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:02 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.46 | Q4 WELL 17 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085911 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-11-27 01:00 | 2023-11-26 01:00 | 2023-11-25 01:00 | 2023-11-26 01:00 | 2023-11-29 00:59 | 2023-11-28 01:00 | 2023-11-30 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:02 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.47 | Q4 WELL 18 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085913 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-11-30 01:00 | 2023-11-29 01:00 | 2023-11-28 01:00 | 2023-11-29 01:00 | 2023-12-02 00:59 | 2023-12-01 01:00 | 2023-12-03 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:02 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.49 | Q4 WELL 20 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085916 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-12-06 01:00 | 2023-12-05 01:00 | 2023-12-04 01:00 | 2023-12-05 01:00 | 2023-12-08 00:59 | 2023-12-07 01:00 | 2023-12-09 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 15:01 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.50 | Q4 WELL 21 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085917 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-12-09 01:00 | 2023-12-08 01:00 | 2023-12-07 01:00 | 2023-12-08 01:00 | 2023-12-11 00:59 | 2023-12-10 01:00 | 2023-12-12 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 14:58 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.51 | Q4 WELL 22 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.087579 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-12-12 01:00 | 2023-12-11 01:00 | 2023-12-10 01:00 | 2023-12-11 01:00 | 2023-12-14 00:59 | 2023-12-13 01:00 | 2023-12-15 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 14:58 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.52 | Q4 WELL 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085918 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-12-15 01:00 | 2023-12-14 01:00 | 2023-12-13 01:00 | 2023-12-14 01:00 | 2023-12-17 00:59 | 2023-12-16 01:00 | 2023-12-18 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 14:57 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.53 | Q4 WELL 24 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085919 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-12-18 01:00 | 2023-12-17 01:00 | 2023-12-16 01:00 | 2023-12-17 01:00 | 2023-12-20 00:59 | 2023-12-19 01:00 | 2023-12-21 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 14:55 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.23 | Q3 WELL 2 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.087574 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-07-26 01:00 | 2023-07-26 01:00 | 2023-07-26 | 2023-07-26 01:00 | 2023-07-28 00:59 | 2023-07-28 | 2023-07-28 00:59 | AUS East Coast WS | JMeyer9 | 2023-07-01 14:20 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.02 | COM494 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.23.085845 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-07 01:00 | 2023-06-07 01:00 |  | 2023-06-07 01:00 | 2023-06-09 00:59 |  | 2023-06-09 00:59 | AUS East Coast WS | JMeyer9 | 2023-06-09 00:10 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.03 | A.1012060.03.01 | COM401 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 401 | RIGLESS - AUSTRALIA | J.25.000147 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-29 01:00 | 2023-05-31 01:00 |  | 2023-05-29 01:00 | 2023-05-31 00:59 |  | 2023-06-02 00:59 | AUS East Coast WS | JMeyer9 | 2023-06-04 15:12 | HFerdjallah |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.02 | A.1012060.02.96 | Well 6 - July 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010416 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-11-07 | 2025-11-07 |  | 2025-11-07 | 2025-11-09 23:59 |  | 2025-11-09 23:59 | AUS East Coast WS | radinegara | 2024-10-25 15:05 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.94 | Well 4 - July 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010414 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-11-01 | 2025-11-01 |  | 2025-11-01 | 2025-11-03 23:59 |  | 2025-11-03 23:59 | AUS East Coast WS | radinegara | 2024-10-25 15:05 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.93 | Well 3 - July 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010413 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-10-29 | 2025-10-29 |  | 2025-10-29 | 2025-10-31 23:59 |  | 2025-10-31 23:59 | AUS East Coast WS | radinegara | 2024-10-25 15:05 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.92 | Well 2 - July 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010412 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-10-26 | 2025-10-26 |  | 2025-10-26 | 2025-10-28 23:59 |  | 2025-10-28 23:59 | AUS East Coast WS | radinegara | 2024-10-25 15:05 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.91 | Well 1 - July 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010411 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-10-23 | 2025-10-23 |  | 2025-10-23 | 2025-10-25 23:59 |  | 2025-10-25 23:59 | AUS East Coast WS | radinegara | 2024-10-25 15:04 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.90 | Well 10 - June 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010410 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-10-20 | 2025-10-20 |  | 2025-10-20 | 2025-10-22 23:59 |  | 2025-10-22 23:59 | AUS East Coast WS | radinegara | 2024-10-25 15:04 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.89 | Well 9 - June 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010409 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-10-17 | 2025-10-17 |  | 2025-10-17 | 2025-10-19 23:59 |  | 2025-10-19 23:59 | AUS East Coast WS | radinegara | 2024-10-25 15:04 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.98 | Well 8 - July 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010418 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-11-13 | 2025-11-13 |  | 2025-11-13 | 2025-11-15 23:59 |  | 2025-11-15 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:28 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.95 | Well 5 - July 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010415 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-11-04 | 2025-11-04 |  | 2025-11-04 | 2025-11-06 23:59 |  | 2025-11-06 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:28 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.97 | Well 7 - July 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010417 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-11-10 | 2025-11-10 |  | 2025-11-10 | 2025-11-12 23:59 |  | 2025-11-12 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:28 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.99 | Well 9 - July 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010419 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-11-16 | 2025-11-16 |  | 2025-11-16 | 2025-11-18 23:59 |  | 2025-11-18 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:28 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.100 | Well 10 - July 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010420 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-11-19 | 2025-11-19 |  | 2025-11-19 | 2025-11-21 23:59 |  | 2025-11-21 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:28 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.88 | Well 8 June 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010408 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-10-14 | 2025-10-14 |  | 2025-10-14 | 2025-10-16 23:59 |  | 2025-10-16 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:27 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.87 | Well 7 - June 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010407 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-10-11 | 2025-10-11 |  | 2025-10-11 | 2025-10-13 23:59 |  | 2025-10-13 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:27 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.86 | Well 6 - June 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010406 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-10-08 | 2025-10-08 |  | 2025-10-08 | 2025-10-10 23:59 |  | 2025-10-10 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:27 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.85 | Well 5 - June 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010405 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-10-05 | 2025-10-05 |  | 2025-10-05 | 2025-10-07 23:59 |  | 2025-10-07 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:27 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.84 | Well 4 - June 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010404 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-10-02 | 2025-10-02 |  | 2025-10-02 | 2025-10-04 23:59 |  | 2025-10-04 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:27 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.83 | Well 3 - June 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010403 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-09-29 | 2025-09-29 |  | 2025-09-29 | 2025-10-01 23:59 |  | 2025-10-01 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:27 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.82 | Well 2 - June 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010402 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-09-26 | 2025-09-26 |  | 2025-09-26 | 2025-09-28 23:59 |  | 2025-09-28 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:27 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.81 | Well 1 - June 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010401 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-09-23 | 2025-09-23 |  | 2025-09-23 | 2025-09-25 23:59 |  | 2025-09-25 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:27 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.80 | Well 10 - May 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010400 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-09-19 | 2025-09-19 |  | 2025-09-19 | 2025-09-21 23:59 |  | 2025-09-21 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:27 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.79 | Well 9 - May 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010399 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-09-16 | 2025-09-16 |  | 2025-09-16 | 2025-09-18 23:59 |  | 2025-09-18 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:27 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.78 | Well 8 - May 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010398 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-09-13 | 2025-09-13 |  | 2025-09-13 | 2025-09-15 23:59 |  | 2025-09-15 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:27 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.77 | Well 7 - May 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010397 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-09-10 | 2025-09-10 |  | 2025-09-10 | 2025-09-12 23:59 |  | 2025-09-12 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:27 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.76 | Well 6 - May 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010396 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-09-07 | 2025-09-07 |  | 2025-09-07 | 2025-09-09 23:59 |  | 2025-09-09 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:27 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.75 | Well 5 - May 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010395 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-09-04 | 2025-09-04 |  | 2025-09-04 | 2025-09-06 23:59 |  | 2025-09-06 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:27 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.74 | Well 4 - May 2023 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010394 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-09-01 | 2025-09-01 |  | 2025-09-01 | 2025-09-03 23:59 |  | 2025-09-03 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:27 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.70 | Well 10 - April 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010390 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-08-29 | 2025-08-29 |  | 2025-08-29 | 2025-08-31 23:59 |  | 2025-08-31 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:27 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.73 | Well 3 - May 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010393 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-08-22 | 2025-08-22 |  | 2025-08-22 | 2025-08-24 23:59 |  | 2025-08-24 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:26 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.72 | Well 2 - May 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010392 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-08-19 | 2025-08-19 |  | 2025-08-19 | 2025-08-21 23:59 |  | 2025-08-21 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:26 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.71 | Well 1 - May 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010391 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-08-16 | 2025-08-16 |  | 2025-08-16 | 2025-08-18 23:59 |  | 2025-08-18 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:26 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.68 | Well 8 - April 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010388 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-08-13 | 2025-08-13 |  | 2025-08-13 | 2025-08-15 23:59 |  | 2025-08-15 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:26 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.67 | Well 7 - April 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010387 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-08-10 | 2025-08-10 |  | 2025-08-10 | 2025-08-12 23:59 |  | 2025-08-12 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:26 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.69 | Well 9 - April 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010389 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-08-07 | 2025-08-07 |  | 2025-08-07 | 2025-08-09 23:59 |  | 2025-08-09 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:26 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.66 | Well 6 - April 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010386 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-06 23:59 |  | 2025-08-06 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:26 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.63 | Well 3 - April 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010383 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-08-01 | 2025-08-01 |  | 2025-08-01 | 2025-08-03 23:59 |  | 2025-08-03 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:26 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.62 | Well 2 - April 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010382 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-07-29 | 2025-07-29 |  | 2025-07-29 | 2025-07-31 23:59 |  | 2025-07-31 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:24 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.65 | Well 5 - April 2023 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010385 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-07-23 | 2025-07-23 |  | 2025-07-23 | 2025-07-25 23:59 |  | 2025-07-25 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:24 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.64 | Well 4 - April 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010384 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-07-20 | 2025-07-20 |  | 2025-07-20 | 2025-07-22 23:59 |  | 2025-07-22 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:24 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.61 | Well 1 - April 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010381 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-07-17 | 2025-07-17 |  | 2025-07-17 | 2025-07-19 23:59 |  | 2025-07-19 23:59 | AUS East Coast WS | radinegara | 2024-10-25 13:24 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.50 | Well#10 in Qct | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010360 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-07-14 | 2025-07-14 |  | 2025-07-14 | 2025-07-16 23:59 |  | 2025-07-16 23:59 | AUS East Coast WS | YHou5 | 2024-10-15 17:27 | CNevarez2 |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.49 | Well#9 in Qct | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010359 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-07-11 | 2025-07-11 |  | 2025-07-11 | 2025-07-13 23:59 |  | 2025-07-13 23:59 | AUS East Coast WS | YHou5 | 2024-10-15 17:27 | CNevarez2 |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.48 | Well#8 in Qct | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010358 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-07-08 | 2025-07-08 |  | 2025-07-08 | 2025-07-10 23:59 |  | 2025-07-10 23:59 | AUS East Coast WS | YHou5 | 2024-10-15 17:27 | CNevarez2 |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.47 | Well#7 in Qct | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010357 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-07-05 | 2025-07-05 |  | 2025-07-05 | 2025-07-07 23:59 |  | 2025-07-07 23:59 | AUS East Coast WS | YHou5 | 2024-10-15 17:26 | CNevarez2 |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.46 | Well#6 in Qct | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010356 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-07-02 | 2025-07-02 |  | 2025-07-02 | 2025-07-04 23:59 |  | 2025-07-04 23:59 | AUS East Coast WS | YHou5 | 2024-10-15 17:26 | CNevarez2 |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.45 | Well#5 in Qct | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010355 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-06-29 | 2025-06-29 |  | 2025-06-29 | 2025-07-01 23:59 |  | 2025-07-01 23:59 | AUS East Coast WS | YHou5 | 2024-10-15 17:26 | CNevarez2 |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.44 | Well#4 in Qct | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010354 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-06-22 | 2025-06-22 |  | 2025-06-22 | 2025-06-24 23:59 |  | 2025-06-24 23:59 | AUS East Coast WS | YHou5 | 2024-10-15 17:26 | CNevarez2 |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 7 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.43 | COM494 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010353 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2025-06-19 | 2025-06-19 |  | 2025-06-19 | 2025-06-21 23:59 |  | 2025-06-21 23:59 | AUS East Coast WS | YHou5 | 2024-10-15 17:26 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 59.4 | 8.3 | 0 | 0 | 26.3 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.42 | COM380 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010352 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2025-06-16 | 2025-06-16 |  | 2025-06-16 | 2025-06-18 23:59 |  | 2025-06-18 23:59 | AUS East Coast WS | YHou5 | 2024-10-15 17:26 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 59.4 | 8.3 | 0 | 0 | 26.3 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.41 | COM402 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010351 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2025-06-13 | 2025-06-13 |  | 2025-06-13 | 2025-06-15 22:59 |  | 2025-06-15 23:59 | AUS East Coast WS | YHou5 | 2024-10-15 17:26 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 59.4 | 8.3 | 0 | 0 | 26.3 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.30 | COM380 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010350 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2025-06-06 | 2025-06-06 |  | 2025-06-06 | 2025-06-08 22:59 |  | 2025-06-08 22:59 | AUS East Coast WS | YHou5 | 2024-10-15 17:17 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 46.9 | 41.7 | 0 | 0 | 31.3 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.29 | RCK075 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010349 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2025-06-03 | 2025-06-03 |  | 2025-06-03 | 2025-06-05 23:59 |  | 2025-06-05 23:59 | AUS East Coast WS | YHou5 | 2024-10-15 17:17 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 81.3 | 50 | 0 | 0 | 47.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.28 | RCK105 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010348 | RPS | FRAC-PROP | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2025-05-31 | 2025-05-31 |  | 2025-05-31 | 2025-06-02 23:59 |  | 2025-06-02 23:59 | AUS East Coast WS | YHou5 | 2024-10-15 17:17 | CNevarez2 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 81.3 | 50 | 0 | 0 | 47.5 |  | 1 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.26 | RCK 259 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 259 | RIGLESS - AUSTRALIA | J.23.010346 | RPS | FRAC-PROP | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-11 | 2023-05-11 |  | 2023-05-11 | 2023-05-15 23:59 |  | 2023-05-15 23:59 | AUS East Coast WS | YHou5 | 2023-11-03 19:10 | JMeyer9 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 5101.42 | 7 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.103 | Test - Archetype | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | PEAT 45 | RIGLESS - AUSTRALIA | J.23.105155 | RPS | STM-MPUMP | InComplete | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-07-31 | 2023-08-01 |  | 2023-08-01 | 2023-08-14 23:59 |  | 2023-08-13 23:59 | AUS East Coast WS | HFerdjallah | 2023-06-25 15:55 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 6 |  |  |  | 62.5 | 33.3 | 100 | 25 | 50 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.27 | RCK101 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 101 | RIGLESS - AUSTRALIA | J.23.010347 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-16 | 2023-05-16 |  | 2023-05-16 | 2023-05-21 23:59 |  | 2023-05-21 23:59 | AUS East Coast WS | YHou5 | 2023-06-03 06:30 | AKohr |  | No |  |  |  |  | Thaw Htet Zin |  | 259.9 | 7 |  |  |  | 87.5 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.23 | RCK 195 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 195 | RIGLESS - AUSTRALIA | J.23.010343 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-02 | 2023-05-02 |  | 2023-05-02 | 2023-05-04 23:59 |  | 2023-05-04 23:59 | AUS East Coast WS | YHou5 | 2023-06-03 06:27 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 87.5 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.25 | RCK 260 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 260 | RIGLESS - AUSTRALIA | J.23.010345 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-08 | 2023-05-08 |  | 2023-05-08 | 2023-05-10 23:59 |  | 2023-05-10 23:59 | AUS East Coast WS | YHou5 | 2023-05-11 06:55 | TZin |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.24 | RCK 228 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 228 | RIGLESS - AUSTRALIA | J.23.010344 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-05 | 2023-05-05 |  | 2023-05-05 | 2023-05-07 23:59 |  | 2023-05-07 23:59 | AUS East Coast WS | YHou5 | 2023-05-07 12:08 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 259.9 | 7 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.53 | RCK 290 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 290 | RIGLESS - AUSTRALIA | J.22.116606 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-26 | 2023-04-26 |  | 2023-04-26 | 2023-05-01 23:59 |  | 2023-05-01 23:59 | AUS East Coast WS | radinegara | 2023-05-07 12:02 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 259.9 | 7 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.52 | RCK 231 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 231 | RIGLESS - AUSTRALIA | J.22.116605 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-17 | 2023-04-17 |  | 2023-04-17 | 2023-04-19 23:59 |  | 2023-04-19 23:59 | AUS East Coast WS | radinegara | 2023-05-07 11:55 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.38 | RCK 288 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 288 | RIGLESS - AUSTRALIA | J.22.116580 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-14 | 2023-04-14 |  | 2023-04-14 | 2023-04-16 23:59 |  | 2023-04-16 23:59 | AUS East Coast WS | YHou5 | 2023-05-07 11:52 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.51 | RCK 263 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 263 | RIGLESS - AUSTRALIA | J.22.116603 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-04-11 | 2023-04-11 |  | 2023-04-11 | 2023-04-13 23:59 |  | 2023-04-13 23:59 | AUS East Coast WS | radinegara | 2023-05-07 11:51 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 93.8 | 66.7 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.22 | RCK 115 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 115 | RIGLESS - AUSTRALIA | J.23.010342 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-04-01 | 2023-04-01 |  | 2023-04-01 | 2023-04-04 23:59 |  | 2023-04-05 23:59 | AUS East Coast WS | YHou5 | 2023-04-26 12:32 | AKohr |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 93.8 | 66.7 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.40 | RCK 262 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 262 | RIGLESS - AUSTRALIA | J.22.116582 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-04-09 | 2023-04-08 |  | 2023-04-08 | 2023-04-10 23:59 |  | 2023-04-09 23:59 | AUS East Coast WS | YHou5 | 2023-04-22 15:14 | TZin |  | No |  |  |  |  | Ramadhani Adi Negara |  | 129.95 | 7 |  |  |  | 93.8 | 66.7 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.39 | RCK 261 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 261 | RIGLESS - AUSTRALIA | J.22.116581 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-04-03 | 2023-04-04 |  | 2023-04-04 | 2023-04-07 23:59 |  | 2023-04-05 23:59 | AUS East Coast WS | YHou5 | 2023-04-17 12:51 | TZin |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 93.8 | 66.7 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.54 | LUK018 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | LUCKY GULLY 18 | RIGLESS - AUSTRALIA | J.22.116607 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-03-28 | 2023-03-29 |  | 2023-03-29 | 2023-03-31 23:59 |  | 2023-03-30 23:59 | AUS East Coast WS | radinegara | 2023-04-06 08:27 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 93.8 | 66.7 | 0 | 75 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.58 | RCK 226 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 226 | RIGLESS - AUSTRALIA | J.22.116611 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-16 | 2023-03-16 |  | 2023-03-16 | 2023-03-21 23:59 |  | 2023-03-21 23:59 | AUS East Coast WS | radinegara | 2023-04-03 09:48 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 87.5 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.102 | Peat 45 DFIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | PEAT 45 | RIGLESS - AUSTRALIA | J.23.038463 | RPS | STM-MPUMP | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-03-16 | 2023-03-17 |  | 2023-03-17 | 2023-03-30 23:59 |  | 2023-03-29 23:59 | AUS East Coast WS | TZin | 2023-04-03 09:48 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 149585.24 | 6 |  |  |  | 93.8 | 66.7 | 100 | 75 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.21 | LUK 017 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | LUCKY GULLY 17 | RIGLESS - AUSTRALIA | J.23.010341 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-03-25 | 2023-03-25 |  | 2023-03-25 | 2023-03-28 23:59 |  | 2023-03-28 23:59 | AUS East Coast WS | YHou5 | 2023-03-30 09:43 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 93.8 | 66.7 | 0 | 75 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.60 | LUK 032 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | LUCKY GULLY 32 | RIGLESS - AUSTRALIA | J.22.116613 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-22 | 2023-03-21 |  | 2023-03-22 | 2023-03-24 23:59 |  | 2023-03-24 23:59 | AUS East Coast WS | radinegara | 2023-03-30 09:38 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 129.95 | 7 |  |  |  | 87.5 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.57 | RCK 258 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 258 | RIGLESS - AUSTRALIA | J.22.116610 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-02-27 | 2023-03-02 |  | 2023-03-02 | 2023-03-04 23:59 |  | 2023-03-02 23:59 | AUS East Coast WS | radinegara | 2023-03-26 11:41 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 93.8 | 50 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.56 | RCK 194 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 194 | RIGLESS - AUSTRALIA | J.22.116609 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-02-26 | 2023-02-27 |  | 2023-02-27 | 2023-03-01 23:59 |  | 2023-03-01 23:59 | AUS East Coast WS | radinegara | 2023-03-26 11:39 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 93.8 | 50 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.59 | LUK 047 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | LUCKY GULLY 47 | RIGLESS - AUSTRALIA | J.22.116612 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-12 | 2023-03-12 |  | 2023-03-12 | 2023-03-15 23:59 |  | 2023-03-15 23:59 | AUS East Coast WS | radinegara | 2023-03-26 11:32 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 65878.2 | 7 |  |  |  | 87.5 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.101 | RCK227 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 227 | RIGLESS - AUSTRALIA | J.23.031546 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-17 | 2023-02-17 |  | 2023-02-19 | 2023-02-24 23:59 |  | 2023-02-21 23:59 | AUS East Coast WS | AKohr | 2023-03-01 23:38 | radinegara |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 9 |  |  |  | 87.5 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.55 | RCK 193 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 193 | RIGLESS - AUSTRALIA | J.22.116608 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-22 | 2023-02-24 |  | 2023-02-24 | 2023-02-27 23:59 |  | 2023-02-25 23:59 | AUS East Coast WS | radinegara | 2023-02-28 15:34 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 87.5 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.37 | LUK016 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | LUCKY GULLY 16 | RIGLESS - AUSTRALIA | J.22.116579 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-17 01:00 | 2022-11-18 01:00 |  | 2022-11-21 01:00 | 2022-11-26 00:59 |  | 2022-11-22 00:59 | AUS East Coast WS | YHou5 | 2022-12-28 17:31 | TZin |  | No |  |  |  |  | Aidan Flynn Kohr |  | 324781.05 | 7 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.35 | CNS 284 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI SOUTH 284 | RIGLESS - AUSTRALIA | J.22.116577 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-11 01:00 | 2022-11-11 |  | 2022-11-11 01:00 | 2022-11-16 00:59 |  | 2022-11-16 00:59 | AUS East Coast WS | YHou5 | 2022-12-09 10:53 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.33 | CNS 286 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI SOUTH 286 | RIGLESS - AUSTRALIA | J.22.116575 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-22 | 2022-10-24 |  | 2022-10-24 | 2022-11-04 00:59 |  | 2022-11-03 23:59 | AUS East Coast WS | YHou5 | 2022-11-19 16:03 | TZin |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.34 | CNS 285 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI SOUTH 285 | RIGLESS - AUSTRALIA | J.22.116576 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-04 | 2022-11-04 |  | 2022-11-04 | 2022-11-07 23:00 |  | 2022-11-07 22:00 | AUS East Coast WS | YHou5 | 2022-11-18 22:56 | TZin |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.36 | CON 477 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 477 | RIGLESS - AUSTRALIA | J.22.116578 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-10 | 2022-11-08 |  | 2022-11-08 | 2022-11-10 23:59 |  | 2022-11-12 23:59 | AUS East Coast WS | YHou5 | 2022-11-18 18:34 | TZin |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 7 |  |  |  | 87.5 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.12 | CON 477 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 477 | RIGLESS - AUSTRALIA | J.21.111255 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-24 11:00 | 2021-04-07 23:00 |  | 2021-05-24 | 2021-05-26 23:59 |  | 2021-05-27 10:59 | AUS East Coast WS | TGunadi | 2022-11-11 17:31 | TZin |  | No |  |  |  |  | Ali Tanha |  | 187736.32 | 4 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.32 | CNN 375 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri North 375 | RIGLESS - AUSTRALIA | J.22.116574 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-10-15 | 2022-10-15 |  | 2022-10-15 | 2022-10-17 23:59 |  | 2022-10-17 23:59 | AUS East Coast WS | YHou5 | 2022-10-28 13:14 | HFerdjallah |  | No |  |  |  |  | Aidan Flynn Kohr |  | 75750.58 | 7 |  |  |  | 93.8 | 66.7 | 0 | 50 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.31 | CNN 335 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri North 335 | RIGLESS - AUSTRALIA | J.22.116573 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-10 | 2022-10-09 |  | 2022-10-10 | 2022-10-13 23:59 |  | 2022-10-13 23:59 | AUS East Coast WS | YHou5 | 2022-10-28 12:48 | HFerdjallah |  | Yes |  |  |  |  | Aidan Flynn Kohr |  | 184532.14 | 7 |  |  |  | 87.5 | 66.7 | 0 | 62.5 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.20 | Well #5 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.21.111265 | RPS | FRAC-PROP | InComplete | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2021-12-16 |  | 2021-12-16 | 2021-12-19 23:59 |  |  | AUS East Coast WS | YHou5 | 2022-10-14 22:30 | FDPSystemUser |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 5 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.19 | Well #4 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.21.111264 | RPS | FRAC-PROP | InComplete | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2021-12-13 |  | 2021-12-13 | 2021-12-16 23:59 |  |  | AUS East Coast WS | YHou5 | 2022-10-14 22:30 | FDPSystemUser |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 5 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.18 | Well #3 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.21.111263 | RPS | FRAC-PROP | InComplete | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2021-12-10 |  | 2021-12-10 | 2021-12-13 23:59 |  |  | AUS East Coast WS | YHou5 | 2022-10-14 22:30 | FDPSystemUser |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 5 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.17 | Well #2 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.21.111262 | RPS | FRAC-PROP | InComplete | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2021-12-06 |  | 2021-12-06 | 2021-12-09 23:59 |  |  | AUS East Coast WS | YHou5 | 2022-10-14 22:30 | FDPSystemUser |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 5 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.16 | Well #1 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.21.111261 | RPS | FRAC-PROP | InComplete | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2021-12-02 |  | 2021-12-02 | 2021-12-05 23:59 |  |  | AUS East Coast WS | YHou5 | 2022-10-14 22:30 | FDPSystemUser |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 5 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.15 | non operational activity | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.21.111260 | RPS | STM-PERS | Low | Confirmed | Design - CEC |  | Not Required | Not Required | In Progress |  | 2021-03-01 |  | 2021-03-01 | 2021-12-31 23:59 |  |  | AUS East Coast WS | ATanha | 2022-10-14 22:30 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 0 | 0 |  |  |  | 81.3 | 66.7 | 100 | 50 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.14 | none operation | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.21.111259 | RPS | STM-PERS | InComplete | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-02-23 |  | 2021-02-23 | 2021-02-28 23:59 |  |  | AUS East Coast WS | ATanha | 2022-10-14 22:30 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 0 | 0 |  |  |  | 50 | 33.3 | 100 | 50 | 50 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.07 | CON 448 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI 448 | RIGLESS - AUSTRALIA | J.21.111258 | RPS | FRAC-PROP | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-05-15 11:00 | 2021-04-04 |  | 2021-05-15 | 2021-05-17 23:59 |  | 2021-05-18 10:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:29 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 187736.32 | 6 |  |  |  | 84.4 | 8.3 | 0 | 25 | 41.3 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.13 | CON 463 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 463 | RIGLESS - AUSTRALIA | J.21.111254 | RPS | FRAC-PROP | InComplete | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress | 2021-03-26 11:00 | 2021-03-26 |  | 2021-03-26 | 2021-03-28 23:59 |  | 2021-03-29 10:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:29 | FDPSystemUser |  | No |  |  |  |  | Trianto Adiputro Gunadi |  | 0 | 6 |  |  |  | 53.1 | 8.3 | 0 | 0 | 23.8 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.03 | CON 430 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 430 | RIGLESS - AUSTRALIA | J.21.111253 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-14 11:00 | 2021-03-10 |  | 2021-03-14 | 2021-04-23 23:59 |  | 2021-04-17 10:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:29 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 187736.32 | 6 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.04 | CON431 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 431 | RIGLESS - AUSTRALIA | J.21.111249 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-24 11:00 | 2021-03-20 |  | 2021-04-24 | 2021-04-26 23:59 |  | 2021-04-27 10:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:29 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 187736.32 | 6 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.01 | Condabri North 368 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI NORTH 368 | RIGLESS - AUSTRALIA | J.21.111248 | RPS | FRAC-PROP | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-03-03 11:00 | 2021-03-03 |  | 2021-03-03 | 2021-03-08 23:59 |  | 2021-03-09 10:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:28 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 119987.38 | 6 |  |  |  | 84.4 | 8.3 | 0 | 25 | 41.3 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.11 | CON 475 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 475 | RIGLESS - AUSTRALIA | J.21.111245 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2021-05-10 11:00 | 2021-04-11 23:00 |  | 2021-05-10 | 2021-05-12 22:59 |  | 2021-05-13 10:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:28 | FDPSystemUser |  | No |  |  |  |  | Trianto Adiputro Gunadi |  | 187736.32 | 5 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.10 | CON 474 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 474 | RIGLESS - AUSTRALIA | J.21.111244 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-08 11:00 | 2021-04-09 23:00 |  | 2021-05-08 | 2021-05-10 23:59 |  | 2021-05-11 10:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:28 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 187736.32 | 5 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.06 | CON 471 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 471 | RIGLESS - AUSTRALIA | J.21.111243 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-11 11:00 | 2021-03-06 |  | 2021-03-11 | 2021-03-13 23:59 |  | 2021-03-14 10:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:28 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 187736.32 | 6 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.09 | CON 463 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 463 | RIGLESS - AUSTRALIA | J.21.111240 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-06 11:00 | 2021-04-07 23:00 |  | 2021-05-06 | 2021-05-08 23:59 |  | 2021-05-09 10:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:27 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 187736.32 | 6 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.02 | CNN 370 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri North 370 | RIGLESS - AUSTRALIA | J.21.111238 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-08 11:00 | 2021-03-08 |  | 2021-03-08 | 2021-03-11 23:59 |  | 2021-03-12 10:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:27 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 119987.38 | 6 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.05 | CON 432 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 432 | RIGLESS - AUSTRALIA | J.21.111237 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-27 11:00 | 2021-03-31 |  | 2021-04-27 | 2021-04-29 23:59 |  | 2021-04-30 10:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:27 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 187736.32 | 9 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.02 | A.1012060.02.08 | CON 476 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 476 | RIGLESS - AUSTRALIA | J.21.111233 | RPS | FRAC-PROP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-02 11:00 | 2021-04-05 23:00 |  | 2021-05-02 | 2021-05-04 23:59 |  | 2021-05-05 10:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:27 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 187736.32 | 5 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1012060 | O.1012060.01 | A.1012060.01.24 | RCK105 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 105 | RIGLESS - AUSTRALIA | J.23.010370 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-05-21 01:00 | 2023-05-21 01:00 |  | 2023-05-21 01:00 | 2023-05-23 23:59 |  | 2023-05-23 23:59 | AUS East Coast WS | JMeyer9 | 2023-06-05 14:50 | AKohr |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.23 | RCK101 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 101 | RIGLESS - AUSTRALIA | J.23.010369 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-05-17 01:00 | 2023-05-17 01:00 |  | 2023-05-17 01:00 | 2023-05-21 00:59 |  | 2023-05-21 00:59 | AUS East Coast WS | JMeyer9 | 2023-06-05 14:42 | AKohr |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.17 | RCK259 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 259 | RIGLESS - AUSTRALIA | J.23.010363 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-10 01:00 | 2023-05-10 01:00 |  | 2023-05-10 01:00 | 2023-05-16 00:59 |  | 2023-05-16 00:59 | AUS East Coast WS | JMeyer9 | 2023-06-03 06:27 | AKohr |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 75 | 50 | 0 | 50 | 55 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.20 | RCK195 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 195 | RIGLESS - AUSTRALIA | J.23.010366 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-02 01:00 | 2023-05-02 01:00 |  | 2023-05-02 01:00 | 2023-05-05 00:59 |  | 2023-05-07 00:59 | AUS East Coast WS | JMeyer9 | 2023-06-01 15:39 | AKohr |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 50 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.40 | COM402 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 402 | RIGLESS - AUSTRALIA | J.23.010376 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-27 | 2023-05-27 |  | 2023-05-27 | 2023-05-29 23:59 |  | 2023-05-29 23:59 | AUS East Coast WS | JMeyer9 | 2023-05-29 20:48 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 25 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.35 | COM380 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 380 | RIGLESS - AUSTRALIA | J.23.010371 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-26 01:00 | 2023-05-26 01:00 |  | 2023-05-26 01:00 | 2023-05-27 01:00 |  | 2023-05-27 01:00 | AUS East Coast WS | JMeyer9 | 2023-05-29 20:36 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 25 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.37 | RCK075 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 75 | RIGLESS - AUSTRALIA | J.23.010373 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-05-25 | 2023-05-24 |  | 2023-05-24 | 2023-05-25 23:59 |  | 2023-05-26 23:59 | AUS East Coast WS | JMeyer9 | 2023-05-26 09:48 | HFerdjallah |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 81.3 | 16.7 | 0 | 25 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.42 | Q4 Well 8 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010378 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-21 | 2023-06-21 |  | 2023-06-21 | 2023-06-23 22:59 |  | 2023-06-23 22:59 | AUS East Coast WS | JMeyer9 | 2023-05-18 20:27 | JMeyer9 |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 2 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.60 | Well 6 - April 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010426 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-07-20 | 2023-07-20 |  | 2023-07-20 | 2023-07-22 23:59 |  | 2023-07-22 23:59 | AUS East Coast WS | radinegara | 2023-05-18 19:36 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.55 | Well 1 - April 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010421 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2023-07-19 |  | 2023-07-19 | 2023-07-21 23:59 |  |  | AUS East Coast WS | radinegara | 2023-05-18 19:35 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.59 | Well 5 - April 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010425 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-07-17 | 2023-07-17 |  | 2023-07-17 | 2023-07-19 23:59 |  | 2023-07-19 23:59 | AUS East Coast WS | radinegara | 2023-05-18 19:35 | JMeyer9 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 2 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.58 | Well 4 - April 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010424 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-07-09 | 2023-07-09 |  | 2023-07-09 | 2023-07-11 23:59 |  | 2023-07-11 23:59 | AUS East Coast WS | radinegara | 2023-05-18 19:32 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.56 | Well 3 - April 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010422 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-07-06 | 2023-07-06 |  | 2023-07-06 | 2023-07-08 23:59 |  | 2023-07-08 23:59 | AUS East Coast WS | radinegara | 2023-05-18 19:30 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.57 | Well 2 - April 23 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010423 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-07-03 | 2023-07-03 |  | 2023-07-03 | 2023-07-05 23:59 |  | 2023-07-05 23:59 | AUS East Coast WS | radinegara | 2023-05-18 19:29 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.44 | Q4 Well 10 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010380 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-27 01:00 | 2023-06-27 01:00 |  | 2023-06-27 01:00 | 2023-06-30 01:59 |  | 2023-06-30 00:59 | AUS East Coast WS | JMeyer9 | 2023-05-18 19:28 | JMeyer9 |  | No |  |  |  |  | Aidan Flynn Kohr |  | 0 | 2 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.38 | Q4 Well 4 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010374 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-24 | 2023-06-24 |  | 2023-06-24 | 2023-06-26 23:59 |  | 2023-06-26 23:59 | AUS East Coast WS | JMeyer9 | 2023-05-18 19:27 | JMeyer9 |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 2 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.22 | Q2 Well 8 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010368 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-17 01:00 | 2023-06-17 01:00 |  | 2023-06-17 01:00 | 2023-06-20 00:59 |  | 2023-06-20 00:59 | AUS East Coast WS | JMeyer9 | 2023-05-18 19:26 | JMeyer9 |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 2 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.39 | Q4 Well 5 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010375 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-15 | 2023-06-15 |  | 2023-06-15 | 2023-06-17 23:59 |  | 2023-06-17 23:59 | AUS East Coast WS | JMeyer9 | 2023-05-18 19:25 | JMeyer9 |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 2 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.41 | Q4 Well 7 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010377 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-11 | 2023-06-11 |  | 2023-06-11 | 2023-06-13 23:59 |  | 2023-06-13 23:59 | AUS East Coast WS | JMeyer9 | 2023-05-18 19:23 | JMeyer9 |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 2 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.43 | Q4 Well 9 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010379 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-07 | 2023-06-07 |  | 2023-06-07 | 2023-06-09 22:59 |  | 2023-06-09 22:59 | AUS East Coast WS | JMeyer9 | 2023-05-18 14:38 | JMeyer9 |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 2 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.36 | Q4 Well 2 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | RIGLESS - AUSTRALIA | J.23.010372 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-04 | 2023-06-04 |  | 2023-06-04 | 2023-06-06 23:59 |  | 2023-06-06 23:59 | AUS East Coast WS | JMeyer9 | 2023-05-18 13:15 | HFerdjallah |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 2 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.19 | RCK260 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 260 | RIGLESS - AUSTRALIA | J.23.010365 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-08 01:00 | 2023-05-08 01:00 |  | 2023-05-08 01:00 | 2023-05-11 00:59 |  | 2023-05-11 00:59 | AUS East Coast WS | JMeyer9 | 2023-05-14 14:45 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.21 | RCK228 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 228 | RIGLESS - AUSTRALIA | J.23.010367 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-05 01:00 | 2023-05-05 01:00 |  | 2023-05-05 01:00 | 2023-05-08 00:59 |  | 2023-05-08 00:59 | AUS East Coast WS | JMeyer9 | 2023-05-14 14:33 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.15 | RCK261 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 261 | RIGLESS - AUSTRALIA | J.23.010361 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-04-04 01:00 | 2023-04-04 01:00 |  | 2023-04-04 01:00 | 2023-04-08 00:59 |  | 2023-04-08 00:59 | AUS East Coast WS | JMeyer9 | 2023-05-07 12:24 | HFerdjallah |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 2 |  |  |  | 75 | 66.7 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.51 | RCK 115 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 115 | RIGLESS - AUSTRALIA | J.22.116599 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-01 01:00 | 2023-03-30 01:00 |  | 2023-04-01 01:00 | 2023-04-05 00:59 |  | 2023-04-05 00:59 | AUS East Coast WS | JMeyer9 | 2023-05-07 12:24 | HFerdjallah |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.18 | RCK290 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 290 | RIGLESS - AUSTRALIA | J.23.010364 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-20 01:00 | 2023-04-20 01:00 |  | 2023-04-27 01:00 | 2023-05-02 00:59 |  | 2023-05-02 00:59 | AUS East Coast WS | JMeyer9 | 2023-05-07 11:59 | HFerdjallah |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 50 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.16 | RCK231 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 231 | RIGLESS - AUSTRALIA | J.23.010362 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-17 01:00 | 2023-04-17 01:00 |  | 2023-04-17 01:00 | 2023-04-20 00:59 |  | 2023-04-20 00:59 | AUS East Coast WS | JMeyer9 | 2023-04-20 08:49 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 83.3 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.53 | RCK288 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 288 | RIGLESS - AUSTRALIA | J.22.116601 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-14 01:00 | 2023-04-13 01:00 |  | 2023-04-14 01:00 | 2023-04-17 00:59 |  | 2023-04-17 00:59 | AUS East Coast WS | JMeyer9 | 2023-04-16 18:10 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 62.5 | 83.3 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.54 | RCK263 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 263 | RIGLESS - AUSTRALIA | J.22.116602 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-11 01:00 | 2023-04-11 01:00 |  | 2023-04-11 01:00 | 2023-04-14 00:59 |  | 2023-04-14 00:59 | AUS East Coast WS | JMeyer9 | 2023-04-13 22:08 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 83.3 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.52 | RCK 262 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 262 | RIGLESS - AUSTRALIA | J.22.116600 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-08 01:00 | 2023-04-07 01:00 |  | 2023-04-08 01:00 | 2023-04-11 00:59 |  | 2023-04-11 00:59 | AUS East Coast WS | JMeyer9 | 2023-04-11 02:21 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.47 | LUK 032 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | LUCKY GULLY 32 | RIGLESS - AUSTRALIA | J.22.116595 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-03-22 01:00 | 2023-03-20 01:00 |  | 2023-03-22 01:00 | 2023-03-25 00:59 |  | 2023-03-25 00:59 | AUS East Coast WS | JMeyer9 | 2023-04-09 11:47 | HFerdjallah |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 75 | 16.7 | 0 | 50 | 45 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.34 | RCK 258 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 258 | RIGLESS - AUSTRALIA | J.22.116592 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-02 01:00 | 2023-02-28 01:00 |  | 2023-03-02 01:00 | 2023-03-05 00:59 |  | 2023-03-05 00:59 | AUS East Coast WS | JMeyer9 | 2023-04-04 14:13 | HFerdjallah |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 33.3 | 0 | 75 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.49 | LUK 018 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | LUCKY GULLY 18 | RIGLESS - AUSTRALIA | J.22.116597 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-03-29 01:00 | 2023-03-27 01:00 |  | 2023-03-29 01:00 | 2023-04-01 00:59 |  | 2023-04-01 00:59 | AUS East Coast WS | JMeyer9 | 2023-04-03 09:44 | HFerdjallah |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 75 | 50 | 0 | 50 | 55 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.48 | LUK 017 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | LUCKY GULLY 17 | RIGLESS - AUSTRALIA | J.22.116596 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-03-25 01:00 | 2023-03-23 01:00 |  | 2023-03-25 01:00 | 2023-03-29 00:59 |  | 2023-03-29 00:59 | AUS East Coast WS | JMeyer9 | 2023-03-30 09:39 | HFerdjallah |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 75 | 50 | 0 | 50 | 55 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.33 | RCK 194 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 261 | RIGLESS - AUSTRALIA | J.22.116591 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-02-27 01:00 | 2023-02-25 01:00 |  | 2023-02-27 01:00 | 2023-03-02 00:59 |  | 2023-03-02 00:59 | AUS East Coast WS | JMeyer9 | 2023-03-27 16:31 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.45 | RCK 226 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 226 | RIGLESS - AUSTRALIA | J.22.116593 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-03-16 01:00 | 2023-03-14 01:00 |  | 2023-03-16 01:00 | 2023-03-22 00:59 |  | 2023-03-22 00:59 | AUS East Coast WS | JMeyer9 | 2023-03-26 16:28 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.46 | LUK 047 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | LUCKY GULLY 47 | RIGLESS - AUSTRALIA | J.22.116594 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-03-12 01:00 | 2023-03-12 01:00 |  | 2023-03-12 01:00 | 2023-03-16 00:59 |  | 2023-03-16 00:59 | AUS East Coast WS | JMeyer9 | 2023-03-26 16:19 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.32 | RCK 193 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 288 | RIGLESS - AUSTRALIA | J.22.116590 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-02-25 01:00 | 2023-02-23 01:00 |  | 2023-02-25 01:00 | 2023-02-28 00:59 |  | 2023-02-28 00:59 | AUS East Coast WS | JMeyer9 | 2023-03-26 14:27 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 83.3 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.31 | RCK 227 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 115 | RIGLESS - AUSTRALIA | J.22.116589 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-02-17 01:00 | 2023-02-15 01:00 |  | 2023-02-17 01:00 | 2023-02-24 00:59 |  | 2023-02-21 00:59 | AUS East Coast WS | JMeyer9 | 2023-03-26 14:12 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.29 | CNS 284 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI SOUTH 284 | RIGLESS - AUSTRALIA | J.22.116587 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-11-11 01:00 | 2022-11-11 |  | 2022-11-11 01:00 | 2022-11-16 00:59 |  | 2022-11-16 00:59 | AUS East Coast WS | JMeyer9 | 2022-12-09 10:52 | HFerdjallah |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 75 | 66.7 | 0 | 50 | 60 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.27 | CNS 285 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI SOUTH 285 | RIGLESS - AUSTRALIA | J.22.116585 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-04 01:00 | 2022-11-04 01:00 |  | 2022-11-04 01:00 | 2022-11-08 |  | 2022-11-07 23:59 | AUS East Coast WS | JMeyer9 | 2022-12-09 10:51 | HFerdjallah |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 83.3 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.50 | LUK016 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | LUCKY GULLY 16 | RIGLESS - AUSTRALIA | J.22.116598 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-20 01:00 | 2022-11-18 01:00 |  | 2022-11-20 01:00 | 2022-11-25 00:59 |  | 2022-11-25 00:59 | AUS East Coast WS | JMeyer9 | 2022-11-29 06:58 | radinegara |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.30 | CON 477 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 477 | RIGLESS - AUSTRALIA | J.22.116588 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-08 | 2022-11-08 01:00 |  | 2022-11-08 01:00 | 2022-11-11 00:59 |  | 2022-11-11 00:59 | AUS East Coast WS | JMeyer9 | 2022-11-12 04:38 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.28 | CNS 286 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI SOUTH 286 | RIGLESS - AUSTRALIA | J.22.116586 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-10-18 | 2022-10-18 |  | 2022-10-18 | 2022-11-04 00:59 |  | 2022-11-03 23:59 | AUS East Coast WS | JMeyer9 | 2022-11-12 03:22 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.25 | CNN 335 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI NORTH 335 | RIGLESS - AUSTRALIA | J.22.116583 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-10-09 | 2022-10-09 |  | 2022-10-10 | 2022-10-12 23:59 |  | 2022-10-12 23:59 | AUS East Coast WS | JMeyer9 | 2022-10-29 13:41 | HFerdjallah |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.26 | CNN 375 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI NORTH 375 | RIGLESS - AUSTRALIA | J.22.116584 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-10-15 | 2022-10-15 |  | 2022-10-15 | 2022-10-17 23:59 |  | 2022-10-17 23:59 | AUS East Coast WS | JMeyer9 | 2022-10-25 15:42 | JMeyer9 |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 2 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.11 | CON 463 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 463 | RIGLESS - AUSTRALIA | J.21.111257 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-05-07 10:00 | 2021-05-05 23:00 |  | 2021-05-06 23:00 | 2021-05-08 22:59 |  | 2021-05-09 09:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:29 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.06 | CON 431 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 431 | RIGLESS - AUSTRALIA | J.21.111256 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-04-24 11:00 | 2021-04-24 |  | 2021-04-24 | 2021-04-26 23:59 |  | 2021-04-28 10:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:29 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.05 | CON 430 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 430 | RIGLESS - AUSTRALIA | J.21.111252 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-03-14 11:00 | 2021-03-13 |  | 2021-03-14 | 2021-04-23 23:59 |  | 2021-04-24 10:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:29 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.04 | CNN 370 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri North 370 | RIGLESS - AUSTRALIA | J.21.111251 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Required | In Progress | 2021-03-09 09:00 | 2021-02-24 |  | 2021-03-08 22:00 | 2021-03-11 21:59 |  | 2021-03-12 08:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:29 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.02 | CoilFRAC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 430 | RIGLESS - AUSTRALIA | J.21.111250 | RPI | CT-FRAC,CT-WBCLEAN, FRAC-PROP | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-02-24 11:00 | 2021-02-24 |  | 2021-02-24 | 2021-02-26 23:59 |  | 2021-02-27 10:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:29 | FDPSystemUser |  | No |  |  |  |  | Trianto Adiputro Gunadi |  | 0 | 2 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.14 | CON 477 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 477 | RIGLESS - AUSTRALIA | J.21.111247 | RPI | CT-FRAC,CT-WBCLEAN | InComplete | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-05-24 11:00 | 2021-05-13 23:00 |  | 2021-05-24 | 2021-05-26 23:59 |  | 2021-05-27 10:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:28 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 0 | 2 |  |  |  | 59.4 | 8.3 | 0 | 0 | 26.3 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.12 | CON 474 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 474 | RIGLESS - AUSTRALIA | J.21.111246 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Required | In Progress | 2021-05-10 10:00 | 2021-05-08 23:00 |  | 2021-05-09 23:00 | 2021-05-11 23:00 |  | 2021-05-13 09:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:28 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.10 | CON 476 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 476 | RIGLESS - AUSTRALIA | J.21.111242 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-05-04 10:00 | 2021-05-02 23:00 |  | 2021-05-03 23:00 | 2021-05-06 22:59 |  | 2021-05-07 09:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:28 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.07 | CON 432 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 432 | RIGLESS - AUSTRALIA | J.21.111241 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-04-27 11:00 | 2021-04-26 |  | 2021-04-27 | 2021-04-29 23:59 |  | 2021-05-01 10:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:28 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.08 | CON 471 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 471 | RIGLESS - AUSTRALIA | J.21.111239 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-03-11 11:00 | 2021-03-05 |  | 2021-03-11 | 2021-03-13 23:59 |  | 2021-03-14 10:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:27 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.09 | CON 448 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 448 | RIGLESS - AUSTRALIA | J.21.111236 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-05-17 10:00 | 2021-04-29 |  | 2021-05-17 | 2021-05-19 23:59 |  | 2021-05-20 09:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:27 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.13 | CON 475 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 475 | RIGLESS - AUSTRALIA | J.21.111235 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-05-12 10:00 | 2021-05-10 23:00 |  | 2021-05-11 23:00 | 2021-05-13 23:00 |  | 2021-05-15 09:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:27 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.01 | CON432 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 432 | RIGLESS - AUSTRALIA | J.21.111234 | RPI | CT-FRAC,CT-WBCLEAN | InComplete | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-01-10 11:00 | 2021-02-21 |  | 2021-02-21 | 2021-02-23 23:59 |  | 2023-02-22 10:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:27 | FDPSystemUser |  | No |  |  |  |  | Trianto Adiputro Gunadi |  | 0 | 2 |  |  |  | 59.4 | 8.3 | 0 | 0 | 26.3 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1012060 | O.1012060.01 | A.1012060.01.03 | CNN 368 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri North 368 | RIGLESS - AUSTRALIA | J.21.111232 | RPI | CT-FRAC,CT-WBCLEAN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-03-03 11:00 | 2021-03-03 |  | 2021-03-03 | 2021-03-07 23:59 |  | 2021-03-08 10:59 | AUS East Coast WS | TGunadi | 2022-10-14 22:26 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1011693 | O.1011693.01 | A.1011693.01.04 | P&A inside 13 5/8" casing | BP DEVELOPMENT AUSTRALIA PTY LTD | IRONBARK 1 | Ocean Apex |  | WCF | REM-PA | InComplete | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-01-03 08:00 | 2021-01-02 |  | 2021-01-03 | 2021-01-05 23:59 |  | 2021-01-06 07:59 | AUS West Coast WS | VWedhaswari | 2021-01-01 09:00 | VWedhaswari |  | No |  |  |  |  | Victoria Rasmi Wedhaswari |  | 0 | 1 |  |  |  | 68.8 | 33.3 | 0 | 12.5 | 40 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011693 | O.1011693.01 | A.1011693.01.03 | Running DLT for Inflow Test | BP DEVELOPMENT AUSTRALIA PTY LTD | IRONBARK 1 | Ocean Apex |  | WCF | CMT-TOOLS | InComplete | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2021-01-02 08:00 | 2021-01-01 |  | 2021-01-02 | 2021-01-03 23:59 |  | 2021-01-04 07:59 | AUS West Coast WS | VWedhaswari | 2020-12-30 07:58 | VWedhaswari |  | No |  |  |  |  | Victoria Rasmi Wedhaswari |  | 0 | 1 |  |  |  | 68.8 | 33.3 | 0 | 0 | 37.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011693 | O.1011693.01 | A.1011693.01.02 | P&A inside 9 58 Liner | BP DEVELOPMENT AUSTRALIA PTY LTD | IRONBARK 1 | Ocean Apex |  | WCF | REM-PA | InComplete | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2020-12-31 08:00 | 2020-12-30 |  | 2020-12-31 | 2021-01-02 23:59 |  | 2021-01-03 07:59 | AUS West Coast WS | VWedhaswari | 2020-12-29 20:49 | VWedhaswari |  | No |  |  |  |  | Victoria Rasmi Wedhaswari |  | 0 | 1 |  |  |  | 68.8 | 33.3 | 0 | 0 | 37.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011693 | O.1011693.01 | A.1011693.01.01 | 13 38 DLT + Stormvalve | BP DEVELOPMENT AUSTRALIA PTY LTD | IRONBARK 1 | Ocean Apex |  | WCF | CMT-TOOLS | High | Unconfirmed - 50% | Design - CEC |  | Design Completed | Not Required | In Progress | 2020-12-20 08:00 | 2020-12-18 |  | 2020-12-20 | 2020-12-22 23:59 |  | 2020-12-23 07:59 | AUS West Coast WS | VWedhaswari | 2020-12-17 21:33 | VWedhaswari |  | No |  |  |  |  | Victoria Rasmi Wedhaswari |  | 0 | 1 |  |  |  | 56.3 | 16.7 | 0 | 0 | 27.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011660 | O.1011660.05 | A.1011660.05.03 | 9-5/8in Intermediate Casing | BEACH ENERGY LTD | Geographe-4 | Ocean Onyx | J.21.109535 | WCF | PRI-INTER | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-04-10 08:00 | 2021-04-01 |  | 2021-04-10 | 2021-04-10 23:59 |  | 2021-04-11 07:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 12:23 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.05 | A.1011660.05.05 | Geographe-4 _ 20in Surface Casing | BEACH ENERGY LTD | GEOGRAPHE 4 | Ocean Onyx | J.21.109534 | WCF | PRI-SURF | Medium | Confirmed | Execute - PSD |  | In Progress | In Progress | In Progress | 2021-04-03 08:00 | 2021-03-01 |  | 2021-04-03 | 2021-04-03 23:59 |  | 2021-04-04 07:59 | AUS West Coast WS | MAlsaman | 2022-10-03 12:23 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.05 | A.1011660.05.04 | Artisan-1 _ 7in Liner | BEACH ENERGY LTD | Geographe-4 | Ocean Onyx | J.21.109531 | WCF | PRI-LIN | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-04-16 08:00 | 2021-04-01 |  | 2021-04-16 | 2021-04-16 23:59 |  | 2021-04-17 07:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 12:23 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.05 | A.1011660.05.01 | Geographe-4 - 36in Conductor | BEACH ENERGY LTD | Geographe-4 | Ocean Onyx | J.21.109343 | WCF | PRI-COND | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-03-28 08:00 | 2021-02-23 |  | 2021-03-28 | 2021-03-28 23:59 |  | 2021-03-29 07:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.05 | A.1011660.05.02 | Geograph-4 _ 13-3/8in Surface Casing | BEACH ENERGY LTD | Geographe-4 | Ocean Onyx | J.21.109341 | WCF | PRI-SURF | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-04-10 08:00 | 2021-04-01 |  | 2021-04-10 | 2021-04-10 23:59 |  | 2021-04-11 07:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.04 | A.1011660.04.03 | TW-1 _ 9-5/8in Intermediate Casing | BEACH ENERGY LTD | THYLACINE WEST-1 | Ocean Onyx | J.21.109536 | WCF | PRI-INTER | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-11-01 08:00 | 2021-10-23 |  | 2021-11-01 | 2021-11-01 23:59 |  | 2021-11-02 07:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 12:23 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.04 | A.1011660.04.02 | TW-1 _ 13-3/8in Surface Casing | BEACH ENERGY LTD | THYLACINE WEST-1 | Ocean Onyx | J.21.109334 | WCF | PRI-SURF | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-10-23 08:00 | 2021-09-16 |  | 2021-10-23 | 2021-10-23 23:59 |  | 2021-10-24 07:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.04 | A.1011660.04.05 | TW-1 _ PnA | BEACH ENERGY LTD | THYLACINE WEST-1 | Ocean Onyx | J.21.109330 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-11-15 08:00 | 2021-10-23 |  | 2021-11-15 | 2021-11-15 23:59 |  | 2021-11-16 07:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.04 | A.1011660.04.01 | TW-1 - 36in Conductor | BEACH ENERGY LTD | THYLACINE WEST-1 | Ocean Onyx | J.21.109329 | WCF | PRI-COND | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-10-18 08:00 | 2021-09-16 |  | 2021-10-18 | 2021-10-18 23:59 |  | 2021-10-19 07:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.04 | A.1011660.04.04 | TW-1 _ 7in Liner | BEACH ENERGY LTD | THYLACINE WEST-1 | Ocean Onyx | J.21.109324 | WCF | PRI-LIN | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-11-07 08:00 | 2021-10-23 |  | 2021-11-07 | 2021-11-07 23:59 |  | 2021-11-08 07:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 11:34 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.04 | A.1011660.04.06 | TW-1 _ PnA#2 | BEACH ENERGY LTD | THYLACINE WEST-1 | Ocean Onyx | J.21.109322 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-11-16 08:00 | 2021-10-24 |  | 2021-11-16 | 2021-11-16 23:59 |  | 2021-11-17 07:59 | AUS West Coast WS | FDPSystemUser | 2022-10-03 11:34 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.03 | A.1011660.03.06 | TN-1 _ PnA#2 | BEACH ENERGY LTD | Thylacine South | Ocean Onyx |  | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-09-29 08:00 | 2021-09-06 |  | 2021-09-29 | 2021-09-29 23:59 |  | 2021-09-30 07:59 | AUS West Coast WS | FDPSystemUser | 2021-02-12 09:42 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.03 | A.1011660.03.05 | TN1 _ PnA | BEACH ENERGY LTD | Thylacine South | Ocean Onyx |  | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-09-28 08:00 | 2021-09-05 |  | 2021-09-28 | 2021-09-28 23:59 |  | 2021-09-29 07:59 | AUS West Coast WS | FDPSystemUser | 2021-02-12 09:42 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.03 | A.1011660.03.04 | TN1 _ 7in Liner | BEACH ENERGY LTD | Thylacine South | Ocean Onyx |  | WCF | PRI-LIN | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-09-20 08:00 | 2021-09-05 |  | 2021-09-20 | 2021-09-20 23:59 |  | 2021-09-21 07:59 | AUS West Coast WS | FDPSystemUser | 2021-02-12 09:41 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.03 | A.1011660.03.03 | TN1 _ 9-5/8in Intermediate Casing | BEACH ENERGY LTD | Thylacine South | Ocean Onyx |  | WCF | PRI-INTER | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-09-14 08:00 | 2021-09-05 |  | 2021-09-14 | 2021-09-14 23:59 |  | 2021-09-15 07:59 | AUS West Coast WS | FDPSystemUser | 2021-02-12 09:31 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.03 | A.1011660.03.02 | TN1 _ 13-3/8in Surface Casing | BEACH ENERGY LTD | Thylacine South | Ocean Onyx |  | WCF | PRI-SURF | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-09-05 08:00 | 2021-07-30 |  | 2021-09-05 | 2021-09-05 23:59 |  | 2021-09-06 07:59 | AUS West Coast WS | FDPSystemUser | 2021-02-12 09:30 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.03 | A.1011660.03.01 | TN1 - 36in Conductor | BEACH ENERGY LTD | Thylacine South | Ocean Onyx |  | WCF | PRI-COND | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-08-31 08:00 | 2021-07-30 |  | 2021-08-31 | 2021-08-31 23:59 |  | 2021-09-01 07:59 | AUS West Coast WS | FDPSystemUser | 2021-02-12 09:29 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.02 | A.1011660.02.02 | Geograph-5 _ 13-3/8in Surface Casing | BEACH ENERGY LTD | GEOGRAPHE-5 | Ocean Onyx | J.21.109336 | WCF | PRI-SURF | InComplete | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-03-25 08:00 | 2021-03-05 |  | 2021-03-25 | 2021-03-25 23:59 |  | 2021-03-26 07:59 | AUS West Coast WS | MAlsaman | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.02 | A.1011660.02.01 | Geograph-5 _ 36in Conductor Casing | BEACH ENERGY LTD | GEOGRAPHE-5 | Ocean Onyx | J.21.109326 | WCF | PRI-COND | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-03-20 08:00 | 2021-03-05 |  | 2021-03-20 | 2021-03-20 23:59 |  | 2021-03-21 07:59 | AUS West Coast WS | MAlsaman | 2022-10-03 11:34 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.02 | A.1011660.02.03 | Geographe-5 _ 9-5/8in Casing | BEACH ENERGY LTD | GEOGRAPHE-5 | Ocean Onyx | J.21.109320 | WCF | PRI-LONG | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-05-10 08:00 | 2021-05-03 |  | 2021-05-10 | 2021-05-10 23:59 |  | 2021-05-11 07:59 | AUS West Coast WS | MAlsaman | 2022-10-03 11:34 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.01 | A.1011660.01.03 | 9-5/8in Intermediate Casing | BEACH ENERGY LTD | ARTISAN-1 | Ocean Onyx | J.21.109533 | WCF | PRI-INTER | InComplete | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-01 08:00 | 2021-02-20 |  | 2021-03-01 | 2021-03-01 23:59 |  | 2021-03-02 07:59 | AUS West Coast WS | MAlsaman | 2022-10-03 12:23 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.01 | A.1011660.01.01 | Artisan-1 - 36in Conductor | BEACH ENERGY LTD | ARTISAN-1 | Ocean Onyx | J.21.109532 | WCF | PRI-COND | InComplete | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-02-15 08:00 | 2021-01-14 |  | 2021-02-15 | 2021-02-15 23:59 |  | 2021-02-16 07:59 | AUS West Coast WS | MAlsaman | 2022-10-03 12:23 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.01 | A.1011660.01.09 | Artisan-1 _ PnA#5 | BEACH ENERGY LTD | ARTISAN-1 | Ocean Onyx | J.21.109340 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-03-18 08:00 | 2021-02-23 |  | 2021-03-18 | 2021-03-18 23:59 |  | 2021-03-19 07:59 | AUS West Coast WS | MAlsaman | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.01 | A.1011660.01.02 | Artisan-1 _ 13-3/8in Surface Casing | BEACH ENERGY LTD | ARTISAN-1 | Ocean Onyx | J.21.109338 | WCF | PRI-SURF | InComplete | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-02-20 08:00 | 2021-01-14 |  | 2021-02-20 | 2021-02-20 23:59 |  | 2021-02-21 07:59 | AUS West Coast WS | MAlsaman | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.01 | A.1011660.01.08 | Artisan-1 _ PnA#4 | BEACH ENERGY LTD | ARTISAN-1 | Ocean Onyx | J.21.109333 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-03-17 08:00 | 2021-02-22 |  | 2021-03-17 | 2021-03-17 23:59 |  | 2021-03-18 07:59 | AUS West Coast WS | MAlsaman | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.01 | A.1011660.01.04 | Artisan-1 _ 7in Liner | BEACH ENERGY LTD | ARTISAN-1 | Ocean Onyx | J.21.109327 | WCF | PRI-LIN | InComplete | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-07 08:00 | 2021-02-20 |  | 2021-03-07 | 2021-03-07 23:59 |  | 2021-03-08 07:59 | AUS West Coast WS | MAlsaman | 2022-10-03 11:34 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.01 | A.1011660.01.06 | Artisan-1 _ PnA#2 | BEACH ENERGY LTD | ARTISAN-1 | Ocean Onyx | J.21.109325 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-03-16 08:00 | 2021-02-21 |  | 2021-03-16 | 2021-03-16 23:59 |  | 2021-03-17 07:59 | AUS West Coast WS | MAlsaman | 2022-10-03 11:34 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.01 | A.1011660.01.05 | Artisan-1 _ PnA | BEACH ENERGY LTD | ARTISAN-1 | Ocean Onyx | J.21.109323 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-03-15 08:00 | 2021-02-20 |  | 2021-03-15 | 2021-03-15 23:59 |  | 2021-03-16 07:59 | AUS West Coast WS | MAlsaman | 2022-10-03 11:34 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011660 | O.1011660.01 | A.1011660.01.07 | Artisan-1 _ PnA#3 | BEACH ENERGY LTD | ARTISAN-1 | Ocean Onyx | J.21.109321 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-03-16 08:00 | 2021-02-21 |  | 2021-03-16 | 2021-03-16 23:59 |  | 2021-03-17 07:59 | AUS West Coast WS | MAlsaman | 2022-10-03 11:34 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1011631 | O.1011631.01 | A.1011631.01.02 | Stag 36 XTRA with EV Multifinger Caliper Tool | JADESTONE ENERGY (AUSTRALIA) PTY LTD | Stag-36H | STAG SNUBBING UNIT 1 |  | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-04-15 |  | 2021-04-30 | 2021-05-16 23:59 |  |  | New Burn WL | frosa2 | 2022-09-03 05:59 | walfaro |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 58600 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1011631 | O.1011631.01 | A.1011631.01.01 | Stag36H EV MIT | JADESTONE ENERGY (AUSTRALIA) PTY LTD | Stag-36H | STAG SNUBBING UNIT 1 |  | RPI | PS-SLK-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-01-07 |  | 2021-01-09 | 2021-01-15 23:59 |  |  | New Burn WL | frosa2 | 2021-01-13 21:07 | RTokabayev |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 58600 | [10 empty] | 0 | [7 empty] | Bilal Ahmad | Wireline Slickline
P.1011402 | O.1011402.01 | A.1011402.01.22 | U 3148-H2Dec2021 | SANTOS LIMITED | MOOMBA 197, Tindilpie 6 | Rigless Australia - 1 | J.21.108805 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-15 10:00 | 2021-12-14 06:00 |  | 2021-12-15 10:00 | 2021-12-17 23:59 |  | 2021-12-17 23:59 | Moomba WL | ymoradi2 | 2022-10-03 11:52 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 11360.1 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1011402 | O.1011402.01 | A.1011402.01.21 | Epsilon 6- Links | SANTOS LIMITED | Epsilon 6 | Rigless Australia - 1 | J.21.108801 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-11 10:00 | 2021-12-11 06:00 |  | 2021-12-11 10:00 | 2021-12-13 23:59 |  | 2021-12-13 23:59 | Moomba WL | DKitney | 2022-10-03 11:52 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 11360.1 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1011402 | O.1011402.01 | A.1011402.01.20 | Baryulah 2- Post Frac | SANTOS LIMITED | BARYULAH 2 | Rigless Australia - 1 | J.21.108798 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-08 10:00 | 2021-12-08 06:00 |  | 2021-12-08 10:00 | 2021-12-10 23:59 |  | 2021-12-10 23:59 | Moomba WL | DKitney | 2022-10-03 11:52 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 20613.11 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1011402 | O.1011402.01 | A.1011402.01.19 | Casimir 1 | SANTOS LIMITED | Casimir 1 (NFE A D) | Rigless Australia - 1 | J.21.108797 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-07 10:00 | 2021-12-07 |  | 2021-12-07 10:00 | 2021-12-08 23:59 |  | 2021-12-08 23:59 | Moomba WL | DKitney | 2022-10-03 11:52 | FDPSystemUser |  | No |  |  |  |  | Kelly Keese |  | 5730.99 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1011402 | O.1011402.01 | A.1011402.01.18 | Frostillicus 2- SCMT | SANTOS LIMITED | Frostillicus 2 | Rigless Australia - 1 | J.21.108793 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-11-24 13:00 | 2021-11-22 09:00 |  | 2021-11-25 06:00 | 2021-11-27 12:00 |  | 2021-11-26 19:00 | Moomba WL | DKitney | 2022-10-03 11:51 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1011402 | O.1011402.01 | A.1011402.01.17 | Hobbes 4- SCMT | SANTOS LIMITED | Hobbes 4 | Rigless Australia - 1 | J.21.108792 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-11-23 13:00 | 2021-11-21 09:00 |  | 2021-11-24 06:00 | 2021-11-26 12:00 |  | 2021-11-25 19:00 | Moomba WL | DKitney | 2022-10-03 11:51 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1011402 | O.1011402.01 | A.1011402.01.16 | Gooranie 14- TTBP | SANTOS LIMITED | GOORANIE 14 | Rigless Australia - 1 | J.21.108790 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-18 13:00 | 2021-11-08 11:00 |  | 2021-11-18 12:00 | 2021-11-20 18:00 |  | 2021-11-20 19:00 | Moomba WL | DKitney | 2022-10-03 11:51 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 41225.94 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1011402 | O.1011402.01 | A.1011402.01.15 | Koree South 1 | SANTOS LIMITED | Koree South 1 | Rigless Australia - 1 | J.21.108783 | RPI | PS-WL-NO | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-10 13:00 | 2021-11-09 11:00 | 2021-11-10 | 2021-11-10 12:00 | 2021-11-12 18:00 | 2021-11-13 | 2021-11-12 19:00 | Moomba WL | KKeese | 2022-10-03 11:41 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 41225.94 | 1 |  |  |  | 91.7 | 66.7 | 100 | 75 | 80 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1011402 | O.1011402.01 | A.1011402.01.14 | Moomba 250 | SANTOS LIMITED | MOOMBA 250 | Rigless Australia - 1 | J.21.108780 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-06 13:00 | 2021-10-27 11:00 | 2021-11-06 | 2021-11-06 12:00 | 2021-11-08 18:00 | 2021-11-09 | 2021-11-08 19:00 | Moomba WL | KKeese | 2022-10-03 11:41 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 41225.94 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1011402 | O.1011402.01 | A.1011402.01.13 | Meranji 7 | SANTOS LIMITED | Meranji 7 | Rigless Australia - 1 | J.21.108765 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-22 13:00 | 2021-10-12 11:00 | 2021-10-22 | 2021-10-22 12:00 | 2021-10-24 18:00 | 2021-10-25 | 2021-10-24 19:00 | Moomba WL | KKeese | 2022-10-03 11:39 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 41225.94 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1011402 | O.1011402.01 | A.1011402.01.12 | SWQ Campain- H2SEP2021 | SANTOS LIMITED | Wackett South 1, Barrolka 11, Barrolka 9, Swan Lake 15, Big Lake 110, Big Lake 138, GOORANIE 14, Kanowana 14 | Rigless Australia - 1 | J.21.108744 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-23 12:00 | 2021-09-22 11:00 | 2021-09-22 23:00 | 2021-09-23 12:00 | 2021-09-25 18:00 | 2021-09-26 | 2021-09-25 18:00 | Moomba WL | ymoradi2 | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 41225.94 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1011402 | O.1011402.01 | A.1011402.01.11 | Challum 10- TTBP | SANTOS LIMITED | Challum 10 | Rigless Australia - 1 | J.21.108740 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-09-18 12:00 | 2021-09-08 11:00 | 2021-09-17 23:00 | 2021-09-18 12:00 | 2021-09-20 18:00 | 2021-09-20 23:00 | 2021-09-20 18:00 | Moomba WL | DKitney | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 41225.94 | 1 |  |  |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1011402 | O.1011402.01 | A.1011402.01.10 | Cherokee 2- SCMT | SANTOS LIMITED | Cherokee 2 | Rigless Australia - 1 | J.21.108739 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-09-10 12:00 | 2021-09-07 15:00 | 2021-09-08 | 2021-09-10 12:00 | 2021-09-12 18:00 | 2021-09-12 | 2021-09-12 18:00 | Moomba WL | DKitney | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1011402 | O.1011402.01 | A.1011402.01.09 | Bolah 5_SCMT | SANTOS LIMITED | Bolah 5 | Rigless Australia - 1 | J.21.108425 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-03-02 06:00 | 2021-02-27 09:00 | 2021-03-01 | 2021-03-02 06:00 | 2021-03-04 12:00 | 2021-03-04 | 2021-03-04 12:00 | Moomba WL | MAl-wakeel | 2022-10-03 11:03 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1011402 | O.1011402.01 | A.1011402.01.08 | Ruby 3_SCMT | SANTOS LIMITED | RUBY 3 | Rigless Australia - 1 | J.21.108422 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-03-03 06:00 | 2021-02-24 09:00 | 2021-03-02 | 2021-03-03 06:00 | 2021-03-05 12:00 | 2021-03-05 | 2021-03-05 12:00 | Moomba WL | MAl-wakeel | 2022-10-03 11:03 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1011402 | O.1011402.01 | A.1011402.01.06 | Daralingie 27 | SANTOS LIMITED | Daralingie 27 | Rigless Australia - 1 | J.21.108421 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-21 12:00 | 2021-02-15 | 2021-02-20 | 2021-02-21 12:00 | 2021-02-23 18:00 | 2021-02-23 | 2021-02-23 18:00 | Moomba WL | KKeese | 2022-10-03 11:03 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1011402 | O.1011402.01 | A.1011402.01.05 | Moomba 263 | SANTOS LIMITED | Moomba 263 | Rigless Australia - 1 | J.21.108420 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-10 12:00 | 2021-02-13 09:00 | 2021-03-11 | 2021-03-10 12:00 | 2021-03-12 18:00 | 2021-03-14 | 2021-03-12 18:00 | Moomba WL | KKeese | 2022-10-03 11:03 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1011402 | O.1011402.01 | A.1011402.01.01 | Beckler 3- PABI | SANTOS LIMITED | BECKLER 3 | Rigless Australia - 1 | J.20.062968 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2020-12-05 12:00 | 2020-11-30 15:00 | 2020-12-05 | 2020-12-05 12:00 | 2020-12-07 18:00 | 2020-12-08 | 2020-12-07 18:00 | Moomba WL | DKitney | 2022-10-03 11:03 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 12163.74 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1011402 | O.1011402.01 | A.1011402.01.07 | Bolah 7_SCMT | SANTOS LIMITED | Bolah 7 | Rigless Australia - 1 | J.21.108419 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-02-25 06:00 | 2021-02-23 09:00 | 2021-02-24 | 2021-02-25 06:00 | 2021-02-27 12:00 | 2021-02-27 | 2021-02-27 12:00 | Moomba WL | MAl-wakeel | 2022-10-03 11:03 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1011402 | O.1011402.01 | A.1011402.01.02 | Alwyn North 2- CBL Revisit | SANTOS LIMITED | Alwyn North 2 | Rigless Australia - 1 | J.20.062967 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2020-12-27 12:00 | 2020-12-07 09:00 | 2020-12-26 | 2020-12-27 12:00 | 2020-12-29 18:00 | 2020-12-29 | 2020-12-29 18:00 | Moomba WL | DKitney | 2022-10-03 11:03 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1011402 | O.1011402.01 | A.1011402.01.04 | Big Lake 104 | SANTOS LIMITED | Big Lake 104 | Rigless Australia - 1 | J.21.108418 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-10 06:00 | 2021-02-08 09:00 | 2021-02-08 | 2021-02-10 06:00 | 2021-02-12 12:00 | 2021-02-11 | 2021-02-12 12:00 | Moomba WL | KKeese | 2022-10-03 11:03 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1011402 | O.1011402.01 | A.1011402.01.03 | Moomba 262 | SANTOS LIMITED | MOOMBA 262 | Rigless Australia - 1 | J.21.108417 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-02-07 12:00 | 2021-01-18 09:00 | 2021-02-06 | 2021-02-07 12:00 | 2021-02-09 18:00 | 2021-02-09 | 2021-02-09 18:00 | Moomba WL | KKeese | 2022-10-03 11:02 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1011289 | O.1011289.01 | A.1011289.01.25 | DC-F WP7 12.25" | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 PRESSURE MANAGEMENT WELL E-WP3 | ENSIGN 963 | J.26.014680 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2023-12-01 08:00 | 2025-12-15 | 2026-02-01 | 2026-02-01 | 2026-02-09 23:59 | 2026-02-10 | 2026-02-09 23:59 | New Burn WL | KKeese | 2025-11-05 13:55 | KKeese |  | No |  |  |  |  | Edmund Brobbey |  | 0 | 5 |  | L0 - No RO |  | 66.7 | 16.7 | 0 | 0 | 25 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1011289 | O.1011289.01 | A.1011289.01.29 | DC-A | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 PRESSURE MANAGEMENT WELL E-WP3 | ENSIGN 963 | J.26.014684 | RPE | ES-OH-NO | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-08-25 | 2026-07-08 | 2026-08-25 | 2026-08-25 | 2026-09-02 23:59 | 2026-09-03 | 2026-09-02 23:59 | New Burn WL | KKeese | 2025-10-14 10:03 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Edmund Brobbey |  | 0 | 2 |  | L3 - Full RO |  | 58.3 | 33.3 | 100 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1011289 | O.1011289.01 | A.1011289.01.28 | DC-A | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 PRESSURE MANAGEMENT WELL E-WP3 | ENSIGN 963 | J.26.014683 | RPE | ES-OH-NO | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-08-11 | 2026-06-24 | 2026-08-11 | 2026-08-11 | 2026-08-19 23:59 | 2026-08-20 | 2026-08-19 23:59 | New Burn WL | KKeese | 2025-10-14 10:03 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Edmund Brobbey |  | 0 | 2 |  | L3 - Full RO |  | 58.3 | 33.3 | 100 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1011289 | O.1011289.01 | A.1011289.01.27 | DC-A | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 PRESSURE MANAGEMENT WELL E-WP3 | ENSIGN 963 | J.26.014682 | RPE | ES-OH-NO | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-08-01 | 2026-06-14 | 2026-08-01 | 2026-08-01 | 2026-08-09 23:59 | 2026-08-10 | 2026-08-09 23:59 | New Burn WL | KKeese | 2025-10-14 10:03 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Edmund Brobbey |  | 0 | 2 |  | L3 - Full RO |  | 58.3 | 33.3 | 100 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1011289 | O.1011289.01 | A.1011289.01.26 | DC-F WP7 8.5" | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 PRESSURE MANAGEMENT WELL E-WP3 | ENSIGN 963 | J.26.014681 | RPE | ES-OH-NO | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2026-04-16 | 2026-02-27 | 2026-04-16 | 2026-04-16 | 2026-04-24 23:59 | 2026-04-25 | 2026-04-24 23:59 | New Burn WL | KKeese | 2025-10-14 10:03 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Edmund Brobbey |  | 0 | 2 |  | L3 - Full RO |  | 58.3 | 33.3 | 100 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1011289 | O.1011289.01 | A.1011289.01.24 | E-WP3 ST1 XPT-FMI | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 PRESSURE MANAGEMENT WELL E-WP3 | ENSIGN 963 | J.25.102443 | RPE | ES-OH-NO | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-08-01 | 2025-06-14 | 2025-08-01 | 2025-08-01 | 2025-08-09 23:59 | 2025-08-10 | 2025-08-09 23:59 | New Burn WL | KKeese | 2025-08-01 16:03 | CKinsella |  | No |  |  |  | ROE WL Mumbai | Edmund Brobbey |  | 300156 | 2 |  | L3 - Full RO |  | 100 | 100 | 100 | 100 | 100 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1011289 | O.1011289.01 | A.1011289.01.18 | CVX_BWI-CETT-Epilogue | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 WATER INJECTION WELL D-WI1, B18M, L26M, F16M, F37M, G75M, L54M, L76M, M42M, M72M, P74M, Z56M | ENSIGN 963 | J.24.149379 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-09-27 | 2024-09-29 | 2024-09-25 | 2024-10-01 | 2024-10-25 23:59 | 2024-11-15 | 2024-10-25 23:59 | New Burn WL | MElsanousi | 2025-07-31 10:20 | CKinsella |  | No |  |  |  | ROE WL Mumbai | Jarrod Sedmak |  | 290747 | 6 |  | L2 - Shift RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1011289 | O.1011289.01 | A.1011289.01.20 | BWI CETT-Epilogue | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 WATER INJECTION WELL D-WI1, B18M, L26M, F16M, F37M, G75M, L54M, L76M, M42M, M72M, P74M, Z56M | ENSIGN 963 | J.25.020158 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-01-06 | 2025-03-30 | 2025-03-26 | 2025-04-01 | 2025-05-31 23:59 | 2025-05-16 | 2025-02-03 23:59 | New Burn WL | MElsanousi | 2025-06-07 10:41 | KKeese |  | No |  |  |  | ROE WL Mumbai | Jarrod Sedmak |  | 0 | 6 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 4 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1011289 | O.1011289.01 | A.1011289.01.23 | GyroData E-WI2 | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 WATER INJECTION WELL E-WI2 | ENSIGN 963 | J.25.098368 | RPE | ES-CH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-05-18 | 2025-05-15 | 2025-05-18 | 2025-05-25 | 2025-05-28 23:59 | 2025-05-22 | 2025-05-21 23:59 | New Burn WL | KKeese | 2025-05-26 11:57 | CKinsella |  | No |  |  |  |  | Edmund Brobbey |  | 60368 | 1 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 2 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1011289 | O.1011289.01 | A.1011289.01.19 | BWI DC:DWI1 ST1 XPT | CHEVRON APG ABU PERTH. | D-WP1 ST1, D-WP2 ST1, D-WI1 ST1 | ENSIGN 963 | J.25.020157 | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-11-05 | 2025-01-10 | 2025-01-30 | 2025-01-30 | 2025-02-12 23:59 | 2025-02-13 | 2025-02-12 23:59 | New Burn WL | MElsanousi | 2025-05-16 18:46 | KKeese |  | No |  |  |  | ROE WL Mumbai | Jarrod Sedmak |  | 121400 | 2 |  | L3 - Full RO |  | 100 | 100 | 100 | 100 | 100 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1011289 | O.1011289.01 | A.1011289.01.17 | BWI DC:DWP1 ST1 XPT-FMI | CHEVRON APG ABU PERTH. | D-WP1 ST1 | ENSIGN 963 | J.24.149378 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-03-16 | 2025-03-13 | 2025-03-16 | 2025-03-16 | 2025-03-29 23:59 | 2025-03-30 | 2025-03-29 23:59 | New Burn WL | MElsanousi | 2025-05-16 18:45 | KKeese |  | No |  |  |  | ROE WL Mumbai | Jarrod Sedmak |  | 197700 | 2 |  | L3 - Full RO |  | 100 | 100 | 100 | 100 | 100 |  | 4 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1011289 | O.1011289.01 | A.1011289.01.16 | BWI DC:DWP2 ST1 XPT-FMI | CHEVRON APG ABU PERTH. | D-WP2 ST1 | ENSIGN 963 | J.24.149369 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-11-20 | 2024-10-27 | 2025-02-21 | 2025-02-28 | 2025-03-08 23:59 | 2025-03-11 | 2024-12-06 23:59 | New Burn WL | MElsanousi | 2025-05-16 18:44 | KKeese |  | No |  |  |  | ROE WL Mumbai | Jarrod Sedmak |  | 197700 | 1 |  | L3 - Full RO |  | 100 | 100 | 100 | 100 | 100 |  | 2 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1011289 | O.1011289.01 | A.1011289.01.08 | BWI DC:D-WP2 USIT-CBL | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 PRESSURE MANAGEMENT WELL D-WP2, GORGON PLANT CO2 PRESSURE MANAGEMENT WELL D-WP1, GORGON PLANT CO2 WATER INJECTION WELL D-WI1, D-WI3 | ENSIGN 963 | J.24.077373 | RPE | ES-CH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-08-27 | 2024-07-20 | 2024-08-01 08:00 | 2024-08-02 | 2025-10-31 23:59 | 2025-11-01 | 2025-10-31 23:59 | New Burn WL | CKinsella | 2025-05-15 15:46 | KKeese |  | No |  |  |  | ROE WL Mumbai | Jarrod Sedmak |  | 328100 | 9 |  | L2 - Shift RO |  | 100 | 100 | 100 | 100 | 100 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1011289 | O.1011289.01 | A.1011289.01.21 | Rig 26 USIT-CBL in 9 5/8" | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 PRESSURE MANAGEMENT WELL E-WP3, GORGON PLANT CO2 PRESSURE MANAGEMENT WELL E-WP4, E-WP4 ST1 | ENSIGN 963 | J.25.056717 | RPE | ES-CH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-03-06 | 2025-02-21 | 2025-03-06 | 2025-03-06 | 2025-05-01 23:59 | 2025-05-02 | 2025-05-01 23:59 | New Burn WL | KKeese | 2025-05-15 15:42 | KKeese |  | No |  |  |  | ROE WL Mumbai | Jarrod Sedmak |  | 92380 | 2 |  | L3 - Full RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1011289 | O.1011289.01 | A.1011289.01.22 | XPT-FMI on E-WP4 ST1 | CHEVRON APG ABU PERTH. | E-WP4 ST1 | ENSIGN 963 | J.25.087878 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-05-01 | 2025-04-28 | 2025-05-01 | 2025-05-01 | 2025-05-14 23:59 | 2025-05-16 | 2025-05-14 23:59 | New Burn WL | KKeese | 2025-05-14 16:15 | CKinsella |  | No |  |  |  | ROE WL Mumbai | Edmund Brobbey |  | 208260 | 1 |  | L3 - Full RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1011289 | O.1011289.01 | A.1011289.01.03 | Perforation BWI Z-WI2 | CHEVRON APG ABU PERTH. | GORGON PLANT DISPOSAL WELL Z-WI2 | ENSIGN 963 | J.23.053780 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2024-10-28 | 2024-10-30 |  | 2024-11-01 | 2024-11-25 23:59 |  | 2024-11-25 23:59 | New Burn WL | VOliveira5 | 2024-12-06 18:10 | ASamokhin |  | No |  |  |  |  | Jarrod Sedmak |  | 1257913.5 | 17 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1011289 | O.1011289.01 | A.1011289.01.15 | CVX_BWI-SATT-Slim Epilogue | CHEVRON APG ABU PERTH. | J68, M55, M17, H17, G71, F62M, E16 | ENSIGN 963 | J.24.148419 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-11-16 | 2024-11-15 |  | 2024-11-16 | 2024-12-10 23:59 |  | 2024-12-10 23:59 | New Burn WL | MElsanousi | 2024-12-05 10:52 | CClark9 |  | No |  |  |  | ROE WL Mumbai | Jarrod Sedmak |  | 38742 | 2 |  | L2 - Shift RO |  | 100 | 66.7 | 100 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1011289 | O.1011289.01 | A.1011289.01.02 | Chevron Nov Activity | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 WATER INJECTION WELL D-WI1 | ENSIGN 963 | J.22.110103 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-11-01 |  | 2022-11-03 | 2022-11-27 23:59 |  |  | New Burn WL | frosa2 | 2024-11-22 10:26 | KKeese |  | No |  |  |  | ROE WL Mumbai | Chris Rowand |  | 1403757.8 | 0 |  |  |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1011289 | O.1011289.01 | A.1011289.01.09 | BWI DC:D-WP1 USIT-CBL | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 PRESSURE MANAGEMENT WELL D-WP1 | ENSIGN 963 | J.24.077374 | RPE | ES-CH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-09-06 | 2024-09-01 |  | 2024-09-06 | 2024-09-19 23:59 |  | 2024-09-19 23:59 | New Burn WL | CKinsella | 2024-09-22 17:39 | CClark9 |  | No |  |  |  | ROE WL Mumbai | Jarrod Sedmak |  | 0 | 4 |  | L2 - Shift RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1011289 | O.1011289.01 | A.1011289.01.14 | BWI DC-D XPT | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 PRESSURE MANAGEMENT WELL D-WP1 | ENSIGN 963 | J.24.148341 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Not Started | In Progress | 2024-10-01 | 2024-09-26 |  | 2024-10-01 | 2024-10-14 23:59 |  | 2024-10-14 23:59 | New Burn WL | MElsanousi | 2024-08-30 13:34 | MElsanousi |  | No |  |  |  | ROE WL Mumbai | Jarrod Sedmak |  | 0 | 2 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1011289 | O.1011289.01 | A.1011289.01.07 | BWI DC:D-WP2 XPT; PEX-FMI | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 PRESSURE MANAGEMENT WELL D-WP1 | ENSIGN 963 | J.24.077372 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2023-12-01 | 2024-11-01 |  | 2024-11-05 | 2024-11-18 23:59 |  | 2024-11-18 23:59 | New Burn WL | CKinsella | 2024-08-29 11:40 | MElsanousi |  | No |  |  |  | ROE WL Mumbai | Jarrod Sedmak |  | 0 | 2 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1011289 | O.1011289.01 | A.1011289.01.04 | CVX BWI CCS D-WI1ST1 | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 WATER INJECTION WELL D-WI1, GORGON PLANT CO2 PRESSURE MANAGEMENT WELL D-WP1, GORGON PLANT CO2 PRESSURE MANAGEMENT WELL D-WP2 | ENSIGN 963 | J.24.022710 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Required | In Progress | 2024-07-01 | 2024-07-01 |  | 2024-07-01 | 2024-08-15 23:59 |  | 2024-08-15 23:59 | New Burn WL | VOliveira5 | 2024-08-15 15:46 | CKinsella |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 4 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 3 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1011289 | O.1011289.01 | A.1011289.01.05 | CCS BWI | CHEVRON APG ABU PERTH. | ​D-WI3 | ENSIGN 963 | J.24.057193 | RPE | ES-CH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | Design Completed | 2024-08-24 22:00 | 2024-08-25 |  | 2024-08-25 | 2024-09-10 23:59 |  | 2024-09-10 21:59 | New Burn WL | MElsanousi | 2024-08-15 15:45 | CKinsella |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 1 |  | L0 - No RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 2 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1011289 | O.1011289.01 | A.1011289.01.06 | CVX BWI CCS D-WI3 | CHEVRON APG ABU PERTH. | D-WP2 ST1, ​D-WI1 ST1, ​D-WP1 ST1 | ENSIGN 963 | J.24.077370 | RPE | ES-CH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2024-09-20 | 2024-09-20 |  | 2024-09-20 | 2024-11-04 23:59 |  | 2024-11-04 23:59 | New Burn WL | CKinsella | 2024-08-15 15:45 | CKinsella |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1011289 | O.1011289.01 | A.1011289.01.12 | CVX BWI CCS E-WP4ST1 | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 PRESSURE MANAGEMENT WELL E-WP4 | ENSIGN 963 | J.24.077377 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-01-10 | 2025-01-10 |  | 2025-01-10 | 2025-02-24 23:59 |  | 2025-02-24 23:59 | New Burn WL | CKinsella | 2024-08-08 09:55 | CKinsella |  | No |  |  |  | ROE WL Mumbai | Jarrod Sedmak |  | 0 | 1 |  | L2 - Shift RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1011289 | O.1011289.01 | A.1011289.01.11 | CVX BWI CCS E-WP3ST1 | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 PRESSURE MANAGEMENT WELL E-WP3 | ENSIGN 963 | J.24.077376 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-01-01 | 2025-01-01 |  | 2025-01-01 | 2025-02-15 23:59 |  | 2025-02-15 23:59 | New Burn WL | CKinsella | 2024-08-08 09:55 | CKinsella |  | No |  |  |  | ROE WL Mumbai | Jarrod Sedmak |  | 0 | 1 |  | L2 - Shift RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1011289 | O.1011289.01 | A.1011289.01.10 | CVX BWI CCS E-WI4 | CHEVRON APG ABU PERTH. |  | ENSIGN 963 | J.24.077375 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-12-31 | 2024-12-31 |  | 2024-12-31 | 2025-02-14 23:59 |  | 2025-02-14 23:59 | New Burn WL | CKinsella | 2024-08-08 09:55 | CKinsella |  | No |  |  |  | ROE WL Mumbai | Jarrod Sedmak |  | 0 | 1 |  | L2 - Shift RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1011289 | O.1011289.01 | A.1011289.01.13 | CVX GS2 | CHEVRON APG ABU PERTH. |  | ENSIGN 963 | J.24.082607 | RPI | PS-SLK-Ops | Low | Cancelled | Execute - PSD |  | Not Started | Not Started | Not Started |  | 2024-06-25 |  | 2024-07-10 | 2024-08-25 23:59 |  |  | New Burn WL | MElsanousi | 2024-05-22 19:39 | MElsanousi |  | No |  |  |  |  | Peter Roche |  | 0 | 0 |  | L0 - No RO |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1011289 | O.1011289.01 | A.1011289.01.01 | E-WI2 HSD | CHEVRON APG ABU PERTH. | E-WI2 | ENSIGN 963 | J.21.108840 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-12-20 |  | 2021-01-15 | 2021-02-06 23:59 |  |  | New Burn WL | crowand | 2022-10-03 09:50 | FDPSystemUser |  | No |  |  |  |  | James Cade |  | 519800.8 |  |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 | [7 empty] | Bilal Ahmad | WL Production Services
P.1011229 | O.1011229.02 | A.1011229.02.01 | N2 pumping - Horseshoe | ARMOUR ENERGY (SURAT BASIN) PTY LTD | HORSESHOE #2 | Rigless Australia - 1 | J.20.063623 | RPS | STM-MPUMP | InComplete | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-13 11:00 | 2020-12-13 |  | 2020-12-13 | 2020-12-18 23:59 |  | 2020-12-19 10:59 | AUS East Coast WS | SKanaan | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Tony Huynh |  | 33154.78 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1011229 | O.1011229.01 | A.1011229.01.01 | N2 and fluid pumping | ARMOUR ENERGY (SURAT BASIN) PTY LTD | WARROON 1 | Rigless Australia - 1 | J.20.063625 | RPS | STM-MPUMP | InComplete | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2020-11-28 11:00 | 2020-11-26 |  | 2020-11-28 | 2020-12-03 23:59 |  | 2020-12-04 10:59 | AUS East Coast WS | SKanaan | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Tony Huynh |  | 60975.18 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1011182 | O.1011182.01 | A.1011182.01.09 | Q1 2022 Rentals | WOODSIDE ENERGY LTD |  | Ocean Apex | J.21.109530 | RPS | SMS-MATSAL | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2022-01-01 |  | 2022-01-01 | 2022-03-31 23:59 |  |  | AUS West Coast WS | SKanaan | 2022-10-03 12:23 | FDPSystemUser |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 0 |  |  |  | 50 | 33.3 | 100 | 25 | 45 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1011182 | O.1011182.01 | A.1011182.01.12 | XNA-02 | WOODSIDE ENERGY LTD | Xena-2 | Ocean Apex | J.22.110800 | RPS | SMS-OHGP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-05-26 | 2022-06-25 |  | 2022-07-10 | 2022-07-19 23:59 |  | 2022-07-24 23:59 | AUS West Coast WS | radinegara | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Ramadhani Adi Negara |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1011182 | O.1011182.01 | A.1011182.01.11 | Q3 2022 rentals | WOODSIDE ENERGY LTD |  | Ocean Apex | J.22.110782 | RPS | SMS-MATSAL | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-07-01 |  | 2022-07-01 | 2022-09-30 23:59 |  |  | AUS West Coast WS | SKanaan | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 0 |  |  |  | 50 | 33.3 | 100 | 25 | 45 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1011182 | O.1011182.01 | A.1011182.01.10 | Q2 2022 Rentals | WOODSIDE ENERGY LTD |  | Ocean Apex | J.22.110780 | RPS | SMS-MATSAL | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2022-04-01 |  | 2022-04-01 | 2022-06-22 23:59 |  |  | AUS West Coast WS | SKanaan | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Yuxiao Hou |  | 0 | 0 |  |  |  | 50 | 33.3 | 100 | 25 | 45 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1011182 | O.1011182.01 | A.1011182.01.08 | Q4 Rental | WOODSIDE ENERGY LTD |  | Ocean Apex | J.21.109397 | RPS | STM-DSL | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2021-10-01 |  | 2021-10-01 | 2021-12-31 23:59 |  |  | AUS West Coast WS | SKanaan | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Zuyue Zhang |  | 0 | 0 |  |  |  | 50 | 33.3 | 100 | 25 | 45 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1011182 | O.1011182.01 | A.1011182.01.07 | non operational activity | WOODSIDE ENERGY LTD |  | Ocean Apex | J.21.109368 | RPS | STM-PERS | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-07-05 | 2021-02-24 |  | 2021-02-24 | 2021-12-31 23:59 |  | 2021-12-31 23:59 | AUS West Coast WS | ATanha | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Tony Huynh |  | 0 | 0 |  |  |  | 75 | 66.7 | 100 | 50 | 70 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1011182 | O.1011182.01 | A.1011182.01.06 | Feb Personnel charges | WOODSIDE ENERGY LTD |  | Ocean Apex | J.21.109331 | RPS | STM-DSL,STM-PERS | Low | Confirmed | Design - CEC |  | Not Required | Not Required | In Progress |  | 2021-02-19 |  | 2021-02-19 | 2021-05-31 23:59 |  |  | AUS West Coast WS | SKanaan | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Tony Huynh |  | 0 | 0 |  |  |  | 75 | 66.7 | 100 | 25 | 65 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1011182 | O.1011182.01 | A.1011182.01.03 | LDA-01 | WOODSIDE ENERGY LTD | LDA01 | Ocean Apex | J.21.109328 | RPS | SMS-OHGP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-07 | 2021-10-01 |  | 2021-12-17 | 2021-12-26 23:59 |  | 2022-01-21 23:59 | AUS West Coast WS | THuynh | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Rizaldi Rachman |  | 2988766 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1011182 | O.1011182.01 | A.1011182.01.05 | SIT | WOODSIDE ENERGY LTD |  | Ocean Apex | J.21.109319 | RPS | SMS-OHGP | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-04-16 08:00 | 2020-12-31 |  | 2021-04-16 | 2021-04-30 23:59 |  | 2021-05-01 07:59 | AUS West Coast WS | THuynh | 2022-10-03 11:34 | FDPSystemUser |  | No |  |  |  |  | Tony Huynh |  | 0 | 1 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1011182 | O.1011182.01 | A.1011182.01.02 | GDA-04 SMS pumping | WOODSIDE ENERGY LTD | GDA-04 | Ocean Apex |  | RPS | SMS-OHGP | Medium | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2021-08-31 | 2021-06-17 |  | 2021-08-31 | 2021-09-14 23:59 |  | 2021-09-14 23:59 | AUS West Coast WS | THuynh | 2022-09-03 05:59 | walfaro |  | No |  |  |  |  | Zuyue Zhang |  | 0 | 1 |  |  |  | 75 | 33.3 | 0 | 25 | 45 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1011182 | O.1011182.01 | A.1011182.01.01 | GDA-03 Pumping SMS | WOODSIDE ENERGY LTD | GDA-03 | Ocean Apex |  | RPS | SMS-OHGP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-25 08:00 | 2021-04-01 |  | 2021-07-25 | 2021-08-08 23:59 |  | 2021-08-09 07:59 | AUS West Coast WS | THuynh | 2022-09-03 05:59 | walfaro |  | No |  |  |  |  | Tony Huynh |  | 261000 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1011182 | O.1011182.01 | A.1011182.01.04 | GDA-05 SMS pumping | WOODSIDE ENERGY LTD | GDA-05 | Ocean Apex |  | RPS | SMS-OHGP | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2021-11-01 | 2021-08-13 |  | 2021-10-22 | 2021-11-05 23:59 |  | 2021-11-15 23:59 | AUS West Coast WS | THuynh | 2022-09-03 05:59 | walfaro |  | No |  |  |  |  | Rizaldi Rachman |  | 0 | 1 |  |  |  | 75 | 50 | 0 | 50 | 55 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Production Services
P.1011181 | O.1011181.99 | A.1011181.99.01 | Barayulah 2 | SANTOS LIMITED | BARYULAH 2 | Wild Desert Rig 22 | J.21.109520 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-05 01:00 | 2021-10-06 |  | 2021-10-06 10:00 | 2021-10-07 09:59 |  | 2021-10-07 00:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:14 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 11702.37 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.98 | A.1011181.98.03 | Daralingie 11 Plug 1C | SANTOS LIMITED | DARALINGIE 11 | Wild Desert Rig 16 | J.21.109519 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2021-09-02 10:00 | 2021-09-02 23:00 |  | 2021-09-02 23:00 | 2021-09-03 22:59 |  | 2021-09-08 14:25 | AUS East Coast WS | GVang2 | 2022-10-03 15:14 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 11484.24 | 5 |  |  |  | 71.9 | 41.7 | 0 | 50 | 51.2 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.98 | A.1011181.98.02 | Daralingie 11 Plug 1B | SANTOS LIMITED | DARALINGIE 11 | Wild Desert Rig 16 | J.21.109276 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-30 22:00 | 2021-08-30 23:00 |  | 2021-08-30 23:00 | 2021-08-31 22:59 |  | 2021-08-31 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 11559.21 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.98 | A.1011181.98.01 | Daralingie 11 Plug 1 | SANTOS LIMITED | DARALINGIE 11 | Wild Desert Rig 16 | J.21.109267 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-27 | 2021-08-27 |  | 2021-08-27 | 2021-08-27 23:59 |  | 2021-08-27 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 23261.58 | 1 |  |  |  | 81.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.97 | A.1011181.97.02 | 4 1/2" Intermediate | SANTOS LIMITED | Moorari 22 | SLR RIG 183 | J.21.109517 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-08 11:00 | 2021-12-08 01:00 |  | 2021-12-09 01:00 | 2021-12-10 00:59 |  | 2021-12-11 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:13 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 22908.59 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.97 | A.1011181.97.01 | 7 5/8" Surface | SANTOS LIMITED | Moorari 22 | SLR RIG 183 | J.21.109516 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-30 11:00 | 2021-11-30 |  | 2021-11-30 01:00 | 2021-12-02 00:59 |  | 2021-12-03 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:13 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 22681.98 | 1 |  |  |  | 78.1 | 25 | 0 | 50 | 48.8 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.96 | A.1011181.96.01 | 7 5/8" Surface | SANTOS LIMITED | Moorari 21 | SLR RIG 183 | J.21.109515 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-15 11:00 | 2021-11-16 |  | 2021-11-16 01:00 | 2021-11-17 00:59 |  | 2021-11-18 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:13 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 27922.29 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.96 | A.1011181.96.02 | 4 1/2" Intermediate | SANTOS LIMITED | MOORARI 021 | SLR RIG 183 | J.21.109261 | WCF | PRI-INTER | Low | Unconfirmed - 50% | Design - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-20 11:00 | 2021-11-20 01:00 |  | 2021-11-21 01:00 | 2021-11-22 00:59 |  | 2021-11-23 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 32828.83 | 1 |  |  |  | 78.1 | 25 | 0 | 50 | 48.8 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.95 | A.1011181.95.02 | 7" Intermediate | SANTOS LIMITED | Barrolka 21 | ENSIGN 974 | J.21.109514 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-18 | 2021-12-18 |  | 2021-12-19 | 2021-12-19 23:59 |  | 2021-12-20 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:13 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 25190.44 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.95 | A.1011181.95.03 | Production | SANTOS LIMITED | BARROLKA 21 | ENSIGN 974 | J.21.109316 | WCF | PRI-LONG | Low | Confirmed | Design - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-31 12:00 | 2021-12-31 |  | 2021-12-31 12:00 | 2022-01-01 12:00 |  | 2022-01-01 12:00 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 23932.2 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.95 | A.1011181.95.01 | 9 5/8" Surface | SANTOS LIMITED | Barrolka 21 | ENSIGN 974 | J.21.109270 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-11 | 2021-12-11 23:00 |  | 2021-12-11 23:00 | 2021-12-12 22:59 |  | 2021-12-12 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 24351.88 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.94 | A.1011181.94.03 | Barrolka 24 Production | SANTOS LIMITED | Barrolka 24 | ENSIGN 974 | J.21.109527 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-11 12:00 | 2021-12-11 |  | 2021-12-11 12:00 | 2021-12-12 12:00 |  | 2021-12-12 12:00 | AUS East Coast WS | GVang2 | 2022-10-03 15:16 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 23741.16 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.94 | A.1011181.94.02 | 7" Intermediate | SANTOS LIMITED | Barrolka 24 | ENSIGN 974 | J.21.109279 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-03 | 2021-12-03 |  | 2021-12-03 | 2021-12-03 23:59 |  | 2021-12-03 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 49168.87 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.94 | A.1011181.94.01 | 9 5/8" Surface | SANTOS LIMITED | Barrolka 24 | ENSIGN 974 | J.21.109277 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-21 | 2021-11-20 23:00 |  | 2021-11-20 23:00 | 2021-11-21 22:59 |  | 2021-11-21 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 26942.94 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.93 | A.1011181.93.02 | 4.5" Production Job | SANTOS LIMITED | Kanook South 1 | Ensign 967 | J.21.109275 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-30 23:00 | 2021-12-01 06:00 |  | 2021-11-30 08:00 | 2021-12-01 16:59 |  | 2021-12-01 22:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 46057.19 | 1 |  |  |  | 78.1 | 25 | 0 | 50 | 48.8 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.93 | A.1011181.93.01 | 7 5/8 Surface | SANTOS LIMITED | Kanook South 1 | Ensign 967 | J.21.109256 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-19 11:00 | 2021-11-20 |  | 2021-11-20 | 2021-11-20 23:59 |  | 2021-11-22 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 13775.91 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.92 | A.1011181.92.01 | 9 5/8 Surface | SANTOS LIMITED | Cook East 1 | Ensign 967 | J.21.109513 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-08 07:00 | 2021-12-08 |  | 2021-12-08 20:00 | 2021-12-09 19:59 |  | 2021-12-11 06:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:13 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 14553.29 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.92 | A.1011181.92.02 | 5.5" Production Job | SANTOS LIMITED | Cook East 1 | Ensign 967 | J.21.109264 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-17 11:00 | 2021-12-18 06:00 |  | 2021-12-18 08:00 | 2021-12-18 16:59 |  | 2021-12-20 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 13265.68 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.91 | A.1011181.91.02 | Waukatanna 2 Plug 1B | SANTOS LIMITED | Waukatanna 2 | Wild Desert Rig 16 | J.21.109295 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-17 23:00 | 2021-10-18 |  | 2021-10-18 | 2021-10-18 23:59 |  | 2021-10-18 23:59 | AUS East Coast WS | ALyons | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 9135.19 | 0 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.91 | A.1011181.91.01 | Waukatanna 2 Plug 1A | SANTOS LIMITED | Waukatanna 2 | Wild Desert Rig 16 | J.21.109257 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-16 23:00 | 2021-10-17 |  | 2021-10-17 | 2021-10-17 23:59 |  | 2021-10-17 22:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 11144.48 | 0 |  |  |  | 81.3 | 33.3 | 0 | 25 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.90 | A.1011181.90.01 | Dummy | SANTOS LIMITED | Well #1 | Wild Desert Rig 16 | J.21.109512 | WCF | PRI-SURF | Low | Unconfirmed - 10% | Close - PSD |  | Not Started | In Progress | In Progress |  | 2021-10-27 23:00 |  | 2021-10-27 23:00 | 2021-10-28 22:59 |  |  | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:13 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.89 | A.1011181.89.01 | Dummy Job September | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.21.109263 | WCF | PRI-SURF,PRI-LONG,PRI-INTER | InComplete | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2021-09-24 23:00 |  | 2021-09-24 23:00 | 2021-09-25 22:59 |  |  | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.88 | A.1011181.88.01 | Dummy | SANTOS LIMITED | Well #1 | ENSIGN 971 | J.21.109511 | WCF | PRI-SURF | InComplete | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2021-07-25 |  | 2021-07-25 | 2021-07-25 23:59 |  |  | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:13 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.87 | A.1011181.87.01 | Dummy | SANTOS LIMITED | Well #1 | Ensign 967 | J.21.109510 | WCF | PRI-SURF | InComplete | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2021-07-30 23:00 |  | 2021-07-30 23:00 | 2021-07-31 22:59 |  |  | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:13 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.86 | A.1011181.86.01 | Dummy | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.21.109259 | WCF | PRI-SURF | InComplete | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2021-09-27 |  | 2021-09-27 | 2021-09-27 23:59 |  |  | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.85 | A.1011181.85.03 | Frostillicus 2 Liner Set | SANTOS LIMITED | Frostillicus 2 | SLR RIG 183 | J.21.109290 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-11-04 23:00 | 2021-11-04 20:00 |  | 2021-11-04 23:00 | 2021-11-05 10:59 |  | 2021-11-05 10:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 12839.92 | 1 |  |  |  | 81.3 | 33.3 | 0 | 62.5 | 55 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.85 | A.1011181.85.02 | 7" Intermediate | SANTOS LIMITED | Frostillicus 2 | SLR RIG 183 | J.21.109266 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-26 11:00 | 2021-10-26 01:00 |  | 2021-10-27 01:00 | 2021-10-28 00:59 |  | 2021-10-29 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 94234.61 | 1 |  |  |  | 81.3 | 16.7 | 0 | 75 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.85 | A.1011181.85.01 | 9-5/8" Surface | SANTOS LIMITED | Frostillicus 2 | SLR RIG 183 | J.21.109251 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-23 11:00 | 2021-10-24 |  | 2021-10-24 01:00 | 2021-10-25 00:59 |  | 2021-10-26 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 28094.19 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.84 | A.1011181.84.02 | 7" Intermediate | SANTOS LIMITED | Hobbes 4 | SLR RIG 183 | J.21.109262 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-14 22:00 | 2021-10-15 12:00 |  | 2021-10-15 12:00 | 2021-10-16 11:59 |  | 2021-10-17 21:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 67439.07 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.84 | A.1011181.84.01 | 9-5/8" Surface | SANTOS LIMITED | Hobbes 4 | SLR RIG 183 | J.21.109248 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-09 23:00 | 2021-10-09 22:00 |  | 2021-10-10 01:00 | 2021-10-11 00:59 |  | 2021-10-11 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 28094.19 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.83 | A.1011181.83.02 | 7" Intermediate | SANTOS LIMITED | McKinlay 24 | SLR RIG 183 | J.21.109509 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-26 | 2021-09-26 |  | 2021-09-26 | 2021-09-26 23:59 |  | 2021-09-26 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:12 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 59213.07 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.83 | A.1011181.83.01 | 9 5/8" Surface | SANTOS LIMITED | McKinlay 24 | SLR RIG 183 | J.21.109508 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-22 | 2021-09-22 |  | 2021-09-22 | 2021-09-22 23:59 |  | 2021-09-22 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:12 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 28094.19 | 1 |  |  |  | 81.3 | 33.3 | 0 | 62.5 | 55 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.82 | A.1011181.82.01 | 9 5/8" Surface | SANTOS LIMITED | Barrolka 22 | ENSIGN 974 | J.21.109254 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-04 | 2021-11-03 23:00 |  | 2021-11-03 23:00 | 2021-11-04 22:59 |  | 2021-11-04 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 38681.51 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.82 | A.1011181.82.02 | 7" Intermediate | SANTOS LIMITED | Barrolka 22 | ENSIGN 974 | J.21.109246 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-10 | 2021-11-10 |  | 2021-11-10 | 2021-11-10 23:59 |  | 2021-11-10 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 43680.94 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.81 | A.1011181.81.01 | Moomba 195 surface 9 5/8" | SANTOS LIMITED | MOOMBA 195 | ENSIGN 971 | J.21.109507 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-09 12:00 | 2021-10-10 02:00 |  | 2021-10-10 10:00 | 2021-10-11 01:59 |  | 2021-10-12 11:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:12 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 34745.61 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.81 | A.1011181.81.03 | Moomba 195 production | SANTOS LIMITED | MOOMBA 195 | ENSIGN 971 | J.21.109258 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-09 11:00 | 2021-11-10 |  | 2021-11-10 | 2021-11-10 23:59 |  | 2021-11-12 10:59 | AUS East Coast WS | ALyons | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 22778.42 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.81 | A.1011181.81.02 | Moomba 195 Intermediate 7" | SANTOS LIMITED | MOOMBA 195 | ENSIGN 971 | J.21.109244 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-26 13:00 | 2021-10-27 02:00 |  | 2021-10-27 02:00 | 2021-10-28 01:59 |  | 2021-10-29 12:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 100799.97 | 0 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.80 | A.1011181.80.02 | 4.5" Production Job | SANTOS LIMITED | Chimera 1 | Ensign 967 | J.21.109265 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-09 23:00 | 2021-11-10 06:00 |  | 2021-11-13 08:00 | 2021-11-13 16:59 |  | 2021-11-13 22:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 50517.55 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.80 | A.1011181.80.01 | 7 5/8 Surface | SANTOS LIMITED | Chimera 1 | Ensign 967 | J.21.109242 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-02 11:00 | 2021-11-03 |  | 2021-11-03 | 2021-11-03 23:59 |  | 2021-11-05 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 31983.59 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.79 | A.1011181.79.01 | 7 5/8 Surface | SANTOS LIMITED | Llama 1 | Ensign 967 | J.21.109506 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-20 | 2021-10-20 |  | 2021-10-20 | 2021-10-20 23:59 |  | 2021-10-21 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:12 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 32061.75 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.79 | A.1011181.79.02 | 4.5" Production Job | SANTOS LIMITED | Llama 1 | Ensign 967 | J.21.109249 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-26 | 2021-10-26 06:00 |  | 2021-10-26 08:00 | 2021-10-26 16:59 |  | 2021-10-27 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 49308.1 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.78 | A.1011181.78.01 | 9 5/8" Surface | SANTOS LIMITED | Coolah 13 | ENSIGN 974 | J.21.109504 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-13 01:00 | 2021-07-12 15:00 |  | 2021-07-12 15:00 | 2021-07-13 14:59 |  | 2021-07-14 00:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:12 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 26123.96 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.78 | A.1011181.78.03 | 3-1/2" Production | SANTOS LIMITED | Coolah 13 | ENSIGN 974 | J.21.109268 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-28 | 2021-07-28 |  | 2021-07-28 | 2021-07-28 23:59 |  | 2021-07-28 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 51186.65 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.78 | A.1011181.78.02 | 7" Intermediate | SANTOS LIMITED | Coolah 13 | ENSIGN 974 | J.21.109253 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-18 10:00 | 2021-07-18 |  | 2021-07-18 | 2021-07-18 23:59 |  | 2021-07-19 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 51507.88 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.77 | A.1011181.77.01 | Tirrawarra 61 Recompletion | SANTOS LIMITED | Tirrawarra 61 | Wild Desert Rig 6 | J.21.109250 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-30 22:00 | 2021-06-30 23:00 |  | 2021-06-30 23:00 | 2021-07-01 22:59 |  | 2021-07-01 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 11702.37 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.76 | A.1011181.76.01 | dummy job | SANTOS LIMITED | Well #1 | ENSIGN 971 | J.21.109260 | WCF | PRI-SURF | InComplete | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2021-09-03 23:00 |  | 2021-09-03 23:00 | 2021-09-04 22:59 |  |  | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.75 | A.1011181.75.01 | 9 5/8" Surface | SANTOS LIMITED | McKinlay 20 | SLR RIG 183 | J.21.109255 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-17 | 2021-08-17 |  | 2021-08-17 | 2021-08-17 23:59 |  | 2021-08-17 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 28094.19 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.75 | A.1011181.75.02 | 7" Intermediate | SANTOS LIMITED | McKinlay 20 | SLR RIG 183 | J.21.109241 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-22 | 2021-08-22 |  | 2021-08-22 | 2021-08-22 23:59 |  | 2021-08-22 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 69662.69 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.74 | A.1011181.74.01 | 9 5/8" Surface | SANTOS LIMITED | Mckinlay 21 | SLR RIG 183 | J.21.109247 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-29 | 2021-08-29 |  | 2021-08-29 | 2021-08-29 23:59 |  | 2021-08-29 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 28094.19 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.74 | A.1011181.74.02 | 7" Intermediate | SANTOS LIMITED | Mckinlay 21 | SLR RIG 183 | J.21.109234 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-05 | 2021-09-05 |  | 2021-09-05 | 2021-09-05 23:59 |  | 2021-09-05 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 59213.07 | 1 |  |  |  | 78.1 | 25 | 0 | 50 | 48.8 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.73 | A.1011181.73.02 | 7" Intermediate | SANTOS LIMITED | McKinlay 23 | SLR RIG 183 | J.21.109237 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-12 11:00 | 2021-09-12 15:00 |  | 2021-09-13 15:00 | 2021-09-14 14:59 |  | 2021-09-15 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 59213.07 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.73 | A.1011181.73.01 | 9 5/8" Surface | SANTOS LIMITED | McKinlay 23 | SLR RIG 183 | J.21.109235 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-10 | 2021-09-10 |  | 2021-09-10 | 2021-09-10 23:59 |  | 2021-09-10 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 28094.19 | 1 |  |  |  | 78.1 | 25 | 0 | 50 | 48.8 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.72 | A.1011181.72.02 | 7" Intermediate | SANTOS LIMITED | Coolah 17 | ENSIGN 974 | J.21.109503 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-03 12:00 | 2021-10-03 01:00 |  | 2021-10-04 02:00 | 2021-10-05 01:59 |  | 2021-10-06 11:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:12 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 37021.8 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.72 | A.1011181.72.01 | 9 5/8" Surface | SANTOS LIMITED | Coolah 17 | ENSIGN 974 | J.21.109502 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-26 | 2021-09-25 23:00 |  | 2021-09-26 | 2021-09-26 23:59 |  | 2021-09-26 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:12 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 68292.56 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.72 | A.1011181.72.03 | Coolah 17 Production | SANTOS LIMITED | Coolah 17 | ENSIGN 974 | J.21.109293 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-13 10:00 | 2021-10-13 |  | 2021-10-13 10:00 | 2021-10-14 23:59 |  | 2021-10-14 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 57828.3 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.71 | A.1011181.71.02 | 7" Intermediate | SANTOS LIMITED | Coolah 16 | ENSIGN 974 | J.21.109501 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-16 11:00 | 2021-09-16 01:00 |  | 2021-09-17 01:00 | 2021-09-18 00:59 |  | 2021-09-19 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:11 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 37021.8 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.71 | A.1011181.71.01 | 9 5/8" Surface | SANTOS LIMITED | Coolah 16 | ENSIGN 974 | J.21.109500 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-11 | 2021-09-11 |  | 2021-09-11 | 2021-09-11 23:59 |  | 2021-09-11 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:11 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 34146.28 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.70 | A.1011181.70.02 | 7" Intermediate | SANTOS LIMITED | Coolah 15 | ENSIGN 974 | J.21.109499 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-26 | 2021-08-26 |  | 2021-08-26 | 2021-08-26 23:59 |  | 2021-08-26 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:11 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 37021.8 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.70 | A.1011181.70.03 | Coolah 15 Production | SANTOS LIMITED | Coolah 15 | ENSIGN 974 | J.21.109278 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-05 10:00 | 2021-09-05 |  | 2021-09-05 10:00 | 2021-09-05 23:59 |  | 2021-09-05 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 38617.72 | 2 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.70 | A.1011181.70.01 | 9 5/8" Surface | SANTOS LIMITED | Coolah 15 | ENSIGN 974 | J.21.109252 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-18 | 2021-08-18 |  | 2021-08-18 | 2021-08-18 23:59 |  | 2021-08-18 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 34146.28 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.69 | A.1011181.69.02 | 5-1/2" Production | SANTOS LIMITED | LIGER 1 | ENSIGN 971 | J.21.109498 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-28 | 2021-09-28 |  | 2021-09-28 | 2021-09-28 23:59 |  | 2021-09-28 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:11 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 69879.55 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.69 | A.1011181.69.01 | 9-5/8" Surface | SANTOS LIMITED | LIGER 1 | ENSIGN 971 | J.21.109497 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-14 | 2021-09-14 01:00 |  | 2021-09-14 01:00 | 2021-09-15 00:59 |  | 2021-09-14 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:11 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 25478.48 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.68 | A.1011181.68.02 | Durham Downs North 10 Intermediate | SANTOS LIMITED | DURHAM DOWNS NORTH 10 (DEVJ) | ENSIGN 971 | J.21.109496 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-13 | 2021-08-13 |  | 2021-08-13 01:00 | 2021-08-14 00:59 |  | 2021-08-13 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:11 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 51414.36 | 0 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.68 | A.1011181.68.01 | 9 5/8" Surface Cement job | SANTOS LIMITED | DURHAM DOWNS NORTH 10 (DEVJ) | ENSIGN 971 | J.21.109230 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-03 | 2021-08-03 |  | 2021-08-03 | 2021-08-03 23:59 |  | 2021-08-03 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 35124.78 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.67 | A.1011181.67.02 | 3.5" Production Job | SANTOS LIMITED | Legbar 1 | Ensign 967 | J.21.109495 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-17 | 2021-10-17 07:00 |  | 2021-10-17 09:00 | 2021-10-17 17:59 |  | 2021-10-17 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:11 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 49308.1 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.67 | A.1011181.67.01 | 7 5/8 Surface | SANTOS LIMITED | Legbar 1 | Ensign 967 | J.21.109245 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-08 01:00 | 2021-10-09 |  | 2021-10-09 | 2021-10-09 23:59 |  | 2021-10-10 00:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 32061.75 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.66 | A.1011181.66.02 | 5.5" Production Job | SANTOS LIMITED | MERLIN 1 | Ensign 967 | J.21.109494 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-03 | 2021-10-02 |  | 2021-10-02 | 2021-10-02 23:59 |  | 2021-10-04 00:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:11 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 49308.1 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.66 | A.1011181.66.01 | 9-5/8 Surface | SANTOS LIMITED | MERLIN 1 | Ensign 967 | J.21.109243 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-22 | 2021-09-22 |  | 2021-09-22 | 2021-09-22 23:59 |  | 2021-09-22 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 35218.45 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.65 | A.1011181.65.01 | 7 5/8 Surface | SANTOS LIMITED | BEARCAT 2 | Ensign 967 | J.21.109493 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-05 | 2021-09-05 |  | 2021-09-05 00:10 | 2021-09-06 00:09 |  | 2021-09-05 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:11 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 31354.29 | 1 |  |  |  | 78.1 | 25 | 0 | 50 | 48.8 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.65 | A.1011181.65.02 | Bearcat 2 production | SANTOS LIMITED | BEARCAT 2 | Ensign 967 | J.21.109231 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-16 | 2021-09-16 |  | 2021-09-16 | 2021-09-16 23:59 |  | 2021-09-16 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 65059.06 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.64 | A.1011181.64.01 | 7 5/8 Surface | SANTOS LIMITED | Cherokee 2 | Ensign 967 | J.21.109492 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-22 | 2021-08-22 |  | 2021-08-22 | 2021-08-22 23:59 |  | 2021-08-22 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:10 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 32018.04 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.64 | A.1011181.64.02 | 3.5" Production Job | SANTOS LIMITED | Cherokee 2 | Ensign 967 | J.21.109227 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-29 | 2021-08-29 |  | 2021-08-29 | 2021-08-29 23:59 |  | 2021-08-29 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 49308.1 | 1 |  |  |  | 78.1 | 25 | 0 | 50 | 48.8 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.63 | A.1011181.63.03 | Daralingie 13 Plug 1D | SANTOS LIMITED | Daralingie 13 | Wild Desert Rig 16 | J.21.109490 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-24 10:00 | 2021-08-24 23:00 |  | 2021-08-24 23:00 | 2021-08-25 22:59 |  | 2021-08-26 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:10 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 11484.24 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.63 | A.1011181.63.01 | Daralingie 13 Plug 1 | SANTOS LIMITED | Daralingie 13 | Wild Desert Rig 16 | J.21.109236 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-20 | 2021-08-20 |  | 2021-08-20 | 2021-08-20 23:59 |  | 2021-08-20 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 11702.37 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.63 | A.1011181.63.02 | Daralingie 13 Plug 1B | SANTOS LIMITED | Daralingie 13 | Wild Desert Rig 16 | J.21.109222 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-21 22:00 | 2021-08-21 23:00 |  | 2021-08-21 23:00 | 2021-08-22 22:59 |  | 2021-08-22 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 11559.21 | 1 |  |  |  | 81.3 | 33.3 | 0 | 62.5 | 55 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.62 | A.1011181.62.02 | 7" Intermediate | SANTOS LIMITED | McKinlay 22 | SLR RIG 183 | J.21.109489 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-06 | 2021-08-06 |  | 2021-08-06 | 2021-08-06 23:59 |  | 2021-08-06 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:10 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 59213.07 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.62 | A.1011181.62.03 | McKinlay 22 Liner set | SANTOS LIMITED | McKinlay 22 | SLR RIG 183 | J.21.109272 | WCF | CMT-EQPRNT, PRI-LIN | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-08-11 | 2021-08-11 |  | 2021-08-11 | 2021-08-11 23:59 |  | 2021-08-11 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 8219.26 | 0 |  |  |  | 81.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.62 | A.1011181.62.01 | 7 5/8" Surface | SANTOS LIMITED | McKinlay 22 | SLR RIG 183 | J.21.109217 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-27 | 2021-07-27 |  | 2021-07-27 | 2021-07-27 23:59 |  | 2021-07-27 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 28094.19 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.61 | A.1011181.61.01 | Dummy | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.21.109488 | WCF | PRI-SURF | InComplete | Cancelled | Close - PSD |  | Not Required | In Progress | In Progress |  | 2021-07-25 23:00 |  | 2021-07-25 23:00 | 2021-07-26 22:59 |  |  | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:10 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 0 | 1 |  |  |  | 50 | 0 | 0 | 0 | 20 |  | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.60 | A.1011181.60.02 | Durham Downs North 9 Intermediate | SANTOS LIMITED | Durham Downs 9 | ENSIGN 971 | J.21.109219 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-07 | 2021-07-07 |  | 2021-07-07 | 2021-07-07 23:59 |  | 2021-07-07 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 51414.36 | 0 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.60 | A.1011181.60.01 | 9 5/8" Surface Cement job | SANTOS LIMITED | Durham Downs 9 | ENSIGN 971 | J.21.109218 | WCF | PRI-SURF | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-23 10:00 | 2021-06-23 01:00 |  | 2021-06-23 09:00 | 2021-06-24 00:59 |  | 2021-06-24 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 39190.2 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.59 | A.1011181.59.02 | 7" Intermediate | SANTOS LIMITED | Coolah 14 | ENSIGN 974 | J.21.109232 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-07 | 2021-08-07 |  | 2021-08-07 | 2021-08-07 23:59 |  | 2021-08-07 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 40200.59 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.59 | A.1011181.59.01 | 9 5/8" Surface | SANTOS LIMITED | Coolah 14 | ENSIGN 974 | J.21.109214 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-01 | 2021-08-01 |  | 2021-08-01 | 2021-08-01 23:59 |  | 2021-08-01 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 22930.39 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.58 | A.1011181.58.01 | 7 5/8 Surface | SANTOS LIMITED | Cherokee 3 | Ensign 967 | J.21.109487 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-08 | 2021-08-08 |  | 2021-08-08 | 2021-08-08 23:59 |  | 2021-08-08 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:10 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 32297.79 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.58 | A.1011181.58.02 | 3.5" Production Job | SANTOS LIMITED | Cherokee 3 | Ensign 967 | J.21.109233 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-17 | 2021-08-17 |  | 2021-08-17 | 2021-08-17 23:59 |  | 2021-08-17 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 70018.65 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.57 | A.1011181.57.01 | 9 5/8" Surface | SANTOS LIMITED |  | Ensign 967 | J.21.109215 | WCF | PRI-SURF | InComplete | Cancelled | Close - PSD |  | Not Required | In Progress | In Progress |  | 2021-06-27 23:00 |  | 2021-06-28 23:00 | 2021-06-29 22:59 |  |  | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.56 | A.1011181.56.01 | 9 5/8" Surface | SANTOS LIMITED | Well #1 | ENSIGN 971 | J.21.109228 | WCF | PRI-SURF | InComplete | Cancelled | Close - PSD |  | Not Required | In Progress | In Progress |  | 2021-05-27 23:00 |  | 2021-05-28 23:00 | 2021-05-29 22:59 |  |  | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.55 | A.1011181.55.01 | 9 5/8" Surface | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.21.109211 | WCF | PRI-SURF | InComplete | Cancelled | Close - PSD |  | Not Required | In Progress | In Progress |  | 2021-04-29 23:00 |  | 2021-04-30 23:00 | 2021-05-01 22:59 |  |  | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.54 | A.1011181.54.02 | 4.5" Production Job | SANTOS LIMITED | Boongala 3 | Ensign 967 | J.21.109486 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-04 | 2021-07-04 06:00 |  | 2021-07-04 08:00 | 2021-07-04 16:59 |  | 2021-07-05 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:10 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 43269.08 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.54 | A.1011181.54.01 | 7 5/8 Surface | SANTOS LIMITED | Boongala 3 | Ensign 967 | J.21.109225 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-25 10:00 | 2021-06-25 |  | 2021-06-25 | 2021-06-25 23:59 |  | 2021-06-26 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 19207.25 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.53 | A.1011181.53.02 | 4.5" Production Job Hot | SANTOS LIMITED | Dilchee 5 | Ensign 967 | J.21.109485 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-22 | 2021-06-21 17:00 |  | 2021-06-21 22:00 | 2021-06-22 06:59 |  | 2021-06-22 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:10 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 43269.08 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.53 | A.1011181.53.01 | 7 5/8 Surface | SANTOS LIMITED | Dilchee 5 | Ensign 967 | J.21.109224 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-11 10:00 | 2021-06-11 16:00 |  | 2021-06-11 16:00 | 2021-06-12 15:59 |  | 2021-06-13 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 19207.25 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.52 | A.1011181.52.02 | 4.5" Production Job | SANTOS LIMITED | Pira 4 | Ensign 967 | J.21.109484 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-17 11:00 | 2021-07-16 07:00 |  | 2021-07-16 08:00 | 2021-07-17 20:59 |  | 2021-07-19 14:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:09 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 23692.48 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.52 | A.1011181.52.01 | 7" Surface | SANTOS LIMITED | Pira 4 | Ensign 967 | J.21.109220 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-07 16:00 | 2021-07-07 16:00 |  | 2021-07-07 16:00 | 2021-07-08 15:59 |  | 2021-07-08 23:00 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 19207.25 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.51 | A.1011181.51.02 | 7" Intermediate | SANTOS LIMITED | Barrolka 23 | ENSIGN 974 | J.21.109483 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-24 01:00 | 2021-10-24 01:00 |  | 2021-10-24 01:00 | 2021-10-25 00:59 |  | 2021-10-25 00:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:09 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 42556.58 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.51 | A.1011181.51.01 | 9 5/8" Surface | SANTOS LIMITED | Barrolka 23 | ENSIGN 974 | J.21.109208 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-15 01:00 | 2021-10-15 |  | 2021-10-15 | 2021-10-15 23:59 |  | 2021-10-16 00:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 25662.85 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.51 | A.1011181.51.03 | Barrolka Contingency | SANTOS LIMITED | Barrolka M (App C) Gas UBDCF | ENSIGN 974 |  | WCF | PRI-LONG | InComplete | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-10-20 11:00 | 2021-10-21 |  | 2021-10-21 | 2021-10-21 23:59 |  | 2021-10-23 10:59 | AUS East Coast WS | GVang2 | 2021-07-04 17:52 | ALyons |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 56.3 | 0 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.50 | A.1011181.50.03 | Big Lake 154 Production | SANTOS LIMITED | Big Lake 154 | ENSIGN 974 | J.21.109505 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-02 | 2021-07-02 |  | 2021-07-02 | 2021-07-02 23:59 |  | 2021-07-02 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:12 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 42556.58 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.50 | A.1011181.50.01 | 9 5/8" Surface | SANTOS LIMITED | Big Lake 154 | ENSIGN 974 | J.21.109482 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-20 18:00 | 2021-06-19 17:00 |  | 2021-06-20 08:00 | 2021-06-21 07:59 |  | 2021-06-21 17:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:09 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 25662.85 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.50 | A.1011181.50.02 | 7" Intermediate | SANTOS LIMITED | Big Lake 154 | ENSIGN 974 | J.21.109221 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-27 10:00 | 2021-06-27 |  | 2021-06-27 | 2021-06-27 23:59 |  | 2021-06-28 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 42556.58 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.49 | A.1011181.49.02 | 4 1/2" Production | SANTOS LIMITED | Raven 6 | ENSIGN 971 | J.21.109481 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-15 11:00 | 2021-05-16 |  | 2021-05-16 | 2021-05-16 23:59 |  | 2021-05-18 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:09 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 40213.19 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.49 | A.1011181.49.01 | 7 5/8" Surface | SANTOS LIMITED | Raven 6 | ENSIGN 971 | J.21.109204 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-08 10:00 | 2021-05-08 01:00 |  | 2021-05-08 01:00 | 2021-05-09 00:59 |  | 2021-05-10 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 25515.59 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.48 | A.1011181.48.02 | 4 1/2" Production (hot) | SANTOS LIMITED | Raven 5 | ENSIGN 971 | J.21.109216 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-28 10:00 | 2021-05-28 |  | 2021-05-28 | 2021-05-28 23:59 |  | 2021-05-29 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 40781.3 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.48 | A.1011181.48.01 | 7 5/8" Surface | SANTOS LIMITED | Raven 5 | ENSIGN 971 | J.21.109213 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-21 10:00 | 2021-05-21 01:00 |  | 2021-05-21 01:00 | 2021-05-22 00:59 |  | 2021-05-24 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 26564.67 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.47 | A.1011181.47.01 | 7 5/8" Surface | SANTOS LIMITED | Gidgealpa 65 | SLR RIG 183 | J.21.109480 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-14 11:00 | 2021-07-14 |  | 2021-07-15 | 2021-07-15 23:59 |  | 2021-07-17 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:09 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 18430.61 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.47 | A.1011181.47.02 | 3 1/2" Production | SANTOS LIMITED | Gidgealpa 65 | SLR RIG 183 | J.21.109197 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-20 03:00 | 2021-07-20 |  | 2021-07-20 | 2021-07-20 23:59 |  | 2021-07-20 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 59213.07 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.46 | A.1011181.46.03 | Big Lake 153 Contingency Plug 1A and 1B | SANTOS LIMITED | Big Lake 153 | ENSIGN 974 | J.21.109239 | WCF | PRI-INTER, REM-PA | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-16 10:00 | 2021-06-16 |  | 2021-06-16 | 2021-06-16 23:59 |  | 2021-06-17 09:59 | AUS East Coast WS | GSingh54 | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 42556.58 | 1 |  |  |  | 81.3 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.46 | A.1011181.46.01 | 9 5/8" Surface | SANTOS LIMITED | Big Lake 153 | ENSIGN 974 | J.21.109209 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-04 10:00 | 2021-06-03 |  | 2021-06-03 | 2021-06-04 23:59 |  | 2021-06-05 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 25662.85 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.46 | A.1011181.46.02 | 7" Intermediate | SANTOS LIMITED | Big Lake 153 | ENSIGN 974 | J.21.109206 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-10 10:00 | 2021-06-10 |  | 2021-06-10 | 2021-06-10 23:59 |  | 2021-06-11 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 42556.58 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.45 | A.1011181.45.03 | Big Lake 153 | SANTOS LIMITED | Big Lake 157 | ENSIGN 974 | J.21.109491 | WCF | PRI-INTER,PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-30 11:00 | 2021-05-30 |  | 2021-05-31 | 2021-05-31 23:59 |  | 2021-06-02 10:59 | AUS East Coast WS | GSingh54 | 2022-10-03 15:10 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 42556.58 | 1 |  |  |  | 81.3 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.45 | A.1011181.45.01 | 9 5/8" Surface | SANTOS LIMITED | Big Lake 157 | ENSIGN 974 | J.21.109479 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-18 11:00 | 2021-05-18 |  | 2021-05-19 | 2021-05-19 23:59 |  | 2021-05-21 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:09 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 34146.28 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.45 | A.1011181.45.02 | 7" Intermediate | SANTOS LIMITED | Big Lake 157 | ENSIGN 974 | J.21.109210 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-24 11:00 | 2021-05-24 |  | 2021-05-25 | 2021-05-25 23:59 |  | 2021-05-27 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 42556.58 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.44 | A.1011181.44.02 | 4 1/2" Production | SANTOS LIMITED | Moonanga 2 | ENSIGN 971 | J.21.109207 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-10 10:00 | 2021-06-10 |  | 2021-06-10 | 2021-06-10 23:59 |  | 2021-06-12 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 69879.55 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.44 | A.1011181.44.01 | 7 5/8" Surface | SANTOS LIMITED | Moonanga 2 | ENSIGN 971 | J.21.109194 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-02 11:00 | 2021-06-03 |  | 2021-06-03 | 2021-06-03 23:59 |  | 2021-06-05 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:23 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 25478.48 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.43 | A.1011181.43.02 | 3.5" Production Job | SANTOS LIMITED | Leghorn 2 | Ensign 967 | J.21.109478 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-08-05 | 2021-08-05 |  | 2021-08-05 | 2021-08-05 23:59 |  | 2021-08-05 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:09 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 48955.45 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.43 | A.1011181.43.01 | 7 5/8 Surface | SANTOS LIMITED | Leghorn 2 | Ensign 967 | J.21.109477 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-27 | 2021-07-27 |  | 2021-07-27 | 2021-07-27 23:59 |  | 2021-07-27 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:09 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 17944.2 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.42 | A.1011181.42.03 | Sturt East 4 Plug 3C | SANTOS LIMITED | Big Lake 30 | Wild Desert Rig 6 | J.21.109168 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-05-24 10:00 | 2021-05-25 |  | 2021-05-25 | 2021-05-25 23:59 |  | 2021-05-26 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.42 | A.1011181.42.01 | Big Lake 30 Plug 1A | SANTOS LIMITED | Big Lake 30 | Wild Desert Rig 6 | J.21.109125 | WCF | REM-PA | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-20 10:00 | 2021-05-20 |  | 2021-05-20 | 2021-05-21 23:59 |  | 2021-05-21 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 11702.37 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.42 | A.1011181.42.02 | Gidgealpa Plug 1A-2, 1A-3 and 1A-4 | SANTOS LIMITED | Big Lake 30 | Wild Desert Rig 6 | J.21.109122 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-05-21 10:00 | 2021-05-22 |  | 2021-05-22 | 2021-05-22 23:59 |  | 2021-05-24 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.41 | A.1011181.41.03 | Sturt East 4 Plug 3C | SANTOS LIMITED | Ipundu 8 | Wild Desert Rig 22 | J.21.109466 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-05-01 11:00 | 2021-05-02 |  | 2021-05-02 | 2021-05-02 23:59 |  | 2021-05-03 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:07 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.41 | A.1011181.41.02 | Gidgealpa Plug 1A-2, 1A-3 and 1A-4 | SANTOS LIMITED | Ipundu 8 | Wild Desert Rig 22 | J.21.109465 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-04-28 11:00 | 2021-05-05 |  | 2021-05-05 | 2021-05-05 23:59 |  | 2021-04-30 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:07 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.41 | A.1011181.41.01 | Ipundu 8 Plug 1A | SANTOS LIMITED | Ipundu 8 | Wild Desert Rig 22 | J.21.109114 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-27 11:00 | 2021-05-02 |  | 2021-05-02 | 2021-05-03 23:59 |  | 2021-04-24 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:20 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 12628.49 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.40 | A.1011181.40.03 | Sturt East 4 Plug 3C | SANTOS LIMITED | Ipundu 7 | Wild Desert Rig 22 | J.21.109471 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-05-13 11:00 | 2021-05-14 |  | 2021-05-14 | 2021-05-14 23:59 |  | 2021-05-15 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:08 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.40 | A.1011181.40.01 | Ipundu 7 Plug 2B | SANTOS LIMITED | Ipundu 7 | Wild Desert Rig 22 | J.21.109151 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-11 11:00 | 2021-05-11 |  | 2021-05-11 | 2021-05-12 23:59 |  | 2021-05-13 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 15942.37 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.40 | A.1011181.40.02 | Ipundu 7 Plug 1C | SANTOS LIMITED | Ipundu 7 | Wild Desert Rig 22 | J.21.109123 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-10 11:00 | 2021-05-11 |  | 2021-05-11 | 2021-05-11 23:59 |  | 2021-05-12 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 13821.51 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.398 | A.1011181.398.01 | Plug 1A | SANTOS LIMITED |  | Wild Desert Rig 16 | J.23.080522 | WCF | REM-PA | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-10-27 23:59 | 2023-10-28 | 2023-10-27 23:59 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:23 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 2 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.397 | A.1011181.397.01 | Plug 1A | SANTOS LIMITED |  | Wild Desert Rig 16 | J.23.080520 | WCF | REM-PA | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-10-15 | 2023-10-15 | 2023-10-15 | 2023-10-15 | 2023-10-15 23:59 | 2023-10-16 | 2023-10-15 23:59 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:23 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 2 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.396 | A.1011181.396.01 | Plug 1A | SANTOS LIMITED |  | Wild Desert Rig 16 | J.23.080519 | WCF | REM-PA | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-27 | 2023-09-27 | 2023-09-26 23:00 | 2023-09-27 | 2023-09-27 23:59 | 2023-09-27 23:00 | 2023-09-27 23:59 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:22 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 2 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.395 | A.1011181.395.01 | Plug 1A | SANTOS LIMITED |  | Wild Desert Rig 16 | J.23.080518 | WCF | REM-PA | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-15 | 2023-09-15 | 2023-09-14 23:00 | 2023-09-15 | 2023-09-15 23:59 | 2023-09-15 23:00 | 2023-09-15 23:59 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:22 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 2 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.394 | A.1011181.394.01 | Plug 1A | SANTOS LIMITED |  | Wild Desert Rig 16 | J.23.080517 | WCF | REM-PA | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-08 | 2023-09-08 | 2023-09-07 23:00 | 2023-09-08 | 2023-09-08 23:59 | 2023-09-08 23:00 | 2023-09-08 23:59 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:22 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 2 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.393 | A.1011181.393.01 | Plug 1A | SANTOS LIMITED |  | Wild Desert Rig 16 | J.23.080516 | WCF | REM-PA | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-02 | 2023-09-02 | 2023-09-01 23:00 | 2023-09-02 | 2023-09-02 23:59 | 2023-09-02 23:00 | 2023-09-02 23:59 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:22 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 2 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.392 | A.1011181.392.01 | Plug 1A | SANTOS LIMITED |  | Wild Desert Rig 16 | J.23.080514 | WCF | REM-PA | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-09 | 2023-08-09 | 2023-08-08 23:00 | 2023-08-09 | 2023-08-09 23:59 | 2023-08-09 23:00 | 2023-08-09 23:59 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:23 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 2 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.391 | A.1011181.391.01 | Plug 1A | SANTOS LIMITED |  | Wild Desert Rig 16 | J.23.080515 | WCF | REM-PA | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-07-26 | 2023-07-26 | 2023-07-25 23:00 | 2023-07-26 | 2023-07-26 23:59 | 2023-07-26 23:00 | 2023-07-26 23:59 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:22 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 2 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.390 | A.1011181.390.01 | Plug 1A | SANTOS LIMITED | MUDLALEE 3 | Wild Desert Rig 16 | J.23.080509 | WCF | REM-PA | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-23 | 2023-07-26 | 2023-07-25 23:00 | 2023-07-26 | 2023-07-26 23:59 | 2023-07-26 23:00 | 2023-07-23 23:59 | AUS East Coast WS | MMendoza26 | 2023-07-31 11:31 | ATimbs |  | No |  |  |  |  | Grace Vang |  | 10087.43 | 2 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.39 | A.1011181.39.03 | Sturt East 4 Plug 3C | SANTOS LIMITED | Ipundu 6 | Wild Desert Rig 22 | J.21.109459 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-05-09 10:00 | 2021-05-09 23:00 |  | 2021-05-09 23:00 | 2021-05-10 22:59 |  | 2021-05-11 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:06 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.39 | A.1011181.39.01 | Ipundu 6 Plug 1A | SANTOS LIMITED | Ipundu 6 | Wild Desert Rig 22 | J.21.109456 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-05 10:00 | 2021-05-04 23:00 |  | 2021-05-04 23:00 | 2021-05-06 22:59 |  | 2021-05-07 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:06 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 13658.75 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.39 | A.1011181.39.02 | Gidgealpa Plug 1A-2, 1A-3 and 1A-4 | SANTOS LIMITED | Ipundu 6 | Wild Desert Rig 22 | J.21.109147 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-05-06 10:00 | 2021-05-06 23:00 |  | 2021-05-06 23:00 | 2021-05-07 22:59 |  | 2021-05-08 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.389 | A.1011181.389.01 | Plug 1A | SANTOS LIMITED | DULLINGARI 35 | Wild Desert Rig 16 | J.23.080507 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-11 | 2023-06-11 | 2023-06-10 23:00 | 2023-06-11 | 2023-06-11 23:59 | 2023-06-11 23:00 | 2023-06-11 23:59 | AUS East Coast WS | MMendoza26 | 2023-07-25 17:58 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 2 |  |  |  | 81.3 | 33.3 | 0 | 100 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.388 | A.1011181.388.01 | Plug 1A | SANTOS LIMITED | DULLINGARI 33 | Wild Desert Rig 16 | J.23.080506 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-06 | 2023-06-06 | 2023-06-05 23:00 | 2023-06-06 | 2023-06-06 23:59 | 2023-06-06 23:00 | 2023-06-06 23:59 | AUS East Coast WS | MMendoza26 | 2023-06-27 13:08 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10087.43 | 2 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.387 | A.1011181.387.01 | 4-1/2" Recompletion | SANTOS LIMITED | HERA 2 | Wild Desert Rig 16 | J.23.080505 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-23 | 2023-07-23 | 2023-07-22 23:00 | 2023-07-23 | 2023-07-23 23:59 | 2023-07-23 23:00 | 2023-07-23 23:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 14:50 | MMendoza26 |  | No |  |  |  |  | Mark Mendoza |  | 10266.61 | 1 |  |  |  | 65.6 | 8.3 | 0 | 0 | 28.7 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.386 | A.1011181.386.01 | Plug 1A | SANTOS LIMITED | MERRIMELIA 22 | Wild Desert Rig 16 | J.23.080504 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-31 | 2023-05-31 |  | 2023-05-31 | 2023-05-31 23:59 |  | 2023-05-31 23:59 | AUS East Coast WS | MMendoza26 | 2023-05-24 11:03 | JNyoo |  | No |  |  |  |  | Grace Vang |  | 10087.43 | 2 |  |  |  | 81.3 | 66.7 | 0 | 50 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.385 | A.1011181.385.02 | 4.5" Production (Slim) | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.080500 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-27 10:00 | 2023-12-27 10:00 | 2023-12-28 01:00 | 2023-12-28 10:00 | 2023-12-29 10:59 | 2023-12-30 01:00 | 2023-12-30 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:54 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.385 | A.1011181.385.01 | 7" Surface (Slim) | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.080497 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-24 | 2023-12-24 03:00 | 2023-12-25 01:00 | 2023-12-25 | 2023-12-25 23:59 | 2023-12-27 01:00 | 2023-12-26 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:54 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.384 | A.1011181.384.02 | 4.5" Production (Slim) | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.080499 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-12 10:00 | 2023-12-12 10:00 | 2023-12-13 01:00 | 2023-12-13 10:00 | 2023-12-14 10:59 | 2023-12-15 01:00 | 2023-12-15 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:54 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.384 | A.1011181.384.01 | 7" Surface (Slim) | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.080495 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-09 | 2023-12-09 03:00 | 2023-12-10 01:00 | 2023-12-10 | 2023-12-10 23:59 | 2023-12-12 01:00 | 2023-12-11 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:54 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.383 | A.1011181.383.02 | 4.5" Production (Slim) | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.080503 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-06 10:00 | 2023-11-06 10:00 | 2023-11-07 01:00 | 2023-11-07 10:00 | 2023-11-08 10:59 | 2023-11-09 01:00 | 2023-11-09 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:54 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.383 | A.1011181.383.01 | 7" Surface (Slim) | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.080494 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-03 | 2023-11-03 03:00 | 2023-11-04 01:00 | 2023-11-04 | 2023-11-04 23:59 | 2023-11-06 01:00 | 2023-11-05 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:54 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.382 | A.1011181.382.03 | 4-1/2" Liner | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.080492 | WCF | PRI-INTER | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-03 21:00 | 2023-12-04 10:00 | 2023-12-04 01:00 | 2023-12-04 10:00 | 2023-12-05 10:59 | 2023-12-06 01:00 | 2023-12-06 20:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:54 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.382 | A.1011181.382.02 | 7" Intermediate | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.080491 | WCF | PRI-INTER | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-29 21:00 | 2023-11-30 10:00 | 2023-11-30 01:00 | 2023-11-30 10:00 | 2023-12-01 10:59 | 2023-12-02 01:00 | 2023-12-02 20:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:54 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.382 | A.1011181.382.01 | 9-5/8" Surface | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.080490 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-24 23:00 | 2023-11-24 04:00 | 2023-11-25 02:00 | 2023-11-25 01:00 | 2023-11-26 00:59 | 2023-11-26 02:00 | 2023-11-26 23:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:54 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.381 | A.1011181.381.03 | 4-1/2" Production | SANTOS LIMITED |  | ENSIGN 971 | J.23.080487 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-16 | 2023-08-17 | 2023-08-16 | 2023-08-17 | 2023-08-17 23:59 | 2023-08-18 | 2023-08-16 23:59 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:07 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.381 | A.1011181.381.02 | 7" Intermediate | SANTOS LIMITED |  | ENSIGN 971 | J.23.080485 | WCF | PRI-INTER | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-12 | 2023-08-13 | 2023-08-12 | 2023-08-13 | 2023-08-13 23:59 | 2023-08-14 | 2023-08-12 23:59 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:07 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.381 | A.1011181.381.01 | 9-5/8" Surface | SANTOS LIMITED | Well #1 | ENSIGN 971 | J.23.080481 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-07 23:00 | 2023-08-06 23:00 | 2023-08-06 23:00 | 2023-08-07 23:00 | 2023-08-08 22:59 | 2023-08-08 23:00 | 2023-08-08 23:59 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:07 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.380 | A.1011181.380.02 | 4.5" Production (Slim) | SANTOS LIMITED | Well #1 | ENSIGN 971 | J.23.080473 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-24 10:00 | 2023-12-24 10:00 | 2023-12-25 01:00 | 2023-12-25 10:00 | 2023-12-26 10:59 | 2023-12-27 01:00 | 2023-12-27 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:07 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.380 | A.1011181.380.01 | 7" Surface (Slim) | SANTOS LIMITED | Well #1 | ENSIGN 971 | J.23.080470 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-21 | 2023-12-21 03:00 | 2023-12-22 01:00 | 2023-12-22 | 2023-12-22 23:59 | 2023-12-24 01:00 | 2023-12-23 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:07 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.38 | A.1011181.38.01 | Moomba 45 Plug 1A-1 and 1A-2 | SANTOS LIMITED | Moomba 45 | Wild Desert Rig 16 | J.21.109476 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-27 10:00 | 2021-06-26 23:00 |  | 2021-06-26 23:00 | 2021-06-28 22:59 |  | 2021-06-29 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:08 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 11702.37 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.38 | A.1011181.38.02 | Moomba 45 Plug C | SANTOS LIMITED | Moomba 45 | Wild Desert Rig 16 | J.21.109469 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-07 | 2021-07-06 23:00 |  | 2021-07-06 23:00 | 2021-07-07 22:59 |  | 2021-07-07 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:08 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 20524.6 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.38 | A.1011181.38.03 | Moomba 45 Plug 2B | SANTOS LIMITED | Moomba 45 | Wild Desert Rig 16 | J.21.109455 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-04 | 2021-07-04 |  | 2021-07-04 | 2021-07-04 23:59 |  | 2021-07-05 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:06 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 53056.41 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.38 | A.1011181.38.04 | Moomba 45 Plug D | SANTOS LIMITED | Moomba 45 | Wild Desert Rig 16 | J.21.109269 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-13 | 2021-07-12 23:00 |  | 2021-07-12 23:00 | 2021-07-13 22:59 |  | 2021-07-13 23:59 | AUS East Coast WS | ALyons | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 16525.43 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.379 | A.1011181.379.02 | 4.5" Production (Slim) | SANTOS LIMITED | Well #1 | ENSIGN 971 | J.23.080471 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-13 10:00 | 2023-12-13 10:00 | 2023-12-14 01:00 | 2023-12-14 10:00 | 2023-12-15 10:59 | 2023-12-16 01:00 | 2023-12-16 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:07 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.379 | A.1011181.379.01 | 7" Surface (Slim) | SANTOS LIMITED | Well #1 | ENSIGN 971 | J.23.080466 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-10 | 2023-12-10 03:00 | 2023-12-11 01:00 | 2023-12-11 | 2023-12-11 23:59 | 2023-12-13 01:00 | 2023-12-12 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:07 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.378 | A.1011181.378.02 | 4.5" Production (Slim) | SANTOS LIMITED | Well #1 | ENSIGN 971 | J.23.080472 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-29 10:00 | 2023-09-29 10:00 | 2023-09-30 | 2023-09-30 10:00 | 2023-10-01 10:59 | 2023-10-02 | 2023-10-02 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:07 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.378 | A.1011181.378.01 | 7" Surface (Slim) | SANTOS LIMITED | Well #1 | ENSIGN 971 | J.23.080465 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-26 | 2023-09-26 03:00 | 2023-09-27 | 2023-09-27 | 2023-09-27 23:59 | 2023-09-29 | 2023-09-28 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:07 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.377 | A.1011181.377.02 | 4.5" Production (Slim) | SANTOS LIMITED | Well #1 | ENSIGN 971 | J.23.080469 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-17 10:00 | 2023-09-17 10:00 | 2023-09-18 | 2023-09-18 10:00 | 2023-09-19 10:59 | 2023-09-20 | 2023-09-20 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:07 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.377 | A.1011181.377.01 | 7" Surface (Slim) | SANTOS LIMITED | Well #1 | ENSIGN 971 | J.23.080463 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-14 | 2023-09-14 03:00 | 2023-09-15 | 2023-09-15 | 2023-09-15 23:59 | 2023-09-17 | 2023-09-16 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:07 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.376 | A.1011181.376.02 | 4.5" Production (Slim) | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.080442 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-29 10:00 | 2023-12-29 10:00 | 2023-12-30 01:00 | 2023-12-30 10:00 | 2023-12-31 10:59 | 2024-01-01 01:00 | 2024-01-01 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.376 | A.1011181.376.01 | 7" Surface (Slim) | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.080439 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-26 | 2023-12-26 03:00 | 2023-12-27 01:00 | 2023-12-27 | 2023-12-27 23:59 | 2023-12-29 01:00 | 2023-12-28 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.375 | A.1011181.375.02 | 4.5" Production (Slim) | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.080440 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-13 10:00 | 2023-12-13 10:00 | 2023-12-14 01:00 | 2023-12-14 10:00 | 2023-12-15 10:59 | 2023-12-16 01:00 | 2023-12-16 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.375 | A.1011181.375.01 | 7" Surface (Slim) | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.080437 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-10 | 2023-12-10 03:00 | 2023-12-11 01:00 | 2023-12-11 | 2023-12-11 23:59 | 2023-12-13 01:00 | 2023-12-12 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.374 | A.1011181.374.02 | 4.5" Production (Slim) | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.080441 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-28 10:00 | 2023-11-28 10:00 | 2023-11-29 01:00 | 2023-11-29 10:00 | 2023-11-30 10:59 | 2023-12-01 01:00 | 2023-12-01 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.374 | A.1011181.374.01 | 7" Surface (Slim) | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.080438 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-25 | 2023-11-25 03:00 | 2023-11-26 01:00 | 2023-11-26 | 2023-11-26 23:59 | 2023-11-28 01:00 | 2023-11-27 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.373 | A.1011181.373.02 | 4.5" Production | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.080434 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-13 10:00 | 2023-11-13 10:00 | 2023-11-14 01:00 | 2023-11-14 10:00 | 2023-11-15 10:59 | 2023-11-16 01:00 | 2023-11-16 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.373 | A.1011181.373.01 | 7-5/8" Surface | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.080430 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-10 | 2023-11-10 03:00 | 2023-11-11 01:00 | 2023-11-11 | 2023-11-11 23:59 | 2023-11-13 01:00 | 2023-11-12 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.372 | A.1011181.372.02 | 4.5" Production | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.080429 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-10-31 10:00 | 2023-10-31 10:00 | 2023-11-01 01:00 | 2023-11-01 10:00 | 2023-11-02 10:59 | 2023-11-03 01:00 | 2023-11-03 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.372 | A.1011181.372.01 | 7-5/8" Surface | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.080426 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-10-28 | 2023-10-28 03:00 | 2023-10-29 01:00 | 2023-10-29 | 2023-10-29 23:59 | 2023-10-31 01:00 | 2023-10-30 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.371 | A.1011181.371.02 | 4.5" Production | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.080428 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-10-17 10:00 | 2023-10-17 10:00 | 2023-10-18 01:00 | 2023-10-18 10:00 | 2023-10-19 10:59 | 2023-10-20 01:00 | 2023-10-20 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.371 | A.1011181.371.01 | 7-5/8" Surface | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.080425 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-10-14 | 2023-10-14 03:00 | 2023-10-15 01:00 | 2023-10-15 | 2023-10-15 23:59 | 2023-10-17 01:00 | 2023-10-16 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.370 | A.1011181.370.02 | 4.5" Production | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.080416 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-10-02 10:00 | 2023-10-02 10:00 | 2023-10-03 | 2023-10-03 11:00 | 2023-10-04 11:59 | 2023-10-05 01:00 | 2023-10-05 11:00 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.370 | A.1011181.370.01 | 7-5/8" Surface | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.080413 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-29 | 2023-09-29 03:00 | 2023-09-30 | 2023-09-30 | 2023-09-30 23:59 | 2023-10-02 | 2023-10-01 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.37 | A.1011181.37.01 | Moomba 48 Plug 1A-1 and 1A-2 | SANTOS LIMITED | Moomba 48 | Wild Desert Rig 6 | J.21.109454 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-14 10:00 | 2021-04-13 23:00 |  | 2021-04-13 23:00 | 2021-04-15 22:59 |  | 2021-04-16 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:06 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 17028.82 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.37 | A.1011181.37.03 | Moomba 48 Plug 1C | SANTOS LIMITED | Moomba 48 | Wild Desert Rig 6 | J.21.109165 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2021-04-19 10:00 | 2021-04-19 23:00 |  | 2021-04-19 23:00 | 2021-04-20 22:59 |  | 2021-04-21 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 10487.65 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.37 | A.1011181.37.02 | Moomba 48 Plug 1B & 1B-1 | SANTOS LIMITED | Moomba 48 | Wild Desert Rig 6 | J.21.109153 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-15 10:00 | 2021-04-15 23:00 |  | 2021-04-15 23:00 | 2021-04-16 22:59 |  | 2021-04-17 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 11559.21 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.369 | A.1011181.369.02 | 4.5" Production | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.080420 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-18 10:00 | 2023-09-18 10:00 | 2023-09-19 | 2023-09-19 10:00 | 2023-09-20 10:59 | 2023-09-21 | 2023-09-21 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.369 | A.1011181.369.01 | 7-5/8" Surface | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.080412 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-15 | 2023-09-15 03:00 | 2023-09-16 | 2023-09-16 | 2023-09-16 23:59 | 2023-09-18 | 2023-09-17 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.368 | A.1011181.368.02 | 4.5" Production | SANTOS LIMITED | MERANJI 28 | ENSIGN 974 | J.23.080414 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-27 10:00 | 2023-07-27 10:00 | 2023-07-28 | 2023-07-28 10:00 | 2023-07-29 10:59 | 2023-07-30 | 2023-07-30 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-30 20:44 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.368 | A.1011181.368.01 | 7-5/8" Surface | SANTOS LIMITED | MERANJI 28 | ENSIGN 974 | J.23.080411 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-17 | 2023-07-17 03:00 | 2023-07-18 | 2023-07-18 | 2023-07-18 23:59 | 2023-07-20 | 2023-07-19 | AUS East Coast WS | MMendoza26 | 2023-07-25 03:03 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.367 | A.1011181.367.02 | 4.5" Production | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.080421 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-23 10:00 | 2023-08-23 10:00 | 2023-08-24 | 2023-08-24 10:00 | 2023-08-25 10:59 | 2023-08-26 | 2023-08-26 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.367 | A.1011181.367.01 | 7-5/8" Surface | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.080419 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-20 | 2023-08-20 03:00 | 2023-08-21 | 2023-08-21 | 2023-08-21 23:59 | 2023-08-23 | 2023-08-22 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.366 | A.1011181.366.02 | 4.5" Production | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.080415 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-10 10:00 | 2023-08-10 10:00 | 2023-08-11 | 2023-08-11 10:00 | 2023-08-12 10:59 | 2023-08-13 | 2023-08-13 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.366 | A.1011181.366.01 | 7-5/8" Surface | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.080410 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-07 | 2023-08-07 03:00 | 2023-08-08 | 2023-08-08 | 2023-08-08 23:59 | 2023-08-10 | 2023-08-09 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.365 | A.1011181.365.03 | 4-1/2" Liner | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.080396 | WCF | PRI-INTER | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-10-24 21:00 | 2023-10-25 10:00 | 2023-10-25 01:00 | 2023-10-25 10:00 | 2023-10-26 10:59 | 2023-10-27 01:00 | 2023-10-27 20:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:54 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.365 | A.1011181.365.02 | 7" Intermediate | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.080395 | WCF | PRI-INTER | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-10-20 21:00 | 2023-10-21 10:00 | 2023-10-21 01:00 | 2023-10-21 10:00 | 2023-10-22 10:59 | 2023-10-23 01:00 | 2023-10-23 20:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:54 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.365 | A.1011181.365.01 | 9-5/8" Surface | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.080394 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-10-15 23:00 | 2023-10-15 04:00 | 2023-10-16 02:00 | 2023-10-16 01:00 | 2023-10-17 00:59 | 2023-10-17 02:00 | 2023-10-17 23:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:54 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.364 | A.1011181.364.02 | 5-1/2" Production | SANTOS LIMITED | Well #1 | SLR 188 | J.23.080368 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-07 10:00 | 2023-09-08 11:00 | 2023-09-08 | 2023-09-08 11:00 | 2023-09-09 10:59 | 2023-09-10 | 2023-09-10 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:38 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.364 | A.1011181.364.01 | 9-5/8" Surface | SANTOS LIMITED | Well #1 | SLR 188 | J.23.080366 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-03 22:00 | 2023-09-04 | 2023-09-04 | 2023-09-04 | 2023-09-04 23:59 | 2023-09-05 | 2023-09-05 22:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:38 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.363 | A.1011181.363.02 | 5-1/2" Production | SANTOS LIMITED | Well #1 | SLR 188 | J.23.080367 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-28 10:00 | 2023-08-29 11:00 | 2023-08-29 | 2023-08-29 11:00 | 2023-08-30 10:59 | 2023-08-31 | 2023-08-31 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:38 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.363 | A.1011181.363.01 | 9-5/8" Surface | SANTOS LIMITED | Well #1 | SLR 188 | J.23.080365 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-24 22:00 | 2023-08-25 | 2023-08-25 | 2023-08-25 | 2023-08-25 23:59 | 2023-08-26 | 2023-08-26 22:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:38 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.362 | A.1011181.362.02 | 4.5" Production | SANTOS LIMITED | Well #1 | SLR 188 | J.24.003090 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-04-04 10:00 | 2024-04-05 11:00 | 2024-04-05 01:00 | 2024-04-05 11:00 | 2024-04-06 10:59 | 2024-04-07 01:00 | 2024-04-07 09:00 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.362 | A.1011181.362.01 | 7-5/8" Surface | SANTOS LIMITED | Well #1 | SLR 188 | J.24.003086 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-03-31 22:00 | 2024-04-01 | 2024-04-01 01:00 | 2024-04-01 | 2024-04-01 23:59 | 2024-04-02 01:00 | 2024-04-02 22:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.361 | A.1011181.361.02 | 4.5" Production | SANTOS LIMITED | Well #1 | SLR 188 | J.24.003088 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-03-18 10:00 | 2024-03-19 11:00 | 2024-03-19 01:00 | 2024-03-19 11:00 | 2024-03-20 10:59 | 2024-03-21 01:00 | 2024-03-21 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.361 | A.1011181.361.01 | 7-5/8" Surface | SANTOS LIMITED | Well #1 | SLR 188 | J.24.003084 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-03-14 22:00 | 2024-03-15 | 2024-03-15 01:00 | 2024-03-15 | 2024-03-15 23:59 | 2024-03-16 01:00 | 2024-03-16 22:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.360 | A.1011181.360.02 | 4.5" Production | SANTOS LIMITED | Well #1 | SLR 188 | J.24.003089 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-02-28 10:00 | 2024-02-29 11:00 | 2024-02-29 01:00 | 2024-02-29 11:00 | 2024-03-01 10:59 | 2024-03-02 01:00 | 2024-03-02 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.360 | A.1011181.360.01 | 7-5/8" Surface | SANTOS LIMITED | Well #1 | SLR 188 | J.24.003083 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-02-24 22:00 | 2024-02-25 | 2024-02-25 01:00 | 2024-02-25 | 2024-02-25 23:59 | 2024-02-26 01:00 | 2024-02-26 22:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.36 | A.1011181.36.05 | Moomba 136 Plug 1D | SANTOS LIMITED | Moomba 136 | Wild Desert Rig 16 | J.21.109518 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-14 12:00 | 2021-08-14 10:00 |  | 2021-08-14 12:00 | 2021-08-15 23:59 |  | 2021-08-15 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:14 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 14021.47 | 2 |  |  |  | 81.3 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.36 | A.1011181.36.03 | Moomba 136 Plug 1B | SANTOS LIMITED | Moomba 136 | Wild Desert Rig 16 | J.21.109468 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-07 23:00 | 2021-08-07 23:00 |  | 2021-08-07 23:00 | 2021-08-08 22:59 |  | 2021-08-08 22:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:08 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 24659.94 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.36 | A.1011181.36.01 | Moomba 136 Plug 1C | SANTOS LIMITED | Moomba 136 | Wild Desert Rig 16 | J.21.109467 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-12 | 2021-08-12 |  | 2021-08-12 | 2021-08-12 23:59 |  | 2021-08-12 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:07 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 9549.16 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.36 | A.1011181.36.06 | Moomba 136 Plug 2D | SANTOS LIMITED | Moomba 136 | Wild Desert Rig 16 | J.21.109286 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-12 12:00 | 2021-08-12 08:00 |  | 2021-08-12 12:00 | 2021-08-12 23:59 |  | 2021-08-12 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 11065.58 | 1 |  |  |  | 65.6 | 8.3 | 0 | 0 | 28.7 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.36 | A.1011181.36.02 | Moomba 136 Plug 1A | SANTOS LIMITED | Moomba 136 | Wild Desert Rig 16 | J.21.109127 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-08 | 2021-08-08 |  | 2021-08-08 | 2021-08-08 23:59 |  | 2021-08-08 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 13869.38 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.36 | A.1011181.36.04 | Plug 2C | SANTOS LIMITED | Moomba 136 | Wild Desert Rig 16 | J.21.109120 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-10 | 2021-08-10 |  | 2021-08-10 | 2021-08-10 23:59 |  | 2021-08-10 23:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:20 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 14514.35 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.359 | A.1011181.359.02 | 4.5" Production | SANTOS LIMITED | Well #1 | SLR 188 | J.24.003087 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-02-09 10:00 | 2024-02-10 11:00 | 2024-02-10 01:00 | 2024-02-10 11:00 | 2024-02-11 10:59 | 2024-02-12 01:00 | 2024-02-12 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.359 | A.1011181.359.01 | 7-5/8" Surface | SANTOS LIMITED | Well #1 | SLR 188 | J.24.003082 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-02-05 22:00 | 2024-02-06 | 2024-02-06 01:00 | 2024-02-06 | 2024-02-06 23:59 | 2024-02-07 01:00 | 2024-02-07 22:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.358 | A.1011181.358.02 | 4.5" Production | SANTOS LIMITED | Well #1 | SLR 188 | J.24.003085 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-01-22 10:00 | 2024-01-23 11:00 | 2024-01-23 01:00 | 2024-01-23 11:00 | 2024-01-24 10:59 | 2024-01-25 01:00 | 2024-01-25 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.358 | A.1011181.358.01 | 7-5/8" Surface | SANTOS LIMITED | Well #1 | SLR 188 | J.24.003081 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-01-18 22:00 | 2024-01-19 | 2024-01-19 01:00 | 2024-01-19 | 2024-01-19 23:59 | 2024-01-20 01:00 | 2024-01-20 22:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.357 | A.1011181.357.02 | 4.5" Production | SANTOS LIMITED | Well #1 | SLR 188 | J.24.003080 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-01-06 10:00 | 2024-01-07 11:00 | 2024-01-07 01:00 | 2024-01-07 11:00 | 2024-01-08 10:59 | 2024-01-09 01:00 | 2024-01-09 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.357 | A.1011181.357.01 | 7-5/8" Surface | SANTOS LIMITED | Well #1 | SLR 188 | J.24.003077 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-01-02 22:00 | 2024-01-03 | 2024-01-03 01:00 | 2024-01-03 | 2024-01-03 23:59 | 2024-01-04 01:00 | 2024-01-04 22:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.356 | A.1011181.356.02 | 4.5" Production | SANTOS LIMITED | Well #1 | SLR 188 | J.24.003079 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-01-01 10:00 | 2024-01-02 11:00 | 2024-01-02 01:00 | 2024-01-02 11:00 | 2024-01-03 10:59 | 2024-01-04 01:00 | 2024-01-04 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.356 | A.1011181.356.01 | 7-5/8" Surface | SANTOS LIMITED | Well #1 | SLR 188 | J.23.080359 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-28 22:00 | 2023-12-29 | 2023-12-29 01:00 | 2023-12-29 | 2023-12-29 23:59 | 2023-12-30 01:00 | 2023-12-30 22:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.355 | A.1011181.355.02 | 4.5" Production | SANTOS LIMITED | Well #1 | SLR 188 | J.23.080360 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-22 10:00 | 2023-12-23 11:00 | 2023-12-23 01:00 | 2023-12-23 11:00 | 2023-12-24 10:59 | 2023-12-25 01:00 | 2023-12-25 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.355 | A.1011181.355.01 | 7-5/8" Surface | SANTOS LIMITED | Well #1 | SLR 188 | J.23.080355 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-18 22:00 | 2023-12-19 | 2023-12-19 01:00 | 2023-12-19 | 2023-12-19 23:59 | 2023-12-20 01:00 | 2023-12-20 22:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.354 | A.1011181.354.02 | 4.5" Production | SANTOS LIMITED | Well #1 | SLR 188 | J.23.080362 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-07 10:00 | 2023-12-08 11:00 | 2023-12-08 01:00 | 2023-12-08 11:00 | 2023-12-09 10:59 | 2023-12-10 01:00 | 2023-12-10 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.354 | A.1011181.354.01 | 7-5/8" Surface | SANTOS LIMITED | Well #1 | SLR 188 | J.23.080354 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-03 22:00 | 2023-12-04 | 2023-12-04 01:00 | 2023-12-04 | 2023-12-04 23:59 | 2023-12-05 01:00 | 2023-12-05 22:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.353 | A.1011181.353.02 | 4.5" Production | SANTOS LIMITED | Well #1 | SLR 188 | J.23.080358 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-20 10:00 | 2023-11-21 11:00 | 2023-11-21 01:00 | 2023-11-21 11:00 | 2023-11-22 10:59 | 2023-11-23 01:00 | 2023-11-23 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:36 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.353 | A.1011181.353.01 | 7-5/8" Surface | SANTOS LIMITED | Well #1 | SLR 188 | J.23.080353 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-16 22:00 | 2023-11-17 | 2023-11-17 01:00 | 2023-11-17 | 2023-11-17 23:59 | 2023-11-18 01:00 | 2023-11-18 22:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:36 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.352 | A.1011181.352.02 | 4.5" Production | SANTOS LIMITED | Well #1 | SLR 188 | J.23.080350 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-04 10:00 | 2023-11-05 11:00 | 2023-11-05 01:00 | 2023-11-05 11:00 | 2023-11-06 10:59 | 2023-11-07 01:00 | 2023-11-07 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:36 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.352 | A.1011181.352.01 | 7-5/8" Surface | SANTOS LIMITED | Well #1 | SLR 188 | J.23.080346 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-10-31 22:00 | 2023-11-01 | 2023-11-01 01:00 | 2023-11-01 | 2023-11-01 23:59 | 2023-11-02 01:00 | 2023-11-02 22:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:36 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.351 | A.1011181.351.02 | 4.5" Production | SANTOS LIMITED | Well #1 | SLR 188 | J.23.080348 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-10-27 10:00 | 2023-10-28 11:00 | 2023-10-28 01:00 | 2023-10-28 11:00 | 2023-10-29 10:59 | 2023-10-30 01:00 | 2023-10-30 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:36 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.351 | A.1011181.351.01 | 7-5/8" Surface | SANTOS LIMITED | Well #1 | SLR 188 | J.23.080341 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-10-23 22:00 | 2023-10-24 | 2023-10-24 01:00 | 2023-10-24 | 2023-10-24 23:59 | 2023-10-25 01:00 | 2023-10-25 22:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:36 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.350 | A.1011181.350.02 | 4.5" Production | SANTOS LIMITED | Well #1 | SLR 188 | J.23.080347 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-10-20 10:00 | 2023-10-21 11:00 | 2023-10-21 01:00 | 2023-10-21 11:00 | 2023-10-22 10:59 | 2023-10-23 01:00 | 2023-10-23 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:36 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.350 | A.1011181.350.01 | 7-5/8" Surface | SANTOS LIMITED | Well #1 | SLR 188 | J.23.080339 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-10-16 22:00 | 2023-10-17 | 2023-10-17 01:00 | 2023-10-17 | 2023-10-17 23:59 | 2023-10-18 01:00 | 2023-10-18 22:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:36 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.35 | A.1011181.35.02 | Moomba 32 Plug 4B-1 and 4B-2 | SANTOS LIMITED | Moomba 32 | Wild Desert Rig 16 | J.21.109451 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-06 11:00 | 2021-03-07 |  | 2021-03-07 | 2021-03-07 23:59 |  | 2021-03-08 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:06 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 11734.74 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.35 | A.1011181.35.01 | Moomba 32 P&A 1A-1 | SANTOS LIMITED | Moomba 32 | Wild Desert Rig 16 | J.21.109138 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-04 11:00 | 2021-03-04 |  | 2021-03-04 | 2021-03-05 23:59 |  | 2021-03-06 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 9092.25 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.35 | A.1011181.35.04 | Sturt East 4 Plug D | SANTOS LIMITED | Moomba 32 | Wild Desert Rig 16 | J.21.109137 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-03-10 11:00 | 2021-03-11 |  | 2021-03-11 | 2021-03-11 23:59 |  | 2021-03-12 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.35 | A.1011181.35.03 | Moomba 32 Plug 1C | SANTOS LIMITED | Moomba 32 | Wild Desert Rig 16 | J.21.109109 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-09 11:00 | 2021-03-10 |  | 2021-03-10 | 2021-03-10 23:59 |  | 2021-03-11 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:20 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 11700.54 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.349 | A.1011181.349.02 | 4.5" Production | SANTOS LIMITED | Well #1 | SLR 188 | J.23.080345 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-10-03 11:00 | 2023-10-04 12:00 | 2023-10-04 01:00 | 2023-10-04 12:00 | 2023-10-05 11:59 | 2023-10-06 01:00 | 2023-10-06 11:00 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:36 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.349 | A.1011181.349.01 | 7-5/8" Surface | SANTOS LIMITED | Well #1 | SLR 188 | J.23.080342 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-29 22:00 | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2023-09-30 23:59 | 2023-10-01 | 2023-10-01 23:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:36 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.348 | A.1011181.348.02 | 4.5" Production | SANTOS LIMITED | Well #1 | SLR 188 | J.23.080344 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-21 10:00 | 2023-09-22 11:00 | 2023-09-22 | 2023-09-22 11:00 | 2023-09-23 10:59 | 2023-09-24 | 2023-09-24 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:36 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.348 | A.1011181.348.01 | 7-5/8" Surface | SANTOS LIMITED | Well #1 | SLR 188 | J.23.080338 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-17 22:00 | 2023-09-18 | 2023-09-18 | 2023-09-18 | 2023-09-18 23:59 | 2023-09-19 | 2023-09-19 22:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:36 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.347 | A.1011181.347.01 | Plug 1A | SANTOS LIMITED | MERRIMELIA 11 | Wild Desert Rig 16 | J.23.079879 | WCF | REM-PA | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-23 | 2023-05-23 |  | 2023-05-23 | 2023-05-23 23:59 |  | 2023-05-23 23:59 | AUS East Coast WS | MMendoza26 | 2023-05-27 14:53 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 10087.43 | 2 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.346 | A.1011181.346.01 | Plug 1A | SANTOS LIMITED | MERRIMELIA 12 | Wild Desert Rig 16 | J.23.078565 | WCF | REM-PA | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-17 | 2023-05-17 |  | 2023-05-17 | 2023-05-17 23:59 |  | 2023-05-17 23:59 | AUS East Coast WS | MMendoza26 | 2023-05-29 14:27 | ATimbs |  | No |  |  |  |  | Grace Vang |  | 10087.43 | 2 |  |  |  | 81.3 | 66.7 | 50 | 50 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.345 | A.1011181.345.01 | Plug 1A | SANTOS LIMITED | MOOMBA 39ST1 | Wild Desert Rig 22 | J.23.070155 | WCF | REM-PA | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-13 | 2023-05-13 |  | 2023-05-13 | 2023-05-13 23:59 |  | 2023-05-13 23:59 | AUS East Coast WS | MMendoza26 | 2023-05-24 10:07 | ATimbs |  | No |  |  |  |  | Grace Vang |  | 19384.14 | 2 |  |  |  | 87.5 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.344 | A.1011181.344.05 | Plug 1E | SANTOS LIMITED | STRZELECKI 8 | Wild Desert Rig 16 | J.23.070150 | WCF | REM-PA | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-24 | 2023-04-24 |  | 2023-04-24 | 2023-04-24 23:59 |  | 2023-04-24 23:59 | AUS East Coast WS | MMendoza26 | 2023-05-12 09:23 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 9310.44 | 2 |  |  |  | 81.3 | 66.7 | 0 | 50 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.344 | A.1011181.344.07 | Plug 1G | SANTOS LIMITED | STRZELECKI 8 | Wild Desert Rig 16 | J.23.071246 | WCF | REM-PA | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-27 | 2023-04-27 |  | 2023-04-27 | 2023-04-27 23:59 |  | 2023-04-27 23:59 | AUS East Coast WS | MMendoza26 | 2023-05-12 09:22 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 9444.97 | 2 |  |  |  | 81.3 | 66.7 | 0 | 50 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.344 | A.1011181.344.06 | Plug 2F (Contingency) | SANTOS LIMITED | STRZELECKI 8 | Wild Desert Rig 16 | J.23.071245 | WCF | REM-PA | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-30 | 2023-04-30 |  | 2023-04-30 | 2023-04-30 23:59 |  | 2023-04-30 23:59 | AUS East Coast WS | MMendoza26 | 2023-05-12 09:06 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 9310.44 | 2 |  |  |  | 81.3 | 66.7 | 0 | 50 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.344 | A.1011181.344.04 | Plug 1D | SANTOS LIMITED | STRZELECKI 8 | Wild Desert Rig 16 | J.23.070148 | WCF | REM-PA,REM-SQ | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-24 | 2023-04-24 |  | 2023-04-24 | 2023-04-24 23:59 |  | 2023-04-24 23:59 | AUS East Coast WS | MMendoza26 | 2023-04-27 09:01 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 9310.44 | 2 |  |  |  | 81.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.344 | A.1011181.344.03 | Plug 1C | SANTOS LIMITED | STRZELECKI 8 | Wild Desert Rig 16 | J.23.070146 | WCF | REM-PA,REM-SQ | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-21 | 2023-04-21 |  | 2023-04-21 | 2023-04-21 23:59 |  | 2023-04-21 23:59 | AUS East Coast WS | MMendoza26 | 2023-04-26 09:20 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 19852.44 | 1 |  |  |  | 87.5 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.344 | A.1011181.344.02 | Plug 1B | SANTOS LIMITED | STRZELECKI 8 | Wild Desert Rig 16 | J.23.070144 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-18 | 2023-04-18 |  | 2023-04-18 | 2023-04-18 23:59 |  | 2023-04-18 23:59 | AUS East Coast WS | MMendoza26 | 2023-04-20 17:36 | VKlimenko8 |  | No |  |  |  |  | Grace Vang |  | 10147.1 | 3 |  |  |  | 81.3 | 66.7 | 0 | 50 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.344 | A.1011181.344.01 | Plug 1A | SANTOS LIMITED | STRZELECKI 8 | Wild Desert Rig 16 | J.23.070142 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-16 | 2023-04-16 |  | 2023-04-16 | 2023-04-16 23:59 |  | 2023-04-16 23:59 | AUS East Coast WS | MMendoza26 | 2023-04-20 17:26 | VKlimenko8 |  | No |  |  |  |  | Grace Vang |  | 9377.08 | 2 |  |  |  | 81.3 | 66.7 | 0 | 50 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.343 | A.1011181.343.03 | 4-1/2" Liner | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.080385 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-19 10:00 | 2023-09-19 10:00 | 2023-09-20 | 2023-09-20 10:00 | 2023-09-21 10:59 | 2023-09-22 | 2023-09-22 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:54 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.343 | A.1011181.343.02 | 7" Intermediate | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.067895 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-15 10:00 | 2023-09-15 10:00 | 2023-09-16 | 2023-09-16 10:00 | 2023-09-17 10:59 | 2023-09-18 | 2023-09-18 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:54 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.343 | A.1011181.343.01 | 9-5/8" Surface | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.067893 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-12 | 2023-09-12 03:00 | 2023-09-13 | 2023-09-13 | 2023-09-13 23:59 | 2023-09-15 | 2023-09-14 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:54 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.342 | A.1011181.342.02 | 4.5" Production (Slim) | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.067885 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-11 10:00 | 2023-08-11 10:00 | 2023-08-12 | 2023-08-12 10:00 | 2023-08-13 10:59 | 2023-08-14 | 2023-08-14 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-20 15:00 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.342 | A.1011181.342.01 | 7" Surface (Slim) | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.067877 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-03 | 2023-08-03 03:00 | 2023-08-04 | 2023-08-04 | 2023-08-04 23:59 | 2023-08-06 | 2023-08-05 | AUS East Coast WS | MMendoza26 | 2023-07-20 15:00 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.341 | A.1011181.341.02 | 4.5" Production (Slim) | SANTOS LIMITED | MOOMBA 310 | SLR RIG 183 | J.23.067884 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-23 10:00 | 2023-07-23 10:00 | 2023-07-24 | 2023-07-24 10:00 | 2023-07-25 10:59 | 2023-07-26 | 2023-07-26 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-25 03:18 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.341 | A.1011181.341.01 | 7" Surface (Slim) | SANTOS LIMITED | MOOMBA 310 | SLR RIG 183 | J.23.067875 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-14 | 2023-07-12 03:00 | 2023-07-13 | 2023-07-13 | 2023-07-13 23:59 | 2023-07-16 | 2023-07-15 | AUS East Coast WS | MMendoza26 | 2023-07-25 02:28 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.340 | A.1011181.340.01 | 7" Surface (Slim) | SANTOS LIMITED | MOOMBA 309 | SLR RIG 183 | J.23.067872 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-27 | 2023-06-27 03:00 | 2023-06-28 | 2023-06-28 | 2023-06-28 23:59 | 2023-06-30 | 2023-06-29 | AUS East Coast WS | MMendoza26 | 2023-07-20 12:21 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.340 | A.1011181.340.02 | 4.5" Production (Slim) | SANTOS LIMITED | MOOMBA 309 | SLR RIG 183 | J.23.067880 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-07 10:00 | 2023-07-07 10:00 | 2023-07-08 | 2023-07-08 10:00 | 2023-07-09 10:59 | 2023-07-10 | 2023-07-10 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-20 10:34 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.34 | A.1011181.34.04 | Sturt East 4 Plug D | SANTOS LIMITED | Moomba 176 | Wild Desert Rig 16 | J.21.109170 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-02-23 11:00 | 2021-02-24 |  | 2021-02-24 | 2021-02-24 23:59 |  | 2021-02-25 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.34 | A.1011181.34.03 | Moomba 176 Plug 1B | SANTOS LIMITED | Moomba 176 | Wild Desert Rig 16 | J.21.109140 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-22 11:00 | 2021-02-23 |  | 2021-02-23 | 2021-02-23 23:59 |  | 2021-02-24 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 8668.77 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.34 | A.1011181.34.01 | Moomba 176 Plug 1A-2 and 1A-3 | SANTOS LIMITED | Moomba 176 | Wild Desert Rig 16 | J.21.109130 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-21 11:00 | 2021-02-21 |  | 2021-02-21 | 2021-02-22 23:59 |  | 2021-02-23 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 22177.29 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.34 | A.1011181.34.02 | Moomba 176 Plug 1A-1 | SANTOS LIMITED | Moomba 176 | Wild Desert Rig 16 | J.21.109111 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-16 11:00 | 2021-02-17 |  | 2021-02-17 | 2021-02-17 23:59 |  | 2021-02-18 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:20 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 6688.41 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.339 | A.1011181.339.02 | 4.5" Production (Slim) | SANTOS LIMITED | BIG LAKE 172 | SLR RIG 183 | J.23.067881 | WCF | PRI-LONG | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-19 10:00 | 2023-06-19 10:00 | 2023-06-19 | 2023-06-20 10:00 | 2023-06-21 10:59 | 2023-06-21 | 2023-06-22 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-23 13:44 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.339 | A.1011181.339.03 | Plug 1 | SANTOS LIMITED | BIG LAKE 172 | SLR RIG 183 | J.23.102020 | WCF | PRI-LONG, REM-PA | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-06-22 10:00 | 2023-06-22 10:00 | 2023-06-22 | 2023-06-23 10:00 | 2023-06-24 10:59 | 2023-06-24 | 2023-06-25 10:00 | AUS East Coast WS | MMendoza26 | 2023-06-27 14:13 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10087.43 | 1 |  |  |  | 93.8 | 66.7 | 0 | 50 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.339 | A.1011181.339.01 | 7" Surface (Slim) | SANTOS LIMITED | BIG LAKE 172 | SLR RIG 183 | J.23.067870 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-05-11 | 2023-05-11 03:00 |  | 2023-05-12 | 2023-05-12 23:59 |  | 2023-05-13 | AUS East Coast WS | MMendoza26 | 2023-05-22 17:53 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 93.8 | 50 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.338 | A.1011181.338.02 | 4.5" Production (Slim) | SANTOS LIMITED | BIG LAKE 171 | SLR RIG 183 | J.23.067874 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-30 10:00 | 2023-04-30 10:00 |  | 2023-05-01 10:00 | 2023-05-02 10:59 |  | 2023-05-03 10:00 | AUS East Coast WS | MMendoza26 | 2023-05-24 10:00 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.338 | A.1011181.338.01 | 7" Surface (Slim) | SANTOS LIMITED | BIG LAKE 171 | SLR RIG 183 | J.23.067869 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-27 | 2023-04-27 03:00 |  | 2023-04-28 | 2023-04-28 23:59 |  | 2023-04-29 | AUS East Coast WS | MMendoza26 | 2023-05-12 12:34 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10267.77 | 1 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.337 | A.1011181.337.02 | 7" Intermediate | SANTOS LIMITED | MOOMBA 258 | ENSIGN 971 | J.23.067857 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-08-07 | 2023-08-08 | 2023-08-07 | 2023-08-08 | 2023-08-08 23:59 | 2023-08-09 | 2023-08-07 23:59 | AUS East Coast WS | MMendoza26 | 2023-09-06 10:42 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10259.47 | 1 |  |  |  | 81.3 | 83.3 | 0 | 75 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.337 | A.1011181.337.04 | KOP | SANTOS LIMITED | MOOMBA 258 | ENSIGN 971 | J.23.123187 | WCF | REM-KOP | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-08-16 | 2023-08-17 | 2023-08-16 | 2023-08-17 | 2023-08-17 23:59 | 2023-08-18 | 2023-08-16 23:59 | AUS East Coast WS | MMendoza26 | 2023-08-25 01:44 | MMendoza26 |  | No |  |  |  |  | Mark Mendoza |  | 8594.17 | 0 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.337 | A.1011181.337.03 | 4-1/2" Production | SANTOS LIMITED | MOOMBA 258 | ENSIGN 971 | J.23.080476 | WCF | PRI-LONG | Medium | Unconfirmed - 90% | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-09-29 | 2023-09-30 | 2023-09-29 | 2023-09-30 | 2023-09-30 23:59 | 2023-10-01 | 2023-09-29 23:59 | AUS East Coast WS | MMendoza26 | 2023-08-25 01:29 | MMendoza26 |  | No |  |  |  |  | Mark Mendoza |  | 10346.98 | 1 |  |  |  | 71.9 | 8.3 | 0 | 0 | 31.3 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.337 | A.1011181.337.01 | 9-5/8" Surface | SANTOS LIMITED | MOOMBA 258 | ENSIGN 971 | J.23.067850 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-27 23:00 | 2023-07-26 23:00 | 2023-07-26 23:00 | 2023-07-27 23:00 | 2023-07-28 22:59 | 2023-07-28 23:00 | 2023-07-28 23:59 | AUS East Coast WS | MMendoza26 | 2023-07-30 19:36 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.336 | A.1011181.336.02 | 4 1/2" Production (Slim, Hot) | SANTOS LIMITED | Well #1 | ENSIGN 971 | J.23.067862 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-02-06 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-07 23:59 | 2024-02-09 | 2024-02-08 23:59 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:08 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.336 | A.1011181.336.01 | 7" Surface (Slim) | SANTOS LIMITED | Well #1 | ENSIGN 971 | J.23.067856 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-01-31 23:00 | 2024-01-31 23:00 | 2024-01-31 23:00 | 2024-02-01 23:00 | 2024-02-02 22:59 | 2024-02-02 23:00 | 2024-02-03 23:59 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:08 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.335 | A.1011181.335.02 | 4 1/2" Production (Slim, Hot) | SANTOS LIMITED | MOOMBA 306 | ENSIGN 971 | J.23.067853 | WCF | PRI-LONG | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-18 | 2023-07-18 | 2023-07-18 | 2023-07-18 | 2023-07-18 23:59 | 2023-07-20 | 2023-07-18 23:59 | AUS East Coast WS | MMendoza26 | 2023-07-25 08:49 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.335 | A.1011181.335.03 | Plug 1 to 6 | SANTOS LIMITED | MOOMBA 306 | ENSIGN 971 | J.23.107714 | WCF | REM-KOP,REM-PA | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-07-10 23:59 | 2023-07-12 | 2023-07-10 23:59 | AUS East Coast WS | MMendoza26 | 2023-07-25 02:35 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10087.43 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.335 | A.1011181.335.01 | 7" Surface (Slim) | SANTOS LIMITED | MOOMBA 306 | ENSIGN 971 | J.23.067848 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-06-19 23:00 | 2023-06-18 23:00 |  | 2023-06-19 23:00 | 2023-06-20 22:59 |  | 2023-06-20 23:59 | AUS East Coast WS | MMendoza26 | 2023-06-19 16:54 | JNyoo |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 87.5 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.334 | A.1011181.334.02 | 4 1/2" Production (Slim, Hot) | SANTOS LIMITED | MOOMBA 305 | ENSIGN 971 | J.23.067863 | WCF | PRI-LONG | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-14 | 2023-06-14 |  | 2023-06-14 | 2023-06-14 23:59 |  | 2023-06-14 23:59 | AUS East Coast WS | MMendoza26 | 2023-06-20 11:31 | ATimbs |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.334 | A.1011181.334.01 | 7" Surface (Slim) | SANTOS LIMITED | MOOMBA 305 | ENSIGN 971 | J.23.067854 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-08 23:00 | 2023-06-07 23:00 |  | 2023-06-08 23:00 | 2023-06-09 22:59 |  | 2023-06-09 23:59 | AUS East Coast WS | MMendoza26 | 2023-06-13 07:21 | VKlimenko8 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.333 | A.1011181.333.02 | 4 1/2" Production (Slim, Hot) | SANTOS LIMITED | MOOMBA 301 | ENSIGN 971 | J.23.067864 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-28 | 2023-05-28 |  | 2023-05-28 | 2023-05-28 23:59 |  | 2023-05-28 23:59 | AUS East Coast WS | MMendoza26 | 2023-06-12 13:37 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 36961.9 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.333 | A.1011181.333.01 | 7-5/8" Surface | SANTOS LIMITED | MOOMBA 301 | ENSIGN 971 | J.23.067855 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-22 23:00 | 2023-05-21 23:00 |  | 2023-05-22 23:00 | 2023-05-23 22:59 |  | 2023-05-23 23:59 | AUS East Coast WS | MMendoza26 | 2023-05-24 08:23 | NAbosnina |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.332 | A.1011181.332.02 | 4.5" Production (Slim) | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.067832 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-01 10:00 | 2023-09-01 10:00 | 2023-09-02 | 2023-09-02 10:00 | 2023-09-03 10:59 | 2023-09-04 | 2023-09-04 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.332 | A.1011181.332.01 | 7" Surface (Slim) | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.067825 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-29 | 2023-08-29 03:00 | 2023-08-30 | 2023-08-30 | 2023-08-30 23:59 | 2023-09-01 | 2023-08-31 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.331 | A.1011181.331.02 | 4.5" Production (Slim) | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.067830 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-03-26 10:00 | 2024-03-26 10:00 | 2024-03-27 | 2024-03-27 10:00 | 2024-03-28 10:59 | 2024-03-29 | 2024-03-29 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.331 | A.1011181.331.01 | 7" Surface (Slim) | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.070081 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-03-23 | 2024-03-23 03:00 | 2024-03-24 | 2024-03-24 | 2024-03-24 23:59 | 2024-03-26 | 2024-03-25 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.330 | A.1011181.330.02 | 4.5" Production | SANTOS LIMITED | ADZUKI 1 | ENSIGN 974 | J.23.067833 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-17 10:00 | 2023-08-17 10:00 | 2023-08-18 | 2023-08-18 10:00 | 2023-08-19 10:59 | 2023-08-20 | 2023-08-20 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-20 15:01 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.330 | A.1011181.330.01 | 7-5/8" Surface | SANTOS LIMITED | ADZUKI 1 | ENSIGN 974 | J.23.067823 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-14 | 2023-08-14 03:00 | 2023-08-15 | 2023-08-15 | 2023-08-15 23:59 | 2023-08-17 | 2023-08-16 | AUS East Coast WS | MMendoza26 | 2023-07-20 15:01 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.33 | A.1011181.33.01 | 9 5/8" Surface Cement job | SANTOS LIMITED | Tarwonga 7 | ENSIGN 971 | J.21.109162 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-11 11:00 | 2021-04-12 01:00 |  | 2021-04-12 09:00 | 2021-04-13 00:59 |  | 2021-04-14 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 39527.24 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.33 | A.1011181.33.02 | Tarwonga 7 7" HZ Intermediate | SANTOS LIMITED | Tarwonga 7 | ENSIGN 971 | J.21.109112 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-17 12:00 | 2021-04-18 01:00 |  | 2021-04-18 01:00 | 2021-04-19 00:59 |  | 2021-04-20 11:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:20 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 51414.36 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.329 | A.1011181.329.02 | 4.5" Production (Slim) | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.067831 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-28 10:00 | 2023-11-28 10:00 | 2023-11-29 | 2023-11-29 10:00 | 2023-11-30 10:59 | 2023-12-01 | 2023-12-01 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.329 | A.1011181.329.01 | 7" Surface (Slim) | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.23.067821 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-11-25 | 2023-11-25 03:00 | 2023-11-26 | 2023-11-26 | 2023-11-26 23:59 | 2023-11-28 | 2023-11-27 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.328 | A.1011181.328.02 | 4.5" Production | SANTOS LIMITED | NAPOWIE 13 | ENSIGN 974 | J.23.067824 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-10 10:00 | 2023-07-10 10:00 | 2023-07-11 | 2023-07-11 10:00 | 2023-07-12 10:59 | 2023-07-13 | 2023-07-13 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-20 10:27 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.328 | A.1011181.328.01 | 7-5/8" Surface | SANTOS LIMITED | NAPOWIE 13 | ENSIGN 974 | J.23.067820 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-29 | 2023-06-29 03:00 | 2023-06-30 | 2023-06-30 | 2023-06-30 23:59 | 2023-07-02 | 2023-07-01 | AUS East Coast WS | MMendoza26 | 2023-07-20 10:18 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.327 | A.1011181.327.01 | 7-5/8" Surface | SANTOS LIMITED | MERUPA 5 | ENSIGN 974 | J.23.067808 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-17 | 2023-06-17 03:00 | 2023-06-18 | 2023-06-18 | 2023-06-18 23:59 | 2023-06-20 | 2023-06-19 | AUS East Coast WS | MMendoza26 | 2023-09-04 18:04 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.327 | A.1011181.327.02 | 4.5" Production | SANTOS LIMITED | MERUPA 5 | ENSIGN 974 | J.23.067816 | WCF | PRI-LONG | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-25 10:00 | 2023-06-25 10:00 | 2023-06-26 | 2023-06-26 10:00 | 2023-06-27 10:59 | 2023-06-28 | 2023-06-28 10:00 | AUS East Coast WS | MMendoza26 | 2023-06-27 13:47 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.326 | A.1011181.326.02 | 4.5" Production | SANTOS LIMITED | MERUPA 4 | ENSIGN 974 | J.23.067817 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-13 10:00 | 2023-06-13 10:00 |  | 2023-06-14 10:00 | 2023-06-15 10:59 |  | 2023-06-16 10:00 | AUS East Coast WS | MMendoza26 | 2023-06-20 16:03 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.326 | A.1011181.326.01 | 7-5/8" Surface | SANTOS LIMITED | MERUPA 4 | ENSIGN 974 | J.23.067805 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-31 | 2023-05-31 03:00 |  | 2023-06-07 | 2023-06-07 23:59 |  | 2023-06-08 | AUS East Coast WS | MMendoza26 | 2023-06-19 18:10 | DTree |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.325 | A.1011181.325.02 | 4-1/2" Production | SANTOS LIMITED | NAPOWIE 12 | ENSIGN 974 | J.23.067810 | WCF | PRI-LONG | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-25 10:00 | 2023-05-25 10:00 |  | 2023-05-31 10:00 | 2023-06-01 10:59 |  | 2023-06-02 10:00 | AUS East Coast WS | MMendoza26 | 2023-06-06 10:53 | ATimbs |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.325 | A.1011181.325.01 | 7-5/8" Surface | SANTOS LIMITED | NAPOWIE 12 | ENSIGN 974 | J.23.067803 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-22 | 2023-05-22 03:00 |  | 2023-05-23 | 2023-05-23 23:59 |  | 2023-05-24 | AUS East Coast WS | MMendoza26 | 2023-05-24 15:58 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.324 | A.1011181.324.02 | 4.5" Production | SANTOS LIMITED | NAPOWIE 11 | ENSIGN 974 | J.23.067813 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-05-15 10:00 | 2023-05-15 10:00 |  | 2023-05-16 10:00 | 2023-05-17 10:59 |  | 2023-05-18 10:00 | AUS East Coast WS | MMendoza26 | 2023-05-24 11:56 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 33828.45 | 1 |  |  |  | 93.8 | 50 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.324 | A.1011181.324.01 | 7.625" surface | SANTOS LIMITED | NAPOWIE 11 | ENSIGN 974 | J.23.067801 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-05 | 2023-05-05 03:00 |  | 2023-05-06 | 2023-05-06 23:59 |  | 2023-05-07 | AUS East Coast WS | MMendoza26 | 2023-05-12 17:46 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 31995.66 | 1 |  |  |  | 87.5 | 66.7 | 0 | 50 | 65 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.323 | A.1011181.323.02 | 4.5" Production | SANTOS LIMITED | TIRRAWARRA 107 | ENSIGN 974 | J.23.067806 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-28 10:00 | 2023-04-28 10:00 |  | 2023-04-29 10:00 | 2023-04-30 10:59 |  | 2023-05-01 10:00 | AUS East Coast WS | MMendoza26 | 2023-05-24 11:02 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 32713.63 | 1 |  |  |  | 56.3 | 66.7 | 0 | 100 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.323 | A.1011181.323.01 | 7 5/8" Surface (Slim) | SANTOS LIMITED | TIRRAWARRA 107 | ENSIGN 974 | J.23.067800 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-20 | 2023-04-20 03:00 |  | 2023-04-21 | 2023-04-21 23:59 |  | 2023-04-22 | AUS East Coast WS | MMendoza26 | 2023-04-24 13:20 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 27278.93 | 1 |  |  |  | 87.5 | 66.7 | 100 | 100 | 85 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.322 | A.1011181.322.02 | 5-1/2" Production | SANTOS LIMITED | Well #1 | SLR 188 | J.23.067783 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-19 10:00 | 2023-08-20 11:00 | 2023-08-20 | 2023-08-20 11:00 | 2023-08-21 10:59 | 2023-08-22 | 2023-08-22 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.322 | A.1011181.322.01 | 9-5/8" Surface | SANTOS LIMITED | Well #1 | SLR 188 | J.23.067774 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-15 22:00 | 2023-08-16 | 2023-08-16 | 2023-08-16 | 2023-08-16 23:59 | 2023-08-17 | 2023-08-17 22:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:37 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.321 | A.1011181.321.02 | 4.5" Production | SANTOS LIMITED | PSYCHE 9 | SLR 188 | J.23.067781 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-30 10:00 | 2023-07-31 11:00 | 2023-07-31 | 2023-07-31 11:00 | 2023-08-01 10:59 | 2023-08-02 | 2023-08-02 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-30 20:04 | GVang2 |  | No |  |  |  |  | Mark Mendoza |  | 10266.61 | 1 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.321 | A.1011181.321.01 | 7" Surface | SANTOS LIMITED | PSYCHE 9 | SLR 188 | J.23.067773 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-26 22:00 | 2023-07-27 | 2023-07-27 | 2023-07-27 | 2023-07-27 23:59 | 2023-07-28 | 2023-07-28 22:59 | AUS East Coast WS | MMendoza26 | 2023-07-25 10:16 | TTruong7 |  | No |  |  |  |  | Mark Mendoza |  | 10266.61 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.320 | A.1011181.320.02 | 4.5" Production | SANTOS LIMITED | PSYCHE 8 | SLR 188 | J.23.067778 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-18 10:00 | 2023-07-19 11:00 | 2023-07-19 | 2023-07-19 11:00 | 2023-07-20 10:59 | 2023-07-21 | 2023-07-21 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-25 01:13 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.320 | A.1011181.320.01 | 7" Surface (Slim) | SANTOS LIMITED | PSYCHE 8 | SLR 188 | J.23.109773 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-14 22:00 | 2023-07-15 | 2023-07-15 | 2023-07-15 | 2023-07-15 23:59 | 2023-07-16 | 2023-07-16 22:59 | AUS East Coast WS | MMendoza26 | 2023-07-20 10:16 | TTruong7 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.32 | A.1011181.32.01 | 7 5/8" Surface | SANTOS LIMITED | Tarwonga 6 | ENSIGN 971 | J.21.109155 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-30 11:00 | 2021-03-31 23:00 |  | 2021-03-31 23:00 | 2021-04-01 22:59 |  | 2021-04-02 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 26608.38 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.32 | A.1011181.32.02 | 4 1/2" Production (hot) | SANTOS LIMITED | Tarwonga 6 | ENSIGN 971 | J.21.109116 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-06 10:00 | 2021-04-06 23:00 |  | 2021-04-06 23:00 | 2021-04-07 22:59 |  | 2021-04-09 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:20 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 40781.3 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.319 | A.1011181.319.01 | 7" Surface | SANTOS LIMITED | WINNINIA NORTH 6 | SLR 188 | J.23.067770 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-30 22:00 | 2023-07-01 | 2023-07-01 | 2023-07-01 | 2023-07-01 23:59 | 2023-07-02 | 2023-07-02 22:59 | AUS East Coast WS | MMendoza26 | 2023-07-24 18:20 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.319 | A.1011181.319.02 | 4.5" Production | SANTOS LIMITED | WINNINIA NORTH 6 | SLR 188 | J.23.067776 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-07-06 10:00 | 2023-07-07 11:00 | 2023-07-07 | 2023-07-07 11:00 | 2023-07-08 10:59 | 2023-07-09 | 2023-07-09 10:00 | AUS East Coast WS | MMendoza26 | 2023-07-20 10:51 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.318 | A.1011181.318.02 | 4.5" Production | SANTOS LIMITED | WINNINIA NORTH 5 | SLR 188 | J.23.067772 | WCF | PRI-LONG | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-25 10:00 | 2023-06-26 11:00 | 2023-06-26 | 2023-06-26 11:00 | 2023-06-27 10:59 | 2023-06-28 | 2023-06-28 10:00 | AUS East Coast WS | MMendoza26 | 2023-06-27 14:03 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.318 | A.1011181.318.01 | 7-5/8" Surface | SANTOS LIMITED | WINNINIA NORTH 5 | SLR 188 | J.23.067769 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-15 22:00 | 2023-06-16 | 2023-06-16 | 2023-06-16 | 2023-06-16 23:59 | 2023-06-17 | 2023-06-17 22:59 | AUS East Coast WS | MMendoza26 | 2023-06-27 13:34 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 87.5 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.317 | A.1011181.317.02 | 5.5" Intermediate | SANTOS LIMITED | Well #1 | ENSIGN 971 | J.23.062437 | WCF | PRI-INTER | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-01-05 13:00 | 2024-01-07 01:00 | 2024-01-06 23:00 | 2024-01-07 13:00 | 2024-01-09 00:59 | 2024-01-09 23:00 | 2024-01-07 00:59 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:07 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.317 | A.1011181.317.01 | 9 5/8" Surface | SANTOS LIMITED | Well #1 | ENSIGN 971 | J.23.062436 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-12-28 01:00 | 2023-12-30 | 2023-12-29 23:00 | 2023-12-30 | 2023-12-30 23:59 | 2024-01-01 23:00 | 2023-12-29 00:59 | AUS East Coast WS | MMendoza26 | 2023-07-20 16:07 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.316 | A.1011181.316.01 | Recompletion | SANTOS LIMITED | ACRUS 1 | Wild Desert Rig 6 | J.23.059091 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-29 23:00 | 2023-04-29 23:00 |  | 2023-04-30 23:00 | 2023-05-01 22:59 |  | 2023-05-02 22:59 | AUS East Coast WS | MMendoza26 | 2023-05-23 10:07 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 87.5 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.315 | A.1011181.315.01 | Plug 1A | SANTOS LIMITED | MARABOOKA 2 | Wild Desert Rig 16 | J.23.058778 | WCF | REM-PA | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-24 23:00 | 2023-03-23 23:00 |  | 2023-03-24 23:00 | 2023-03-25 22:59 |  | 2023-03-25 22:59 | AUS East Coast WS | MMendoza26 | 2023-05-27 15:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 9444.97 | 2 |  |  |  | 81.3 | 66.7 | 100 | 50 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.314 | A.1011181.314.01 | Plug 1A | SANTOS LIMITED | STRZELECKI 29 | Wild Desert Rig 22 | J.23.043580 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-05 | 2023-03-05 |  | 2023-03-05 | 2023-03-05 23:59 |  | 2023-03-05 23:59 | AUS East Coast WS | MMendoza26 | 2023-03-09 10:59 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 9838.51 | 2 |  |  |  | 50 | 33.3 | 0 | 100 | 50 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.313 | A.1011181.313.02 | 4 1/2" Production (hot) | SANTOS LIMITED | MOOMBA 294 | ENSIGN 971 | J.23.037811 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-03 | 2023-03-03 |  | 2023-03-03 | 2023-03-03 23:59 |  | 2023-03-03 23:59 | AUS East Coast WS | MMendoza26 | 2023-02-23 13:59 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 48874.16 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.313 | A.1011181.313.01 | 7" Surface | SANTOS LIMITED | MOOMBA 294 | ENSIGN 971 | J.23.037810 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-25 23:00 | 2023-02-25 23:00 |  | 2023-02-25 23:00 | 2023-02-26 22:59 |  | 2023-02-26 23:59 | AUS East Coast WS | MMendoza26 | 2023-02-20 15:47 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 30086.7 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.312 | A.1011181.312.06 | Plug 1G | SANTOS LIMITED | MARABOOKA 1 | Wild Desert Rig 16 | J.23.044742 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-15 | 2023-03-15 |  | 2023-03-15 | 2023-03-15 23:59 |  | 2023-03-15 23:59 | AUS East Coast WS | MMendoza26 | 2023-03-14 15:43 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 9838.51 | 2 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.312 | A.1011181.312.03 | Plug 1E | SANTOS LIMITED | MARABOOKA 1 | Wild Desert Rig 16 | J.23.037432 | WCF | REM-PA,REM-SQ | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-15 | 2023-03-15 |  | 2023-03-15 | 2023-03-15 23:59 |  | 2023-03-15 23:59 | AUS East Coast WS | MMendoza26 | 2023-03-14 14:56 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 9793.87 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.312 | A.1011181.312.04 | Plug 1F | SANTOS LIMITED | MARABOOKA 1 | Wild Desert Rig 16 | J.23.037433 | WCF | REM-PA,REM-SQ | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-16 | 2023-03-16 |  | 2023-03-16 | 2023-03-16 23:59 |  | 2023-03-16 23:59 | AUS East Coast WS | MMendoza26 | 2023-03-14 13:04 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 9838.51 | 2 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.312 | A.1011181.312.02 | Plug 1B 1C 1D | SANTOS LIMITED | MARABOOKA 1 | Wild Desert Rig 16 | J.23.037430 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-11 | 2023-03-11 |  | 2023-03-11 | 2023-03-11 23:59 |  | 2023-03-11 23:59 | AUS East Coast WS | MMendoza26 | 2023-03-14 12:10 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10748.93 | 3 |  |  |  | 81.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.312 | A.1011181.312.05 | Cancelled | SANTOS LIMITED | MARABOOKA 1 | Wild Desert Rig 16 | J.23.044704 | WCF | REM-PA | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2023-03-12 |  | 2023-03-15 | 2023-03-18 23:59 |  |  | AUS East Coast WS | MMendoza26 | 2023-02-27 12:49 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.312 | A.1011181.312.01 | Plug 1A | SANTOS LIMITED | MARABOOKA 1 | Wild Desert Rig 16 | J.23.037428 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-02-24 | 2023-02-24 |  | 2023-02-24 | 2023-02-24 23:59 |  | 2023-02-24 23:59 | AUS East Coast WS | MMendoza26 | 2023-02-27 12:11 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 9838.51 | 2 |  |  |  | 87.5 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.311 | A.1011181.311.01 | Plug 1A | SANTOS LIMITED | STRZELECKI 14 | Wild Desert Rig 16 | J.23.031101 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-02 | 2023-07-01 | 2023-07-02 | 2023-07-02 | 2023-07-02 23:59 | 2023-07-03 | 2023-07-02 23:59 | AUS East Coast WS | MMendoza26 | 2023-07-20 02:09 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10080.28 | 2 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.310 | A.1011181.310.01 | Plug 1A | SANTOS LIMITED | STRZELECKI 5 | Wild Desert Rig 16 | J.23.030043 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-25 | 2023-01-25 |  | 2023-01-25 | 2023-01-25 23:59 |  | 2023-01-25 23:59 | AUS East Coast WS | MMendoza26 | 2023-02-22 13:19 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 9838.51 | 2 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.31 | A.1011181.31.01 | 9 5/8" Surface | SANTOS LIMITED | Big Lake 155 | ENSIGN 974 | J.21.109472 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-30 10:00 | 2021-04-29 |  | 2021-04-30 | 2021-04-30 23:59 |  | 2021-05-01 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:08 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 34146.28 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.31 | A.1011181.31.03 | Big Lake 155 Plug 1A and 1B | SANTOS LIMITED | Big Lake 155 | ENSIGN 974 | J.21.109240 | WCF | REM-PA | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-15 10:00 | 2021-05-14 |  | 2021-05-14 | 2021-05-14 23:59 |  | 2021-05-16 10:59 | AUS East Coast WS | GSingh54 | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 37021.8 | 0 |  |  |  | 81.3 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.31 | A.1011181.31.02 | 7" Intermediate | SANTOS LIMITED | Big Lake 155 | ENSIGN 974 | J.21.109144 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-06 11:00 | 2021-05-06 |  | 2021-05-07 | 2021-05-07 23:59 |  | 2021-05-09 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 37021.8 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.309 | A.1011181.309.01 | Plug 1A | SANTOS LIMITED | STREZLECKI 17 | Wild Desert Rig 16 | J.23.026825 | WCF | REM-PA | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2023-01-17 | 2023-01-17 |  | 2023-01-17 | 2023-01-17 23:59 |  | 2023-01-17 23:59 | AUS East Coast WS | MMendoza26 | 2023-01-25 14:55 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 9444.97 | 2 |  |  |  | 87.5 | 50 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.308 | A.1011181.308.02 | 4.5" Production | SANTOS LIMITED | BIG LAKE 164 | SLR RIG 183 | J.23.026448 | WCF | PRI-INTER | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2023-01-28 20:00 | 2023-01-29 10:00 |  | 2023-01-29 10:00 | 2023-01-30 09:59 |  | 2023-01-31 19:59 | AUS East Coast WS | GVang2 | 2023-05-27 15:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 56297.98 | 1 |  |  |  | 87.5 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.308 | A.1011181.308.01 | 7-5/8" Surface | SANTOS LIMITED | BIG LAKE 164 | SLR RIG 183 | J.23.026446 | WCF | PRI-SURF | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-22 21:00 | 2023-01-22 23:00 |  | 2023-01-22 23:00 | 2023-01-23 22:59 |  | 2023-01-24 21:59 | AUS East Coast WS | GVang2 | 2023-01-24 17:16 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 39662.97 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.307 | A.1011181.307.02 | 4 1/2" Production (hot) | SANTOS LIMITED | Well #1 | ENSIGN 971 | J.23.025631 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-01-12 | 2024-01-12 | 2024-01-12 | 2024-01-12 | 2024-01-12 23:59 | 2024-01-14 | 2024-01-12 23:59 | AUS East Coast WS | GVang2 | 2023-07-20 16:08 | MMendoza26 |  | No |  |  |  |  | Gaurav Kumar Singh |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.307 | A.1011181.307.01 | 7 5/8" Surface | SANTOS LIMITED | Well #1 | ENSIGN 971 | J.23.025626 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-01-05 23:00 | 2024-01-06 23:00 | 2024-01-05 23:00 | 2024-01-06 23:00 | 2024-01-07 22:59 | 2024-01-07 23:00 | 2024-01-08 23:59 | AUS East Coast WS | GVang2 | 2023-07-20 16:08 | MMendoza26 |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.306 | A.1011181.306.02 | 4 1/2" Production (Slim, Hot) | SANTOS LIMITED | MOOMBA 299 | ENSIGN 971 | J.23.025632 | WCF | PRI-LONG | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2023-05-17 | 2023-05-17 |  | 2023-05-17 | 2023-05-17 23:59 |  | 2023-05-17 23:59 | AUS East Coast WS | GVang2 | 2023-05-23 11:55 | ATimbs |  | No |  |  |  |  | Grace Vang |  | 46448.96 | 1 |  |  |  | 93.8 | 50 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.306 | A.1011181.306.01 | 7" Surface (Slim) | SANTOS LIMITED | MOOMBA 299 | ENSIGN 971 | J.23.025625 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-05-08 23:00 | 2023-05-07 23:00 |  | 2023-05-08 23:00 | 2023-05-09 22:59 |  | 2023-05-09 23:59 | AUS East Coast WS | GVang2 | 2023-05-22 17:35 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 93.8 | 50 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.305 | A.1011181.305.01 | 7 5/8" Surface | SANTOS LIMITED | MOOMBA 300 | ENSIGN 971 | J.23.025622 | WCF | PRI-SURF | Low | Unconfirmed - 10% | Design - CEC |  | Design Completed | Design Completed | In Progress | 2023-04-26 23:00 | 2023-04-25 23:00 | 2023-04-25 | 2023-04-26 23:00 | 2023-04-27 22:59 | 2023-04-28 | 2023-04-27 23:59 | AUS East Coast WS | GVang2 | 2025-08-25 13:47 | MAngarita2 |  | No |  |  |  |  | Ariel Lyons |  | 34956.22 | 1 |  | L0 - No RO |  | 87.5 | 66.7 | 0 | 50 | 65 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.305 | A.1011181.305.02 | 4 1/2" Production (hot) | SANTOS LIMITED | MOOMBA 300 | ENSIGN 971 | J.23.025628 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-07 | 2023-05-07 |  | 2023-05-07 | 2023-05-07 23:59 |  | 2023-05-07 23:59 | AUS East Coast WS | GVang2 | 2023-05-23 13:57 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 42571.37 | 1 |  |  |  | 87.5 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.304 | A.1011181.304.02 | 4 1/2" Production (hot) | SANTOS LIMITED | MOOMBA 297 | ENSIGN 971 | J.23.025629 | WCF | PRI-LONG | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-20 | 2023-04-20 |  | 2023-04-22 | 2023-04-22 23:59 |  | 2023-04-20 23:59 | AUS East Coast WS | GVang2 | 2023-04-25 07:30 | ATimbs |  | No |  |  |  |  | Grace Vang |  | 46554.35 | 1 |  |  |  | 87.5 | 66.7 | 100 | 100 | 85 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.304 | A.1011181.304.01 | 7" Surface | SANTOS LIMITED | MOOMBA 297 | ENSIGN 971 | J.23.025623 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-09 23:00 | 2023-04-09 23:00 |  | 2023-04-09 23:00 | 2023-04-10 22:59 |  | 2023-04-10 23:59 | AUS East Coast WS | GVang2 | 2023-04-20 14:45 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 25478.48 | 1 |  |  |  | 81.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.303 | A.1011181.303.02 | 5.5" Intermediate | SANTOS LIMITED | CUISINIER 34 | Ensign 967 | J.23.062522 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-24 13:00 | 2023-04-26 01:00 |  | 2023-04-26 13:00 | 2023-04-28 00:59 |  | 2023-04-26 00:59 | AUS East Coast WS | GVang2 | 2023-05-24 10:06 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 41289.19 | 1 |  |  |  | 87.5 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.303 | A.1011181.303.01 | 9 5/8" Surface | SANTOS LIMITED | CUISINIER 34 | Ensign 967 | J.23.062521 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-04-18 01:00 | 2023-04-20 |  | 2023-04-20 | 2023-04-20 23:59 |  | 2023-04-19 00:59 | AUS East Coast WS | GVang2 | 2023-04-26 10:24 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 29534.12 | 1 |  |  |  | 62.5 | 50 | 0 | 25 | 45 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.302 | A.1011181.302.02 | 5.5" Production | SANTOS LIMITED | CUISINIER 33 | Ensign 967 | J.23.062520 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-04-12 13:00 | 2023-04-14 01:00 |  | 2023-04-14 13:00 | 2023-04-16 00:59 |  | 2023-04-14 00:59 | AUS East Coast WS | GVang2 | 2023-04-21 11:19 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 54111 | 0 |  |  |  | 93.8 | 50 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.302 | A.1011181.302.01 | 9 5/8" Surface | SANTOS LIMITED | CUISINIER 33 | Ensign 967 | J.23.062519 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-08 01:00 | 2023-04-10 |  | 2023-04-10 | 2023-04-10 23:59 |  | 2023-04-09 00:59 | AUS East Coast WS | GVang2 | 2023-04-20 12:36 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 28502.45 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.301 | A.1011181.301.02 | 5.5" Production | SANTOS LIMITED | CUISINIER 32 | Ensign 967 | J.23.025614 | WCF | PRI-INTER | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2023-05-15 12:00 | 2023-05-16 |  | 2023-05-16 12:00 | 2023-05-17 23:59 |  | 2023-05-18 23:59 | AUS East Coast WS | GVang2 | 2023-05-27 14:53 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 54111 | 1 |  |  |  | 87.5 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.301 | A.1011181.301.01 | 9 5/8" Surface | SANTOS LIMITED | CUISINIER 32 | Ensign 967 | J.23.025607 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-29 | 2023-04-29 23:00 |  | 2023-04-30 01:00 | 2023-05-01 00:59 |  | 2023-05-02 23:59 | AUS East Coast WS | GVang2 | 2023-05-22 14:53 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 28679 | 1 |  |  |  | 87.5 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.300 | A.1011181.300.02 | 4.5" Production | SANTOS LIMITED | TIGON 1 | Ensign 967 | J.23.025613 | WCF | PRI-INTER | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-18 12:00 | 2023-05-20 |  | 2023-05-30 12:00 | 2023-05-31 23:59 |  | 2023-06-03 23:59 | AUS East Coast WS | GVang2 | 2023-05-30 14:59 | ATimbs |  | No |  |  |  |  | Grace Vang |  | 10560.94 | 1 |  |  |  | 81.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.300 | A.1011181.300.01 | 7-5/8" Surface | SANTOS LIMITED | TIGON 1 | Ensign 967 | J.23.025605 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-08 | 2023-05-10 23:00 |  | 2023-05-10 23:00 | 2023-05-11 22:59 |  | 2023-05-13 23:59 | AUS East Coast WS | GVang2 | 2023-05-23 09:47 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.30 | A.1011181.30.01 | 9 5/8" Surface | SANTOS LIMITED | Beckler 7 | ENSIGN 974 | J.21.109474 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-07 10:00 | 2021-04-06 23:00 |  | 2021-04-07 23:00 | 2021-04-08 22:59 |  | 2021-04-10 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:08 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 25662.85 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.30 | A.1011181.30.02 | 7" Intermediate | SANTOS LIMITED | Beckler 7 | ENSIGN 974 | J.21.109154 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-14 09:00 | 2021-04-12 23:00 |  | 2021-04-13 23:00 | 2021-04-14 22:59 |  | 2021-04-15 08:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 43461.57 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.299 | A.1011181.299.02 | 5.5" Intermediate | SANTOS LIMITED | CUISINIER 31 | Ensign 967 | J.23.025610 | WCF | PRI-INTER | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-01 11:00 | 2023-04-02 23:00 |  | 2023-04-03 11:00 | 2023-04-04 22:59 |  | 2023-04-02 22:59 | AUS East Coast WS | GVang2 | 2023-05-27 15:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 54111 | 1 |  |  |  | 87.5 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.299 | A.1011181.299.01 | 9 5/8" Surface | SANTOS LIMITED | CUISINIER 31 | Ensign 967 | J.23.025603 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-27 23:00 | 2023-03-29 22:00 |  | 2023-03-29 22:00 | 2023-03-30 21:59 |  | 2023-03-28 22:59 | AUS East Coast WS | GVang2 | 2023-04-11 15:40 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 32444.78 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.298 | A.1011181.298.01 | 7 5/8" Surface | SANTOS LIMITED | COLOY 1 | Ensign 967 | J.23.025602 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-10 23:00 | 2023-03-12 22:00 |  | 2023-03-12 22:00 | 2023-03-13 21:59 |  | 2023-03-11 22:59 | AUS East Coast WS | GVang2 | 2023-03-27 00:55 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 36374.92 | 1 |  |  |  | 68.8 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.298 | A.1011181.298.02 | 4.5" Intermediate | SANTOS LIMITED | COLOY 1 | Ensign 967 | J.23.025608 | WCF | PRI-INTER | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2023-03-15 11:00 | 2023-03-16 23:00 |  | 2023-03-23 11:00 | 2023-03-24 22:59 |  | 2023-03-16 22:59 | AUS East Coast WS | GVang2 | 2023-03-24 20:33 | ATimbs |  | No |  |  |  |  | Grace Vang |  | 54111 | 1 |  |  |  | 87.5 | 66.7 | 0 | 50 | 65 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.297 | A.1011181.297.02 | 5.5" Intermediate | SANTOS LIMITED | MAYA 2 | Ensign 967 | J.23.025599 | WCF | PRI-INTER,PRI-LONG | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-26 12:00 | 2023-03-03 |  | 2023-03-03 12:00 | 2023-03-04 23:59 |  | 2023-03-02 23:59 | AUS East Coast WS | GVang2 | 2023-03-11 18:25 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 54111 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.297 | A.1011181.297.01 | 9 5/8" Surface | SANTOS LIMITED | MAYA 2 | Ensign 967 | J.23.025594 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-22 | 2023-02-23 23:00 |  | 2023-02-23 23:00 | 2023-02-24 22:59 |  | 2023-02-22 23:59 | AUS East Coast WS | GVang2 | 2023-02-23 12:11 | NAbosnina |  | No |  |  |  |  | Grace Vang |  | 7597.63 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.296 | A.1011181.296.01 | 7 5/8" Surface | SANTOS LIMITED | DAMPIERRE 1 | Ensign 967 | J.23.025592 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-02-11 | 2023-02-12 23:00 |  | 2023-02-12 23:00 | 2023-02-13 22:59 |  | 2023-02-13 22:59 | AUS East Coast WS | GVang2 | 2023-02-22 11:54 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10345.22 | 1 |  |  |  | 87.5 | 50 | 0 | 50 | 60 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.296 | A.1011181.296.02 | 4 1/2" Production | SANTOS LIMITED | DAMPIERRE 1 | Ensign 967 | J.23.025596 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-15 12:00 | 2023-02-17 |  | 2023-02-17 12:00 | 2023-02-18 23:59 |  | 2023-02-16 23:59 | AUS East Coast WS | GVang2 | 2023-02-21 10:57 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10296.9 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.295 | A.1011181.295.02 | 4.5" Intermediate | SANTOS LIMITED | INDIGO 1 | Ensign 967 | J.23.025597 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-30 12:00 | 2023-02-01 |  | 2023-02-01 12:00 | 2023-02-02 23:59 |  | 2023-01-31 23:59 | AUS East Coast WS | GVang2 | 2023-02-20 10:35 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 43229.13 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.295 | A.1011181.295.01 | 7 5/8" Surface | SANTOS LIMITED | INDIGO 1 | Ensign 967 | J.23.025590 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-26 | 2023-01-27 23:00 |  | 2023-01-27 23:00 | 2023-01-28 22:59 |  | 2023-01-26 23:59 | AUS East Coast WS | GVang2 | 2023-02-09 10:10 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 31700.33 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.294 | A.1011181.294.02 | 5.5" Intermediate | SANTOS LIMITED | TEQUILA 2 | Ensign 967 | J.23.025595 | WCF | PRI-INTER | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-17 12:00 | 2023-01-19 |  | 2023-01-19 12:00 | 2023-01-20 23:59 |  | 2023-01-18 23:59 | AUS East Coast WS | GVang2 | 2023-05-27 15:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 50383.81 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.294 | A.1011181.294.01 | 9 5/8" Surface | SANTOS LIMITED | TEQUILA 2 | Ensign 967 | J.23.025589 | WCF | PRI-SURF | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2023-01-13 | 2023-01-14 23:00 |  | 2023-01-14 23:00 | 2023-01-15 22:59 |  | 2023-01-13 23:59 | AUS East Coast WS | GVang2 | 2023-01-24 16:07 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 34068.8 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.293 | A.1011181.293.02 | 4.5" Production | SANTOS LIMITED | DULLINGARI NORTH 27 | SLR 188 | J.23.025587 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-02 21:00 | 2023-06-05 11:00 |  | 2023-06-05 11:00 | 2023-06-06 10:59 |  | 2023-06-05 20:59 | AUS East Coast WS | GVang2 | 2023-06-13 11:33 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.293 | A.1011181.293.01 | 7-5/8" Surface | SANTOS LIMITED | DULLINGARI NORTH 27 | SLR 188 | J.23.025582 | WCF | PRI-SURF | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-27 22:00 | 2023-05-30 |  | 2023-05-30 | 2023-05-30 23:59 |  | 2023-05-29 22:59 | AUS East Coast WS | GVang2 | 2023-05-29 11:56 | ATimbs |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.292 | A.1011181.292.02 | 4.5" Production | SANTOS LIMITED | DULLINGARI NORTH 26 | SLR 188 | J.23.025588 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-20 21:00 | 2023-05-23 11:00 |  | 2023-05-23 11:00 | 2023-05-24 10:59 |  | 2023-05-23 20:59 | AUS East Coast WS | GVang2 | 2023-05-29 09:28 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 66.7 | 50 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.292 | A.1011181.292.01 | 7-5/8" Surface | SANTOS LIMITED | DULLINGARI NORTH 26 | SLR 188 | J.23.025581 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-08 22:00 | 2023-05-15 |  | 2023-05-15 | 2023-05-15 23:59 |  | 2023-05-14 22:59 | AUS East Coast WS | GVang2 | 2023-05-23 09:58 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 87.5 | 50 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.291 | A.1011181.291.02 | 4.5" Production | SANTOS LIMITED | Well #1 | SLR 188 | J.23.025585 | WCF | PRI-INTER | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-04-19 21:00 | 2024-04-22 11:00 | 2024-04-22 | 2024-04-22 11:00 | 2024-04-23 10:59 | 2024-04-24 | 2024-04-22 20:59 | AUS East Coast WS | GVang2 | 2023-07-21 13:38 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.291 | A.1011181.291.01 | 7-5/8" Surface | SANTOS LIMITED | Well #1 | SLR 188 | J.23.025580 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2024-04-13 22:00 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 2024-04-16 23:59 | 2024-04-17 | 2024-04-15 22:59 | AUS East Coast WS | GVang2 | 2023-07-21 13:38 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.290 | A.1011181.290.02 | 4.5" Production | SANTOS LIMITED | DORODILLO 8 | SLR 188 | J.23.025584 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-22 21:00 | 2023-04-25 11:00 |  | 2023-04-25 11:00 | 2023-04-26 10:59 |  | 2023-04-25 20:59 | AUS East Coast WS | GVang2 | 2023-04-21 12:09 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10422.71 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.290 | A.1011181.290.01 | 7-5/8" Surface | SANTOS LIMITED | DORODILLO 8 | SLR 188 | J.23.025579 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-16 22:00 | 2023-04-17 |  | 2023-04-19 | 2023-04-19 23:59 |  | 2023-04-18 22:59 | AUS East Coast WS | GVang2 | 2023-04-19 13:37 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.29 | A.1011181.29.02 | 4.5" Production Job | SANTOS LIMITED | Houby 1 | Ensign 967 | J.21.109146 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-16 11:00 | 2021-05-17 06:00 |  | 2021-05-17 08:00 | 2021-05-17 16:59 |  | 2021-05-19 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 37257.69 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.29 | A.1011181.29.01 | 7 5/8 Surface | SANTOS LIMITED | Houby 1 | Ensign 967 | J.21.109106 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-04 11:00 | 2021-05-05 |  | 2021-05-05 | 2021-05-05 23:59 |  | 2021-05-07 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:20 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 29302.74 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.289 | A.1011181.289.01 | 7-5/8" Surface | SANTOS LIMITED | ARRAKIS 2 | SLR 188 | J.23.025570 | WCF | PRI-SURF | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-04 22:00 | 2023-05-05 |  | 2023-05-05 | 2023-05-05 23:59 |  | 2023-05-06 22:59 | AUS East Coast WS | GVang2 | 2023-05-23 14:23 | ATimbs |  | No |  |  |  |  | Grace Vang |  | 7519.02 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.289 | A.1011181.289.02 | 4.5" Production | SANTOS LIMITED | ARRAKIS 2 | SLR 188 | J.23.025576 | WCF | PRI-LONG | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-08 10:00 | 2023-05-09 11:00 |  | 2023-05-09 11:00 | 2023-05-10 10:59 |  | 2023-05-11 10:00 | AUS East Coast WS | GVang2 | 2023-05-22 17:13 | ATimbs |  | No |  |  |  |  | Grace Vang |  | 10266.61 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.288 | A.1011181.288.02 | 4.5" Production | SANTOS LIMITED | DORODILLO 7 | SLR 188 | J.23.025575 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-10 21:00 | 2023-04-13 11:00 |  | 2023-04-13 11:00 | 2023-04-14 10:59 |  | 2023-04-13 20:59 | AUS East Coast WS | GVang2 | 2023-05-09 10:15 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10377.26 | 1 |  |  |  | 81.3 | 16.7 | 0 | 75 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.288 | A.1011181.288.01 | 7-5/8" Surface | SANTOS LIMITED | DORODILLO 7 | SLR 188 | J.23.025572 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-04 22:00 | 2023-04-07 |  | 2023-04-07 | 2023-04-07 23:59 |  | 2023-04-06 22:59 | AUS East Coast WS | GVang2 | 2023-04-12 10:52 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10345.22 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.287 | A.1011181.287.02 | 4.5" Production | SANTOS LIMITED | DORODILLO 5 | SLR 188 | J.23.025573 | WCF | PRI-INTER | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-30 20:00 | 2023-04-30 10:00 |  | 2023-05-01 10:00 | 2023-05-02 09:59 |  | 2023-05-03 19:59 | AUS East Coast WS | GVang2 | 2023-05-27 14:53 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 7438.65 | 1 |  |  |  | 87.5 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.287 | A.1011181.287.01 | 7-5/8" Surface | SANTOS LIMITED | DORODILLO 5 | SLR 188 | J.23.025569 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-25 21:00 | 2023-04-25 23:00 |  | 2023-04-26 23:00 | 2023-04-27 22:59 |  | 2023-04-28 21:59 | AUS East Coast WS | GVang2 | 2023-04-26 14:56 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 7597.63 | 1 |  |  |  | 81.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.286 | A.1011181.286.02 | 4.5" Production | SANTOS LIMITED | DORODILLO 6 | SLR 188 | J.23.025571 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-19 20:00 | 2023-03-22 10:00 |  | 2023-03-26 10:00 | 2023-03-27 09:59 |  | 2023-03-26 19:59 | AUS East Coast WS | GVang2 | 2023-03-28 14:30 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10367.37 | 1 |  |  |  | 81.3 | 66.7 | 50 | 50 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.286 | A.1011181.286.01 | 7-5/8" Surface | SANTOS LIMITED | DORODILLO 6 | SLR 188 | J.23.025568 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-13 21:00 | 2023-03-15 23:00 |  | 2023-03-15 23:00 | 2023-03-16 22:59 |  | 2023-03-15 21:59 | AUS East Coast WS | GVang2 | 2023-03-27 01:16 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10345.22 | 1 |  |  |  | 81.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.285 | A.1011181.285.03 | 4-1/2" Liner | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.080383 | WCF | PRI-INTER | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-06 23:00 | 2023-09-06 12:00 | 2023-09-07 02:00 | 2023-09-07 12:00 | 2023-09-08 12:59 | 2023-09-09 02:00 | 2023-09-09 22:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:54 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.285 | A.1011181.285.02 | 7" Intermediate | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.025565 | WCF | PRI-INTER | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-02 23:00 | 2023-09-02 12:00 | 2023-09-03 02:00 | 2023-09-03 12:00 | 2023-09-04 12:59 | 2023-09-05 02:00 | 2023-09-05 22:59 | AUS East Coast WS | GVang2 | 2023-07-21 13:54 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.285 | A.1011181.285.01 | 9-5/8" Surface | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.025560 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-28 | 2023-08-28 05:00 | 2023-08-29 02:00 | 2023-08-29 02:00 | 2023-08-30 01:59 | 2023-08-30 02:00 | 2023-08-31 00:59 | AUS East Coast WS | GVang2 | 2023-07-21 13:54 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.284 | A.1011181.284.03 | 4-1/2" Liner | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.080375 | WCF | PRI-INTER | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-25 23:00 | 2023-08-26 12:00 | 2023-08-26 02:00 | 2023-08-26 12:00 | 2023-08-27 12:59 | 2023-08-28 02:00 | 2023-08-28 22:59 | AUS East Coast WS | MMendoza26 | 2023-07-20 15:00 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.284 | A.1011181.284.02 | 7" Intermediate | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.025566 | WCF | PRI-INTER | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-20 23:00 | 2023-08-21 12:00 | 2023-08-21 02:00 | 2023-08-21 12:00 | 2023-08-22 12:59 | 2023-08-23 02:00 | 2023-08-23 22:59 | AUS East Coast WS | GVang2 | 2023-07-20 15:00 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.284 | A.1011181.284.01 | 9-5/8" Surface | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.025558 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-15 | 2023-08-15 05:00 | 2023-08-16 02:00 | 2023-08-16 02:00 | 2023-08-17 01:59 | 2023-08-17 02:00 | 2023-08-18 00:59 | AUS East Coast WS | GVang2 | 2023-07-20 15:00 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.283 | A.1011181.283.02 | 4.5" Production | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.025564 | WCF | PRI-INTER | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-15 23:00 | 2023-08-16 12:00 | 2023-08-16 02:00 | 2023-08-16 12:00 | 2023-08-17 12:59 | 2023-08-18 02:00 | 2023-08-18 22:59 | AUS East Coast WS | GVang2 | 2023-07-20 15:01 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.283 | A.1011181.283.01 | 7" Surface | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.025557 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-11 | 2023-08-11 05:00 | 2023-08-12 02:00 | 2023-08-12 02:00 | 2023-08-13 01:59 | 2023-08-13 02:00 | 2023-08-14 00:59 | AUS East Coast WS | GVang2 | 2023-07-20 15:01 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.282 | A.1011181.282.03 | 4-1/2" Liner | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.080381 | WCF | PRI-INTER | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-16 23:00 | 2023-08-17 12:00 | 2023-08-17 02:00 | 2023-08-17 12:00 | 2023-08-18 12:59 | 2023-08-19 02:00 | 2023-08-19 22:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:53 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.282 | A.1011181.282.02 | 7" Intermediate | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.025562 | WCF | PRI-INTER | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-12 23:00 | 2023-08-13 12:00 | 2023-08-13 02:00 | 2023-08-13 12:00 | 2023-08-14 12:59 | 2023-08-15 02:00 | 2023-08-15 22:59 | AUS East Coast WS | GVang2 | 2023-07-21 13:53 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.282 | A.1011181.282.01 | 9-5/8" Surface | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.025556 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-08-10 | 2023-08-09 05:00 | 2023-08-10 02:00 | 2023-08-10 02:00 | 2023-08-11 01:59 | 2023-08-11 02:00 | 2023-08-12 00:59 | AUS East Coast WS | GVang2 | 2023-07-21 13:36 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.281 | A.1011181.281.03 | 4-1/2" Liner | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.080386 | WCF | PRI-INTER | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-10-07 22:00 | 2023-10-08 11:00 | 2023-10-08 01:00 | 2023-10-08 11:00 | 2023-10-09 11:59 | 2023-10-10 01:00 | 2023-10-10 21:59 | AUS East Coast WS | MMendoza26 | 2023-07-21 13:53 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.281 | A.1011181.281.02 | 7" Intermediate | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.025554 | WCF | PRI-INTER | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-10-03 22:00 | 2023-10-04 11:00 | 2023-10-04 01:00 | 2023-10-04 11:00 | 2023-10-05 11:59 | 2023-10-06 01:00 | 2023-10-06 21:59 | AUS East Coast WS | GVang2 | 2023-07-21 13:53 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.281 | A.1011181.281.01 | 9-5/8" Surface | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.23.025553 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-09-28 23:00 | 2023-09-28 04:00 | 2023-09-29 01:00 | 2023-09-29 01:00 | 2023-09-30 00:59 | 2023-09-30 01:00 | 2023-09-30 23:59 | AUS East Coast WS | GVang2 | 2023-07-21 13:53 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.280 | A.1011181.280.03 | Plug 1D | SANTOS LIMITED | TANTANNA 2 | Wild Desert Rig 16 | J.22.134327 | WCF | REM-PA | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-08 | 2023-01-08 |  | 2023-01-08 | 2023-01-08 23:59 |  | 2023-01-08 23:59 | AUS East Coast WS | ALyons | 2023-01-24 12:13 | GSingh54 |  | No |  |  |  |  | Ariel Lyons |  | 9793.87 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.280 | A.1011181.280.01 | Plug 1A | SANTOS LIMITED | TANTANNA 2 | Wild Desert Rig 16 | J.22.134322 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-12-20 | 2022-12-20 |  | 2022-12-20 | 2022-12-20 23:59 |  | 2022-12-20 23:59 | AUS East Coast WS | ALyons | 2023-01-23 16:58 | MMendoza26 |  | No |  |  |  |  | Ariel Lyons |  | 9838.51 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.280 | A.1011181.280.04 | Plug 1C | SANTOS LIMITED | TANTANNA 2 | Wild Desert Rig 16 | J.22.135335 | WCF | REM-PA,REM-SQ | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-06 | 2023-01-06 |  | 2023-01-06 | 2023-01-06 23:59 |  | 2023-01-06 23:59 | AUS East Coast WS | ALyons | 2023-01-20 12:08 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 9838.51 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.280 | A.1011181.280.02 | Plug 1B | SANTOS LIMITED | TANTANNA 2 | Wild Desert Rig 16 | J.22.134325 | WCF | REM-PA,REM-SQ | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-04 | 2023-01-04 |  | 2023-01-04 | 2023-01-04 23:59 |  | 2023-01-04 23:59 | AUS East Coast WS | ALyons | 2023-01-20 12:06 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10748.93 | 2 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.28 | A.1011181.28.01 | 7 5/8 Surface | SANTOS LIMITED | Viper 1 | Ensign 967 | J.21.109450 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-24 10:00 | 2021-05-25 |  | 2021-05-25 | 2021-05-25 23:59 |  | 2021-05-27 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:05 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 25836.34 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.28 | A.1011181.28.02 | 4.5" Production Job | SANTOS LIMITED | Viper 1 | Ensign 967 | J.21.109133 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-03 10:00 | 2021-06-03 06:00 |  | 2021-06-03 08:00 | 2021-06-03 16:59 |  | 2021-06-05 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 43269.08 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.279 | A.1011181.279.01 | Personnel | SANTOS LIMITED | Well #1 | ENSIGN 971 | J.22.131966 | WCF | CMT-PERS | Low | Confirmed | Design - CEC |  | Not Required | Not Required | In Progress |  | 2022-12-02 | 2022-11-01 | 2022-12-02 | 2023-07-24 23:59 | 2023-07-25 |  | AUS East Coast WS | JAhmed8 | 2023-06-28 10:22 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 0 | 0 |  |  |  | 75 | 66.7 | 100 | 50 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.278 | A.1011181.278.03 | Plug 1C | SANTOS LIMITED | TANTANNA 11 | Wild Desert Rig 16 | J.22.132071 | WCF | REM-PA | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-09 | 2022-12-09 |  | 2022-12-09 | 2022-12-09 23:59 |  | 2022-12-09 23:59 | AUS East Coast WS | ALyons | 2023-05-27 15:31 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 9793.87 | 1 |  |  |  | 81.3 | 66.7 | 0 | 25 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.278 | A.1011181.278.02 | Plug 1B | SANTOS LIMITED | TANTANNA 11 | Wild Desert Rig 16 | J.22.130393 | WCF | REM-PA,REM-SQ | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-07 | 2022-12-07 |  | 2022-12-07 | 2022-12-07 23:59 |  | 2022-12-07 23:59 | AUS East Coast WS | ALyons | 2022-12-20 16:32 | GVang2 |  | No |  |  |  |  | Ariel Lyons |  | 9838.51 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.278 | A.1011181.278.01 | Plug 1A | SANTOS LIMITED | TANTANNA 11 | Wild Desert Rig 16 | J.22.130391 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-04 | 2022-12-04 |  | 2022-12-04 | 2022-12-04 23:59 |  | 2022-12-04 23:59 | AUS East Coast WS | ALyons | 2022-12-20 15:03 | GVang2 |  | No |  |  |  |  | Ariel Lyons |  | 9838.51 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.277 | A.1011181.277.01 | Plug 1A | SANTOS LIMITED | DULLINGARI 9 | Wild Desert Rig 16 | J.22.128277 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-24 | 2022-11-24 |  | 2022-11-24 | 2022-11-24 23:59 |  | 2022-11-24 23:59 | AUS East Coast WS | ALyons | 2022-12-19 11:48 | GVang2 |  | No |  |  |  |  | Ariel Lyons |  | 9838.51 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.277 | A.1011181.277.03 | Plug 1C | SANTOS LIMITED | DULLINGARI 9 | Wild Desert Rig 16 | J.22.128276 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-29 | 2022-11-29 |  | 2022-11-29 | 2022-11-29 23:59 |  | 2022-11-29 23:59 | AUS East Coast WS | ALyons | 2022-12-12 11:57 | GVang2 |  | No |  |  |  |  | Ariel Lyons |  | 9793.87 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.277 | A.1011181.277.02 | Plug 1B | SANTOS LIMITED | DULLINGARI 9 | Wild Desert Rig 16 | J.22.128278 | WCF | REM-PA,REM-SQ | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-27 | 2022-11-27 |  | 2022-11-27 | 2022-11-27 23:59 |  | 2022-11-27 23:59 | AUS East Coast WS | ALyons | 2022-12-12 11:01 | GVang2 |  | No |  |  |  |  | Ariel Lyons |  | 9838.51 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.276 | A.1011181.276.03 | Plug 1D | SANTOS LIMITED | TARWONGA 2 | Wild Desert Rig 16 | J.22.125869 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-20 18:00 | 2022-11-20 18:00 |  | 2022-11-20 18:00 | 2022-11-21 17:59 |  | 2022-11-21 17:59 | AUS East Coast WS | ALyons | 2022-11-29 15:44 | GVang2 |  | No |  |  |  |  | Ariel Lyons |  | 9793.87 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.276 | A.1011181.276.04 | Plug C | SANTOS LIMITED | TARWONGA 2 | Wild Desert Rig 16 | J.22.127211 | WCF | REM-PA,REM-SQ | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-19 | 2022-11-19 |  | 2022-11-19 | 2022-11-19 23:59 |  | 2022-11-19 23:59 | AUS East Coast WS | ALyons | 2022-11-29 15:26 | GVang2 |  | No |  |  |  |  | Ariel Lyons |  | 9793.87 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.276 | A.1011181.276.02 | Plug 1B | SANTOS LIMITED | TARWONGA 2 | Wild Desert Rig 16 | J.22.125868 | WCF | REM-PA,REM-SQ | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2022-11-18 | 2022-11-18 |  | 2022-11-18 | 2022-11-18 23:59 |  | 2022-11-18 23:59 | AUS East Coast WS | ALyons | 2022-11-29 15:22 | GVang2 |  | No |  |  |  |  | Ariel Lyons |  | 9838.51 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.276 | A.1011181.276.01 | Plug 1A | SANTOS LIMITED | TARWONGA 2 | Wild Desert Rig 16 | J.22.125866 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-16 | 2022-11-16 |  | 2022-11-16 | 2022-11-16 23:59 |  | 2022-11-16 23:59 | AUS East Coast WS | ALyons | 2022-11-29 02:04 | GVang2 |  | No |  |  |  |  | Ariel Lyons |  | 9838.51 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.275 | A.1011181.275.01 | Plug 1A-1+2 | SANTOS LIMITED | COOROO NORTH 1 | Wild Desert Rig 6 | J.22.125148 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-13 | 2022-11-13 |  | 2022-11-13 | 2022-11-13 23:59 |  | 2022-11-13 23:59 | AUS East Coast WS | ALyons | 2022-12-19 17:41 | GVang2 |  | No |  |  |  |  | Ariel Lyons |  | 9838.51 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.275 | A.1011181.275.04 | Plug 1A-3+4 | SANTOS LIMITED | COOROO NORTH 1 | Wild Desert Rig 6 | J.22.126202 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-14 | 2022-11-14 |  | 2022-11-14 | 2022-11-14 23:59 |  | 2022-11-14 23:59 | AUS East Coast WS | ALyons | 2022-11-29 14:18 | GVang2 |  | No |  |  |  |  | Ariel Lyons |  | 9838.51 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.275 | A.1011181.275.03 | Plug 1C | SANTOS LIMITED | COOROO NORTH 1 | Wild Desert Rig 6 | J.22.125911 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-20 11:00 | 2022-11-20 11:00 |  | 2022-11-20 11:00 | 2022-11-21 10:59 |  | 2022-11-21 10:59 | AUS East Coast WS | ALyons | 2022-11-29 12:47 | GVang2 |  | No |  |  |  |  | Ariel Lyons |  | 9793.87 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.275 | A.1011181.275.02 | Plug 1B | SANTOS LIMITED | COOROO NORTH 1 | Wild Desert Rig 6 | J.22.125912 | WCF | REM-PA,REM-SQ | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-18 11:00 | 2022-11-18 11:00 |  | 2022-11-18 11:00 | 2022-11-19 10:59 |  | 2022-11-19 10:59 | AUS East Coast WS | ALyons | 2022-11-22 14:58 | ZMellor |  | No |  |  |  |  | Ariel Lyons |  | 9838.51 | 2 |  |  |  | 81.3 | 33.3 | 0 | 100 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.275 | A.1011181.275.05 | Personnel | SANTOS LIMITED |  | Wild Desert Rig 6 | J.22.126356 | WCF | CMT-PERS | Low | Confirmed | Design - CEC |  | Not Required | Not Required | In Progress |  | 2022-11-09 |  | 2022-11-09 | 2022-11-30 23:59 |  |  | AUS East Coast WS | JAhmed8 | 2022-11-13 16:09 | JAhmed8 |  | No |  |  |  |  | Junaid Ahmed |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.274 | A.1011181.274.02 | 4.5" Production | SANTOS LIMITED | BOBS WELL 4 | SLR 188 | J.23.012941 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-09 21:00 | 2023-03-12 11:00 |  | 2023-03-12 11:00 | 2023-03-13 10:59 |  | 2023-03-12 20:59 | AUS East Coast WS | GVang2 | 2023-04-04 11:47 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10349.44 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.274 | A.1011181.274.01 | 7-5/8" Surface | SANTOS LIMITED | BOBS WELL 4 | SLR 188 | J.23.012942 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-28 22:00 | 2023-03-03 |  | 2023-03-03 | 2023-03-03 23:59 |  | 2023-03-02 22:59 | AUS East Coast WS | GVang2 | 2023-03-18 11:14 | VKlimenko8 |  | No |  |  |  |  | Grace Vang |  | 30997.91 | 1 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.273 | A.1011181.273.02 | 4.5" Production | SANTOS LIMITED | FORTANNA 2 | SLR 188 | J.23.012946 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-18 21:00 | 2023-02-25 11:00 |  | 2023-02-25 11:00 | 2023-02-26 10:59 |  | 2023-02-25 20:59 | AUS East Coast WS | GVang2 | 2023-02-27 13:30 | JNyoo |  | No |  |  |  |  | Grace Vang |  | 10367.37 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.273 | A.1011181.273.01 | 7-5/8" Surface | SANTOS LIMITED | FORTANNA 2 | SLR 188 | J.23.012939 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-12 22:00 | 2023-02-15 |  | 2023-02-15 | 2023-02-15 23:59 |  | 2023-02-14 22:59 | AUS East Coast WS | GVang2 | 2023-02-20 15:23 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.272 | A.1011181.272.02 | 4.5" Production | SANTOS LIMITED | EUROPA 1 | SLR 188 | J.23.012944 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-10 21:00 | 2023-02-13 11:00 |  | 2023-02-13 11:00 | 2023-02-14 10:59 |  | 2023-02-13 20:59 | AUS East Coast WS | GVang2 | 2023-02-20 12:15 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10816.3 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.272 | A.1011181.272.01 | 7-5/8" Surface | SANTOS LIMITED | EUROPA 1 | SLR 188 | J.23.012945 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-19 22:00 | 2023-02-06 |  | 2023-02-07 | 2023-02-07 23:59 |  | 2023-02-06 22:59 | AUS East Coast WS | GVang2 | 2023-02-20 11:49 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 27595 | 1 |  |  |  | 68.8 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.271 | A.1011181.271.02 | 7in Production Casing | SANTOS LIMITED | STRZELECKI 35 | SLR 188 | J.23.012938 | WCF | PRI-LONG | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-12-10 21:00 | 2023-01-13 11:00 |  | 2023-01-14 11:00 | 2023-01-15 10:59 |  | 2022-12-13 20:59 | AUS East Coast WS | GVang2 | 2023-05-27 15:31 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 14725.28 | 1 |  |  |  | 81.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.271 | A.1011181.271.01 | 9-5/8" Surface | SANTOS LIMITED | STRZELECKI 35 | SLR 188 | J.22.122639 | WCF | PRI-SURF | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-20 22:00 | 2022-12-25 |  | 2022-12-26 | 2022-12-26 23:59 |  | 2022-11-22 22:59 | AUS East Coast WS | GVang2 | 2023-01-13 09:50 | GSingh54 |  | No |  |  |  |  | Tareq AlSaman |  | 10776.27 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.270 | A.1011181.270.02 | 7" Production | SANTOS LIMITED | MARABOOKA 19 | SLR 188 | J.22.122636 | WCF | PRI-INTER | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-23 21:00 | 2022-11-28 11:00 |  | 2022-12-02 11:00 | 2022-12-03 10:59 |  | 2022-11-26 20:59 | AUS East Coast WS | GVang2 | 2023-05-27 15:31 | FDPSystemUser |  | Yes |  |  |  |  | Tareq AlSaman |  | 187283.18 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.270 | A.1011181.270.01 | 9-5/8" Surface | SANTOS LIMITED | MARABOOKA 19 | SLR 188 | J.22.122635 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-20 22:00 | 2022-11-29 |  | 2022-11-29 | 2022-11-29 23:59 |  | 2022-11-22 22:59 | AUS East Coast WS | GVang2 | 2022-11-29 01:26 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 26288.69 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.27 | A.1011181.27.02 | Sturt East 4 Plug 1B | SANTOS LIMITED | Well #1 | Wild Desert Rig 16 | J.21.109464 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-04-22 10:00 | 2021-07-11 |  | 2021-07-11 | 2021-07-11 23:59 |  | 2021-04-24 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:07 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.27 | A.1011181.27.03 | Sturt East 4 Plug 3C | SANTOS LIMITED | Well #1 | Wild Desert Rig 16 | J.21.109152 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-04-25 10:00 | 2021-07-08 |  | 2021-07-08 | 2021-07-08 23:59 |  | 2021-04-27 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.27 | A.1011181.27.05 | Sturt East 4 Plug 3E | SANTOS LIMITED | Well #1 | Wild Desert Rig 16 | J.21.109131 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-07-04 10:00 | 2021-07-04 |  | 2021-07-04 | 2021-07-04 23:59 |  | 2021-07-06 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.27 | A.1011181.27.04 | Sturt East 4 Plug D | SANTOS LIMITED | Well #1 | Wild Desert Rig 16 | J.21.109119 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-04-26 10:00 | 2021-07-07 |  | 2021-07-07 | 2021-07-07 23:59 |  | 2021-04-28 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:20 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.27 | A.1011181.27.01 | SturtEast4 Plug 1A | SANTOS LIMITED | Well #1 | Wild Desert Rig 16 | J.21.109107 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-04-19 10:00 | 2021-07-14 |  | 2021-07-14 | 2021-07-15 23:59 |  | 2021-04-22 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:20 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.269 | A.1011181.269.02 | 4.5" Production | SANTOS LIMITED | BIG LAKE 169 | SLR RIG 183 | J.23.012921 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-09 21:00 | 2023-04-10 11:00 |  | 2023-04-10 11:00 | 2023-04-11 10:59 |  | 2023-04-12 20:59 | AUS East Coast WS | GVang2 | 2023-04-19 13:52 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10417.72 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.269 | A.1011181.269.01 | 7" Surface | SANTOS LIMITED | BIG LAKE 169 | SLR RIG 183 | J.23.012920 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-04 22:00 | 2023-04-03 03:00 |  | 2023-04-05 | 2023-04-05 23:59 |  | 2023-04-06 22:59 | AUS East Coast WS | GVang2 | 2023-04-11 15:09 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10345.22 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.268 | A.1011181.268.02 | 4.5" Production | SANTOS LIMITED | BIG LAKE 168 | SLR RIG 183 | J.23.012899 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-30 21:00 | 2023-03-31 11:00 |  | 2023-03-31 11:00 | 2023-04-01 10:59 |  | 2023-04-02 20:59 | AUS East Coast WS | GVang2 | 2023-04-19 14:54 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10360.98 | 1 |  |  |  | 87.5 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.268 | A.1011181.268.01 | 7-5/8" Surface | SANTOS LIMITED | BIG LAKE 168 | SLR RIG 183 | J.23.012916 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-25 22:00 | 2023-03-26 |  | 2023-03-26 | 2023-03-26 23:59 |  | 2023-03-27 22:59 | AUS East Coast WS | GVang2 | 2023-03-27 01:02 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10345.22 | 1 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.267 | A.1011181.267.01 | 7" Surface | SANTOS LIMITED | BIG LAKE 167 | SLR RIG 183 | J.23.012913 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-08 22:00 | 2023-03-06 03:00 |  | 2023-03-09 | 2023-03-09 23:59 |  | 2023-03-10 22:59 | AUS East Coast WS | GVang2 | 2023-05-08 10:04 | JAhmed8 |  | No |  |  |  |  | Grace Vang |  | 10313.22 | 1 |  |  |  | 50 | 33.3 | 0 | 75 | 45 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.267 | A.1011181.267.02 | 4.5" Production | SANTOS LIMITED | BIG LAKE 167 | SLR RIG 183 | J.23.012914 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-13 21:00 | 2023-03-14 11:00 |  | 2023-03-14 11:00 | 2023-03-15 10:59 |  | 2023-03-16 20:59 | AUS East Coast WS | GVang2 | 2023-03-27 12:28 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 10412.81 | 1 |  |  |  | 81.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.266 | A.1011181.266.02 | 4.5" Production | SANTOS LIMITED | BIG LAKE 166 | SLR RIG 183 | J.23.012910 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-02-25 21:00 | 2023-02-26 11:00 |  | 2023-02-26 11:00 | 2023-02-27 10:59 |  | 2023-02-28 20:59 | AUS East Coast WS | GVang2 | 2023-03-07 16:12 | NAbosnina |  | No |  |  |  |  | Grace Vang |  | 10412.81 | 1 |  |  |  | 87.5 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.266 | A.1011181.266.01 | 7-5/8" Surface | SANTOS LIMITED | BIG LAKE 166 | SLR RIG 183 | J.23.012909 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-20 22:00 | 2023-02-20 03:00 |  | 2023-02-21 | 2023-02-21 23:59 |  | 2023-02-22 22:59 | AUS East Coast WS | GVang2 | 2023-02-21 11:38 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10345.22 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.265 | A.1011181.265.01 | 7" Surface | SANTOS LIMITED | BIG LAKE 165 | SLR RIG 183 | J.23.018085 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-05 18:00 | 2023-02-05 |  | 2023-02-05 20:00 | 2023-02-06 19:59 |  | 2023-02-07 18:59 | AUS East Coast WS | GVang2 | 2023-02-20 17:34 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 29933.34 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.265 | A.1011181.265.02 | 4.5" Production | SANTOS LIMITED | BIG LAKE 165 | SLR RIG 183 | J.23.018086 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-09 21:00 | 2023-02-10 11:00 |  | 2023-02-14 11:00 | 2023-02-15 10:59 |  | 2023-02-16 20:59 | AUS East Coast WS | GVang2 | 2023-02-20 13:34 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 35225.54 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.264 | A.1011181.264.01 | 7" Surface | SANTOS LIMITED | TIRRAWARRA 103 | ENSIGN 974 | J.23.012713 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-26 22:00 | 2023-01-26 22:00 |  | 2023-02-02 22:00 | 2023-02-03 21:59 |  | 2023-01-27 21:59 | AUS East Coast WS | GVang2 | 2023-02-20 16:48 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 29875.64 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.264 | A.1011181.264.02 | 4.5" Production | SANTOS LIMITED | TIRRAWARRA 103 | ENSIGN 974 | J.23.012712 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-12 23:00 | 2023-02-12 23:00 |  | 2023-02-12 23:00 | 2023-02-13 22:59 |  | 2023-02-13 22:59 | AUS East Coast WS | GVang2 | 2023-02-16 11:38 | JNyoo |  | No |  |  |  |  | Grace Vang |  | 47846.64 | 1 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.263 | A.1011181.263.02 | 4.5" Production | SANTOS LIMITED | TIRRAWARRA 104 | ENSIGN 974 | J.23.012714 | WCF | PRI-INTER | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-29 23:00 | 2023-03-29 23:00 |  | 2023-03-29 23:00 | 2023-03-30 22:59 |  | 2023-03-30 22:59 | AUS East Coast WS | GVang2 | 2023-04-26 10:12 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 47846.64 | 1 |  |  |  | 81.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.263 | A.1011181.263.01 | 7" Surface | SANTOS LIMITED | TIRRAWARRA 104 | ENSIGN 974 | J.23.012715 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-03-20 22:00 | 2023-03-20 22:00 |  | 2023-03-20 22:00 | 2023-03-21 21:59 |  | 2023-03-21 21:59 | AUS East Coast WS | GVang2 | 2023-03-27 10:08 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 29875.64 | 1 |  |  |  | 87.5 | 66.7 | 0 | 50 | 65 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.262 | A.1011181.262.02 | 4.5" Production | SANTOS LIMITED | TIRRAWARRA 109 | ENSIGN 974 | J.23.012711 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-11 23:00 | 2023-03-11 23:00 |  | 2023-03-11 23:00 | 2023-03-12 22:59 |  | 2023-03-12 22:59 | AUS East Coast WS | GVang2 | 2023-03-23 11:56 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 55728.43 | 1 |  |  |  | 81.3 | 16.7 | 0 | 75 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.262 | A.1011181.262.01 | 7 5/8" Surface | SANTOS LIMITED | TIRRAWARRA 109 | ENSIGN 974 | J.23.012710 | WCF | PRI-SURF | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2023-03-04 22:00 | 2023-03-04 22:00 |  | 2023-03-04 22:00 | 2023-03-05 21:59 |  | 2023-03-05 21:59 | AUS East Coast WS | GVang2 | 2023-03-11 17:11 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 33213.66 | 1 |  |  |  | 87.5 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.261 | A.1011181.261.02 | 4.5" Production | SANTOS LIMITED | TIRRAWARRA 105 | ENSIGN 974 | J.23.012716 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-13 23:00 | 2023-04-13 23:00 |  | 2023-04-13 23:00 | 2023-04-14 22:59 |  | 2023-04-14 22:59 | AUS East Coast WS | GVang2 | 2023-04-19 15:12 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 47846.64 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.261 | A.1011181.261.01 | 7" Surface (Slim) | SANTOS LIMITED | TIRRAWARRA 105 | ENSIGN 974 | J.23.012717 | WCF | PRI-SURF | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2023-04-02 22:00 | 2023-04-02 22:00 |  | 2023-04-02 22:00 | 2023-04-03 21:59 |  | 2023-04-03 21:59 | AUS East Coast WS | GVang2 | 2023-04-14 12:17 | ATimbs |  | No |  |  |  |  | Grace Vang |  | 29875.64 | 1 |  |  |  | 87.5 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.260 | A.1011181.260.02 | 4.5" Production | SANTOS LIMITED | TIRRAWARRA 108 | ENSIGN 974 | J.23.012708 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-03-15 23:00 | 2023-03-15 23:00 |  | 2023-03-15 23:00 | 2023-03-16 22:59 |  | 2023-03-16 22:59 | AUS East Coast WS | GVang2 | 2023-03-09 15:59 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 37431.36 | 1 |  |  |  | 87.5 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.260 | A.1011181.260.01 | 7" Surface | SANTOS LIMITED | TIRRAWARRA 108 | ENSIGN 974 | J.23.012709 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-08 22:00 | 2023-02-08 22:00 |  | 2023-02-21 22:00 | 2023-02-22 21:59 |  | 2023-02-09 21:59 | AUS East Coast WS | GVang2 | 2023-02-24 10:01 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10344.33 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.26 | A.1011181.26.03 | Gidgealpa 57 Plug 1B | SANTOS LIMITED | Gidgealpa 57 | Wild Desert Rig 16 | J.21.109453 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-02-04 11:00 | 2021-02-05 20:30 |  | 2021-02-05 20:30 | 2021-02-06 20:29 |  | 2021-02-06 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:06 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 11484.24 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.26 | A.1011181.26.01 | Gidgealpa 57 P&A 1A-1 | SANTOS LIMITED | Gidgealpa 57 | Wild Desert Rig 16 | J.21.109160 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-02 11:00 | 2021-02-02 |  | 2021-02-02 | 2021-02-03 23:59 |  | 2021-02-04 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 11702.37 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.26 | A.1011181.26.05 | Sturt East 4 Plug 3E | SANTOS LIMITED | Gidgealpa 57 | Wild Desert Rig 16 | J.21.109145 | WCF | REM-PA | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-02-10 11:00 | 2021-02-11 |  | 2021-02-11 | 2021-02-11 23:59 |  | 2021-02-12 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.26 | A.1011181.26.04 | Gidgealpa 57 Plug 1C | SANTOS LIMITED | Gidgealpa 57 | Wild Desert Rig 16 | J.21.109142 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-07 11:00 | 2021-02-08 |  | 2021-02-08 | 2021-02-08 23:59 |  | 2021-02-09 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 13424.44 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.26 | A.1011181.26.02 | Gidgealpa Plug 1A-2, 1A-3 and 1A-4 | SANTOS LIMITED | Gidgealpa 57 | Wild Desert Rig 16 | J.21.109139 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-03 11:00 | 2021-02-04 |  | 2021-02-04 | 2021-02-04 23:59 |  | 2021-02-05 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 11559.21 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.259 | A.1011181.259.02 | 4 1/2" Production (hot) | SANTOS LIMITED | MOOMBA 298 | ENSIGN 971 | J.23.025636 | WCF | PRI-LONG | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-06 | 2023-04-06 |  | 2023-04-06 | 2023-04-06 23:59 |  | 2023-04-06 23:59 | AUS East Coast WS | GVang2 | 2023-04-14 15:11 | ATimbs |  | No |  |  |  |  | Grace Vang |  | 44220.12 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.259 | A.1011181.259.01 | 7 5/8" Surface | SANTOS LIMITED | MOOMBA 298 | ENSIGN 971 | J.23.056510 | WCF | PRI-SURF | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-15 23:00 | 2023-03-15 23:00 |  | 2023-03-26 23:00 | 2023-03-27 22:59 |  | 2023-03-16 23:59 | AUS East Coast WS | GVang2 | 2023-03-27 19:52 | ATimbs |  | No |  |  |  |  | Grace Vang |  | 30106.44 | 1 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.258 | A.1011181.258.02 | 4 1/2" Production (hot) | SANTOS LIMITED | MOOMBA 291 | ENSIGN 971 | J.23.048359 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-03-17 | 2023-03-17 |  | 2023-03-17 | 2023-03-17 23:59 |  | 2023-03-17 23:59 | AUS East Coast WS | GVang2 | 2023-03-27 01:41 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 38384.05 | 1 |  |  |  | 87.5 | 50 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.258 | A.1011181.258.01 | 7 5/8" Surface | SANTOS LIMITED | MOOMBA 291 | ENSIGN 971 | J.23.012697 | WCF | PRI-SURF | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2023-03-06 23:00 | 2023-03-06 23:00 |  | 2023-03-06 23:00 | 2023-03-07 22:59 |  | 2023-03-07 23:59 | AUS East Coast WS | GVang2 | 2023-03-23 10:14 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 29933.34 | 1 |  |  |  | 87.5 | 16.7 | 0 | 100 | 60 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.257 | A.1011181.257.02 | 4 1/2" Production (hot) | SANTOS LIMITED | MOOMBA 292 | ENSIGN 971 | J.23.012696 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-03 | 2023-03-03 |  | 2023-03-03 | 2023-03-03 23:59 |  | 2023-03-03 23:59 | AUS East Coast WS | GVang2 | 2023-03-24 10:18 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 34375.39 | 1 |  |  |  | 81.3 | 66.7 | 0 | 50 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.257 | A.1011181.257.01 | 7" Surface | SANTOS LIMITED | MOOMBA 292 | ENSIGN 971 | J.23.012695 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-23 23:00 | 2023-02-23 23:00 |  | 2023-02-23 23:00 | 2023-02-24 22:59 |  | 2023-02-24 23:59 | AUS East Coast WS | GVang2 | 2023-02-24 16:04 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 9023.78 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.256 | A.1011181.256.02 | 4 1/2" Production (hot) | SANTOS LIMITED | MOOMBA 293 | ENSIGN 971 | J.23.012694 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-11 | 2023-02-11 |  | 2023-02-11 | 2023-02-11 23:59 |  | 2023-02-11 23:59 | AUS East Coast WS | GVang2 | 2023-02-20 18:04 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 48874.16 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.256 | A.1011181.256.01 | 7 5/8" Surface | SANTOS LIMITED | MOOMBA 293 | ENSIGN 971 | J.23.012693 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-05 23:00 | 2023-02-05 23:00 |  | 2023-02-05 23:00 | 2023-02-06 22:59 |  | 2023-02-06 23:59 | AUS East Coast WS | GVang2 | 2023-02-20 16:43 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 30086.7 | 1 |  |  |  | 81.3 | 16.7 | 0 | 100 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.255 | A.1011181.255.01 | 7 5/8" Surface | SANTOS LIMITED | Well #1 | ENSIGN 971 | J.23.012692 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-01-23 23:00 | 2023-01-23 23:00 |  | 2023-01-23 23:00 | 2023-01-24 22:59 |  | 2023-01-24 23:59 | AUS East Coast WS | GVang2 | 2023-02-16 10:23 | MMendoza26 |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.255 | A.1011181.255.02 | 4 1/2" Production (hot) | SANTOS LIMITED | MOOMBA 294 | ENSIGN 971 | J.23.012691 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2023-01-29 | 2023-02-11 |  | 2023-02-18 | 2023-02-22 23:59 |  | 2023-01-29 23:59 | AUS East Coast WS | GVang2 | 2023-02-16 10:22 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.254 | A.1011181.254.02 | 4 1/2" Production (hot) | SANTOS LIMITED | MOOMBA 287 | ENSIGN 971 | J.23.019651 | WCF | PRI-LONG | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-26 | 2023-01-26 |  | 2023-01-26 | 2023-01-26 23:59 |  | 2023-01-26 23:59 | AUS East Coast WS | GVang2 | 2023-05-27 15:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 42997.71 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.254 | A.1011181.254.01 | 7 5/8" Surface | SANTOS LIMITED | MOOMBA 287 | ENSIGN 971 | J.23.012690 | WCF | PRI-SURF | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-18 23:00 | 2023-01-18 23:00 |  | 2023-01-18 23:00 | 2023-01-19 22:59 |  | 2023-01-19 23:59 | AUS East Coast WS | GVang2 | 2023-01-25 11:39 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 49673.79 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.253 | A.1011181.253.02 | 4 1/2" Production (hot) | SANTOS LIMITED | MOOMBA 288 | ENSIGN 971 | J.23.012689 | WCF | PRI-LONG | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-15 02:00 | 2023-01-15 |  | 2023-01-15 02:00 | 2023-01-16 01:59 |  | 2023-01-16 01:59 | AUS East Coast WS | GVang2 | 2023-05-27 15:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 37671.88 | 1 |  |  |  | 81.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.253 | A.1011181.253.01 | 7 5/8" Surface | SANTOS LIMITED | MOOMBA 288 | ENSIGN 971 | J.22.122477 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-01-06 23:00 | 2023-01-06 23:00 |  | 2023-01-06 23:00 | 2023-01-07 22:59 |  | 2023-01-07 23:59 | AUS East Coast WS | GVang2 | 2023-01-13 15:23 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 32359.51 | 1 |  |  |  | 75 | 50 | 0 | 100 | 65 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.252 | A.1011181.252.01 | 7" Surface | SANTOS LIMITED | MOOMBA 289 | ENSIGN 971 | J.22.122475 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-27 23:00 | 2022-12-27 23:00 |  | 2022-12-27 23:00 | 2022-12-28 22:59 |  | 2022-12-28 23:59 | AUS East Coast WS | GVang2 | 2023-01-13 12:05 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 40131.96 | 1 |  |  |  | 75 | 66.7 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.252 | A.1011181.252.02 | 4 1/2" Production (hot) | SANTOS LIMITED | MOOMBA 289 | ENSIGN 971 | J.22.122476 | WCF | PRI-LONG | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-04 | 2023-01-04 |  | 2023-01-04 | 2023-01-04 23:59 |  | 2023-01-04 23:59 | AUS East Coast WS | GVang2 | 2023-01-13 09:14 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 53209.57 | 1 |  |  |  | 81.3 | 33.3 | 0 | 100 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.251 | A.1011181.251.02 | 4 1/2" Production (hot) | SANTOS LIMITED | MOOMBA 290 | ENSIGN 971 | J.22.122474 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-23 | 2022-12-23 |  | 2022-12-23 | 2022-12-23 23:59 |  | 2022-12-23 23:59 | AUS East Coast WS | GVang2 | 2022-12-28 09:21 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 59377.71 | 1 |  |  |  | 81.3 | 16.7 | 0 | 75 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.251 | A.1011181.251.01 | 7" Surface | SANTOS LIMITED | MOOMBA 290 | ENSIGN 971 | J.22.122473 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-16 23:00 | 2022-12-16 23:00 |  | 2022-12-16 23:00 | 2022-12-17 22:59 |  | 2022-12-17 23:59 | AUS East Coast WS | GVang2 | 2022-12-20 09:57 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 29426.52 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.250 | A.1011181.250.02 | 4 1/2" Production (hot) | SANTOS LIMITED | MOOMBA 283 | ENSIGN 971 | J.22.122471 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-14 | 2022-12-14 |  | 2022-12-14 | 2022-12-14 23:59 |  | 2022-12-14 23:59 | AUS East Coast WS | GVang2 | 2022-12-13 12:54 | NAbosnina |  | No |  |  |  |  | Grace Vang |  | 32613.35 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.250 | A.1011181.250.01 | 7" Surface | SANTOS LIMITED | MOOMBA 283 | ENSIGN 971 | J.22.122472 | WCF | PRI-SURF | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-25 23:00 | 2022-11-25 23:00 |  | 2022-12-01 23:00 | 2022-12-02 22:59 |  | 2022-11-26 23:59 | AUS East Coast WS | GVang2 | 2022-12-09 23:15 | ATimbs |  | No |  |  |  |  | Grace Vang |  | 35140.89 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.25 | A.1011181.25.02 | 4 1/2" Production (hot) | SANTOS LIMITED | Moomba 259 | ENSIGN 971 | J.21.109159 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-03-07 11:00 | 2021-03-08 |  | 2021-03-08 | 2021-03-08 23:59 |  | 2021-03-10 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 69879.55 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.25 | A.1011181.25.01 | 7 5/8" Surface | SANTOS LIMITED | Moomba 259 | ENSIGN 971 | J.21.109113 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-21 11:00 | 2021-02-22 |  | 2021-02-22 | 2021-02-22 23:59 |  | 2021-02-24 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:20 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 25478.48 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.249 | A.1011181.249.02 | 5.5" Intermediate | SANTOS LIMITED | MINOS 4 | Ensign 967 | J.23.012947 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-12 12:00 | 2023-01-14 |  | 2023-01-14 12:00 | 2023-01-15 23:59 |  | 2023-01-13 23:59 | AUS East Coast WS | GVang2 | 2023-01-27 12:09 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 54111 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.249 | A.1011181.249.01 | 9 5/8" Surface | SANTOS LIMITED | MINOS 4 | Ensign 967 | J.23.012948 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-08 | 2023-01-09 23:00 |  | 2023-01-09 23:00 | 2023-01-10 22:59 |  | 2023-01-08 23:59 | AUS East Coast WS | GVang2 | 2023-01-16 15:31 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 31700.33 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.248 | A.1011181.248.03 | Plug 1C&1D | SANTOS LIMITED | DULLINGARI NORTH 8 | Wild Desert Rig 16 | J.22.122084 | WCF | REM-PA,REM-SQ | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-11-27 | 2022-11-27 |  | 2022-11-27 | 2022-11-27 23:59 |  | 2022-11-27 23:59 | AUS East Coast WS | ALyons | 2022-11-20 15:08 | ALyons |  | No |  |  |  |  | Ariel Lyons |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.248 | A.1011181.248.02 | Plug 1B | SANTOS LIMITED | DULLINGARI NORTH 8 | Wild Desert Rig 16 | J.22.122211 | WCF | REM-PA,REM-SQ | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-11-25 | 2022-11-25 |  | 2022-11-25 | 2022-11-25 23:59 |  | 2022-11-25 23:59 | AUS East Coast WS | ALyons | 2022-11-20 15:08 | ALyons |  | No |  |  |  |  | Ariel Lyons |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.248 | A.1011181.248.01 | Plug 1A | SANTOS LIMITED | DULLINGARI NORTH 8 | Wild Desert Rig 16 | J.22.122210 | WCF | REM-PA | Low | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2022-11-23 | 2022-11-23 |  | 2022-11-23 | 2022-11-23 23:59 |  | 2022-11-23 23:59 | AUS East Coast WS | ALyons | 2022-11-20 15:07 | ALyons |  | No |  |  |  |  | Ariel Lyons |  | 9838.51 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.247 | A.1011181.247.03 | Plug 2D | SANTOS LIMITED | NACCOWLAH WEST 5 | Wild Desert Rig 6 | J.22.119344 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-11 | 2022-11-11 |  | 2022-11-11 | 2022-11-11 23:59 |  | 2022-11-11 23:59 | AUS East Coast WS | ALyons | 2022-12-26 23:47 | GVang2 |  | No |  |  |  |  | Ariel Lyons |  | 14027.68 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.247 | A.1011181.247.02 | Plug 2B | SANTOS LIMITED | NACCOWLAH WEST 5 | Wild Desert Rig 6 | J.22.119343 | WCF | REM-PA,REM-SQ | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-29 13:00 | 2022-10-29 13:00 |  | 2022-10-29 13:00 | 2022-10-30 12:59 |  | 2022-10-30 12:59 | AUS East Coast WS | ALyons | 2022-12-19 21:39 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 9838.51 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.247 | A.1011181.247.04 | Plug 3C | SANTOS LIMITED | NACCOWLAH WEST 5 | Wild Desert Rig 6 | J.22.122019 | WCF | REM-PA,REM-SQ | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-31 13:00 | 2022-10-31 13:00 |  | 2022-10-31 13:00 | 2022-11-01 12:59 |  | 2022-11-01 12:59 | AUS East Coast WS | ALyons | 2022-12-16 13:56 | ATimbs |  | No |  |  |  |  | Ariel Lyons |  | 9838.51 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.247 | A.1011181.247.01 | Plug 1A | SANTOS LIMITED | NACCOWLAH WEST 5 | Wild Desert Rig 6 | J.22.118211 | WCF | REM-PA | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-26 | 2022-10-26 |  | 2022-10-26 | 2022-10-26 23:59 |  | 2022-10-26 23:59 | AUS East Coast WS | ALyons | 2022-12-16 13:56 | ATimbs |  | No |  |  |  |  | Ariel Lyons |  | 9838.51 | 2 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.246 | A.1011181.246.04 | Plug 1E | SANTOS LIMITED | STRZELECKI 4 | Wild Desert Rig 16 | J.22.117553 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-29 | 2022-10-29 |  | 2022-10-29 | 2022-10-29 23:59 |  | 2022-10-29 23:59 | AUS East Coast WS | ALyons | 2022-12-19 12:37 | GVang2 |  | No |  |  |  |  | Ariel Lyons |  | 14027.68 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.246 | A.1011181.246.03 | Plug 1C | SANTOS LIMITED | STRZELECKI 4 | Wild Desert Rig 16 | J.22.117549 | WCF | REM-PA,REM-SQ | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-26 | 2022-10-26 |  | 2022-10-26 | 2022-10-26 23:59 |  | 2022-10-26 23:59 | AUS East Coast WS | ALyons | 2022-11-29 17:31 | ATimbs |  | No |  |  |  |  | Ariel Lyons |  | 9793.87 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.246 | A.1011181.246.05 | Plug 2D | SANTOS LIMITED | STRZELECKI 4 | Wild Desert Rig 16 | J.22.120882 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-27 13:00 | 2022-10-27 13:00 |  | 2022-10-27 13:00 | 2022-10-28 12:59 |  | 2022-10-28 12:59 | AUS East Coast WS | ALyons | 2022-11-29 14:31 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 14027.68 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.246 | A.1011181.246.02 | Plug 1B | SANTOS LIMITED | STRZELECKI 4 | Wild Desert Rig 16 | J.22.117548 | WCF | REM-PA,REM-SQ | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-24 | 2022-10-24 |  | 2022-10-24 | 2022-10-24 23:59 |  | 2022-10-24 23:59 | AUS East Coast WS | ALyons | 2022-10-28 14:36 | GVang2 |  | No |  |  |  |  | Ariel Lyons |  | 9838.51 | 2 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.246 | A.1011181.246.01 | Plug 1A | SANTOS LIMITED | STRZELECKI 4 | Wild Desert Rig 16 | J.22.117562 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-22 | 2022-10-22 |  | 2022-10-22 | 2022-10-22 23:59 |  | 2022-10-22 23:59 | AUS East Coast WS | ALyons | 2022-10-28 11:13 | GVang2 |  | No |  |  |  |  | Ariel Lyons |  | 9838.51 | 2 |  |  |  | 43.8 | 50 | 0 | 100 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.245 | A.1011181.245.02 | Plug 2B | SANTOS LIMITED | STRZELECKI 18 | Wild Desert Rig 16 | J.22.113581 | WCF | REM-PA,REM-SQ | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-13 | 2022-10-14 |  | 2022-10-14 | 2022-10-14 23:59 |  | 2022-10-13 23:59 | AUS East Coast WS | MAlsaman | 2022-10-27 12:10 | GVang2 |  | No |  |  |  |  | Tareq AlSaman |  | 9838.51 | 1 |  |  |  | 43.8 | 33.3 | 0 | 75 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.245 | A.1011181.245.05 | Plug 1E | SANTOS LIMITED | STRZELECKI 18 | Wild Desert Rig 16 | J.22.116829 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-18 | 2022-10-18 |  | 2022-10-18 | 2022-10-18 23:59 |  | 2022-10-18 23:59 | AUS East Coast WS | ALyons | 2022-10-26 12:16 | GVang2 |  | No |  |  |  |  | Ariel Lyons |  | 14027.68 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.245 | A.1011181.245.04 | Plug 2D | SANTOS LIMITED | STRZELECKI 18 | Wild Desert Rig 16 | J.22.116529 | WCF | REM-PA,REM-SQ | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-17 | 2022-10-17 |  | 2022-10-17 | 2022-10-17 23:59 |  | 2022-10-17 23:59 | AUS East Coast WS | ALyons | 2022-10-25 11:00 | GVang2 |  | No |  |  |  |  | Ariel Lyons |  | 9793.87 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.245 | A.1011181.245.03 | Plug 2C | SANTOS LIMITED | STRZELECKI 18 | Wild Desert Rig 16 | J.22.116437 | WCF | REM-PA,REM-SQ | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-15 | 2022-10-15 |  | 2022-10-15 | 2022-10-15 23:59 |  | 2022-10-15 23:59 | AUS East Coast WS | ALyons | 2022-10-25 01:00 | GVang2 |  | No |  |  |  |  | Ariel Lyons |  | 9793.87 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.245 | A.1011181.245.01 | Plug 1A | SANTOS LIMITED | STRZELECKI 18 | Wild Desert Rig 16 | J.22.113517 | WCF | REM-PA,REM-SQ | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-11 | 2022-10-11 |  | 2022-10-11 | 2022-10-11 23:59 |  | 2022-10-11 23:59 | AUS East Coast WS | MAlsaman | 2022-10-25 00:09 | GVang2 |  | No |  |  |  |  | Tareq AlSaman |  | 9838.51 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.244 | A.1011181.244.02 | Plug 1B | SANTOS LIMITED | YANDA 9 ST1 | Wild Desert Rig 6 | J.22.113588 | WCF | REM-PA,REM-SQ | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-12 | 2022-10-11 |  | 2022-10-12 | 2022-10-12 23:59 |  | 2022-10-12 23:59 | AUS East Coast WS | MAlsaman | 2022-10-27 18:53 | GVang2 |  | No |  |  |  |  | Tareq AlSaman |  | 9793.87 | 2 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.244 | A.1011181.244.03 | Plug 1C | SANTOS LIMITED | YANDA 9 ST1 | Wild Desert Rig 6 | J.22.114990 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-16 | 2022-10-15 |  | 2022-10-16 | 2022-10-16 23:59 |  | 2022-10-16 23:59 | AUS East Coast WS | MAlsaman | 2022-10-27 15:28 | GVang2 |  | No |  |  |  |  | Tareq AlSaman |  | 7671.55 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.244 | A.1011181.244.01 | Plug 1A | SANTOS LIMITED | YANDA 9 ST1 | Wild Desert Rig 6 | J.22.113292 | WCF | REM-PA,REM-SQ | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-07 | 2022-10-06 |  | 2022-10-07 | 2022-10-07 23:59 |  | 2022-10-07 23:59 | AUS East Coast WS | MAlsaman | 2022-10-27 14:24 | GVang2 |  | No |  |  |  |  | Tareq AlSaman |  | 9838.51 | 2 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.243 | A.1011181.243.02 | Plug 1B | SANTOS LIMITED | GIDGEALPA 25 | Wild Desert Rig 16 | J.22.110966 | WCF | REM-PA,REM-SQ | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-04 01:00 | 2022-10-03 01:00 |  | 2022-10-04 01:00 | 2022-10-05 00:59 |  | 2022-10-05 00:59 | AUS East Coast WS | MAlsaman | 2022-10-28 18:43 | GVang2 |  | No |  |  |  |  | Tareq AlSaman |  | 10603.24 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.243 | A.1011181.243.03 | Plug 1C | SANTOS LIMITED | GIDGEALPA 25 | Wild Desert Rig 16 | J.22.110743 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-06 | 2022-10-05 01:00 |  | 2022-10-06 | 2022-10-06 23:59 |  | 2022-10-06 23:59 | AUS East Coast WS | MAlsaman | 2022-10-28 18:27 | GVang2 |  | No |  |  |  |  | Tareq AlSaman |  | 10541.08 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.243 | A.1011181.243.01 | Plug 1A | SANTOS LIMITED | GIDGEALPA 25 | Wild Desert Rig 16 | J.22.110742 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-30 | 2022-09-28 |  | 2022-10-01 | 2022-10-01 23:59 |  | 2022-09-30 23:59 | AUS East Coast WS | MAlsaman | 2022-10-28 18:03 | GVang2 |  | No |  |  |  |  | Tareq AlSaman |  | 10647.88 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.242 | A.1011181.242.02 | Plug 1B | SANTOS LIMITED | Muteroo 1 | Wild Desert Rig 16 | J.22.110739 | WCF | REM-PA,REM-SQ | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-21 | 2022-09-20 |  | 2022-09-21 | 2022-09-21 23:59 |  | 2022-09-21 23:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:34 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 8238.39 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.242 | A.1011181.242.03 | Plug 1C | SANTOS LIMITED | Muteroo 1 | Wild Desert Rig 16 | J.22.110733 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-24 | 2022-09-23 |  | 2022-09-24 | 2022-09-24 23:59 |  | 2022-09-24 23:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:34 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 9731.71 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.242 | A.1011181.242.01 | Plug 1A | SANTOS LIMITED | Muteroo 1 | Wild Desert Rig 16 | J.22.110731 | WCF | REM-PA,REM-SQ | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-19 | 2022-09-18 |  | 2022-09-19 | 2022-09-19 23:59 |  | 2022-09-19 23:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:34 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 9821.55 | 2 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.241 | A.1011181.241.02 | 4.5" Production | SANTOS LIMITED | TIRRAWARRA 102 | ENSIGN 974 | J.23.008728 | WCF | PRI-INTER | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-19 02:00 | 2023-01-19 |  | 2023-01-19 02:00 | 2023-01-20 01:59 |  | 2023-01-20 01:59 | AUS East Coast WS | GVang2 | 2023-05-27 15:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 37440.65 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.241 | A.1011181.241.01 | 7 5/8" Surface | SANTOS LIMITED | TIRRAWARRA 102 | ENSIGN 974 | J.23.008726 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-25 23:00 | 2023-01-25 23:00 |  | 2023-01-25 23:00 | 2023-01-26 22:59 |  | 2023-01-26 22:59 | AUS East Coast WS | GVang2 | 2023-01-27 11:19 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 34537.45 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.240 | A.1011181.240.02 | 4.5" Production | SANTOS LIMITED | TIRRAWARRA 101 | ENSIGN 974 | J.23.008723 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-29 | 2023-01-29 |  | 2023-01-29 | 2023-01-29 23:59 |  | 2023-01-29 23:59 | AUS East Coast WS | GVang2 | 2023-02-14 01:54 | MMendoza26 |  | No |  |  |  |  | Grace Vang |  | 38486.42 | 1 |  |  |  | 81.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.240 | A.1011181.240.01 | 7 5/8" Surface | SANTOS LIMITED | TIRRAWARRA 101 | ENSIGN 974 | J.23.008721 | WCF | PRI-SURF | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-19 23:00 | 2023-01-19 23:00 |  | 2023-01-19 23:00 | 2023-01-20 22:59 |  | 2023-01-20 22:59 | AUS East Coast WS | GVang2 | 2023-01-25 15:10 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 34538.19 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.24 | A.1011181.24.01 | 7 5/8" Surface | SANTOS LIMITED | Moomba 261 | ENSIGN 971 | J.21.109461 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-03-08 11:00 | 2021-03-09 |  | 2021-03-09 | 2021-03-09 23:59 |  | 2021-03-11 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:07 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 23016.91 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.24 | A.1011181.24.02 | 4 1/2" Production (hot) | SANTOS LIMITED | Moomba 261 | ENSIGN 971 | J.21.109157 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-15 11:00 | 2021-03-16 |  | 2021-03-16 | 2021-03-16 23:59 |  | 2021-03-18 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 69879.55 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.239 | A.1011181.239.01 | 7 5/8" Surface | SANTOS LIMITED | TIRRAWARRA 100 | ENSIGN 974 | J.23.008722 | WCF | PRI-SURF | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-25 23:00 | 2022-12-25 23:00 |  | 2022-12-25 23:00 | 2022-12-26 22:59 |  | 2022-12-26 22:59 | AUS East Coast WS | GVang2 | 2023-01-13 14:46 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 29526.32 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.239 | A.1011181.239.02 | 4.5" Production | SANTOS LIMITED | TIRRAWARRA 100 | ENSIGN 974 | J.23.008727 | WCF | PRI-INTER | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-04 | 2023-01-04 |  | 2023-01-04 | 2023-01-04 23:59 |  | 2023-01-04 23:59 | AUS East Coast WS | GVang2 | 2023-01-12 16:22 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 35027.24 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.238 | A.1011181.238.02 | 4.5" Production | SANTOS LIMITED | TIRRAWARRA 99 | ENSIGN 974 | J.23.008725 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-21 | 2022-12-21 |  | 2022-12-21 | 2022-12-21 23:59 |  | 2022-12-21 23:59 | AUS East Coast WS | GVang2 | 2022-12-27 23:00 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 50246.54 | 1 |  |  |  | 68.8 | 66.7 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.238 | A.1011181.238.01 | 7 5/8" Surface | SANTOS LIMITED | TIRRAWARRA 99 | ENSIGN 974 | J.23.008719 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-09 23:00 | 2022-12-09 23:00 |  | 2022-12-15 23:00 | 2022-12-16 22:59 |  | 2022-12-16 22:59 | AUS East Coast WS | GVang2 | 2022-12-19 16:23 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 51940.52 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.237 | A.1011181.237.02 | 4.5" Production | SANTOS LIMITED | QUARTPOT 2 | ENSIGN 974 | J.23.008724 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-08 | 2022-12-08 |  | 2022-12-08 | 2022-12-08 23:59 |  | 2022-12-08 23:59 | AUS East Coast WS | GVang2 | 2022-12-20 16:02 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 35027.24 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.237 | A.1011181.237.01 | 7 5/8" Surface | SANTOS LIMITED | QUARTPOT 2 | ENSIGN 974 | J.22.110725 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-29 23:00 | 2022-11-29 23:00 |  | 2022-11-29 23:00 | 2022-11-30 22:59 |  | 2022-11-30 22:59 | AUS East Coast WS | GVang2 | 2022-12-12 12:24 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 32277.82 | 1 |  |  |  | 75 | 50 | 0 | 50 | 55 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.236 | A.1011181.236.01 | 7-5/8" Surface | SANTOS LIMITED | BIG LAKE 163 | SLR RIG 183 | J.22.110728 | WCF | PRI-SURF | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2023-01-05 22:00 | 2023-01-06 | 2023-01-06 | 2023-01-06 | 2023-01-06 23:59 | 2023-01-08 | 2023-01-07 22:59 | AUS East Coast WS | GVang2 | 2025-08-25 13:46 | MAngarita2 |  | No |  |  |  |  | Grace Vang |  | 30594.96 | 1 |  | L0 - No RO |  | 87.5 | 33.3 | 0 | 50 | 55 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.236 | A.1011181.236.02 | 4.5" Production | SANTOS LIMITED | BIG LAKE 163 | SLR RIG 183 | J.22.110730 | WCF | PRI-INTER | Medium | Unconfirmed - 10% | Design - CEC |  | Design Completed | Design Completed | In Progress | 2023-01-15 21:00 | 2023-01-16 11:00 |  | 2023-01-16 11:00 | 2023-01-17 10:59 |  | 2023-01-18 20:59 | AUS East Coast WS | GVang2 | 2023-01-15 14:23 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 56297.98 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.235 | A.1011181.235.02 | 4.5" Production | SANTOS LIMITED | BIG LAKE 162 | SLR RIG 183 | J.22.110734 | WCF | PRI-INTER | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-29 21:00 | 2022-12-30 11:00 |  | 2022-12-30 11:00 | 2022-12-31 10:59 |  | 2023-01-01 20:59 | AUS East Coast WS | GVang2 | 2023-01-13 08:24 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 50258.18 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.235 | A.1011181.235.01 | 7-5/8" Surface | SANTOS LIMITED | BIG LAKE 162 | SLR RIG 183 | J.22.110723 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-18 22:00 | 2022-12-19 |  | 2022-12-19 | 2022-12-19 23:59 |  | 2022-12-20 22:59 | AUS East Coast WS | GVang2 | 2022-12-27 23:07 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 25821.59 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.234 | A.1011181.234.02 | 4.5" Production | SANTOS LIMITED | BIG LAKE 161 | SLR RIG 183 | J.22.110726 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-11 21:00 | 2022-12-12 11:00 |  | 2022-12-12 11:00 | 2022-12-13 10:59 |  | 2022-12-14 20:59 | AUS East Coast WS | GVang2 | 2022-12-16 16:32 | DTree |  | No |  |  |  |  | Grace Vang |  | 33278.56 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.234 | A.1011181.234.01 | 7-5/8" Surface | SANTOS LIMITED | BIG LAKE 161 | SLR RIG 183 | J.22.110729 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-04 10:00 | 2022-12-04 12:00 |  | 2022-12-04 12:00 | 2022-12-05 11:59 |  | 2022-12-06 10:59 | AUS East Coast WS | GVang2 | 2022-12-12 10:24 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 25198.97 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.233 | A.1011181.233.01 | 7-5/8" Surface | SANTOS LIMITED | MOOMBA 303 | SLR RIG 183 | J.22.110721 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-16 02:00 | 2022-11-16 03:00 |  | 2022-11-16 04:00 | 2022-11-17 03:59 |  | 2022-11-18 02:59 | AUS East Coast WS | GVang2 | 2022-11-29 13:58 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 43671.29 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.233 | A.1011181.233.02 | 4.5" Production | SANTOS LIMITED | MOOMBA 303 | SLR RIG 183 | J.22.110722 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-25 21:00 | 2022-11-26 11:00 |  | 2022-11-26 11:00 | 2022-11-27 10:59 |  | 2022-11-28 20:59 | AUS East Coast WS | GVang2 | 2022-11-29 00:39 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 57804.47 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.232 | A.1011181.232.01 | 7-5/8" Surface | SANTOS LIMITED | MOOMBA 302 | SLR RIG 183 | J.22.110720 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-03 03:00 | 2022-11-03 03:00 |  | 2022-11-03 05:00 | 2022-11-04 04:59 |  | 2022-11-05 03:59 | AUS East Coast WS | GVang2 | 2022-11-28 17:24 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 47441.4 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.232 | A.1011181.232.02 | 4.5" Production | SANTOS LIMITED | MOOMBA 302 | SLR RIG 183 | J.22.110724 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-11 21:00 | 2022-11-12 11:00 |  | 2022-11-12 11:00 | 2022-11-13 10:59 |  | 2022-11-14 20:59 | AUS East Coast WS | GVang2 | 2022-11-28 17:10 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 61333.05 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.231 | A.1011181.231.02 | Plug 1B | SANTOS LIMITED | Mudera North 1 | Wild Desert Rig 16 | J.22.110735 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-09-14 | 2022-09-10 |  | 2022-09-14 | 2022-09-14 23:59 |  | 2022-09-14 23:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:34 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 9838.51 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.231 | A.1011181.231.01 | Plug 1A | SANTOS LIMITED | Mudera North 1 | Wild Desert Rig 16 | J.22.110719 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-09-12 | 2022-09-11 |  | 2022-09-12 | 2022-09-12 23:59 |  | 2022-09-12 23:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:33 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 9793.87 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.230 | A.1011181.230.01 | CPI Increase | SANTOS LIMITED | Well #1 | SLR 188 | J.22.110703 | WCF | PRI-SURF, CMT-ENG,CMT-EQPRNT,CMT-MATSAL | Low | Cancelled | Close - PSD |  | Not Required | Design Completed | Not Required |  | 2022-09-06 01:00 |  | 2022-09-06 01:00 | 2022-09-07 00:59 |  |  | AUS East Coast WS | GVang2 | 2022-10-03 14:33 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 87737.49 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.23 | A.1011181.23.01 | 7 5/8" Surface | SANTOS LIMITED | Moomba 260 | ENSIGN 971 | J.21.109475 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-07 11:00 | 2021-02-08 |  | 2021-02-08 | 2021-02-08 23:59 |  | 2021-02-10 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:08 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 25478.48 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.23 | A.1011181.23.02 | 4 1/2" Production (hot) | SANTOS LIMITED | Moomba 260 | ENSIGN 971 | J.21.109117 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-16 11:00 | 2021-02-17 |  | 2021-02-17 | 2021-02-17 23:59 |  | 2021-02-19 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:20 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 69879.55 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.229 | A.1011181.229.03 | Plug 1C | SANTOS LIMITED | Dullingari 20 | Wild Desert Rig 16 | J.22.110718 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-09-06 | 2022-09-04 10:41 |  | 2022-09-06 | 2022-09-06 23:59 |  | 2022-09-06 23:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:33 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 10541.08 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.229 | A.1011181.229.01 | Plug 1A | SANTOS LIMITED | Dullingari 20 | Wild Desert Rig 16 | J.22.110714 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-01 | 2022-08-31 |  | 2022-09-01 | 2022-09-01 23:59 |  | 2022-09-01 23:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:33 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 9257.92 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.229 | A.1011181.229.02 | Plug 1B | SANTOS LIMITED | Dullingari 20 | Wild Desert Rig 16 | J.22.110705 | WCF | REM-PA,REM-SQ | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-09-03 | 2022-09-02 |  | 2022-09-03 | 2022-09-03 23:59 |  | 2022-09-03 23:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:33 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 9244.88 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.228 | A.1011181.228.01 | 9 5/8" Surface | SANTOS LIMITED | ZEUS 15 | Ensign 967 | J.23.008670 | WCF | PRI-SURF | Low | Unconfirmed - 10% | Design - CEC |  | Design Completed | Design Completed | In Progress | 2023-01-04 | 2023-01-05 23:00 | 2023-01-05 | 2023-01-05 23:00 | 2023-01-06 22:59 | 2023-01-08 | 2023-01-04 23:59 | AUS East Coast WS | GVang2 | 2025-08-25 13:45 | MAngarita2 |  | No |  |  |  |  | Grace Vang |  | 37557.46 | 1 |  | L0 - No RO |  | 87.5 | 66.7 | 0 | 50 | 65 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.228 | A.1011181.228.02 | 5.5" Intermediate | SANTOS LIMITED | ZEUS 15 | Ensign 967 | J.23.008687 | WCF | PRI-INTER | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-08 12:00 | 2023-01-10 |  | 2023-01-10 12:00 | 2023-01-11 23:59 |  | 2023-01-09 23:59 | AUS East Coast WS | GVang2 | 2023-05-27 15:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 58465.18 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.227 | A.1011181.227.01 | 9 5/8" Surface | SANTOS LIMITED | ZEUS 14 | Ensign 967 | J.22.110713 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-30 | 2022-12-31 23:00 |  | 2022-12-31 23:00 | 2023-01-01 22:59 |  | 2022-12-30 23:59 | AUS East Coast WS | GVang2 | 2022-12-29 09:10 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 32245.17 | 1 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.227 | A.1011181.227.02 | 7" Intermediate | SANTOS LIMITED | ZEUS 14 | Ensign 967 | J.23.008669 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-03 12:00 | 2023-01-05 |  | 2023-01-05 12:00 | 2023-01-06 23:59 |  | 2023-01-04 23:59 | AUS East Coast WS | GVang2 | 2022-12-29 09:07 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 32120.42 | 1 |  |  |  | 56.3 | 66.7 | 0 | 100 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.226 | A.1011181.226.02 | 5-1/2" Production | SANTOS LIMITED | ZEUS 13 | Ensign 967 | J.22.110707 | WCF | PRI-INTER | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-20 12:00 | 2022-12-22 |  | 2022-12-22 12:00 | 2022-12-23 23:59 |  | 2022-12-21 23:59 | AUS East Coast WS | GVang2 | 2023-05-27 15:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 37085.41 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.226 | A.1011181.226.01 | 9 5/8" Surface | SANTOS LIMITED | ZEUS 13 | Ensign 967 | J.22.110701 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-16 | 2022-12-17 23:00 |  | 2022-12-17 23:00 | 2022-12-18 22:59 |  | 2022-12-16 23:59 | AUS East Coast WS | GVang2 | 2022-12-20 12:59 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 32287.28 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.225 | A.1011181.225.01 | 9 5/8" Surface | SANTOS LIMITED | TENNAPERRA 11 | Ensign 967 | J.22.110712 | WCF | PRI-SURF | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-04 | 2022-12-05 23:00 |  | 2022-12-05 23:00 | 2022-12-06 22:59 |  | 2022-12-04 23:59 | AUS East Coast WS | GVang2 | 2023-05-27 15:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 29933.34 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.225 | A.1011181.225.02 | 5.5" Production | SANTOS LIMITED | TENNAPERRA 11 | Ensign 967 | J.22.110716 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-08 12:00 | 2022-12-10 |  | 2022-12-10 12:00 | 2022-12-11 23:59 |  | 2022-12-09 23:59 | AUS East Coast WS | GVang2 | 2022-12-19 15:04 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 33318.91 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.224 | A.1011181.224.02 | 5.5" Production Job | SANTOS LIMITED | ALWYN 9 | Ensign 967 | J.22.110698 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-26 | 2022-11-28 06:00 |  | 2022-11-28 08:00 | 2022-11-28 16:59 |  | 2022-11-26 23:59 | AUS East Coast WS | GVang2 | 2022-12-09 16:37 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 36738.9 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.224 | A.1011181.224.01 | 9 5/8 Surface | SANTOS LIMITED | ALWYN 9 | Ensign 967 | J.22.110710 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-22 | 2022-11-24 |  | 2022-11-24 | 2022-11-24 23:59 |  | 2022-11-22 23:59 | AUS East Coast WS | GVang2 | 2022-12-07 17:02 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 48965.39 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.223 | A.1011181.223.01 | 9 5/8 Surface | SANTOS LIMITED | ULANDI 17 | Ensign 967 | J.22.110709 | WCF | PRI-SURF | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-18 01:00 | 2022-11-20 00:01 |  | 2022-11-20 01:00 | 2022-11-21 00:59 |  | 2022-11-19 00:59 | AUS East Coast WS | GVang2 | 2022-11-29 13:52 | ATimbs |  | No |  |  |  |  | Grace Vang |  | 40135.51 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.223 | A.1011181.223.02 | 5.5" Production Job | SANTOS LIMITED | ULANDI 17 | Ensign 967 | J.22.110711 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-19 | 2022-11-21 06:00 |  | 2022-11-21 08:00 | 2022-11-21 16:59 |  | 2022-11-19 23:59 | AUS East Coast WS | GVang2 | 2022-11-28 12:31 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 39827.76 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.222 | A.1011181.222.02 | Meranji 16 - Plug 1B | SANTOS LIMITED | Meranji 16 | Wild Desert Rig 16 | J.22.110700 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-03 | 2022-08-07 |  | 2022-08-08 | 2022-08-08 23:59 |  | 2022-08-03 23:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:32 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 9922.68 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.222 | A.1011181.222.01 | Meranji 16 - Plug 1A | SANTOS LIMITED | Meranji 16 | Wild Desert Rig 16 | J.22.110699 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-02 | 2022-08-06 |  | 2022-08-07 | 2022-08-07 23:59 |  | 2022-08-02 23:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:32 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 8009.45 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.221 | A.1011181.221.01 | Tirrawarra 76 | SANTOS LIMITED | Tirrawarra 76 | Wild Desert Rig 16 | J.22.110693 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-07-20 | 2022-07-21 |  | 2022-07-22 | 2022-07-22 23:59 |  | 2022-07-20 23:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:32 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 10213.54 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.220 | A.1011181.220.02 | 7" Production | SANTOS LIMITED | STRZELECKI 36 | SLR 188 | J.22.110704 | WCF | PRI-INTER | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-21 02:00 | 2022-12-15 |  | 2022-12-21 11:00 | 2022-12-22 10:59 |  | 2022-12-22 23:59 | AUS East Coast WS | GVang2 | 2022-12-28 20:10 | ATimbs |  | No |  |  |  |  | Tareq AlSaman |  | 14711.68 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.220 | A.1011181.220.01 | 9-5/8" Surface Casing | SANTOS LIMITED | STRZELECKI 36 | SLR 188 | J.22.110964 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-06 04:00 | 2022-12-06 03:00 |  | 2022-12-07 | 2022-12-07 23:59 |  | 2022-12-06 23:59 | AUS East Coast WS | GVang2 | 2022-12-19 14:45 | GVang2 |  | No |  |  |  |  | Tareq AlSaman |  | 10776.27 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.22 | A.1011181.22.02 | 4 1/2" Production (hot) | SANTOS LIMITED | MOOMBA 262 | ENSIGN 971 | J.21.109449 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-28 11:00 | 2021-01-28 |  | 2021-01-28 | 2021-01-28 23:59 |  | 2021-01-30 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:05 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 69879.55 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.22 | A.1011181.22.01 | 7 5/8" Surface | SANTOS LIMITED | MOOMBA 262 | ENSIGN 971 | J.21.109156 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-19 11:00 | 2021-01-20 |  | 2021-01-20 | 2021-01-20 23:59 |  | 2021-01-22 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 25478.48 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.219 | A.1011181.219.02 | 7" Production Casing | SANTOS LIMITED | STRZELECKI 34 | SLR 188 | J.22.110702 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-24 08:00 | 2023-01-26 11:00 |  | 2023-01-26 22:00 | 2023-01-27 21:59 |  | 2022-12-27 07:59 | AUS East Coast WS | GVang2 | 2023-01-25 16:50 | GVang2 |  | No |  |  |  |  | Tareq AlSaman |  | 12837.22 | 1 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.219 | A.1011181.219.01 | 9-5/8" Surface Casing | SANTOS LIMITED | STRZELECKI 34 | SLR 188 | J.22.110963 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-27 | 2023-01-17 23:00 |  | 2023-01-18 | 2023-01-18 23:59 |  | 2022-11-27 23:59 | AUS East Coast WS | GVang2 | 2023-01-24 13:45 | GVang2 |  | No |  |  |  |  | Tareq AlSaman |  | 10776.27 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.218 | A.1011181.218.02 | 4.5" Production | SANTOS LIMITED | DILCHEE 6 | SLR 188 | J.22.110691 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-10 22:00 | 2022-11-18 12:00 |  | 2022-11-18 12:00 | 2022-11-19 11:59 |  | 2022-11-18 21:59 | AUS East Coast WS | GVang2 | 2022-11-28 14:14 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 53088.65 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.218 | A.1011181.218.01 | 7-5/8" Surface | SANTOS LIMITED | DILCHEE 6 | SLR 188 | J.22.110685 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-06 23:00 | 2022-11-09 |  | 2022-11-09 01:00 | 2022-11-10 00:59 |  | 2022-11-08 23:59 | AUS East Coast WS | GVang2 | 2022-11-23 12:17 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 46565.02 | 1 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.217 | A.1011181.217.02 | 4.5" Production | SANTOS LIMITED | PIRA 6 | SLR 188 | J.22.110690 | WCF | PRI-INTER | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-31 22:00 | 2022-11-03 12:00 |  | 2022-11-03 12:00 | 2022-11-04 11:59 |  | 2022-11-03 21:59 | AUS East Coast WS | GVang2 | 2022-11-29 15:10 | JAhmed8 |  | No |  |  |  |  | Grace Vang |  | 45971.9 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.217 | A.1011181.217.01 | 7-5/8" Surface | SANTOS LIMITED | PIRA 6 | SLR 188 | J.22.110681 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-25 23:00 | 2022-10-28 01:00 |  | 2022-10-28 01:00 | 2022-10-29 00:59 |  | 2022-10-27 23:59 | AUS East Coast WS | GVang2 | 2022-11-21 16:20 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 7830.48 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.216 | A.1011181.216.02 | 4.5" Production | SANTOS LIMITED | PIRA 5 | SLR 188 | J.22.110965 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-10-20 22:00 | 2022-10-23 12:00 |  | 2022-10-23 12:00 | 2022-10-24 11:59 |  | 2022-10-23 21:59 | AUS East Coast WS | GVang2 | 2022-10-27 15:04 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 63786.91 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.216 | A.1011181.216.01 | 7-5/8" Surface | SANTOS LIMITED | PIRA 5 | SLR 188 | J.22.110687 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-12 23:00 | 2022-10-15 |  | 2022-10-15 01:00 | 2022-10-16 00:59 |  | 2022-10-14 23:59 | AUS East Coast WS | GVang2 | 2022-10-27 11:59 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 41352.57 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.215 | A.1011181.215.02 | 4.5" Production (Slim) | SANTOS LIMITED | BIG LAKE 170 | SLR RIG 183 | J.23.008668 | WCF | PRI-LONG | Medium | Unconfirmed - 50% | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-21 10:00 | 2023-04-21 10:00 |  | 2023-04-22 10:00 | 2023-04-23 10:59 |  | 2023-04-24 10:00 | AUS East Coast WS | GVang2 | 2023-04-24 17:51 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10410.75 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.215 | A.1011181.215.01 | 7" Surface (Slim) | SANTOS LIMITED | BIG LAKE 170 | SLR RIG 183 | J.23.008667 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-16 | 2023-04-16 03:00 |  | 2023-04-17 | 2023-04-17 23:59 |  | 2023-04-18 | AUS East Coast WS | GVang2 | 2023-04-19 15:56 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10267.77 | 1 |  |  |  | 81.3 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.214 | A.1011181.214.02 | 4.5" Production | SANTOS LIMITED | MOOMBA 296 | SLR RIG 183 | J.22.110962 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-22 21:00 | 2022-10-23 11:00 |  | 2022-10-26 11:00 | 2022-10-27 10:59 |  | 2022-10-28 20:59 | AUS East Coast WS | GVang2 | 2022-10-29 18:01 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 39535.03 | 1 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.214 | A.1011181.214.01 | 7-5/8" Surface | SANTOS LIMITED | MOOMBA 296 | SLR RIG 183 | J.22.110686 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-09 22:01 | 2022-10-10 |  | 2022-10-10 00:01 | 2022-10-11 |  | 2022-10-11 23:00 | AUS East Coast WS | GVang2 | 2022-10-24 15:28 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 30955.06 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.213 | A.1011181.213.02 | 4.5" Production | SANTOS LIMITED | Moomba 295 | SLR RIG 183 | J.22.110696 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-05 22:00 | 2022-10-06 12:00 |  | 2022-10-06 12:00 | 2022-10-07 11:59 |  | 2022-10-08 21:59 | AUS East Coast WS | GVang2 | 2022-10-24 16:47 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 30632.35 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.213 | A.1011181.213.01 | 7-5/8" Surface | SANTOS LIMITED | Moomba 295 | SLR RIG 183 | J.22.110692 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-01 | 2022-10-01 01:00 |  | 2022-10-01 02:00 | 2022-10-02 01:59 |  | 2022-10-03 01:59 | AUS East Coast WS | GVang2 | 2022-10-20 11:09 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 45301.89 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.212 | A.1011181.212.02 | 3.5" Production | SANTOS LIMITED | Quasar 2 | SLR 188 | J.22.110697 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-04 12:00 | 2022-10-04 12:00 |  | 2022-10-06 12:00 | 2022-10-07 11:59 |  | 2022-10-07 11:59 | AUS East Coast WS | GVang2 | 2022-10-24 23:39 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 52526.08 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.212 | A.1011181.212.01 | 7-5/8" Surface | SANTOS LIMITED | QUASAR 2 | SLR 188 | J.22.110961 | WCF | PRI-SURF | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-27 17:00 | 2022-09-27 |  | 2022-09-27 17:00 | 2022-09-28 16:59 |  | 2022-09-28 16:59 | AUS East Coast WS | GVang2 | 2022-10-24 15:54 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 83840.94 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.211 | A.1011181.211.02 | 4.5" Production | SANTOS LIMITED | Big Lake 159 | SLR RIG 183 | J.22.110960 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-09-06 21:00 | 2022-09-07 11:00 |  | 2022-09-07 11:00 | 2022-09-08 10:59 |  | 2022-09-09 20:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:22 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 60554.73 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.211 | A.1011181.211.01 | 7-5/8" Surface | SANTOS LIMITED | Big Lake 159 | SLR RIG 183 | J.22.110958 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-09-01 22:00 | 2022-09-02 |  | 2022-09-02 | 2022-09-02 23:59 |  | 2022-09-03 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:22 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 26924.42 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.210 | A.1011181.210.02 | 4.5" Production | SANTOS LIMITED | Big Lake 158 | SLR RIG 183 | J.22.110689 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-20 21:00 | 2022-08-21 11:00 |  | 2022-08-21 11:00 | 2022-08-22 10:59 |  | 2022-08-23 20:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:32 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 58043.29 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.210 | A.1011181.210.01 | 7-5/8" Surface | SANTOS LIMITED | Big Lake 158 | SLR RIG 183 | J.22.110677 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-12 02:00 | 2022-08-12 03:00 |  | 2022-08-12 04:00 | 2022-08-13 03:59 |  | 2022-08-14 02:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:32 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 26924.42 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.21 | A.1011181.21.02 | 7" Intermediate | SANTOS LIMITED | Dullingari 56 | ENSIGN 974 | J.21.109149 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-23 11:00 | 2021-03-23 |  | 2021-03-24 | 2021-03-24 23:59 |  | 2021-03-26 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 42957.21 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.21 | A.1011181.21.01 | 9 5/8" Surface | SANTOS LIMITED | Dullingari 56 | ENSIGN 974 | J.21.109124 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-16 11:00 | 2021-03-16 |  | 2021-03-17 | 2021-03-17 23:59 |  | 2021-03-19 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 25662.85 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.209 | A.1011181.209.02 | 4.5" Production | SANTOS LIMITED | Moomba 276 | SLR RIG 183 | J.22.110959 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-01 21:00 | 2022-08-07 11:00 |  | 2022-08-07 11:00 | 2022-08-08 10:59 |  | 2022-08-09 20:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:22 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 63066.17 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.209 | A.1011181.209.01 | 7-5/8" Surface | SANTOS LIMITED | Moomba 276 | SLR RIG 183 | J.22.110678 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-07-28 | 2022-07-28 |  | 2022-07-28 02:00 | 2022-07-29 01:59 |  | 2022-07-30 00:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:32 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 31947.29 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.208 | A.1011181.208.01 | 7-5/8" Surface | SANTOS LIMITED | MOOMBA 270 | SLR RIG 183 | J.22.110688 | WCF | PRI-SURF | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2022-07-17 | 2022-07-20 23:59 |  | 2022-07-21 | 2022-07-21 23:59 |  | 2022-07-17 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:32 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 24412.98 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.208 | A.1011181.208.02 | 4.5" Production | SANTOS LIMITED | Moomba 270 | SLR RIG 183 | J.22.110682 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-07-26 | 2022-07-26 11:00 |  | 2022-07-26 11:00 | 2022-07-27 10:59 |  | 2022-07-27 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:32 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 31743.24 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.207 | A.1011181.207.01 | 7-5/8" Surface | SANTOS LIMITED | Moomba 269 | SLR RIG 183 | J.22.110957 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-06-29 22:00 | 2022-06-29 21:00 |  | 2022-06-30 | 2022-06-30 23:59 |  | 2022-07-01 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:22 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 28094.19 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.207 | A.1011181.207.02 | 4.5" Production | SANTOS LIMITED | Moomba 269 | SLR RIG 183 | J.22.110674 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-07-08 21:00 | 2022-07-09 11:00 |  | 2022-07-09 11:00 | 2022-07-10 10:59 |  | 2022-07-11 20:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:32 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 63066.17 | 1 |  |  |  | 87.5 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.206 | A.1011181.206.02 | 4 1/2" Production (hot) | SANTOS LIMITED | MOOMBA 283 | ENSIGN 971 | J.22.110684 | WCF | PRI-LONG | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-12-04 |  | 2022-12-04 | 2022-12-04 23:59 |  |  | AUS East Coast WS | GVang2 | 2022-10-31 15:08 | GVang2 |  | No |  |  |  |  | Gaurav Kumar Singh |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.206 | A.1011181.206.01 | 7 5/8" Surface | SANTOS LIMITED | MOOMBA 283 | ENSIGN 971 | J.22.110679 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-11-23 23:00 | 2022-11-29 23:00 |  | 2022-11-29 23:00 | 2022-11-30 22:59 |  | 2022-11-24 22:59 | AUS East Coast WS | GVang2 | 2022-10-31 15:05 | GVang2 |  | No |  |  |  |  | Ariel Lyons |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.205 | A.1011181.205.02 | 4 1/2" Production (hot) | SANTOS LIMITED | MOOMBA 284 | ENSIGN 971 | J.22.110683 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-26 | 2022-11-26 |  | 2022-11-29 | 2022-11-29 23:59 |  | 2022-11-29 23:59 | AUS East Coast WS | GVang2 | 2022-12-13 00:02 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 56817.27 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.205 | A.1011181.205.01 | 7" Surface | SANTOS LIMITED | MOOMBA 284 | ENSIGN 971 | J.22.110954 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-18 23:00 | 2022-11-18 23:00 |  | 2022-11-18 23:00 | 2022-11-19 22:59 |  | 2022-11-19 23:59 | AUS East Coast WS | GVang2 | 2022-11-29 09:58 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 35146.69 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.204 | A.1011181.204.02 | 4 1/2" Production (hot) | SANTOS LIMITED | MOOMBA 285 | ENSIGN 971 | J.22.110956 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-16 | 2022-11-16 |  | 2022-11-16 | 2022-11-16 23:59 |  | 2022-11-16 23:59 | AUS East Coast WS | GVang2 | 2022-11-28 17:46 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 39960.55 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.204 | A.1011181.204.01 | 7 5/8" Surface | SANTOS LIMITED | MOOMBA 285 | ENSIGN 971 | J.22.110673 | WCF | PRI-SURF | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-09 23:00 | 2022-11-09 23:00 |  | 2022-11-09 23:00 | 2022-11-10 22:59 |  | 2022-11-10 23:59 | AUS East Coast WS | GVang2 | 2022-11-28 15:34 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 50897.15 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.203 | A.1011181.203.02 | 4 1/2" Production (hot) | SANTOS LIMITED | MOOMBA 286 | ENSIGN 971 | J.22.110955 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-08 | 2022-11-08 |  | 2022-11-08 | 2022-11-08 23:59 |  | 2022-11-08 23:59 | AUS East Coast WS | GVang2 | 2022-11-28 23:28 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 54475.63 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.203 | A.1011181.203.01 | 7 5/8" Surface | SANTOS LIMITED | MOOMBA 286 | ENSIGN 971 | J.22.110680 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-30 01:00 | 2022-10-30 01:00 |  | 2022-10-30 01:00 | 2022-10-31 00:59 |  | 2022-10-31 00:59 | AUS East Coast WS | GVang2 | 2022-11-21 16:31 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 30740.42 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.202 | A.1011181.202.07 | Moomba 291 | SANTOS LIMITED | MOOMBA 282 | ENSIGN 971 | J.22.122461 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-12-08 03:00 | 2022-12-08 02:00 |  | 2022-12-08 02:00 | 2022-12-09 01:59 |  | 2022-12-09 02:59 | AUS East Coast WS | GVang2 | 2022-10-31 15:37 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.202 | A.1011181.202.06 | Moomba 290 | SANTOS LIMITED | MOOMBA 282 | ENSIGN 971 | J.22.122459 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-12-08 03:00 | 2022-12-08 02:00 |  | 2022-12-08 02:00 | 2022-12-09 01:59 |  | 2022-12-09 02:59 | AUS East Coast WS | GVang2 | 2022-10-31 15:37 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.202 | A.1011181.202.05 | Moomba 289 | SANTOS LIMITED | MOOMBA 282 | ENSIGN 971 | J.22.122458 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-12-08 03:00 | 2022-12-08 02:00 |  | 2022-12-08 02:00 | 2022-12-09 01:59 |  | 2022-12-09 02:59 | AUS East Coast WS | GVang2 | 2022-10-31 15:36 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.202 | A.1011181.202.04 | Moomba 288 | SANTOS LIMITED | MOOMBA 282 | ENSIGN 971 | J.22.122456 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-12-08 03:00 | 2022-12-08 02:00 |  | 2022-12-08 02:00 | 2022-12-09 01:59 |  | 2022-12-09 02:59 | AUS East Coast WS | GVang2 | 2022-10-31 15:36 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.202 | A.1011181.202.03 | Moomba 287 | SANTOS LIMITED | MOOMBA 282 | ENSIGN 971 | J.22.122454 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-12-08 03:00 | 2022-12-08 02:00 |  | 2022-12-08 02:00 | 2022-12-09 01:59 |  | 2022-12-09 02:59 | AUS East Coast WS | GVang2 | 2022-10-31 15:36 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.202 | A.1011181.202.02 | 4 1/2" Production (hot) | SANTOS LIMITED | MOOMBA 282 | ENSIGN 971 | J.22.110669 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-19 01:00 | 2022-10-19 01:00 |  | 2022-10-19 01:00 | 2022-10-20 00:59 |  | 2022-10-20 00:59 | AUS East Coast WS | GVang2 | 2022-10-27 00:41 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 42525.75 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.202 | A.1011181.202.01 | 7 5/8" Surface | SANTOS LIMITED | MOOMBA 282 | ENSIGN 971 | J.22.110671 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-14 03:00 | 2022-10-14 02:00 |  | 2022-10-14 02:00 | 2022-10-15 01:59 |  | 2022-10-15 02:59 | AUS East Coast WS | GVang2 | 2022-10-20 14:44 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 26805.64 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.201 | A.1011181.201.01 | 9 5/8 Surface | SANTOS LIMITED | ISOPTERA 6 | Ensign 967 | J.22.110950 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-15 | 2022-11-17 |  | 2022-11-17 | 2022-11-17 23:59 |  | 2022-11-15 23:59 | AUS East Coast WS | GVang2 | 2022-11-28 18:10 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 40823.63 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.201 | A.1011181.201.02 | 5.5" Production Job | SANTOS LIMITED | ISOPTERA 6 | Ensign 967 | J.22.110676 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-16 | 2022-11-18 06:00 |  | 2022-11-18 08:00 | 2022-11-18 16:59 |  | 2022-11-16 23:59 | AUS East Coast WS | GVang2 | 2022-11-23 13:39 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 67271.88 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.200 | A.1011181.200.02 | 5.5" Production Job | SANTOS LIMITED | ISOPTERA 7 | Ensign 967 | J.22.110953 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-10 | 2022-11-12 06:00 |  | 2022-11-12 08:00 | 2022-11-12 16:59 |  | 2022-11-10 23:59 | AUS East Coast WS | GVang2 | 2022-11-24 17:27 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 64101.67 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.200 | A.1011181.200.01 | 9 5/8 Surface | SANTOS LIMITED | ISOPTERA 7 | Ensign 967 | J.22.110949 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-09 01:00 | 2022-11-11 |  | 2022-11-11 01:00 | 2022-11-12 00:59 |  | 2022-11-10 00:59 | AUS East Coast WS | GVang2 | 2022-11-24 17:01 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 38090.63 | 1 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.20 | A.1011181.20.02 | 7" Intermediate | SANTOS LIMITED | Dullingari 62 | ENSIGN 974 | J.21.109470 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-03-01 11:00 | 2021-03-05 |  | 2021-03-06 | 2021-03-06 23:59 |  | 2021-03-04 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:08 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 42616.91 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.20 | A.1011181.20.01 | 9 5/8" Surface | SANTOS LIMITED | Dullingari 62 | ENSIGN 974 | J.21.109136 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-26 11:00 | 2021-02-26 |  | 2021-02-27 | 2021-02-27 23:59 |  | 2021-03-01 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 25662.85 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.199 | A.1011181.199.01 | 9 5/8 Surface | SANTOS LIMITED | BUGITO 4 | Ensign 967 | J.22.110662 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-06 05:00 | 2022-11-08 |  | 2022-11-08 05:00 | 2022-11-09 04:59 |  | 2022-11-07 04:59 | AUS East Coast WS | GVang2 | 2022-11-28 12:08 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 27330.21 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.199 | A.1011181.199.02 | 5.5" Production Job | SANTOS LIMITED | BUGITO 4 | Ensign 967 | J.22.110951 | WCF | PRI-LONG | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-07 | 2022-11-09 06:00 |  | 2022-11-09 08:00 | 2022-11-09 16:59 |  | 2022-11-07 23:59 | AUS East Coast WS | GVang2 | 2022-11-28 09:44 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 31962.01 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.198 | A.1011181.198.02 | 5.5" Production Job | SANTOS LIMITED | ISOPTERA 4 | Ensign 967 | J.22.110952 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-01 | 2022-11-03 06:00 |  | 2022-11-03 08:00 | 2022-11-03 16:59 |  | 2022-11-01 23:59 | AUS East Coast WS | GVang2 | 2022-11-28 12:19 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 39803.53 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.198 | A.1011181.198.01 | 9 5/8 Surface | SANTOS LIMITED | ISOPTERA 4 | Ensign 967 | J.22.110668 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-31 01:00 | 2022-11-02 00:01 |  | 2022-11-02 01:00 | 2022-11-03 00:59 |  | 2022-11-01 00:59 | AUS East Coast WS | GVang2 | 2022-11-22 11:45 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 26357.33 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.197 | A.1011181.197.02 | 5.5" Production Job | SANTOS LIMITED | ISOPTERA 5 | Ensign 967 | J.22.110672 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-27 | 2022-10-29 06:00 |  | 2022-10-29 08:00 | 2022-10-29 16:59 |  | 2022-10-27 23:59 | AUS East Coast WS | GVang2 | 2022-10-29 13:34 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 39000.6 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.197 | A.1011181.197.01 | 9 5/8 Surface | SANTOS LIMITED | ISOPTERA 5 | Ensign 967 | J.22.110667 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-26 00:01 | 2022-10-28 |  | 2022-10-28 00:01 | 2022-10-29 |  | 2022-10-27 | AUS East Coast WS | GVang2 | 2022-10-27 13:04 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 33268.8 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.196 | A.1011181.196.02 | 5.5" Production Job | SANTOS LIMITED | SECCANTE 9 | Ensign 967 | J.22.110659 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-21 01:00 | 2022-10-23 07:00 |  | 2022-10-23 09:00 | 2022-10-23 17:59 |  | 2022-10-22 00:59 | AUS East Coast WS | GVang2 | 2022-10-24 15:02 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 43409.9 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.196 | A.1011181.196.01 | 9 5/8 Surface | SANTOS LIMITED | SECCANTE 9 | Ensign 967 | J.22.110655 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-20 01:00 | 2022-10-22 00:01 |  | 2022-10-22 01:00 | 2022-10-23 00:59 |  | 2022-10-21 00:59 | AUS East Coast WS | GVang2 | 2022-10-21 11:53 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 33106.45 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.195 | A.1011181.195.02 | 5.5" Production Job | SANTOS LIMITED | SECCANTE 8 | Ensign 967 | J.22.110665 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-07 01:00 | 2022-10-09 07:00 |  | 2022-10-09 09:00 | 2022-10-09 17:59 |  | 2022-10-08 00:59 | AUS East Coast WS | GVang2 | 2022-10-19 14:40 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 30273.83 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.195 | A.1011181.195.01 | 9 5/8 Surface | SANTOS LIMITED | SECCANTE 8 | Ensign 967 | J.22.110661 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-08 01:00 | 2022-10-08 00:01 |  | 2022-10-08 01:00 | 2022-10-09 00:59 |  | 2022-10-09 00:59 | AUS East Coast WS | GVang2 | 2022-10-19 13:08 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 36367.87 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.194 | A.1011181.194.02 | 5.5" Production Job | SANTOS LIMITED | WALLACE 2 | Ensign 967 | J.22.110675 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-15 01:00 | 2022-10-15 07:00 |  | 2022-10-15 09:00 | 2022-10-15 17:59 |  | 2022-10-16 00:59 | AUS East Coast WS | GVang2 | 2022-10-21 16:11 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 10532.77 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.194 | A.1011181.194.01 | 9 5/8 Surface | SANTOS LIMITED | WALLACE 2 | Ensign 967 | J.22.110948 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-14 01:00 | 2022-10-14 00:01 |  | 2022-10-14 01:00 | 2022-10-15 00:59 |  | 2022-10-15 00:59 | AUS East Coast WS | GVang2 | 2022-10-19 12:15 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 38930.68 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.193 | A.1011181.193.02 | 5.5" Production Job | SANTOS LIMITED | RAGNO 4 | Ensign 967 | J.22.110664 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-05 01:00 | 2022-10-05 07:00 |  | 2022-10-05 09:00 | 2022-10-05 17:59 |  | 2022-10-06 00:59 | AUS East Coast WS | GVang2 | 2022-10-27 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 27197.88 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.193 | A.1011181.193.01 | 9 5/8 Surface | SANTOS LIMITED | RAGNO 4 | Ensign 967 | J.22.110670 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-10-04 01:00 | 2022-10-04 00:01 |  | 2022-10-04 01:00 | 2022-10-05 00:59 |  | 2022-10-05 00:59 | AUS East Coast WS | GVang2 | 2022-10-24 10:37 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 27991.1 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.192 | A.1011181.192.02 | 5.5" Production Job | SANTOS LIMITED | Ragno 003 | Ensign 967 | J.22.110663 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-30 08:00 | 2022-09-30 06:00 |  | 2022-09-30 08:00 | 2022-09-30 16:59 |  | 2022-09-30 16:59 | AUS East Coast WS | GVang2 | 2022-10-26 16:25 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 33858.93 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.192 | A.1011181.192.01 | 9 5/8 Surface | SANTOS LIMITED | Ragno 003 | Ensign 967 | J.22.110654 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-26 | 2022-09-26 |  | 2022-09-26 | 2022-09-26 23:59 |  | 2022-09-26 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 32387.08 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.191 | A.1011181.191.01 | 9 5/8 Surface | SANTOS LIMITED | Ragno 2 | Ensign 967 | J.22.110660 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-09-17 | 2022-09-19 |  | 2022-09-19 | 2022-09-19 23:59 |  | 2022-09-17 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 29084.59 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.191 | A.1011181.191.02 | 5.5" Production Job | SANTOS LIMITED | Ragno 2 | Ensign 967 | J.22.110652 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-25 08:00 | 2022-09-25 06:00 |  | 2022-09-25 08:00 | 2022-09-25 16:59 |  | 2022-09-25 16:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 34845.13 | 1 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.190 | A.1011181.190.01 | 9 5/8 Surface | SANTOS LIMITED | Jena 29 | Ensign 967 | J.22.110946 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-09-13 00:02 | 2022-09-13 00:01 |  | 2022-09-13 00:02 | 2022-09-14 00:01 |  | 2022-09-14 00:01 | AUS East Coast WS | GVang2 | 2022-10-03 15:20 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 27313.27 | 1 |  |  |  | 50 | 66.7 | 0 | 100 | 60 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.190 | A.1011181.190.02 | 5.5" Production Job | SANTOS LIMITED | Jena 29 | Ensign 967 | J.22.110657 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-16 | 2022-09-16 06:00 |  | 2022-09-16 08:00 | 2022-09-16 16:59 |  | 2022-09-16 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 53237.17 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.19 | A.1011181.19.01 | 9 5/8" Surface | SANTOS LIMITED | Dullingari 63 | ENSIGN 974 | J.21.109448 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-07 11:00 | 2021-02-07 |  | 2021-02-08 | 2021-02-08 23:59 |  | 2021-02-10 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:05 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 25662.85 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.19 | A.1011181.19.02 | 7" Intermediate | SANTOS LIMITED | Dullingari 63 | ENSIGN 974 | J.21.109134 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-13 11:00 | 2021-02-13 |  | 2021-02-14 | 2021-02-14 23:59 |  | 2021-02-16 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 42556.58 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.189 | A.1011181.189.01 | 9 5/8 Surface | SANTOS LIMITED | Odonata 3 | Ensign 967 | J.22.110944 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-09-05 | 2022-09-05 |  | 2022-09-05 | 2022-09-05 23:59 |  | 2022-09-05 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:20 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 26838.12 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.189 | A.1011181.189.02 | 5.5" Production Job | SANTOS LIMITED | Odonata 3 | Ensign 967 | J.22.110666 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-09-10 08:00 | 2022-09-10 06:00 |  | 2022-09-10 08:00 | 2022-09-10 16:59 |  | 2022-09-10 16:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:32 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 61477.83 | 1 |  |  |  | 75 | 66.7 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.188 | A.1011181.188.02 | 5.5" Production Job | SANTOS LIMITED | Nungeroo West 1 | Ensign 967 | J.22.110658 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-29 08:00 | 2022-08-29 06:00 |  | 2022-08-29 08:00 | 2022-08-29 16:59 |  | 2022-08-29 16:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 42873.6 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.188 | A.1011181.188.01 | 9 5/8 Surface | SANTOS LIMITED | Nungeroo West 1 | Ensign 967 | J.22.110653 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-25 | 2022-08-25 |  | 2022-08-25 | 2022-08-25 23:59 |  | 2022-08-25 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 34072.95 | 1 |  |  |  | 87.5 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.187 | A.1011181.187.04 | Plug 1D | SANTOS LIMITED | Burley 3 | Wild Desert Rig 16 | J.22.110706 | WCF | REM-PA,REM-SQ | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-07-11 | 2022-07-10 |  | 2022-07-11 | 2022-07-11 23:59 |  | 2022-07-11 23:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:33 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 29751.14 | 3 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.187 | A.1011181.187.02 | Burley 3 - Plug 1B | SANTOS LIMITED | Burley 3 | Wild Desert Rig 16 | J.22.110695 | WCF | REM-PA,REM-SQ | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-06-18 | 2022-06-17 |  | 2022-06-18 | 2022-06-18 23:59 |  | 2022-06-18 23:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:32 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 11273.94 | 5 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.187 | A.1011181.187.03 | Plug 1C | SANTOS LIMITED | Burley 3 | Wild Desert Rig 16 | J.22.110694 | WCF | REM-PA,REM-SQ | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-07-11 | 2022-07-10 |  | 2022-07-11 | 2022-07-11 23:59 |  | 2022-07-11 23:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:32 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 13501.98 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.187 | A.1011181.187.01 | Plug 1A | SANTOS LIMITED | Burley 3 | Wild Desert Rig 16 | J.22.110651 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-06-13 | 2022-06-03 |  | 2022-06-14 | 2022-06-14 23:59 |  | 2022-06-14 23:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:31 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 10556.08 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.186 | A.1011181.186.02 | 4.5" Production Job | SANTOS LIMITED | Marsilea 2 | SLR 188 | J.22.110646 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-18 07:00 | 2022-09-18 05:00 |  | 2022-09-18 07:00 | 2022-09-18 15:59 |  | 2022-09-18 15:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 94728.14 | 1 |  |  |  | 37.5 | 16.7 | 0 | 100 | 40 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.186 | A.1011181.186.01 | 7 5/8 Surface | SANTOS LIMITED | Marsilea 2 | SLR 188 | J.22.110644 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-09-09 23:30 | 2022-09-09 23:00 |  | 2022-09-09 23:00 | 2022-09-10 22:59 |  | 2022-09-10 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 26670.78 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.185 | A.1011181.185.02 | 4.5" Production Job | SANTOS LIMITED | Swan Lake 18 | SLR 188 | J.22.110943 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-09-07 07:00 | 2022-09-01 06:00 |  | 2022-09-09 07:00 | 2022-09-09 15:59 |  | 2022-09-07 15:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:20 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 48138.32 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.185 | A.1011181.185.01 | 7 5/8 Surface | SANTOS LIMITED | Swan Lake 18 | SLR 188 | J.22.110634 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-22 | 2022-08-22 15:00 |  | 2022-08-22 15:00 | 2022-08-23 14:59 |  | 2022-08-23 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 29052.94 | 1 |  |  |  | 50 | 50 | 0 | 75 | 50 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.184 | A.1011181.184.02 | 4.5" Production Job | SANTOS LIMITED | Swan Lake 17 | SLR 188 | J.22.110942 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-18 | 2022-08-18 05:00 |  | 2022-08-18 07:00 | 2022-08-18 15:59 |  | 2022-08-18 16:00 | AUS East Coast WS | GVang2 | 2022-10-03 15:20 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 53161.2 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.184 | A.1011181.184.01 | 7 5/8 Surface | SANTOS LIMITED | Swan Lake 17 | SLR 188 | J.22.110638 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-09 23:00 | 2022-08-09 23:00 |  | 2022-08-09 23:00 | 2022-08-10 22:59 |  | 2022-08-10 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 29082.32 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.183 | A.1011181.183.01 | 7 5/8 Surface | SANTOS LIMITED | Gidgealpa 66 | SLR 188 | J.22.110941 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-07-19 23:00 | 2022-07-21 23:00 |  | 2022-07-21 23:00 | 2022-07-22 22:59 |  | 2022-07-20 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:20 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 46630.14 | 1 |  |  |  | 87.5 | 33.3 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.183 | A.1011181.183.02 | 4.5" Production Job | SANTOS LIMITED | Gidgealpa 66 | SLR 188 | J.22.110642 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-07-25 07:00 | 2022-07-28 05:00 |  | 2022-07-28 07:00 | 2022-07-28 15:59 |  | 2022-07-25 15:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 53161.2 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.182 | A.1011181.182.02 | 5.5" Production Job | SANTOS LIMITED | Gidgealpa 68 | SLR 188 | J.22.110641 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-07-17 07:00 | 2022-07-17 05:00 |  | 2022-07-17 07:00 | 2022-07-17 15:59 |  | 2022-07-17 15:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 43115.45 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.182 | A.1011181.182.01 | 9-5/8 Surface | SANTOS LIMITED | Gidgealpa 68 | SLR 188 | J.22.110639 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-07-09 23:00 | 2022-07-09 23:00 |  | 2022-07-09 23:00 | 2022-07-10 22:59 |  | 2022-07-10 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 31983.59 | 1 |  |  |  | 87.5 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.181 | A.1011181.181.01 | 9-5/8 Surface | SANTOS LIMITED | Gidgealpa 67 | SLR 188 | J.22.110939 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-06-25 23:00 | 2022-06-25 23:00 |  | 2022-06-25 23:00 | 2022-06-26 22:59 |  | 2022-06-26 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:20 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 32061.75 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.181 | A.1011181.181.02 | 5.5" Production Job | SANTOS LIMITED | Gidgealpa 67 | SLR 188 | J.22.110636 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-07-03 07:00 | 2022-07-03 05:00 |  | 2022-07-03 07:00 | 2022-07-03 15:59 |  | 2022-07-03 15:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 49308.1 | 1 |  |  |  | 68.8 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.180 | A.1011181.180.02 | Plug 1B | SANTOS LIMITED | Keleary 3 | Wild Desert Rig 16 | J.22.110637 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-05-28 08:00 | 2022-05-27 23:00 |  | 2022-05-28 08:00 | 2022-05-29 08:00 |  | 2022-05-29 21:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:31 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 8951.61 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.180 | A.1011181.180.01 | Plug 1A | SANTOS LIMITED | Keleary 3 | Wild Desert Rig 16 | J.22.110635 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-05-26 11:00 | 2022-05-25 08:00 |  | 2022-05-26 11:00 | 2022-05-27 02:59 |  | 2022-05-27 14:00 | AUS East Coast WS | MAlsaman | 2022-10-03 14:31 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 26052.38 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.180 | A.1011181.180.03 | Plug 1C | SANTOS LIMITED | Keleary 3 | Wild Desert Rig 16 | J.22.110633 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-05-31 | 2022-05-30 |  | 2022-05-31 | 2022-05-31 23:59 |  | 2022-05-31 23:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:31 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 13367.12 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.18 | A.1011181.18.02 | 4.5" Production Job | SANTOS LIMITED | Anna North 4 | Ensign 967 | J.21.109118 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-22 10:00 | 2021-04-23 05:00 |  | 2021-04-23 07:00 | 2021-04-23 15:59 |  | 2021-04-25 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:20 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 49308.1 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.18 | A.1011181.18.01 | 7 5/8 Surface | SANTOS LIMITED | Anna North 4 | Ensign 967 | J.21.109115 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-13 10:00 | 2021-04-13 23:00 |  | 2021-04-13 23:00 | 2021-04-14 22:59 |  | 2021-04-16 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:20 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 32061.75 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.179 | A.1011181.179.01 | Dummy Job February | SANTOS LIMITED | Well #1 | ENSIGN 971 | J.22.110632 | WCF | PRI-SURF | Low | Unconfirmed - 10% | Design - CEC |  | Not Started | In Progress | In Progress |  | 2022-07-18 22:00 |  | 2022-07-18 22:00 | 2022-07-19 21:59 |  |  | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.178 | A.1011181.178.01 | Plug 1A | SANTOS LIMITED | Coonatie 10 | Wild Desert Rig 16 | J.22.110938 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-05-06 11:00 | 2022-05-06 08:00 |  | 2022-05-06 11:00 | 2022-05-07 02:59 |  | 2022-05-07 14:00 | AUS East Coast WS | MAlsaman | 2022-10-03 15:20 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 26052.38 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.178 | A.1011181.178.02 | Plug 1B | SANTOS LIMITED | Coonatie 10 | Wild Desert Rig 16 | J.22.110631 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-05-24 22:00 | 2022-05-23 23:00 |  | 2022-05-24 08:00 | 2022-05-25 08:00 |  | 2022-05-25 21:59 | AUS East Coast WS | MAlsaman | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 8951.61 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.177 | A.1011181.177.03 | Plug 1C | SANTOS LIMITED | Naccowlah West 15 | Wild Desert Rig 22 | J.22.110940 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-11-06 | 2022-11-06 |  | 2022-11-06 | 2022-11-06 23:59 |  | 2022-11-06 23:59 | AUS East Coast WS | MAlsaman | 2022-12-19 12:16 | GVang2 |  | No |  |  |  |  | Tareq AlSaman |  | 4917.22 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.177 | A.1011181.177.02 | Plug 1B | SANTOS LIMITED | Naccowlah West 15 | Wild Desert Rig 22 | J.22.110937 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-05-27 22:00 | 2022-05-26 23:00 |  | 2022-05-28 08:00 | 2022-05-29 08:00 |  | 2022-05-28 21:59 | AUS East Coast WS | GSingh54 | 2022-10-03 15:19 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 24246.31 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.177 | A.1011181.177.01 | Plug 1A | SANTOS LIMITED | Naccowlah West 15 | Wild Desert Rig 22 | J.22.110936 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-05-23 11:00 | 2022-05-22 23:00 |  | 2022-05-23 11:00 | 2022-05-24 02:59 |  | 2022-05-24 02:59 | AUS East Coast WS | GSingh54 | 2022-10-03 15:19 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 26052.38 | 1 |  |  |  | 81.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.176 | A.1011181.176.02 | Plug 1B | SANTOS LIMITED | Meranji 15 | Wild Desert Rig 16 | J.22.110935 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-05-02 22:00 | 2022-05-01 23:00 |  | 2022-05-02 08:00 | 2022-05-03 08:00 |  | 2022-05-03 21:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:19 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 8951.61 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.176 | A.1011181.176.01 | Plug 1A | SANTOS LIMITED | Meranji 15 | Wild Desert Rig 16 | J.22.110934 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-23 21:00 | 2022-04-22 23:00 |  | 2022-04-23 11:00 | 2022-04-24 02:59 |  | 2022-04-24 14:00 | AUS East Coast WS | GVang2 | 2022-10-03 15:19 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 26052.38 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.175 | A.1011181.175.01 | Dummy Job February | SANTOS LIMITED | Well #1 | Ensign 967 | J.22.110627 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2022-07-02 22:00 |  | 2022-07-02 22:00 | 2022-07-03 21:59 |  |  | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.174 | A.1011181.174.01 | Dummy Job February | SANTOS LIMITED | Well #1 | SLR RIG 183 | J.22.110933 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2022-05-06 22:00 |  | 2022-05-06 22:00 | 2022-05-07 21:59 |  |  | AUS East Coast WS | GVang2 | 2022-10-03 15:19 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.173 | A.1011181.173.02 | 4 1/2" Production (hot) | SANTOS LIMITED | MOOMBA 281 | ENSIGN 971 | J.22.110630 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-12 | 2022-10-12 01:00 |  | 2022-10-12 01:00 | 2022-10-13 00:59 |  | 2022-10-13 01:00 | AUS East Coast WS | GVang2 | 2022-10-24 14:13 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 41321.07 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.173 | A.1011181.173.01 | 7" Surface | SANTOS LIMITED | MOOMBA 281 | ENSIGN 971 | J.22.110629 | WCF | PRI-SURF | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-02 03:00 | 2022-10-02 03:00 |  | 2022-10-02 03:00 | 2022-10-03 02:59 |  | 2022-10-03 02:59 | AUS East Coast WS | GVang2 | 2022-10-20 13:35 | GSingh54 |  | No |  |  |  |  | Grace Vang |  | 28555.74 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.172 | A.1011181.172.02 | 4 1/2" Production (hot) | SANTOS LIMITED | Moomba 280 | ENSIGN 971 | J.22.110628 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-29 23:00 | 2022-09-30 |  | 2022-09-30 | 2022-09-30 23:59 |  | 2022-09-30 22:59 | AUS East Coast WS | GVang2 | 2022-10-24 09:56 | GVang2 |  | No |  |  |  |  | Gaurav Kumar Singh |  | 35750.05 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.172 | A.1011181.172.01 | 7 5/8" Surface | SANTOS LIMITED | Moomba 280 | ENSIGN 971 | J.22.110626 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-09-17 01:00 | 2022-09-17 01:00 |  | 2022-09-17 01:00 | 2022-09-18 00:59 |  | 2022-09-18 00:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 48676.65 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.171 | A.1011181.171.02 | 4 1/2" Production (hot) | SANTOS LIMITED | Moomba 277 | ENSIGN 971 | J.22.110932 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-23 | 2022-08-23 |  | 2022-08-23 | 2022-08-23 23:59 |  | 2022-08-23 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:19 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 46643.71 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.171 | A.1011181.171.01 | 7 5/8" Surface | SANTOS LIMITED | Moomba 277 | ENSIGN 971 | J.22.110624 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-08-15 01:00 | 2022-08-15 01:00 |  | 2022-08-15 01:00 | 2022-08-16 00:59 |  | 2022-08-16 00:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 30340.97 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.170 | A.1011181.170.01 | 7" Surface | SANTOS LIMITED | Moomba 278 | ENSIGN 971 | J.22.110931 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-12 01:00 | 2022-08-12 01:00 |  | 2022-08-12 01:00 | 2022-08-13 00:59 |  | 2022-08-13 00:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:19 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 30340.97 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.170 | A.1011181.170.02 | 4 1/2" Production (hot) | SANTOS LIMITED | Moomba 278 | ENSIGN 971 | J.22.110622 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-02 | 2022-09-02 |  | 2022-09-02 | 2022-09-02 23:59 |  | 2022-09-02 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 60684.66 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.17 | A.1011181.17.03 | Dummy Job 1 | SANTOS LIMITED | Anna North 3 | Ensign 967 | J.21.109229 | WCF | PRI-LONG | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-04-26 10:00 | 2021-04-27 05:00 |  | 2021-04-27 07:00 | 2021-04-27 15:59 |  | 2021-04-29 09:59 | AUS East Coast WS | GSingh54 | 2022-10-03 14:24 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.17 | A.1011181.17.01 | 7 5/8 Surface | SANTOS LIMITED | Anna North 3 | Ensign 967 | J.21.109150 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-01 11:00 | 2021-04-02 |  | 2021-04-02 | 2021-04-02 23:59 |  | 2021-04-04 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 31564.63 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.17 | A.1011181.17.02 | 4.5" Production Job | SANTOS LIMITED | Anna North 3 | Ensign 967 | J.21.109105 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-11 10:00 | 2021-04-12 05:00 |  | 2021-04-12 07:00 | 2021-04-12 15:59 |  | 2021-04-14 09:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:20 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 51422.72 | 1 |  |  |  | 81.3 | 33.3 | 0 | 62.5 | 55 |  | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.169 | A.1011181.169.02 | 4 1/2" Production (hot) | SANTOS LIMITED | Moomba 279 | ENSIGN 971 | J.22.110930 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-10 01:00 | 2022-09-10 |  | 2022-09-10 | 2022-09-10 23:59 |  | 2022-09-10 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:19 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 59519.21 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.169 | A.1011181.169.01 | 7" Surface | SANTOS LIMITED | Moomba 279 | ENSIGN 971 | J.22.110623 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-10 01:00 | 2022-08-10 01:00 |  | 2022-08-10 01:00 | 2022-08-11 00:59 |  | 2022-08-11 00:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 31178.29 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.168 | A.1011181.168.01 | 7 5/8" Surface | SANTOS LIMITED | Moomba 275 | ENSIGN 971 | J.22.110929 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-07-20 01:00 | 2022-07-20 01:00 |  | 2022-07-20 01:00 | 2022-07-22 00:59 |  | 2022-07-21 00:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:18 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 20295.22 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.168 | A.1011181.168.02 | 4 1/2" Production (hot) | SANTOS LIMITED | Moomba 275 | ENSIGN 971 | J.22.110625 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-07-25 | 2022-08-02 |  | 2022-08-02 10:00 | 2022-08-03 09:59 |  | 2022-07-31 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 82245.61 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.167 | A.1011181.167.01 | 7" Surface | SANTOS LIMITED | Moomba 267 | ENSIGN 971 | J.22.110621 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-07-02 01:00 | 2022-07-02 01:00 |  | 2022-07-02 01:00 | 2022-07-03 00:59 |  | 2022-07-03 00:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 25478.48 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.167 | A.1011181.167.02 | 4 1/2" Production (hot) | SANTOS LIMITED | Moomba 267 | ENSIGN 971 | J.22.110620 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-07-13 | 2022-07-13 |  | 2022-07-13 | 2022-07-13 23:59 |  | 2022-07-13 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 67176.99 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.166 | A.1011181.166.02 | 4 1/2" Production (hot) | SANTOS LIMITED | Moomba 268 | ENSIGN 971 | J.22.110928 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | In Progress | Design Completed | Design Completed | 2022-06-18 12:00 | 2022-06-29 |  | 2022-06-29 12:00 | 2022-06-30 11:59 |  | 2022-06-19 11:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:18 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 69879.55 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.166 | A.1011181.166.01 | 7 5/8" Surface | SANTOS LIMITED | Moomba 268 | ENSIGN 971 | J.22.110927 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-06-17 01:00 | 2022-06-17 01:00 |  | 2022-06-17 01:00 | 2022-06-18 00:59 |  | 2022-06-18 00:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:18 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 25478.48 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.165 | A.1011181.165.02 | 4 1/2" Production (hot) | SANTOS LIMITED | Moomba 273 | ENSIGN 971 | J.22.110617 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-06-10 | 2022-06-10 |  | 2022-06-10 | 2022-06-10 23:59 |  | 2022-06-10 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 69879.55 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.165 | A.1011181.165.01 | 7" Surface | SANTOS LIMITED | Moomba 273 | ENSIGN 971 | J.22.110616 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-05-29 01:00 | 2022-05-29 01:00 |  | 2022-05-29 01:00 | 2022-05-30 00:59 |  | 2022-05-30 00:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 25478.48 | 1 |  |  |  | 56.3 | 66.7 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.164 | A.1011181.164.02 | 4.5" Production | SANTOS LIMITED | Yarrow 3 | ENSIGN 974 | J.22.110618 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-25 | 2022-09-25 |  | 2022-09-25 | 2022-09-25 23:59 |  | 2022-09-25 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 35027.24 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.164 | A.1011181.164.01 | 7 5/8" Surface | SANTOS LIMITED | Yarrow 3 | ENSIGN 974 | J.22.110612 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-17 23:00 | 2022-09-17 23:00 |  | 2022-09-17 23:00 | 2022-09-18 22:59 |  | 2022-09-18 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 2947.23 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.163 | A.1011181.163.03 | 7" Intermediate | SANTOS LIMITED | Dullingari 67 | ENSIGN 974 | J.22.110926 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-07 12:00 | 2022-08-07 |  | 2022-08-07 12:00 | 2022-08-08 23:59 |  | 2022-08-08 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:18 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 30930.31 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.163 | A.1011181.163.02 | 7" Intermediate | SANTOS LIMITED | Dullingari 67 | ENSIGN 974 | J.22.110619 | WCF | PRI-INTER | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-09-18 |  | 2022-09-18 | 2022-09-18 23:59 |  |  | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.163 | A.1011181.163.01 | 9 5/8" Surface | SANTOS LIMITED | Dullingari 67 | ENSIGN 974 | J.22.110614 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-08-03 | 2022-08-02 23:00 |  | 2022-08-02 23:00 | 2022-08-03 22:59 |  | 2022-08-03 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 41250.25 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.162 | A.1011181.162.02 | 7" Intermediate | SANTOS LIMITED | Dullingari 68 | ENSIGN 974 | J.22.110925 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-07-18 10:00 | 2022-07-19 |  | 2022-07-19 10:00 | 2022-07-20 09:59 |  | 2022-07-19 09:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:18 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 50102.77 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.162 | A.1011181.162.01 | 9 5/8" Surface | SANTOS LIMITED | Dullingari 68 | ENSIGN 974 | J.22.110611 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-07-13 | 2022-07-13 23:00 |  | 2022-07-13 23:00 | 2022-07-14 22:59 |  | 2022-07-13 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 25713.44 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.161 | A.1011181.161.02 | 7" Intermediate | SANTOS LIMITED | Dullingari 66 | ENSIGN 974 | J.22.110924 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-07-01 | 2022-07-01 |  | 2022-07-01 | 2022-07-01 23:59 |  | 2022-07-01 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:18 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 43680.94 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.161 | A.1011181.161.01 | 9 5/8" Surface | SANTOS LIMITED | Dullingari 66 | ENSIGN 974 | J.22.110615 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-06-23 | 2022-06-22 23:00 |  | 2022-06-22 23:00 | 2022-06-23 22:59 |  | 2022-06-23 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 38681.51 | 1 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.160 | A.1011181.160.02 | 7" Intermediate | SANTOS LIMITED | Dullingari 64 | ENSIGN 974 | J.22.110613 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-06-14 | 2022-06-14 |  | 2022-06-14 | 2022-06-14 23:59 |  | 2022-06-14 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 43680.94 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.160 | A.1011181.160.01 | 9 5/8" Surface | SANTOS LIMITED | Dullingari 64 | ENSIGN 974 | J.22.110609 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-06-08 | 2022-06-07 23:00 |  | 2022-06-07 23:00 | 2022-06-08 22:59 |  | 2022-06-08 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 38681.51 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.16 | A.1011181.16.01 | 7 5/8 Surface | SANTOS LIMITED | Anna North 2 | Ensign 967 | J.21.109460 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-16 11:00 | 2021-03-17 |  | 2021-03-17 | 2021-03-17 23:59 |  | 2021-03-19 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:07 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 19207.25 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.16 | A.1011181.16.02 | 4.5" Production Job | SANTOS LIMITED | Anna North 2 | Ensign 967 | J.21.109161 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-03-27 11:00 | 2021-03-28 06:00 |  | 2021-03-28 08:00 | 2021-03-28 16:59 |  | 2021-03-30 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 52602.41 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.159 | A.1011181.159.02 | Plug 1B | SANTOS LIMITED | Correa 1 | Wild Desert Rig 16 | J.22.110610 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-29 23:00 | 2022-03-29 |  | 2022-03-29 09:00 | 2022-03-30 09:00 |  | 2022-03-30 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 33033.75 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.159 | A.1011181.159.01 | Plug 1A | SANTOS LIMITED | Correa 1 | Wild Desert Rig 16 | J.22.110608 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-26 22:00 | 2022-03-26 |  | 2022-03-26 12:00 | 2022-03-27 03:59 |  | 2022-03-27 15:00 | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 26052.38 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.158 | A.1011181.158.03 | Plug 1C | SANTOS LIMITED | Kurunda 1 | Wild Desert Rig 16 | J.22.110923 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-02-26 11:00 | 2022-02-26 |  | 2022-02-26 11:00 | 2022-02-27 00:55 |  | 2022-02-27 00:55 | AUS East Coast WS | GVang2 | 2022-10-03 15:18 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 17081.36 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.158 | A.1011181.158.02 | Plug 1B | SANTOS LIMITED | Kurunda 1 | Wild Desert Rig 16 | J.22.110607 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-02-25 10:00 | 2022-02-25 |  | 2022-02-25 10:00 | 2022-02-26 10:00 |  | 2022-02-26 10:00 | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 15206.79 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.158 | A.1011181.158.01 | Plug 1A | SANTOS LIMITED | Kurunda 1 | Wild Desert Rig 16 | J.22.110604 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-02-21 | 2022-02-21 |  | 2022-02-21 01:00 | 2022-02-21 16:59 |  | 2022-02-21 17:00 | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 26052.38 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.157 | A.1011181.157.01 | 4.5" Production Job | SANTOS LIMITED | Well #1 | SLR 188 | J.22.110606 | WCF | PRI-LONG | Low | Cancelled | Close - PSD |  | In Progress | Design Completed | Design Completed | 2022-11-05 09:00 | 2022-11-05 |  | 2022-11-05 08:00 | 2022-11-05 16:59 |  | 2022-11-05 17:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 139384.71 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.156 | A.1011181.156.04 | Plug 1D | SANTOS LIMITED | Kidman North 2 | Wild Desert Rig 16 | J.22.110922 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-02-12 11:00 | 2022-02-12 |  | 2022-02-12 11:00 | 2022-02-13 00:55 |  | 2022-02-13 00:55 | AUS East Coast WS | GVang2 | 2022-10-03 15:18 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.156 | A.1011181.156.01 | Plug 1A | SANTOS LIMITED | Kidman North 2 | Wild Desert Rig 16 | J.22.110599 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-02-09 | 2022-02-09 |  | 2022-02-09 01:00 | 2022-02-09 16:59 |  | 2022-02-09 17:00 | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.156 | A.1011181.156.02 | Plug 1B | SANTOS LIMITED | Kidman North 2 | Wild Desert Rig 16 | J.22.110595 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-02-11 10:00 | 2022-02-11 |  | 2022-02-11 10:00 | 2022-02-12 10:00 |  | 2022-02-12 10:00 | AUS East Coast WS | GVang2 | 2022-10-03 14:30 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 17826.96 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.156 | A.1011181.156.03 | Plug 1C | SANTOS LIMITED | Kidman North 2 | Wild Desert Rig 16 | J.22.110588 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-02-17 12:00 | 2022-02-17 |  | 2022-02-17 | 2022-02-18 |  | 2022-02-17 12:00 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 14919.92 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.155 | A.1011181.155.02 | 7" Intermediate | SANTOS LIMITED | Dullingari 65 | ENSIGN 974 | J.22.110589 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-05-21 23:00 | 2022-05-21 23:00 |  | 2022-05-21 23:00 | 2022-05-22 22:59 |  | 2022-05-22 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 43680.94 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.155 | A.1011181.155.01 | 9 5/8" Surface | SANTOS LIMITED | Dullingari 65 | ENSIGN 974 | J.22.110586 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-05-16 23:00 | 2022-05-16 22:00 |  | 2022-05-16 22:00 | 2022-05-17 21:59 |  | 2022-05-17 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 25662.85 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.154 | A.1011181.154.01 | 9 5/8" Surface | SANTOS LIMITED | Bow 3 | ENSIGN 974 | J.22.110585 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-23 23:00 | 2022-04-23 23:00 |  | 2022-04-23 23:00 | 2022-04-24 22:59 |  | 2022-04-24 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 9575.17 | 1 |  |  |  | 81.3 | 66.7 | 0 | 37.5 | 60 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.154 | A.1011181.154.02 | 7" Intermediate | SANTOS LIMITED | Bow 3 | ENSIGN 974 | J.22.110573 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-05-02 23:00 | 2022-05-02 23:00 |  | 2022-05-02 23:00 | 2022-05-03 22:59 |  | 2022-05-03 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 9712.83 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.153 | A.1011181.153.02 | 7" Intermediate | SANTOS LIMITED | Beckler 8 | ENSIGN 974 | J.22.110583 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-27 23:00 | 2022-04-27 23:00 |  | 2022-04-27 23:00 | 2022-04-28 22:59 |  | 2022-04-28 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 43680.94 | 1 |  |  |  | 81.3 | 33.3 | 0 | 25 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.153 | A.1011181.153.01 | 9 5/8" Surface | SANTOS LIMITED | Beckler 8 | ENSIGN 974 | J.22.110578 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-01 | 2022-03-31 23:00 |  | 2022-03-31 23:00 | 2022-04-01 22:59 |  | 2022-04-01 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 36833.34 | 1 |  |  |  | 81.3 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.152 | A.1011181.152.02 | 7" Intermediate | SANTOS LIMITED | Meranji 26 | ENSIGN 974 | J.22.110579 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-18 | 2022-03-18 |  | 2022-03-18 | 2022-03-18 23:59 |  | 2022-03-18 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 23813.13 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.152 | A.1011181.152.01 | 9 5/8" Surface | SANTOS LIMITED | Meranji 26 | ENSIGN 974 | J.22.110572 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-11 | 2022-03-10 23:00 |  | 2022-03-10 23:00 | 2022-03-11 22:59 |  | 2022-03-11 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 32811.44 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.151 | A.1011181.151.01 | 9 5/8" Surface | SANTOS LIMITED | Meranji 25 | ENSIGN 974 | J.22.110920 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-02-19 | 2022-02-18 23:00 |  | 2022-02-18 23:00 | 2022-02-19 22:59 |  | 2022-02-19 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:17 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 26640.84 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.151 | A.1011181.151.02 | 7" Intermediate | SANTOS LIMITED | Meranji 25 | ENSIGN 974 | J.22.110581 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-02-25 | 2022-02-25 |  | 2022-02-25 | 2022-02-25 23:59 |  | 2022-02-25 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 25946.51 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.150 | A.1011181.150.02 | 4.5" Production | SANTOS LIMITED | Moomba 266 | SLR RIG 183 | J.22.110580 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-06-20 21:00 | 2022-06-21 11:00 |  | 2022-06-21 11:00 | 2022-06-22 10:59 |  | 2022-06-23 20:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 59213.07 | 1 |  |  |  | 81.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.150 | A.1011181.150.01 | 7-5/8" Surface | SANTOS LIMITED | Moomba 266 | SLR RIG 183 | J.22.110575 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-06-15 01:00 | 2022-06-15 |  | 2022-06-15 03:00 | 2022-06-16 02:59 |  | 2022-06-17 01:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 28094.19 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.15 | A.1011181.15.02 | Annabella 1 P&A | SANTOS LIMITED | Annabella 1 | Ensign 967 | J.21.109148 | WCF | PRI-LONG, REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-03-10 11:00 | 2021-03-11 06:00 |  | 2021-03-12 08:00 | 2021-03-12 16:59 |  | 2021-03-14 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 85943.82 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.15 | A.1011181.15.01 | 7 5/8 Surface | SANTOS LIMITED | Annabella 1 | Ensign 967 | J.21.109135 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-28 11:00 | 2021-03-01 |  | 2021-03-01 | 2021-03-01 23:59 |  | 2021-03-03 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 23873.92 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.149 | A.1011181.149.02 | 4-1/2" Production | SANTOS LIMITED | Big Lake 160 | SLR RIG 183 | J.22.110574 | WCF | PRI-INTER,PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-09-16 21:00 | 2022-09-17 23:00 |  | 2022-09-17 23:00 | 2022-09-18 22:59 |  | 2022-09-19 20:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 58468.33 | 1 |  |  |  | 87.5 | 33.3 | 0 | 100 | 65 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.149 | A.1011181.149.01 | 7-5/8" Surface | SANTOS LIMITED | Big Lake 160 | SLR RIG 183 | J.22.110569 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-09-05 22:00 | 2022-09-05 21:00 |  | 2022-09-06 | 2022-09-06 23:59 |  | 2022-09-07 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 42303.72 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.148 | A.1011181.148.01 | 9 5/8 Surface | SANTOS LIMITED | Narcoonowie 11 | Ensign 967 | J.22.110576 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-07-21 10:00 | 2022-07-21 |  | 2022-07-21 10:00 | 2022-07-22 09:59 |  | 2022-07-22 09:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 34072.95 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.148 | A.1011181.148.02 | 5.5" Production Job | SANTOS LIMITED | Narcoonowie 11 | Ensign 967 | J.22.110568 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-07-28 08:00 | 2022-07-28 06:00 |  | 2022-07-28 08:00 | 2022-07-28 16:59 |  | 2022-07-28 16:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 50649.76 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.147 | A.1011181.147.01 | 9 5/8 Surface | SANTOS LIMITED | Narcoonowie 13 | Ensign 967 | J.22.110570 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-13 | 2022-08-13 |  | 2022-08-13 | 2022-08-13 23:59 |  | 2022-08-13 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 29050.07 | 1 |  |  |  | 87.5 | 33.3 | 0 | 100 | 65 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.147 | A.1011181.147.02 | 5.5" Production Job | SANTOS LIMITED | Narcoonowie 13 | Ensign 967 | J.22.110563 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-17 08:00 | 2022-08-17 06:00 |  | 2022-08-17 08:00 | 2022-08-17 16:59 |  | 2022-08-17 16:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 48138.32 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.146 | A.1011181.146.01 | 9 5/8 Surface | SANTOS LIMITED | Cooroo North West 7 | Ensign 967 | J.22.110919 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-07-01 | 2022-07-01 |  | 2022-07-01 | 2022-07-01 23:59 |  | 2022-07-01 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:17 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 31983.59 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.146 | A.1011181.146.02 | 5.5" Production Job | SANTOS LIMITED | Cooroo North West 7 | Ensign 967 | J.22.110571 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-07-08 08:00 | 2022-07-08 06:00 |  | 2022-07-08 08:00 | 2022-07-08 16:59 |  | 2022-07-05 16:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 73332.4 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.145 | A.1011181.145.01 | 9 5/8 Surface | SANTOS LIMITED | Hector South East 2 | Ensign 967 | J.22.110566 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-06-18 | 2022-06-18 |  | 2022-06-18 | 2022-06-18 23:59 |  | 2022-06-18 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 31983.59 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.145 | A.1011181.145.02 | 4.5" Production Job | SANTOS LIMITED | Hector South East 2 | Ensign 967 | J.22.110565 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-06-24 08:00 | 2022-06-24 06:00 |  | 2022-06-24 08:00 | 2022-06-24 16:59 |  | 2022-06-24 16:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 21226.76 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.144 | A.1011181.144.01 | 9 5/8 Surface | SANTOS LIMITED | Narcoonowie 12 | Ensign 967 | J.22.110567 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-03 | 2022-08-04 |  | 2022-08-04 | 2022-08-04 23:59 |  | 2022-08-03 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 34072.95 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.144 | A.1011181.144.02 | 5.5" Production Job | SANTOS LIMITED | Narcoonowie 12 | Ensign 967 | J.22.110560 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-08-08 08:00 | 2022-08-08 06:00 |  | 2022-08-08 08:00 | 2022-08-08 16:59 |  | 2022-08-08 16:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 48138.32 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.143 | A.1011181.143.04 | Plug 3C2 | SANTOS LIMITED | Pondrinie 6 | Wild Desert Rig 16 | J.22.110918 | WCF | REM-PA | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2022-01-24 12:00 | 2022-01-24 12:00 |  | 2022-01-25 | 2022-01-26 11:59 |  | 2022-01-25 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:17 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.143 | A.1011181.143.02 | Plug 1B | SANTOS LIMITED | Pondrinie 6 | Wild Desert Rig 16 | J.22.110562 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-17 10:00 | 2022-01-17 |  | 2022-01-17 10:00 | 2022-01-18 10:00 |  | 2022-01-18 10:00 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 17826.96 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.143 | A.1011181.143.03 | Plug 1C | SANTOS LIMITED | Pondrinie 6 | Wild Desert Rig 16 | J.22.110559 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-22 12:00 | 2022-01-22 |  | 2022-01-22 | 2022-01-23 |  | 2022-01-22 12:00 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 14919.92 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.143 | A.1011181.143.01 | Pondrinie 6 Plug 1A | SANTOS LIMITED | Pondrinie 6 | Wild Desert Rig 16 | J.22.110556 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-15 | 2022-01-15 |  | 2022-01-15 01:00 | 2022-01-15 16:59 |  | 2022-01-15 17:00 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 26052.38 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.142 | A.1011181.142.01 | Roti 2 | SANTOS LIMITED | Roti 2 | Wild Desert Rig 22 | J.22.110564 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-14 22:00 | 2022-01-14 23:00 |  | 2022-01-14 23:00 | 2022-01-15 14:59 |  | 2022-01-15 12:00 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 26052.38 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.141 | A.1011181.141.03 | PnA | SANTOS LIMITED | Coolah 18 | ENSIGN 974 | J.22.110921 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-21 12:00 | 2022-01-21 |  | 2022-01-21 12:00 | 2022-01-22 12:00 |  | 2022-01-22 12:00 | AUS East Coast WS | GVang2 | 2022-10-03 15:17 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 55885.69 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.141 | A.1011181.141.02 | 7" Intermediate | SANTOS LIMITED | Coolah 18 | ENSIGN 974 | J.22.110561 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-17 01:00 | 2022-01-17 01:00 |  | 2022-01-18 01:00 | 2022-01-19 00:59 |  | 2022-01-20 00:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 25190.44 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.141 | A.1011181.141.01 | 9 5/8" Surface | SANTOS LIMITED | Coolah 18 | ENSIGN 974 | J.22.110554 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-09 01:00 | 2022-01-10 |  | 2022-01-10 | 2022-01-10 23:59 |  | 2022-01-11 00:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 24351.88 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.140 | A.1011181.140.03 | Plug 3C | SANTOS LIMITED | Kurunda 4 | Wild Desert Rig 16 | J.22.110917 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-08 12:00 | 2022-01-08 |  | 2022-01-08 12:00 | 2022-01-09 12:00 |  | 2022-01-09 12:00 | AUS East Coast WS | GVang2 | 2022-10-03 15:17 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 14919.92 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.140 | A.1011181.140.02 | Plug 2B | SANTOS LIMITED | Kurunda 4 | Wild Desert Rig 16 | J.22.110916 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-06 10:00 | 2022-01-06 |  | 2022-01-06 10:00 | 2022-01-07 10:00 |  | 2022-01-07 10:00 | AUS East Coast WS | GVang2 | 2022-10-03 15:17 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 17826.96 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.140 | A.1011181.140.04 | Plug 3C2 | SANTOS LIMITED | Kurunda 4 | Wild Desert Rig 16 | J.22.110557 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-07 12:00 | 2022-01-07 |  | 2022-01-07 12:00 | 2022-01-08 23:59 |  | 2022-01-08 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 18386.28 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.140 | A.1011181.140.01 | Kurunda 4 Plug 1A | SANTOS LIMITED | Kurunda 4 | Wild Desert Rig 16 | J.22.110552 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-04 22:00 | 2022-01-04 23:00 |  | 2022-01-04 23:00 | 2022-01-05 14:59 |  | 2022-01-05 12:00 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.14 | A.1011181.14.02 | 3 1/2" production job | SANTOS LIMITED | Bolah 5 | Ensign 967 | J.21.109129 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-21 11:00 | 2021-02-22 06:00 |  | 2021-02-23 08:00 | 2021-02-23 16:59 |  | 2021-02-25 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 67646.13 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.14 | A.1011181.14.01 | 7 5/8" Surface cement job | SANTOS LIMITED | Bolah 5 | Ensign 967 | J.21.109121 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-08 11:00 | 2021-02-08 |  | 2021-02-09 08:00 | 2021-02-10 16:00 |  | 2021-02-11 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:20 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 30991.34 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.139 | A.1011181.139.02 | Ipundu North 8 | SANTOS LIMITED | IPUNDU NORTH 8 | Wild Desert Rig 22 | J.21.109529 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-16 | 2021-12-17 02:00 |  | 2021-12-17 09:00 | 2021-12-18 00:59 |  | 2021-12-16 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:17 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 26052.38 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.139 | A.1011181.139.01 | Ipundu 10 | SANTOS LIMITED | IPUNDU NORTH 10 | Wild Desert Rig 22 | J.21.109528 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-16 | 2021-12-17 02:00 |  | 2021-12-17 09:00 | 2021-12-18 00:59 |  | 2021-12-16 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:17 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 26052.38 | 1 |  |  |  | 81.3 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.138 | A.1011181.138.02 | Dummy Job February | SANTOS LIMITED | Well #1 | ENSIGN 971 | J.22.110915 | WCF | PRI-SURF | Low | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2022-04-27 21:00 |  | 2022-04-27 21:00 | 2022-04-28 20:59 |  |  | AUS East Coast WS | GVang2 | 2022-10-03 15:17 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.138 | A.1011181.138.01 | Dummy | SANTOS LIMITED | Well #1 | ENSIGN 971 | J.22.110555 | WCF | PRI-SURF | Low | Unconfirmed - 90% | Design - CEC |  | Not Started | In Progress | In Progress |  | 2022-01-19 22:00 |  | 2022-01-19 22:00 | 2022-01-20 21:59 |  |  | AUS East Coast WS | GVang2 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 0 | 2 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.137 | A.1011181.137.01 | Ipundu North 6 | SANTOS LIMITED | IPUNDU NORTH 6 | Wild Desert Rig 22 | J.21.109312 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-10 | 2021-12-11 02:00 |  | 2021-12-11 09:00 | 2021-12-12 00:59 |  | 2021-12-10 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 26052.38 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.136 | A.1011181.136.01 | Ipundu North 10 | SANTOS LIMITED | IPUNDU NORTH 10 | Wild Desert Rig 22 | J.21.109523 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-29 | 2021-11-30 02:00 |  | 2021-11-30 09:00 | 2021-12-01 00:59 |  | 2021-11-29 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:15 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 26052.38 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.135 | A.1011181.135.05 | Plug 4 | SANTOS LIMITED | Kurunda 3 | Wild Desert Rig 16 | J.21.109526 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-10 12:00 | 2021-12-10 |  | 2021-12-10 12:00 | 2021-12-11 12:00 |  | 2021-12-11 12:00 | AUS East Coast WS | GVang2 | 2022-10-03 15:16 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 14919.92 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.135 | A.1011181.135.04 | Plug 3C | SANTOS LIMITED | Kurunda 3 | Wild Desert Rig 16 | J.21.109525 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-01 12:00 | 2021-12-01 |  | 2021-12-11 12:00 | 2021-12-12 12:00 |  | 2021-12-12 12:00 | AUS East Coast WS | GVang2 | 2022-10-03 15:15 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 15597.35 | 2 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.135 | A.1011181.135.03 | Plug 1B | SANTOS LIMITED | Kurunda 3 | Wild Desert Rig 16 | J.21.109310 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-26 23:30 | 2021-11-26 |  | 2021-12-11 23:30 | 2021-12-12 12:00 |  | 2021-11-27 12:00 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 20707.28 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.135 | A.1011181.135.02 | Plug 1A-1 | SANTOS LIMITED | Kurunda 3 | Wild Desert Rig 16 | J.21.109306 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-25 10:00 | 2021-11-25 |  | 2021-11-25 10:00 | 2021-11-26 10:00 |  | 2021-11-26 10:00 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 17826.96 | 1 |  |  |  | 81.3 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.135 | A.1011181.135.01 | Kurunda 3 Plug 1A-0 | SANTOS LIMITED | Kurunda 3 | Wild Desert Rig 16 | J.21.109304 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-26 | 2021-11-27 02:00 |  | 2021-11-27 09:00 | 2021-11-28 00:59 |  | 2021-11-26 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 26052.38 | 1 |  |  |  | 78.1 | 25 | 0 | 50 | 48.8 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.134 | A.1011181.134.01 | 7 5/8" Surface | SANTOS LIMITED | Moomba 265 | SLR RIG 183 | J.22.110551 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-05-29 11:00 | 2022-05-29 |  | 2022-05-29 01:00 | 2022-05-31 00:59 |  | 2022-06-01 10:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 28094.19 | 1 |  |  |  | 71.9 | 58.3 | 0 | 75 | 61.3 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.134 | A.1011181.134.02 | 4 1/2" Intermediate | SANTOS LIMITED | Moomba 265 | SLR RIG 183 | J.22.110547 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-06-08 11:00 | 2022-06-08 01:00 |  | 2022-06-09 01:00 | 2022-06-10 00:59 |  | 2022-06-11 10:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 59213.07 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.133 | A.1011181.133.01 | 7 5/8" Surface | SANTOS LIMITED | Moolion South 1 | SLR RIG 183 | J.22.110550 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-05-11 05:00 | 2022-05-11 01:00 |  | 2022-05-11 05:00 | 2022-05-13 04:59 |  | 2022-05-13 04:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 28094.19 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.133 | A.1011181.133.02 | 4 1/2" Intermediate | SANTOS LIMITED | Moolion South 1 | SLR RIG 183 | J.22.110549 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-05-22 11:00 | 2022-05-22 01:00 |  | 2022-05-23 01:00 | 2022-05-24 00:59 |  | 2022-05-25 10:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 59213.07 | 1 |  |  |  | 87.5 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.132 | A.1011181.132.02 | 4 1/2" Intermediate | SANTOS LIMITED | Kudrieke 4 | SLR RIG 183 | J.22.110914 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-05-06 | 2022-05-05 |  | 2022-05-06 | 2022-05-06 23:59 |  | 2022-05-06 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:15 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 9720.48 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.132 | A.1011181.132.01 | 7 5/8" Surface | SANTOS LIMITED | Kudrieke 4 | SLR RIG 183 | J.22.110536 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-23 | 2022-04-24 22:00 |  | 2022-04-23 | 2022-04-24 23:59 |  | 2022-04-24 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 9575.17 | 1 |  |  |  | 81.3 | 66.7 | 0 | 25 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.131 | A.1011181.131.01 | 7 5/8" Surface | SANTOS LIMITED | Tirrawarra 98 | SLR RIG 183 | J.22.110546 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-12 20:00 | 2022-04-12 |  | 2022-04-12 10:00 | 2022-04-14 09:59 |  | 2022-04-15 19:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 28094.19 | 1 |  |  |  | 81.3 | 33.3 | 0 | 25 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.131 | A.1011181.131.02 | 4 1/2" Intermediate | SANTOS LIMITED | Tirrawarra 98 | SLR RIG 183 | J.22.110544 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-17 10:00 | 2022-04-17 |  | 2022-04-18 | 2022-04-18 23:59 |  | 2022-04-20 09:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 59213.07 | 1 |  |  |  | 81.3 | 66.7 | 0 | 25 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.130 | A.1011181.130.01 | 7 5/8" Surface | SANTOS LIMITED | Tirrawarra 97 | SLR RIG 183 | J.22.110548 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-01 11:00 | 2022-04-01 |  | 2022-04-01 01:00 | 2022-04-03 00:59 |  | 2022-04-04 09:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 22414.19 | 1 |  |  |  | 81.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.130 | A.1011181.130.02 | 4 1/2" Intermediate | SANTOS LIMITED | Tirrawarra 97 | SLR RIG 183 | J.22.110545 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-08 10:00 | 2022-04-08 |  | 2022-04-09 | 2022-04-09 23:59 |  | 2022-04-11 09:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 34747.89 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.13 | A.1011181.13.01 | Patroclus 3 Squeeze | SANTOS LIMITED | PATROCLUS 3 | Wild Desert Rig 22 | J.21.109166 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-29 11:00 | 2021-01-29 |  | 2021-01-29 | 2021-01-30 23:59 |  | 2021-01-31 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 11722.88 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.129 | A.1011181.129.02 | 4 1/2" Intermediate | SANTOS LIMITED | Tirrawarra 96 | SLR RIG 183 | J.22.110542 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-24 11:00 | 2022-03-24 01:00 |  | 2022-03-25 01:00 | 2022-03-26 00:59 |  | 2022-03-27 10:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 31331.93 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.129 | A.1011181.129.01 | 7 5/8" Surface | SANTOS LIMITED | Tirrawarra 96 | SLR RIG 183 | J.22.110540 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-16 01:00 | 2022-03-16 |  | 2022-03-16 01:00 | 2022-03-17 |  | 2022-03-17 01:00 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 20874.92 | 1 |  |  |  | 81.3 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.128 | A.1011181.128.02 | 4 1/2" Intermediate | SANTOS LIMITED | Meranji 27 | SLR RIG 183 | J.22.110913 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-16 | 2022-03-15 01:00 |  | 2022-03-16 01:00 | 2022-03-17 00:59 |  | 2022-03-13 00:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:15 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 39764.83 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.128 | A.1011181.128.01 | 7 5/8" Surface | SANTOS LIMITED | Meranji 27 | SLR RIG 183 | J.22.110539 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-02-26 11:00 | 2022-02-26 |  | 2022-02-26 01:00 | 2022-02-26 23:59 |  | 2022-02-25 09:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 29903.91 | 1 |  |  |  | 81.3 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.127 | A.1011181.127.01 | 7 5/8" Surface | SANTOS LIMITED | Kudrieke 3 | SLR RIG 183 | J.22.110912 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-14 01:00 | 2022-01-14 01:00 |  | 2022-01-14 01:00 | 2022-01-16 00:59 |  | 2022-01-16 00:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:15 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 25610.77 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.127 | A.1011181.127.02 | 4 1/2" Intermediate | SANTOS LIMITED | Kudrieke 3 | SLR RIG 183 | J.22.110543 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-24 11:00 | 2022-01-24 01:00 |  | 2022-01-25 01:00 | 2022-01-26 00:59 |  | 2022-01-27 10:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 27254.8 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.126 | A.1011181.126.02 | 4 1/2" Intermediate | SANTOS LIMITED | WOOLKINA 003 | SLR RIG 183 | J.22.110535 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-03 11:00 | 2022-01-03 01:00 |  | 2022-01-04 01:00 | 2022-01-05 00:59 |  | 2022-01-06 10:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 23404.17 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.126 | A.1011181.126.01 | 7 5/8" Surface | SANTOS LIMITED | WOOLKINA 003 | SLR RIG 183 | J.21.109303 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-27 22:00 | 2021-12-27 |  | 2021-12-27 12:00 | 2021-12-29 11:59 |  | 2021-12-30 21:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 22156.29 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.125 | A.1011181.125.01 | 7 5/8" Surface | SANTOS LIMITED | Moorari 23 | SLR RIG 183 | J.21.109302 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-13 22:00 | 2021-12-13 |  | 2021-12-13 12:00 | 2021-12-15 11:59 |  | 2021-12-16 21:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 25035.79 | 1 |  |  |  | 81.3 | 33.3 | 0 | 62.5 | 55 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.125 | A.1011181.125.02 | 4 1/2" Intermediate | SANTOS LIMITED | Moorari 23 | SLR RIG 183 | J.21.109301 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-23 11:00 | 2021-12-23 01:00 |  | 2021-12-24 01:00 | 2021-12-25 00:59 |  | 2021-12-26 10:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 24773.93 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.124 | A.1011181.124.02 | 4.5" Intermediate | SANTOS LIMITED | Swan Lake 19 | ENSIGN 974 | J.22.110911 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-09-06 23:30 | 2022-09-06 22:00 |  | 2022-09-06 23:00 | 2022-09-07 22:59 |  | 2022-09-07 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:15 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 38459.78 | 1 |  |  |  | 87.5 | 66.7 | 0 | 50 | 65 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.124 | A.1011181.124.01 | 9 5/8" Surface | SANTOS LIMITED | Swan Lake 19 | ENSIGN 974 | J.22.110541 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-23 23:00 | 2022-08-23 22:00 |  | 2022-08-23 22:00 | 2022-08-24 21:59 |  | 2022-08-24 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 27789.6 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.123 | A.1011181.123.02 | 4.5" Intermediate | SANTOS LIMITED | BROLGA 9 | ENSIGN 974 | J.22.110910 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-26 | 2022-11-26 |  | 2022-11-26 | 2022-11-26 23:59 |  | 2022-11-26 23:59 | AUS East Coast WS | GVang2 | 2022-11-28 23:18 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 51855.22 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.123 | A.1011181.123.01 | 7 5/8" Surface | SANTOS LIMITED | BROLGA 9 | ENSIGN 974 | J.22.110529 | WCF | PRI-SURF | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-16 22:00 | 2022-11-16 22:00 |  | 2022-11-16 22:00 | 2022-11-17 21:59 |  | 2022-11-17 21:59 | AUS East Coast WS | GVang2 | 2022-11-28 17:20 | ATimbs |  | No |  |  |  |  | Grace Vang |  | 31685.48 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.122 | A.1011181.122.02 | 4.5" Production | SANTOS LIMITED | BROLGA 8 | ENSIGN 974 | J.22.110538 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-13 | 2022-11-13 |  | 2022-11-13 | 2022-11-13 23:59 |  | 2022-11-13 23:59 | AUS East Coast WS | GVang2 | 2022-11-28 11:39 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 61948.22 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.122 | A.1011181.122.01 | 9 5/8" Surface | SANTOS LIMITED | BROLGA 8 | ENSIGN 974 | J.22.110530 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-04 | 2022-11-03 22:00 |  | 2022-11-03 22:00 | 2022-11-04 21:59 |  | 2022-11-04 23:59 | AUS East Coast WS | GVang2 | 2022-11-21 17:24 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 7880.85 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.121 | A.1011181.121.02 | 4.5" Production | SANTOS LIMITED | BROLGA 10 | ENSIGN 974 | J.22.110537 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-27 | 2022-10-27 |  | 2022-10-27 | 2022-10-27 23:59 |  | 2022-10-27 23:59 | AUS East Coast WS | GVang2 | 2022-10-31 10:47 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 47846.64 | 1 |  |  |  | 81.3 | 66.7 | 0 | 50 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.121 | A.1011181.121.01 | 9 5/8" Surface | SANTOS LIMITED | BROLGA 10 | ENSIGN 974 | J.22.110532 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-19 23:00 | 2022-10-19 23:00 |  | 2022-10-19 23:00 | 2022-10-20 22:59 |  | 2022-10-20 22:59 | AUS East Coast WS | GVang2 | 2022-10-24 14:31 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 29875.64 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.120 | A.1011181.120.02 | 7" Intermediate | SANTOS LIMITED | Pennie 2 | ENSIGN 974 | J.22.110526 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-24 | 2022-10-08 |  | 2022-10-11 | 2022-10-11 23:59 |  | 2022-10-25 10:17 | AUS East Coast WS | GVang2 | 2022-10-28 12:04 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 49296.77 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.120 | A.1011181.120.01 | 9 5/8" Surface | SANTOS LIMITED | Pennie 2 | ENSIGN 974 | J.22.110909 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-01 23:00 | 2022-10-01 23:00 |  | 2022-10-01 23:00 | 2022-10-02 23:59 |  | 2022-10-02 23:59 | AUS East Coast WS | GVang2 | 2022-10-24 16:07 | GVang2 |  | No |  |  |  |  | Grace Vang |  | 26917.49 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.12 | A.1011181.12.01 | Muteroo 4 Plug A | SANTOS LIMITED | MUTEROO 4 | Wild Desert Rig 16 | J.21.109458 | WCF | REM-PA | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-10 11:00 | 2021-01-10 |  | 2021-01-10 | 2021-01-12 23:59 |  | 2021-01-13 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:06 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 23880.66 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.12 | A.1011181.12.02 | Muteroo 4 Plug B | SANTOS LIMITED | Muteroo 4 | Wild Desert Rig 16 | J.21.109141 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-15 11:00 | 2021-01-15 |  | 2021-01-15 | 2021-01-15 23:59 |  | 2021-01-16 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 25512.48 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.12 | A.1011181.12.03 | Muteroo 4 Plug C | SANTOS LIMITED | Muteroo 4 | Wild Desert Rig 16 | J.21.109108 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-18 11:00 | 2021-01-18 |  | 2021-01-18 | 2021-01-18 23:59 |  | 2021-01-19 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:20 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 16361.18 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.119 | A.1011181.119.01 | 7 5/8" Surface | SANTOS LIMITED | Moomba 271 | ENSIGN 971 | J.22.110908 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-26 23:00 | 2022-04-26 23:00 |  | 2022-04-26 23:00 | 2022-04-27 22:59 |  | 2022-04-27 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:14 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 9575.17 | 1 |  |  |  | 81.3 | 66.7 | 0 | 50 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.119 | A.1011181.119.02 | 4 1/2" Production (hot) | SANTOS LIMITED | Moomba 271 | ENSIGN 971 | J.22.110533 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-05-02 23:00 | 2022-05-02 23:00 |  | 2022-05-02 23:00 | 2022-05-03 22:59 |  | 2022-05-03 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 9796.19 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.118 | A.1011181.118.01 | 7 5/8" Surface | SANTOS LIMITED | Moomba 272 | ENSIGN 971 | J.22.110528 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-03 10:00 | 2022-04-03 23:00 |  | 2022-04-03 23:00 | 2022-04-04 22:59 |  | 2022-04-06 09:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 31936.95 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.118 | A.1011181.118.02 | 4 1/2" Production (hot) | SANTOS LIMITED | Moomba 272 | ENSIGN 971 | J.22.110522 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-18 23:00 | 2022-04-18 23:00 |  | 2022-04-18 23:00 | 2022-04-19 22:59 |  | 2022-04-19 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:27 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 9618.5 | 1 |  |  |  | 81.3 | 66.7 | 0 | 50 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ariel Lyons | WS Well Integrity
P.1011181 | O.1011181.117 | A.1011181.117.01 | 7 5/8" Surface | SANTOS LIMITED | Moomba 227(Dev AD) | ENSIGN 971 | J.22.110525 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-22 11:00 | 2022-03-23 |  | 2022-03-23 | 2022-03-23 23:59 |  | 2022-03-25 10:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:27 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 13425.2 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.117 | A.1011181.117.02 | 4 1/2" Production (hot) | SANTOS LIMITED | Moomba 227(Dev AD) | ENSIGN 971 | J.22.110521 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-31 11:00 | 2022-04-01 |  | 2022-04-01 | 2022-04-01 23:59 |  | 2022-04-03 09:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:27 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 38842.41 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.116 | A.1011181.116.01 | 7 5/8" Surface | SANTOS LIMITED | Moomba 226 (Dev B) | ENSIGN 971 | J.22.110531 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-02-25 11:00 | 2022-02-26 |  | 2022-02-26 | 2022-02-26 23:59 |  | 2022-02-28 10:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 29808.31 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.116 | A.1011181.116.02 | 4 1/2" Production (hot) | SANTOS LIMITED | Moomba 226 (Dev B) | ENSIGN 971 | J.22.110524 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-08 11:00 | 2022-03-09 |  | 2022-03-09 | 2022-03-09 23:59 |  | 2022-03-11 10:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:27 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 31752.29 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.115 | A.1011181.115.02 | 4 1/2" Production (hot) | SANTOS LIMITED | Moomba 274 | ENSIGN 971 | J.22.110534 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-05-25 23:00 | 2022-05-25 23:00 |  | 2022-05-25 23:00 | 2022-05-26 22:59 |  | 2022-05-26 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 69879.55 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.115 | A.1011181.115.01 | 7 5/8" Surface | SANTOS LIMITED | Moomba 274 | ENSIGN 971 | J.22.110527 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-05-07 | 2022-05-07 |  | 2022-05-07 | 2022-05-07 23:59 |  | 2022-05-07 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:27 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 9650.91 | 1 |  |  |  | 87.5 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.114 | A.1011181.114.02 | 4.5" Production Job | SANTOS LIMITED | Barrolka 25 | Ensign 967 | J.22.110506 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-05-22 07:00 | 2022-05-22 05:00 |  | 2022-05-22 07:00 | 2022-05-22 15:59 |  | 2022-05-22 15:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:27 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 49308.1 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.114 | A.1011181.114.01 | 7 5/8 Surface | SANTOS LIMITED | Barrolka 25 | Ensign 967 | J.22.110500 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-05-11 23:00 | 2022-05-11 23:00 |  | 2022-05-11 23:00 | 2022-05-12 22:59 |  | 2022-05-12 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 31983.59 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.113 | A.1011181.113.01 | 7 5/8 Surface | SANTOS LIMITED | Bolah 10 | Ensign 967 | J.22.110501 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-27 23:00 | 2022-04-27 23:00 |  | 2022-04-27 23:00 | 2022-04-28 22:59 |  | 2022-04-28 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 9575.17 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.113 | A.1011181.113.02 | 4.5" Production Job | SANTOS LIMITED | Bolah 10 | Ensign 967 | J.22.110498 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-05-05 07:00 | 2022-05-05 05:00 |  | 2022-05-05 07:00 | 2022-05-05 15:59 |  | 2022-05-05 15:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 9677.65 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.112 | A.1011181.112.02 | 4.5" Production Job | SANTOS LIMITED | Barrolka 26 | Ensign 967 | J.22.110907 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-06-10 | 2022-06-10 05:00 |  | 2022-06-10 07:00 | 2022-06-10 15:59 |  | 2022-06-11 10:00 | AUS East Coast WS | GVang2 | 2022-10-03 15:14 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 49308.1 | 1 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.112 | A.1011181.112.01 | 7 5/8 Surface | SANTOS LIMITED | Barrolka 26 | Ensign 967 | J.22.110491 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-05-27 23:00 | 2022-05-27 23:00 |  | 2022-05-27 23:00 | 2022-05-28 22:59 |  | 2022-05-28 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 31983.59 | 1 |  |  |  | 87.5 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.111 | A.1011181.111.02 | 4.5" Production Job | SANTOS LIMITED | Bolah 9 | Ensign 967 | J.22.110906 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-20 23:00 | 2022-04-21 05:00 |  | 2022-04-21 07:00 | 2022-04-21 15:59 |  | 2022-04-21 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:14 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 98616.2 | 1 |  |  |  | 81.3 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.111 | A.1011181.111.01 | 7 5/8 Surface | SANTOS LIMITED | Bolah 9 | Ensign 967 | J.22.110494 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-05 23:00 | 2022-04-06 |  | 2022-04-06 | 2022-04-06 23:59 |  | 2022-04-06 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 16362.79 | 1 |  |  |  | 81.3 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.110 | A.1011181.110.02 | 4.5" Production Job | SANTOS LIMITED | Bolah 8 | Ensign 967 | J.22.110502 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-31 23:00 | 2022-04-01 06:00 |  | 2022-04-01 08:00 | 2022-04-01 16:59 |  | 2022-04-01 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:27 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 32426.04 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.110 | A.1011181.110.01 | 7 5/8 Surface | SANTOS LIMITED | Bolah 8 | Ensign 967 | J.22.110495 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-25 | 2022-03-25 |  | 2022-03-25 | 2022-03-25 23:59 |  | 2022-03-25 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 20633.52 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.11 | A.1011181.11.01 | 7 5/8" Surface cement job | SANTOS LIMITED | BOLAH 7 | Ensign 967 | J.21.109457 | WCF | PRI-SURF | Low | Confirmed | Design - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-23 11:00 | 2021-01-23 |  | 2021-01-24 08:00 | 2021-01-26 16:00 |  | 2021-01-27 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:06 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 31691.44 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.11 | A.1011181.11.02 | 3 1/2" production job | SANTOS LIMITED | Bolah 7 | Ensign 967 | J.21.109110 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-02 11:00 | 2021-02-03 06:00 |  | 2021-02-05 08:00 | 2021-02-05 16:59 |  | 2021-02-07 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:20 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 67646.13 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.109 | A.1011181.109.01 | 7 5/8 Surface | SANTOS LIMITED | Pelican 14 | Ensign 967 | J.22.110499 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-02-14 | 2022-02-14 |  | 2022-02-16 | 2022-02-16 23:59 |  | 2022-02-17 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 23128.95 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.109 | A.1011181.109.02 | 4.5" Production Job | SANTOS LIMITED | Pelican 14 | Ensign 967 | J.22.110489 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-04 23:00 | 2022-03-05 06:00 |  | 2022-03-05 08:00 | 2022-03-05 16:59 |  | 2022-03-05 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 33489.9 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.108 | A.1011181.108.01 | 7 5/8 Surface | SANTOS LIMITED | Meranji 24 | Ensign 967 | J.22.110905 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-06 11:00 | 2022-03-07 |  | 2022-03-07 | 2022-03-07 23:59 |  | 2022-03-09 10:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:14 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 0 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.108 | A.1011181.108.02 | 4.5" Production Job | SANTOS LIMITED | Meranji 24 | Ensign 967 | J.22.110493 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-11 23:00 | 2022-03-12 06:00 |  | 2022-03-12 08:00 | 2022-03-12 16:59 |  | 2022-03-12 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 20850.59 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.107 | A.1011181.107.01 | 7 5/8 Surface | SANTOS LIMITED | Kappa 2 | Ensign 967 | J.22.110497 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-07 11:00 | 2022-01-08 |  | 2022-01-08 | 2022-01-08 23:59 |  | 2022-01-10 10:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 19831.24 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.107 | A.1011181.107.02 | 4.5" Production Job | SANTOS LIMITED | Kappa 2 | Ensign 967 | J.22.110490 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-20 23:00 | 2022-01-21 06:00 |  | 2022-01-24 08:00 | 2022-01-24 16:59 |  | 2022-01-24 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 21226.76 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.106 | A.1011181.106.02 | 5.5" Production Job | SANTOS LIMITED | Chef 1 | Ensign 967 | J.21.109300 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-28 23:00 | 2021-12-29 06:00 |  | 2021-12-29 08:00 | 2021-12-29 16:59 |  | 2021-12-29 22:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 34460.75 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.106 | A.1011181.106.01 | 7 5/8 Surface | SANTOS LIMITED | Chef 1 | Ensign 967 | J.21.109296 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-22 11:00 | 2021-12-23 |  | 2021-12-23 | 2021-12-23 23:59 |  | 2021-12-25 10:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 22769.97 | 1 |  |  |  | 81.3 | 33.3 | 0 | 62.5 | 55 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.105 | A.1011181.105.06 | Plug 7F-2 | SANTOS LIMITED | Rakoona 1 | Wild Desert Rig 6 | J.21.109524 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-23 12:00 | 2021-11-23 |  | 2021-11-23 12:00 | 2021-11-24 12:00 |  | 2021-11-24 12:00 | AUS East Coast WS | GVang2 | 2022-10-03 15:15 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 16115.56 | 1 |  |  |  | 81.3 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.105 | A.1011181.105.01 | Rakoona 1 | SANTOS LIMITED | Rakoona 1 | Wild Desert Rig 6 | J.21.109522 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-28 08:00 | 2021-10-28 08:00 |  | 2021-10-28 09:00 | 2021-10-29 08:59 |  | 2021-10-29 08:59 | AUS East Coast WS | GVang2 | 2022-10-03 15:14 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 32521.82 | 3 |  |  |  | 81.3 | 33.3 | 0 | 62.5 | 55 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.105 | A.1011181.105.07 | Plug 8 | SANTOS LIMITED | Rakoona 1 | Wild Desert Rig 6 | J.21.109311 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-25 12:00 | 2021-11-25 |  | 2021-11-25 12:00 | 2021-11-26 12:00 |  | 2021-11-26 12:00 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 13283.3 | 1 |  |  |  | 81.3 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.105 | A.1011181.105.05 | Plug 7 | SANTOS LIMITED | Rakoona 1 | Wild Desert Rig 6 | J.21.109309 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-19 12:00 | 2021-11-19 |  | 2021-11-19 12:00 | 2021-11-20 12:59 |  | 2021-11-20 12:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 15684.09 | 1 |  |  |  | 78.1 | 25 | 0 | 50 | 48.8 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.105 | A.1011181.105.03 | Plug 5D | SANTOS LIMITED | Rakoona 1 | Wild Desert Rig 6 | J.21.109308 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-05 23:00 | 2021-11-05 |  | 2021-11-05 23:00 | 2021-11-06 18:59 |  | 2021-11-06 18:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 24895.72 | 1 |  |  |  | 81.3 | 33.3 | 0 | 62.5 | 55 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.105 | A.1011181.105.04 | Plug 6 | SANTOS LIMITED | Rakoona 1 | Wild Desert Rig 6 | J.21.109305 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-13 13:00 | 2021-11-13 |  | 2021-11-13 13:00 | 2021-11-14 13:00 |  | 2021-11-14 13:00 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 14922.38 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.105 | A.1011181.105.02 | Rakoona Plug 4D1 | SANTOS LIMITED | Rakoona 1 | Wild Desert Rig 6 | J.21.109292 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-30 09:00 | 2021-10-30 02:00 |  | 2021-10-30 09:00 | 2021-10-31 00:59 |  | 2021-10-31 00:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 27137.88 | 1 |  |  |  | 81.3 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.104 | A.1011181.104.01 | Moomba 140 Plug 1A-1 | SANTOS LIMITED | Moomba 140 | Wild Desert Rig 16 | J.21.109521 | WCF | REM-PA | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-24 21:00 | 2021-10-24 08:00 |  | 2021-10-24 22:00 | 2021-10-25 08:00 |  | 2021-10-25 21:09 | AUS East Coast WS | GVang2 | 2022-10-03 15:14 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 11702.37 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.104 | A.1011181.104.02 | Plug 1A-2 and 1A-3 | SANTOS LIMITED | Moomba 140 | Wild Desert Rig 16 | J.21.109299 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-27 12:15 | 2021-10-27 01:00 |  | 2021-10-27 12:15 | 2021-10-28 01:00 |  | 2021-10-28 01:00 | AUS East Coast WS | GVang2 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 13565.2 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.104 | A.1011181.104.03 | Moomba 140 Plug 1B | SANTOS LIMITED | Moomba 140 | Wild Desert Rig 16 | J.21.109297 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-28 16:00 | 2021-10-28 10:00 |  | 2021-10-28 16:00 | 2021-10-29 03:59 |  | 2021-10-29 03:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 18624.2 | 1 |  |  |  | 81.3 | 33.3 | 0 | 62.5 | 55 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.104 | A.1011181.104.04 | Moomba 140 Plug 1C | SANTOS LIMITED | MOOMBA 140 | Wild Desert Rig 16 | J.21.109287 | WCF | REM-PA | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-11-02 20:00 | 2021-11-02 |  | 2021-11-02 20:00 | 2021-11-03 10:59 |  | 2021-11-03 10:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 17264.75 | 1 |  |  |  | 81.3 | 33.3 | 0 | 25 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.103 | A.1011181.103.01 | Meranji 2 | SANTOS LIMITED | Meranji 2 | Wild Desert Rig 16 | J.21.109298 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-07 | 2021-10-07 23:00 |  | 2021-10-08 09:00 | 2021-10-09 08:59 |  | 2021-10-08 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 11702.37 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.101 | A.1011181.101.01 | Dummy | SANTOS LIMITED | Well #1 | Ensign 967 | J.21.109289 | WCF | PRI-SURF | Low | Unconfirmed - 10% | Design - CEC |  | Not Started | In Progress | In Progress |  | 2021-11-23 22:00 |  | 2021-11-23 22:00 | 2021-11-24 21:59 |  |  | AUS East Coast WS | GVang2 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Gaurav Kumar Singh |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.100 | A.1011181.100.01 | Dummy | SANTOS LIMITED | Well #1 | Ensign 967 | J.21.109294 | WCF | PRI-SURF | Low | Unconfirmed - 10% | Design - CEC |  | Not Started | In Progress | In Progress |  | 2021-12-17 22:00 |  | 2021-12-17 22:00 | 2021-12-18 21:59 |  |  | AUS East Coast WS | GVang2 | 2022-10-03 14:26 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 0 | 2 |  |  |  | 25 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Grace Vang | WS Well Integrity
P.1011181 | O.1011181.10 | A.1011181.10.01 | Dullingari North 25 Surface | SANTOS LIMITED | Dullingari North 25 | ENSIGN 974 | J.21.109473 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-19 11:00 | 2021-01-19 |  | 2021-01-20 | 2021-01-20 23:59 |  | 2021-01-22 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:08 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 25545.87 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gaurav Kumar Singh | WS Well Integrity
P.1011181 | O.1011181.10 | A.1011181.10.02 | Dullingari North 25 Intermediate | SANTOS LIMITED | Dullingari North 25 | ENSIGN 974 | J.21.109158 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-25 11:00 | 2021-01-25 |  | 2021-01-26 | 2021-01-26 23:59 |  | 2021-01-28 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 44353.91 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.09 | A.1011181.09.01 | 7 5/8" Surface cement job | SANTOS LIMITED | RUBY 3 | Ensign 967 | J.21.109447 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-10 11:00 | 2021-01-11 |  | 2021-01-11 08:00 | 2021-01-11 16:00 |  | 2021-01-13 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:05 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 23725.18 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.09 | A.1011181.09.02 | 3 1/2" production job | SANTOS LIMITED | RUBY 3 | Ensign 967 | J.21.109132 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-16 11:00 | 2021-01-17 06:00 |  | 2021-01-17 08:00 | 2021-01-17 16:59 |  | 2021-01-19 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 40191.98 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.08 | A.1011181.08.01 | Dullingari N24 P&A | SANTOS LIMITED | Dullingari North 24 | ENSIGN 974 | J.20.063617 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-20 11:00 | 2020-12-21 |  | 2020-12-21 | 2020-12-21 23:59 |  | 2020-12-23 10:59 | AUS East Coast WS | ALyons | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 60112.46 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.07 | A.1011181.07.01 | Surface Cement Job | SANTOS LIMITED | MOOMBA 264 | ENSIGN 971 | J.21.109463 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-02 11:00 | 2021-01-03 |  | 2021-01-03 | 2021-01-03 23:59 |  | 2021-01-05 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 15:07 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 25024.04 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.07 | A.1011181.07.02 | Production Cement Job | SANTOS LIMITED | MOOMBA 264 | ENSIGN 971 | J.21.109128 | WCF | PRI-LONG | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-13 11:00 | 2021-01-14 |  | 2021-01-14 | 2021-01-14 23:59 |  | 2021-01-16 10:59 | AUS East Coast WS | FDPSystemUser | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 73814.59 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.06 | A.1011181.06.03 | Sturt East 4 Plug 3C | SANTOS LIMITED | Sturt East 4 | Wild Desert Rig 16 | J.20.063624 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-15 11:00 | 2020-12-16 |  | 2020-12-16 | 2020-12-16 23:59 |  | 2020-12-17 10:59 | AUS East Coast WS | ALyons | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 11484.24 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.06 | A.1011181.06.04 | Sturt East 4 Plug D | SANTOS LIMITED | Sturt East 4 | Wild Desert Rig 16 | J.20.063616 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-16 11:00 | 2020-12-17 |  | 2020-12-17 | 2020-12-17 23:59 |  | 2020-12-18 10:59 | AUS East Coast WS | ALyons | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 13424.44 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.06 | A.1011181.06.01 | SturtEast4 Plug 1A | SANTOS LIMITED | Sturt East 4 | Wild Desert Rig 16 | J.20.063615 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-09 11:00 | 2020-12-10 |  | 2020-12-10 | 2020-12-11 23:59 |  | 2020-12-12 10:59 | AUS East Coast WS | GSingh54 | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 21073.93 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.06 | A.1011181.06.05 | Sturt East 4 Plug 3E | SANTOS LIMITED | STURT EAST 4 | Wild Desert Rig 16 | J.20.063613 | WCF | REM-PA | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2020-12-19 11:00 | 2020-12-20 |  | 2020-12-20 | 2020-12-20 23:59 |  | 2020-12-21 10:59 | AUS East Coast WS | ALyons | 2022-10-03 14:20 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 14150.77 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.06 | A.1011181.06.02 | Sturt East 4 Plug 1B | SANTOS LIMITED | Sturt East 4 | Wild Desert Rig 16 | J.20.063612 | WCF | REM-PA | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-12 11:00 | 2020-12-13 |  | 2020-12-13 | 2020-12-13 23:59 |  | 2020-12-14 10:59 | AUS East Coast WS | ALyons | 2022-10-03 14:20 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 13275.26 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.05 | A.1011181.05.01 | Moon North West 1 7 5/8 Surface | SANTOS LIMITED | MOON NORTH WEST 1 | Ensign 967 | J.20.063619 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-23 11:00 | 2020-12-24 |  | 2020-12-24 | 2020-12-24 23:59 |  | 2020-12-26 10:59 | AUS East Coast WS | GSingh54 | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 22449.84 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.05 | A.1011181.05.02 | Moon North West 1 4.5" Production Job | SANTOS LIMITED | MOON NORTH WEST 1 | Ensign 967 | J.21.109126 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-02 11:00 | 2021-01-03 06:00 |  | 2021-01-03 08:00 | 2021-01-03 16:59 |  | 2021-01-05 10:59 | AUS East Coast WS | GSingh54 | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 52655.65 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.04 | A.1011181.04.02 | Dullingari North 23 Intermediate | SANTOS LIMITED | DULLINGARI NORTH 23 | ENSIGN 974 | J.21.109452 | WCF | PRI-INTER | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-04 11:00 | 2021-01-04 |  | 2021-01-04 | 2021-01-06 23:59 |  | 2021-01-07 10:59 | AUS East Coast WS | ALyons | 2022-10-03 15:06 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 45368.76 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.04 | A.1011181.04.01 | Dullingari North 23 Surface | SANTOS LIMITED | DULLINGARI NORTH 23 | ENSIGN 974 | J.20.063618 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-30 11:00 | 2020-12-30 |  | 2020-12-30 | 2021-01-01 23:59 |  | 2021-01-02 10:59 | AUS East Coast WS | ALyons | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 25583.81 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.03 | A.1011181.03.02 | Beanbush 3 Intermediate | SANTOS LIMITED | Beanbush 3 | ENSIGN 971 | J.21.109462 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-13 12:00 | 2021-12-14 01:00 |  | 2021-12-14 01:00 | 2021-12-15 00:59 |  | 2021-12-16 11:59 | AUS East Coast WS | ALyons | 2022-10-03 15:07 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 21518.75 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.03 | A.1011181.03.05 | Kick Off Plug | SANTOS LIMITED | BEANBUSH 003 | ENSIGN 971 | J.21.109317 | WCF | REM-PA | Low | Confirmed | Prepare - Mob |  | Design Completed | Design Completed | In Progress | 2021-12-23 | 2021-12-23 |  | 2021-12-23 | 2021-12-24 23:59 |  | 2021-12-24 23:59 | AUS East Coast WS | GSingh54 | 2022-10-03 14:29 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 22521.67 | 0 |  |  |  | 81.3 | 33.3 | 0 | 0 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.03 | A.1011181.03.04 | KOP | SANTOS LIMITED | Beanbush 3 | ENSIGN 971 | J.21.109313 | WCF | REM-KOP | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-21 12:00 | 2021-12-21 |  | 2021-12-21 12:00 | 2021-12-22 12:00 |  | 2021-12-22 12:00 | AUS East Coast WS | GVang2 | 2022-10-03 14:28 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 47257.76 | 0 |  |  |  | 62.5 | 0 | 0 | 0 | 25 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.03 | A.1011181.03.03 | Beanbush 3 Production | SANTOS LIMITED | Beanbush 3 | ENSIGN 971 | J.22.110481 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-22 12:00 | 2022-01-22 |  | 2022-01-22 12:00 | 2022-01-23 23:59 |  | 2022-01-23 23:59 | AUS East Coast WS | GVang2 | 2022-10-03 14:25 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 78774.11 | 1 |  |  |  | 81.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.03 | A.1011181.03.01 | 13-3/8" Surface Cement job | SANTOS LIMITED | Beanbush 3 | ENSIGN 971 | J.21.109143 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-28 11:00 | 2021-11-29 |  | 2021-11-29 08:00 | 2021-11-29 23:59 |  | 2021-12-01 10:59 | AUS East Coast WS | ALyons | 2022-10-03 14:21 | FDPSystemUser |  | No |  |  |  |  | Grace Vang |  | 56554.91 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.02 | A.1011181.02.01 | 7 5/8" Surface cement job | SANTOS LIMITED | Brumby 14 | Ensign 967 | J.20.063620 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-08 11:00 | 2020-12-09 |  | 2020-12-09 08:00 | 2020-12-09 16:00 |  | 2020-12-11 10:59 | AUS East Coast WS | ALyons | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 25514.98 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.02 | A.1011181.02.02 | 3 1/2" production job | SANTOS LIMITED | BRUMBY 014 | Ensign 967 | J.20.063614 | WCF | PRI-LONG | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-15 11:00 | 2020-12-16 06:00 |  | 2020-12-16 08:00 | 2020-12-16 16:59 |  | 2020-12-18 10:59 | AUS East Coast WS | ALyons | 2022-10-03 14:20 | FDPSystemUser |  | No |  |  |  |  | Ariel Lyons |  | 58632.23 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.01 | A.1011181.01.01 | Surface Cement Job | SANTOS LIMITED | Kowloon 1 | ENSIGN 971 | J.20.063622 | WCF | PRI-SURF | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-11 11:00 | 2020-12-12 |  | 2020-12-12 | 2020-12-12 23:59 |  | 2020-12-14 10:59 | AUS East Coast WS | JAhmed8 | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Junaid Ahmed |  | 40535.93 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011181 | O.1011181.01 | A.1011181.01.02 | Production Cement Job | SANTOS LIMITED | Kowloon 1 | ENSIGN 971 | J.20.063621 | WCF | PRI-LONG | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-23 11:00 | 2020-12-24 |  | 2020-12-24 | 2020-12-24 23:59 |  | 2020-12-26 10:59 | AUS East Coast WS | JAhmed8 | 2022-10-03 14:22 | FDPSystemUser |  | No |  |  |  |  | Junaid Ahmed |  | 60913.71 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1011174 | O.1011174.01 | A.1011174.01.01 | Tuna Ops December | ESSO AUSTRALIA LTD | TUNA A 16L |  | J.20.063038 | RPI | PS-SLK-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-11-27 |  | 2020-12-02 | 2020-12-14 23:59 |  |  | New Burn WL | frosa2 | 2022-10-03 09:50 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 |  |  |  |  | 41.7 | 50 | 0 | 37.5 | 38.8 |  | 0 | [7 empty] | Luis Cardenas | Wireline Slickline
P.1010728 | O.1010728.02 | A.1010728.02.01 | PNX | CARBON TRANSPORT AND STORAGE CORPORATION (CTSCO) PTY LIMITED |  |  | J.22.110256 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-08-12 |  | 2022-08-12 | 2022-08-16 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1010728 | O.1010728.01 | A.1010728.01.01 | CBL-Perforation | CARBON TRANSPORT AND STORAGE CORPORATION (CTSCO) PTY LIMITED | West Moonie 1 |  | J.20.063511 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-11-15 06:00 |  | 2020-11-15 10:00 | 2020-11-22 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 8747.56 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1010724 | O.1010724.09 | A.1010724.09.02 | 7in Casing Cement Job | OMV NEW ZEALAND LTD | MA-08B | Archer Emerald | J.22.110866 | WCF | PRI-INTER | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2023-03-07 | 2023-03-04 |  | 2023-03-07 | 2023-03-07 23:59 |  | 2023-03-07 23:59 | New Plymouth WS | MAlsaman | 2023-05-27 17:31 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 162937.53 | 1 |  |  |  | 81.3 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1010724 | O.1010724.09 | A.1010724.09.01 | Plug & Abandonment | OMV NEW ZEALAND LTD | MA-08B | Archer Emerald | J.22.110903 | WCF | REM-PA | High | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2023-01-19 19:00 | 2023-01-15 |  | 2023-01-19 19:00 | 2023-01-20 18:59 |  | 2023-01-20 18:59 | New Plymouth WS | MAlsaman | 2023-05-27 17:31 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 2600.47 | 1 |  |  |  | 81.3 | 16.7 | 0 | 50 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1010724 | O.1010724.09 | A.1010724.09.03 | 4.5in Liner Cement Job | OMV NEW ZEALAND LTD | MA-08B | Archer Emerald | J.23.008731 | WCF | PRI-LIN | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-26 | 2023-03-22 |  | 2023-03-26 | 2023-03-26 23:59 |  | 2023-03-26 23:59 | New Plymouth WS | MAlsaman | 2023-03-27 13:54 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 115830.45 | 1 |  |  |  | 81.3 | 33.3 | 100 | 50 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1010724 | O.1010724.09 | A.1010724.09.04 | Cement Plug Inside 7-5/8in Casing | OMV NEW ZEALAND LTD | MA-08B | Archer Emerald | J.23.031119 | WCF | REM-PA | High | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2023-01-27 18:00 | 2023-01-26 |  | 2023-01-27 18:00 | 2023-01-28 23:59 |  | 2023-01-28 23:59 | New Plymouth WS | MAlsaman | 2023-01-25 17:26 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1010724 | O.1010724.08 | A.1010724.08.02 | 7in Liner Job | OMV NEW ZEALAND LTD | MA-09C | Archer Emerald | J.22.110868 | WCF | PRI-INTER | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-22 17:00 | 2022-10-23 |  | 2022-12-04 17:00 | 2022-12-05 16:59 |  | 2022-11-23 16:59 | New Plymouth WS | MAlsaman | 2023-05-27 17:31 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 119283.04 | 1 |  |  |  | 81.3 | 16.7 | 0 | 50 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1010724 | O.1010724.08 | A.1010724.08.03 | 4.5in Liner Cement Job | OMV NEW ZEALAND LTD | MA-09C | Archer Emerald | J.22.110858 | WCF | PRI-LIN | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-18 | 2022-10-27 |  | 2022-12-18 | 2022-12-18 23:59 |  | 2022-12-18 23:59 | New Plymouth WS | MAlsaman | 2023-05-27 17:31 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 96941.59 | 1 |  |  |  | 81.3 | 16.7 | 0 | 50 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1010724 | O.1010724.08 | A.1010724.08.01 | Plug & Abandonment | OMV NEW ZEALAND LTD | MA-09C | Archer Emerald | J.22.110869 | WCF | REM-PA | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-22 | 2022-10-01 |  | 2022-11-03 | 2022-11-03 23:59 |  | 2022-10-22 23:59 | New Plymouth WS | MAlsaman | 2022-11-30 00:32 | MAlsaman |  | No |  |  |  |  | Tareq AlSaman |  | 2977.58 | 1 |  |  |  | 81.3 | 50 | 0 | 50 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1010724 | O.1010724.07 | A.1010724.07.03 | P&A & Squeeze Job | OMV NEW ZEALAND LTD | MA 14 | Archer Emerald | J.21.109412 | WCF | REM-PA | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-10-12 | 2021-09-17 |  | 2021-10-12 | 2021-10-12 23:59 |  | 2021-10-12 23:59 | New Plymouth WS | MAlsaman | 2022-10-03 16:39 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 16334.58 | 1 |  |  |  | 81.3 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1010724 | O.1010724.07 | A.1010724.07.01 | 7inch casing | OMV NEW ZEALAND LTD | MA-14 | Archer Emerald | J.21.109409 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-10 | 2021-11-01 |  | 2021-11-10 | 2021-11-10 23:59 |  | 2021-11-13 11:59 | New Plymouth WS | VWedhaswari | 2022-10-03 16:39 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 146019.94 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1010724 | O.1010724.07 | A.1010724.07.02 | 4.5inch Liner | OMV NEW ZEALAND LTD | MA-14 | Archer Emerald | J.21.109404 | WCF | PRI-LIN | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-14 18:00 | 2021-11-16 |  | 2021-11-23 18:00 | 2021-11-24 17:59 |  | 2021-11-28 05:59 | New Plymouth WS | VWedhaswari | 2022-10-03 16:38 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 97242.39 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1010724 | O.1010724.06 | A.1010724.06.02 | 4-1/2inch Liner | OMV NEW ZEALAND LTD | MA-02A | Archer Emerald | J.21.109446 | WCF | PRI-LIN | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-12 12:00 | 2021-06-20 |  | 2021-09-12 | 2021-09-16 23:59 |  | 2021-09-17 11:59 | New Plymouth WS | VWedhaswari | 2022-10-03 17:05 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 174265.2 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1010724 | O.1010724.06 | A.1010724.06.01 | P&A | OMV NEW ZEALAND LTD | MA-02A | Archer Emerald | J.21.109403 | WCF | REM-PA | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-08 12:00 | 2021-07-23 |  | 2021-08-08 | 2021-08-17 23:59 |  | 2021-08-18 11:59 | New Plymouth WS | VWedhaswari | 2022-10-03 16:38 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 1747.05 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1010724 | O.1010724.05 | A.1010724.05.01 | Squeeze Job | OMV NEW ZEALAND LTD | MA 13 | Archer Emerald | J.21.109408 | WCF | REM-SQ | Medium | Unconfirmed - 50% | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-05-11 12:00 | 2021-05-10 |  | 2021-05-11 | 2021-06-10 23:59 |  | 2021-06-11 11:59 | New Plymouth WS | VWedhaswari | 2022-10-03 16:39 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 26041.83 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1010724 | O.1010724.04 | A.1010724.04.01 | 7inch Casing | OMV NEW ZEALAND LTD | MA-01A | Archer Emerald | J.21.109444 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-20 06:00 | 2021-04-13 |  | 2021-04-19 18:00 | 2021-05-05 17:59 |  | 2021-05-06 05:59 | New Plymouth WS | VWedhaswari | 2022-10-03 17:05 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 104546 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1010724 | O.1010724.04 | A.1010724.04.02 | Personnel + Equipment | OMV NEW ZEALAND LTD | MA-01A | Archer Emerald | J.21.109413 | WCF | CMT-PERS,CMT-EQPRNT | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-03-04 13:00 | 2021-02-28 |  | 2021-03-04 | 2021-03-31 23:59 |  | 2021-04-01 12:59 | New Plymouth WS | VWedhaswari | 2022-10-03 16:39 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1010724 | O.1010724.04 | A.1010724.04.03 | Personnel April | OMV NEW ZEALAND LTD | MA 01A | Archer Emerald | J.21.109405 | WCF | CMT-PERS,CMT-EQPRNT | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2021-05-05 13:00 | 2021-05-01 |  | 2021-05-05 | 2021-06-01 23:59 |  | 2021-06-02 12:59 | New Plymouth WS | VWedhaswari | 2022-10-03 16:38 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 |  |  |  | 62.5 | 50 | 100 | 25 | 55 |  | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1010724 | O.1010724.03 | A.1010724.03.01 | 7in Casing | OMV NEW ZEALAND LTD | MA-11A | Archer Emerald | J.21.109443 | WCF | PRI-INTER | InComplete | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-01 13:00 | 2021-02-17 |  | 2021-05-01 | 2021-05-11 23:59 |  | 2021-05-12 12:59 | New Plymouth WS | VWedhaswari | 2022-10-03 17:04 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1010724 | O.1010724.02 | A.1010724.02.01 | 7in Casing Cementing | OMV NEW ZEALAND LTD | MA-11A | Archer Emerald | J.21.109411 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-01 13:00 | 2021-02-15 |  | 2021-03-01 | 2021-03-09 23:59 |  | 2021-03-10 12:59 | New Plymouth WS | VWedhaswari | 2022-10-03 16:39 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 130323.75 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1010724 | O.1010724.02 | A.1010724.02.03 | Equipment and personnel_FEB | OMV NEW ZEALAND LTD | MA 11A | Archer Emerald | J.21.109410 | WCF | CMT-EQPRNT,CMT-PERS | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2021-02-24 14:00 | 2021-02-19 |  | 2021-02-24 01:00 | 2021-02-27 00:59 |  | 2021-02-27 13:59 | New Plymouth WS | VWedhaswari | 2022-10-03 16:39 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 62700 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1010724 | O.1010724.02 | A.1010724.02.02 | Compressor Recharge MA-11 | OMV NEW ZEALAND LTD | MA 11A | Archer Emerald | J.21.109406 | WCF | CMT-RECHARGE | Low | Confirmed | Design - CEC |  | Not Required | Not Required | In Progress |  | 2021-02-19 |  | 2021-02-23 | 2021-02-25 23:59 |  |  | New Plymouth WS | VWedhaswari | 2022-10-03 16:39 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 23981.01 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victoria Rasmi Wedhaswari | WS Well Integrity
P.1010724 | O.1010724.01 | A.1010724.01.02 | Casing Leak Squeeze | OMV NEW ZEALAND LTD | MA 03A | Archer Emerald | J.21.109445 | WCF | REM-SQ | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-01-08 23:00 | 2021-01-07 06:00 |  | 2021-01-08 10:00 | 2021-01-10 23:59 |  | 2021-01-11 12:59 | New Plymouth WS | VWedhaswari | 2022-10-03 17:05 | FDPSystemUser |  | No |  |  |  |  | Victoria Rasmi Wedhaswari |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1010724 | O.1010724.01 | A.1010724.01.01 | 7" Casing Cementing | OMV NEW ZEALAND LTD | MA-03A | Archer Emerald | J.22.110860 | WCF | PRI-INTER | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-31 | 2021-12-25 |  | 2022-02-06 | 2022-02-06 23:59 |  | 2022-02-18 23:59 | New Plymouth WS | VWedhaswari | 2022-10-03 16:39 | FDPSystemUser |  | No |  |  |  |  | Tareq AlSaman |  | 103035 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Junaid Ahmed | WS Well Integrity
P.1010623 | O.1010623.02 | A.1010623.02.01 | Bottle rental - Pharos-1 | SANTOS NA BROWSE BASIN PTY LTD | Pharos-1 | Noble Tom Prosser | J.21.108329 | RPE | FSA-SF-JOB | Medium | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-03-09 |  | 2021-03-09 | 2021-03-10 23:59 |  |  | APG TS | GRoxo | 2022-10-03 06:25 | FDPSystemUser |  | No |  | [AUNB-FSA] - Perth- New Burn OLP |  |  | David Rowe |  | 0 | [10 empty] | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TS Downhole Reservoir Testing
P.1010623 | O.1010623.01 | A.1010623.01.02 | Ex-COP - RSA rental bottle - MDT Proteus-1 | SANTOS NA BROWSE BASIN PTY LTD |  | Transocean Legend | J.21.108328 | RPE | FSA-SF-JOB | Medium | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-03-08 |  | 2021-03-08 | 2021-03-09 |  |  | APG TS | GRoxo | 2022-10-03 06:25 | FDPSystemUser |  | No |  | [AUJN-FSA] - AU - Jandakot OLP |  |  | David Rowe |  | 0 | [10 empty] | 0 | [7 empty] | Richard Steers | TS Downhole Reservoir Testing
P.1010623 | O.1010623.01 | A.1010623.01.01 | Ex-COP RSA Bottle rental - Proteus-1 | SANTOS NA BROWSE BASIN PTY LTD | PROTEUS 1 | Transocean Legend | J.21.108327 | RPE | FSA-SF-JOB | Medium | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-03-09 |  | 2021-03-09 | 2021-03-10 23:59 |  |  | APG TS | GRoxo | 2022-10-03 06:25 | FDPSystemUser |  | No |  | [AUNB-FSA] - Perth- New Burn OLP |  |  | David Rowe |  | 0 | [10 empty] | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TS Downhole Reservoir Testing
P.1010623 | O.1010623.01 | A.1010623.01.03 | Ex - COP - RSA Bottle rental - Boreas-1 | SANTOS NA BROWSE BASIN PTY LTD |  | Transocean Legend | J.21.108326 | RPE | FSA-SF-JOB | Medium | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-03-08 22:00 |  | 2021-03-08 23:00 | 2021-03-09 23:00 |  |  | APG TS | GRoxo | 2022-10-03 06:25 | FDPSystemUser |  | No |  | [AUNB-FSA] - Perth- New Burn OLP |  |  | David Rowe |  | 0 | [10 empty] | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TS Downhole Reservoir Testing
P.1010350 | O.1010350.11 | A.1010350.11.06 | Dedicated CH_Oct24 | SANTOS LIMITED | THE ROCK 39, RM40-122-1, RM40-122-2, THE ROCK 35, THE ROCK 33, THE ROCK 38, THE ROCK 34, FAIRVIEW 183, FV15-49-1, FV18-89-1 | EASTERNWELL 24 | J.24.159633 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2024-09-30 | 2024-09-18 |  | 2024-09-25 | 2024-12-26 00:59 |  | 2024-12-26 00:59 | Roma WL | JEsmeralda | 2024-12-23 18:46 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 0 |  | L0 - No RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1010350 | O.1010350.11 | A.1010350.11.01 | Dedicated CH_Jun24 | SANTOS LIMITED | Well #25, Well #26, Well #27, Well #28, THE ROCK 39, Well #23, RM40-122-1, RM40-122-2, THE ROCK 38, THE ROCK 34, THE ROCK 33, THE ROCK 35, RM90-108-1, RM90-109-1, Well #39, FV17-86-1, FV16-71-1, FV17-87-1, RM90-139-1, FV16-73-1, FV16-70-1 | EASTERNWELL 24 | J.25.005368 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2024-03-01 | 2024-05-25 |  | 2024-06-01 | 2024-06-30 23:59 |  | 2024-06-30 23:59 | Roma WL | JEsmeralda | 2024-12-12 17:25 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 6 |  | L0 - No RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1010350 | O.1010350.11 | A.1010350.11.07 | Dedicated CH_Nov24 | SANTOS LIMITED | THE ROCK 39, RM40-122-1, RM40-122-2, THE ROCK 35, THE ROCK 33, THE ROCK 38, THE ROCK 34, FAIRVIEW 183, FV18-89-1, AVALON 35 | EASTERNWELL 24 | J.24.171679 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2024-10-30 | 2024-10-18 |  | 2024-10-25 | 2024-11-24 00:59 |  | 2024-11-30 | Roma WL | JEsmeralda | 2024-12-05 06:56 | CKok3 |  | No |  |  |  |  | Irwan Wongso |  | 0 | 11 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1010350 | O.1010350.11 | A.1010350.11.04 | Dedicated CH_Aug24__2 | SANTOS LIMITED | Well #25, Well #26, Well #27, Well #28, THE ROCK 39, Well #23, RM40-122-1, RM40-122-2, THE ROCK 38, THE ROCK 34, THE ROCK 33, THE ROCK 35, RM90-108-1, RM90-109-1, Well #39, FV17-86-1, FV16-71-1, FV17-87-1, RM90-139-1, FV12-78 1, FV16-74-1, FV17-85-1, FV17-88-1, FV16-72-1, FV16-75-1, MOUNT KINGSLEY 55 | EASTERNWELL 24 | J.24.138736 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2024-04-13 23:00 | 2024-08-02 |  | 2024-08-09 | 2024-09-07 23:59 |  | 2024-09-07 23:59 | Roma WL | SAli112 | 2024-10-09 19:45 | CClark9 |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 22 |  | L0 - No RO |  | 100 | 100 | 0 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1010350 | O.1010350.11 | A.1010350.11.02 | Dedicated CH_Jul24 | SANTOS LIMITED | Well #25, Well #26, Well #27, Well #28, THE ROCK 39, Well #23, RM40-122-1, RM40-122-2, THE ROCK 38, THE ROCK 34, THE ROCK 33, THE ROCK 35, RM90-108-1, RM90-109-1, Well #39, FV17-86-1, FV16-71-1, FV17-87-1, RM90-139-1, FV12-78 1, FV16-74-1, FV17-85-1, FV17-88-1 | EASTERNWELL 24 | J.24.119042 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2024-03-01 | 2024-06-19 |  | 2024-06-26 | 2024-07-25 23:59 |  | 2024-07-25 23:59 | Roma WL | JEsmeralda | 2024-10-09 19:45 | CClark9 |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 22 |  | L0 - No RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1010350 | O.1010350.11 | A.1010350.11.03 | Dedicated CH_Aug24 | SANTOS LIMITED | Well #25, Well #26, Well #27, Well #28, THE ROCK 39, Well #23, RM40-122-1, RM40-122-2, THE ROCK 38, THE ROCK 34, THE ROCK 33, THE ROCK 35, RM90-108-1, RM90-109-1, Well #39, FV17-86-1, FV16-71-1, FV17-87-1, RM90-139-1, FV12-78 1, FV16-74-1, FV17-85-1, FV17-88-1, FV16-72-1, FV16-75-1 | EASTERNWELL 24 | J.24.131358 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-03-30 | 2024-07-18 |  | 2024-07-25 | 2024-08-23 23:59 |  | 2024-08-23 23:59 | Roma WL | JEsmeralda | 2024-10-09 19:45 | CClark9 |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 22 |  | L0 - No RO |  | 100 | 100 | 0 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1010350 | O.1010350.11 | A.1010350.11.05 | Dedicated CH_Sep24 | SANTOS LIMITED | FV15-45-1, FV15-42-1, FV15-43-1 | EASTERNWELL 24 | J.24.143478 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-08-28 | 2024-08-18 |  | 2024-08-25 | 2024-09-23 23:59 |  | 2024-09-23 23:59 | Roma WL | JEsmeralda | 2024-10-05 10:22 | MPerrtiangha |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 17 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1010350 | O.1010350.10 | A.1010350.10.10 | Dedicated CH_May24 | SANTOS LIMITED | RM90-104-1, RM90-125, RM90-71-1, RM90-51-1, RM90-74-1, RM09-22-1, FAIRVIEW 66, RM27-48-1, FV15-06 1, RM27-46-1, RM90-35-1, FV12-78 1, RM90-98-1, RM90-65-1, FV17-86-1 | MPC 001 | J.24.087494 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2024-03-01 | 2024-04-11 |  | 2024-05-01 | 2024-05-02 23:59 |  | 2024-05-14 23:59 | Roma WL | JEsmeralda | 2024-12-12 17:17 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 13 |  | L0 - No RO |  | 91.7 | 83.3 | 100 | 100 | 92.5 |  | 2 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1010350 | O.1010350.10 | A.1010350.10.08 | Dedicated CH_Mar24 | SANTOS LIMITED | RM90-104-1, RM90-125, RM90-71-1, RM90-51-1, RM90-74-1, RM09-22-1, FAIRVIEW 66, RM27-48-1, FV15-06 1, RM27-46-1 | MPC 001 | J.24.060085 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-03-01 | 2024-02-16 |  | 2024-03-01 | 2024-04-19 23:59 |  | 2024-04-19 23:59 | Roma WL | JEsmeralda | 2024-12-12 17:16 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 11 |  | L0 - No RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1010350 | O.1010350.10 | A.1010350.10.02 | Aug23_PNA WD24 | SANTOS LIMITED | RM49-172-1, RM13-69-1, RM07-07-1, RM09-82-1, RM12-45-1, GRAFTON RANGE 4, BEAUFORT 3, BEAUFORT 6 | MPC 001 | J.23.117761 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-08-01 | 2023-07-31 | 2023-07-31 04:00 | 2023-08-01 | 2023-08-31 23:59 | 2023-09-01 | 2023-08-31 23:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 6 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1010350 | O.1010350.10 | A.1010350.10.03 | PNA_Dedicated Sep23 | SANTOS LIMITED | RM49-172-1, RM13-69-1, RM07-07-1, RM09-82-1, RM12-45-1, GRAFTON RANGE 4, BEAUFORT 3, BEAUFORT 6, MOOGA 2, OK STATION 1, DAWSON 1, DAWSON 2 | MPC 001 | J.23.130621 | RPI | PS-WL-NO | Low | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2023-09-04 | 2023-09-03 | 2023-09-03 04:00 | 2023-09-04 | 2023-09-29 23:59 | 2023-09-30 02:00 | 2023-09-30 01:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 6 |  | L0 - No RO |  | 75 | 50 | 100 | 100 | 77.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1010350 | O.1010350.10 | A.1010350.10.04 | PNA_Dedicated Oct 23 | SANTOS LIMITED | RM49-172-1, RM13-69-1, RM07-07-1, RM09-82-1, RM12-45-1, GRAFTON RANGE 4, BEAUFORT 3, BEAUFORT 6, MOOGA 2, MOUNT ALDIS 2, NEW COUNTRY 1, RM09-50-1, RM68-63-1, FV12-14-3, FV15-06 1, RM49-73-1 | MPC 001 | J.23.139935 | RPI | PS-WL-NO | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2023-09-28 | 2023-09-27 |  | 2023-09-28 | 2023-11-30 23:59 |  | 2023-12-01 00:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 6 |  | L0 - No RO |  | 75 | 50 | 100 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1010350 | O.1010350.10 | A.1010350.10.06 | Completions_Dedicated Dec23 | SANTOS LIMITED | RM49-172-1, RM13-69-1, RM07-07-1, RM09-82-1, RM12-45-1, GRAFTON RANGE 4, BEAUFORT 3, BEAUFORT 6, MOOGA 2, MOUNT ALDIS 2, NEW COUNTRY 1, RM09-50-1, RM68-63-1, FV12-14-3, FV15-06 1, LAMEN 1, LAMEN 3, BEAUFORT 2, TIMBURY HILLS 2 | MPC 001 | J.23.169506 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-12-13 | 2023-11-29 |  | 2023-12-13 | 2024-01-31 23:59 |  | 2024-01-31 23:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 6 |  | L0 - No RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1010350 | O.1010350.10 | A.1010350.10.07 | Dedicated CH_Feb24 | SANTOS LIMITED | RM90-104-1, RM90-125, RM90-71-1, RM90-51-1, RM90-74-1, RM09-22-1, FAIRVIEW 66 | MPC 001 | J.24.043687 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-01-24 | 2024-01-10 |  | 2024-01-24 | 2024-04-01 |  | 2024-04-01 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 8 |  | L0 - No RO |  | 83.3 | 66.7 | 100 | 100 | 85 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1010350 | O.1010350.10 | A.1010350.10.09 | Dedicated CH_Apr24 | SANTOS LIMITED | RM90-104-1, RM90-125, RM90-71-1, RM90-51-1, RM90-74-1, RM09-22-1, FAIRVIEW 66, RM27-48-1, FV15-06 1, RM27-46-1, RM90-35-1, FV12-78 1, MEDML01, RM40-122-1, RM90-98-1 | MPC 001 | J.24.073535 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-03-25 | 2024-03-11 | 2024-03-22 13:00 | 2024-03-25 | 2024-04-30 23:59 | 2024-05-01 | 2024-05-18 23:59 | Roma WL | JEsmeralda | 2024-05-02 21:37 | SLie4 |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 11 |  | L0 - No RO |  | 100 | 100 | 0 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1010350 | O.1010350.10 | A.1010350.10.05 | PNA_Dedicated Nov 23 | SANTOS LIMITED | RM49-172-1, RM13-69-1, RM07-07-1, RM09-82-1, RM12-45-1, GRAFTON RANGE 4, BEAUFORT 3, BEAUFORT 6, MOOGA 2, MOUNT ALDIS 2 | MPC 001 | J.23.157948 | RPI | PS-WL-NO | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2023-10-25 | 2023-10-24 | 2023-10-24 05:00 | 2023-10-25 | 2023-11-24 23:59 | 2023-11-25 01:00 | 2023-11-24 23:59 | Roma WL | JEsmeralda | 2023-10-24 11:32 | JEsmeralda |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 6 |  | L0 - No RO |  | 58.3 | 33.3 | 100 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1010350 | O.1010350.10 | A.1010350.10.01 | Perforation 3-3-8in | SANTOS LIMITED | RM49-172-1, RM13-69-1, RM07-07-1, RM09-82-1, RM12-45-1 | MPC 001 | J.23.073307 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-23 | 2023-04-22 |  | 2023-04-23 | 2023-05-08 23:59 |  | 2023-05-08 23:59 | Roma WL | SAli63 | 2023-05-09 08:16 | SLie4 |  | No |  |  |  |  | Jon Lawrie |  | 0 | 6 |  | L0 - No RO |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.09 | A.1010350.09.03 | Perforation 3-3/8" and 4.5" | SANTOS LIMITED | RM50-133-1 | EASTERNWELL 24 | J.23.092947 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-06-03 | 2023-05-26 | 2023-05-31 | 2023-05-31 | 2023-06-15 23:59 | 2023-06-16 | 2023-06-15 23:59 | Roma WL | NAndilla | 2023-08-20 14:08 | SLie4 |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 6 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1010350 | O.1010350.09 | A.1010350.09.02 | Santos 3 3-8in Perforations | SANTOS LIMITED | FV07-07-5, FV07-52-01 | EASTERNWELL 24 | J.23.083178 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-13 | 2023-05-13 |  | 2023-05-13 | 2023-05-27 23:59 |  | 2023-05-27 23:59 | Roma WL | SAli63 | 2023-05-26 06:25 | NAndilla |  | No |  |  |  |  | Jon Lawrie |  | 0 | 5 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.09 | A.1010350.09.01 | 3 3-8 Perforations | SANTOS LIMITED | RM96-05-1 | EASTERNWELL 24 | J.23.068877 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-04-17 | 2023-04-17 |  | 2023-04-17 | 2023-04-20 23:59 |  | 2023-04-20 23:59 | Roma WL | SAli63 | 2023-04-20 16:11 | AMuhammad9 |  | No |  |  |  |  | Jon Lawrie |  | 0 | 5 |  | L0 - No RO |  | 83.3 | 33.3 | 0 | 50 | 50 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.08 | A.1010350.08.01 | Perforation and CBL | SANTOS LIMITED | FV07-04-5, FV07-39-1 | Morpheus 7 | J.23.038869 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-15 18:00 | 2023-02-14 14:00 |  | 2023-02-15 18:00 | 2023-02-26 23:59 |  | 2023-02-26 23:59 | Roma WL | MRony2 | 2023-03-02 12:44 | MRony2 |  | No |  |  |  |  | Jon Lawrie |  | 37872.64 | 7 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.08 | A.1010350.08.02 | Perforation 3-3/8", and cement evaluation. | SANTOS LIMITED | FV07-04-5, FV07-39-1 | Morpheus 7 | J.23.038901 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2023-02-12 |  | 2023-02-14 | 2023-02-25 23:59 |  |  | Roma WL | NAndilla | 2023-02-16 07:07 | MRony2 |  | No |  |  |  |  | Jon Lawrie |  | 0 | 0 |  | L0 - No RO |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.07 | A.1010350.07.03 | Perforation and GR-CCL Drift run | SANTOS LIMITED | BGDML-01 | EASTERNWELL 29 | J.22.131698 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2022-12-07 04:44 | 2022-12-05 10:00 |  | 2022-12-06 20:44 | 2022-12-11 16:59 |  | 2022-12-12 00:59 | Roma WL | MRony2 | 2022-12-12 09:06 | VCao2 |  | No |  |  |  |  | Jon Lawrie |  | 5977.91 | 21 |  |  |  | 66.7 | 50 | 0 | 100 | 65 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.07 | A.1010350.07.02 | CBL | SANTOS LIMITED | RM08-79-1 | EASTERNWELL 29 | J.22.128955 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-25 04:44 | 2022-11-24 18:00 |  | 2022-11-25 04:44 | 2022-11-26 00:59 |  | 2022-11-26 00:59 | Roma WL | MRony2 | 2022-11-26 17:31 | JEsmeralda |  | No |  |  |  |  | Jon Lawrie |  | 5977.91 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.07 | A.1010350.07.01 | RST | SANTOS LIMITED | RM15-87-1 | EASTERNWELL 29 | J.22.116171 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-10-13 |  | 2022-10-13 16:00 | 2022-10-14 00:59 |  |  | Roma WL | MRony2 | 2022-10-16 15:32 | VCao2 |  | No |  |  |  |  | Jon Lawrie |  | 15139.7 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.06 | A.1010350.06.05 | 3-3/8" Perforation_AC23-64-1 AC23-65-1 | SANTOS LIMITED | AC23-65-1, AC23-64-1 | MPC 001 | J.23.105901 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-29 | 2023-06-28 | 2023-06-29 | 2023-06-29 | 2023-07-04 23:59 | 2023-07-05 | 2023-07-04 23:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 8574.4 | 2 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1010350 | O.1010350.06 | A.1010350.06.06 | 3-3/8" Perforation_Kaimanna 34 | SANTOS LIMITED | AC23-65-1, AC23-64-1, KAIMANNA 23 | MPC 001 | J.23.121563 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-08-10 | 2023-08-09 | 2023-08-10 | 2023-08-10 | 2023-08-15 23:59 | 2023-08-16 | 2023-08-15 23:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 8574.4 | 2 |  | L0 - No RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1010350 | O.1010350.06 | A.1010350.06.04 | Plug and perforation | SANTOS LIMITED | BOTTLE TREE 12, BOTTLE TREE 11 | MPC 001 | J.23.081368 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-05-08 08:00 | 2023-05-08 |  | 2023-05-08 08:00 | 2023-05-11 23:59 |  | 2023-05-11 23:59 | Roma WL | SAli63 | 2023-05-14 19:27 | NAndilla |  | No |  |  |  |  | Jon Lawrie |  | 0 | 3 |  | L0 - No RO |  | 91.7 | 25 | 0 | 50 | 50 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.06 | A.1010350.06.03 | FV13-29-1 Plug SLDT | SANTOS LIMITED | FV13-29 1 | MPC 001 | J.23.024349 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-08 11:00 | 2023-01-06 |  | 2023-01-08 11:00 | 2023-01-12 10:59 |  | 2023-01-12 10:59 | Roma WL | MRony2 | 2023-01-15 11:41 | JEsmeralda |  | No |  |  |  |  | Jon Lawrie |  | 5867.12 | 7 |  | L0 - No RO |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.06 | A.1010350.06.02 | Pipe recovery | SANTOS LIMITED | RM50-132-1 | MPC 001 | J.22.110902 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-06-28 04:00 | 2022-06-27 |  | 2022-06-28 04:00 | 2022-07-01 06:59 |  | 2022-07-16 06:59 | Roma WL | MRony2 | 2022-10-03 15:04 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 18583.5 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.06 | A.1010350.06.01 | Perforation | SANTOS LIMITED | FV13-76-2 | MPC 001 | J.22.110901 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-05-06 08:00 | 2022-05-05 16:00 |  | 2022-05-06 08:00 | 2022-05-24 10:59 |  | 2022-05-24 10:59 | Roma WL | MRony2 | 2022-10-03 15:04 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 15172.19 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.05 | A.1010350.05.11 | Grafton Range PnA | SANTOS LIMITED | GRAFTON RANGE 28, GRAFTON RANGE 30 | EASTERNWELL 24 | J.22.135307 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2023-12-21 |  | 2023-12-22 10:00 | 2023-12-31 23:59 |  |  | Roma WL | PLima7 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 22053.93 | 3 |  | L0 - No RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.05 | A.1010350.05.06 | PnA Fairvew 40 | SANTOS LIMITED | FAIRVIEW 121, FAIRVIEW 40 | EASTERNWELL 24 | J.22.123754 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-04 23:00 | 2022-11-04 10:00 |  | 2022-11-04 23:00 | 2022-11-08 19:29 |  | 2022-11-08 19:29 | Roma WL | PLima7 | 2023-03-01 20:23 | JEsmeralda |  | No |  |  |  |  | Jon Lawrie |  | 3395.06 | 4 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 62.5 | 68.8 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.05 | A.1010350.05.08 | FV12-87-1 | SANTOS LIMITED | FV12-87-1 | EASTERNWELL 24 | J.22.129536 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-29 | 2022-11-26 |  | 2022-11-29 | 2022-12-02 23:59 |  | 2022-12-02 23:59 | Roma WL | JEsmeralda | 2023-03-01 19:50 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 3395.06 | 4 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.05 | A.1010350.05.10 | Perforation 3 3/8 HSD | SANTOS LIMITED | RM96-03-1, FV12-112-1 | EASTERNWELL 24 | J.22.133798 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-15 11:00 | 2022-12-13 18:00 |  | 2022-12-16 10:00 | 2022-12-17 23:59 |  | 2022-12-17 00:59 | Roma WL | PLima7 | 2023-03-01 19:09 | JEsmeralda |  | No |  |  |  |  | Jon Lawrie |  | 8479.53 | 1 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.05 | A.1010350.05.09 | Dedicated truck_ RM08-95-1 | SANTOS LIMITED | RM08-95-1 | EASTERNWELL 24 | J.22.132556 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-10 | 2022-12-07 |  | 2022-12-10 | 2022-12-13 23:59 |  | 2022-12-13 23:59 | Roma WL | PLima7 | 2023-03-01 18:09 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 3395.06 | 4 |  |  |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.05 | A.1010350.05.07 | FV38 | SANTOS LIMITED | FAIRVIEW 121, FAIRVIEW 40, FAIRVIEW 38 | EASTERNWELL 24 | J.22.124606 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-11-09 10:00 |  | 2022-11-09 23:00 | 2022-11-13 19:29 |  |  | Roma WL | MRony2 | 2022-11-16 09:50 | JEsmeralda |  | No |  |  |  |  | Jon Lawrie |  | 3395.06 | 3 |  |  |  | 83.3 | 83.3 | 0 | 37.5 | 61.3 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.05 | A.1010350.05.04 | Cutter | SANTOS LIMITED | KELSALL 26 | EASTERNWELL 24 | J.22.110420 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-18 | 2022-09-17 22:00 |  | 2022-09-18 | 2022-09-19 23:59 |  | 2022-09-19 23:59 | Roma WL | PLima7 | 2022-10-19 21:33 | MRony2 |  | No |  |  |  |  | Jon Lawrie |  | 18583.5 | 1 |  | L0 - No RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.05 | A.1010350.05.05 | PMIT | SANTOS LIMITED | FAIRVIEW 252 | EASTERNWELL 24 | J.22.117247 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-09-28 |  | 2022-09-29 10:00 | 2022-10-01 23:59 |  |  | Roma WL | MRony2 | 2022-10-17 18:34 | MRony2 |  | No |  |  |  |  | Jon Lawrie |  | 21410.01 | 2 |  |  |  | 66.7 | 83.3 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.05 | A.1010350.05.03 | Perforation | SANTOS LIMITED | Daldowie 20 | EASTERNWELL 24 | J.22.110407 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-08-07 18:00 |  | 2022-08-10 10:00 | 2022-08-11 23:59 |  |  | Roma WL | PLima7 | 2022-10-03 14:18 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 8479.53 | 1 |  |  |  | 58.3 | 83.3 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.05 | A.1010350.05.02 | PMIT_Pipe recovery | SANTOS LIMITED | FV11-74-21, FV11-69-21 | EASTERNWELL 24 | J.22.110366 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-05-30 |  | 2022-05-31 10:00 | 2022-06-02 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 30409.36 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.05 | A.1010350.05.01 | PMIT and Pipe recovery | SANTOS LIMITED | FV11-74-21 | EASTERNWELL 24 | J.22.110348 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-05-18 |  | 2022-05-19 10:00 | 2022-05-25 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:16 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 30409.36 | 2 |  |  |  | 66.7 | 33.3 | 0 | 100 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.04 | A.1010350.04.01 | FV11-75-21 | SANTOS LIMITED | FV11-75-21 | EASTERNWELL 24 | J.21.109018 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-04-13 14:00 |  | 2021-04-14 | 2021-04-15 23:59 |  |  | Roma WL | EDelange | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 21741.39 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.04 | A.1010350.04.02 | FV12-94-1 | SANTOS LIMITED | FV12-94-1 | EASTERNWELL 24 | J.21.108998 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-06-22 |  | 2021-06-22 10:00 | 2021-06-23 09:59 |  |  | Roma WL | JEsmeralda | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 21741.39 | 1 |  |  |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.03 | A.1010350.03.01 | Roller rental | SANTOS LIMITED | FAIRVIEW 532 | EASTERNWELL 24 | J.21.108960 | RPI | PS-WL-NO | Low | Confirmed | Design - PSD |  | Not Started | Not Started | In Progress |  | 2021-02-01 |  | 2021-02-01 | 2021-02-06 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5198.18 |  |  | L3 - Full RO |  | 50 | 33.3 | 100 | 75 | 57.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.02 | A.1010350.02.09 | 3 3/8" HSD_FV17-66-1 | SANTOS LIMITED | FV17-84-1, FV17-66-1 | EASTERNWELL 24 | J.23.108213 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-07-06 | 2023-07-04 | 2023-07-05 23:00 | 2023-07-06 | 2023-07-09 22:59 | 2023-07-09 23:00 | 2023-07-09 22:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 8574.4 | 1 |  | L0 - No RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1010350 | O.1010350.02 | A.1010350.02.10 | HSD 3-3/8" FV06-60-1 | SANTOS LIMITED | FV06-60-1 | EASTERNWELL 24 | J.23.109473 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-09 | 2023-07-09 | 2023-07-09 | 2023-07-09 | 2023-07-14 23:59 | 2023-07-15 | 2023-07-14 23:59 | Roma WL | NAndilla | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1010350 | O.1010350.02 | A.1010350.02.11 | Cased Hole dedicated Truck Stim Gun job and CBL | SANTOS LIMITED | RM49-64-1 | EASTERNWELL 24 | J.23.114807 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-24 | 2023-07-18 | 2023-07-15 | 2023-07-24 | 2023-07-31 23:59 | 2023-08-01 | 2023-07-31 23:59 | Roma WL | NAndilla | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 3942.82 | 1 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1010350 | O.1010350.02 | A.1010350.02.08 | 3 3/8" HSD_FV17-84-1 | SANTOS LIMITED | FV17-84-1 | EASTERNWELL 24 | J.23.103357 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-27 | 2023-06-24 | 2023-06-26 23:00 | 2023-06-27 | 2023-06-30 22:59 | 2023-06-30 23:00 | 2023-06-30 22:59 | Roma WL | JEsmeralda | 2023-07-02 18:08 | handoko |  | No |  |  |  |  | Jon Lawrie |  | 8574.4 | 1 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1010350 | O.1010350.02 | A.1010350.02.07 | Tubing cutter 2-7/8 | SANTOS LIMITED | FV12-14-3 | EASTERNWELL 24 | J.23.100377 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-10 | 2023-06-07 |  | 2023-06-07 | 2023-06-17 23:59 |  | 2023-06-17 23:59 | Roma WL | NAndilla | 2023-06-15 09:25 | KKeese |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1010350 | O.1010350.02 | A.1010350.02.06 | Tubing Cutter and Caliper job | SANTOS LIMITED | FV12-14-3, FV11-75 21 | EASTERNWELL 24 | J.23.096580 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-03 | 2023-06-03 |  | 2023-06-03 | 2023-06-07 23:59 |  | 2023-06-07 23:59 | Roma WL | NAndilla | 2023-06-08 14:30 | KKeese |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1010350 | O.1010350.02 | A.1010350.02.05 | TCP GR-CCL and Power Cutter for 2 7/8in | SANTOS LIMITED | FV08-02 1, FV08-02 2 | EASTERNWELL 24 | J.23.069394 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-10 16:00 | 2023-04-09 |  | 2023-04-10 16:00 | 2023-04-12 15:59 |  | 2023-04-12 15:59 | Roma WL | SAli63 | 2023-04-23 17:52 | ysaeedabadian |  | No |  |  |  |  | Jon Lawrie |  | 58663.87 | 2 |  | L0 - No RO |  | 83.3 | 16.7 | 0 | 50 | 45 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.02 | A.1010350.02.04 | RM96-05-1 | SANTOS LIMITED | RM96-05-1 | EASTERNWELL 24 | J.23.060431 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-18 01:00 | 2023-04-17 |  | 2023-04-18 | 2023-04-25 23:59 |  | 2023-04-25 23:59 | Roma WL | JEsmeralda | 2023-04-19 15:06 | SAli63 |  | No |  |  |  |  | Jon Lawrie |  | 15854.45 | 4 |  | L0 - No RO |  | 79.2 | 33.3 | 0 | 0 | 33.8 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.02 | A.1010350.02.03 | Perforation/Plug | SANTOS LIMITED | RM15-57-1 | EASTERNWELL 24 | J.23.044408 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2023-02-27 18:00 | 2023-02-17 10:00 |  | 2023-02-27 18:00 | 2023-03-04 00:59 |  | 2023-03-04 00:59 | Roma WL | MRony2 | 2023-03-12 19:26 | MRony2 |  | No |  |  |  |  | Jon Lawrie |  | 15854.45 | 3 |  | L0 - No RO |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.02 | A.1010350.02.02 | EWE-24_erf/Plug | SANTOS LIMITED | NORTH SCOTIA 4, WOODROYD 7 | EASTERNWELL 24 | J.23.031518 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2023-02-05 18:00 | 2023-01-26 16:00 |  | 2023-02-05 18:00 | 2023-02-16 00:59 |  | 2023-02-16 00:59 | Roma WL | MRony2 | 2023-03-01 18:00 | JEsmeralda |  | No |  |  |  |  | Jon Lawrie |  | 77592.65 | 6 |  | L0 - No RO |  | 41.7 | 66.7 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.02 | A.1010350.02.01 | Perforation 3 3/8" HSD | SANTOS LIMITED | Fairview 275 | EASTERNWELL 24 | J.21.108963 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-04-03 |  | 2021-04-04 | 2021-04-07 22:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 16959.06 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.28 | Lynd Range 1 | SANTOS LIMITED | FV12-21-1 | EASTERNWELL 24 | J.22.110900 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress | 2022-04-19 09:00 | 2022-04-18 05:00 |  | 2022-04-19 09:00 | 2022-04-23 23:59 |  | 2022-04-26 22:59 | Roma WL | MRony2 | 2022-10-03 15:04 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 6 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.20 | Perfo FV12-21-1 | SANTOS LIMITED | FV12-21-1 | EASTERNWELL 24 | J.21.109442 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-08-04 10:00 | 2021-07-31 06:00 |  | 2021-08-05 10:00 | 2021-08-06 23:59 |  | 2021-08-06 23:59 | Roma WL | MRony2 | 2022-10-03 15:04 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 32098.77 | 3 |  |  |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.13 | Perfo | SANTOS LIMITED | FV11-107-1 | EASTERNWELL 24 | J.21.109441 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-05-12 05:00 | 2021-05-11 12:00 |  | 2021-05-12 06:00 | 2021-05-16 21:59 |  | 2021-05-16 20:59 | Roma WL | MRony2 | 2022-10-03 15:04 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 32098.77 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.12 | FV17-61-1 - Perfo-GR-Gyro | SANTOS LIMITED | FV17-61-1 | EASTERNWELL 24 | J.21.109440 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-09 06:00 | 2021-03-08 12:00 |  | 2021-03-09 06:00 | 2021-03-13 21:59 |  | 2021-03-13 21:59 | Roma WL | MRony2 | 2022-10-03 15:04 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 32098.77 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.06 | USIT-CBL, Gyro and Perforation FV17-58-1 | SANTOS LIMITED | FV17-58-1 | EASTERNWELL 24 | J.20.063657 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-30 18:00 | 2020-12-30 12:00 |  | 2020-12-30 18:00 | 2021-01-06 09:59 |  | 2021-01-06 09:59 | Roma WL | MRony2 | 2022-10-03 15:04 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 59038.34 |  |  |  |  | 75 | 33.3 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.04 | Perfo - FV210 | SANTOS LIMITED | FAIRVIEW 210 | EASTERNWELL 24 | J.20.063656 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-12 18:00 | 2020-12-12 06:00 |  | 2020-12-12 18:00 | 2020-12-16 18:29 |  | 2020-12-16 18:29 | Roma WL | MRony2 | 2022-10-03 15:04 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 105521.77 |  |  | L0 - No RO |  | 75 | 50 | 0 | 75 | 60 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.27 | Bellington 1 | SANTOS LIMITED | FV12-21-1 | EASTERNWELL 24 | J.22.110327 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress |  | 2022-04-11 05:00 |  | 2022-04-12 09:00 | 2022-04-16 22:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 6 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.25 | Perforation | SANTOS LIMITED | FV15-18 1 | EASTERNWELL 24 | J.22.110300 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-02-27 23:00 | 2022-02-26 06:00 |  | 2022-02-27 23:00 | 2022-03-02 12:59 |  | 2022-03-05 12:59 | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 32455.49 | 6 |  | L0 - No RO |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.26 | Perforation | SANTOS LIMITED | FV18-78-1 | EASTERNWELL 24 | J.22.110294 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-03-16 05:00 |  | 2022-03-17 20:00 | 2022-03-22 09:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 6367.77 | 6 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.21 | Well 1_ Perfo | SANTOS LIMITED | FV12-119-1 | EASTERNWELL 24 | J.22.110278 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-11 10:00 | 2022-01-10 06:00 |  | 2022-01-11 10:00 | 2022-01-14 23:59 |  | 2022-01-18 23:59 | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 64554.26 | 6 |  | L0 - No RO |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.22 | Well 2 | SANTOS LIMITED | FV12-106-1 | EASTERNWELL 24 | J.22.110277 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-20 10:00 | 2022-01-11 06:00 |  | 2022-01-20 10:00 | 2022-01-26 23:59 |  | 2022-01-30 21:11 | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 97009.75 | 6 |  | L0 - No RO |  | 75 | 50 | 0 | 62.5 | 56.3 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.24 | Well 4 | SANTOS LIMITED | FV16-30-2 | EASTERNWELL 24 | J.22.110275 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-02-23 20:00 |  | 2022-02-24 | 2022-02-28 13:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 32455.49 | 6 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.23 | Well 3 | SANTOS LIMITED | FV12-86-1 | EASTERNWELL 24 | J.22.110274 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-01-29 06:00 |  | 2022-01-30 10:00 | 2022-02-05 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 32455.49 | 6 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.19 | Perfo | SANTOS LIMITED | FV12-94-1 | EASTERNWELL 24 | J.21.109047 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2021-06-25 |  | 2021-06-25 06:00 | 2021-07-03 21:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 32098.77 | 5 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.17 | Perfo | SANTOS LIMITED | FV12-100-1 | EASTERNWELL 24 | J.21.109043 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2021-06-11 12:00 |  | 2021-06-12 06:00 | 2021-06-15 21:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 32098.77 | 5 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.15 | Perfo | SANTOS LIMITED | FV12-107-1 | EASTERNWELL 24 | J.21.109042 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2021-05-24 12:00 |  | 2021-05-26 06:00 | 2021-05-31 21:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 32098.77 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.16 | Perfo FV12-105-1 | SANTOS LIMITED | FV12-105-1 | EASTERNWELL 24 | J.21.109035 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-05-31 12:00 |  | 2021-06-01 06:00 | 2021-06-05 21:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 32098.77 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.18 | Perfo | SANTOS LIMITED | FV17-16-2 | EASTERNWELL 24 | J.21.109034 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2021-06-19 05:00 |  | 2021-06-19 06:00 | 2021-06-21 21:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 32098.77 | 5 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.14 | Perfo | SANTOS LIMITED | FV11-108-1 | EASTERNWELL 24 | J.21.109031 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2021-05-18 12:00 |  | 2021-05-19 06:00 | 2021-05-23 21:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 32098.77 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.05 | Perfo - Gyro - FV16-69-1 | SANTOS LIMITED | FV16-69-1 | EASTERNWELL 24 | J.20.063587 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-12-16 08:00 |  | 2020-12-16 12:00 | 2020-12-21 03:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 24301.49 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.03 | GR-Perfo FV15-41-1 | SANTOS LIMITED | FV15-41-1 | EASTERNWELL 24 | J.20.063584 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-11-23 06:00 |  | 2020-11-23 18:00 | 2020-11-27 18:29 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 26796.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.09 | FV17-60-1 GR-Perforation | SANTOS LIMITED | FV17-60-1 | EASTERNWELL 24 | J.21.108961 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-18 20:00 | 2021-01-18 12:00 |  | 2021-01-18 20:00 | 2021-01-23 11:59 |  | 2021-01-23 11:59 | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 100713.45 |  |  | L0 - No RO |  | 75 | 50 | 0 | 75 | 60 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.07 | FV17-59-1 OH log, Liner Correlation, Gyro & Perforation | SANTOS LIMITED | FV17-59-1 | EASTERNWELL 24 | J.21.108959 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-01-06 12:00 |  | 2021-01-06 20:00 | 2021-01-14 11:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 39987.65 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.02 | Density-Perforation | SANTOS LIMITED | FV11-105-1 | EASTERNWELL 24 | J.20.063499 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-11-11 06:00 |  | 2020-11-11 18:00 | 2020-11-15 18:29 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 24392.46 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.01 | Moonah 1 Perforaration | SANTOS LIMITED | MOONAH 1 | EASTERNWELL 24 | J.20.063496 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-11-04 23:00 |  | 2020-11-05 18:00 | 2020-11-07 18:29 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 25367.12 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.10 | FV10-19-1 GR-CCL Correlation Perforation | SANTOS LIMITED | FV10-19-1 | EASTERNWELL 24 | J.21.108958 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-02-24 12:00 |  | 2021-02-25 20:00 | 2021-02-27 11:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 26250.81 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.11 | FV15-08-1 GR-CCL correlation and Perforation | SANTOS LIMITED | FV15-08-1 | EASTERNWELL 24 | J.21.108957 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-02-20 12:00 |  | 2021-02-21 20:00 | 2021-02-26 11:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 31042.88 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1010350 | O.1010350.01 | A.1010350.01.08 | FV16-06-2 GR- Gyro-Perforation | SANTOS LIMITED | FV16-06-2 | EASTERNWELL 24 | J.21.108956 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-01-14 12:00 |  | 2021-01-14 20:00 | 2021-01-19 11:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 39987.65 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1010082 | O.1010082.09 | A.1010082.09.01 | monthly N2 rental | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-2-02 | Maersk Deliverer | J.24.056778 | RPI | CT-NONSERV | Low | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2024-03-01 |  | 2024-03-01 | 2024-04-30 23:59 |  |  | AUS West Coast WS | CNevarez2 | 2024-12-17 18:02 | CNevarez2 |  | No |  |  |  |  | Jose Luis Tejeda |  | 0 | 1 |  |  |  | 43.8 | 33.3 | 100 | 25 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1010082 | O.1010082.08 | A.1010082.08.01 | N2 Pumping | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.24.054347 | RPI | CT-NONSERV | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-11-14 | 2024-11-02 |  | 2024-11-22 | 2024-11-25 23:59 |  | 2024-12-05 23:59 | AUS West Coast WS | JHernandez246 | 2024-12-17 18:05 | CNevarez2 |  | No |  |  |  |  | Cesar Nevarez Carmona |  | 0 | 0 |  | L0 - No RO |  | 81.3 | 66.7 | 100 | 50 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1010082 | O.1010082.08 | A.1010082.08.03 | Monthly rental | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-1A-02 | Maersk Deliverer | J.24.147650 | RPI | CT-NONSERV | Low | Cancelled | Close - PSD |  | Not Required | Not Required | Not Started |  | 2024-09-01 |  | 2024-09-01 | 2024-10-31 23:59 |  |  | AUS West Coast WS | CNevarez2 | 2024-11-05 10:22 | CNevarez2 |  | No |  |  |  |  | Cesar Nevarez Carmona |  | 0 | 0 |  | L0 - No RO |  | 75 | 33.3 | 100 | 25 | 55 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1010082 | O.1010082.08 | A.1010082.08.02 | Standby rentals | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-1A-02 | Maersk Deliverer | J.24.147648 | RPI | CT-N2ONLY | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-09-01 | 2024-09-01 |  | 2024-09-01 | 2024-09-22 23:59 |  | 2024-09-22 23:59 | AUS West Coast WS | CNevarez2 | 2024-08-28 10:18 | CNevarez2 |  | No |  |  |  |  | Cesar Nevarez Carmona |  | 0 | 0 |  | L0 - No RO |  | 37.5 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1010082 | O.1010082.07 | A.1010082.07.01 | Plugs Recovery N2 Pumping | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.24.051349 | RPI | CT-N2ONLY | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2024-08-26 | 2024-08-10 |  | 2024-08-26 | 2024-09-19 23:59 |  | 2024-09-19 23:59 | AUS West Coast WS | JHernandez246 | 2024-08-22 16:32 | CNevarez2 |  | No |  |  |  |  | Jose Luis Tejeda |  | 0 | 0 |  | L0 - No RO |  | 43.8 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1010082 | O.1010082.06 | A.1010082.06.01 | BDC-2-03 | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-2-03, BDC 02 04, BDC-2-01ST1, BDC-2-02 | Maersk Deliverer | J.24.051348 | RPI | CT-N2ONLY | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-06-14 | 2024-07-19 |  | 2024-08-07 | 2024-08-25 23:59 |  | 2024-06-25 23:59 | AUS West Coast WS | JHernandez246 | 2024-08-26 14:33 | CNevarez2 |  | No |  |  |  |  | Cesar Nevarez Carmona |  | 187463.37 | 0 |  | L0 - No RO |  | 93.8 | 83.3 | 100 | 100 | 92.5 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1010082 | O.1010082.05 | A.1010082.05.01 | BDC-2-02 N2 Pumping | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-2-02 | Maersk Deliverer | J.24.051347 | RPI | CT-N2ONLY | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-05-14 | 2024-05-14 |  | 2024-05-14 | 2024-06-25 23:59 |  | 2024-06-25 23:59 | AUS West Coast WS | JHernandez246 | 2024-07-10 11:27 | CNevarez2 |  | No |  |  |  |  | Jose Luis Tejeda |  | 119882.35 | 0 |  |  |  | 93.8 | 83.3 | 100 | 100 | 92.5 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1010082 | O.1010082.04 | A.1010082.04.02 | N2 Pumping BDC-2-01ST1 | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-2-01ST1 | Maersk Deliverer | J.24.044153 | RPI | CT-N2ONLY | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2024-02-08 | 2024-02-04 |  | 2024-02-08 | 2024-02-29 23:59 |  | 2024-02-29 23:59 | AUS West Coast WS | JHernandez246 | 2024-03-14 14:57 | CNevarez2 |  | No |  |  |  |  | Jose Luis Tejeda |  | 160896.88 | 0 |  |  |  | 81.3 | 66.7 | 100 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1010082 | O.1010082.04 | A.1010082.04.01 | N2 Pumping | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-2-01ST1 | Maersk Deliverer | J.24.044146 | RPI | CT-LIFT | Low | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2024-02-04 |  | 2024-02-08 | 2024-02-20 23:59 |  |  | AUS West Coast WS | JHernandez246 | 2024-01-22 16:21 | JHernandez246 |  | No |  |  |  |  | Jose Luis Tejeda |  | 0 | 1 |  |  |  | 18.8 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Cesar Nevarez Carmona | WS Well Intervention
P.1010082 | O.1010082.03 | A.1010082.03.14 | BDC-2-04 N2 Operations | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC 02 04 | Maersk Deliverer | J.23.169016 | RPI | CT-N2ONLY | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2023-11-25 | 2023-11-19 |  | 2023-11-25 | 2023-11-27 23:59 |  | 2023-11-27 23:59 | AUS West Coast WS | JHernandez246 | 2023-11-29 06:26 | JHernandez246 |  | No |  |  |  |  | Jose Luis Tejeda |  | 117668.91 | 1 |  |  |  | 81.3 | 66.7 | 0 | 0 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Paulo Zuliani | WS Well Intervention
P.1010082 | O.1010082.03 | A.1010082.03.11 | N2 Job | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC 02 04 | Maersk Deliverer | J.23.062951 | RPI | CT-N2ONLY | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-10-20 | 2023-03-28 10:00 |  | 2023-11-07 | 2023-11-20 |  | 2024-06-29 22:00 | AUS West Coast WS | OMosleh | 2023-11-23 13:17 | JHernandez246 |  | Yes |  |  |  |  | Feras Manja |  | 196391.37 | 1 |  |  |  | 81.3 | 33.3 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Paulo Zuliani | WS Well Intervention
P.1010082 | O.1010082.03 | A.1010082.03.12 | Coiled Tubing Perforation | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.23.080480 | RPI | CTM-RECHARGE | Low | Confirmed | Design - CEC |  | In Progress | Design Completed | Design Completed | 2023-08-14 | 2023-07-10 | 2023-08-01 | 2023-08-01 | 2023-09-15 23:59 | 2023-09-16 | 2023-09-15 23:59 | AUS West Coast WS | CFancio | 2023-08-14 08:47 | EGafieva |  | Yes |  |  |  |  | Elvira Oates-Boardman |  | 0 | 0 |  |  |  | 87.5 | 50 | 100 | 50 | 70 |  | 0 |  |  |  | 0 |  |  |  | Paulo Zuliani | WS Well Intervention
P.1010082 | O.1010082.03 | A.1010082.03.13 | Test- Crew Archetype | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-03-06 | Maersk Deliverer | J.23.105158 | RPI | CT-N2ONLY | InComplete | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-07-14 | 2023-07-12 10:00 |  | 2023-08-01 | 2023-08-23 |  | 2023-08-22 22:00 | AUS West Coast WS | HFerdjallah | 2023-06-25 14:02 | HFerdjallah |  | Yes |  |  |  |  | Caio Henrique Teixeira Fancio |  | 0 | 1 |  |  |  | 31.3 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Caio Henrique Teixeira Fancio | WS Well Intervention
P.1010082 | O.1010082.03 | A.1010082.03.09 | Q1 2023 Inpex Rentals | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC 5 02 P | Maersk Deliverer | J.22.122438 | RPI | CT-NONSERV | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2023-01-01 |  | 2023-01-01 | 2023-07-31 23:59 |  |  | AUS West Coast WS | HFerdjallah | 2023-06-06 12:40 | PZuliani |  | No |  |  |  |  | Jacob Patrick Meyer |  | 0 | 1 |  |  |  | 50 | 33.3 | 100 | 25 | 45 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1010082 | O.1010082.03 | A.1010082.03.10 | BDC-3-06 N2 Operation | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-03-06 | Maersk Deliverer | J.22.124764 | RPI | CT-N2ONLY | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-18 | 2022-11-09 |  | 2022-12-06 | 2022-12-10 |  | 2022-12-10 | AUS West Coast WS | JMeyer9 | 2023-01-19 15:27 | HFerdjallah |  | Yes |  |  |  |  | Jacob Patrick Meyer |  | 240454.49 | 1 |  |  |  | 87.5 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1010082 | O.1010082.03 | A.1010082.03.05 | Q4 2022 Rentals | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC 5 02 P | Maersk Deliverer | J.22.110898 | RPI | CT-NONSERV | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2022-10-23 |  | 2022-10-23 | 2022-12-31 23:59 |  |  | AUS West Coast WS | SKanaan | 2022-11-30 23:32 | PZuliani |  | No |  |  |  |  | Daniyar Argynov |  | 0 | 1 |  |  |  | 56.3 | 33.3 | 100 | 25 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1010082 | O.1010082.03 | A.1010082.03.03 | Coiled Tubing Perforation EPP1 | INPEX OPERATIONS AUSTRALIA PTY LTD | EPP 1_BDC4 | Maersk Deliverer | J.22.110756 | RPI | CT-PERF,CT-TOOLCON | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-14 | 2022-08-23 |  | 2022-10-14 | 2022-10-18 |  | 2022-10-18 | AUS West Coast WS | DArgynov | 2022-10-30 14:07 | HFerdjallah |  | Yes |  |  |  |  | Jacob Patrick Meyer |  | 558906.26 | 3 |  |  |  | 81.3 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Hamza Ferdjallah | WS Well Intervention
P.1010082 | O.1010082.03 | A.1010082.03.07 | N2 Pressure testing plug | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-1D-02 | Maersk Deliverer | J.22.110899 | RPI | CT-N2ONLY | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-02-08 | 2022-02-01 |  | 2022-02-08 | 2022-03-08 23:59 |  | 2022-03-08 23:59 | AUS West Coast WS | SKanaan | 2022-10-03 12:03 | FDPSystemUser |  | No |  |  |  |  | Daniyar Argynov |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1010082 | O.1010082.03 | A.1010082.03.08 | N2 Pressure Test | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-1D-04 | Maersk Deliverer | J.22.110826 | RPI | CT-N2ONLY | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-06-08 | 2022-05-24 |  | 2022-06-08 | 2022-06-22 23:59 |  | 2022-06-22 23:59 | AUS West Coast WS | SKanaan | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Samer Kanaan |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1010082 | O.1010082.03 | A.1010082.03.04 | Q2 2022 rentals | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.22.110778 | RPI | CT-EQPRNT | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2022-04-01 |  | 2022-04-01 | 2022-06-23 23:59 |  |  | AUS West Coast WS | SKanaan | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Daniyar Argynov |  | 0 | 1 |  |  |  | 50 | 33.3 | 100 | 50 | 50 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1010082 | O.1010082.03 | A.1010082.03.06 | Q3 2022 Rentals | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC 5 02 P | Maersk Deliverer | J.22.110772 | RPI | CT-NONSERV | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2022-07-01 |  | 2022-07-01 | 2022-09-23 23:59 |  |  | AUS West Coast WS | SKanaan | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Daniyar Argynov |  | 0 | 1 |  |  |  | 50 | 33.3 | 100 | 25 | 45 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1010082 | O.1010082.03 | A.1010082.03.02 | INPEX Q4 rental | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.21.109389 | RPI | CT-NONSERV | Low | Confirmed | Design - CEC |  | In Progress | Not Required | In Progress | 2020-11-27 08:00 | 2021-09-01 |  | 2021-09-01 | 2021-12-31 23:59 |  | 2022-03-10 07:59 | AUS West Coast WS | OMosleh | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Tony Huynh |  | 0 | 0 |  |  |  | 75 | 33.3 | 100 | 25 | 55 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1010082 | O.1010082.03 | A.1010082.03.01 | Non operational | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.22.110744 | RPI | CT-NONSERV | InComplete | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-04-29 08:00 | 2022-02-01 |  | 2022-02-01 | 2022-02-28 23:59 |  | 2022-07-01 07:59 | AUS West Coast WS | SKanaan | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Ali Tanha |  | 0 | 0 |  |  |  | 87.5 | 33.3 | 100 | 25 | 60 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1010082 | O.1010082.02 | A.1010082.02.01 | BDC-3-05P (EPP2) | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-3-05P | Maersk Deliverer | J.23.121551 | RPI | CT-PERF,CT-TOOLCON | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-08-16 16:06 | 2023-08-03 |  | 2023-08-16 16:06 | 2023-10-31 23:59 |  | 2023-10-31 23:59 | AUS West Coast WS | EGafieva | 2024-03-21 16:17 | CNevarez2 |  | Yes |  |  |  |  | Elvira Oates-Boardman |  | 1503803.29 | 1 |  |  |  | 87.5 | 50 | 0 | 50 | 60 |  | 0 |  |  |  | 0 |  |  |  | Paulo Zuliani | WS Well Intervention
P.1010082 | O.1010082.01 | A.1010082.01.01 | Coiled Tubing Perforation BDC-04-06 | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC 4 06 P | Maersk Deliverer | J.21.109318 | RPI | CT-PERF,CT-TOOLCON | High | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-02-04 08:00 | 2021-05-12 |  | 2021-05-20 | 2021-05-24 |  | 2021-03-08 07:59 | AUS West Coast WS | RShah18 | 2022-10-03 11:34 | FDPSystemUser |  | Yes |  |  |  |  | Rabia Ishfaq Shah |  | 845015 | 1 |  |  |  | 81.3 | 50 | 0 | 25 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Samer Kanaan | WS Well Intervention
P.1009961 | O.1009961.01 | A.1009961.01.01 | SLK memory camera and caliper | JADESTONE ENERGY (AUSTRALIA) PTY LTD | 21H |  | J.20.063037 | RPI | PS-SLK-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-10-29 |  | 2020-10-31 | 2020-11-05 23:59 |  |  | New Burn WL | frosa2 | 2022-10-03 09:50 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 |  |  |  |  | 41.7 | 50 | 0 | 37.5 | 38.8 |  | 0 | [7 empty] | Luis Cardenas | Wireline Slickline
P.1009833 | O.1009833.02 | A.1009833.02.05 | USIT-CBL | SANTOS LIMITED | CATTLE CREEK 1 | Wild Desert Rig 4 | J.22.110390 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-07-19 10:00 |  | 2022-07-20 07:07 | 2022-07-20 23:59 |  |  | Roma WL | MRony2 | 2022-10-19 13:26 | MRony2 |  | No |  |  |  |  | Jon Lawrie |  | 30094.22 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1009833 | O.1009833.02 | A.1009833.02.03 | Perfo_PNX_RM15-104-1 | SANTOS LIMITED | RM15-104-1, RM15-83-1 | Wild Desert Rig 4 | J.22.110897 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-02-14 03:00 | 2022-02-13 |  | 2022-02-14 03:00 | 2022-02-21 23:59 |  | 2022-02-21 23:59 | Roma WL | MRony2 | 2022-10-03 15:03 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 42170.24 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1009833 | O.1009833.02 | A.1009833.02.04 | PNX_RM15-83-1 | SANTOS LIMITED | RM08-88-1 | Wild Desert Rig 4 | J.22.110311 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-04-21 |  | 2022-04-22 03:00 | 2022-04-23 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1009833 | O.1009833.02 | A.1009833.02.02 | Perforation | SANTOS LIMITED | RM08-88-1 | Wild Desert Rig 4 | J.21.109080 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-12-16 |  | 2021-12-17 03:00 | 2021-12-18 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 15334.63 | 1 |  |  |  | 83.3 | 50 | 0 | 62.5 | 58.8 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1009833 | O.1009833.02 | A.1009833.02.01 | USIT-CBL | SANTOS LIMITED | RM22-18-1 | Wild Desert Rig 4 | J.21.108974 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-03-04 15:00 |  | 2021-03-04 17:00 | 2021-03-05 11:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 23235.87 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1009833 | O.1009833.01 | A.1009833.01.02 | USIT-CBL RM68-73-1 | SANTOS LIMITED | RM 68-73-1, RM68-73 1 | EASTERNWELL 22 | J.20.063655 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-11-28 06:00 | 2020-11-27 06:00 |  | 2020-11-28 06:00 | 2020-11-30 05:59 |  | 2020-11-30 05:59 | Roma WL | MRony2 | 2022-10-03 15:03 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 21741.39 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1009833 | O.1009833.01 | A.1009833.01.07 | USIT-CBL_FV18-69-1 | SANTOS LIMITED | FV18-69-1 | EASTERNWELL 22 | J.21.109050 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-06-24 10:00 |  | 2021-06-25 06:00 | 2021-06-27 05:59 |  |  | Roma WL | EDelange | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 21741.39 | 1 |  |  |  | 58.3 | 50 | 0 | 0 | 32.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1009833 | O.1009833.01 | A.1009833.01.06 | USIT-CBL | SANTOS LIMITED | YANALAH 1 | EASTERNWELL 22 | J.21.109039 | RPI | PS-WL-Ops | Low | Unconfirmed - 50% | Design - CEC |  | Design Completed | Not Required | In Progress | 2021-04-24 23:00 | 2021-04-24 18:00 |  | 2021-04-24 22:00 | 2021-04-26 21:59 |  | 2021-04-27 08:59 | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 0 |  | L3 - Full RO |  | 66.7 | 16.7 | 0 | 0 | 25 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1009833 | O.1009833.01 | A.1009833.01.01 | USIT-CBL RM15-37-1 | SANTOS LIMITED | RM15-37-1 | EASTERNWELL 22 | J.20.063586 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-10-30 06:00 |  | 2020-10-31 06:00 | 2020-11-02 05:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 20246.91 |  |  |  |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1009833 | O.1009833.01 | A.1009833.01.04 | USIT-CCBL | SANTOS LIMITED | Wallumbilla South 2, Yanalah 1 | EASTERNWELL 22 | J.21.109023 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-02-13 10:00 |  | 2021-02-13 14:00 | 2021-02-15 13:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 21741.39 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1009833 | O.1009833.01 | A.1009833.01.03 | USIT-CBL | SANTOS LIMITED | Wallumbilla South 2 | EASTERNWELL 22 | J.21.109020 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-01-29 14:00 |  | 2021-01-29 18:00 | 2021-01-31 17:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 21741.39 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1009833 | O.1009833.01 | A.1009833.01.05 | USIT-CBL RM23-09-1 | SANTOS LIMITED | RM23-09-1 | EASTERNWELL 22 | J.21.109002 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-03-29 18:00 |  | 2021-03-29 22:00 | 2021-03-31 21:59 |  |  | Roma WL | MMclean3 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 21741.39 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1009487 | O.1009487.02 | A.1009487.02.01 | Vent and Relief Line | SANTOS NA (19-12) PTY LTD | Bay Undan | Rigless Australia - 1 |  | RPI | TSWT-DSGN | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-02-11 |  | 2021-02-28 | 2022-03-31 23:59 |  |  | APG TS | GRoxo | 2022-09-03 05:59 | walfaro |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Yudha Swara |  | 10000 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1009487 | O.1009487.02 | A.1009487.02.02 | Vent and Relief line | SANTOS NA (19-12) PTY LTD | Bay Undan | Rigless Australia - 1 |  | RPI | TSWT-RENTAL | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-03-26 |  | 2021-03-26 | 2021-04-30 23:59 |  |  | APG TS | GRoxo | 2022-09-03 05:59 | walfaro |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Yudha Swara |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1009487 | O.1009487.02 | A.1009487.02.03 | Vent and Relief Line rent - Billing to Timor | SANTOS NA (19-12) PTY LTD | Bay Undan | Rigless Australia - 1 |  | RPI | TSWT-RENTAL | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress |  | 2021-05-11 23:59 |  | 2021-05-11 23:59 | 2021-05-13 23:59 |  |  | APG TS | GRoxo | 2022-09-03 05:59 | walfaro |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Yudha Swara |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1009487 | O.1009487.02 | A.1009487.02.05 | Vent and Relief line rent - Billing to Timor | SANTOS NA (19-12) PTY LTD | Bay Undan | Rigless Australia - 1 |  | RPI | TSWT-RENTAL | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-06-25 |  | 2021-06-26 | 2021-11-30 23:59 |  |  | APG TS | GRoxo | 2021-10-29 09:36 | GRoxo |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Yudha Swara |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1009487 | O.1009487.02 | A.1009487.02.04 | Vent and relief line rent - Billing to Timor | SANTOS NA (19-12) PTY LTD | Bay Undan | Rigless Australia - 1 |  | RPI | TSWT-RENTAL | Medium | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress |  | 2021-05-26 |  | 2021-05-26 | 2021-06-25 23:59 |  |  | APG TS | GRoxo | 2021-09-02 21:15 | GRoxo |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Gabriela Soter Roxo Teckemeier |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1009487 | O.1009487.01 | A.1009487.01.04 | 3rd Well - DS-06 | SANTOS NA (19-12) PTY LTD | DS06 | Noble Tom Prosser | J.21.108324 | RPI | TSWT-SEPVX-JOB | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2021-10-06 | 2021-10-26 |  | 2021-11-19 22:00 | 2021-12-07 21:59 |  | 2021-11-15 23:59 | APG TS | MSwara | 2024-11-19 20:19 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Gabriela Soter Roxo Teckemeier |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 50 | 0 | 25 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1009487 | O.1009487.01 | A.1009487.01.02 | 1st Well - W13ST2 | SANTOS NA (19-12) PTY LTD | W13ST2, Bay Undan | Noble Tom Prosser |  | RPI | TSWT-SEPVX-JOB | Medium | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2021-07-12 14:00 | 2021-06-21 |  | 2021-07-12 14:00 | 2021-08-10 13:59 |  | 2021-08-17 13:59 | APG TS | MSwara | 2024-11-19 20:19 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Yudha Swara |  | 1007.49 | 1 |  | L0 - No RO |  | 50 | 50 | 0 | 37.5 | 41.3 |  | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1009487 | O.1009487.01 | A.1009487.01.08 | DS06 | SANTOS NA (19-12) PTY LTD | W13ST2 | Noble Tom Prosser | J.21.108344 | RPI | TSWT-SEPVX-JOB | Medium | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-09-24 |  | 2021-11-07 14:00 | 2021-12-06 13:59 |  |  | APG TS | GRoxo | 2024-11-19 20:19 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Gabriela Soter Roxo Teckemeier |  | 0 | 1 |  |  |  | 66.7 | 16.7 | 0 | 0 | 25 |  | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1009487 | O.1009487.01 | A.1009487.01.07 | W10 | SANTOS NA (19-12) PTY LTD | W13ST2 | Noble Tom Prosser | J.21.108343 | RPI | TSWT-SEPVX-JOB | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-08-15 |  | 2021-09-05 14:00 | 2021-10-04 13:59 |  |  | APG TS | GRoxo | 2024-11-19 20:19 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Gabriela Soter Roxo Teckemeier |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1009487 | O.1009487.01 | A.1009487.01.03 | 2nd Well - W10 | SANTOS NA (19-12) PTY LTD | W10 | Noble Tom Prosser | J.21.108325 | RPI | TSWT-SEPONLY-JOB | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2021-09-18 | 2021-08-27 |  | 2021-09-18 | 2021-10-07 23:59 |  | 2021-10-12 23:59 | APG TS | MSwara | 2024-11-19 20:14 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Yudha Swara |  | 0 | 1 |  | L0 - No RO |  | 50 | 50 | 0 | 0 | 30 |  | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1009487 | O.1009487.01 | A.1009487.01.05 | 2022 Timor Leste Campaign - Well 01 | SANTOS NA (19-12) PTY LTD | DS06, W10, W13ST2, Bay Undan | Noble Tom Prosser |  | RPI | TSWT-SEPONLY-JOB | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-04-26 | 2022-05-01 |  | 2022-06-01 | 2022-06-25 23:59 |  | 2022-06-25 23:59 | APG TS | GRoxo | 2024-11-19 20:14 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Yudha Swara |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1009487 | O.1009487.01 | A.1009487.01.10 | 2022 Timor Leste Campaign Well 03 | SANTOS NA (19-12) PTY LTD | DS06, W10, W13ST2, Bay Undan | Noble Tom Prosser |  | RPI | TSWT-SEPONLY-JOB | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-08-01 | 2022-07-31 |  | 2022-08-01 | 2022-08-25 23:59 |  | 2022-08-25 23:59 | APG TS | GRoxo | 2024-11-19 20:14 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Yudha Swara |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1009487 | O.1009487.01 | A.1009487.01.11 | 2022 Timor Leste Campaign - Well 04 | SANTOS NA (19-12) PTY LTD | DS06, W10, W13ST2, Bay Undan | Noble Tom Prosser |  | RPI | TSWT-SEPONLY-JOB | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-08-31 |  | 2022-09-01 | 2022-09-25 23:59 |  |  | APG TS | GRoxo | 2024-11-19 20:14 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Yudha Swara |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1009487 | O.1009487.01 | A.1009487.01.09 | 2022 Timor Leste Campaign - Well 02 | SANTOS NA (19-12) PTY LTD | DS06, W10, W13ST2, Bay Undan | Noble Tom Prosser |  | RPI | TSWT-SEPONLY-JOB | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-07-01 | 2022-06-30 |  | 2022-07-01 | 2022-07-25 23:59 |  | 2022-07-25 23:59 | APG TS | GRoxo | 2024-11-19 20:14 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Yudha Swara |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1009487 | O.1009487.01 | A.1009487.01.12 | 2022 Timor Leste Campaign - Well 05 | SANTOS NA (19-12) PTY LTD | DS06, W10, W13ST2, Bay Undan | Noble Tom Prosser |  | RPI | TSWT-SEPONLY-JOB | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-09-30 |  | 2022-10-01 | 2022-12-25 23:59 |  |  | APG TS | GRoxo | 2024-11-19 20:14 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Yudha Swara |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1009487 | O.1009487.01 | A.1009487.01.01 | Design Phase - SWT Flowback | SANTOS NA (19-12) PTY LTD | DS06, W10, W13ST2, Bay Undan | Noble Tom Prosser |  | RPI | TSWT-DSGN | Medium | Confirmed | Design - PSD |  | In Progress | Not Started | In Progress | 2021-03-03 | 2021-03-03 |  | 2021-03-03 | 2022-01-31 23:59 |  | 2021-12-08 23:59 | APG TS | GRoxo | 2022-09-03 05:59 | walfaro |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Yudha Swara |  | 159425.49 | 3 |  | L0 - No RO | [7 empty] | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1009487 | O.1009487.01 | A.1009487.01.06 | Design Phase - SWT Flowback | SANTOS NA (19-12) PTY LTD | DS06, W10, W13ST2, Bay Undan | Noble Tom Prosser |  | RPI | TSWT-DSGN | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2021-06-17 08:01 | 2021-03-26 |  | 2021-03-26 | 2021-05-25 23:59 |  | 2021-06-18 08:12 | APG TS | GRoxo | 2022-09-03 05:59 | walfaro |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Yudha Swara |  | 0 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1009485 | O.1009485.01 | A.1009485.01.02 | tank for flowback | TORNADO SOLUTIONS PTY LTD | STAG 21H | Island Performer LWI | J.20.062347 | RPI | TSWT-FLOWBACK-JOB | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-12-23 |  | 2021-01-01 | 2021-01-31 23:59 |  |  | APG TS | GRoxo | 2022-10-03 06:24 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Allwyn Francis |  | 99340 | [10 empty] | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1009485 | O.1009485.01 | A.1009485.01.01 | Flowback Tanks | TORNADO SOLUTIONS PTY LTD | STAG 21H | Island Performer LWI | J.21.108323 | RPI | TSWT-FLOWBACK-JOB | High | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-01-15 |  | 2021-01-15 | 2021-01-22 23:59 |  |  | APG TS | GRoxo | 2022-10-03 06:24 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Pablo Andres Caceres Flores |  | 0 | [10 empty] | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1009294 | O.1009294.01 | A.1009294.01.01 | RPI Epilogue | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.24.089947 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2024-04-25 |  | 2024-04-25 | 2024-04-30 23:59 |  |  | New Burn WL | JSedmak | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Angelia Hermawan |  | 0 | 0 |  | L0 - No RO |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1009159 | O.1009159.01 | A.1009159.01.01 | OH logging | AGL ENERGY LIMITED | Churchie West-1 | EASTERNWELL 3 | J.20.063580 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Required | In Progress |  | 2020-10-04 13:00 |  | 2020-10-05 12:00 | 2020-10-07 10:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 32813.52 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1009159 | O.1009159.01 | A.1009159.01.02 | Pipe recovery - Churchie West 1 | AGL ENERGY LIMITED | CHURCHIE WEST-1 | EASTERNWELL 3 | J.20.063577 | RPE | ES-CH-NO | High | Unconfirmed - 90% | Design - CEC |  | Design Completed | Not Started | In Progress | 2020-09-29 11:00 | 2020-09-29 10:00 |  | 2020-09-29 11:00 | 2020-09-29 18:59 |  | 2020-09-29 18:59 | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 5263.16 |  |  | L0 - No RO |  | 66.7 | 66.7 | 100 | 75 | 72.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1008990 | O.1008990.01 | A.1008990.01.01 | Well site Chemistry | INPEX BROWSE E&P PTY LTD |  | ICHTHYS VENTURER | J.20.062346 | RPI | PSVS-NOSEPNOVX | High | Unconfirmed - 10% | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-12-30 |  | 2020-12-30 | 2021-01-31 23:59 |  |  | APG TS | GRoxo | 2022-10-03 06:24 | FDPSystemUser |  | No |  | [AUJN-PSVS] - AU - Jandakot PSVS |  |  | Yagan Bibby |  | 0 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TS Production Testing
P.1008951 | O.1008951.01 | A.1008951.01.01 | VX Calibration - EP | JADESTONE ENERGY (AUSTRALIA) PTY LTD | STAG 48H | STAG SNUBBING UNIT 1 | J.20.062345 | RPI | PSVS-VXONLY | Medium | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-10-21 | 2022-02-08 08:00 | 2020-10-22 | 2020-10-29 23:59 | 2022-02-16 08:00 |  | APG TS | GRoxo | 2024-04-05 23:15 | FDPSystemUser |  | No |  | [AUJN-PSVS] - AU - Jandakot PSVS |  |  | Pablo Andres Caceres Flores |  | 17014.29 |  |  |  |  | 41.7 | 16.7 | 0 | 75 | 40 |  | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TS Production Testing
P.1008951 | O.1008951.01 | A.1008951.01.02 | STAG Calibration 2022 | JADESTONE ENERGY (AUSTRALIA) PTY LTD | STAG 48H | STAG SNUBBING UNIT 1 | J.22.109452 | RPI | PSVS-SERVICES | Medium | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2022-01-21 |  | 2022-01-27 13:00 | 2022-02-03 12:59 |  |  | APG TS | GRoxo | 2022-10-03 06:29 | FDPSystemUser |  | No |  | [AUJN-PSVS] - AU - Jandakot PSVS |  |  | Pablo Andres Caceres Flores |  | 0 | 1 |  |  |  | 75 | 50 | 100 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Production Testing
P.1008919 | O.1008919.03 | A.1008919.03.01 | CBL-VDL | IMPERIAL OIL AND GAS PTY LTD | CARPENTARIA-3H | SILVER CITY 40 | J.22.119781 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-03 15:00 | 2022-11-03 |  | 2022-11-03 15:00 | 2022-11-08 14:59 |  | 2022-11-08 14:59 | Roma WL | MRony2 | 2022-12-05 13:34 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 47580.56 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1008919 | O.1008919.02 | A.1008919.02.02 | Re-imbursible | IMPERIAL OIL AND GAS PTY LTD | CARPENTARIA 1 | SAXTON 183 | J.20.063574 | RPE | ES-OH-NO | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-11-22 |  | 2020-11-23 | 2020-11-24 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 26451.74 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1008919 | O.1008919.02 | A.1008919.02.01 | prejob payment | IMPERIAL OIL AND GAS PTY LTD | CARPENTARIA 1 | SAXTON 183 | J.20.063572 | RPE | ES-OH-NO | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-10-11 |  | 2020-10-12 | 2020-10-17 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 426569.98 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1008919 | O.1008919.01 | A.1008919.01.03 | OH | IMPERIAL OIL AND GAS PTY LTD | CARPENTARIA 4, Carpentaria 1 | Silver City 4 | J.22.110263 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-12-28 | 2022-12-22 |  | 2022-12-28 | 2023-01-04 |  | 2023-01-14 | Roma WL | MRony2 | 2023-01-15 21:16 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 374563.8 | 5 |  | L2 - Shift RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1008919 | O.1008919.01 | A.1008919.01.04 | Ultratrack_FMI | IMPERIAL OIL AND GAS PTY LTD |  | Silver City 4 | J.22.110346 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-10-13 |  | 2022-10-16 | 2022-10-18 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:16 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1008919 | O.1008919.01 | A.1008919.01.02 | OH well | IMPERIAL OIL AND GAS PTY LTD | Carpentaria 2 | Silver City 4 | J.21.109028 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-11-20 |  | 2021-11-20 | 2021-12-03 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 486888.7 | 6 |  |  |  | 75 | 33.3 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1008919 | O.1008919.01 | A.1008919.01.01 | Carpenteria-1 | IMPERIAL OIL AND GAS PTY LTD | Carpentaria 1 | Silver City 4 | J.20.063569 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-10-07 |  | 2020-10-10 | 2020-10-27 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 439519.95 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1008665 | O.1008665.01 | A.1008665.01.01 | USIT-CBL-XTRA | JADESTONE ENERGY (AUSTRALIA) PTY LTD | STAG 21H | STAG SNUBBING UNIT 1 | J.20.063036 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-18 |  | 2020-09-26 | 2020-09-30 23:59 |  |  | New Burn WL | CJones19 | 2022-10-03 09:49 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 233832 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1008190 | O.1008190.01 | A.1008190.01.03 | Ironbark Feb | BP AUSTRALIA (APG) | IronBark-1 | Ocean Apex | J.21.108839 | RPE | ES-OH-NO | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-02-09 |  | 2021-02-09 | 2021-03-10 23:59 |  |  | New Burn WL | CJones19 | 2022-10-03 09:49 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1008190 | O.1008190.01 | A.1008190.01.02 | Ironbark Jan | BP AUSTRALIA (APG) | IronBark-1 | Ocean Apex | J.21.108838 | RPE | ES-OH-NO | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-01-09 |  | 2021-01-09 | 2021-02-08 23:59 |  |  | New Burn WL | CJones19 | 2022-10-03 09:49 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1008190 | O.1008190.01 | A.1008190.01.01 | BP ¦ Ironbark-1 ¦ 8.5in OH Section | BP AUSTRALIA (APG) | IronBark-1 | Ocean Apex | J.20.063035 | RPE | ES-OH-NO | High | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-12-29 |  | 2020-12-31 | 2021-01-14 23:59 |  |  | New Burn WL | CJones19 | 2022-10-03 09:49 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Bilal Ahmad | WL Evaluation Services
P.1008188 | O.1008188.02 | A.1008188.02.02 | Mckee-2 | TODD ENERGY LIMITED |  | Big Ben | J.21.109087 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-06-13 |  | 2021-06-14 | 2021-06-21 23:59 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 16:18 | FDPSystemUser |  | Yes |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Paulo Zuliani | WL Evaluation Services
P.1008188 | O.1008188.02 | A.1008188.02.01 | Mckee-1 | TODD ENERGY LIMITED |  | Big Ben | J.21.109085 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-05-14 |  | 2021-05-15 | 2021-05-22 23:59 |  |  | New Plymouth WL | PZuliani | 2022-10-03 16:18 | FDPSystemUser |  | Yes |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Paulo Zuliani | WL Evaluation Services
P.1008188 | O.1008188.01 | A.1008188.01.02 | MHW-32 | TODD ENERGY LIMITED | MANGAHEWA 32 | Big Ben | J.21.109439 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-03-20 | 2021-03-19 |  | 2021-03-20 | 2021-03-27 23:59 |  | 2021-03-27 23:59 | New Plymouth WL | VOliveira5 | 2022-10-03 17:03 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 143729 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Paulo Zuliani | WL Evaluation Services
P.1008188 | O.1008188.01 | A.1008188.01.03 | Proppant for TODD | TODD ENERGY LIMITED | MANGAHEWA 31 | Big Ben | J.21.109097 | RPE | ES-CH-NO | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2021-03-29 |  | 2021-03-29 | 2021-03-30 23:59 |  |  | New Plymouth WL | PZuliani | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 197500 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Paulo Zuliani | WL Evaluation Services
P.1008188 | O.1008188.01 | A.1008188.01.01 | MHW-31 | TODD ENERGY LIMITED | MANGAHEWA 31 | Big Ben | J.21.109084 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-02-06 |  | 2021-02-14 | 2021-02-21 23:59 |  |  | New Plymouth WL | PZuliani | 2022-10-03 16:18 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 166558.5 | [10 empty] | 0 | [7 empty] | Paulo Zuliani | WL Evaluation Services
P.1008026 | O.1008026.03 | A.1008026.03.03 | ADZ OH | ARMOUR ENERGY (SURAT BASIN) PTY LTD | WARROON 1 |  | J.24.096883 | RPI | PS-WL-Ops | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2024-08-30 |  | 2024-09-01 | 2024-11-30 23:59 |  |  | Roma WL | KKeese | 2024-08-12 13:24 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1008026 | O.1008026.03 | A.1008026.03.02 | HULY ADZ Activity | ARMOUR ENERGY (SURAT BASIN) PTY LTD | Warroon 1 |  | J.24.096876 | RPI | PS-WL-Ops | InComplete | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2024-07-13 |  | 2024-07-15 | 2024-07-17 23:59 |  |  | Roma WL | KKeese | 2024-07-23 14:52 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1008026 | O.1008026.03 | A.1008026.03.01 | Perforation | ARMOUR ENERGY (SURAT BASIN) PTY LTD | Warroon 1 |  | J.22.110896 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2022-01-08 | 2022-01-06 |  | 2022-01-08 | 2022-01-10 23:59 |  | 2022-01-12 23:59 | Roma WL | MRony2 | 2022-10-03 15:03 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 21182.59 | 1 |  |  |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1008026 | O.1008026.02 | A.1008026.02.01 | Pre job payment | ARMOUR ENERGY (SURAT BASIN) PTY LTD | WARROON 1 |  | J.20.063561 | RPI | PS-WL-NO | InComplete | Unconfirmed - 90% | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-08-19 |  | 2020-08-19 | 2020-08-25 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 19634.18 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1008026 | O.1008026.02 | A.1008026.02.02 | Advance payment | ARMOUR ENERGY (SURAT BASIN) PTY LTD | WARROON 1 |  | J.20.063551 | RPI | PS-WL-NO | InComplete | Unconfirmed - 90% | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-11-20 |  | 2020-11-20 | 2020-11-26 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 12573.1 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1008026 | O.1008026.01 | A.1008026.01.02 | PNX | ARMOUR ENERGY (SURAT BASIN) PTY LTD | Warroon 1 |  | J.20.063567 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-10-13 |  | 2020-10-16 | 2020-10-18 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 37112.74 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1008026 | O.1008026.01 | A.1008026.01.01 | PNX job | ARMOUR ENERGY (SURAT BASIN) PTY LTD | Warroon 1 |  | J.20.063563 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-08-20 16:00 |  | 2020-08-23 16:00 | 2020-08-26 15:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 23326.84 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1008026 | O.1008026.01 | A.1008026.01.03 | Plug and perf | ARMOUR ENERGY (SURAT BASIN) PTY LTD | Warroon 1 |  | J.20.063556 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-11-07 |  | 2020-11-07 09:00 | 2020-11-09 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 28358.02 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1008026 | O.1008026.01 | A.1008026.01.06 | PNX | ARMOUR ENERGY (SURAT BASIN) PTY LTD | Warroon 1 |  | J.21.108986 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2021-08-14 |  | 2021-08-14 09:00 | 2021-08-16 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1008026 | O.1008026.01 | A.1008026.01.10 | P$P | ARMOUR ENERGY (SURAT BASIN) PTY LTD |  |  | J.22.110250 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-07-20 |  | 2022-07-20 09:00 | 2022-07-22 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 3 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1008026 | O.1008026.01 | A.1008026.01.05 | P&P | ARMOUR ENERGY (SURAT BASIN) PTY LTD | Warroon 1 |  | J.22.110249 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-11-05 01:00 |  | 2022-11-07 10:00 | 2022-11-10 00:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1008026 | O.1008026.01 | A.1008026.01.09 | P&P | ARMOUR ENERGY (SURAT BASIN) PTY LTD |  |  | J.22.110248 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-07-16 |  | 2022-07-16 09:00 | 2022-07-18 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 3 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1008026 | O.1008026.01 | A.1008026.01.04 | PNX | ARMOUR ENERGY (SURAT BASIN) PTY LTD | Warroon 1 |  | J.22.110247 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-09-07 |  | 2022-09-07 09:00 | 2022-09-09 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1008026 | O.1008026.01 | A.1008026.01.08 | Myall Creek 2 PNX | ARMOUR ENERGY (SURAT BASIN) PTY LTD | Myall Creek 2 |  | J.22.110246 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-01-11 01:00 |  | 2022-01-12 10:00 | 2022-01-15 00:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 37946.72 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1008026 | O.1008026.01 | A.1008026.01.07 | 2nd PNX well | ARMOUR ENERGY (SURAT BASIN) PTY LTD |  |  | J.22.110245 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-09-26 01:00 |  | 2022-09-26 10:00 | 2022-09-29 00:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 1 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1008021 | O.1008021.02 | A.1008021.02.01 | Pre job ticket | CARBON TRANSPORT AND STORAGE CORPORATION (CTSCO) PTY LIMITED | WEST MOONIE 1 | EASTERNWELL 101 | J.20.063565 | RPE | ES-OH-NO | Low | Unconfirmed - 90% | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-08-05 |  | 2020-08-05 | 2020-08-10 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 191483.91 |  |  | L0 - No RO |  | 50 | 33.3 | 100 | 75 | 57.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1008021 | O.1008021.02 | A.1008021.02.02 | Non Ops | CARBON TRANSPORT AND STORAGE CORPORATION (CTSCO) PTY LIMITED | WEST MOONIE 1 | EASTERNWELL 101 | J.20.063559 | RPE | ES-OH-NO | Low | Unconfirmed - 90% | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-09-22 |  | 2020-09-22 | 2020-09-25 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 5198.18 |  |  | L0 - No RO |  | 50 | 33.3 | 100 | 75 | 57.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1008021 | O.1008021.01 | A.1008021.01.04 | Heath 1 _Intermediate | CARBON TRANSPORT AND STORAGE CORPORATION (CTSCO) PTY LIMITED | WEST MOONIE 1 | EASTERNWELL 101 | J.23.085255 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-01 | 2023-09-27 |  | 2023-09-27 | 2023-09-29 23:59 |  | 2023-10-03 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 47839.51 | 1 |  | L3 - Full RO |  | 41.7 | 33.3 | 0 | 50 | 37.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1008021 | O.1008021.01 | A.1008021.01.07 | CTSO Intermediate 3 | CARBON TRANSPORT AND STORAGE CORPORATION (CTSCO) PTY LIMITED | STURM-1 | EASTERNWELL 101 | J.23.085727 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-11-10 | 2023-11-07 |  | 2023-11-08 | 2023-11-10 23:59 |  | 2023-11-15 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 1 |  | L0 - No RO |  | 75 | 83.3 | 0 | 50 | 62.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1008021 | O.1008021.01 | A.1008021.01.06 | CTSCO Intermediate 2 | CARBON TRANSPORT AND STORAGE CORPORATION (CTSCO) PTY LIMITED | CALLUM-1 | EASTERNWELL 101 | J.23.085726 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-10-17 02:00 | 2023-10-16 06:00 | 2023-10-16 | 2023-10-17 03:00 | 2023-10-20 02:59 | 2023-10-21 | 2023-10-20 02:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 54993.5 | 5 |  | L0 - No RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1008021 | O.1008021.01 | A.1008021.01.08 | CTSCO TD Section_Well 1 | CARBON TRANSPORT AND STORAGE CORPORATION (CTSCO) PTY LIMITED | HEALTH 1 | EASTERNWELL 101 | J.23.085728 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-10-04 | 2023-10-03 | 2023-10-01 14:00 | 2023-10-04 | 2023-10-10 23:59 | 2023-10-14 | 2023-10-10 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 4 |  | L3 - Full RO |  | 75 | 83.3 | 0 | 75 | 70 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1008021 | O.1008021.01 | A.1008021.01.09 | CTSCO TD Section 2 | CARBON TRANSPORT AND STORAGE CORPORATION (CTSCO) PTY LIMITED | CALLUM-1 | EASTERNWELL 101 | J.23.085729 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-10-22 | 2023-10-22 | 2023-10-19 | 2023-11-13 | 2023-11-23 23:59 | 2023-11-02 | 2023-10-24 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 332274.2 | 2 |  | L3 - Full RO |  | 75 | 66.7 | 0 | 50 | 57.5 |  | 2 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1008021 | O.1008021.01 | A.1008021.01.13 | Sturm 1 | CARBON TRANSPORT AND STORAGE CORPORATION (CTSCO) PTY LIMITED | CALLUM-1, STURM-1 | EASTERNWELL 101 | J.23.165998 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-10-23 | 2023-10-23 |  | 2023-11-14 | 2023-11-24 23:59 |  | 2023-10-25 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 332274.2 | 4 |  | L3 - Full RO |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1008021 | O.1008021.01 | A.1008021.01.14 | CTSCO Sienna 1 | CARBON TRANSPORT AND STORAGE CORPORATION (CTSCO) PTY LIMITED | SIENNA-1 | EASTERNWELL 101 | J.23.168264 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-10-26 | 2023-10-26 |  | 2023-11-17 | 2023-11-27 23:59 |  | 2023-10-28 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 50187.13 | 4 |  | L2 - Shift RO |  | 91.7 | 66.7 | 0 | 62.5 | 66.3 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1008021 | O.1008021.01 | A.1008021.01.15 | Sienna 1 TD | CARBON TRANSPORT AND STORAGE CORPORATION (CTSCO) PTY LIMITED | SIENNA-1 | EASTERNWELL 101 | J.23.169304 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-11-11 | 2023-11-23 |  | 2023-12-03 | 2023-12-13 23:59 |  | 2023-12-13 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 50187.13 | 3 |  | L2 - Shift RO |  | 75 | 33.3 | 0 | 100 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1008021 | O.1008021.01 | A.1008021.01.12 | TECH ACCESS CTSCO 3 | CARBON TRANSPORT AND STORAGE CORPORATION (CTSCO) PTY LIMITED | WEST MOONIE 1 | EASTERNWELL 101 | J.24.022188 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2024-04-01 |  | 2024-04-02 | 2024-04-04 23:59 |  |  | Roma WL | KKeese | 2024-01-10 16:29 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 |  |  |  |  | 8.3 | 0 | 0 | 0 | 2.5 |  | 1 | [7 empty] | Kelly Keese | WL Evaluation Services
P.1008021 | O.1008021.01 | A.1008021.01.11 | TECH ACCESS CTSCO 2 | CARBON TRANSPORT AND STORAGE CORPORATION (CTSCO) PTY LIMITED | WEST MOONIE 1 | EASTERNWELL 101 | J.24.022187 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2024-02-06 |  | 2024-02-07 | 2024-02-09 23:59 |  |  | Roma WL | KKeese | 2024-01-10 15:53 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 |  |  |  |  | 8.3 | 0 | 0 | 0 | 2.5 |  | 0 | [7 empty] | Kelly Keese | WL Evaluation Services
P.1008021 | O.1008021.01 | A.1008021.01.10 | TECH ACCESS CTSCO 1 | CARBON TRANSPORT AND STORAGE CORPORATION (CTSCO) PTY LIMITED | WEST MOONIE 1 | EASTERNWELL 101 | J.24.022186 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2024-01-06 |  | 2024-01-07 | 2024-01-09 23:59 |  |  | Roma WL | KKeese | 2023-12-30 08:24 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 |  |  |  |  | 8.3 | 0 | 0 | 0 | 2.5 |  | 0 | [7 empty] | Kelly Keese | WL Evaluation Services
P.1008021 | O.1008021.01 | A.1008021.01.05 | CTSCO TD Section | CARBON TRANSPORT AND STORAGE CORPORATION (CTSCO) PTY LIMITED | WEST MOONIE 1 | EASTERNWELL 101 | J.23.085256 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2023-09-17 | 2023-09-15 | 2023-09-18 | 2023-09-20 23:59 | 2023-09-21 |  | Roma WL | KKeese | 2023-08-28 10:52 | KKeese |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 | 0 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1008021 | O.1008021.01 | A.1008021.01.02 | TD Logging | CARBON TRANSPORT AND STORAGE CORPORATION (CTSCO) PTY LIMITED | West Moonie 1 | EASTERNWELL 101 | J.20.063654 | RPE | ES-OH-Ops | Low | Operationally Complete | Execute - PSD |  | In Progress | Not Started | In Progress | 2020-09-08 | 2020-09-07 |  | 2020-09-08 | 2020-09-12 23:59 |  | 2020-09-13 23:59 | Roma WL | MRony2 | 2022-10-03 15:03 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 157431.77 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1008021 | O.1008021.01 | A.1008021.01.03 | 8.5in Logging | CARBON TRANSPORT AND STORAGE CORPORATION (CTSCO) PTY LIMITED | West Moonie 2 | EASTERNWELL 101 | J.21.109438 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-07-17 23:00 | 2021-07-17 10:00 |  | 2021-07-18 10:00 | 2021-07-23 09:59 |  | 2021-07-23 22:59 | Roma WL | MSchvartz | 2022-10-03 15:03 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 579941.52 | 4 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1008021 | O.1008021.01 | A.1008021.01.01 | Intermedaite section logging | CARBON TRANSPORT AND STORAGE CORPORATION (CTSCO) PTY LIMITED | West Moonie 1 | EASTERNWELL 101 | J.20.063554 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-14 |  | 2020-08-15 | 2020-08-17 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 15756.99 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1007923 | O.1007923.01 | A.1007923.01.01 | July Ops | JADESTONE ENERGY (AUSTRALIA) PTY LTD | STAG 37H |  | J.20.063034 | RPI | PS-SLK-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-23 |  | 2020-07-27 | 2020-08-25 23:59 |  |  | New Burn WL | frosa2 | 2022-10-03 09:49 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 148370 | [10 empty] | 0 | [7 empty] | Luis Cardenas | Wireline Slickline
P.1007732 | O.1007732.01 | A.1007732.01.01 | P&A | BRIDGEPORT ENERGY LIMITED |  |  | J.22.110252 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-08-18 |  | 2022-08-19 | 2022-08-20 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1007542 | O.1007542.01 | A.1007542.01.03 | Sav 64 UCI | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri South 105 | SAVANNA DRILLING #64 | J.20.063546 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-06-26 |  | 2020-06-26 | 2020-06-27 23:59 |  |  | Roma WL | SClark17 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 24455.04 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1007542 | O.1007542.01 | A.1007542.01.02 | Sav 64 UCI | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri 122, Condabri 123 | SAVANNA DRILLING #64 | J.20.063544 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-06-20 |  | 2020-06-20 | 2020-06-21 23:59 |  |  | Roma WL | SClark17 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 24455.04 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1007542 | O.1007542.01 | A.1007542.01.01 | UCI | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri 122 | SAVANNA DRILLING #64 | J.20.063543 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-18 |  | 2020-06-18 | 2020-06-19 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 24455.04 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1007477 | O.1007477.01 | A.1007477.01.01 | Plug sell | SANTOS LIMITED | FV18-35 1 |  | J.20.063540 | RPI | PS-WL-NO | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-06-10 |  | 2020-06-10 | 2020-06-15 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 3248.86 |  |  | L0 - No RO |  | 50 | 33.3 | 100 | 75 | 57.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1007132 | O.1007132.02 | A.1007132.02.02 | DNRME ¦ NB01D ¦ 6.125in Section ¦ MDT-GR | SILVER CITY DRILLING | NB01D | Silver City 4 | J.20.063538 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-23 12:00 |  | 2020-06-23 20:00 | 2020-06-25 19:59 |  |  | Roma WL | EBrobbey | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 45019.49 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1007132 | O.1007132.02 | A.1007132.02.03 | DNRME I NB04D I 6.125in Section i MDT-GR | SILVER CITY DRILLING | NB04D | Silver City 4 | J.20.063535 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Required | In Progress |  | 2020-06-28 12:00 |  | 2020-06-28 20:00 | 2020-06-30 19:59 |  |  | Roma WL | EDelange | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 45019.49 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1007132 | O.1007132.02 | A.1007132.02.04 | DNRME I NB03D I 6.125in Section I MDT-GR | SILVER CITY DRILLING | NB03 | Silver City 4 | J.20.063533 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-03 12:00 |  | 2020-07-03 20:00 | 2020-07-05 19:59 |  |  | Roma WL | EDelange | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 45019.49 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1007132 | O.1007132.02 | A.1007132.02.01 | DNRME ¦ NB02D ¦ 6.125in Section ¦ MDT | SILVER CITY DRILLING | NB02D | Silver City 4 | J.20.063530 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-10 12:00 |  | 2020-06-10 20:00 | 2020-06-12 19:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 45019.49 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1006876 | O.1006876.01 | A.1006876.01.01 | People to MI and WS | SCHLUMBERGER APG |  |  | J.20.063033 | RPI | PS-SLK-NO | Medium | Cancelled | Close - PSD |  | In Progress | Not Required | In Progress |  | 2020-05-24 |  | 2020-05-24 | 2020-06-30 23:59 |  |  | New Burn WL | frosa2 | 2022-10-03 09:49 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | Wireline Slickline
P.1006876 | O.1006876.01 | A.1006876.01.02 | Q3 people | SCHLUMBERGER APG |  |  | J.20.063032 | RPI | PS-WL-NO | InComplete | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-01 |  | 2020-07-31 | 2020-09-30 23:59 |  |  | New Burn WL | frosa2 | 2022-10-03 09:49 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1006763 | O.1006763.01 | A.1006763.01.01 | September Ops | NEWCREST MINING LIMITED - LIHIR GOLD MINE |  |  | J.20.063610 | RPI | PS-WL-NO | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-08-26 |  | 2020-08-26 | 2020-09-25 23:59 |  |  | Port Moresby WL | LParedes | 2022-10-03 13:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1006755 | O.1006755.01 | A.1006755.01.01 | Black Watch 1 Rechargeable | BEACH ENERGY LTD | Black Watch-1 | ENSIGN 931 | J.20.062966 | RPE | ES-OH-NO | Medium | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-05-17 |  | 2020-07-03 | 2020-07-11 23:59 |  |  | Moomba WL | IWahbi | 2022-10-03 11:02 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1006703 | O.1006703.03 | A.1006703.03.01 | Cased hole density | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Reedy Creek 183, Reedy Creek 182 | SAVANNA DRILLING #70 | J.21.109071 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-10-04 |  | 2021-10-04 23:00 | 2021-10-05 14:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 1 |  |  |  | 58.3 | 50 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1006703 | O.1006703.02 | A.1006703.02.01 | Plug_recharge | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | COMBABULA 85 | SAVANNA DRILLING #70 | J.20.063508 | RPI | PS-WL-NO | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-06-14 |  | 2020-06-14 | 2020-06-18 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 8359.32 |  |  | L0 - No RO |  | 50 | 33.3 | 100 | 75 | 57.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1006703 | O.1006703.01 | A.1006703.01.09 | UCI 3rd well_CON202_MPC4 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri 202 | SAVANNA DRILLING #70 | J.20.063653 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-06-11 05:00 | 2020-06-09 |  | 2020-06-11 05:00 | 2020-06-13 04:59 |  | 2020-06-13 04:59 | Roma WL | MRony2 | 2022-10-03 15:03 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 50960.56 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1006703 | O.1006703.01 | A.1006703.01.02 | UCI | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #70 | J.20.063652 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-07-09 |  | 2020-07-10 | 2020-07-11 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 15:03 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 |  |  |  |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1006703 | O.1006703.01 | A.1006703.01.11 | UCI 5th well | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri North 095 | SAVANNA DRILLING #70 | J.20.063651 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress | 2020-06-19 22:00 | 2020-06-19 10:00 |  | 2020-06-19 22:00 | 2020-06-21 21:59 |  | 2020-06-21 21:59 | Roma WL | ZWahid | 2022-10-03 15:03 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 24455.04 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1006703 | O.1006703.01 | A.1006703.01.08 | UCI_2nd well_COM218 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Combabula 218 | SAVANNA DRILLING #70 | J.20.063650 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-06-05 12:00 | 2020-06-05 10:00 |  | 2020-06-05 12:00 | 2020-06-07 11:59 |  | 2020-06-07 11:59 | Roma WL | MRony2 | 2022-10-03 15:02 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 24455.04 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1006703 | O.1006703.01 | A.1006703.01.14 | UCI | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri North 42 | SAVANNA DRILLING #70 | J.20.063649 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress | 2020-06-28 12:00 | 2020-06-28 10:00 |  | 2020-06-28 12:00 | 2020-06-29 10:23 |  | 2020-07-10 11:59 | Roma WL | SClark17 | 2022-10-03 15:02 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 24455.04 |  |  |  |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1006703 | O.1006703.01 | A.1006703.01.15 | Origin UCI | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri North 22 | SAVANNA DRILLING #70 | J.20.063527 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-06-29 10:00 |  | 2020-06-29 12:00 | 2020-06-30 10:23 |  |  | Roma WL | SClark17 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 24455.04 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1006703 | O.1006703.01 | A.1006703.01.07 | UCI_1st well_COM085 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Combabula 85 | SAVANNA DRILLING #70 | J.20.063524 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress |  | 2020-05-30 16:00 |  | 2020-06-01 | 2020-06-02 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 24455.04 |  |  |  |  | 66.7 | 50 | 0 | 50 | 50 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1006703 | O.1006703.01 | A.1006703.01.12 | UCI | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri North 082 | SAVANNA DRILLING #70 | J.20.063519 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-06-24 10:00 |  | 2020-06-24 12:00 | 2020-06-25 10:23 |  |  | Roma WL | ZWahid | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 24455.04 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1006703 | O.1006703.01 | A.1006703.01.05 | UCI | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #70 | J.22.110244 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-09-21 |  | 2022-09-22 | 2022-09-23 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 |  |  |  |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1006703 | O.1006703.01 | A.1006703.01.16 | Origin UCI | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri 237 | SAVANNA DRILLING #70 | J.20.063513 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-06-30 10:00 |  | 2020-06-30 12:00 | 2020-07-01 10:23 |  |  | Roma WL | SClark17 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 24455.04 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1006703 | O.1006703.01 | A.1006703.01.03 | UCI | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #70 | J.22.110243 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-08-25 |  | 2022-08-26 | 2022-08-27 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 |  |  |  |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1006703 | O.1006703.01 | A.1006703.01.01 | UCI | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #70 | J.20.063504 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-07-02 |  | 2020-07-03 | 2020-07-04 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 |  |  |  |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1006703 | O.1006703.01 | A.1006703.01.10 | UCI 4th well _CON073 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri 73 | SAVANNA DRILLING #70 | J.20.063501 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress |  | 2020-06-13 16:00 |  | 2020-06-13 18:00 | 2020-06-15 17:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 24455.04 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1006703 | O.1006703.01 | A.1006703.01.13 | Origin UCI | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri 012 | SAVANNA DRILLING #70 | J.20.063498 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-06-28 10:00 |  | 2020-06-28 12:00 | 2020-06-29 10:23 |  |  | Roma WL | SClark17 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 24455.04 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1006703 | O.1006703.01 | A.1006703.01.06 | UCI | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #70 | J.22.110240 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-09-28 |  | 2022-09-29 | 2022-09-30 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 |  |  |  |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1006703 | O.1006703.01 | A.1006703.01.04 | UCI | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #70 | J.22.110239 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-08-31 |  | 2022-09-01 | 2022-09-02 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 |  |  |  |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1006697 | O.1006697.01 | A.1006697.01.01 | OH logging | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Carinya 11 | Ensign 958 | J.20.063522 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-09 13:00 |  | 2020-09-09 16:00 | 2020-09-19 15:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 1115611.44 |  |  |  |  | 50 | 50 | 0 | 50 | 45 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1006697 | O.1006697.01 | A.1006697.01.02 | Carinya 11_Intermediate_8.75in_AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Carinya 11 | Ensign 958 | J.20.063515 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-01 16:00 |  | 2020-09-02 08:00 | 2020-09-04 02:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 16530.21 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1006696 | O.1006696.01 | A.1006696.01.01 | micro seismic | ANGLO AMERICAN AUSTRALIA LTD |  |  | J.22.110242 | RPE | ES-OH-Ops | InComplete | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-11-10 |  | 2022-11-16 | 2022-11-23 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1006557 | O.1006557.02 | A.1006557.02.01 | Non-OPS | SANTOS LIMITED | FAIRVIEW 532 | EASTERNWELL 24 | J.20.063582 | RPI | PS-WL-NO | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-12-08 |  | 2020-12-08 | 2020-12-11 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 5198.18 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1006557 | O.1006557.01 | A.1006557.01.01 | RM49-43-1 | SANTOS LIMITED | RM49-43-1 | EASTERNWELL 24 | J.20.063648 | RPE | ES-CH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-05-10 14:00 | 2020-05-09 |  | 2020-05-10 14:00 | 2020-05-11 14:00 |  | 2020-05-11 14:00 | Roma WL | MRony2 | 2022-10-03 15:02 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 6660.17 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1006557 | O.1006557.01 | A.1006557.01.02 | RM49-45-1 | SANTOS LIMITED | RM49-45-1 | EASTERNWELL 24 | J.20.063491 | RPE | ES-CH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-13 |  | 2020-05-14 14:00 | 2020-05-15 14:00 |  |  | Roma WL | ZWahid | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 12670.57 |  |  |  |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1006556 | O.1006556.01 | A.1006556.01.01 | RE 006_OH | CADIA HOLDINGS PTY LTD | RE 006 | EASTERNWELL 103 | J.20.063488 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-12 |  | 2020-05-13 | 2020-05-16 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 57082.52 |  |  |  |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1006183 | O.1006183.02 | A.1006183.02.01 | May ops and rentals | CHEVRON APG ABU PERTH. | Well #1 |  | J.20.063031 | RPI | PS-SLK-NO | InComplete | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-04-16 |  | 2020-04-29 | 2020-06-25 |  |  | New Burn WL | FDPSystemUser | 2022-10-03 09:49 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | Wireline Slickline
P.1006183 | O.1006183.01 | A.1006183.01.01 | May ops and rentals | CHEVRON APG ABU PERTH. | BWI CO2 Injection Wells |  |  | RPI | PS-SLK-NO | InComplete | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-04-16 |  | 2020-04-29 | 2020-05-25 |  |  | New Burn WL | frosa2 | 2020-12-23 02:48 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | Wireline Slickline
P.1006183 | O.1006183.01 | A.1006183.01.02 | jun Rentals | CHEVRON APG ABU PERTH. | BWI CO2 Injection Wells |  |  | RPI | PS-SLK-NO | Low | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-06-07 |  | 2020-06-07 | 2020-06-25 23:59 |  |  | New Burn WL | frosa2 | 2020-12-23 02:48 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 67042.5 | [10 empty] | 0 | [7 empty] | Luis Cardenas | Wireline Slickline
P.1006099 | O.1006099.01 | A.1006099.01.11 | MPBT-DB on Vali 2 | VINTAGE ENERGY LTD | VALI 2 |  | J.23.170170 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-12-02 | 2023-12-01 |  | 2023-12-02 | 2023-12-03 23:59 |  | 2023-12-03 23:59 | Moomba WL | ymoradi2 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 80620.53 | 1 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1006099 | O.1006099.01 | A.1006099.01.10 | Vali1 ST1 Perfo | VINTAGE ENERGY LTD | VALI 1ST1 |  | J.22.109945 | RPI | PS-WL-Ops | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2022-07-05 |  | 2022-07-06 | 2022-07-07 23:59 |  |  | Moomba WL | RTwigg | 2022-10-03 12:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1006099 | O.1006099.01 | A.1006099.01.09 | Odin-1 Packer Set | VINTAGE ENERGY LTD | ODIN 001 |  | J.22.109944 | RPI | PS-WL-Ops | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2022-07-02 |  | 2022-07-03 | 2022-07-04 23:59 |  |  | Moomba WL | RTwigg | 2022-10-03 12:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1006099 | O.1006099.01 | A.1006099.01.08 | Vali-3 Packer Setting and Perfo | VINTAGE ENERGY LTD | VALI-3 |  | J.22.109943 | RPI | PS-WL-Ops | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2022-06-30 |  | 2022-07-01 | 2022-07-02 23:59 |  |  | Moomba WL | RTwigg | 2022-10-03 12:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1006099 | O.1006099.01 | A.1006099.01.07 | Vali-2 Packer Setting and Perfo | VINTAGE ENERGY LTD | VALI 2 |  | J.22.109942 | RPI | PS-WL-Ops | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2022-06-26 |  | 2022-06-29 | 2022-06-30 23:59 |  |  | Moomba WL | RTwigg | 2022-10-03 12:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1006099 | O.1006099.01 | A.1006099.01.06 | Vali 3 SCMT | VINTAGE ENERGY LTD | VALI-3 |  | J.21.108811 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-12-23 | 2021-12-22 |  | 2021-12-23 | 2021-12-25 23:59 |  | 2021-12-25 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 11:53 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1006099 | O.1006099.01 | A.1006099.01.05 | Vali 2 SCMT | VINTAGE ENERGY LTD | VALI-2 |  | J.21.108809 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-23 23:59 |  | 2021-12-23 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 11:53 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | 2 |  |  |  | 83.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1006099 | O.1006099.01 | A.1006099.01.04 | Perforation Odin 1 | VINTAGE ENERGY LTD | Odin 1 |  | J.21.108767 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-26 | 2021-10-21 | 2021-10-25 | 2021-10-26 | 2021-10-26 23:59 | 2021-10-31 | 2021-10-27 23:59 | Moomba WL | ymoradi2 | 2022-10-03 11:39 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1006099 | O.1006099.01 | A.1006099.01.03 | Odin1-SCMT | VINTAGE ENERGY LTD | Odin 1 |  | J.21.108757 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-10-09 | 2021-10-08 | 2021-10-08 | 2021-10-09 | 2021-10-09 23:59 | 2021-10-14 | 2021-10-10 23:59 | Moomba WL | YLee25 | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 21358.02 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1006099 | O.1006099.01 | A.1006099.01.02 | Vali-1 ST1 Packer Tail Pipe | VINTAGE ENERGY LTD | Vali-1 ST-1 |  | J.20.062965 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-10-16 18:00 | 2020-10-14 18:00 | 2020-10-16 | 2020-10-16 18:00 | 2020-10-23 18:00 | 2020-10-24 | 2020-10-23 18:00 | Moomba WL | AHermawan | 2022-10-03 11:02 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 |  |  |  |  | 75 | 50 | 0 | 62.5 | 56.3 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1006099 | O.1006099.01 | A.1006099.01.01 | Vali-1 CBL-VDL | VINTAGE ENERGY LTD | Vali - 1 |  | J.20.062964 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-05-19 18:30 | 2020-05-20 23:00 | 2020-05-20 | 2020-05-20 23:00 | 2020-05-23 23:00 | 2020-05-24 | 2020-05-23 04:00 | Moomba WL | MAl-wakeel | 2022-10-03 11:02 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005812 | O.1005812.01 | A.1005812.01.01 | March Rentals | ESSO AUSTRALIA LTD |  | Ocean Monarch | J.20.063030 | RPE | ES-OH-NO | InComplete | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-03-20 |  | 2020-03-20 | 2020-03-25 |  |  | New Burn WL | frosa2 | 2022-10-03 09:49 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 28347.95 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1005789 | O.1005789.01 | A.1005789.01.01 | TCP Shoot and Pull | CHEVRON APG ABU PERTH. | GORGON PLANT CO2 WATER INJECTION WELL D-WI1 | RIGLESS - AUSTRALIA | J.20.062344 | RPI | TCP-TEMP-JOB | InComplete | Confirmed | Prepare - Mob |  | Not Started | In Progress | In Progress |  | 2020-05-01 |  | 2020-05-01 | 2020-06-01 |  |  | APG TS | MSwara | 2024-11-19 20:07 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 211336.24 |  |  |  |  | 41.7 | 16.7 | 0 | 25 | 25 |  | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TCP-Tubing-Conveyed Perforation
P.1005752 | O.1005752.01 | A.1005752.01.01 | March Operations | JADESTONE ENERGY (EAGLE) PTY LTD |  | Montara Oil Platform | J.20.063029 | RPI | PS-SLK-NO | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-03-16 |  | 2020-03-16 | 2020-03-25 |  |  | New Burn WL | frosa2 | 2022-10-03 09:49 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | Wireline Slickline
P.1005722 | O.1005722.01 | A.1005722.01.01 | Gular-1 | AGR (AUSTRALIA) PTY LTD |  | Noble Tom Prosser | J.20.063028 | RPE | ES-OH-NO | InComplete | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-03-14 |  | 2020-03-18 | 2020-03-24 |  |  | New Burn WL | LParedes | 2022-10-03 09:48 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1005719 | O.1005719.01 | A.1005719.01.01 | Sculpin-1 | ESSO AUSTRALIA LTD |  | Ocean Monarch | J.20.063027 | RPE | ES-OH-NO | InComplete | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-03-14 |  | 2020-03-18 | 2020-03-24 |  |  | New Burn WL | LParedes | 2022-10-03 09:48 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1005313 | O.1005313.01 | A.1005313.01.01 | DMR 758 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Durham Ranch 758 | EASTERNWELL 101 | J.20.063579 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-09 |  | 2020-03-09 | 2020-03-10 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 29156.78 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1005156 | O.1005156.02 | A.1005156.02.31 | Gidgealpa wells Integrity Logging | SANTOS LIMITED | GIDGEALPA 1 | Rigless Australia - 1 | J.22.137334 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-01-17 | 2023-01-16 |  | 2023-01-17 | 2023-02-15 23:59 |  | 2023-01-19 23:59 | Moomba WL | miqbal13 | 2023-02-02 13:30 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.30 | Gidgealpa 1/Gidgealpa 6 | SANTOS LIMITED | Gidgealpa 1, Gidgealpa 6, GIDGEALPA 10 | Rigless Australia - 1 | J.22.110089 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-08-23 08:00 | 2022-08-22 08:00 |  | 2022-08-23 08:00 | 2022-09-17 23:59 |  | 2022-09-17 23:59 | Moomba WL | ADuong4 | 2022-10-03 12:39 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.29 | Leghorn 2 - CBL-VDL | SANTOS LIMITED | Leghorn 2 | Rigless Australia - 1 | J.21.108658 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-08-19 06:00 | 2021-08-18 | 2021-08-19 | 2021-08-19 06:00 | 2021-08-22 23:59 | 2021-08-23 | 2021-08-22 23:59 | Moomba WL | ADuong4 | 2022-10-03 11:26 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 5589.99 | 2 |  |  |  | 91.7 | 66.7 | 100 | 75 | 80 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.28 | Well #27 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108632 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2021-09-23 23:00 | 2021-09-24 | 2021-09-24 | 2021-09-24 | 2021-09-26 23:59 | 2021-09-27 | 2021-09-26 22:59 | Moomba WL | IWahbi | 2022-10-03 11:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.27 | Well #26 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108631 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2021-09-17 23:00 | 2021-09-18 | 2021-09-18 | 2021-09-18 | 2021-09-20 23:59 | 2021-09-21 | 2021-09-20 22:59 | Moomba WL | IWahbi | 2022-10-03 11:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.26 | Well #25 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108630 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2021-09-11 23:00 | 2021-09-12 | 2021-09-12 | 2021-09-12 | 2021-09-14 23:59 | 2021-09-15 | 2021-09-14 22:59 | Moomba WL | IWahbi | 2022-10-03 11:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.25 | Well #24 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108629 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2021-09-05 23:00 | 2021-09-06 | 2021-09-06 | 2021-09-06 | 2021-09-08 23:59 | 2021-09-09 | 2021-09-08 22:59 | Moomba WL | IWahbi | 2022-10-03 11:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.24 | Well #23 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108628 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2021-08-30 23:00 | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-09-02 23:59 | 2021-09-03 | 2021-09-02 22:59 | Moomba WL | IWahbi | 2022-10-03 11:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.23 | Well #22 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108627 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2021-08-24 23:00 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-27 23:59 | 2021-08-28 | 2021-08-28 00:59 | Moomba WL | IWahbi | 2022-10-03 11:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.22 | Well #21 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108626 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2021-08-18 23:00 | 2021-08-19 | 2021-08-19 | 2021-08-19 | 2021-08-21 23:59 | 2021-08-22 | 2021-08-22 00:59 | Moomba WL | IWahbi | 2022-10-03 11:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.21 | Well #20 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108625 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2021-08-12 23:00 | 2021-08-13 | 2021-08-13 | 2021-08-13 | 2021-08-15 23:59 | 2021-08-16 | 2021-08-16 00:59 | Moomba WL | IWahbi | 2022-10-03 11:23 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.20 | Well #20 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108624 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2021-08-06 23:00 | 2021-08-07 | 2021-08-07 | 2021-08-07 | 2021-08-09 23:59 | 2021-08-10 | 2021-08-10 00:59 | Moomba WL | IWahbi | 2022-10-03 11:23 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.19 | Well #19 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108623 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2021-07-31 23:00 | 2021-08-01 | 2021-08-01 | 2021-08-01 | 2021-08-03 23:59 | 2021-08-04 | 2021-08-04 00:59 | Moomba WL | IWahbi | 2022-10-03 11:23 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.18 | Well #18 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108622 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2021-07-25 23:00 | 2021-07-26 | 2021-07-26 | 2021-07-26 | 2021-07-28 23:59 | 2021-07-29 | 2021-07-29 00:59 | Moomba WL | IWahbi | 2022-10-03 11:23 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.17 | Well #17 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108523 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Required | In Progress | 2021-07-19 23:00 | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-07-22 23:59 | 2021-07-23 | 2021-07-23 00:59 | Moomba WL | IWahbi | 2022-10-03 11:13 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.16 | Well #16 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108522 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Required | In Progress | 2021-07-13 23:00 | 2021-07-14 | 2021-07-14 | 2021-07-14 | 2021-07-16 23:59 | 2021-07-17 | 2021-07-17 00:59 | Moomba WL | IWahbi | 2022-10-03 11:13 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.15 | Well #15 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108521 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Required | In Progress | 2021-07-07 23:00 | 2021-07-08 | 2021-07-08 | 2021-07-08 | 2021-07-10 23:59 | 2021-07-11 | 2021-07-11 00:59 | Moomba WL | IWahbi | 2022-10-03 11:13 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.14 | Well #14 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108520 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Required | In Progress | 2021-07-01 23:00 | 2021-07-02 | 2021-07-02 | 2021-07-02 | 2021-07-04 23:59 | 2021-07-05 | 2021-07-05 00:59 | Moomba WL | IWahbi | 2022-10-03 11:13 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | 0 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.13 | Well #13 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108519 | RPI | PS-WL-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Required | In Progress | 2021-06-25 23:00 | 2021-06-26 | 2021-06-26 | 2021-06-26 | 2021-06-28 23:59 | 2021-06-29 | 2021-06-29 00:59 | Moomba WL | IWahbi | 2022-10-03 11:13 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.12 | Well #12 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108518 | RPI | PS-WL-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Required | In Progress | 2021-06-19 23:00 | 2021-06-20 | 2021-06-20 | 2021-06-20 | 2021-06-22 23:59 | 2021-06-23 | 2021-06-23 00:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:13 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.11 | Well #11 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108517 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-06-13 23:00 | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-06-16 23:59 | 2021-06-17 | 2021-06-17 00:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:12 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.10 | Well #10 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108516 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-06-09 | 2021-06-08 23:00 | 2021-06-08 | 2021-06-08 23:00 | 2021-06-11 22:59 | 2021-06-11 | 2021-06-11 23:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:12 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.09 | Well #9 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108515 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-06-03 | 2021-06-02 23:00 | 2021-06-02 | 2021-06-02 23:00 | 2021-06-05 22:59 | 2021-06-05 | 2021-06-05 23:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:12 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.08 | Well #8 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108514 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-05-28 | 2021-05-27 23:00 | 2021-05-27 | 2021-05-27 23:00 | 2021-05-30 22:59 | 2021-05-30 | 2021-05-30 23:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:12 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.07 | Well #7 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108513 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-05-22 | 2021-05-21 23:00 | 2021-05-21 | 2021-05-21 23:00 | 2021-05-24 22:59 | 2021-05-24 | 2021-05-24 23:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:12 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.06 | Well #6 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108512 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-05-15 23:00 | 2021-05-15 23:00 | 2021-05-15 23:00 | 2021-05-15 23:00 | 2021-05-18 22:59 | 2021-05-19 | 2021-05-18 23:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:12 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.05 | Well #5 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108511 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-05-09 23:00 | 2021-05-09 23:00 | 2021-05-09 23:00 | 2021-05-09 23:00 | 2021-05-12 22:59 | 2021-05-12 23:00 | 2021-05-12 22:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:12 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.04 | Well #4 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108510 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-05-02 23:00 | 2021-05-03 | 2021-05-02 23:00 | 2021-05-03 | 2021-05-05 23:59 | 2021-05-05 23:00 | 2021-05-05 22:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:12 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.03 | Anna North 3_Dirft, Spent Gun, SCMT | SANTOS LIMITED | Anna North 3 | Rigless Australia - 1 | J.21.108509 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-04-27 | 2021-04-27 | 2021-04-27 | 2021-04-27 | 2021-04-29 23:59 | 2021-04-30 | 2021-04-29 23:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:12 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.02 | Moomba 259 | SANTOS LIMITED | Moomba 259 | Rigless Australia - 1 | J.21.108508 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-03-17 12:00 | 2021-03-17 12:00 | 2021-03-17 | 2021-03-17 12:00 | 2021-03-20 11:59 | 2021-03-21 | 2021-03-20 11:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:12 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6669.6 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.02 | A.1005156.02.01 | Moomba 260 | SANTOS LIMITED | Moomba 260 | Rigless Australia - 1 | J.21.108507 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-03-16 15:00 | 2021-03-16 15:00 | 2021-03-16 15:00 | 2021-03-16 15:00 | 2021-03-19 14:59 | 2021-03-19 15:00 | 2021-03-19 14:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6669.6 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.01 | A.1005156.01.13 | Cancelled | SANTOS LIMITED | BARROLKA 26 | Rigless Australia - 1 | J.22.109950 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-07-03 10:18 | 2022-07-03 |  | 2022-07-04 | 2022-07-10 18:00 |  | 2022-07-10 18:00 | Moomba WL | JMoraes2 | 2022-10-03 12:26 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1005156 | O.1005156.01 | A.1005156.01.03 | SCMT-3 | SANTOS LIMITED | Jarrar 7 | Rigless Australia - 1 | J.20.062963 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-03-01 15:30 | 2020-02-29 06:00 | 2020-03-04 | 2020-03-04 17:00 | 2020-03-05 18:00 | 2020-03-06 | 2020-03-04 21:30 | Moomba WL | ysaeedabadian | 2022-10-03 11:02 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 5478.19 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.01 | A.1005156.01.02 | SCMT-2 | SANTOS LIMITED | JARRAR 6 | Rigless Australia - 1 | J.20.062962 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-02-28 01:30 | 2020-02-28 06:00 | 2020-03-01 | 2020-03-01 06:00 | 2020-03-04 18:00 | 2020-03-05 | 2020-03-03 | Moomba WL | ysaeedabadian | 2022-10-03 11:02 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 10956.38 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.01 | A.1005156.01.06 | Cement Evaluation | SANTOS LIMITED | Hera 6 | Rigless Australia - 1 | J.20.062961 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-04-23 15:00 | 2020-04-25 | 2020-04-25 | 2020-04-25 06:00 | 2020-04-26 12:00 | 2020-04-27 | 2020-04-25 07:00 | Moomba WL | DKitney | 2022-10-03 11:02 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.01 | A.1005156.01.05 | Cement Evaluation | SANTOS LIMITED | Hera 5 | Rigless Australia - 1 | J.20.062960 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-04-22 06:00 | 2020-04-24 06:00 | 2020-04-24 | 2020-04-24 06:00 | 2020-04-25 | 2020-04-26 | 2020-04-23 09:00 | Moomba WL | DKitney | 2022-10-03 11:02 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.01 | A.1005156.01.10 | Wackett 5 SCMT | SANTOS LIMITED | Wackett 5 | Rigless Australia - 1 | J.20.062959 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress | 2020-05-29 | 2020-05-27 06:00 | 2020-05-31 | 2020-05-30 06:00 | 2020-06-01 06:00 | 2020-06-03 | 2020-06-02 08:00 | Moomba WL | MSchvartz | 2022-10-03 11:02 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.01 | A.1005156.01.04 | SCMT-4 | SANTOS LIMITED | JARRAR 8 | Rigless Australia - 1 | J.20.062958 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2020-03-03 02:38 | 2020-03-02 | 2020-03-04 | 2020-03-04 | 2020-03-10 18:00 | 2020-03-11 | 2020-03-10 07:30 | Moomba WL | ysaeedabadian | 2022-10-03 11:01 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 19103.31 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.01 | A.1005156.01.07 | CBL Jarrar 8 | SANTOS LIMITED | Jarrar 8 | Rigless Australia - 1 | J.20.062957 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Required | Not Started | In Progress |  | 2020-06-27 18:00 |  | 2020-06-30 | 2020-07-01 18:00 |  |  | Moomba WL | AHermawan | 2022-10-03 11:01 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.01 | A.1005156.01.08 | CBL | SANTOS LIMITED | Jarrar 8 | Rigless Australia - 1 | J.20.062956 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-07-02 | 2020-05-09 06:00 | 2020-07-04 | 2020-07-03 06:00 | 2020-07-04 06:00 | 2020-07-06 | 2020-07-05 08:00 | Moomba WL | AHermawan | 2022-10-03 11:01 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.01 | A.1005156.01.01 | SCMT | SANTOS LIMITED | Cougar East 1 | Rigless Australia - 1 | J.20.062955 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-02-28 22:30 | 2020-02-23 | 2020-03-01 | 2020-03-01 06:00 | 2020-03-06 18:00 | 2020-03-07 | 2020-03-05 10:30 | Moomba WL | ysaeedabadian | 2022-10-03 11:01 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 10324.7 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.01 | A.1005156.01.12 | Cooroo 7 SCMT | SANTOS LIMITED | Cooroo 7 (APP A) | Rigless Australia - 1 | J.20.062954 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-06-07 | 2020-06-08 06:00 | 2020-06-09 | 2020-06-08 06:00 | 2020-06-10 06:00 | 2020-06-12 | 2020-06-11 08:00 | Moomba WL | MSchvartz | 2022-10-03 11:01 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1005156 | O.1005156.01 | A.1005156.01.11 | Cooroo NW 5 SCMT | SANTOS LIMITED | Cooroo North West 5 | Rigless Australia - 1 | J.20.062953 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress | 2020-05-30 | 2020-05-31 06:00 | 2020-06-01 | 2020-05-31 06:00 | 2020-06-02 06:00 | 2020-06-04 | 2020-06-03 08:00 | Moomba WL | MSchvartz | 2022-10-03 11:01 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005156 | O.1005156.01 | A.1005156.01.09 | CBL | SANTOS LIMITED | Jarrar 8 | Rigless Australia - 1 | J.20.062952 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Required | Not Started | In Progress |  | 2020-06-28 |  | 2020-06-28 | 2020-06-30 06:00 |  |  | Moomba WL | AHermawan | 2022-10-03 11:01 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005107 | O.1005107.01 | A.1005107.01.01 | Logging Job MAUI-8 - OH | OMV NEW ZEALAND LTD | Maui-8 | COSLProspector | J.20.063596 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Not Required | Not Started | In Progress |  | 2020-05-25 |  | 2020-06-01 | 2020-06-30 |  |  | New Plymouth WL | PZuliani | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 22233.33 |  |  |  |  | 50 | 0 | 0 | 25 | 22.5 |  | 0 | [7 empty] | Paulo Zuliani | WL Evaluation Services
P.1005016 | O.1005016.02 | A.1005016.02.02 | Enterprise-1 WL PS | BEACH ENERGY LTD | Enterprise 1 | Easternwell 106 | J.20.062951 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-29 06:00 | 2020-11-12 18:00 | 2020-12-28 | 2020-12-29 06:00 | 2021-01-05 06:00 | 2021-01-05 | 2021-01-05 06:00 | Moomba WL | EBrobbey | 2022-10-03 11:01 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 532544.01 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005016 | O.1005016.02 | A.1005016.02.01 | Enterprise-1 - WL ES | BEACH ENERGY LTD | Enterprise 1 | Easternwell 106 | J.20.062947 | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2020-12-23 | 2020-10-27 | 2020-12-21 | 2020-12-23 | 2021-01-22 20:22 | 2021-01-22 | 2021-01-22 20:22 | Moomba WL | FDPSystemUser | 2022-10-03 11:00 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 455306.17 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1005016 | O.1005016.01 | A.1005016.01.02 | Tubing Cutter 2-3/8" | BEACH ENERGY LTD | Haselgrove-4 | Easternwell 106 | J.20.062950 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-03-22 03:00 | 2020-03-22 10:00 |  | 2020-03-23 | 2020-03-25 18:00 |  | 2020-04-17 12:30 | Moomba WL | eismail | 2022-10-03 11:01 | FDPSystemUser |  | No |  |  |  |  | Shannon Gilbert |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005016 | O.1005016.01 | A.1005016.01.04 | IBC - TCP Correlation | BEACH ENERGY LTD | Haselgrove-4 DW1 | Easternwell 106 | J.20.062949 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-06-01 | 2020-05-28 | 2020-05-29 | 2020-06-01 | 2020-06-30 23:59 | 2020-06-12 | 2020-06-30 23:59 | Moomba WL | RTwigg | 2022-10-03 11:00 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 72319.69 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005016 | O.1005016.01 | A.1005016.01.03 | Haselgrove 4 DW1 Rental | BEACH ENERGY LTD | Haselgrove-4 DW1 | Easternwell 106 | J.20.062948 | RPI | PS-WL-NO | Low | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-04-03 06:00 |  | 2020-07-04 | 2020-07-05 19:00 |  |  | Moomba WL | IWahbi | 2022-10-03 11:00 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 17316.44 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1005016 | O.1005016.01 | A.1005016.01.01 | Haselgrove-4 | BEACH ENERGY LTD | Haselgrove-4 | Easternwell 106 | J.20.062946 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-02-27 03:00 | 2020-02-20 | 2020-02-28 | 2020-02-28 | 2020-03-24 20:22 | 2020-04-01 | 2020-03-30 13:30 | Moomba WL | AGamero | 2022-10-03 11:00 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 118883.3 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1004974 | O.1004974.01 | A.1004974.01.01 | Rental for unit/Equipment | EXXONMOBIL PNG LIMITED | TRICERATOPS 2 | Superior Energy Rig 32 | J.20.063647 | RPI | PS-WL-NO | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2020-09-01 | 2020-09-01 |  | 2020-09-01 | 2021-03-31 |  | 2021-03-31 | Port Moresby WL | DGemmel | 2022-10-03 14:02 | FDPSystemUser |  | No |  |  |  |  | Danny Gemmell |  | 0 |  |  | L0 - No RO |  | 41.7 | 33.3 | 100 | 50 | 47.5 |  | 0 | [7 empty] | Danny Gemmell | WL Production Services
P.1004974 | O.1004974.01 | A.1004974.01.03 | August Ops | EXXONMOBIL PNG LIMITED | TRICERATOPS 2 | Superior Energy Rig 32 | J.20.063611 | RPI | PS-WL-NO | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2020-12-02 | 2020-10-26 |  | 2020-10-26 | 2021-02-25 |  | 2021-04-03 | Port Moresby WL | LParedes | 2022-10-03 13:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 33.3 | 100 | 50 | 47.5 |  | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1004974 | O.1004974.01 | A.1004974.01.04 | September Ops | EXXONMOBIL PNG LIMITED | TRICERATOPS 2 | Superior Energy Rig 32 | J.20.063609 | RPI | PS-WL-NO | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2020-09-01 | 2020-08-26 |  | 2020-08-26 | 2020-09-25 |  | 2020-10-01 | Port Moresby WL | LParedes | 2022-10-03 13:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 33.3 | 100 | 50 | 47.5 |  | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1004974 | O.1004974.01 | A.1004974.01.02 | Jul | EXXONMOBIL PNG LIMITED | TRICERATOPS 2 | Superior Energy Rig 32 | J.20.063602 | RPI | PS-WL-NO | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2020-09-01 | 2020-07-01 |  | 2020-07-01 | 2020-07-25 |  | 2020-09-25 | Port Moresby WL | LParedes | 2022-10-03 13:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 33.3 | 100 | 50 | 47.5 |  | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1004966 | O.1004966.01 | A.1004966.01.02 | Bauer North Namur (Dev 2) | BEACH ENERGY LTD |  | Saxon Rig 183 | J.20.062945 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-07-27 | 2020-07-27 | 2020-07-27 | 2020-07-27 | 2020-07-31 | 2020-08-01 | 2020-07-31 | Moomba WL | OBass | 2022-10-03 11:00 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1004966 | O.1004966.01 | A.1004966.01.01 | Bauer North Namur (Dev 1) | BEACH ENERGY LTD |  | Saxon Rig 183 | J.20.062944 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-07-19 | 2020-07-19 | 2020-07-19 | 2020-07-19 | 2020-07-23 | 2020-07-24 | 2020-07-23 | Moomba WL | OBass | 2022-10-03 11:00 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1004966 | O.1004966.01 | A.1004966.01.03 | Bauer North Namur (Dev 3) | BEACH ENERGY LTD |  | Saxon Rig 183 | J.20.062943 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-08-04 | 2020-08-04 | 2020-08-04 | 2020-08-04 | 2020-08-08 | 2020-08-09 | 2020-08-08 | Moomba WL | OBass | 2022-10-03 11:00 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1004928 | O.1004928.01 | A.1004928.01.02 | PS-2 | OMV NEW ZEALAND LTD |  | Maui B Platform | J.21.109089 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-07-08 |  | 2021-07-08 | 2021-07-12 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 16:19 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Paulo Zuliani | WL Production Services
P.1004928 | O.1004928.01 | A.1004928.01.01 | Explosives Sale | OMV NEW ZEALAND LTD | Maui-B5 | Maui B Platform | J.21.109088 | RPI | PS-WL-NO | Low | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-02-06 |  | 2021-02-07 | 2021-02-08 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 16:18 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 34119.51 | [10 empty] | 0 | [7 empty] | Paulo Zuliani | WL Production Services
P.1004926 | O.1004926.01 | A.1004926.01.01 | Kapuni | TODD ENERGY LIMITED | Kapuni 7 | RIGLESS - NEW ZEALAND | J.20.063591 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2020-03-10 |  | 2020-03-11 | 2020-03-18 |  |  | New Plymouth WL | VOliveira5 | 2022-10-03 16:18 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 78637.31 | [10 empty] | 0 | [7 empty] | Paulo Zuliani | WL Production Services
P.1004924 | O.1004924.01 | A.1004924.01.05 | Denison Yandina 6 and Sprinton 11 PNX | DENISON GAS | YANDINA 6, SPRINGTON 11 | RIGLESS - AUSTRALIA | J.25.140792 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-14 23:59 | 2025-09-21 | 2025-09-15 00:59 | Roma WL | CKok3 | 2025-09-15 09:16 | CKok3 |  | No |  |  |  | ROE WL Jakarta | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 100 | 50 | 75 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1004924 | O.1004924.01 | A.1004924.01.04 | Denison Yadina 6 PNX | DENISON GAS | YANDINA 6, SPRINGTON 11 | RIGLESS - AUSTRALIA | J.25.104811 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2025-07-19 | 2025-07-19 | 2025-07-19 | 2025-07-19 | 2025-07-25 23:59 | 2025-07-26 | 2025-07-26 00:59 | Roma WL | CKok3 | 2025-07-29 21:53 | SAli112 |  | No |  |  |  | ROE WL Jakarta | Irwan Wongso |  | 42446.91 | 1 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1004924 | O.1004924.01 | A.1004924.01.03 | Denison Sprinton 11 PNX | DENISON GAS |  | RIGLESS - AUSTRALIA | J.25.104809 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2025-07-05 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 2025-07-11 23:59 | 2025-07-12 | 2025-07-12 00:59 | Roma WL | CKok3 | 2025-07-24 08:25 | CKok3 |  | No |  |  |  |  | Irwan Wongso |  | 0 | 1 |  | L0 - No RO |  | 66.7 | 66.7 | 0 | 50 | 55 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1004924 | O.1004924.01 | A.1004924.01.02 | 2nd well | DENISON GAS |  | RIGLESS - AUSTRALIA | J.22.110260 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-01-27 22:00 |  | 2022-01-29 22:00 | 2022-01-30 22:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 | 0 |  |  |  | 25 | 33.3 | 0 | 25 | 25 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1004924 | O.1004924.01 | A.1004924.01.01 | Yellowbank 9 - SonicScanner | DENISON GAS | Yellowbank 9 | RIGLESS - AUSTRALIA | J.20.063529 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-11-03 06:00 |  | 2020-11-03 12:00 | 2020-11-04 12:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 18404.81 | 0 |  |  |  | 58.3 | 83.3 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1004923 | O.1004923.01 | A.1004923.01.01 | Microseimic | CADIA HOLDINGS PTY LTD | RE 006, RE 007, RE 008 | RIGLESS - AUSTRALIA | J.20.063578 | RPE | ES-CH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Required | In Progress |  | 2020-08-12 |  | 2020-08-18 | 2020-09-14 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 1093533.46 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004923 | O.1004923.01 | A.1004923.01.02 | Cancelled operation | CADIA HOLDINGS PTY LTD | RE 006 | RIGLESS - AUSTRALIA | J.20.063557 | RPE | ES-CH-NO | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-08-06 |  | 2020-08-06 | 2020-08-11 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 27818.71 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004922 | O.1004922.01 | A.1004922.01.06 | PEX-GPIT | GALILEE ENERGY LIMITED | KUMBARILLA CENTRAL 1 | SAVANNA DRILLING #406 | J.21.109437 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Close - PSD |  | In Progress | Not Started | In Progress | 2021-11-24 01:00 | 2021-11-23 10:00 |  | 2021-11-24 10:00 | 2021-11-25 14:00 |  | 2021-11-30 15:00 | Roma WL | MRony2 | 2022-10-03 15:02 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 0 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004922 | O.1004922.01 | A.1004922.01.03 | Galilee_KC3_PEX-HRLA-BHC-FMI_MDT | GALILEE ENERGY LIMITED | Kumbarilla Central 3 | SAVANNA DRILLING #406 | J.20.063646 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2020-04-25 05:00 | 2020-04-25 11:00 |  | 2020-04-26 11:00 | 2020-05-01 11:00 |  | 2020-04-30 15:00 | Roma WL | ZWahid | 2022-10-03 15:02 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 28947.37 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004922 | O.1004922.01 | A.1004922.01.02 | Galilee ¦ Kumbarilla Central 2 ¦ FMI-BHC-HRLA-PEX-SP | GALILEE ENERGY LIMITED | Kumbarilla Central 2 | SAVANNA DRILLING #406 | J.20.063575 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-19 08:00 |  | 2020-04-19 13:00 | 2020-04-24 13:00 |  |  | Roma WL | ZWahid | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 28947.37 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004922 | O.1004922.01 | A.1004922.01.09 | 4th well | GALILEE ENERGY LIMITED | Kumbarilla Central 1 | SAVANNA DRILLING #406 | J.22.110262 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-07-21 09:00 |  | 2022-07-22 09:00 | 2022-07-23 13:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004922 | O.1004922.01 | A.1004922.01.01 | Galilee ¦ Kumbarilla Central 1 ¦ BHC-GPIT-HRLA-PEX-SP | GALILEE ENERGY LIMITED | Kumbarilla Central 1 | SAVANNA DRILLING #406 | J.20.063570 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-08 10:00 |  | 2020-04-09 10:00 | 2020-04-15 14:00 |  |  | Roma WL | ZWahid | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 20240.42 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004922 | O.1004922.01 | A.1004922.01.08 | 3rd well | GALILEE ENERGY LIMITED | Kumbarilla Central 1 | SAVANNA DRILLING #406 | J.22.110258 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-06-16 09:00 |  | 2022-06-17 09:00 | 2022-06-18 13:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Kiwi McConkey |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004922 | O.1004922.01 | A.1004922.01.10 | 5th Well | GALILEE ENERGY LIMITED | Kumbarilla Central 1 | SAVANNA DRILLING #406 | J.22.110253 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-10-16 10:00 |  | 2022-10-17 10:00 | 2022-10-18 14:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004922 | O.1004922.01 | A.1004922.01.05 | Galilee 4Cbo 3 | GALILEE ENERGY LIMITED |  | SAVANNA DRILLING #406 | J.20.063550 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Not Required | Not Started | In Progress |  | 2020-05-30 11:00 |  | 2020-05-31 11:00 | 2020-06-05 11:00 |  |  | Roma WL | ZWahid | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004922 | O.1004922.01 | A.1004922.01.04 | Glenaras 17_PEX-HRLA-BHC-FMI_MDT-GR | GALILEE ENERGY LIMITED | Glenaras 17 | SAVANNA DRILLING #406 | J.20.063548 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Required | In Progress |  | 2020-05-01 11:00 |  | 2020-05-04 | 2020-05-17 |  |  | Roma WL | ZWahid | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 204954.52 |  |  |  |  | 66.7 | 50 | 0 | 50 | 50 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004922 | O.1004922.01 | A.1004922.01.07 | 2nd well | GALILEE ENERGY LIMITED | Kumbarilla Central 1 | SAVANNA DRILLING #406 | J.22.110251 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-07-08 11:00 |  | 2022-07-09 11:00 | 2022-07-10 15:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004921 | O.1004921.02 | A.1004921.02.02 | Prejob payment | DENISON GAS | PUNCHBOWL GULLY 2 | Ensign 48 | J.20.063645 | RPE | ES-OH-NO | Medium | Confirmed | Prepare - Mob |  | Design Completed | Not Started | In Progress | 2020-09-25 09:56 | 2020-09-24 08:00 |  | 2020-09-24 23:00 | 2020-09-30 22:59 |  | 2020-10-09 22:59 | Roma WL | MRony2 | 2022-10-03 15:02 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 98440.55 |  |  | L0 - No RO |  | 66.7 | 50 | 100 | 75 | 67.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004921 | O.1004921.02 | A.1004921.02.01 | Yellowbank9_Advance payment | DENISON GAS | YELLOWBANK 9 | Ensign 48 | J.20.063532 | RPE | ES-OH-NO | Low | Unconfirmed - 90% | Design - PSD |  | Not Started | Not Started | In Progress |  | 2020-09-14 |  | 2020-09-14 | 2020-09-23 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 98440.55 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004921 | O.1004921.01 | A.1004921.01.06 | QC | DENISON GAS |  | Ensign 48 | J.22.110895 | RPE | ES-CH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-07-16 23:00 | 2022-07-16 23:00 |  | 2022-07-16 23:00 | 2022-07-19 23:00 |  | 2022-07-20 23:00 | Roma WL | MRony2 | 2022-10-03 15:02 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 0 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004921 | O.1004921.01 | A.1004921.01.03 | PEX-MDT-FMI | DENISON GAS |  | Ensign 48 | J.22.110257 | RPE | ES-CH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-08-09 23:00 |  | 2022-08-09 23:00 | 2022-08-13 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004921 | O.1004921.01 | A.1004921.01.05 | QC | DENISON GAS |  | Ensign 48 | J.21.108999 | RPE | ES-CH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-07-29 23:00 |  | 2021-07-29 23:00 | 2021-08-01 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004921 | O.1004921.01 | A.1004921.01.04 | QC | DENISON GAS |  | Ensign 48 | J.21.108997 | RPE | ES-CH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-05-21 23:00 |  | 2021-05-21 23:00 | 2021-05-24 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004921 | O.1004921.01 | A.1004921.01.02 | Yellowbank 9 ¦ HRLA-PEX-ECS-SP ¦ FMI-SSCAN-PPC ¦ MDT-GR | DENISON GAS | Yellowbank 9 | Ensign 48 | J.20.063541 | RPE | ES-OH-NO | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-10-10 12:00 |  | 2020-10-10 23:00 | 2020-10-12 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 129983.75 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004921 | O.1004921.01 | A.1004921.01.01 | QC-FMI-SS-MDT | DENISON GAS | PUNCHBOWL GULLY 2 | Ensign 48 | J.20.063536 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2020-09-27 23:00 | 2020-09-26 23:00 |  | 2020-09-27 23:00 | 2020-10-02 23:00 |  | 2020-10-02 23:00 | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 110510.07 |  |  | L2 - Shift RO |  | 58.3 | 50 | 0 | 62.5 | 51.2 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004918 | O.1004918.01 | A.1004918.01.04 | Workover_June | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #69 | J.21.109006 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-09-10 |  | 2021-09-11 | 2021-09-13 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 | 0 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1004918 | O.1004918.01 | A.1004918.01.01 | Pipe Recovery_Mar | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #69 | J.21.108989 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-06-15 23:00 |  | 2021-06-16 23:00 | 2021-06-18 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004918 | O.1004918.01 | A.1004918.01.03 | Workover_May | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #69 | J.21.108985 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-06-29 |  | 2021-06-30 | 2021-07-02 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004918 | O.1004918.01 | A.1004918.01.02 | Workover_APril | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #69 | J.21.108981 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-06-28 23:00 |  | 2021-06-29 23:00 | 2021-07-01 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004917 | O.1004917.02 | A.1004917.02.01 | QC | QGC |  | Saxon Rig 165 | J.22.110255 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-07-10 |  | 2022-07-12 | 2022-07-13 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004917 | O.1004917.01 | A.1004917.01.01 | MDT 1st Well | QGC |  | Saxon Rig 165 | J.20.063568 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-10-28 |  | 2020-10-29 | 2020-10-31 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 |  |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004917 | O.1004917.01 | A.1004917.01.02 | 2nd well | QGC |  | Saxon Rig 165 | J.22.110254 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-08-11 23:00 |  | 2022-08-12 23:00 | 2022-08-14 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004816 | O.1004816.02 | A.1004816.02.01 | IBS Processing View | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | DURHAM RANCH 237 | Rigless Australia - 1 | J.20.063525 | RPI | PS-WL-NO | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-02-19 |  | 2020-02-19 | 2020-02-20 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 2599.09 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004816 | O.1004816.01 | A.1004816.01.05 | Carinya 11 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Carinya 11 | Rigless Australia - 1 | J.21.108994 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2021-06-16 |  | 2021-06-16 | 2021-06-19 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 28810.92 | 1 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1004816 | O.1004816.01 | A.1004816.01.01 | CBL Campaign in Dec | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 474, CON 475, CONDABRI 430, CONDABRI 431, CONDABRI 448, CONDABRI 463, CONDABRI 477, CONDABRI 476 | Rigless Australia - 1 | J.20.063520 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2020-11-19 |  | 2020-11-30 | 2020-12-14 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4191.03 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004816 | O.1004816.01 | A.1004816.01.04 | 2nd part of SCMT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 474, CON 475, CONDABRI 430, CONDABRI 431, CONDABRI 448, CONDABRI 463, CONDABRI 477, CONDABRI 476, CONDABRI 432, CONDABRI 471, Condabri North 368, Condabri North 370 | Rigless Australia - 1 | J.20.063517 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-12-04 |  | 2020-12-04 | 2020-12-14 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 7342.43 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004816 | O.1004816.01 | A.1004816.01.03 | CBL_Rigless | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | Rigless Australia - 1 | J.21.108972 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-06-20 21:00 |  | 2021-07-23 23:00 | 2021-08-06 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1004816 | O.1004816.01 | A.1004816.01.02 | CBL Rigless | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | Rigless Australia - 1 | J.21.108970 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-05-26 23:00 |  | 2021-06-29 01:00 | 2021-07-13 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004780 | O.1004780.03 | A.1004780.03.03 | Crane Rental CND39 DFIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI NORTH DEEP 39 | Rigless Australia - 1 | J.20.063644 | RPI | PS-WL-NO | InComplete | Confirmed | Execute - PSD |  | Not Started | Not Started | In Progress |  | 2020-03-16 |  | 2020-03-18 | 2020-03-19 |  |  | Roma WL | ZWahid | 2022-10-03 15:02 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 16644.74 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004780 | O.1004780.03 | A.1004780.03.01 | Crane Rental CND27 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI NORTH DEEP 27 | Rigless Australia - 1 | J.20.063642 | RPI | PS-WL-NO | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-02-24 |  | 2020-02-24 | 2020-02-25 |  |  | Roma WL | ZWahid | 2022-10-03 15:02 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 17989.6 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004780 | O.1004780.03 | A.1004780.03.02 | Crane rental for IBC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI NORTH DEEP 39 | Rigless Australia - 1 | J.20.063641 | RPI | PS-WL-NO | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-02-24 |  | 2020-02-24 | 2020-02-25 |  |  | Roma WL | MRony2 | 2022-10-03 15:01 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 17989.6 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004780 | O.1004780.02 | A.1004780.02.02 | Perforation and Plug | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri North Deep 27, CONDABRI NORTH DEEP 39 | Rigless Australia - 1 | J.20.063507 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-05-15 |  | 2020-05-17 | 2020-05-30 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 51199.25 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004780 | O.1004780.02 | A.1004780.02.03 | Perforation_Plug 2nd well | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI NORTH DEEP 39 | Rigless Australia - 1 | J.20.063505 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-05-28 |  | 2020-05-29 | 2020-06-11 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 51199.25 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004780 | O.1004780.02 | A.1004780.02.01 | DFIT - CND039 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI NORTH DEEP 39 | Rigless Australia - 1 | J.20.063502 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-02-22 12:00 |  | 2020-02-22 12:00 | 2020-03-05 06:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 55941.2 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004780 | O.1004780.01 | A.1004780.01.01 | Data processing | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI NORTH DEEP 39 | Rigless Australia - 1 | J.20.063643 | RPE | ES-OH-NO | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-02-05 |  | 2020-02-06 | 2020-02-07 |  |  | Roma WL | MRony2 | 2022-10-03 15:02 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 2599.09 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.37 | RCK221_QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #408 | J.21.109436 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2021-07-03 05:00 | 2021-06-30 20:00 |  | 2021-07-02 06:00 | 2021-07-02 16:00 |  | 2021-07-03 15:00 | Roma WL | MRony2 | 2022-10-03 15:01 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.13 | Origin ¦ Orana North 317 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 317 | SAVANNA DRILLING #408 | J.20.063640 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-04-11 12:00 | 2020-04-11 10:00 |  | 2020-04-11 22:00 | 2020-04-12 08:00 |  | 2020-04-11 22:00 | Roma WL | MRony2 | 2022-10-03 15:01 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.26 | Origin ¦ Reedy Creek 099 ¦ 8.75in Section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Reedy Creek 99 | SAVANNA DRILLING #408 | J.20.063585 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-24 20:00 |  | 2020-05-25 06:00 | 2020-05-25 16:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 |  |  |  |  | 33.3 | 50 | 0 | 50 | 40 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.21 | Origin ¦ Orana North 316 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 316 | SAVANNA DRILLING #408 | J.20.063583 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-06 15:00 |  | 2020-05-07 06:00 | 2020-05-07 16:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.05 | ORN 295 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | ORANA NORTH 295 | SAVANNA DRILLING #408 | J.20.063581 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Execute - PSD |  | In Progress | Not Started | In Progress | 2020-03-08 10:00 | 2020-03-23 10:00 |  | 2020-03-23 10:00 | 2020-03-23 20:00 |  | 2020-03-08 20:00 | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 4970.76 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.29 | Origin ¦ Reedy Creek 158 ¦ 8.75in Section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Reedy Creek 158 | SAVANNA DRILLING #408 | J.20.063576 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-05-30 20:00 |  | 2020-06-01 06:00 | 2020-06-01 16:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.06 | Orana North 301 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | ORANA NORTH 301 | SAVANNA DRILLING #408 | J.20.063571 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-25 |  | 2020-03-26 03:00 | 2020-03-27 13:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.24 | Origin ¦ Orana North 325 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 325 | SAVANNA DRILLING #408 | J.20.063566 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-10 16:00 |  | 2020-05-11 14:00 | 2020-05-12 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.07 | ORN300 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 300 | SAVANNA DRILLING #408 | J.20.063564 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-29 |  | 2020-03-30 10:00 | 2020-03-30 20:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.28 | Origin ¦ Reedy Creek South 034 ¦ 8.75in Section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Reedy Creek South 034 | SAVANNA DRILLING #408 | J.20.063562 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-28 20:00 |  | 2020-05-30 06:00 | 2020-05-30 16:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 |  |  |  |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.18 | Origin ¦ Orana North 323 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 323 | SAVANNA DRILLING #408 | J.20.063560 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-30 12:00 |  | 2020-04-30 23:00 | 2020-05-01 09:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.15 | CON428_QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri 428 | SAVANNA DRILLING #408 | J.20.063558 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-20 |  | 2020-04-21 05:00 | 2020-04-21 15:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.14 | Origin ¦ Condabri 426 ¦ AIT-PEX-GPIT_MDT-GR | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri 426 | SAVANNA DRILLING #408 | J.20.063555 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-15 08:00 |  | 2020-04-15 23:00 | 2020-04-18 09:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.04 | ORN294 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 294 | SAVANNA DRILLING #408 | J.20.063553 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-19 |  | 2020-03-19 22:00 | 2020-03-20 08:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.31 | Origin ¦ Reedy Creek 098 ¦ 8.75in Section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Reedy Creek 98 | SAVANNA DRILLING #408 | J.20.063552 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-04 20:00 |  | 2020-06-06 06:00 | 2020-06-06 16:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.25 | Origin ¦ Talinga 186 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Talinga 186 | SAVANNA DRILLING #408 | J.20.063549 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-13 12:00 |  | 2020-05-14 03:00 | 2020-05-14 13:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.17 | ORN314_QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 314 | SAVANNA DRILLING #408 | J.20.063547 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2020-04-28 12:00 |  | 2020-04-28 22:00 | 2020-04-29 08:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.32 | Origin ¦ Reedy Creek 129 ¦ 8.75in Section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Reedy Creek 129 | SAVANNA DRILLING #408 | J.20.063545 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-06 20:00 |  | 2020-06-08 06:00 | 2020-06-08 16:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.16 | Origin ¦ Condabri North 360 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri North 360 | SAVANNA DRILLING #408 | J.20.063542 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-23 |  | 2020-04-25 12:00 | 2020-04-25 22:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 |  |  |  |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.12 | Orana North 310 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 310 | SAVANNA DRILLING #408 | J.20.063539 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-09 10:00 |  | 2020-04-09 22:00 | 2020-04-10 08:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.27 | Origin ¦ Reedy Creek South 036 ¦ 8.75in Section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Reedy Creek South 036 | SAVANNA DRILLING #408 | J.20.063537 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-26 20:00 |  | 2020-05-28 06:00 | 2020-05-28 16:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.22 | Origin ¦ Orana North 327 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 327 | SAVANNA DRILLING #408 | J.20.063534 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-08 12:00 |  | 2020-05-09 10:00 | 2020-05-09 20:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 10136.46 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.20 | Origin ¦ Orana North 315 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 315 | SAVANNA DRILLING #408 | J.20.063531 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-04 12:00 |  | 2020-05-04 22:00 | 2020-05-05 08:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.03 | ORN 293_TC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | ORN 293 | SAVANNA DRILLING #408 | J.20.063528 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-16 |  | 2020-03-17 10:00 | 2020-03-17 20:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.23 | Origin ¦ Orana North 325 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 325 | SAVANNA DRILLING #408 | J.20.063521 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-10 12:00 |  | 2020-05-10 19:00 | 2020-05-11 05:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 |  |  |  |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.11 | Orana North 311 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 311 | SAVANNA DRILLING #408 | J.20.063518 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-07 |  | 2020-04-07 | 2020-04-07 10:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.08 | ORN299 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 299 | SAVANNA DRILLING #408 | J.20.063516 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-30 |  | 2020-03-30 14:00 | 2020-03-31 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.01 | RCK102_QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Reedy Creek 102 | SAVANNA DRILLING #408 | J.20.063514 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-19 |  | 2020-02-20 10:00 | 2020-02-21 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.38 | RCK222_QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #408 | J.21.108966 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-08-18 19:00 |  | 2021-08-20 05:00 | 2021-08-20 15:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.30 | Origin ¦ Reedy Creek 068 ¦ 8.75in Section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Reedy Creek 68 | SAVANNA DRILLING #408 | J.20.063512 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-02 20:00 |  | 2020-06-04 06:00 | 2020-06-04 16:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.19 | Origin ¦ Orana North 323 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 323 | SAVANNA DRILLING #408 | J.20.063510 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-30 12:00 |  | 2020-05-01 22:00 | 2020-05-02 08:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.39 | RCK253_QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #408 | J.21.108964 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-08-21 19:00 |  | 2021-08-23 05:00 | 2021-08-23 15:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.36 | RCK187_QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #408 | J.22.110241 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-02-23 21:00 |  | 2022-02-25 07:00 | 2022-02-25 17:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.34 | Origin ¦ Reedy Creek 097 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Reedy Creek 97 | SAVANNA DRILLING #408 | J.20.063495 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-14 20:00 |  | 2020-06-15 06:00 | 2020-06-15 16:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.33 | Origin ¦ Reedy Creek 128 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Reedy Creek 128 | SAVANNA DRILLING #408 | J.20.063493 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-11 20:00 |  | 2020-06-12 10:00 | 2020-06-12 20:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 10136.46 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.35 | RCK188_QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #408 | J.22.110238 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-08-27 18:00 |  | 2022-08-29 04:00 | 2022-08-29 14:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.10 | Orana North 303 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 303 | SAVANNA DRILLING #408 | J.20.063489 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-04 |  | 2020-04-04 21:00 | 2020-04-05 21:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.09 | Origin ¦ Orana North 302 ¦ AIT-PEX-GPIT ¦ MDT-GR | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 302 | SAVANNA DRILLING #408 | J.20.063487 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-01 08:00 |  | 2020-04-01 17:00 | 2020-04-02 03:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004754 | O.1004754.01 | A.1004754.01.02 | ORN292_TC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North | SAVANNA DRILLING #408 |  | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2020-03-14 21:00 | 2020-03-14 |  | 2020-03-14 21:00 | 2020-03-15 07:00 |  | 2020-03-15 07:00 | Roma WL | MRony2 | 2020-11-13 10:25 | JColeman |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 25 | 20 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004750 | O.1004750.06 | A.1004750.06.01 | Peat 449 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | PEAT-449 | RIGLESS - AUSTRALIA | J.25.059714 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-06-29 10:00 | 2025-09-19 | 2025-09-19 | 2025-09-20 06:00 | 2025-10-11 05:59 | 2025-10-24 | 2025-10-18 23:59 | Roma WL | CKok3 | 2025-10-08 12:45 | SAli112 |  | No |  |  |  |  | Irwan Wongso |  | 22555.21 | 2 |  | L0 - No RO |  | 100 | 100 | 0 | 100 | 90 |  | 4 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1004750 | O.1004750.06 | A.1004750.06.03 | Peat 448 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | PEA 448 | RIGLESS - AUSTRALIA | J.25.059716 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2025-10-08 | 2025-10-08 | 2025-09-29 | 2025-10-08 | 2025-10-14 23:59 | 2025-10-15 | 2025-10-14 23:59 | Roma WL | CKok3 | 2025-10-08 09:38 | SAli112 |  | No |  |  |  |  | Irwan Wongso |  | 22555.21 | 1 |  | L0 - No RO |  | 100 | 100 | 0 | 100 | 90 |  | 4 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1004750 | O.1004750.06 | A.1004750.06.02 | Peat 450 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | PEAT 450 | RIGLESS - AUSTRALIA | J.25.059715 | RPI | PS-WL-Ops | High | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2024-12-13 | 2025-09-01 | 2025-09-01 | 2025-09-07 | 2025-09-27 23:59 | 2025-09-22 | 2025-09-27 23:59 | Roma WL | CKok3 | 2025-10-01 14:11 | handoko |  | No |  |  |  |  | Irwan Wongso |  | 22555.21 | 11 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 2 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1004750 | O.1004750.06 | A.1004750.06.04 | Origin Peat 449 and 450 Tractor | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | PEAT-449, PEAT 450 | RIGLESS - AUSTRALIA | J.25.123950 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-11-07 | 2025-07-07 | 2025-07-05 | 2025-07-07 | 2025-07-31 23:59 | 2025-07-30 | 2025-07-31 23:59 | Roma WL | CKok3 | 2025-08-18 14:05 | APutra7 |  | No |  |  |  |  | Irwan Wongso |  | 42848.93 | 2 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1004750 | O.1004750.05 | A.1004750.05.01 | Frac | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Carinya 11 | Rigless Australia - 1 | J.21.109069 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-10-19 06:00 |  | 2021-10-19 10:00 | 2021-10-26 09:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 23255.36 | 3 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1004750 | O.1004750.04 | A.1004750.04.01 | SCMT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Carinya 11 | Rigless Australia - 1 | J.21.109044 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-05-05 |  | 2021-05-05 10:00 | 2021-05-09 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 13628.98 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1004750 | O.1004750.03 | A.1004750.03.01 | WAP in Jan,2021 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 474, CON 475, Condabri 265, Condabri 267, CONDABRI 430, CONDABRI 431, CONDABRI 448, CONDABRI 471, CONDABRI 463, Condabri North 370, CONDABRI 477, CONDABRI 432, Condabri North 368, Condabri 266, CONDABRI 476 | Rigless Australia - 1 | J.21.109009 | RPI | PS-WL-Ops | Low | Operationally Complete | Execute - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-01-23 10:00 |  | 2021-01-24 06:00 | 2021-02-12 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 47602.32 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1004750 | O.1004750.02 | A.1004750.02.01 | Crane rental_April | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 291 | Rigless Australia - 1 | J.20.063526 | RPE | ES-CH-NO | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-04-18 |  | 2020-04-18 | 2020-04-23 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 30685.35 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004750 | O.1004750.02 | A.1004750.02.02 | Crane rental | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK 291 | Rigless Australia - 1 | J.20.063509 | RPE | ES-CH-NO | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-04-18 |  | 2020-04-18 | 2020-04-23 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 28727.58 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004750 | O.1004750.01 | A.1004750.01.03 | WAP_Perfo_Apr20 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Reedy Creek 170, Reedy Creek 171, Reedy Creek 201, Condabri South 167, Condabri South 178, Reedy Creek 115, Reedy Creek 230, Reedy Creek 231, Reedy Creek 262, Reedy Creek 263, Reedy Creek 261, LUCKY GULLY 280, Reedy Creek 198, Reedy Creek 199, Reedy Creek 291, Reedy Creek 200, Reedy Creek 233, Reedy Creek 202, Reedy Creek 234, Reedy Creek 235, Reedy Creek 236 | Rigless Australia - 1 | J.20.063639 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-04-04 04:00 | 2020-04-02 |  | 2020-04-05 | 2020-05-03 |  | 2020-05-02 23:00 | Roma WL | MRony2 | 2022-10-03 15:01 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 18762.18 |  |  |  |  | 58.3 | 33.3 | 0 | 25 | 35 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004750 | O.1004750.01 | A.1004750.01.02 | WAP_Perfo_Mar20 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | Rigless Australia - 1 | J.20.063638 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-02-25 | 2020-02-25 |  | 2020-02-25 | 2020-03-24 |  | 2020-03-24 | Roma WL | MRony2 | 2022-10-03 15:01 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004750 | O.1004750.01 | A.1004750.01.04 | WAP_Perfo_May20 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Reedy Creek 261, Reedy Creek 262, Lucky Gully 280, LUCKY GULLY 22, Reedy Creek 264, Reedy Creek 263, Reedy Creek 265, Reedy Creek 288, Reedy Creek 232, Reedy Creek 231 | Rigless Australia - 1 | J.20.063637 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-05-07 23:00 | 2020-05-07 |  | 2020-05-08 | 2020-05-25 |  | 2020-06-24 23:00 | Roma WL | MRony2 | 2022-10-03 15:01 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 23801.16 |  |  |  |  | 75 | 50 | 0 | 50 | 52.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004750 | O.1004750.01 | A.1004750.01.01 | WAP_Perfo_Feb,20 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | LUCKY GULLY 22, REEDY CREEK 230, LUCKY GULLY 280, REEDY CREEK 264, REEDY CREEK 115, REEDY CREEK 170, REEDY CREEK 171, REEDY CREEK 201 | Rigless Australia - 1 | J.20.063573 | RPI | PS-WL-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Design Completed | In Progress | 2020-02-10 | 2020-02-10 |  | 2020-02-10 | 2020-02-28 |  | 2020-02-28 | Roma WL | MRony2 | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 15367.12 |  |  | L0 - No RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004750 | O.1004750.01 | A.1004750.01.05 | WAP_Perfo_Jun20 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Reedy Creek 264 | Rigless Australia - 1 | J.20.063523 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress |  | 2020-06-07 |  | 2020-06-08 | 2020-07-06 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 11900.58 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004716 | O.1004716.01 | A.1004716.01.06 | CNN362_QC & MDT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #406 | J.20.063636 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-04-13 12:00 | 2020-04-12 12:00 |  | 2020-04-13 12:00 | 2020-04-15 12:00 |  | 2020-04-15 12:00 | Roma WL | MRony2 | 2022-10-03 15:01 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004716 | O.1004716.01 | A.1004716.01.04 | RCK099_QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #406 | J.20.063635 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-03-24 12:00 | 2020-03-23 12:00 |  | 2020-03-24 12:00 | 2020-03-25 12:00 |  | 2020-03-25 12:00 | Roma WL | MRony2 | 2022-10-03 15:01 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004716 | O.1004716.01 | A.1004716.01.01 | COM423_QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Combabula 423 | SAVANNA DRILLING #406 | J.20.063634 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-02-20 | 2020-02-15 12:00 |  | 2020-02-20 | 2020-02-21 |  | 2020-02-21 | Roma WL | MRony2 | 2022-10-03 15:01 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004716 | O.1004716.01 | A.1004716.01.10 | CNN384_QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #406 | J.20.063506 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-24 12:00 |  | 2020-04-25 12:00 | 2020-04-26 12:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004716 | O.1004716.01 | A.1004716.01.03 | CNN384_PEX-AIT-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri North 384 | SAVANNA DRILLING #406 | J.20.063503 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-25 12:00 |  | 2020-03-26 12:00 | 2020-03-28 12:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004716 | O.1004716.01 | A.1004716.01.02 | Origin ¦ Condabri North 362 ¦ AIT-PEX-GPIT ¦ MDT-GR | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri North 362 | SAVANNA DRILLING #406 | J.20.063500 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-14 12:00 |  | 2020-03-16 22:00 | 2020-03-19 22:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 88791.42 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004716 | O.1004716.01 | A.1004716.01.07 | CON428_QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #406 | J.20.063497 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2020-03-02 14:00 | 2020-03-26 12:00 |  | 2020-03-26 14:00 | 2020-03-27 14:00 |  | 2020-03-03 14:00 | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004716 | O.1004716.01 | A.1004716.01.05 | Con426_QC ad MDT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #406 | J.20.063494 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-28 12:00 |  | 2020-03-29 12:00 | 2020-03-31 12:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004716 | O.1004716.01 | A.1004716.01.09 | CNN038_QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #406 | J.20.063492 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-20 12:00 |  | 2020-04-21 12:00 | 2020-04-22 12:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004716 | O.1004716.01 | A.1004716.01.08 | CNN360_QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #406 | J.20.063490 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-07 12:00 |  | 2020-04-08 12:00 | 2020-04-09 12:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004681 | O.1004681.01 | A.1004681.01.03 | Sapura ¦ Eagle-1 ¦ Valaris-107 ¦ Cased Hole Services | SAPURAOMV UPSTREAM (WESTERN AUSTRALIA) PTY LTD | EAGLE 1 | ENSCO 107 | J.21.108855 | RPE | ES-CH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2021-05-23 | 2021-05-18 |  | 2021-05-23 | 2021-06-01 13:00 |  | 2021-05-23 13:00 | New Burn WL | EBrobbey | 2022-10-03 09:51 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 1 |  | L0 - No RO |  | 50 | 50 | 0 | 25 | 37.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1004681 | O.1004681.01 | A.1004681.01.01 | Sapura ¦ Eagle-1 ¦ Valaris-107 ¦ Open Hole Services | SAPURAOMV UPSTREAM (WESTERN AUSTRALIA) PTY LTD | Eagle-1 | ENSCO 107 | J.21.108837 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-04-15 |  | 2021-06-05 | 2021-06-19 |  |  | New Burn WL | RTokabayev | 2022-10-03 09:48 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 613389.66 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1004681 | O.1004681.01 | A.1004681.01.02 | Eagle-1 OH Logging M2 | SAPURAOMV UPSTREAM (WESTERN AUSTRALIA) PTY LTD |  | ENSCO 107 | J.21.108836 | RPE | ES-OH-NO | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-05-26 |  | 2021-05-26 | 2021-06-25 |  |  | New Burn WL | LParedes | 2022-10-03 09:48 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 |  |  |  |  | 41.7 | 33.3 | 100 | 50 | 47.5 |  | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004630 | O.1004630.02 | A.1004630.02.08 | Reindeer Dec | SANTOS WESTERN AUSTRALIA |  | Reindeer Platform | J.23.008568 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-05-06 | 2023-05-05 |  | 2023-05-06 | 2023-05-25 23:59 |  | 2023-05-25 23:59 | New Burn WL | BAhmad | 2022-11-29 09:27 | JDukas |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004630 | O.1004630.02 | A.1004630.02.07 | Reindeer Nov | SANTOS WESTERN AUSTRALIA |  | Reindeer Platform | J.23.008567 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-04-06 | 2023-04-05 |  | 2023-04-06 | 2023-04-25 23:59 |  | 2023-04-25 23:59 | New Burn WL | BAhmad | 2022-11-29 09:27 | JDukas |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004630 | O.1004630.02 | A.1004630.02.06 | Reindeer Oct | SANTOS WESTERN AUSTRALIA | Reindeer-2, Reindeer-3, Reindeer-4 | Reindeer Platform | J.22.110122 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-10-12 |  | 2022-10-16 | 2022-11-04 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:56 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1004630 | O.1004630.02 | A.1004630.02.05 | Reindeer Sep | SANTOS WESTERN AUSTRALIA |  | Reindeer Platform | J.23.008566 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2023-02-14 |  | 2023-02-15 | 2023-03-06 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:56 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004630 | O.1004630.02 | A.1004630.02.04 | Reindeer Aug | SANTOS WESTERN AUSTRALIA |  | Reindeer Platform | J.23.008565 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2023-01-14 |  | 2023-01-15 | 2023-02-03 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:56 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004630 | O.1004630.02 | A.1004630.02.03 | Reindeer Jul | SANTOS WESTERN AUSTRALIA |  | Reindeer Platform | J.22.110121 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-12-14 |  | 2022-12-15 | 2023-01-03 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:56 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004630 | O.1004630.02 | A.1004630.02.02 | Reindeer Jun | SANTOS WESTERN AUSTRALIA |  | Reindeer Platform | J.22.110120 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-08-26 |  | 2022-08-27 | 2022-09-15 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:56 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004630 | O.1004630.02 | A.1004630.02.01 | Reindeer March | SANTOS WESTERN AUSTRALIA | Reindeer-2, Reindeer-3, Reindeer-4 | Reindeer Platform | J.22.110107 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-03-25 |  | 2022-03-28 | 2022-05-05 23:59 |  |  | New Burn WL | frosa2 | 2022-10-03 09:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  |  |  | 75 | 33.3 | 0 | 0 | 32.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004630 | O.1004630.01 | A.1004630.01.01 | Reindeer Santos | SANTOS WESTERN AUSTRALIA | Reindeer-3, Reindeer-4, Reindeer-2 | Reindeer Platform | J.20.063026 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-06 |  | 2020-07-08 | 2020-07-25 |  |  | New Burn WL | frosa2 | 2022-10-03 09:48 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1004630 | O.1004630.01 | A.1004630.01.02 | Reindeer Santos 2 | SANTOS WESTERN AUSTRALIA | Reindeer-2, Reindeer-3, Reindeer-4 | Reindeer Platform | J.20.063025 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-10-17 |  | 2020-10-22 | 2020-11-20 |  |  | New Burn WL | LParedes | 2022-10-03 09:48 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1004627 | O.1004627.01 | A.1004627.01.02 | Logging Tawhaki-1 | OMV GSB LIMITED | TAWHAKI-1 | COSLProspector |  | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-07 |  | 2020-02-18 | 2020-02-24 |  |  | New Plymouth WL | VOliveira5 | 2020-11-13 12:25 | JColeman |  | No |  |  |  |  | Victor Oliveira |  | 696913 | [10 empty] | 0 | [7 empty] | Paulo Zuliani | WL Evaluation Services
P.1004627 | O.1004627.01 | A.1004627.01.01 | GSB Tawhaki-1 - Rental | OMV GSB LIMITED | TAWHAKI-1 | COSLProspector |  | RPE | ES-OH-NO | InComplete | Operationally Complete | Close - PSD |  | Not Required | Not Started | In Progress |  | 2020-01-26 |  | 2020-01-26 | 2020-03-15 |  |  | New Plymouth WL | PZuliani | 2020-11-13 12:25 | JColeman |  | Yes |  |  |  |  | Victor Oliveira |  | 47033.33 | [10 empty] | 0 | [7 empty] | Paulo Zuliani | WL Evaluation Services
P.1004585 | O.1004585.01 | A.1004585.01.01 | Wandoo | VERMILION OIL & GAS AUSTRALIA PTY LTD | Wandoo B15 | Wandoo B | J.20.063024 | RPI | PS-SLK-NO | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-01-26 |  | 2020-01-26 | 2020-03-25 |  |  | New Burn WL | frosa2 | 2022-10-03 09:48 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 344550 | [10 empty] | 0 | [7 empty] | Luis Cardenas | Wireline Slickline
P.1004585 | O.1004585.01 | A.1004585.01.04 | Voga Owned Tools | VERMILION OIL & GAS AUSTRALIA PTY LTD | Wandoo B15 | Wandoo B | J.20.063023 | RPI | PS-SLK-NO | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-04-16 |  | 2020-04-16 | 2020-04-25 |  |  | New Burn WL | frosa2 | 2022-10-03 09:48 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 6800 | [10 empty] | 0 | [7 empty] | Luis Cardenas | Wireline Slickline
P.1004585 | O.1004585.01 | A.1004585.01.02 | VOGA Feb ops | VERMILION OIL & GAS AUSTRALIA PTY LTD | Wandoo B15 | Wandoo B | J.20.063022 | RPI | PS-SLK-NO | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-02-01 |  | 2020-02-01 | 2020-03-02 |  |  | New Burn WL | frosa2 | 2022-10-03 09:48 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 7200 | [10 empty] | 0 | [7 empty] | Luis Cardenas | Wireline Slickline
P.1004585 | O.1004585.01 | A.1004585.01.03 | March Ops/ rental | VERMILION OIL & GAS AUSTRALIA PTY LTD | Wandoo B15 | Wandoo B | J.20.063021 | RPI | PS-SLK-NO | High | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-03-21 |  | 2020-03-26 | 2020-03-31 |  |  | New Burn WL | frosa2 | 2022-10-03 09:48 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 129995 | [10 empty] | 0 | [7 empty] | Luis Cardenas | Wireline Slickline
P.1004584 | O.1004584.01 | A.1004584.01.01 | CORE CSIRO Sampling Analysis | CSIRO |  | RIGLESS - AUSTRALIA | J.20.062343 | RPE | FSA-ROCK-JOB | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-01-28 14:50 |  | 2020-01-28 14:50 | 2020-12-31 14:50 |  |  | APG TS | RWallis | 2022-10-03 06:24 | FDPSystemUser |  | No |  |  |  |  | Wayne Wallis |  | 23414 | [10 empty] | 0 | [7 empty] | Richard Steers | TS Downhole Reservoir Testing
P.1004580 | O.1004580.01 | A.1004580.01.01 | Jadestone MPFM Check Offshore | JADESTONE ENERGY (AUSTRALIA) PTY LTD | Well #1 | STAG SNUBBING UNIT 1 | J.22.109440 | RPI | TSWT-VXONLY-JOB | High | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2022-02-04 |  | 2022-02-04 | 2022-05-17 |  |  | APG TS | AFrancis4 | 2024-11-19 20:21 | FDPSystemUser |  | No |  |  |  |  | Allwyn Francis |  | 5912.93 | 0 |  | L0 - No RO |  | 33.3 | 0 | 0 | 25 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Richard Steers | TS Surface Testing
P.1004498 | O.1004498.07 | A.1004498.07.03 | July_23_PEX-AIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | REEDY CREEK SOUTH 2, REEDY CREEK SOUTH 3, REEDY CREEK SOUTH 21, MUGGLETON 334, MUGGLETON 335, MUGGLETON 358, MUGGLETON 357, MUGGLETON 336, MUGGLETON 315 | SAVANNA DRILLING #449 | J.23.102013 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-29 | 2023-06-25 | 2023-06-29 | 2023-06-29 | 2023-07-31 23:59 | 2023-08-10 | 2023-07-31 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 7797.27 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1004498 | O.1004498.07 | A.1004498.07.04 | ORN 363 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | MUGGLETON 269, MUGGLETON 291, MUGGLETON 271, MUGGLETON 270, MUGGLETON 293, REEDY CREEK SOUTH 19, REEDY CREEK SOUTH 20, REEDY CREEK SOUTH 1, ORANA NORTH 363 | SAVANNA DRILLING #449 | J.23.142605 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-10-01 | 2023-09-28 |  | 2023-10-01 | 2023-10-04 23:59 |  | 2023-10-05 00:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 121962.31 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1004498 | O.1004498.07 | A.1004498.07.02 | Jun23_PEX-AIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | MUGGLETON 269, MUGGLETON 291, MUGGLETON 271, MUGGLETON 270, MUGGLETON 293, REEDY CREEK SOUTH 19, REEDY CREEK SOUTH 20, REEDY CREEK SOUTH 1 | SAVANNA DRILLING #449 | J.23.100065 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-08 | 2023-06-05 | 2023-06-10 | 2023-06-08 | 2023-06-25 23:59 | 2023-07-05 | 2023-06-25 23:59 | Roma WL | JEsmeralda | 2023-10-05 20:33 | NSchwenke |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 7797.27 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1004498 | O.1004498.07 | A.1004498.07.01 | May23_PEX-AIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | MUGGLETON 311, MUGGLETON 247, MUGGLETON 222, MUGGLETON 246, MUGGLETON 245, MUGGLETON 289, MUGGLETON 290 | SAVANNA DRILLING #449 | J.23.086494 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-24 | 2023-05-21 | 2023-05-23 04:00 | 2023-05-24 | 2023-06-10 23:59 | 2023-06-17 | 2023-06-10 23:59 | Roma WL | JEsmeralda | 2023-07-02 17:18 | handoko |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 7797.27 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1004498 | O.1004498.06 | A.1004498.06.10 | Triple Combo | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.22.110894 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-03-09 | 2022-03-08 |  | 2022-03-09 | 2022-03-16 23:59 |  | 2022-03-16 23:59 | Roma WL | MRony2 | 2022-10-03 15:00 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.06 | A.1004498.06.08 | Triple Combo | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.22.110893 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-02-21 | 2022-02-20 |  | 2022-02-21 | 2022-02-26 23:59 |  | 2022-02-26 23:59 | Roma WL | MRony2 | 2022-10-03 15:00 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.06 | A.1004498.06.07 | Triple Combo | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.22.110892 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-02-14 | 2022-02-13 |  | 2022-02-14 | 2022-02-19 23:59 |  | 2022-02-19 23:59 | Roma WL | MRony2 | 2022-10-03 15:00 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.06 | A.1004498.06.06 | Triple Combo | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.22.110891 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-02-07 | 2022-02-06 |  | 2022-02-07 | 2022-02-12 23:59 |  | 2022-02-12 23:59 | Roma WL | MRony2 | 2022-10-03 15:00 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.06 | A.1004498.06.01 | Triple Combo | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.21.109435 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2021-12-12 | 2021-12-11 |  | 2021-12-12 | 2021-12-17 23:59 |  | 2021-12-17 23:59 | Roma WL | MRony2 | 2022-10-03 15:00 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.06 | A.1004498.06.12 | MDT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.22.110295 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-03-26 |  | 2022-03-27 | 2022-03-30 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.06 | A.1004498.06.11 | Triple Combo | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.22.110289 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-03-18 |  | 2022-03-19 | 2022-03-26 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.06 | A.1004498.06.09 | Triple Combo | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.22.110285 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-03-01 |  | 2022-03-02 | 2022-03-07 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.06 | A.1004498.06.04 | Triple Combo | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.22.110282 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-01-23 |  | 2022-01-24 | 2022-01-29 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.06 | A.1004498.06.05 | Triple Combo | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.22.110281 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-01-30 |  | 2022-01-31 | 2022-02-05 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.06 | A.1004498.06.03 | Teipple Combo | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.22.110276 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-01-15 |  | 2022-01-16 | 2022-01-21 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.06 | A.1004498.06.02 | TC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.21.109067 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-12-12 |  | 2021-12-13 | 2021-12-18 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.05 | A.1004498.05.11 | MDT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Murrungama 1 | SAVANNA DRILLING #449 | J.21.109434 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-10-26 03:00 | 2021-10-25 10:00 |  | 2021-10-26 12:00 | 2021-10-29 12:59 |  | 2021-11-03 02:59 | Roma WL | MRony2 | 2022-10-03 15:00 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 101234.57 | 2 |  |  |  | 91.7 | 50 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.05 | A.1004498.05.08 | Multi Well Operations Nov 3rd week | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI 467, CONDABRI NORTH 379 | SAVANNA DRILLING #449 | J.21.109433 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2021-11-18 01:00 | 2021-11-18 01:00 |  | 2021-11-18 01:00 | 2021-11-26 01:59 |  | 2021-11-26 01:59 | Roma WL | EDelange | 2022-10-03 15:00 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 3 |  | L0 - No RO |  | 83.3 | 50 | 0 | 0 | 40 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.05 | A.1004498.05.12 | MDT_Nov | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.22.110264 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-01-09 01:00 |  | 2022-01-10 01:00 | 2022-01-13 01:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.05 | A.1004498.05.01 | Multi Well Operations 13-19 August | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri North 375, Condabri North 335, Condabri North 387 | SAVANNA DRILLING #449 | J.21.109005 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-08-13 |  | 2021-08-13 | 2021-08-21 00:59 |  |  | Roma WL | EDelange | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.05 | A.1004498.05.10 | Multi Well Operations Nov 2nd week | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.21.108983 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-11-24 01:00 |  | 2021-12-01 01:00 | 2021-12-09 01:59 |  |  | Roma WL | EDelange | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.05 | A.1004498.05.09 | Multi Well Operations1st week Nov | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.21.108979 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-12-08 01:00 |  | 2021-12-08 01:00 | 2021-12-16 01:59 |  |  | Roma WL | EDelange | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.05 | A.1004498.05.07 | Multi Well Operations Oct 2nd week | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Murrungama 7, Murrungama 8, Murrungama 3, Murrungama 10 | SAVANNA DRILLING #449 | J.21.108977 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-10-29 06:00 |  | 2021-10-30 22:00 | 2021-11-14 22:59 |  |  | Roma WL | EDelange | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | 2 |  |  |  | 83.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.05 | A.1004498.05.06 | Multi Well Operations Oct 1st week | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri North 331, Condabri North 332, Condabri North 338, Murrungama 14 | SAVANNA DRILLING #449 | J.21.108975 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-10-05 |  | 2021-10-05 | 2021-10-13 00:59 |  |  | Roma WL | EDelange | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 7017.54 | 2 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.05 | A.1004498.05.05 | Multi Well Operations Sep 5th week | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri 461, Condabri North 326, Condabri North 330 | SAVANNA DRILLING #449 | J.21.108973 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-09-22 |  | 2021-09-22 | 2021-09-30 00:59 |  |  | Roma WL | EDelange | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 7017.54 | 3 |  |  |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.05 | A.1004498.05.04 | Multi Well Operations 4th Sep | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri South 224, Condabri South 225, Condabri 469 | SAVANNA DRILLING #449 | J.21.108969 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-09-11 |  | 2021-09-14 | 2021-09-26 00:59 |  |  | Roma WL | EDelange | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | 3 |  |  |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.05 | A.1004498.05.03 | Multi Well Operations 2nd week of Sep | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri South 284, Condabri South 227, Condabri South 226, Condabri South 225 | SAVANNA DRILLING #449 | J.21.108967 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-09-04 |  | 2021-09-04 | 2021-09-16 00:59 |  |  | Roma WL | EDelange | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | 3 |  |  |  | 66.7 | 33.3 | 0 | 75 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.05 | A.1004498.05.02 | Multi Well Operations Jul 29-Aug 5 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri North 382, Condabri North 388, Condabri South 285, Condabri South 286, Condabri South 284 | SAVANNA DRILLING #449 | J.21.108965 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-08-23 18:00 |  | 2021-08-24 10:00 | 2021-09-01 10:59 |  |  | Roma WL | EDelange | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | 3 |  |  |  | 75 | 66.7 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.04 | A.1004498.04.13 | AIT-PEX-GPIT-MDT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 400 | SAVANNA DRILLING #449 | J.21.109432 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-05-18 10:00 | 2021-05-17 12:00 |  | 2021-05-18 10:00 | 2021-05-20 16:00 |  | 2021-05-23 16:00 | Roma WL | MRony2 | 2022-10-03 15:00 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.04 | A.1004498.04.08 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri 479, CONDABRI 434, CONDABRI 472, CONDABRI 485, CONDABRI 438 | SAVANNA DRILLING #449 | J.21.109431 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-05-28 20:00 | 2021-05-28 |  | 2021-05-28 20:00 | 2021-06-05 02:00 |  | 2021-06-05 02:00 | Roma WL | MRony2 | 2022-10-03 15:00 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.04 | A.1004498.04.05 | Origin AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | ORANA NORTH 47, ORANA NORTH 48, ORANA NORTH 50 | SAVANNA DRILLING #449 | J.21.109429 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-04-28 12:00 | 2021-04-28 12:00 |  | 2021-04-28 12:00 | 2021-05-05 05:59 |  | 2021-05-05 05:59 | Roma WL | MMclean3 | 2022-10-03 15:00 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.04 | A.1004498.04.12 | Multi Well Operations Jul31-Aug7 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri 369, Condabri 424, Condabri 453, Condabri North 374 | SAVANNA DRILLING #449 | J.21.109038 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-07-31 |  | 2021-07-31 20:00 | 2021-08-11 02:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 7017.54 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.04 | A.1004498.04.11 | Multi Well Operation Jul 21-28 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri 442, Condabri 444, Condabri 443 | SAVANNA DRILLING #449 | J.21.109037 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-07-21 |  | 2021-07-21 20:00 | 2021-07-29 02:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.04 | A.1004498.04.07 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | ORANA NORTH 72, Condabri 479, Condabri 480 | SAVANNA DRILLING #449 | J.21.109032 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-05-21 12:00 |  | 2021-05-22 02:00 | 2021-05-27 08:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 7017.54 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.04 | A.1004498.04.09 | Multi well operations - Jun 7-14 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI 438 | SAVANNA DRILLING #449 | J.21.109030 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-06-07 |  | 2021-06-08 10:00 | 2021-06-15 16:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 4 |  |  |  | 58.3 | 16.7 | 0 | 25 | 30 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.04 | A.1004498.04.10 | Multi Well Operation Jul 12-19 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri 339, Condabri 440, Condabri 478 | SAVANNA DRILLING #449 | J.21.109027 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-07-12 12:00 |  | 2021-07-12 12:00 | 2021-07-17 18:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.04 | A.1004498.04.14 | Multiple wells | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI 438, CONDABRI 485, CONDABRI SOUTH 289 | SAVANNA DRILLING #449 | J.21.108996 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2021-06-13 17:00 | 2021-06-12 |  | 2021-06-13 17:00 | 2021-06-20 23:00 |  | 2021-06-25 23:00 | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | 4 |  | L3 - Full RO |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.04 | A.1004498.04.06 | AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | ORANA NORTH 40, ORANA NORTH 61 | SAVANNA DRILLING #449 | J.21.108988 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-05-05 06:00 |  | 2021-05-05 20:00 | 2021-05-17 02:00 |  |  | Roma WL | MMclean3 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.04 | A.1004498.04.04 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 401, ORANA NORTH 47, ORANA NORTH 48, ORANA NORTH 50, ORANA NORTH 40 | SAVANNA DRILLING #449 | J.21.108984 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-04-24 |  | 2021-04-25 08:00 | 2021-05-02 01:59 |  |  | Roma WL | MMclean3 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.04 | A.1004498.04.03 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | ORANA NORTH 70, ORANA NORTH 69, ORANA NORTH 68, ORANA NORTH 71 | SAVANNA DRILLING #449 | J.21.108982 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-04-14 |  | 2021-04-15 20:00 | 2021-04-26 13:59 |  |  | Roma WL | MMclean3 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.04 | A.1004498.04.02 | 449 multi well Apr 8-15 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | ORANA NORTH 93, ORANA NORTH 91, ORANA NORTH 90 | SAVANNA DRILLING #449 | J.21.108980 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-04-08 |  | 2021-04-09 02:00 | 2021-04-13 19:59 |  |  | Roma WL | MMclean3 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.04 | A.1004498.04.01 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 399, ORANA NORTH 83 | SAVANNA DRILLING #449 | J.21.108978 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-04-01 |  | 2021-04-01 06:00 | 2021-04-05 23:59 |  |  | Roma WL | MMclean3 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.40 | QC+MDT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.21.109430 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-05-18 17:00 | 2021-05-18 07:00 |  | 2021-05-18 20:00 | 2021-05-21 05:59 |  | 2021-05-21 04:59 | Roma WL | MRony2 | 2022-10-03 15:00 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.28 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.21.108955 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-04-06 06:00 |  | 2021-04-06 19:00 | 2021-04-11 04:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 0 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.26 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.21.108954 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-03-16 07:00 |  | 2021-03-29 20:00 | 2021-04-05 04:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.05 | Condabri North 371 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri North 371 | SAVANNA DRILLING #449 | J.20.063486 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-10-19 12:00 |  | 2020-10-21 01:00 | 2020-10-23 10:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.38 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.21.108953 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-08-26 06:00 |  | 2021-08-26 19:00 | 2021-08-27 04:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:08 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.30 | QC + MDT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.21.108952 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-04-18 06:00 |  | 2021-04-18 19:00 | 2021-04-20 04:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:08 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 0 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.23 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 122, Orana North 121, Orana North 120, Orana North 139, Orana North 140 | SAVANNA DRILLING #449 | J.21.108951 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-01-28 04:00 |  | 2021-01-28 17:00 | 2021-02-06 02:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:07 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 14035.08 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.14 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Talinga 212 | SAVANNA DRILLING #449 | J.20.063469 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2020-11-15 18:00 |  | 2020-11-16 15:00 | 2020-11-17 00:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:07 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.08 | Condabri North 117 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri North 117 | SAVANNA DRILLING #449 | J.20.063468 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-10-30 06:00 |  | 2020-10-30 07:00 | 2020-10-31 16:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:06 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.04 | Condabri North 141 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI NORTH 141 | SAVANNA DRILLING #449 | J.21.108950 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2020-12-30 | 2021-05-31 14:00 |  | 2021-06-01 03:00 | 2021-06-02 12:59 |  | 2021-01-03 12:49 | Roma WL | MRony2 | 2022-10-03 14:06 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | 0 |  | L3 - Full RO |  | 58.3 | 50 | 0 | 62.5 | 51.2 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.03 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI NORTH 291 | SAVANNA DRILLING #449 | J.20.063467 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2020-10-12 12:00 |  | 2020-10-13 02:00 | 2020-10-13 11:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:06 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.36 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.21.108949 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-08-20 06:00 |  | 2021-08-20 19:00 | 2021-08-21 04:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:05 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.31 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.21.108948 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-04-21 06:00 |  | 2021-04-21 19:00 | 2021-04-27 04:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:05 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 0 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.19 | Talinga 266 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Talinga 266 | SAVANNA DRILLING #449 | J.20.063459 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2020-11-26 12:00 |  | 2020-11-26 21:00 | 2020-11-27 06:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:05 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.16 | Origin I Talinga 230 I 8.75 in section I AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Talinga 230 | SAVANNA DRILLING #449 | J.20.063458 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2020-11-20 04:00 |  | 2020-11-20 17:00 | 2020-11-21 02:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:05 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.12 | Origin ¦ Talinga 249 ¦ 8.5 in section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | TALINGA 249 | SAVANNA DRILLING #449 | J.21.108947 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2021-04-27 21:00 | 2021-09-27 14:00 |  | 2021-09-28 01:00 | 2021-09-28 10:59 |  | 2021-04-28 07:59 | Roma WL | MRony2 | 2022-10-03 14:05 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 7017.54 | 0 |  | L0 - No RO |  | 58.3 | 50 | 0 | 62.5 | 51.2 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.10 | Condabri north 125 AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri North 125 | SAVANNA DRILLING #449 | J.20.063457 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-11-05 06:00 |  | 2020-11-05 06:00 | 2020-11-05 15:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:05 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.34 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.21.108946 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-05-17 06:00 |  | 2021-05-18 19:00 | 2021-05-23 04:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:03 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 0 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.33 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.21.108945 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-05-07 06:00 |  | 2021-05-07 19:00 | 2021-05-27 04:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:02 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 0 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.27 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.21.108944 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-03-30 07:00 |  | 2021-03-30 20:00 | 2021-04-05 04:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:02 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | 0 |  |  |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.09 | Condabri North 148 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri North 148 | SAVANNA DRILLING #449 | J.20.063439 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-11-01 12:00 |  | 2020-11-02 01:00 | 2020-11-03 10:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:02 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.39 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.21.108942 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-08-29 06:00 |  | 2021-08-29 19:00 | 2021-08-30 04:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:01 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.24 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 143, ORANA NORTH 38, ORANA NORTH 39, ORANA NORTH 31, Orana North 467, Orana North 468 | SAVANNA DRILLING #449 | J.21.108941 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-02-10 20:00 |  | 2021-02-11 08:00 | 2021-02-28 17:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:01 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.20 | Orana North Surface + Production | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | ORANA NORTH 191, Orana North 215 | SAVANNA DRILLING #449 | J.20.063429 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-11-28 04:00 |  | 2020-11-28 17:00 | 2020-12-05 02:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:01 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 40123.45 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.37 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.21.108940 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-08-23 06:00 |  | 2021-08-23 19:00 | 2021-08-24 04:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:00 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.18 | Talinga 267 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Talinga 267 | SAVANNA DRILLING #449 | J.20.063426 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-11-23 04:00 |  | 2020-11-23 17:00 | 2020-11-25 02:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:00 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.07 | Condabri North 370 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI NORTH 370 | SAVANNA DRILLING #449 | J.21.108939 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2020-12-28 12:00 | 2021-05-30 14:00 |  | 2021-05-30 15:00 | 2021-06-02 00:59 |  | 2020-12-29 | Roma WL | MRony2 | 2022-10-03 14:00 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | 0 |  | L3 - Full RO |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.02 | CNN 292 AIT-PEX-GPIT-MDT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI NORTH 292 | SAVANNA DRILLING #449 | J.21.108938 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2020-12-07 20:00 | 2021-05-09 14:00 |  | 2021-05-09 22:00 | 2021-05-10 07:59 |  | 2020-12-08 05:59 | Roma WL | MRony2 | 2022-10-03 14:00 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 87589.34 |  |  | L2 - Shift RO |  | 75 | 50 | 0 | 62.5 | 56.3 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.35 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.21.108936 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-05-10 06:00 |  | 2021-05-10 19:00 | 2021-05-19 12:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:00 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.22 | AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 123, CONDABRI NORTH 141, TALINGA 160 | SAVANNA DRILLING #449 | J.21.108935 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-01-21 12:00 |  | 2021-01-22 18:00 | 2021-01-28 03:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:59 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.21 | ORN124_QC/MDT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 124 | SAVANNA DRILLING #449 | J.21.108934 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-01-16 18:00 |  | 2021-01-17 16:00 | 2021-01-18 01:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:59 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 101234.57 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.06 | Condabri North 368 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri North 368 | SAVANNA DRILLING #449 | J.20.063420 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-10-25 |  | 2020-10-25 01:00 | 2020-10-26 10:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:59 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.32 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.21.108933 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-04-29 06:00 |  | 2021-04-29 19:00 | 2021-05-04 04:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:58 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.15 | Origin I Talinga 248 I 8.75 in section I AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Talinga 248 | SAVANNA DRILLING #449 | J.20.063409 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2020-11-17 12:00 |  | 2020-11-18 01:00 | 2020-11-18 10:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:58 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.13 | Origin ¦ Talinga 231 ¦ 8.75 in section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Talinga 231 | SAVANNA DRILLING #449 | J.20.063408 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-11-13 12:00 |  | 2020-11-14 | 2020-11-14 09:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:58 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.11 | Condabri North 276 AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI NORTH 276 | SAVANNA DRILLING #449 | J.20.063407 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-11-07 12:00 |  | 2020-11-07 12:00 | 2020-11-07 21:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:58 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.01 | Origin ¦ Condabri 466 ¦ 8.75 in section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI 466 | SAVANNA DRILLING #449 | J.20.063406 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-10-05 14:00 |  | 2020-10-06 | 2020-10-06 12:00 |  |  | Roma WL | FDPSystemUser | 2022-10-03 13:58 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.25 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | ORANA NORTH 35, ORANA NORTH 34, ORANA NORTH 30, ORANA NORTH 29 | SAVANNA DRILLING #449 | J.21.108932 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-03-02 06:00 |  | 2021-03-02 19:00 | 2021-03-10 04:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:57 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 14035.08 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.17 | Talinga 268 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Talinga 268 | SAVANNA DRILLING #449 | J.20.063398 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-11-22 12:00 |  | 2020-11-22 17:00 | 2020-11-23 17:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:57 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.03 | A.1004498.03.29 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.21.108931 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-04-13 06:00 |  | 2021-04-13 19:00 | 2021-04-16 05:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:56 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 0 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.35 | Origin ¦ Condabri North 378 ¦ 8.75 in section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI NORTH 378 | SAVANNA DRILLING #449 | J.20.063485 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-17 19:00 |  | 2020-09-18 06:00 | 2020-09-18 19:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:09 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.30 | Origin ¦ Condabri 463 ¦ 7.875 in section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI 463 | SAVANNA DRILLING #449 | J.20.063484 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-25 13:00 |  | 2020-08-26 16:00 | 2020-08-27 05:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:08 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.29 | Origin ¦ Condabri 448 ¦ 7.875 in section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI 448 | SAVANNA DRILLING #449 | J.20.063483 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-23 13:00 |  | 2020-08-24 03:00 | 2020-08-24 16:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:08 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.24 | Origin ¦ CNS-287 ¦ 8.75in section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CNS 287 | SAVANNA DRILLING #449 | J.20.063482 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-30 13:00 |  | 2020-07-31 | 2020-08-02 13:00 |  |  | Roma WL | ZWahid | 2022-10-03 14:08 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.21 | Origin ¦ Talinga 196 ¦ 12.25in section ¦ AIT-PEX | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Talinga 196 | SAVANNA DRILLING #449 | J.20.063481 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-12 09:00 |  | 2020-07-12 12:00 | 2020-07-13 01:00 |  |  | Roma WL | ZWahid | 2022-10-03 14:08 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 7342.43 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.03 | Origin ¦ Orana North 187 ¦ 12.25in Section ¦ AIT-PEX | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 187 | SAVANNA DRILLING #449 | J.20.063480 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-06 12:00 |  | 2020-06-06 23:00 | 2020-06-07 12:00 |  |  | Roma WL | ZWahid | 2022-10-03 14:08 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.48 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 201 | SAVANNA DRILLING #449 | J.22.110237 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-01-11 |  | 2022-01-11 03:00 | 2022-01-11 16:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:07 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.16 | Origin ¦ Orana North 227 ¦ 8.75in sextion ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 227 | SAVANNA DRILLING #449 | J.20.063476 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-03 15:00 |  | 2020-07-03 20:00 | 2020-07-04 09:00 |  |  | Roma WL | ZWahid | 2022-10-03 14:07 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.11 | Origin ¦ Orana North 200 ¦ 12.25in section ¦ AIT-PEX | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 200 | SAVANNA DRILLING #449 | J.20.063475 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-25 15:00 |  | 2020-06-25 18:00 | 2020-06-26 07:00 |  |  | Roma WL | ZWahid | 2022-10-03 14:07 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 7342.43 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.08 | Origin ¦ Reedy Creek 070 ¦ 7.875in Section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Reedy Creek 70 | SAVANNA DRILLING #449 | J.20.063474 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-21 15:00 |  | 2020-06-22 02:00 | 2020-06-22 15:00 |  |  | Roma WL | ZWahid | 2022-10-03 14:07 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.47 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 201 | SAVANNA DRILLING #449 | J.22.110236 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-01-10 |  | 2022-01-10 03:00 | 2022-01-10 16:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:06 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.46 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 201 | SAVANNA DRILLING #449 | J.22.110235 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-01-08 |  | 2022-01-08 03:00 | 2022-01-08 16:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:06 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.43 | Origin QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 215 | SAVANNA DRILLING #449 | J.22.110234 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-01-09 20:00 |  | 2022-01-10 07:00 | 2022-01-10 20:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:06 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.40 | Origin ¦ Condabri 465 ¦ 7.875 in section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI 465 | SAVANNA DRILLING #449 | J.20.063466 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-10-01 19:00 |  | 2020-10-02 | 2020-10-02 13:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:06 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.28 | Origin QC_Con475_AIT-PEX-GPIT-GR-SP | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 475 | SAVANNA DRILLING #449 | J.20.063465 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-19 18:00 |  | 2020-08-20 20:00 | 2020-08-21 09:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:06 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.22 | Origin ¦ Talinga 196 ¦ 8.75in section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Talinga 196 | SAVANNA DRILLING #449 | J.20.063464 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-14 20:00 |  | 2020-07-15 04:00 | 2020-07-15 17:00 |  |  | Roma WL | ZWahid | 2022-10-03 14:06 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.19 | Origin ¦ Orana North 201 ¦ 12.25in section ¦ AIT-PEX | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 201 | SAVANNA DRILLING #449 | J.20.063463 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-07 09:00 |  | 2020-07-10 02:00 | 2020-07-10 15:00 |  |  | Roma WL | ZWahid | 2022-10-03 14:06 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 7342.43 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.12 | Origin ¦ Orana North 200 ¦ 8.75in section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 200 | SAVANNA DRILLING #449 | J.20.063462 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-26 15:00 |  | 2020-06-26 22:00 | 2020-06-27 11:00 |  |  | Roma WL | ZWahid | 2022-10-03 14:06 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 7342.43 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.42 | Origin QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 215 | SAVANNA DRILLING #449 | J.22.110233 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-02-20 20:00 |  | 2022-02-21 07:00 | 2022-02-21 20:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:05 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.39 | Origin ¦ Condabri 432 ¦ 7.875 in section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI 432 | SAVANNA DRILLING #449 | J.20.063456 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-28 19:00 |  | 2020-09-29 09:00 | 2020-09-29 22:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:05 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.17 | Origin ¦ Orana North 211 ¦ 12.25in section ¦ AIT-PEX | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 211 | SAVANNA DRILLING #449 | J.20.063455 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-07 09:00 |  | 2020-07-07 14:00 | 2020-07-08 03:00 |  |  | Roma WL | ZWahid | 2022-10-03 14:04 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 7342.43 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.09 | Origin ¦ Orana North 199 ¦ 12.25in Section ¦ AIT-PEX | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 199 | SAVANNA DRILLING #449 | J.20.063451 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-24 15:00 |  | 2020-06-25 02:00 | 2020-06-25 15:00 |  |  | Roma WL | ZWahid | 2022-10-03 14:04 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.06 | Origin ¦ Reedy Creek 131 ¦ 8.75in Section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Reedy Creek 131 | SAVANNA DRILLING #449 | J.20.063450 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-13 15:00 |  | 2020-06-14 04:00 | 2020-06-14 17:00 |  |  | Roma WL | ZWahid | 2022-10-03 14:04 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.02 | Origin ¦ Orana North 188 ¦ 8.75in Section ¦ HRLA-PEX-GPIT-SP | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 188 | SAVANNA DRILLING #449 | J.20.063449 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-05 15:00 |  | 2020-06-06 02:00 | 2020-06-06 15:00 |  |  | Roma WL | ZWahid | 2022-10-03 14:04 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.50 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 201 | SAVANNA DRILLING #449 | J.22.110232 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-01-13 |  | 2022-01-13 03:00 | 2022-01-13 16:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:03 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.38 | Origin ¦ Condabri 438 ¦ 7.875 in section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI 431 | SAVANNA DRILLING #449 | J.20.063446 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-26 19:00 |  | 2020-09-27 12:00 | 2020-09-28 01:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:03 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.31 | Origin ¦ Condabri 476 ¦ 7.875 in section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI 476 | SAVANNA DRILLING #449 | J.20.063445 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-28 17:00 |  | 2020-08-29 06:00 | 2020-08-29 19:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:03 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.26 | Origin QC_CON-342 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 342 | SAVANNA DRILLING #449 | J.20.063444 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-06 |  | 2020-08-06 | 2020-08-08 13:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:03 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.15 | Origin ¦ Orana North 227 ¦ 12.25in section ¦ AIT-PEX | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 227 | SAVANNA DRILLING #449 | J.20.063443 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-02 06:00 |  | 2020-07-02 18:00 | 2020-07-03 07:00 |  |  | Roma WL | ZWahid | 2022-10-03 14:03 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 7342.43 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.14 | Origin ¦ Orana North 228 ¦ 8.75in section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 228 | SAVANNA DRILLING #449 | J.20.063442 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-29 15:00 |  | 2020-06-29 16:00 | 2020-06-30 05:00 |  |  | Roma WL | ZWahid | 2022-10-03 14:03 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 7342.43 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.44 | Origin QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 215 | SAVANNA DRILLING #449 | J.21.108943 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-12-30 17:00 |  | 2021-12-31 04:00 | 2021-12-31 17:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:02 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.36 | Origin ¦ Condabri 430 ¦ 8.75 in section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI 430 | SAVANNA DRILLING #449 | J.20.063438 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-20 19:00 |  | 2020-09-20 20:00 | 2020-09-21 09:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:02 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.33 | Origin ¦ Condabri South 269 ¦ 7.875 in section ¦ AIT-PEX-GPIT ¦ SSCAN-FMI ¦ MDT-GR | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI SOUTH 269 | SAVANNA DRILLING #449 | J.20.063437 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-03 13:00 |  | 2020-09-04 | 2020-09-08 13:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:02 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.13 | Origin ¦ Orana North 228 ¦ 12.25in section ¦ AIT-PEX | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 228 | SAVANNA DRILLING #449 | J.20.063436 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-28 15:00 |  | 2020-06-28 18:00 | 2020-06-29 07:00 |  |  | Roma WL | ZWahid | 2022-10-03 14:02 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 7342.43 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.04 | Origin ¦ Orana North 187 ¦ 8.75in Section ¦ HRLA-PEX-GPIT-SP | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 187 | SAVANNA DRILLING #449 | J.20.063435 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-09 15:00 |  | 2020-06-10 02:00 | 2020-06-10 15:00 |  |  | Roma WL | ZWahid | 2022-10-03 14:02 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.51 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 201 | SAVANNA DRILLING #449 | J.22.110231 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-01-15 |  | 2022-01-15 03:00 | 2022-01-15 16:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:01 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.34 | Origin ¦ Condabri South 272 ¦ 7.875 in section ¦ AIT-PEX-GPIT ¦ SSCAN-FMI ¦ MDT-GR | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI SOUTH 272 | SAVANNA DRILLING #449 | J.20.063432 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-09 13:00 |  | 2020-09-12 20:00 | 2020-09-13 09:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:01 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.20 | Origin ¦ Orana North 201 ¦ 8.75in section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 201 | SAVANNA DRILLING #449 | J.20.063425 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-10 09:00 |  | 2020-07-11 12:00 | 2020-07-12 01:00 |  |  | Roma WL | ZWahid | 2022-10-03 14:00 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.41 | Origin QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 215 | SAVANNA DRILLING #449 | J.21.108937 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-12-22 19:00 |  | 2021-12-23 06:00 | 2021-12-23 19:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:00 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.23 | Origin ¦ Condabri 468 ¦ 8.75in section ¦ AIT-PEX-GPIT ¦ MDT-GR | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Condabri 468 | SAVANNA DRILLING #449 | J.20.063424 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-26 13:00 |  | 2020-07-27 | 2020-07-29 13:00 |  |  | Roma WL | ZWahid | 2022-10-03 14:00 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 7342.43 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.05 | Origin ¦ Reedy Creek South 017 ¦ 8.75in Section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Reedy Creek South 017 | SAVANNA DRILLING #449 | J.20.063423 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-06-10 15:00 |  | 2020-06-11 10:00 | 2020-06-11 23:00 |  |  | Roma WL | ZWahid | 2022-10-03 14:00 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.27 | Origin QC_Con-474_PEX-AIT-GPIT-GR-SP | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CON 474 | SAVANNA DRILLING #449 | J.20.063419 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-14 12:00 |  | 2020-08-14 12:00 | 2020-08-17 12:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:59 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.07 | Origin ¦ Reedy Creek 100 ¦ 7.875in Section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Reedy Creek 100 | SAVANNA DRILLING #449 | J.20.063418 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-17 10:00 |  | 2020-06-18 | 2020-06-18 13:00 |  |  | Roma WL | ZWahid | 2022-10-03 13:59 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.45 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 201 | SAVANNA DRILLING #449 | J.22.110230 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-01-07 06:00 |  | 2022-01-07 09:00 | 2022-01-07 22:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:58 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.25 | Origin ¦ CNS-288 ¦ AIT-PEX-GPIT-GR-SP | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CNS 288 | SAVANNA DRILLING #449 | J.20.063413 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-03 09:00 |  | 2020-08-03 20:00 | 2020-08-05 09:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:58 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.18 | Origin ¦ Orana North 211 ¦ 8.75in section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 211 | SAVANNA DRILLING #449 | J.20.063405 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-09 09:00 |  | 2020-07-09 12:00 | 2020-07-10 01:00 |  |  | Roma WL | ZWahid | 2022-10-03 13:58 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.10 | Origin ¦ Orana North 199 ¦ 8.75in Section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 199 | SAVANNA DRILLING #449 | J.20.063404 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-27 15:00 |  | 2020-06-28 02:00 | 2020-06-28 15:00 |  |  | Roma WL | ZWahid | 2022-10-03 13:57 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.37 | Origin ¦ Condabri 471 ¦ 7.875 in section ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI 471 | SAVANNA DRILLING #449 | J.20.063397 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-23 11:00 |  | 2020-09-23 18:00 | 2020-09-24 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:57 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 7017.54 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.32 | Condabri 477 / 7.875in section / AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | CONDABRI 477 | SAVANNA DRILLING #449 | J.20.063396 | RPE | ES-OH-Ops | Low | Operationally Complete | Execute - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-01 08:00 |  | 2020-09-01 20:00 | 2020-09-03 09:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:57 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.49 | QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 201 | SAVANNA DRILLING #449 | J.22.110229 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-01-12 |  | 2022-01-12 03:00 | 2022-01-12 16:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:56 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.02 | A.1004498.02.01 | Origin ¦ Orana North 188 ¦ 12.25in Section ¦ AIT-PEX | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 188 | SAVANNA DRILLING #449 | J.20.063392 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-03 15:00 |  | 2020-06-04 02:00 | 2020-06-04 15:00 |  |  | Roma WL | FDPSystemUser | 2022-10-03 13:56 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.29 | Origin ¦ Orana North 318 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 318 | SAVANNA DRILLING #449 | J.20.063479 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-26 05:00 |  | 2020-04-26 07:00 | 2020-04-27 07:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 14:08 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 |  |  |  |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.27 | Origin ¦ Orana North 296 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 296 | SAVANNA DRILLING #449 | J.20.063478 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-22 18:00 |  | 2020-04-23 02:30 | 2020-04-24 02:30 |  |  | Roma WL | MRony2 | 2022-10-03 14:08 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 |  |  |  |  | 50 | 33.3 | 0 | 25 | 32.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.26 | ORN297_QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 297 | SAVANNA DRILLING #449 | J.20.063477 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-19 18:00 |  | 2020-04-21 16:00 | 2020-04-22 16:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:08 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.46 | SAV449 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.20.063473 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-06-05 21:00 |  | 2020-06-05 21:00 | 2020-06-06 21:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 14:07 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.25 | Origin ¦ Orana North 288 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 288 | SAVANNA DRILLING #449 | J.20.063472 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-18 15:00 |  | 2020-04-18 15:00 | 2020-04-20 15:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:07 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.14 | Origin ¦ Orana North 300¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 300 | SAVANNA DRILLING #449 | J.20.063471 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-23 07:00 |  | 2020-03-24 | 2020-03-25 |  |  | Roma WL | MRony2 | 2022-10-03 14:07 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.02 | TAL289_QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Talinga 289 | SAVANNA DRILLING #449 | J.20.063470 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-28 |  | 2020-02-29 | 2020-03-01 |  |  | Roma WL | MRony2 | 2022-10-03 14:07 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Kiwi McConkey |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.39 | Origin ¦ Orana North 190 ¦ 8.75in Section ¦ HRLA-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 190 | SAVANNA DRILLING #449 | J.20.063461 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-22 21:00 |  | 2020-05-23 19:00 | 2020-05-24 19:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 14:05 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 8609.49 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.15 | ORN 321 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | ORANA NORTH 321 | SAVANNA DRILLING #449 | J.20.063460 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2020-02-05 14:00 | 2020-03-23 |  | 2020-03-28 14:00 | 2020-03-29 14:00 |  | 2020-02-23 14:00 | Roma WL | MRony2 | 2022-10-03 14:05 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 4970.76 |  |  | L3 - Full RO |  | 41.7 | 33.3 | 0 | 25 | 30 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.40 | Origin ¦ Orana North 189 ¦ 12.25in Section ¦ AIT-PEX | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 189 | SAVANNA DRILLING #449 | J.20.063454 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-26 21:00 |  | 2020-05-26 21:00 | 2020-05-27 21:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 14:04 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 |  |  |  |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.38 | Origin ¦ Orana North 190 ¦ 12.25in Section ¦ AIT-PEX | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 190 | SAVANNA DRILLING #449 | J.20.063453 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-21 20:00 |  | 2020-05-21 22:00 | 2020-05-22 22:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 14:04 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.10 | TAL301 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Talinga 301 | SAVANNA DRILLING #449 | J.20.063452 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-16 12:00 |  | 2020-03-17 12:00 | 2020-03-18 12:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:04 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.12 | Origin ¦ Talinga 302 ¦ AIT-PEX ¦ MAST-PPC-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Talinga 302 | SAVANNA DRILLING #449 | J.20.063448 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-20 08:00 |  | 2020-03-20 19:00 | 2020-03-21 19:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:04 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.03 | TAL294_QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Talinga 294 | SAVANNA DRILLING #449 | J.20.063447 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-02 |  | 2020-03-03 | 2020-03-05 |  |  | Roma WL | MRony2 | 2022-10-03 14:04 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Kiwi McConkey |  | 4320.99 |  |  |  |  | 50 | 33.3 | 0 | 50 | 40 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.07 | TAL292_QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Talinga 292 | SAVANNA DRILLING #449 | J.20.063441 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-07 12:30 |  | 2020-03-08 | 2020-03-09 |  |  | Roma WL | MRony2 | 2022-10-03 14:03 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Kiwi McConkey |  | 4320.99 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.08 | TAL295_QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | TALINGA 295 | SAVANNA DRILLING #449 | J.20.063440 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2020-02-04 | 2020-03-11 12:40 |  | 2020-03-12 | 2020-03-13 |  | 2020-03-16 13:43 | Roma WL | MRony2 | 2022-10-03 14:03 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Kiwi McConkey |  | 0 |  |  | L3 - Full RO |  | 41.7 | 33.3 | 0 | 25 | 30 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.35 | Origin ¦ Orana North 198 ¦ GPIT-HRLA-PEX-SP | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 198 | SAVANNA DRILLING #449 | J.20.063434 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-08 18:00 |  | 2020-05-09 | 2020-05-10 |  |  | Roma WL | SAndersen6 | 2022-10-03 14:02 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 |  |  |  |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.04 | TAL297_QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.20.063433 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-09 |  | 2020-03-10 | 2020-03-11 |  |  | Roma WL | MRony2 | 2022-10-03 14:02 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.28 | Origin ¦ Orana North 318 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 318 | SAVANNA DRILLING #449 | J.20.063431 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-24 18:00 |  | 2020-04-24 23:00 | 2020-04-25 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:01 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.20 | ORN 313 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 313 | SAVANNA DRILLING #449 | J.20.063430 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-03 14:00 |  | 2020-04-05 12:00 | 2020-04-06 12:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:01 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 |  |  |  |  | 50 | 33.3 | 0 | 25 | 32.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.18 | ORN307 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 307 | SAVANNA DRILLING #449 | J.20.063428 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-02 00:30 |  | 2020-04-02 12:00 | 2020-04-04 12:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:01 | FDPSystemUser |  | No |  |  |  |  | Laura Vaiciulyte |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.06 | TAL298_QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Talinga 298 | SAVANNA DRILLING #449 | J.20.063427 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2020-03-05 12:00 |  | 2020-03-06 | 2020-03-07 |  |  | Roma WL | MRony2 | 2022-10-03 14:01 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Kiwi McConkey |  | 4320.99 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.45 | SAV449 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.20.063422 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-06-09 21:00 |  | 2020-06-09 21:00 | 2020-06-10 21:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 14:00 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.33 | Origin ¦ Orana North 212 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 212 | SAVANNA DRILLING #449 | J.20.063421 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-02 19:00 |  | 2020-05-02 21:00 | 2020-05-03 21:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 14:00 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 |  |  |  |  | 58.3 | 33.3 | 0 | 50 | 42.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.42 | Origin ¦ Orana North 176 ¦ 12.25in Section ¦ HRLA-PEX | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 176 | SAVANNA DRILLING #449 | J.20.063417 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-29 21:00 |  | 2020-05-29 21:00 | 2020-05-30 21:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 13:59 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 |  |  |  |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.30 | Origin ¦ Orana North 329 ¦ AIT-PEX-GPIT ¦ MSIP-PPC-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 329 | SAVANNA DRILLING #449 | J.20.063416 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-27 10:00 |  | 2020-04-27 16:00 | 2020-04-28 16:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 13:59 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.22 | Origin ¦ Orana North 304 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 304 | SAVANNA DRILLING #449 | J.20.063415 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-11 10:00 |  | 2020-04-12 01:00 | 2020-04-13 01:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:59 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.17 | ORN306 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 306 | SAVANNA DRILLING #449 | J.20.063414 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-28 12:00 |  | 2020-04-04 15:00 | 2020-04-05 15:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:59 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.37 | Origin ¦ Orana North 213 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 213 | SAVANNA DRILLING #449 | J.20.063412 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-13 18:00 |  | 2020-05-14 16:00 | 2020-05-15 16:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 13:58 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 |  |  |  |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.16 | TAL303 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Talinga 303 | SAVANNA DRILLING #449 | J.20.063411 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-26 12:00 |  | 2020-03-26 18:00 | 2020-03-27 18:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:58 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.05 | Tal297_QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Talinga 297 | SAVANNA DRILLING #449 | J.20.063410 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-09 |  | 2020-03-10 22:00 | 2020-03-11 22:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:58 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.36 | Origin ¦ Orana North 213 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 213 | SAVANNA DRILLING #449 | J.20.063403 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-09 18:00 |  | 2020-05-10 10:00 | 2020-05-11 10:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 13:57 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.31 | Origin ¦ Orana North 329 ¦ AIT-PEX-GPIT ¦ MSIP-PPC-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 329 | SAVANNA DRILLING #449 | J.20.063402 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-27 18:00 |  | 2020-04-29 00:30 | 2020-04-30 00:30 |  |  | Roma WL | SAndersen6 | 2022-10-03 13:57 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 |  |  |  |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.23 | Origin ¦ Orana North 290 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 290 | SAVANNA DRILLING #449 | J.20.063401 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-13 12:00 |  | 2020-04-14 05:00 | 2020-04-15 05:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:57 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.11 | TAL300 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Talinga 300 | SAVANNA DRILLING #449 | J.20.063400 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-20 12:00 |  | 2020-03-20 12:00 | 2020-03-21 12:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:57 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.09 | TAL_299_QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | TALINGA 299 | SAVANNA DRILLING #449 | J.20.063399 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2020-02-17 14:00 | 2020-03-13 12:00 |  | 2020-03-28 14:00 | 2020-04-03 23:00 |  | 2020-03-11 23:00 | Roma WL | MRony2 | 2022-10-03 13:57 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 |  |  | L3 - Full RO |  | 41.7 | 33.3 | 0 | 25 | 30 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.41 | Origin ¦ Orana North 189 ¦ 8.75in Section ¦ HRLA-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 189 | SAVANNA DRILLING #449 | J.20.063395 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-28 21:00 |  | 2020-05-28 21:00 | 2020-05-29 21:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 13:57 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.32 | Origin ¦ Oana North 215 ¦ PEX-HRLA-GPIT ¦ MDT-GR | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 215 | SAVANNA DRILLING #449 | J.20.063394 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Required | In Progress |  | 2020-05-01 18:00 |  | 2020-05-01 18:00 | 2020-05-04 18:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 13:56 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 72547.11 |  |  |  |  | 58.3 | 16.7 | 0 | 25 | 30 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.19 | ORN 308 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 308 | SAVANNA DRILLING #449 | J.20.063393 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-03 12:00 |  | 2020-04-04 15:00 | 2020-04-05 21:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:56 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.44 | SAV449 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD |  | SAVANNA DRILLING #449 | J.20.063391 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-06-11 21:00 |  | 2020-06-11 21:00 | 2020-06-12 21:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 13:56 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.43 | Origin ¦ Orana North 176 ¦ 8.75in Section ¦ HRLA-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 176 | SAVANNA DRILLING #449 | J.20.063390 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-05-30 21:00 |  | 2020-05-31 11:00 | 2020-06-01 11:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 13:56 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 84632.88 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.34 | Origin ¦ Orana North 212 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 212 | SAVANNA DRILLING #449 | J.20.063389 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-02 19:00 |  | 2020-05-03 20:00 | 2020-05-05 20:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 13:56 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.24 | Origin ¦ Orana North 289 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 289 | SAVANNA DRILLING #449 | J.20.063388 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-15 12:00 |  | 2020-04-15 23:00 | 2020-04-16 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:56 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.21 | Origin ¦ ORN 309 ¦ AIT-PEX-GPIT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Orana North 309 | SAVANNA DRILLING #449 | J.20.063387 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-09 10:00 |  | 2020-04-09 23:00 | 2020-04-10 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:56 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.13 | Origin ¦ Talinga 302 ¦ 8.75in ¦ AIT-PEX-GPIT ¦ MAST-PPC-GPIT-GR | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Talinga 302 | SAVANNA DRILLING #449 | J.20.063386 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-22 02:00 |  | 2020-03-22 02:00 | 2020-03-23 02:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:56 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4970.76 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004498 | O.1004498.01 | A.1004498.01.01 | TAL290_QC | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | TALINGA 290 | SAVANNA DRILLING #449 | J.20.063385 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Required | In Progress | 2020-02-03 14:00 | 2020-02-14 |  | 2020-02-20 14:00 | 2020-02-21 14:00 |  | 2020-02-21 14:00 | Roma WL | JLawrie | 2022-10-03 13:55 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 5068.23 |  |  | L0 - No RO |  | 58.3 | 0 | 0 | 25 | 25 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004385 | O.1004385.04 | A.1004385.04.03 | PPC-USIT | ORIGIN ENERGY B2 PTY LTD |  | Silver City 40 | J.22.110890 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-11-25 01:00 | 2022-11-24 |  | 2022-11-25 | 2022-11-30 23:59 |  | 2022-12-01 00:59 | Roma WL | MRony2 | 2022-11-26 19:13 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004385 | O.1004385.04 | A.1004385.04.02 | OH for Origin NT | ORIGIN ENERGY B2 PTY LTD | Velkerri 76 S2-1 | Silver City 40 | J.23.008587 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2023-02-10 |  | 2023-02-15 | 2023-03-01 23:59 |  |  | Roma WL | MRony2 | 2022-11-06 14:11 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004385 | O.1004385.04 | A.1004385.04.01 | PPC log | ORIGIN ENERGY B2 PTY LTD | Velkerri 76 S2-1 | Silver City 40 | J.21.109428 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-08-28 | 2021-08-23 |  | 2021-08-28 | 2021-09-11 23:59 |  | 2021-09-11 23:59 | Roma WL | MRony2 | 2022-10-03 14:59 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  |  |  | 58.3 | 50 | 100 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004385 | O.1004385.03 | A.1004385.03.03 | Demob tools | ORIGIN ENERGY B2 PTY LTD | KYALLA 117 N2-1 | ENSIGN 963 | J.20.063380 | RPI | PS-WL-NO | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-04-16 |  | 2020-04-16 | 2020-04-21 |  |  | Roma WL | MRony2 | 2022-10-03 13:55 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 12643.27 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004385 | O.1004385.03 | A.1004385.03.04 | Quarantine fee | ORIGIN ENERGY B2 PTY LTD | KYALLA 117 N2-1 | ENSIGN 963 | J.20.063377 | RPI | PS-WL-NO | Low | Unconfirmed - 90% | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-10-09 |  | 2020-10-09 | 2020-10-14 |  |  | Roma WL | MRony2 | 2022-10-03 13:54 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 20542.06 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004385 | O.1004385.03 | A.1004385.03.02 | Unit rental_April | ORIGIN ENERGY B2 PTY LTD | KYALLA 117 N2-1 | ENSIGN 963 | J.20.063370 | RPI | PS-WL-NO | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-04-16 |  | 2020-04-16 | 2020-04-21 |  |  | Roma WL | MRony2 | 2022-10-03 13:54 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 39311.24 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004385 | O.1004385.03 | A.1004385.03.01 | Rental Unit March | ORIGIN ENERGY B2 PTY LTD | KYALLA 117 N2-1 | ENSIGN 963 | J.20.063369 | RPI | PS-WL-NO | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-03-18 |  | 2020-03-18 | 2020-03-25 |  |  | Roma WL | ZWahid | 2022-10-03 13:54 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 64977.26 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004385 | O.1004385.02 | A.1004385.02.01 | Techlog coaching | ORIGIN ENERGY B2 PTY LTD | KYALLA 117 N2-1 | ENSIGN 963 | J.20.063376 | RPE | ES-OH-NO | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-03-15 |  | 2020-03-15 | 2020-03-20 |  |  | Roma WL | MRony2 | 2022-10-03 13:54 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 6985.06 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004385 | O.1004385.01 | A.1004385.01.01 | Kyalla 117 Ops | ORIGIN ENERGY B2 PTY LTD | KYALLA 117 N2-1, CND 039 | Silver City 40 | J.20.063382 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-22 |  | 2020-01-24 12:00 | 2020-02-02 |  |  | Roma WL | JLawrie | 2022-10-03 13:55 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 128093.24 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004385 | O.1004385.01 | A.1004385.01.06 | Plug | ORIGIN ENERGY B2 PTY LTD | KYALLA 117 N2-1 | Silver City 40 | J.20.063379 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-10-12 |  | 2020-10-12 | 2020-10-25 |  |  | Roma WL | MRony2 | 2022-10-03 13:55 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 77397.16 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004385 | O.1004385.01 | A.1004385.01.03 | Origin NT - Open Hole 1 | ORIGIN ENERGY B2 PTY LTD | Velkerri 76 S2-1 | Silver City 40 | J.21.108929 | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-09-26 |  | 2021-10-01 13:00 | 2021-10-30 12:00 |  |  | Roma WL | ZWahid | 2022-10-03 13:55 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004385 | O.1004385.01 | A.1004385.01.04 | Origin NT - CBL 2 | ORIGIN ENERGY B2 PTY LTD |  | Silver City 40 | J.21.108928 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-08-21 |  | 2021-08-22 | 2021-08-29 |  |  | Roma WL | ZWahid | 2022-10-03 13:54 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1004385 | O.1004385.01 | A.1004385.01.02 | Kyalla-117 CBL | ORIGIN ENERGY B2 PTY LTD | KYALLA 117 N2-1 | Silver City 40 | J.20.063372 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-25 |  | 2020-02-26 | 2020-03-01 |  |  | Roma WL | ZWahid | 2022-10-03 13:54 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004385 | O.1004385.01 | A.1004385.01.05 | Pump Down Perfo Plug | ORIGIN ENERGY B2 PTY LTD | KYALLA 117 N2-1 | Silver City 40 | J.20.063367 | RPI | PS-WL-Ops | High | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2020-08-06 | 2020-08-31 |  | 2020-09-13 | 2020-10-06 |  | 2020-10-06 02:00 | Roma WL | ZWahid | 2022-10-03 13:54 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 45484.08 |  |  | L0 - No RO |  | 75 | 50 | 0 | 50 | 52.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004382 | O.1004382.02 | A.1004382.02.02 | 2nd PLT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | SOUTH BURUNGA 2 | RIGLESS - AUSTRALIA | J.20.063384 | RPI | PS-WL-NO | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-02-24 |  | 2020-02-24 | 2020-02-25 |  |  | Roma WL | MRony2 | 2022-10-03 13:55 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 18026.38 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004382 | O.1004382.02 | A.1004382.02.05 | Crane rental_April MPBT_PLT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | SOUTH BURUNGA 2 | RIGLESS - AUSTRALIA | J.20.063381 | RPI | PS-WL-NO | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-03-23 |  | 2020-03-23 | 2020-03-24 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:55 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 26593.02 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004382 | O.1004382.02 | A.1004382.02.04 | Rental March Crane & Movement | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | SOUTH BURUNGA 2 | RIGLESS - AUSTRALIA | J.20.063378 | RPI | PS-WL-NO | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-03-23 |  | 2020-03-23 | 2020-03-24 23:00 |  |  | Roma WL | ZWahid | 2022-10-03 13:55 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004382 | O.1004382.02 | A.1004382.02.06 | Mob-demob | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | SOUTH BURUNGA 2 | RIGLESS - AUSTRALIA | J.20.063374 | RPI | PS-WL-NO | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-03-23 |  | 2020-03-23 | 2020-03-24 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:54 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 11490.29 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004382 | O.1004382.02 | A.1004382.02.03 | Crane for PLT-1 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | SOUTH BURUNGA 2 | RIGLESS - AUSTRALIA | J.20.063373 | RPI | PS-WL-NO | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-02-23 |  | 2020-02-23 | 2020-02-24 |  |  | Roma WL | MRony2 | 2022-10-03 13:54 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 13525.02 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004382 | O.1004382.02 | A.1004382.02.01 | Rental Crane Nov-Dec 2019 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | Monthly Rental | RIGLESS - AUSTRALIA |  | RPI | PS-WL-NO | InComplete | Confirmed | Design - PSD |  | Not Started | Not Started | In Progress |  | 2020-01-31 |  | 2020-02-02 | 2020-02-02 |  |  | Roma WL | ZWahid | 2020-01-31 19:21 | ZWahid |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004382 | O.1004382.01 | A.1004382.01.02 | Deep Gas Wireline - PLT 2 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | SOUTH BURUNGA 2 | RIGLESS - AUSTRALIA | J.20.063383 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-20 |  | 2020-02-20 18:00 | 2020-02-26 18:00 |  |  | Roma WL | ZWahid | 2022-10-03 13:55 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 95026.98 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004382 | O.1004382.01 | A.1004382.01.04 | Westgrove 9 | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | SOUTH BURUNGA 2 | RIGLESS - AUSTRALIA | J.21.108930 | RPI | PS-WL-NO | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-07-29 |  | 2021-07-31 | 2021-08-12 |  |  | Roma WL | MRony2 | 2022-10-03 13:55 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1004382 | O.1004382.01 | A.1004382.01.05 | Deep Gas Wireline - PLT MPBT and DBA | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | SOUTH BURUNGA 2 | RIGLESS - AUSTRALIA | J.20.063375 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-04-04 |  | 2020-04-06 15:00 | 2020-04-14 15:00 |  |  | Roma WL | ZWahid | 2022-10-03 13:54 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 95026.98 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004382 | O.1004382.01 | A.1004382.01.01 | Deep Gas Wireline - PLT | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | SOUTH BURUNGA 2 | RIGLESS - AUSTRALIA | J.20.063371 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-31 |  | 2020-01-31 18:00 | 2020-02-06 18:00 |  |  | Roma WL | JLawrie | 2022-10-03 13:54 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 95026.98 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004382 | O.1004382.01 | A.1004382.01.03 | Deep Gas Wireline - MPBT and DBA | ORIGIN ENERGY UPSTREAM OPERATOR PTY LTD | SOUTH BURUNGA 2 | RIGLESS - AUSTRALIA | J.20.063368 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-03-15 |  | 2020-03-18 12:00 | 2020-04-02 12:00 |  |  | Roma WL | ZWahid | 2022-10-03 13:54 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 113973.33 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004337 | O.1004337.01 | A.1004337.01.01 | AIT-PEX-GPIT - Combabula 400 | ORIGIN ENERGY RESOURCES LIMITED | COMBABULA 400 | SAVANNA DRILLING #406 | J.20.063366 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2020-01-16 20:00 | 2020-01-16 |  | 2020-01-17 20:00 | 2020-01-18 20:00 |  | 2020-01-17 20:00 | Roma WL | RWijaya | 2022-10-03 13:53 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 6049.38 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 25 | 20 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004337 | O.1004337.01 | A.1004337.01.04 | RCK135 PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED | Reedy Creek 135 | SAVANNA DRILLING #406 | J.20.063365 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-27 12:36 |  | 2020-01-28 12:06 | 2020-01-30 12:36 |  |  | Roma WL | MHanna2 | 2022-10-03 13:53 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004337 | O.1004337.01 | A.1004337.01.02 | AIT-PEX-GPIT - RCK104 | ORIGIN ENERGY RESOURCES LIMITED | Reedy Creek 104 | SAVANNA DRILLING #406 | J.20.063364 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-17 10:00 |  | 2020-01-20 10:00 | 2020-01-21 10:00 |  |  | Roma WL | PLima7 | 2022-10-03 13:53 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004337 | O.1004337.01 | A.1004337.01.06 | Sav406_RCK103 | ORIGIN ENERGY RESOURCES LIMITED | REEDY CREEK 103 | SAVANNA DRILLING #406 | J.20.063363 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2020-01-29 00:56 | 2020-02-01 12:36 |  | 2020-02-03 00:56 | 2020-02-05 01:26 |  | 2020-01-31 01:26 | Roma WL | MRony2 | 2022-10-03 13:53 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 25 | 20 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004337 | O.1004337.01 | A.1004337.01.05 | Reedy Creek 073 | ORIGIN ENERGY RESOURCES LIMITED | REEDY CREEK 73 | SAVANNA DRILLING #406 | J.20.063362 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2020-01-30 14:53 | 2020-01-29 |  | 2020-01-30 12:00 | 2020-02-01 12:02 |  | 2020-02-01 12:02 | Roma WL | MHanna2 | 2022-10-03 13:53 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 25 | 20 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004337 | O.1004337.01 | A.1004337.01.03 | AIT-PEX-GPIT - RCK074 | ORIGIN ENERGY RESOURCES LIMITED | Reedy Creek 74 | SAVANNA DRILLING #406 | J.20.063361 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-20 10:00 |  | 2020-01-23 10:00 | 2020-01-24 10:00 |  |  | Roma WL | PLima7 | 2022-10-03 13:53 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1004336 | O.1004336.01 | A.1004336.01.01 | LAV02-ST1 Workover | WOODSIDE ENERGY LTD | LAVERDA NORTH 2 | ENSCO DPS-1 | J.20.062342 | RPI | TSWT-DSGN | InComplete | Unconfirmed - 90% | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-04-30 |  | 2020-05-01 10:55 | 2020-06-01 |  |  | APG TS | RWallis | 2022-10-03 06:24 | FDPSystemUser |  | No |  |  |  |  | Wayne Wallis |  | 56194.09 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Richard Steers | TS Surface Testing
P.1004336 | O.1004336.01 | A.1004336.01.03 | Well test Bleed off Operations | WOODSIDE ENERGY LTD | Laverda North 2 | ENSCO DPS-1 | J.20.062341 | RPI | TSWT-FPDO-JOB | InComplete | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-05-17 |  | 2020-06-11 | 2020-07-16 23:59 |  |  | APG TS | AFrancis4 | 2022-10-03 06:23 | FDPSystemUser |  | No |  | [AUNB-TSWT] - Perth- New Burn STT |  |  | Allwyn Francis |  | 2365984.71 | [10 empty] | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1004336 | O.1004336.01 | A.1004336.01.02 | Lav02 Well test operations offshore | WOODSIDE ENERGY LTD | Laverda North 2 | ENSCO DPS-1 | J.20.062340 | RPI | TSWT-FLOWBACK-JOB | InComplete | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-05-17 |  | 2020-05-21 | 2020-06-25 23:59 |  |  | APG TS | AFrancis4 | 2022-10-03 06:23 | FDPSystemUser |  | No |  | [AUNB-TSWT] - Perth- New Burn STT |  |  | Allwyn Francis |  | 0 | [10 empty] | 0 | [7 empty] | Richard Steers | TS Surface Testing
P.1004319 | O.1004319.03 | A.1004319.03.02 | Jarrar7-3 3/8" HSD+GR | SANTOS LIMITED | Jarrar 7 | Wild Desert Rig 20 | J.20.062942 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-03-09 10:00 | 2020-03-07 | 2020-03-09 | 2020-03-09 10:00 | 2020-03-11 | 2020-03-12 | 2020-03-11 | Moomba WL | ymoradi2 | 2022-10-03 11:00 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1004319 | O.1004319.03 | A.1004319.03.03 | Jarrar-8_3 3/8"HSD+GR | SANTOS LIMITED | Jarrar 8 | Wild Desert Rig 20 | J.20.062934 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-05-17 | 2020-05-15 |  | 2020-05-17 | 2021-05-20 14:00 |  | 2020-07-24 01:00 | Moomba WL | ymoradi2 | 2022-10-03 10:59 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  |  |  | 66.7 | 0 | 0 | 0 | 20 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1004319 | O.1004319.03 | A.1004319.03.04 | Zeus4_Perforation_3 3/8" HSD | SANTOS LIMITED |  | Wild Desert Rig 20 | J.20.062932 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Design Completed | In Progress | 2020-03-13 | 2020-03-12 |  | 2020-03-13 | 2020-03-14 |  | 2020-03-14 | Moomba WL | ymoradi2 | 2022-10-03 10:59 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1004319 | O.1004319.03 | A.1004319.03.01 | Jarrar-6_3 3/8" HSD perforation+GR | SANTOS LIMITED | JARRAR 6 | Wild Desert Rig 20 | J.20.062931 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-03-06 06:00 | 2020-03-04 16:00 |  | 2020-03-06 06:00 | 2020-03-08 |  | 2020-03-08 | Moomba WL | ymoradi2 | 2022-10-03 10:59 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1004319 | O.1004319.02 | A.1004319.02.01 | Irtalie East 6 - HSD Perfo | SANTOS LIMITED | Irtalie East 6 | Wild Desert Rig 20 | J.20.062930 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-05-03 11:30 | 2020-05-01 12:00 |  | 2020-05-04 16:00 | 2020-05-06 08:00 |  | 2020-05-05 03:30 | Moomba WL | AHermawan | 2022-10-03 10:59 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1004319 | O.1004319.01 | A.1004319.01.01 | Endeavour 7 Rig Support | SANTOS LIMITED | Endeavour 7 | Wild Desert Rig 20 | J.20.062941 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-01-18 06:00 | 2020-01-18 |  | 2020-01-18 06:00 | 2020-01-20 06:00 |  | 2020-01-20 06:00 | Moomba WL | SGilbert | 2022-10-03 11:00 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1004319 | O.1004319.01 | A.1004319.01.09 | Jarrar 8 Perfo | SANTOS LIMITED | Jarrar 8 | Wild Desert Rig 20 | J.20.062940 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-05-26 | 2020-05-25 |  | 2020-05-26 | 2020-05-28 23:59 |  | 2020-05-28 23:59 | Moomba WL | ymoradi2 | 2022-10-03 11:00 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1004319 | O.1004319.01 | A.1004319.01.08 | Jarrar 7 perfo | SANTOS LIMITED | Jarrar 7 | Wild Desert Rig 20 | J.20.062939 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-05-21 | 2020-05-20 |  | 2020-05-21 | 2020-05-23 23:59 |  | 2020-05-23 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:59 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1004319 | O.1004319.01 | A.1004319.01.07 | Jarrar 6 Perfo | SANTOS LIMITED | Jarrar 6 | Wild Desert Rig 20 | J.20.062938 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-05-16 12:00 | 2020-05-16 |  | 2020-05-16 12:00 | 2020-05-19 02:59 |  | 2020-05-19 02:59 | Moomba WL | ymoradi2 | 2022-10-03 10:59 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1004319 | O.1004319.01 | A.1004319.01.03 | Talgeberry 2 -3 3/8" HSD Perfo | SANTOS LIMITED | Talgeberry 2 | Wild Desert Rig 20 | J.20.062937 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-02-13 | 2020-02-01 |  | 2020-02-13 | 2020-02-15 |  | 2020-02-15 | Moomba WL | SGilbert | 2022-10-03 10:59 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 19318.04 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1004319 | O.1004319.01 | A.1004319.01.06 | Irtalie East 6- 3 3/8" HSD Perfo | SANTOS LIMITED | Irtalie East 6 | Wild Desert Rig 20 | J.20.062936 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-05-09 13:00 | 2020-05-09 18:00 |  | 2020-05-10 08:00 | 2020-05-11 |  | 2020-05-10 05:00 | Moomba WL | ymoradi2 | 2022-10-03 10:59 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1004319 | O.1004319.01 | A.1004319.01.02 | Tekyah 3 PErforation | SANTOS LIMITED | TAKYAH 3 | Wild Desert Rig 20 | J.20.062935 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-01-29 12:00 | 2020-01-21 |  | 2020-01-29 12:00 | 2020-01-31 12:00 |  | 2020-01-31 12:00 | Moomba WL | SGilbert | 2022-10-03 10:59 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 8099.81 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1004319 | O.1004319.01 | A.1004319.01.04 | patroclus 2 | SANTOS LIMITED | Patroclus 2 | Wild Desert Rig 20 | J.20.062933 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-04-03 06:00 | 2020-03-29 |  | 2020-04-03 06:00 | 2020-04-05 05:00 |  | 2020-04-05 05:00 | Moomba WL | SGilbert | 2022-10-03 10:59 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 8336.05 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1004319 | O.1004319.01 | A.1004319.01.05 | Zues 4 Perforation | SANTOS LIMITED | Zeus Dev F | Wild Desert Rig 20 |  | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-04-15 | 2020-04-14 | 2020-04-14 | 2020-04-15 | 2020-04-16 01:00 | 2020-04-19 | 2020-04-18 01:00 | Moomba WL | SGilbert | 2020-04-22 08:18 | AGamero |  | No |  |  |  |  | Rob Twigg |  | 19318.04 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1004301 | O.1004301.03 | A.1004301.03.02 | March Rentals | ESSO AUSTRALIA LTD | BTW W2 | Noble Tom Prosser | J.20.063020 | RPI | PS-SLK-NO | InComplete | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-03-20 |  | 2020-03-20 | 2020-03-25 |  |  | New Burn WL | frosa2 | 2022-10-03 09:48 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | Wireline Slickline
P.1004301 | O.1004301.03 | A.1004301.03.01 | FS2 contingency ops | ESSO AUSTRALIA LTD | BTW W2 | Noble Tom Prosser | J.20.063016 | RPI | PS-SLK-Rental-Ops | High | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-03-18 |  | 2020-04-10 | 2020-04-25 |  |  | New Burn WL | frosa2 | 2022-10-03 09:47 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 265111.58 | [10 empty] | 0 | [7 empty] | Luis Cardenas | Wireline Slickline
P.1004301 | O.1004301.01 | A.1004301.01.02 | Sculpin-1 | ESSO AUSTRALIA LTD | BTW W2 | Noble Tom Prosser | J.20.063019 | RPE | ES-OH-NO | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-06 |  | 2020-02-13 10:00 | 2020-04-11 10:00 |  |  | New Burn WL | LParedes | 2022-10-03 09:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004301 | O.1004301.01 | A.1004301.01.01 | West Barracouta 1 & 2 | ESSO AUSTRALIA LTD | BTW W2 | Noble Tom Prosser | J.20.063017 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-06 |  | 2020-02-13 10:00 | 2020-04-11 10:00 |  |  | New Burn WL | LParedes | 2022-10-03 09:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 268326.44 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004300 | O.1004300.01 | A.1004300.01.01 | Esso SIT Resolve | ESSO AUSTRALIA LTD |  | Noble Tom Prosser | J.20.063018 | RPI | PS-WL-NO | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-01-20 |  | 2020-01-20 | 2020-01-24 |  |  | New Burn WL | frosa2 | 2022-10-03 09:47 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1004298 | O.1004298.01 | A.1004298.01.01 | Well TBD | SANTOS LIMITED |  | Saxon Rig 183 | J.20.062929 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-04-06 | 2020-04-06 |  | 2020-04-06 | 2020-04-09 |  | 2020-04-09 | Moomba WL | AGamero | 2022-10-03 10:59 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1004276 | O.1004276.01 | A.1004276.01.10 | Bayu October | SANTOS NA (19-12) PTY LTD |  | RIGLESS - AUSTRALIA | J.23.008562 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-06-18 | 2025-06-17 | 2025-06-18 16:00 | 2025-06-18 | 2025-07-10 23:59 | 2025-06-29 16:00 | 2025-07-14 09:08 | New Burn WL | BAhmad | 2025-06-30 11:08 | MElsanousi |  | No |  |  |  |  | Justin Dukas |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 2 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004276 | O.1004276.01 | A.1004276.01.12 | Bayu December | SANTOS NA (19-12) PTY LTD |  | RIGLESS - AUSTRALIA | J.23.008564 | RPI | PS-WL-Ops | High | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2025-08-18 | 2025-08-17 |  | 2025-08-18 | 2025-09-09 23:59 |  | 2025-09-13 09:08 | New Burn WL | BAhmad | 2024-01-31 19:57 | MElsanousi |  | No |  |  |  |  | Justin Dukas |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 2 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004276 | O.1004276.01 | A.1004276.01.11 | Nov Activity | SANTOS NA (19-12) PTY LTD |  | RIGLESS - AUSTRALIA | J.23.008563 | RPI | PS-WL-Ops | High | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2025-07-19 | 2025-07-18 |  | 2025-07-19 | 2025-08-10 23:59 |  | 2025-08-14 09:08 | New Burn WL | BAhmad | 2024-01-31 19:57 | MElsanousi |  | No |  |  |  |  | Justin Dukas |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 2 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004276 | O.1004276.01 | A.1004276.01.08 | Bayu Undan_Nov | SANTOS NA (19-12) PTY LTD |  | RIGLESS - AUSTRALIA | J.23.008558 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-10-19 | 2024-10-18 |  | 2024-10-19 | 2024-11-10 23:59 |  | 2024-11-14 09:08 | New Burn WL | BAhmad | 2023-11-14 17:50 | JDukas |  | No |  |  |  |  | James Cade |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004276 | O.1004276.01 | A.1004276.01.07 | Sept Activity Bayu Rigless | SANTOS NA (19-12) PTY LTD |  | RIGLESS - AUSTRALIA | J.22.110106 | RPI | PS-WL-NO | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-04-29 | 2023-04-25 |  | 2023-04-29 | 2023-05-18 23:59 |  | 2023-05-18 23:59 | New Burn WL | frosa2 | 2023-01-10 16:49 | JDukas |  | No |  |  |  |  | Justin Dukas |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 33.3 | 100 | 50 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004276 | O.1004276.01 | A.1004276.01.15 | Bayu August Operations | SANTOS NA (19-12) PTY LTD | BU-D09 | RIGLESS - AUSTRALIA | J.22.110163 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-09-28 |  | 2022-10-05 | 2022-11-07 23:59 |  |  | New Burn WL | JDukas | 2022-10-03 10:01 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1004276 | O.1004276.01 | A.1004276.01.14 | Bayu June ops | SANTOS NA (19-12) PTY LTD | BU-D09, BU-D04, BU-D15 | RIGLESS - AUSTRALIA | J.22.110158 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-05-28 |  | 2022-06-12 | 2022-07-08 23:59 |  |  | New Burn WL | JDukas | 2022-10-03 10:01 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 50416.75 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1004276 | O.1004276.01 | A.1004276.01.13 | Bayu Feb ops | SANTOS NA (19-12) PTY LTD | BU-W10, BU-W13, W12 | RIGLESS - AUSTRALIA | J.22.110138 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-01-15 |  | 2022-01-26 | 2022-02-28 23:59 |  |  | New Burn WL | JDukas | 2022-10-03 09:59 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 586562.19 | 3 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004276 | O.1004276.01 | A.1004276.01.09 | Bayu Undan Oct21 Australian Rentals | SANTOS NA (19-12) PTY LTD | BU-D04 | RIGLESS - AUSTRALIA | J.21.108885 | RPI | PS-WL-NO | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2021-10-14 |  | 2021-10-14 | 2021-10-18 23:59 |  |  | New Burn WL | crowand | 2022-10-03 09:55 | FDPSystemUser |  | No |  |  |  |  | James Cade |  | 311000.88 | 0 |  | L0 - No RO |  | 50 | 33.3 | 100 | 50 | 50 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004276 | O.1004276.01 | A.1004276.01.06 | Aug Activity Bayu Rigless | SANTOS NA (19-12) PTY LTD | BU-D04, BU-D09 | RIGLESS - AUSTRALIA | J.21.108854 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-10-14 |  | 2021-10-25 | 2021-11-23 23:59 |  |  | New Burn WL | frosa2 | 2022-10-03 09:51 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 151656.84 | 2 |  |  |  | 91.7 | 50 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004276 | O.1004276.01 | A.1004276.01.05 | May Crew and Rentals | SANTOS NA (19-12) PTY LTD | BU- D10 | RIGLESS - AUSTRALIA | J.21.108853 | RPI | PS-WL-NO | Low | Confirmed | Execute - PSD |  | Not Required | Not Started | In Progress |  | 2021-05-03 |  | 2021-05-03 | 2021-05-07 23:59 |  |  | New Burn WL | crowand | 2022-10-03 09:51 | FDPSystemUser |  | No |  |  |  |  | James Cade |  | 0 | 0 |  | L0 - No RO |  | 58.3 | 50 | 100 | 50 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004276 | O.1004276.01 | A.1004276.01.01 | Intervention Ops | SANTOS NA (19-12) PTY LTD | BU-D06, BU- D10 | RIGLESS - AUSTRALIA | J.20.063012 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-31 |  | 2020-09-07 | 2020-09-25 |  |  | New Burn WL | LParedes | 2022-10-03 09:47 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 122076.1 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1004276 | O.1004276.01 | A.1004276.01.04 | March Ops | SANTOS NA (19-12) PTY LTD |  | RIGLESS - AUSTRALIA | J.21.108829 | RPI | PS-WL-NO | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-03-25 00:03 |  | 2021-03-26 00:03 | 2021-04-22 00:03 |  |  | New Burn WL | frosa2 | 2022-10-03 09:46 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1004276 | O.1004276.01 | A.1004276.01.03 | Feb OPS | SANTOS NA (19-12) PTY LTD |  | RIGLESS - AUSTRALIA | J.21.108824 | RPI | PS-WL-NO | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-02-25 00:02 |  | 2021-02-26 00:01 | 2021-03-25 00:02 |  |  | New Burn WL | frosa2 | 2022-10-03 09:45 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1004276 | O.1004276.01 | A.1004276.01.02 | DPP Q1 21 Resolve Campaign | SANTOS NA (19-12) PTY LTD | BU- D10 | RIGLESS - AUSTRALIA | J.21.108823 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2021-03-23 |  | 2021-04-14 | 2021-05-10 |  |  | New Burn WL | frosa2 | 2022-10-03 09:45 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 187577.2 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004274 | O.1004274.01 | A.1004274.01.22 | Artisan 1 FIS Samples | BEACH ENERGY LTD | ARTISAN-1 | Ocean Onyx | J.23.105366 | RPI | PS-WL-NO | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | Not Started |  | 2023-06-24 |  | 2023-06-25 | 2023-06-30 23:59 |  |  | New Burn WL | miqbal13 | 2023-06-26 11:24 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 12000 | 0 |  | L0 - No RO |  | 41.7 | 33.3 | 100 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1004274 | O.1004274.01 | A.1004274.01.21 | TN2 ¦ CH operations | BEACH ENERGY LTD | THYLACINE NORTH-2 | Ocean Onyx | J.22.110149 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-06-06 |  | 2022-06-06 06:00 | 2022-07-04 05:59 |  |  | New Burn WL | JDukas | 2022-10-03 10:00 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1004274 | O.1004274.01 | A.1004274.01.20 | TW2¦ CH Operation | BEACH ENERGY LTD | THYLACINE WEST-2 | Ocean Onyx | J.22.110148 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-04-07 |  | 2022-04-09 06:00 | 2022-04-26 05:59 |  |  | New Burn WL | JDukas | 2022-10-03 10:00 | FDPSystemUser |  | No |  |  |  | ROE WL Abu Dhabi | Rob Twigg |  | 0 | 6 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004274 | O.1004274.01 | A.1004274.01.19 | TWI¦ OH & CH Operation | BEACH ENERGY LTD | THYLACINE WEST-1 | Ocean Onyx | J.22.110143 | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-01-31 |  | 2022-02-08 06:00 | 2022-03-07 05:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:59 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 103861.27 | 3 |  |  |  | 83.3 | 33.3 | 0 | 50 | 50 |  | 0 |  |  |  | 0 |  |  |  | Alonso Alejandro Gamero Acuna | WL Evaluation Services
P.1004274 | O.1004274.01 | A.1004274.01.18 | Beach ¦ Thylacine North 1 ¦ Ocean Onyx ¦ CCL-CBL-VDL-XPT-GR | BEACH ENERGY LTD | THYLACINE NORTH-1 | Ocean Onyx | J.21.108887 | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-11-30 |  | 2021-12-06 06:00 | 2021-12-09 05:59 |  |  | New Burn WL | EBrobbey | 2022-10-03 09:58 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 61513.97 | 3 |  |  |  | 91.7 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1004274 | O.1004274.01 | A.1004274.01.17 | Beach ¦ Geographe-4 ¦ Ocean Onyx ¦ Intervention | BEACH ENERGY LTD | Geographe-4 | Ocean Onyx | J.21.108882 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-11-01 |  | 2021-11-01 | 2021-11-11 |  |  | New Burn WL | BAhmad | 2022-10-03 09:55 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 0 | 0 |  |  |  | 75 | 66.7 | 100 | 75 | 75 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004274 | O.1004274.01 | A.1004274.01.16 | Oct-Beach Activity | BEACH ENERGY LTD | GEOGRAPHE 4, GEOGRAPHE 5 | Ocean Onyx | J.21.108881 | RPI | PS-WL-NO | High | Confirmed | Design - CEC |  | Design Completed | Not Started | In Progress | 2021-09-14 | 2021-10-01 |  | 2021-10-01 | 2021-10-11 |  | 2021-10-13 | New Burn WL | BAhmad | 2022-10-03 09:55 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Justin Dukas |  | 0 | 0 |  | L3 - Full RO |  | 75 | 66.7 | 100 | 75 | 75 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004274 | O.1004274.01 | A.1004274.01.15 | Dec Activity_Beach | BEACH ENERGY LTD | GEOGRAPHE 4, GEOGRAPHE 5 | Ocean Onyx | J.21.108857 | RPI | PS-WL-NO | High | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2021-10-31 | 2021-11-15 |  | 2021-11-17 | 2021-11-27 |  | 2021-11-29 | New Burn WL | BAhmad | 2022-10-03 09:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Felipe Donizeti Rosa |  | 0 | 0 |  | L3 - Full RO |  | 50 | 33.3 | 100 | 50 | 50 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004274 | O.1004274.01 | A.1004274.01.14 | July Activity | BEACH ENERGY LTD | GEOGRAPHE 4, GEOGRAPHE 5, ARTISAN-1 | Ocean Onyx | J.21.108846 | RPI | PS-WL-NO | High | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2021-09-02 | 2021-09-01 |  | 2021-09-02 | 2021-09-12 00:59 |  | 2021-09-12 00:59 | New Burn WL | frosa2 | 2022-10-03 09:51 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 596.98 | 6 |  | L0 - No RO |  | 58.3 | 33.3 | 100 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004274 | O.1004274.01 | A.1004274.01.13 | June Activity | BEACH ENERGY LTD | GEOGRAPHE 4, GEOGRAPHE 5 | Ocean Onyx | J.21.108845 | RPI | PS-WL-NO | High | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2021-08-17 | 2021-09-02 |  | 2021-09-03 | 2021-09-24 |  | 2021-09-25 | New Burn WL | frosa2 | 2022-10-03 09:50 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Felipe Donizeti Rosa |  | 529762.18 | 0 |  | L3 - Full RO |  | 58.3 | 33.3 | 100 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004274 | O.1004274.01 | A.1004274.01.12 | Aug Activity | BEACH ENERGY LTD | GEOGRAPHE 4, GEOGRAPHE 5 | Ocean Onyx | J.21.108844 | RPI | PS-WL-NO | High | Confirmed | Design - CEC |  | Design Completed | Not Started | In Progress | 2021-05-17 | 2021-09-01 |  | 2021-09-03 | 2021-09-22 |  | 2021-12-24 | New Burn WL | frosa2 | 2022-10-03 09:50 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Felipe Donizeti Rosa |  | 190448.34 | 0 |  | L3 - Full RO |  | 66.7 | 50 | 100 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004274 | O.1004274.01 | A.1004274.01.04 | Ocean Onyx M3 | BEACH ENERGY LTD |  | Ocean Onyx | J.21.108835 | RPE | ES-CH-NO | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-03-26 |  | 2021-03-26 | 2021-04-25 |  |  | New Burn WL | LParedes | 2022-10-03 09:47 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004274 | O.1004274.01 | A.1004274.01.08 | Ocean Onyx M7 | BEACH ENERGY LTD |  | Ocean Onyx | J.21.108834 | RPE | ES-OH-NO | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-07-26 |  | 2021-07-26 | 2021-08-25 |  |  | New Burn WL | LParedes | 2022-10-03 09:47 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004274 | O.1004274.01 | A.1004274.01.02 | Ocean Onyx Project non Operational for fixed rental | BEACH ENERGY LTD |  | Ocean Onyx | J.21.108831 | RPI | PS-WL-NO | High | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-02-01 |  | 2021-04-01 | 2022-07-18 |  |  | New Burn WL | LParedes | 2022-10-03 09:46 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Felipe Donizeti Rosa |  | 1981.81 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004274 | O.1004274.01 | A.1004274.01.06 | Ocean Onyx M5 | BEACH ENERGY LTD |  | Ocean Onyx | J.21.108826 | RPE | ES-OH-NO | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-05-26 |  | 2021-05-26 | 2021-06-25 |  |  | New Burn WL | LParedes | 2022-10-03 09:45 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004274 | O.1004274.01 | A.1004274.01.03 | Ocean Onyx M2 | BEACH ENERGY LTD |  | Ocean Onyx | J.21.108825 | RPE | ES-OH-NO | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-02-26 |  | 2021-02-26 | 2021-03-25 |  |  | New Burn WL | LParedes | 2022-10-03 09:45 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004274 | O.1004274.01 | A.1004274.01.11 | Beach Energy ¦ Artisan-1 ¦ Ocean Onyx | BEACH ENERGY LTD | ARTISAN-1 | Ocean Onyx | J.21.108822 | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-02-26 |  | 2021-03-08 | 2021-03-22 00:59 |  |  | New Burn WL | frosa2 | 2022-10-03 09:44 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 436534.9 | [10 empty] | 0 | [7 empty] | Bilal Ahmad | WL Evaluation Services
P.1004274 | O.1004274.01 | A.1004274.01.09 | Ocean Onyx M8 | BEACH ENERGY LTD |  | Ocean Onyx | J.21.108820 | RPE | ES-OH-NO | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-08-26 |  | 2021-08-26 | 2021-09-25 |  |  | New Burn WL | LParedes | 2022-10-03 09:44 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004274 | O.1004274.01 | A.1004274.01.10 | Ocean Onyx M9 | BEACH ENERGY LTD |  | Ocean Onyx | J.21.108819 | RPE | ES-OH-NO | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-09-26 |  | 2021-09-26 | 2021-10-25 |  |  | New Burn WL | LParedes | 2022-10-03 09:43 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004274 | O.1004274.01 | A.1004274.01.07 | Ocean Onyx M6 | BEACH ENERGY LTD |  | Ocean Onyx | J.21.108817 | RPE | ES-OH-NO | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2021-06-26 | 2021-06-26 |  | 2021-06-26 | 2021-07-26 |  | 2021-07-26 | New Burn WL | LParedes | 2022-10-03 09:43 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004274 | O.1004274.01 | A.1004274.01.05 | Ocean Onyx M4 | BEACH ENERGY LTD |  | Ocean Onyx | J.21.108816 | RPE | ES-OH-NO | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2021-04-26 | 2021-04-26 |  | 2021-04-26 | 2021-05-25 |  | 2021-05-25 | New Burn WL | LParedes | 2022-10-03 09:42 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004274 | O.1004274.01 | A.1004274.01.01 | Tractor Logging | BEACH ENERGY LTD |  | Ocean Onyx | J.20.062983 | RPE | ES-OH-NO | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-07-31 | 2020-07-31 |  | 2020-07-31 | 2021-10-03 |  | 2021-10-03 | New Burn WL | LParedes | 2022-10-03 09:42 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004260 | O.1004260.01 | A.1004260.01.09 | Julimar M8 | WOODSIDE ENERGY LTD |  | Ocean Apex | J.20.063015 | RPI | PS-SLK-NO | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-26 |  | 2020-08-26 | 2020-09-25 |  |  | New Burn WL | LParedes | 2022-10-03 09:47 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | Wireline Slickline
P.1004260 | O.1004260.01 | A.1004260.01.11 | March MPSR benchmarking rentals | WOODSIDE ENERGY LTD |  | Ocean Apex | J.20.063011 | RPE | ES-OH-NO | InComplete | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-03-17 |  | 2020-03-17 | 2020-03-25 |  |  | New Burn WL | JCade | 2022-10-03 09:47 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Felipe Donizeti Rosa |  | 22736 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004260 | O.1004260.01 | A.1004260.01.16 | Jula02 Slickline | WOODSIDE ENERGY LTD | JULA02 | Ocean Apex | J.20.063009 | RPI | PS-SLK-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-04 |  | 2020-08-15 01:00 | 2020-08-25 23:59 |  |  | New Burn WL | CStevens6 | 2022-10-03 09:46 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | Wireline Slickline
P.1004260 | O.1004260.01 | A.1004260.01.08 | Julimar M7 (USIT CBL JULA 02) | WOODSIDE ENERGY LTD | JULA02 | Ocean Apex | J.20.063008 | RPE | ES-CH-Ops | High | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-26 |  | 2020-08-08 | 2020-08-25 |  |  | New Burn WL | LParedes | 2022-10-03 09:46 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 141660 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004260 | O.1004260.01 | A.1004260.01.03 | Julimar M2 | WOODSIDE ENERGY LTD |  | Ocean Apex | J.20.063006 | RPE | ES-OH-NO | High | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-02-26 |  | 2020-02-26 | 2020-03-25 |  |  | New Burn WL | LParedes | 2022-10-03 09:45 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004260 | O.1004260.01 | A.1004260.01.10 | Julimar M9 | WOODSIDE ENERGY LTD |  | Ocean Apex | J.20.062998 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-10-19 |  | 2020-10-19 | 2020-10-25 |  |  | New Burn WL | LParedes | 2022-10-03 09:44 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1004260 | O.1004260.01 | A.1004260.01.06 | Julimar M5 | WOODSIDE ENERGY LTD |  | Ocean Apex | J.20.062997 | RPE | ES-OH-NO | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-05-26 |  | 2020-06-08 | 2020-06-25 |  |  | New Burn WL | LParedes | 2022-10-03 09:44 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004260 | O.1004260.01 | A.1004260.01.02 | Julimar M1 | WOODSIDE ENERGY LTD |  | Ocean Apex | J.20.062996 | RPE | ES-OH-NO | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-02-15 |  | 2020-02-15 | 2020-02-25 |  |  | New Burn WL | LParedes | 2022-10-03 09:44 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004260 | O.1004260.01 | A.1004260.01.15 | MDT-XTRA_JULA-02 | WOODSIDE ENERGY LTD | JULA02 | Ocean Apex | J.20.062993 | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-06-26 |  | 2020-07-08 | 2020-07-24 23:59 |  |  | New Burn WL | BAhmad | 2022-10-03 09:44 | FDPSystemUser |  | No |  |  |  |  | James Cade |  | 962651.53 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004260 | O.1004260.01 | A.1004260.01.01 | Julimar | WOODSIDE ENERGY LTD |  | Ocean Apex | J.20.062989 | RPE | ES-OH-NO | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-02-15 |  | 2020-02-15 | 2020-07-28 |  |  | New Burn WL | LParedes | 2022-10-03 09:43 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004260 | O.1004260.01 | A.1004260.01.05 | Julimar M4 | WOODSIDE ENERGY LTD |  | Ocean Apex | J.20.062987 | RPE | ES-OH-NO | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-04-25 17:00 | 2020-04-26 |  | 2020-04-26 | 2020-05-25 |  | 2020-05-24 17:00 | New Burn WL | LParedes | 2022-10-03 09:43 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004260 | O.1004260.01 | A.1004260.01.14 | Slickline Jula04 | WOODSIDE ENERGY LTD | JULA04 | Ocean Apex | J.20.062986 | RPI | PS-SLK-Rental-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress | 2020-06-28 | 2020-06-26 |  | 2020-06-28 | 2020-07-25 23:59 |  | 2020-07-25 23:59 | New Burn WL | frosa2 | 2022-10-03 09:43 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | Wireline Slickline
P.1004260 | O.1004260.01 | A.1004260.01.07 | Julimar M6 | WOODSIDE ENERGY LTD |  | Ocean Apex | J.20.062982 | RPE | ES-OH-NO | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-06-25 17:00 | 2020-06-26 |  | 2020-06-26 | 2020-07-25 |  | 2020-07-24 17:00 | New Burn WL | LParedes | 2022-10-03 09:42 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004260 | O.1004260.01 | A.1004260.01.04 | Julimar Jula-02 USIT-CBL | WOODSIDE ENERGY LTD | JULA-A | Ocean Apex |  | RPE | ES-OH-NO | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-04-17 |  | 2020-04-26 | 2020-05-25 |  |  | New Burn WL | LParedes | 2022-09-03 05:59 | walfaro |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004260 | O.1004260.01 | A.1004260.01.13 | MDT - XTRA | WOODSIDE ENERGY LTD | JULA-K | Ocean Apex |  | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-05-24 |  | 2020-06-11 | 2020-06-25 23:59 |  |  | New Burn WL | BAhmad | 2020-11-13 07:25 | JColeman |  | No |  |  |  |  | James Cade |  | 887168.58 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004260 | O.1004260.01 | A.1004260.01.12 | Slickline MPI | WOODSIDE ENERGY LTD | JULIMAR | Ocean Apex |  | RPE | ES-CH-NO | InComplete | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-04-17 |  | 2020-04-17 | 2020-07-07 |  |  | New Burn WL | frosa2 | 2020-11-13 07:25 | JColeman |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 59154.5 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.55 | IBC-CBL | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.24.019261 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-01-13 01:42 | 2025-01-13 | 2025-01-12 18:00 | 2025-01-13 07:42 | 2025-02-16 07:42 | 2025-02-16 18:00 | 2025-02-16 09:49 | New Burn WL | VOliveira5 | 2025-05-16 12:24 | MElsanousi |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 3 |  | L0 - No RO |  | 66.7 | 0 | 0 | 0 | 20 |  | 10 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1004258 | O.1004258.01 | A.1004258.01.60 | INPEX-SLK | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-3-05P, BDC 3 03, BDC-03-06 | Maersk Deliverer | J.24.019266 | RPI | PS-SLK-Rental-Ops | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-04-29 05:22 | 2025-04-28 |  | 2025-04-29 | 2025-05-24 23:59 |  | 2025-05-23 05:23 | New Burn WL | VOliveira5 | 2025-02-26 13:12 | MElsanousi |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 9 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1004258 | O.1004258.01 | A.1004258.01.54 | Inpex-Icthys-SLK BDC-1A-02 | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-1A-02 | Maersk Deliverer | J.24.019260 | RPI | PS-SLK-Rental-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-11-19 07:22 | 2024-11-08 |  | 2024-11-19 | 2024-12-14 23:59 |  | 2024-12-13 08:23 | New Burn WL | VOliveira5 | 2024-11-25 13:43 | CStevens6 |  | No |  |  |  |  | Jarrod Sedmak |  | 84600 | 1 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 7 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1004258 | O.1004258.01 | A.1004258.01.47 | BDC-1A-02 XTRA-EPILOGUE | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-1A-02 | Maersk Deliverer | J.23.085289 | RPE | ES-CH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-10-18 12:46 | 2024-10-15 |  | 2024-11-04 07:42 | 2024-12-03 12:00 |  | 2024-12-03 12:00 | New Burn WL | VOliveira5 | 2024-11-12 10:21 | APutra7 |  | No |  |  |  |  | Jarrod Sedmak |  | 210865.5 | 5 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 9 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.50 | Inpex-Icthys-SLK | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-3-05P, BDC 3 03, BDC-03-06 | Maersk Deliverer | J.23.156345 | RPI | PS-SLK-Rental-Ops | High | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2024-10-20 | 2024-10-20 |  | 2024-10-20 | 2024-11-14 23:59 |  | 2024-11-14 23:59 | New Burn WL | VOliveira5 | 2024-10-28 19:40 | MElsanousi |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 4 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1004258 | O.1004258.01 | A.1004258.01.64 | Inpex_ND_Pipe Recovery | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC 02 04 | Maersk Deliverer | J.23.175075 | RPE | ES-CH-Ops | High | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2023-12-14 07:42 | 2023-12-14 |  | 2023-12-14 07:42 | 2023-12-18 07:42 |  | 2023-12-18 07:42 | New Burn WL | MElsanousi | 2024-09-04 12:55 | MElsanousi |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 1 |  | L0 - No RO |  | 66.7 | 50 | 0 | 0 | 35 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.53 | Inpex-Ichthys-SLK BDC-2-03 | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC 02 04, BDC-2-01, BDC-2-02, BDC-2-03 | Maersk Deliverer | J.24.019259 | RPI | PS-SLK-Rental-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-08-04 07:22 | 2024-07-19 |  | 2024-08-04 | 2024-08-29 23:59 |  | 2024-08-28 07:23 | New Burn WL | VOliveira5 | 2024-09-02 10:06 | CStevens6 |  | No |  |  |  |  | Jarrod Sedmak |  | 189000 | 1 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 5 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1004258 | O.1004258.01 | A.1004258.01.44 | IBC-CBL_BDC-2-03 | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-2-03 | Maersk Deliverer | J.23.085287 | RPE | ES-CH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-07-06 | 2024-07-05 |  | 2024-07-20 07:42 | 2024-08-04 07:42 |  | 2024-08-16 23:59 | New Burn WL | VOliveira5 | 2024-08-30 10:58 | APutra7 |  | No |  |  |  |  | Jarrod Sedmak |  | 7600 | 3 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 4 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.11 | Maersk - Deliverer M10 | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.21.108830 | RPI | PS-WL-NO | High | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-04-23 07:42 | 2024-03-23 23:42 |  | 2024-04-23 07:42 | 2027-01-22 07:42 |  | 2027-01-22 07:42 | New Burn WL | LParedes | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 1 |  | L0 - No RO |  | 75 | 33.3 | 100 | 50 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Luis Cardenas | WL Production Services
P.1004258 | O.1004258.01 | A.1004258.01.34 | Inpex August | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.22.110155 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-20 07:42 | 2023-02-03 |  | 2023-09-20 07:42 | 2023-10-24 07:42 |  | 2023-10-24 07:42 | New Burn WL | JDukas | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1004258 | O.1004258.01 | A.1004258.01.40 | INPEX ¦ BDC-3-05P ¦ Noble Deliverer ¦ NGI-MAST ¦ XPT ¦ IBC-CBL | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-3-05P | Maersk Deliverer | J.23.052841 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-07-21 07:42 | 2023-06-15 |  | 2023-07-21 07:42 | 2023-09-24 07:42 |  | 2023-08-24 15:49 | New Burn WL | VOliveira5 | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Jarrod Sedmak |  | 353710 | 3 |  | L0 - No RO |  | 100 | 100 | 0 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.43 | IBC-CBL / SLK | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC 02 04 | Maersk Deliverer | J.23.085286 | RPE | ES-CH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-11-01 07:42 | 2023-11-01 |  | 2023-11-01 07:42 | 2023-12-05 07:42 |  | 2023-12-05 15:49 | New Burn WL | VOliveira5 | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 308900 | 3 |  | L0 - No RO |  | 91.7 | 83.3 | 100 | 62.5 | 81.3 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.45 | IBC-CBL / SLK | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-2-01ST1 | Maersk Deliverer | J.23.085288 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2024-01-23 07:42 | 2024-01-20 | 2024-01-23 | 2024-01-23 07:42 | 2024-02-25 07:42 | 2024-02-27 | 2024-02-25 15:49 | New Burn WL | VOliveira5 | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 575485 | 3 |  | L0 - No RO |  | 91.7 | 83.3 | 100 | 100 | 92.5 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1004258 | O.1004258.01 | A.1004258.01.48 | Inpex-SLK BDC-3-05P BDC-3-06 BDC-3-03 | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-3-05P, BDC 3 03, BDC-03-06 | Maersk Deliverer | J.23.119975 | RPI | PS-SLK-Rental-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-08-04 | 2023-08-03 | 2023-08-04 | 2023-08-04 | 2023-10-20 23:59 | 2023-09-18 | 2023-09-30 23:59 | New Burn WL | CStevens6 | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 120600 | 1 |  | L0 - No RO |  | 83.3 | 66.7 | 100 | 100 | 85 |  | 1 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1004258 | O.1004258.01 | A.1004258.01.49 | Inpex-Icthys-SLK BDC-2-04 | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC 02 04 | Maersk Deliverer | J.23.156342 | RPI | PS-SLK-Rental-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-11-14 10:22 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-12-09 23:59 | 2023-12-09 | 2023-12-08 10:23 | New Burn WL | VOliveira5 | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Jarrod Sedmak |  | 86400 | 1 |  | L0 - No RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 2 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1004258 | O.1004258.01 | A.1004258.01.63 | IBC-CBL | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.24.019269 | RPI | PS-WL-Ops | High | Cancelled | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-11-15 | 2024-11-14 | 2024-11-15 | 2024-11-15 | 2024-12-10 23:59 | 2024-12-11 | 2024-12-10 23:59 | New Burn WL | VOliveira5 | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 3 |  | L0 - No RO |  | 75 | 0 | 0 | 0 | 22.5 |  | 10 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1004258 | O.1004258.01 | A.1004258.01.51 | Inpex-Icthys-SLK | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-2-01 | Maersk Deliverer | J.24.019257 | RPI | PS-SLK-Rental-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-02-12 10:22 | 2024-01-26 | 2024-02-12 | 2024-02-12 | 2024-03-08 23:59 | 2024-03-08 | 2024-03-07 10:23 | New Burn WL | VOliveira5 | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Jarrod Sedmak |  | 136800 | 2 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 1 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1004258 | O.1004258.01 | A.1004258.01.56 | IBC-CBL | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.24.019262 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-09-29 07:42 | 2024-09-29 | 2024-09-29 | 2024-09-29 07:42 | 2024-11-02 07:42 | 2024-11-03 | 2024-11-02 15:49 | New Burn WL | VOliveira5 | 2024-08-21 13:52 | FDPSystemUser |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 3 |  | L0 - No RO |  | 66.7 | 0 | 0 | 0 | 20 |  | 7 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1004258 | O.1004258.01 | A.1004258.01.52 | Inpex-Icthys-SLK | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-2-02 | Maersk Deliverer | J.24.019258 | RPI | PS-SLK-Rental-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-06-04 | 2024-05-22 |  | 2024-06-04 | 2024-06-29 23:59 |  | 2024-06-29 23:59 | New Burn WL | VOliveira5 | 2024-06-19 16:11 | CStevens6 |  | No |  |  |  |  | Jarrod Sedmak |  | 50400 | 1 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 2 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | Wireline Slickline
P.1004258 | O.1004258.01 | A.1004258.01.46 | IBC-CBL BDC-2-02 | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-2-02 | Maersk Deliverer | J.23.085298 | RPE | ES-CH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-05-13 | 2024-05-01 | 2024-05-18 16:00 | 2024-05-23 07:42 | 2024-06-05 07:42 | 2024-06-06 | 2024-06-05 23:59 | New Burn WL | VOliveira5 | 2024-05-30 12:34 | APutra7 |  | No |  |  |  |  | Jarrod Sedmak |  | 340355 | 2 |  | L0 - No RO |  | 100 | 100 | 100 | 100 | 100 |  | 3 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.65 | BDC-2-02 RPI for Epilogue | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-2-02 | Maersk Deliverer | J.24.104683 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Not Started | Not Started | Not Started |  | 2024-05-20 |  | 2024-05-23 | 2024-06-05 23:59 |  |  | New Burn WL | JSedmak | 2024-05-24 16:19 | JSedmak |  | No |  |  |  |  | Arie Hidaya Putra |  | 784850 | 0 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohamed ElSanousi | WL Production Services
P.1004258 | O.1004258.01 | A.1004258.01.59 | IBC-CBL | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.24.019265 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2025-02-10 04:42 | 2025-02-10 | 2025-02-09 21:00 | 2025-02-10 07:42 | 2025-03-16 07:42 | 2025-03-16 21:00 | 2025-03-16 12:49 | New Burn WL | VOliveira5 | 2024-05-21 10:27 | MElsanousi |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 3 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 15 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.58 | IBC-CBL | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.24.019264 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-12-28 07:42 | 2024-12-28 | 2024-12-28 | 2024-12-28 07:42 | 2025-01-31 07:42 | 2025-02-01 | 2025-01-31 15:49 | New Burn WL | VOliveira5 | 2024-05-21 10:26 | MElsanousi |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 3 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 13 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.61 | INPEX-SLK | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-3-05P, BDC 3 03, BDC-03-06 | Maersk Deliverer | J.24.019267 | RPI | PS-SLK-Rental-Ops | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-10-06 10:22 | 2024-10-05 | 2024-10-06 | 2024-10-06 | 2024-10-31 23:59 | 2024-10-31 | 2024-10-30 10:23 | New Burn WL | VOliveira5 | 2024-05-21 10:26 | MElsanousi |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 7 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1004258 | O.1004258.01 | A.1004258.01.57 | IBC-CBL | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.24.019263 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-11-13 07:42 | 2024-11-13 | 2024-11-13 | 2024-11-13 07:42 | 2024-12-17 07:42 | 2024-12-18 | 2024-12-17 15:49 | New Burn WL | VOliveira5 | 2024-05-21 10:24 | MElsanousi |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 3 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 11 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.14 | Slickline Ops BDC-4-06P | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-4-06P | Maersk Deliverer | J.21.108818 | RPI | PS-SLK-Rental-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-05-12 | 2021-01-25 07:42 |  | 2021-05-12 | 2021-06-26 |  | 2021-06-26 | New Burn WL | frosa2 | 2024-03-26 16:25 | CStevens6 |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 1 |  |  |  | 50 | 50 | 0 | 50 | 45 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | Wireline Slickline
P.1004258 | O.1004258.01 | A.1004258.01.62 | Inpex-SLK | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-3-05P, BDC 3 03, BDC-03-06 | Maersk Deliverer | J.24.019268 | RPI | PS-SLK-Rental-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-07-05 10:22 | 2024-07-04 | 2024-07-05 | 2024-07-05 | 2024-07-30 23:59 | 2024-07-30 | 2024-07-29 10:23 | New Burn WL | VOliveira5 | 2023-10-19 10:41 | VOliveira5 |  | No |  |  |  |  | Jarrod Sedmak |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 1 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1004258 | O.1004258.01 | A.1004258.01.38 | Inpex-SLK BDC-3-03 | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC 3 03 | Maersk Deliverer | J.22.110180 | RPI | PS-SLK-Rental-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2022-11-07 | 2022-11-05 | 2022-11-06 16:00 | 2022-11-07 | 2023-06-29 | 2023-06-29 00:01 | 2023-07-04 | New Burn WL | VOliveira5 | 2023-07-03 13:45 | APutri |  | No |  |  |  |  | Justin Dukas |  | 75600 | 1 |  | L0 - No RO |  | 91.7 | 50 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1004258 | O.1004258.01 | A.1004258.01.41 | Inpex BDC-3-06ST1 Slickline Ops | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-03-06 | Maersk Deliverer | J.23.062959 | RPI | PS-SLK-Rental-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-01 | 2023-04-01 |  | 2023-04-01 | 2023-05-01 23:59 |  | 2023-05-01 23:59 | New Burn WL | CStevens6 | 2023-05-04 12:04 | VOliveira5 |  | No |  |  |  |  | Justin Dukas |  | 1802 | 2 |  | L0 - No RO |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1004258 | O.1004258.01 | A.1004258.01.42 | BDC-3-06ST1 EV Camera | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-03-06 | Maersk Deliverer | J.23.071959 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-04-20 | 2023-04-17 |  | 2023-04-20 | 2023-04-23 23:59 |  | 2023-04-23 23:59 | New Burn WL | AHermawan | 2023-04-22 16:13 | AHermawan |  | No |  |  |  |  | Justin Dukas |  | 9.5 | 1 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1004258 | O.1004258.01 | A.1004258.01.39 | IBC-CBL / | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-03-06 | Maersk Deliverer | J.23.052840 | RPE | ES-CH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Required | In Progress | 2023-04-18 | 2023-03-24 |  | 2023-03-24 07:42 | 2023-04-27 07:42 |  | 2023-04-27 23:59 | New Burn WL | VOliveira5 | 2023-04-18 09:53 | VOliveira5 |  | No |  |  |  |  | Jarrod Sedmak |  | 318856 | 1 |  | L0 - No RO |  | 83.3 | 100 | 0 | 100 | 85 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.28 | Inpex¦ OH Activity | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-4-06P | Maersk Deliverer | J.23.008559 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-05-06 08:52 | 2023-04-15 |  | 2023-04-19 | 2023-05-07 |  | 2023-05-26 | New Burn WL | BAhmad | 2023-02-17 16:14 | JDukas |  | No |  |  |  |  | Justin Dukas |  | 0 | 2 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004258 | O.1004258.01 | A.1004258.01.24 | BDC-3 OSP EPP-2 Open Hole | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-4-06P | Maersk Deliverer | J.23.008557 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-09-29 | 2023-03-22 |  | 2023-03-26 | 2023-04-13 |  | 2025-03-01 | New Burn WL | MMclean3 | 2023-02-17 16:13 | JDukas |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 2 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004258 | O.1004258.01 | A.1004258.01.33 | BDC-3-03 WL | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-3-03 (D) | Maersk Deliverer | J.22.110154 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-10 07:42 | 2022-11-07 07:42 |  | 2022-11-10 07:42 | 2022-11-25 07:42 |  | 2022-11-25 07:42 | New Burn WL | JDukas | 2022-12-28 13:39 | APutri |  | No |  |  |  |  | Justin Dukas |  | 11400 | 1 |  | L0 - No RO |  | 83.3 | 66.7 | 0 | 50 | 60 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1004258 | O.1004258.01 | A.1004258.01.36 | SLK ops Maersk Deliverer BDC-5-02P (EPP-1) | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-05-02P | Maersk Deliverer | J.22.110166 | RPI | PS-SLK-Rental-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Required | Design Completed |  | 2022-09-28 |  | 2022-09-30 | 2022-10-23 23:59 |  |  | New Burn WL | JDukas | 2022-10-24 14:22 | VOliveira5 |  | No |  |  |  |  | Clinton Stevens |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1004258 | O.1004258.01 | A.1004258.01.37 | Inpex pipe recovery contingency | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-05-02P | Maersk Deliverer | J.22.110171 | RPE | ES-CH-NO | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-07-23 |  | 2022-07-30 | 2022-08-05 |  |  | New Burn WL | JDukas | 2022-10-03 10:02 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.35 | Slickline Ops BDC-1D-04 and BDC-1D-02 | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-1D-04, BDC-1D-02 | Maersk Deliverer | J.22.110165 | RPI | PS-SLK-Rental-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed |  | 2022-05-25 |  | 2022-05-27 | 2022-06-19 23:59 |  |  | New Burn WL | CStevens6 | 2022-10-03 10:01 | FDPSystemUser |  | No |  |  |  |  | Clinton Stevens |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | Wireline Slickline
P.1004258 | O.1004258.01 | A.1004258.01.32 | Inpex May | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.22.110153 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-07-10 07:42 |  | 2022-07-15 07:42 | 2022-09-24 07:42 |  |  | New Burn WL | JDukas | 2022-10-03 10:00 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004258 | O.1004258.01 | A.1004258.01.31 | Inpex BDC-5-02P (EPP-1) CH logging operations | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-05-02P | Maersk Deliverer | J.22.110152 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-09-22 07:42 |  | 2022-10-01 07:42 | 2022-10-15 07:42 |  |  | New Burn WL | JDukas | 2022-10-03 10:00 | FDPSystemUser |  | No |  |  |  |  | Jarrod Sedmak |  | 11477 | 0 |  |  |  | 75 | 83.3 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1004258 | O.1004258.01 | A.1004258.01.30 | Slickline Ops BDC-1D-02 | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-1D-02 | Maersk Deliverer | J.22.110145 | RPI | PS-SLK-Rental-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-01-25 |  | 2022-01-26 | 2022-02-20 23:59 |  |  | New Burn WL | CStevens6 | 2022-10-03 10:00 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | Wireline Slickline
P.1004258 | O.1004258.01 | A.1004258.01.29 | INPEX ¦ BDC-1D-04 ¦ Maersk Deliverer ¦ IBC-CBL-VDL-GR-CCL-XTRA | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-1D-04 | Maersk Deliverer | J.22.110116 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-04-01 07:42 |  | 2022-04-15 07:42 | 2022-05-31 07:42 |  |  | New Burn WL | BAhmad | 2022-10-03 09:55 | FDPSystemUser |  | No |  |  |  |  | Justin Dukas |  | 383480 | 1 |  |  |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Production Services
P.1004258 | O.1004258.01 | A.1004258.01.27 | Inpex_Dec | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-1D-02 | Maersk Deliverer | J.22.110112 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-12-27 |  | 2022-01-13 07:42 | 2022-01-31 07:42 |  |  | New Burn WL | BAhmad | 2022-10-03 09:54 | FDPSystemUser |  | No |  |  |  |  | James Cade |  | 343130 | 1 |  |  |  | 83.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004258 | O.1004258.01 | A.1004258.01.26 | Inpex_Nov | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.21.108876 | RPI | PS-WL-NO | High | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2021-11-01 07:42 | 2021-11-01 07:42 |  | 2021-11-01 07:42 | 2021-11-16 07:42 |  | 2021-11-16 07:42 | New Burn WL | BAhmad | 2022-10-03 09:54 | FDPSystemUser |  | No |  |  |  |  | James Cade |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 33.3 | 100 | 50 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004258 | O.1004258.01 | A.1004258.01.25 | Inpex_Oct 21 | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.21.108875 | RPI | PS-WL-NO | High | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2021-10-01 07:42 | 2021-10-01 07:42 |  | 2021-10-01 07:42 | 2021-10-16 07:42 |  | 2021-10-16 07:42 | New Burn WL | BAhmad | 2022-10-03 09:54 | FDPSystemUser |  | No |  |  |  |  | James Cade |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 33.3 | 100 | 50 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004258 | O.1004258.01 | A.1004258.01.23 | INPEX ¦ BDC-3-03 ¦ Maersk Deliverer ¦ IBC-CBL-VDL-GR-CCL-XTRA | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-3-03 (D) | Maersk Deliverer | J.21.108859 | RPE | ES-CH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-09-01 07:42 |  | 2021-09-01 07:42 | 2021-09-11 07:42 |  |  | New Burn WL | frosa2 | 2022-10-03 09:52 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 203150 | 1 |  |  |  | 58.3 | 50 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.22 | EV Camera and Caliper | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC 4 06 P | Maersk Deliverer | J.21.108856 | RPI | PS-WL-NO | Medium | Unconfirmed - 10% | Design - CEC |  | In Progress | Not Started | In Progress | 2021-05-27 | 2021-05-17 |  | 2021-05-27 | 2021-06-01 23:59 |  | 2021-06-01 23:59 | New Burn WL | frosa2 | 2022-10-03 09:51 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 33.3 | 100 | 50 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004258 | O.1004258.01 | A.1004258.01.21 | Aug Activity | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.21.108848 | RPE | ES-CH-NO | High | Unconfirmed - 90% | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-08-01 07:42 | 2021-08-01 07:42 |  | 2021-08-01 07:42 | 2021-09-02 07:42 |  | 2021-09-02 07:42 | New Burn WL | frosa2 | 2022-10-03 09:51 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 203150 | 1 |  | L0 - No RO |  | 91.7 | 66.7 | 100 | 50 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.20 | Aug Activity | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.21.108847 | RPE | ES-CH-NO | High | Confirmed | Design - CEC |  | Design Completed | Not Started | In Progress | 2021-07-01 07:42 | 2021-07-01 07:42 |  | 2021-07-01 07:42 | 2021-07-11 07:42 |  | 2021-07-11 07:42 | New Burn WL | frosa2 | 2022-10-03 09:51 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 1 |  | L0 - No RO |  | 50 | 33.3 | 100 | 50 | 50 |  | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.18 | BDC-4-06P #1 | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-4-06P | Maersk Deliverer | J.20.063014 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-11-10 |  | 2020-11-28 | 2021-02-20 23:59 |  |  | New Burn WL | CJones19 | 2022-10-03 09:47 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 337661.2 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.10 | Maersk - Deliverer M9 | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.21.108833 | RPE | ES-OH-NO | High | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-02-20 07:42 |  | 2021-02-20 07:42 | 2021-03-22 07:42 |  |  | New Burn WL | LParedes | 2022-10-03 09:46 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 |  |  |  |  | 50 | 33.3 | 100 | 50 | 50 |  | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.09 | Maersk - Deliverer M8 | INPEX OPERATIONS AUSTRALIA PTY LTD | EPP 3_BDC4 | Maersk Deliverer | J.21.108832 | RPE | ES-OH-NO | High | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-05-27 |  | 2021-05-27 | 2021-06-25 |  |  | New Burn WL | LParedes | 2022-10-03 09:46 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 |  |  |  |  | 50 | 33.3 | 100 | 50 | 50 |  | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.02 | Maersk - Deliverer M1 | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.20.063007 | RPE | ES-OH-NO | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-02-26 |  | 2020-02-26 | 2020-03-25 |  |  | New Burn WL | LParedes | 2022-10-03 09:46 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.17 | ES BDC-4-06P | INPEX OPERATIONS AUSTRALIA PTY LTD | EPP 3_BDC4 | Maersk Deliverer | J.21.108828 | RPE | ES-OH-NO | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-04-26 |  | 2021-04-26 | 2021-05-26 |  |  | New Burn WL | CJones19 | 2022-10-03 09:46 | FDPSystemUser |  | Yes |  |  |  |  | Felipe Donizeti Rosa |  | 0 |  |  |  |  | 41.7 | 33.3 | 100 | 50 | 47.5 |  | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.16 | SLK Feb | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.21.108827 | RPI | PS-SLK-NO | Medium | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-03-22 00:02 |  | 2021-03-23 00:02 | 2021-04-21 00:02 |  |  | New Burn WL | frosa2 | 2022-10-03 09:46 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 |  |  |  |  | 33.3 | 33.3 | 100 | 50 | 45 |  | 0 | [7 empty] | Luis Cardenas | Wireline Slickline
P.1004258 | O.1004258.01 | A.1004258.01.08 | Maersk Deliverer BDC-5-02P (EPP-1) OH logging | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-05-02P | Maersk Deliverer | J.22.110101 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-08-05 |  | 2022-08-22 | 2022-09-22 |  |  | New Burn WL | LParedes | 2022-10-03 09:45 | FDPSystemUser |  | No |  |  |  |  | Jarrod Sedmak |  | 1462593.64 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Victor Oliveira | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.01 | Phase -2 | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.20.063005 | RPE | ES-CH-Ops | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-03-01 |  | 2020-03-01 | 2020-07-27 |  |  | New Burn WL | LParedes | 2022-10-03 09:45 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 |  |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.12 | March retainer | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.20.063002 | RPE | ES-CH-NO | InComplete | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-03-16 |  | 2020-03-16 | 2020-03-25 |  |  | New Burn WL | JCade | 2022-10-03 09:45 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Felipe Donizeti Rosa |  | 64879.61 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.06 | Maersk - Deliverer M5 | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.20.063001 | RPE | ES-CH-NO | High | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-26 |  | 2020-06-26 | 2020-07-25 |  |  | New Burn WL | LParedes | 2022-10-03 09:45 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 57380.94 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.07 | Maersk - Deliverer M6 | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.20.063000 | RPE | ES-OH-NO | High | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2020-03-01 | 2020-07-26 |  | 2020-07-26 | 2020-08-25 |  | 2022-07-26 | New Burn WL | LParedes | 2022-10-03 09:45 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 114761.88 |  |  | L0 - No RO |  | 58.3 | 33.3 | 100 | 75 | 60 |  | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.05 | Maersk - Deliverer M4 | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.20.062995 | RPE | ES-CH-NO | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-05-26 |  | 2020-05-26 | 2020-06-25 |  |  | New Burn WL | LParedes | 2022-10-03 09:44 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 |  |  |  |  | 41.7 | 33.3 | 100 | 50 | 47.5 |  | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.03 | Maersk - Deliverer M2 | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.20.062994 | RPE | ES-CH-NO | High | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-03-26 |  | 2020-03-26 | 2020-04-25 |  |  | New Burn WL | LParedes | 2022-10-03 09:44 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 94180.94 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.15 | SLK January 21 | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.21.108821 | RPI | PS-SLK-NO | Medium | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-02-19 00:01 |  | 2021-02-20 00:01 | 2021-03-22 00:01 |  |  | New Burn WL | frosa2 | 2022-10-03 09:44 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 |  |  |  |  | 33.3 | 33.3 | 100 | 50 | 45 |  | 0 | [7 empty] | Luis Cardenas | Wireline Slickline
P.1004258 | O.1004258.01 | A.1004258.01.04 | Maersk - Deliverer M3 | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.20.062992 | RPE | ES-OH-NO | High | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-04-26 |  | 2020-04-26 | 2020-05-25 |  |  | New Burn WL | LParedes | 2022-10-03 09:43 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 57380.94 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.13 | Personnel for unit install | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.20.062985 | RPE | ES-CH-NO | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress | 2020-03-16 | 2020-03-16 |  | 2020-03-16 | 2020-03-25 |  | 2020-03-25 | New Burn WL | LParedes | 2022-10-03 09:43 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 28800 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004258 | O.1004258.01 | A.1004258.01.19 | INPEX IBC-CBL | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-4-06P | Maersk Deliverer | J.21.108815 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-04-12 06:00 | 2021-04-21 |  | 2021-04-22 06:00 | 2021-04-24 06:00 |  | 2021-06-05 06:00 | New Burn WL | frosa2 | 2022-10-03 09:42 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Bilal Ahmad | WL Production Services
P.1004255 | O.1004255.01 | A.1004255.01.01 | BlackWatch - 1 | BEACH ENERGY LTD | Black Watch-1 | ENSIGN 931 | J.20.063013 | RPI | PS-WL-NO | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-01-23 |  | 2020-01-23 | 2020-03-25 |  |  | New Burn WL | LParedes | 2022-10-03 09:47 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1004255 | O.1004255.01 | A.1004255.01.05 | Enterprise-1 Month 2 | BEACH ENERGY LTD | Black Watch-1 | ENSIGN 931 | J.20.063010 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-10-27 |  | 2020-10-27 | 2020-11-25 |  |  | New Burn WL | LParedes | 2022-10-03 09:46 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004255 | O.1004255.01 | A.1004255.01.10 | BW1_April Rentals | BEACH ENERGY LTD | Black Watch-1 | ENSIGN 931 | J.20.063004 | RPI | PS-WL-NO | InComplete | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-04-13 |  | 2020-04-13 | 2020-04-25 |  |  | New Burn WL | BAhmad | 2022-10-03 09:45 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 63870.44 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1004255 | O.1004255.01 | A.1004255.01.02 | Enterprise -1 | BEACH ENERGY LTD | Black Watch-1 | ENSIGN 931 | J.20.063003 | RPE | ES-CH-NO | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-01 |  | 2020-09-01 | 2020-09-25 |  |  | New Burn WL | LParedes | 2022-10-03 09:45 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004255 | O.1004255.01 | A.1004255.01.03 | Blackwatch 1 FPIT | BEACH ENERGY LTD | Black Watch-1 | ENSIGN 931 | J.20.062999 | RPI | PS-WL-NO | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-02-17 15:00 |  | 2020-02-17 15:00 | 2020-02-21 22:00 |  |  | New Burn WL | crowand | 2022-10-03 09:44 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 81419.92 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1004255 | O.1004255.01 | A.1004255.01.08 | 5-1/2in CBL and MXAR | BEACH ENERGY LTD | Black Watch-1 | ENSIGN 931 | J.20.062991 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-03-24 |  | 2020-04-03 | 2020-04-25 |  |  | New Burn WL | crowand | 2022-10-03 09:43 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 678081.81 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1004255 | O.1004255.01 | A.1004255.01.06 | Enterprise-1 Month 3 | BEACH ENERGY LTD | Black Watch-1 | ENSIGN 931 | J.20.062990 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-11-26 |  | 2020-11-26 | 2020-12-25 |  |  | New Burn WL | LParedes | 2022-10-03 09:43 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004255 | O.1004255.01 | A.1004255.01.04 | Enterprise-1 Month 1 | BEACH ENERGY LTD | Black Watch-1 | ENSIGN 931 | J.20.062988 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-26 |  | 2020-09-26 | 2020-10-26 |  |  | New Burn WL | LParedes | 2022-10-03 09:43 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1004255 | O.1004255.01 | A.1004255.01.07 | Blackwatch 9-5/8in logging | BEACH ENERGY LTD | Black Watch-1 | ENSIGN 931 | J.20.062984 | RPI | PS-WL-NO | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress | 2020-03-04 18:00 | 2020-02-25 |  | 2020-03-05 18:00 | 2020-03-08 18:00 |  | 2020-03-07 18:00 | New Burn WL | crowand | 2022-10-03 09:42 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1004255 | O.1004255.01 | A.1004255.01.09 | march rentals | BEACH ENERGY LTD | Black Watch-1 | ENSIGN 931 | J.20.062981 | RPI | PS-WL-NO | InComplete | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-03-21 |  | 2020-03-21 | 2020-03-25 |  |  | New Burn WL | frosa2 | 2022-10-03 09:42 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 424647.43 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1004123 | O.1004123.01 | A.1004123.01.01 | Scarborough SWT Preparation | WOODSIDE ENERGY LTD | SCARBOROUGH CAMPAIGN | ENSCO DPS-1 |  | RPI | TSWT-DSGN | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2021-03-03 |  | 2021-03-03 | 2021-03-03 00:10 |  |  | APG TS | RWallis | 2021-04-30 05:31 | JColeman |  | No |  |  |  |  | Wayne Wallis |  | 46566 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Richard Steers | TS Surface Testing
P.1004006 | O.1004006.01 | A.1004006.01.01 | Perforation + Packer | ORIGIN ENERGY RESOURCES LIMITED | SOUTH BURUNGA 2 | Rigless Australia - 1 | J.20.063360 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-01-10 12:00 |  | 2020-01-11 | 2020-01-20 |  |  | Roma WL | AKharisma | 2022-10-03 13:53 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004006 | O.1004006.01 | A.1004006.01.02 | CND 027 DFIT | ORIGIN ENERGY RESOURCES LIMITED | Condabri North Deep 27 | Rigless Australia - 1 | J.20.063359 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-01-11 11:00 |  | 2020-01-11 16:00 | 2020-01-18 06:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:53 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 60108.84 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1004006 | O.1004006.01 | A.1004006.01.03 | CND039 CBL - IBC | ORIGIN ENERGY RESOURCES LIMITED | CONDABRI NORTH DEEP 39 | Rigless Australia - 1 | J.20.063358 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-21 |  | 2020-01-21 | 2020-01-25 |  |  | Roma WL | SClark17 | 2022-10-03 13:53 | FDPSystemUser |  | No |  |  |  |  | Ibrahim Mahmood |  | 127291.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1003848 | O.1003848.01 | A.1003848.01.01 | Rig Visit | COOPER ENERGY LIMITED |  | HELIX Q7000 | J.19.060373 | RPI | TSWT-DSGN | InComplete | Confirmed | Design - PSD |  | Not Started | Not Started | In Progress |  | 2019-12-23 |  | 2019-12-23 | 2019-12-23 |  |  | APG TS | PFlores15 | 2022-10-03 06:23 | FDPSystemUser |  | No |  |  |  |  | Allwyn Francis |  | 0 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Richard Steers | TS Surface Testing
P.1003792 | O.1003792.02 | A.1003792.02.02 | Suite 2__GPIT-HRLA-PEX_FMI-MSIP_MDT | ORIGIN ENERGY RESOURCES LIMITED | CND 039 | EASTERNWELL 101 |  | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-06 08:00 |  | 2020-01-08 12:00 | 2020-01-11 12:00 |  |  | Roma WL | EBrobbey | 2020-11-13 10:25 | JColeman |  | No |  |  |  |  | Edmund Brobbey |  | 206461.72 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1003792 | O.1003792.02 | A.1003792.02.01 | EWE 101 | ORIGIN ENERGY RESOURCES LIMITED | CND 039 | EASTERNWELL 101 |  | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-01-02 09:00 | 2020-01-01 20:00 | 2020-01-02 | 2020-01-02 09:00 | 2020-01-05 09:00 | 2020-01-06 | 2020-01-05 09:00 | Roma WL | SAndersen6 | 2020-03-09 21:33 | ysaeedabadian |  | No |  |  |  | ROE WL Mumbai | Yazdan Saeedabadian |  | 145775.57 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1003792 | O.1003792.01 | A.1003792.01.01 | CND 039 | ORIGIN ENERGY RESOURCES LIMITED | CONDABRI NORTH DEEP 39 | EASTERNWELL 101 | J.19.060677 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-18 15:00 |  | 2019-12-19 06:00 | 2019-12-22 |  |  | Roma WL | RDell | 2022-10-03 13:53 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Raymond Dell |  | 701.75 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1003770 | O.1003770.01 | A.1003770.01.03 | TLD | SANTOS LIMITED | RM50-52-1 | EWE 18 | J.19.060676 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-29 06:00 |  | 2019-12-29 08:00 | 2019-12-30 08:00 |  |  | Roma WL | ysaeedabadian | 2022-10-03 13:52 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 59389.22 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1003770 | O.1003770.01 | A.1003770.01.01 | Dual Density | SANTOS LIMITED | RM49-46-1 | EWE 18 | J.19.060675 | RPE | ES-CH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Required | In Progress | 2019-12-18 10:00 | 2019-12-18 |  | 2019-12-18 10:00 | 2019-12-19 |  | 2019-12-19 14:00 | Roma WL | MRony2 | 2022-10-03 13:52 | FDPSystemUser |  | No |  |  |  |  | Lisa Delange |  | 12833.01 |  |  | L0 - No RO |  | 58.3 | 0 | 0 | 25 | 25 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1003770 | O.1003770.01 | A.1003770.01.02 | TLD-APS | SANTOS LIMITED | RM49-46-1 | EWE 18 | J.19.060674 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-22 06:00 |  | 2019-12-22 08:00 | 2019-12-23 08:00 |  |  | Roma WL | EDelange | 2022-10-03 13:52 | FDPSystemUser |  | No |  |  |  |  | Lisa Delange |  | 29694.61 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1003652 | O.1003652.02 | A.1003652.02.02 | Bargie 5_CH | BRIDGEPORT ENERGY LIMITED | Bargie 5 | Bridgeport Drilling 1 | J.20.063356 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-01-08 06:00 |  | 2020-01-08 06:00 | 2020-01-11 18:00 |  |  | Roma WL | APutra7 | 2022-10-03 13:52 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1003652 | O.1003652.02 | A.1003652.02.01 | Perforation_Bridgeport | BRIDGEPORT ENERGY LIMITED | Black Stump 6 | Bridgeport Drilling 1 | J.19.060673 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-20 |  | 2019-12-20 | 2019-12-26 |  |  | Roma WL | JAnderson60 | 2022-10-03 13:52 | FDPSystemUser |  | No |  |  |  |  | Ke Tao |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1003652 | O.1003652.02 | A.1003652.02.04 | Forth well Bridgeport | BRIDGEPORT ENERGY LIMITED | Bargie 5 | Bridgeport Drilling 1 | J.22.110227 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2022-03-17 06:00 |  | 2022-03-17 06:00 | 2022-03-20 17:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:52 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1003652 | O.1003652.02 | A.1003652.02.03 | Bodalla South 22 | BRIDGEPORT ENERGY LIMITED | Bodalla South 22 | Bridgeport Drilling 1 | J.20.063354 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-01-28 06:00 |  | 2020-01-30 06:00 | 2020-02-02 18:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:52 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1003652 | O.1003652.01 | A.1003652.01.05 | Cruella 1 QC-SS | BRIDGEPORT ENERGY LIMITED | CRUELLA 1 | CONDOR RIG 1 | J.24.131367 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-09-10 | 2024-08-27 |  | 2024-08-29 | 2024-09-30 23:59 |  | 2024-10-09 | Roma WL | JEsmeralda | 2024-12-12 17:01 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 248724 | 2 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 3 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1003652 | O.1003652.01 | A.1003652.01.06 | Riddler 1 | BRIDGEPORT ENERGY LIMITED | RIDDLER 1 | CONDOR RIG 1 | J.24.142239 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-09-22 | 2024-09-13 |  | 2024-09-15 | 2024-09-20 23:59 |  | 2024-09-24 | Roma WL | KKeese | 2024-12-12 16:58 | KKeese |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 41500 | 3 |  | L3 - Full RO |  | 83.3 | 100 | 0 | 100 | 85 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1003652 | O.1003652.01 | A.1003652.01.03 | Bridgeport ¦ Bodalla South 22 ¦ BHC-HRLA-PEX-GPIT-SP | BRIDGEPORT ENERGY LIMITED | Bodalla South 22 | CONDOR RIG 1 | J.20.063357 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-25 |  | 2020-01-27 20:00 | 2020-02-02 20:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:52 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1003652 | O.1003652.01 | A.1003652.01.02 | Bargie 5_OH | BRIDGEPORT ENERGY LIMITED | Bargie 5 | CONDOR RIG 1 | J.20.063355 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-04 |  | 2020-01-05 | 2020-01-11 |  |  | Roma WL | JEsmeralda | 2022-10-03 13:52 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1003652 | O.1003652.01 | A.1003652.01.04 | Bridgeport Forth Well | BRIDGEPORT ENERGY LIMITED | Bargie 5 | CONDOR RIG 1 | J.21.108927 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-08-12 |  | 2021-08-13 | 2021-08-18 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:52 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1003652 | O.1003652.01 | A.1003652.01.01 | Blackstump06_OH | BRIDGEPORT ENERGY LIMITED | Black Stump 6 | CONDOR RIG 1 | J.19.060672 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-13 |  | 2019-12-13 | 2019-12-23 |  |  | Roma WL | JEsmeralda | 2022-10-03 13:52 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 |  |  |  |  | 50 | 33.3 | 0 | 37.5 | 36.3 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1003500 | O.1003500.01 | A.1003500.01.01 | GR-CCL-DD-APS | SANTOS LIMITED | RM50-22-1 | SAVANNA DRILLING #71 | J.19.060671 | RPE | ES-CH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-09 |  | 2019-12-09 | 2019-12-10 15:00 |  |  | Roma WL | AGamero | 2022-10-03 13:51 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 4753.74 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1003242 | O.1003242.01 | A.1003242.01.01 | Theia_Proppant Embedment, Fractu | THEIA ENERGY |  | Rigless Australia - 1 | J.19.060371 | RPE | FSA-ROCK-JOB | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2019-11-18 |  | 2019-11-18 | 2020-08-30 |  |  | APG TS | LSimaremare | 2022-10-03 06:23 | FDPSystemUser |  | No |  |  |  |  | Wayne Wallis |  | 68350 | [10 empty] | 0 | [7 empty] | Richard Steers | TS Downhole Reservoir Testing
P.1003241 | O.1003241.01 | A.1003241.01.01 | Santos Dorado-3 Bottle Rentals | SANTOS WESTERN AUSTRALIA |  | Noble Tom Prosser | J.19.060372 | RPE | FSA-ROCK-JOB | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2019-11-18 |  | 2019-11-18 | 2020-01-25 |  |  | APG TS | LSimaremare | 2022-10-03 06:23 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 1372.5 | [10 empty] | 0 | [7 empty] | Richard Steers | TS Downhole Reservoir Testing
P.1003169 | O.1003169.02 | A.1003169.02.01 | TCP Shoot and Stay | SANTOS LIMITED | Merrimelia 43 | Wild Desert Rig 6 | J.20.062338 | RPI | TCP-PERM-JOB | InComplete | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-06-04 |  | 2020-06-10 | 2020-06-17 23:59 |  |  | APG TS | GRoxo | 2022-10-03 06:23 | FDPSystemUser |  | No |  |  |  |  | Zhong Wei Gao |  | 63992.59 | [10 empty] | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TCP-Tubing-Conveyed Perforation
P.1003169 | O.1003169.01 | A.1003169.01.05 | Wackett 5 TCP | SANTOS LIMITED | WACKETT 5 | Wild Desert Rig 6 | J.20.062339 | RPI | TCP-PERM-JOB | InComplete | Confirmed | Execute - PSD |  | Not Started | Design Completed | In Progress |  | 2020-06-01 00:03 |  | 2020-06-03 00:03 | 2020-06-07 00:03 |  |  | APG TS | GRoxo | 2022-10-03 06:23 | FDPSystemUser |  | No |  |  |  |  | Wayne Wallis |  | 74330.79 | [10 empty] | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TCP-Tubing-Conveyed Perforation
P.1003169 | O.1003169.01 | A.1003169.01.04 | Toolachee 50 | SANTOS LIMITED | TOOLACHEE 50 | Wild Desert Rig 6 | J.20.062337 | RPI | TCP-PERM-JOB | Medium | Unconfirmed - 90% | Design - CEC |  | Not Started | In Progress | In Progress |  | 2020-07-28 |  | 2020-08-01 | 2020-08-05 |  |  | APG TS | RWallis | 2022-10-03 06:23 | FDPSystemUser |  | No |  |  |  |  | Wayne Wallis |  | 0 | [10 empty] | 0 | [7 empty] | Richard Steers | TCP-Tubing-Conveyed Perforation
P.1003169 | O.1003169.01 | A.1003169.01.01 | Lepard 2 TCP | SANTOS LIMITED | LEPARD 2 | Wild Desert Rig 6 | J.19.060370 | RPI | TCP-PERM-JOB | InComplete | Confirmed | Design - CEC |  | Not Started | In Progress | In Progress |  | 2019-11-29 |  | 2019-11-29 | 2019-12-15 |  |  | APG TS | RWallis | 2022-10-03 06:23 | FDPSystemUser |  | No |  |  |  |  | Wayne Wallis |  | 138674.6 | [10 empty] | 0 | [7 empty] | Richard Steers | TCP-Tubing-Conveyed Perforation
P.1003169 | O.1003169.01 | A.1003169.01.03 | Big Lake 102 | SANTOS LIMITED | Big Lake 102 | Wild Desert Rig 6 | J.20.062336 | RPI | TCP-PERM-JOB | InComplete | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2020-02-28 |  | 2020-02-28 | 2020-03-09 |  |  | APG TS | RWallis | 2022-10-03 06:23 | FDPSystemUser |  | No |  |  |  |  | Wayne Wallis |  | 121752.22 | [10 empty] | 0 | [7 empty] | Richard Steers | TCP-Tubing-Conveyed Perforation
P.1003169 | O.1003169.01 | A.1003169.01.02 | Napowie-1 TCP | SANTOS LIMITED | Napowie APP A | Wild Desert Rig 6 |  | RPI | TCP-PERM-JOB | InComplete | Operationally Complete | Close - PSD |  | Not Required | In Progress | In Progress |  | 2019-12-01 |  | 2019-12-01 | 2019-12-11 |  |  | APG TS | RWallis | 2020-11-26 07:57 | FDPSystemUser |  | No |  |  |  |  | Wayne Wallis |  | 47339.56 | [10 empty] | 0 | [7 empty] | Richard Steers | TCP-Tubing-Conveyed Perforation
P.1003166 | O.1003166.01 | A.1003166.01.01 | COP_BOTTLE RENTALS_PHAROS | CONOCOPHILLIPS AUSTRALIA & TIMOR-LESTE (APG) | Pharos-1 | Noble Tom Prosser |  | RPE | FSA-BR | InComplete | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2019-11-14 |  | 2019-11-14 | 2020-11-06 |  |  | APG TS | LSimaremare | 2022-11-03 07:09 | RWallis |  | No |  |  |  |  | Josh Markowski |  | 15882 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Richard Steers | TS Downhole Reservoir Testing
P.1003165 | O.1003165.01 | A.1003165.01.01 | COP_BOTTLE RENTALS | CONOCOPHILLIPS AUSTRALIA & TIMOR-LESTE (APG) |  | Transocean Legend |  | RPE | FSA-BR | InComplete | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2019-11-18 |  | 2019-11-18 | 2020-11-06 |  |  | APG TS | LSimaremare | 2022-11-03 07:09 | RWallis |  | No |  |  |  |  | Josh Markowski |  | 35402 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Richard Steers | TS Downhole Reservoir Testing
P.1002862 | O.1002862.01 | A.1002862.01.01 | Vintage Energy 1 | VINTAGE ENERGY | VALI-1 | Saxon Rig 185 | J.20.062928 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-01-12 12:00 | 2020-01-10 |  | 2020-01-12 12:00 | 2020-01-17 12:00 |  | 2020-01-17 12:00 | Moomba WL | OBass | 2022-10-03 10:59 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1002862 | O.1002862.01 | A.1002862.01.02 | Vintage Energy 2 | VINTAGE ENERGY | VALI-1 | Saxon Rig 185 | J.19.060541 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2019-12-25 12:00 | 2019-12-25 |  | 2019-12-25 12:00 | 2019-12-26 09:00 |  | 2019-12-26 18:00 | Moomba WL | AHermawan | 2022-10-03 10:58 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1002471 | O.1002471.01 | A.1002471.01.01 | OSLC October logging | SANTOS - BRISBANE |  | ENSIGN 111 | J.19.060540 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2019-10-25 |  | 2019-10-25 | 2019-10-27 |  |  | Moomba WL | OMosleh | 2022-10-03 10:58 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1002383 | O.1002383.01 | A.1002383.01.04 | Barrolka 4 | SANTOS LIMITED | Barrolka North East 4 | ENSIGN 971 | J.19.060539 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2019-12-23 | 2019-12-23 |  | 2019-12-23 | 2019-12-28 |  | 2019-12-28 | Moomba WL | KKeese | 2022-10-03 10:58 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1002383 | O.1002383.01 | A.1002383.01.01 | UBD tailpipe setting Coolah 10 | SANTOS LIMITED | Coolah 10 | ENSIGN 971 | J.19.060538 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2019-10-23 13:00 | 2019-10-23 12:00 |  | 2019-10-23 13:00 | 2019-10-28 |  | 2019-10-28 | Moomba WL | ymoradi2 | 2022-10-03 10:58 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1002383 | O.1002383.01 | A.1002383.01.05 | UBD Tailpipe | SANTOS LIMITED | Barrolka North East 5 | ENSIGN 971 | J.20.062927 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-01-18 13:00 | 2020-01-13 11:00 |  | 2020-01-18 13:00 | 2020-01-20 11:00 |  | 2020-01-20 11:00 | Moomba WL | ASetya | 2022-10-03 10:58 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1002383 | O.1002383.01 | A.1002383.01.03 | Coolah 11 | SANTOS LIMITED | Coolah 11 | ENSIGN 971 | J.19.060537 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2019-12-01 20:00 | 2019-12-01 11:13 |  | 2019-12-01 20:00 | 2019-12-07 20:00 |  | 2019-12-07 20:00 | Moomba WL | DParker16 | 2022-10-03 10:58 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 5730.99 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1002383 | O.1002383.01 | A.1002383.01.02 | Coolah 9 | SANTOS LIMITED | Coolah 9 | ENSIGN 971 | J.19.060536 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2019-11-11 06:00 | 2019-11-10 |  | 2019-11-11 06:00 | 2019-11-15 08:00 |  | 2019-11-15 08:00 | Moomba WL | DParker16 | 2022-10-03 10:58 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 5730.99 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1002380 | O.1002380.01 | A.1002380.01.01 | Dombey-1 | BEACH ENERGY LTD | DOMBEY 001 DW1 | ENSIGN 931 | J.19.060369 | RPI | TCP-PERM-JOB | InComplete | Operationally Complete | Close - PSD |  | Not Started | Design Completed | In Progress |  | 2019-10-20 10:14 |  | 2019-10-15 | 2020-01-07 |  |  | APG TS | RWallis | 2022-10-03 06:22 | FDPSystemUser |  | No |  |  |  |  | Wayne Wallis |  | 198585.28 | [10 empty] | 0 | [7 empty] | Richard Steers | TCP-Tubing-Conveyed Perforation
P.1002322 | O.1002322.02 | A.1002322.02.01 | Enterprise-1 Flowback | BEACH ENERGY LTD | Enterprise 1 | EASTERNWELL 106 | J.20.062335 | RPI | TSWT-FLOWBACK-JOB | High | Operationally Complete | Close - PSD |  | In Progress | Not Required | In Progress |  | 2020-12-02 |  | 2020-12-07 | 2020-12-17 23:59 |  |  | APG TS | JMarkowski | 2022-10-03 06:22 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Hidayah Sofia Hidzir |  | 0 | [10 empty] | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1002322 | O.1002322.02 | A.1002322.02.02 | TCP Shoot and Drop | BEACH ENERGY LTD | Enterprise 1 | EASTERNWELL 106 | J.20.062332 | RPI | TCP-PERM-JOB | Medium | Operationally Complete | Close - PSD |  | Not Started | Design Completed | In Progress |  | 2020-11-06 |  | 2020-12-10 | 2021-01-19 23:59 |  |  | APG TS | MSwara | 2022-10-03 06:22 | FDPSystemUser |  | No |  | [AUNB-DST] - Perth- New Burn TST |  |  | Yudha Swara |  | 0 | [10 empty] | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TCP-Tubing-Conveyed Perforation
P.1002322 | O.1002322.01 | A.1002322.01.01 | 2020-002B - Beach Energy - Otway Onshore - SWT | BEACH ENERGY LTD | Black Watch-1 | ENSIGN 931 | J.20.062333 | RPI | TSWT-SEPONLY-JOB | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-22 |  | 2020-02-12 | 2020-08-01 |  |  | APG TS | JMarkowski | 2024-11-19 20:14 | FDPSystemUser |  | No |  |  |  |  | Hidayah Sofia Hidzir |  | 19493.18 |  |  |  |  | 50 | 16.7 | 0 | 25 | 27.5 |  | 0 | [7 empty] | Richard Steers | TS Surface Testing
P.1002322 | O.1002322.01 | A.1002322.01.02 | 2020-002B - Beach Energy - Otway Onshore - TCP | BEACH ENERGY LTD | Black Watch-1 | ENSIGN 931 | J.20.062334 | RPI | TCP-PERM-JOB | InComplete | Operationally Complete | Close - PSD |  | Not Started | In Progress | In Progress |  | 2020-02-20 |  | 2020-06-11 | 2020-08-16 |  |  | APG TS | HHidzir | 2022-10-03 06:22 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 301754.5 |  |  |  |  | 41.7 | 33.3 | 0 | 37.5 | 33.8 |  | 0 | [7 empty] | Richard Steers | TCP-Tubing-Conveyed Perforation
P.1002320 | O.1002320.02 | A.1002320.02.01 | LAND TCP 750 Meters | BEACH ENERGY LTD | Well #1 | Ocean Onyx | J.22.109448 | RPI | TCP-TEMP-JOB | Medium | Cancelled | Close - PSD |  | Not Required | In Progress | In Progress |  | 2022-08-21 |  | 2022-09-21 | 2022-10-15 23:59 |  |  | APG TS | GRoxo | 2024-11-19 20:07 | FDPSystemUser |  | No |  |  |  |  | Pablo Andres Caceres Flores |  | 0 | 1 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TCP-Tubing-Conveyed Perforation
P.1002320 | O.1002320.01 | A.1002320.01.02 | Geographe - 5 Flow Back | BEACH ENERGY LTD | GEOGRAPHE-5 | Ocean Onyx | J.22.109439 | RPI | TSWT-SEPONLY-JOB | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-09-14 | 2022-06-26 |  | 2022-09-14 | 2022-09-25 23:59 |  | 2022-10-09 23:59 | APG TS | GRoxo | 2024-11-19 20:14 | FDPSystemUser | M.1000057.03.57 | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Ferly Komul |  | 42115.48 | 1 |  |  |  | 58.3 | 33.3 | 0 | 50 | 42.5 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1002320 | O.1002320.01 | A.1002320.01.03 | Geographe - 4 Flow Back | BEACH ENERGY LTD | GEOGRAPHE 4 | Ocean Onyx | J.21.108331 | RPI | TSWT-SEPONLY-JOB | High | Confirmed | Design - PSD |  | In Progress | Not Started | In Progress | 2021-06-26 | 2021-09-26 |  | 2021-09-26 | 2021-10-25 23:59 |  | 2021-07-25 23:59 | APG TS | GRoxo | 2024-11-19 20:14 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Ferly Komul |  | 101344.44 | 1 |  | L0 - No RO |  | 41.7 | 16.7 | 0 | 25 | 25 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1002320 | O.1002320.01 | A.1002320.01.08 | Thylacine North 2 | BEACH ENERGY LTD | THYLACINE NORTH-2 | Ocean Onyx | J.22.109445 | RPI | TSWT-SEPONLY-JOB | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-04-15 | 2022-04-15 |  | 2022-04-15 | 2022-08-22 23:59 |  | 2022-08-22 23:59 | APG TS | GRoxo | 2024-11-19 20:14 | FDPSystemUser | M.1000057.08.57 | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Ferly Komul |  | 121832.88 | 1 |  |  |  | 75 | 66.7 | 100 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1002320 | O.1002320.01 | A.1002320.01.05 | Thylacine North 1 | BEACH ENERGY LTD | GEOGRAPHE 5 | Ocean Onyx | J.21.108342 | RPI | TSWT-SEPONLY-JOB | High | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2021-12-27 | 2021-10-26 |  | 2021-12-27 | 2022-01-26 23:59 |  | 2022-01-26 23:59 | APG TS | GRoxo | 2024-11-19 20:14 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Ferly Komul |  | 0 | 1 |  | L0 - No RO |  | 75 | 16.7 | 0 | 0 | 27.5 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1002320 | O.1002320.01 | A.1002320.01.07 | Thylacine West 2 | BEACH ENERGY LTD | THYLACINE WEST 2 | Ocean Onyx | J.22.109444 | RPI | TSWT-SEPONLY-JOB | High | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress |  | 2022-03-02 |  | 2022-04-15 | 2022-05-29 |  |  | APG TS | GRoxo | 2024-11-19 20:14 | FDPSystemUser | M.1000057.06.57 | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Ferly Komul |  | 42121.48 | 1 |  | L0 - No RO |  | 75 | 66.7 | 0 | 62.5 | 61.3 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1002320 | O.1002320.01 | A.1002320.01.09 | Artisan 1 | BEACH ENERGY LTD | GEOGRAPHE-5 | Ocean Onyx | J.22.109446 | RPI | TSWT-SEPONLY-JOB | High | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-06-01 |  | 2022-06-01 | 2022-07-25 23:59 |  |  | APG TS | GRoxo | 2024-11-19 20:14 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Pablo Andres Caceres Flores |  | 0 | 1 |  |  |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1002320 | O.1002320.01 | A.1002320.01.06 | Thylacine West 1 | BEACH ENERGY LTD | THYLACINE WEST 1 | Ocean Onyx | J.22.109443 | RPI | TSWT-SEPONLY-JOB | High | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2022-01-01 | 2022-02-12 |  | 2022-02-12 | 2022-03-31 23:59 |  | 2022-04-18 23:59 | APG TS | GRoxo | 2024-11-19 20:14 | FDPSystemUser |  | No |  | [AUJN-TSWT] - AU - Jandakot STT |  |  | Ferly Komul |  | 42122.48 | 1 |  | L0 - No RO |  | 75 | 33.3 | 0 | 37.5 | 43.8 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TS Surface Testing
P.1002320 | O.1002320.01 | A.1002320.01.04 | 2020-002A - Beach Energy - Otway Offshore - Equipment Rental (After call off) | BEACH ENERGY LTD | THYLACINE NORTH 1, THYLACINE WEST 1, GEOGRAPHE 4, GEOGRAPHE 5, THYLACINE WEST 2, THYLACINE NORTH 2 | Ocean Onyx | J.21.108332 | RPI | TSWT-DSGN | Medium | Confirmed | Design - PSD |  | In Progress | Not Started | In Progress | 2020-05-11 08:00 | 2021-06-15 |  | 2021-06-15 | 2022-08-10 |  | 2024-06-20 | APG TS | GRoxo | 2022-10-03 06:25 | FDPSystemUser |  | No |  | [AUNB-TSWT] - Perth- New Burn STT |  |  | Allwyn Francis |  | 0 | 0 |  | L0 - No RO |  | 58.3 | 33.3 | 100 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1002320 | O.1002320.01 | A.1002320.01.01 | 2020-002A - Beach Energy - Otway Offshore - Equipment Rental | BEACH ENERGY LTD | THYLACINE NORTH-1, THYLACINE WEST-1, Geographe-4, GEOGRAPHE-5 | Ocean Onyx | J.21.108322 | RPI | TSWT-DSGN | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-03-11 |  | 2021-03-26 | 2021-06-14 |  |  | APG TS | JMarkowski | 2022-10-03 06:22 | FDPSystemUser |  | No |  | [AUNB-TSWT] - Perth- New Burn STT |  |  | Allwyn Francis |  | 144891.05 | 0 |  |  |  | 66.7 | 50 | 100 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1002147 | O.1002147.04 | A.1002147.04.01 | JULA03 SWT Flowback | WOODSIDE ENERGY LTD | JULA03 | Ocean Apex | J.20.062323 | RPI | TSWT-SEPONLY-JOB | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-10-31 17:42 |  | 2020-11-14 17:41 | 2020-11-29 17:42 |  |  | APG TS | RWallis | 2024-11-19 20:14 | FDPSystemUser |  | No |  |  |  |  | Wayne Wallis |  | 0 | [10 empty] | 0 | [7 empty] | Richard Steers | TS Surface Testing
P.1002147 | O.1002147.04 | A.1002147.04.02 | JULA03 Sampling Analysis | WOODSIDE ENERGY LTD | JULA03 | Ocean Apex | J.20.062321 | RPE | FSA-SF-JOB | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-10-31 17:43 |  | 2020-11-14 17:43 | 2020-11-29 17:43 |  |  | APG TS | RWallis | 2022-10-03 06:21 | FDPSystemUser |  | No |  |  |  |  | Wayne Wallis |  | 0 | [10 empty] | 0 | [7 empty] | Richard Steers | TS Downhole Reservoir Testing
P.1002147 | O.1002147.03 | A.1002147.03.01 | JULA02 SWT Flowback | WOODSIDE ENERGY LTD | JULA02, JULIMAR CAMPAIGN | Ocean Apex | J.20.062325 | RPI | TSWT-SEPONLY-JOB | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-31 17:57 |  | 2020-09-14 17:57 | 2020-09-29 17:57 |  |  | APG TS | RWallis | 2024-11-19 20:14 | FDPSystemUser |  | No |  | [AUNB-TSWT] - Perth- New Burn STT |  |  | Wayne Wallis |  | 0 |  |  |  |  | 58.3 | 25 | 0 | 25 | 32.5 |  | 0 | [7 empty] | Richard Steers | TS Surface Testing
P.1002147 | O.1002147.03 | A.1002147.03.02 | JULA02 Sampling Analysis | WOODSIDE ENERGY LTD | JULA02 | Ocean Apex | J.20.062330 | RPE | FSA-SF-JOB | High | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-31 17:59 |  | 2020-09-14 17:59 | 2020-09-29 17:59 |  |  | APG TS | RWallis | 2022-10-03 06:22 | FDPSystemUser |  | No |  |  |  |  | Wayne Wallis |  | 0 | [10 empty] | 0 | [7 empty] | Richard Steers | TS Downhole Reservoir Testing
P.1002147 | O.1002147.02 | A.1002147.02.01 | JULA01 - Julimar SWT FLowback | WOODSIDE ENERGY LTD | JULA01 | Ocean Apex | J.21.108321 | RPI | TSWT-SEPONLY-JOB | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-02-08 17:30 |  | 2021-02-22 17:30 | 2021-03-09 17:31 |  |  | APG TS | RWallis | 2024-11-19 20:14 | FDPSystemUser |  | No |  | [AUNB-TSWT] - Perth- New Burn STT |  |  | Wayne Wallis |  | 0 |  |  |  |  | 50 | 33.3 | 0 | 75 | 47.5 |  | 0 | [7 empty] | Richard Steers | TS Surface Testing
P.1002147 | O.1002147.02 | A.1002147.02.05 | Flow Back JULA01 | WOODSIDE ENERGY LTD | JULA01 | Ocean Apex | J.20.062328 | RPI | TSWT-FLOWBACK-JOB | High | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-09-14 |  | 2020-09-14 | 2020-09-17 |  |  | APG TS | FAraujo | 2022-10-03 06:21 | FDPSystemUser |  | No |  |  |  |  | Flavio Silva De Araujo |  | 0 | [10 empty] | 0 | [7 empty] | Richard Steers | TS Surface Testing
P.1002147 | O.1002147.02 | A.1002147.02.04 | Flow Back | WOODSIDE ENERGY LTD | JULA01 | Ocean Apex | J.20.062327 | RPI | TSWT-FLOWBACK-JOB | High | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-09-14 |  | 2020-09-14 | 2020-09-17 |  |  | APG TS | FAraujo | 2022-10-03 06:21 | FDPSystemUser |  | No |  |  |  |  | Flavio Silva De Araujo |  | 0 | [10 empty] | 0 | [7 empty] | Richard Steers | TS Surface Testing
P.1002147 | O.1002147.02 | A.1002147.02.02 | JULA01 - Julimar Sampling Analysis | WOODSIDE ENERGY LTD | JULA01 | Ocean Apex | J.21.108320 | RPE | FSA-SF-JOB | High | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-02-08 17:32 |  | 2021-02-22 17:32 | 2021-03-03 02:02 |  |  | APG TS | RWallis | 2022-10-03 06:21 | FDPSystemUser |  | No |  |  |  |  | Wayne Wallis |  | 0 | [10 empty] | 0 | [7 empty] | Richard Steers | TS Downhole Reservoir Testing
P.1002147 | O.1002147.02 | A.1002147.02.03 | Julimar Flow Back | WOODSIDE ENERGY LTD | JULA01 | Ocean Apex | J.20.062320 | RPI | TSWT-DSGN | High | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-09-14 |  | 2020-09-14 | 2020-09-17 |  |  | APG TS | FAraujo | 2022-10-03 06:21 | FDPSystemUser |  | No |  |  |  |  | Flavio Silva De Araujo |  | 0 | [10 empty] | 0 | [7 empty] | Richard Steers | TS Surface Testing
P.1002147 | O.1002147.01 | A.1002147.01.01 | JULA04 - Julimar SWT Flowback | WOODSIDE ENERGY LTD | JULA04, JULIMAR CAMPAIGN | Ocean Apex | J.20.062324 | RPI | TSWT-SEPONLY-JOB | InComplete | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-01-31 |  | 2020-03-31 | 2020-04-30 |  |  | APG TS | RWallis | 2024-11-19 20:14 | FDPSystemUser |  | No |  | [AUNB-TSWT] - Perth- New Burn STT |  |  | Wayne Wallis |  | 3150150.43 |  |  |  |  | 41.7 | 50 | 0 | 75 | 50 |  | 0 | [7 empty] | Richard Steers | TS Surface Testing
P.1002147 | O.1002147.01 | A.1002147.01.02 | JULA04 - Julimar Sampling Analysis | WOODSIDE ENERGY LTD |  | Ocean Apex | J.20.062331 | RPE | FSA-SF-JOB | InComplete | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-01-30 |  | 2020-03-31 | 2020-10-31 |  |  | APG TS | RWallis | 2022-10-03 06:22 | FDPSystemUser |  | No |  | [AUNB-FSA] - Perth- New Burn OLP |  |  | Allwyn Francis |  | 0 | [10 empty] | 0 | [7 empty] | Richard Steers | TS Downhole Reservoir Testing
P.1002147 | O.1002147.01 | A.1002147.01.06 | Flow Back | WOODSIDE ENERGY LTD |  | Ocean Apex | J.20.062329 | RPI | TSWT-DSGN | InComplete | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-01-22 |  | 2020-01-22 | 2020-01-25 |  |  | APG TS | FAraujo | 2022-10-03 06:21 | FDPSystemUser |  | No |  |  |  |  | Flavio Silva De Araujo |  | 0 | [10 empty] | 0 | [7 empty] | Richard Steers | TS Surface Testing
P.1002147 | O.1002147.01 | A.1002147.01.03 | Woodside-Julimar-Ocean Apex-Flowback | WOODSIDE ENERGY LTD |  | Ocean Apex | J.20.062326 | RPI | TSWT-FLOWBACK-JOB | InComplete | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-27 |  | 2020-03-31 | 2020-11-29 |  |  | APG TS | AFrancis4 | 2022-10-03 06:21 | FDPSystemUser |  | No |  |  |  |  | Allwyn Francis |  | 0 | [10 empty] | 0 | [7 empty] | Richard Steers | TS Surface Testing
P.1002147 | O.1002147.01 | A.1002147.01.04 | Flow Back | WOODSIDE ENERGY LTD | JULA04 | Ocean Apex | J.20.062322 | RPI | TSWT-FLOWBACK-JOB | InComplete | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-01-19 |  | 2020-01-20 | 2020-01-31 |  |  | APG TS | FAraujo | 2022-10-03 06:21 | FDPSystemUser |  | No |  |  |  |  | Flavio Silva De Araujo |  | 0 | [10 empty] | 0 | [7 empty] | Richard Steers | TS Surface Testing
P.1002147 | O.1002147.01 | A.1002147.01.05 | Flow Back | WOODSIDE ENERGY LTD | JULIMAR CAMPAIGN | Ocean Apex |  | RPI | TSWT-DSGN | InComplete | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-01-20 |  | 2020-01-21 | 2020-01-22 |  |  | APG TS | FAraujo | 2020-06-11 18:36 | RSteers |  | No |  |  |  |  | Flavio Silva De Araujo |  | 481318 | [10 empty] | 0 | [7 empty] | Richard Steers | TS Surface Testing
P.1002114 | O.1002114.01 | A.1002114.01.01 | 2020-004-Woodside-DPS01-Pyxis and Scarborough | WOODSIDE BURRUP PTY. LTD | PLA08 | ENSCO DPS-1 | J.20.062312 | RPI | TSWT-FLOWBACK-JOB | High | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2020-07-19 |  | 2020-08-16 | 2020-10-31 |  |  | APG TS | AFrancis4 | 2022-10-03 06:19 | FDPSystemUser |  | No |  | [AUNB-TSWT] - Perth- New Burn STT |  |  | Allwyn Francis |  | 6858413.89 | [10 empty] | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1002114 | O.1002114.01 | A.1002114.01.02 | 2020-004-Woodside-DPS-01-Scarborough Preparation | WOODSIDE BURRUP PTY. LTD | PLA08 | ENSCO DPS-1 | J.22.109437 | RPI | TSWT-DSGN | Medium | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2022-07-18 |  | 2022-07-18 | 2022-08-20 |  |  | APG TS | RWallis | 2022-10-03 06:19 | FDPSystemUser |  | No |  |  |  |  | Wayne Wallis |  | 316178.61 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1002109 | O.1002109.02 | A.1002109.02.04 | Design Support Plover & Brewster | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC 02 04, BDC 5 02 P, BDC 3 03, BDC-03-06, BDC 3 05 | Maersk Deliverer | J.21.108319 | RPI | TCP-RENTAL | High | Confirmed | Execute - PSD |  | Not Started | Design Completed | In Progress |  | 2021-03-03 | 2021-03-01 08:00 | 2021-03-03 | 2024-12-31 23:59 | 2024-12-16 |  | APG TS | JEscudero | 2024-06-04 14:06 | PZuliani |  | No |  |  |  |  | Yudha Swara |  | 7929787.53 | 0 |  |  |  | 75 | 50 | 100 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP-Tubing-Conveyed Perforation
P.1002109 | O.1002109.02 | A.1002109.02.06 | PLOVER# CT Perforation BDC-3-05P (EPP2) | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC 3 05 | Maersk Deliverer | J.23.008517 | RPI | TCP-PERM-JOB | High | Confirmed | Prepare - Mob |  | Not Required | Design Completed | In Progress |  | 2022-11-01 | 2023-06-04 | 2023-06-20 | 2023-09-30 23:59 | 2023-10-01 |  | APG TS | GRoxo | 2023-09-13 18:25 | MSwara |  | No |  |  |  |  | Yudha Swara |  | 376485.7 | 1 |  |  |  | 75 | 66.7 | 0 | 62.5 | 61.3 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP-Tubing-Conveyed Perforation
P.1002109 | O.1002109.02 | A.1002109.02.03 | PLOVER # CT Perforating - BDC-5-02 (EPP-1) | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC 5 02 P | Maersk Deliverer | J.22.109436 | RPI | TCP-PERM-JOB | High | Operationally Complete | Close - PSD |  | Not Required | Design Completed | Design Completed |  | 2022-08-31 |  | 2022-10-07 | 2022-10-25 23:59 |  |  | APG TS | JEscudero | 2022-10-25 07:30 | MSwara |  | No |  |  |  |  | Yudha Swara |  | 0 | 1 |  |  |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TCP-Tubing-Conveyed Perforation
P.1002109 | O.1002109.02 | A.1002109.02.07 | Monthly - Design Support | INPEX OPERATIONS AUSTRALIA PTY LTD | EPP 3_BDC4 | Maersk Deliverer | J.21.108336 | RPI | TCP-DSGN | High | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2021-07-16 |  | 2021-07-16 | 2021-08-15 23:59 |  |  | APG TS | GRoxo | 2022-10-03 06:26 | FDPSystemUser |  | No |  |  |  |  | Jose Escudero |  | 0 | 1 |  |  |  | 50 | 33.3 | 100 | 50 | 50 |  | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TCP-Tubing-Conveyed Perforation
P.1002109 | O.1002109.02 | A.1002109.02.05 | Monthly - Design Support | INPEX OPERATIONS AUSTRALIA PTY LTD | EPP 3_BDC4 | Maersk Deliverer | J.21.108335 | RPI | TCP-RENTAL | High | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress |  | 2021-03-26 23:00 |  | 2021-03-26 23:00 | 2021-06-30 22:59 |  |  | APG TS | GRoxo | 2022-10-03 06:26 | FDPSystemUser |  | No |  |  |  |  | Jose Escudero |  | 0 | 1 |  |  |  | 50 | 33.3 | 100 | 50 | 50 |  | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TCP-Tubing-Conveyed Perforation
P.1002109 | O.1002109.02 | A.1002109.02.02 | PLOVER#1_BDC-4-06_CT Perforation | INPEX OPERATIONS AUSTRALIA PTY LTD | EPP 3_BDC4 | Maersk Deliverer | J.21.108318 | RPI | TCP-STB | High | Operationally Complete | Close - PSD |  | Not Started | Design Completed | In Progress |  | 2021-06-27 |  | 2021-07-01 | 2021-08-24 |  |  | APG TS | JEscudero | 2022-10-03 06:19 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 1479609.48 | 1 |  |  |  | 75 | 50 | 100 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TCP-Tubing-Conveyed Perforation
P.1002109 | O.1002109.02 | A.1002109.02.01 | DESIGN - Coil Tubing TCP - 4.72" HSD | INPEX OPERATIONS AUSTRALIA PTY LTD | EPP 3_BDC4 | Maersk Deliverer | J.20.062311 | RPI | TCP-PERM-JOB | InComplete | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-04-15 |  | 2020-04-15 | 2020-12-31 |  |  | APG TS | RSteers | 2022-10-03 06:19 | FDPSystemUser |  | No |  |  |  |  | Jose Escudero |  | 2041167.87 | [10 empty] | 0 | [7 empty] | Richard Steers | TCP-Tubing-Conveyed Perforation
P.1002109 | O.1002109.01 | A.1002109.01.09 | 09 - End of Project Gun Unloading | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-2-01 | Maersk Deliverer | J.24.088642 | RPI | TCP-NO-OP | Medium | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2024-10-01 | 2024-11-14 | 2024-11-16 | 2025-02-28 23:59 | 2025-06-02 |  | APG TS | MSwara | 2025-05-30 11:57 | fkomul |  | No |  | [AUSG-TCP] - |  |  | Yudha Swara |  | 185615.9 | 1 |  |  |  | 58.3 | 50 | 100 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP-Tubing-Conveyed Perforation
P.1002109 | O.1002109.01 | A.1002109.01.08 | TCP 3.5" CRA HPHT Guns / BDC-1A-I (02) | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-1A-02 | Maersk Deliverer | J.24.000779 | RPI | TCP-PERM-JOB | Medium | Operationally Complete | Close - PSD |  | Not Required | Design Completed | In Progress |  | 2024-04-01 |  | 2024-09-16 | 2024-11-30 23:59 |  |  | APG TS | MSwara | 2024-11-27 14:08 | FDPSystemUser |  | No |  | [AUSG-TCP] - |  |  | Yudha Swara |  | 255920 | 1 |  |  |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP-Tubing-Conveyed Perforation
P.1002109 | O.1002109.01 | A.1002109.01.10 | TCP 3.5" CRA HPHT / BDC-2-03 Operations | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-2-03 | Maersk Deliverer | J.24.102632 | RPI | TCP-PERM-JOB | Medium | Operationally Complete | Close - PSD |  | In Progress | Design Completed | Design Completed | 2024-07-22 | 2024-05-28 |  | 2024-07-08 | 2024-08-23 23:59 |  | 2024-08-23 23:59 | APG TS | EKondratiev | 2024-08-27 09:05 | MSwara |  | No |  | [AUSG-TCP] - |  |  | Yudha Swara |  | 185680 | 1 |  |  |  | 87.5 | 83.3 | 100 | 87.5 | 87.5 |  | 0 |  | Working | D10072402172¦R01 | 0 |  |  |  | Evgeniy Kondratiev | TCP-Tubing-Conveyed Perforation
P.1002109 | O.1002109.01 | A.1002109.01.06 | TCP 3.5" CRA HPHT Guns / BDC-2-03 (C) Gun Loading | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-2-03 | Maersk Deliverer | J.24.000777 | RPI | TCP-NO-OP | Medium | Operationally Complete | Close - PSD |  | Not Required | Not Required | Design Completed |  | 2024-04-15 |  | 2024-06-06 | 2024-06-25 23:59 |  |  | APG TS | MSwara | 2024-07-25 08:46 | MSwara |  | No |  | [AUSG-TCP] - |  |  | Yudha Swara |  | 175960 | 1 |  |  |  | 100 | 83.3 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP-Tubing-Conveyed Perforation
P.1002109 | O.1002109.01 | A.1002109.01.07 | TCP 3.5" CRA HPHT Guns / BDC-2-02 (D) | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-2-02 | Maersk Deliverer | J.24.000778 | RPI | TCP-PERM-JOB | Medium | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2024-02-10 |  | 2024-02-10 | 2024-06-07 23:59 |  |  | APG TS | MSwara | 2024-06-20 14:50 | EKondratiev |  | No |  | [AUSG-TCP] - |  |  | Yudha Swara |  | 261380 | 1 |  |  |  | 83.3 | 66.7 | 100 | 100 | 85 |  | 0 |  | Working | D13032407191¦R01 | 0 |  |  |  | Evgeniy Kondratiev | TCP-Tubing-Conveyed Perforation
P.1002109 | O.1002109.01 | A.1002109.01.05 | TCP 3.5" CRA HPHT Guns / BDC-2-01 (A) | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-2-01 | Maersk Deliverer | J.23.031096 | RPI | TCP-PERM-JOB | Medium | Operationally Complete | Close - PSD |  | Not Required | Not Required | In Progress |  | 2023-07-25 |  | 2023-12-01 | 2024-02-23 23:59 |  |  | APG TS | MSwara | 2024-02-26 11:35 | MSwara |  | No |  | [AUSG-TCP] - |  |  | Yudha Swara |  | 510070.55 | 1 |  |  |  | 75 | 66.7 | 100 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP-Tubing-Conveyed Perforation
P.1002109 | O.1002109.01 | A.1002109.01.04 | TCP 3.5" CRA HPHT Guns / BDC-2-04 (B) | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC 02 04 | Maersk Deliverer | J.23.030364 | RPI | TCP-PERM-JOB | Medium | Operationally Complete | Close - PSD |  | Not Required | Design Completed | In Progress |  | 2023-06-01 |  | 2023-09-24 | 2023-11-30 23:59 |  |  | APG TS | MSwara | 2024-01-03 13:34 | MSwara |  | No |  | [AUSG-TCP] - |  |  | Yudha Swara |  | 351635 | 1 |  |  |  | 75 | 50 | 0 | 25 | 45 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP-Tubing-Conveyed Perforation
P.1002109 | O.1002109.01 | A.1002109.01.02 | TCP 3.5" Cr Guns / BDC-3-03 (D) | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC 3 03 | Maersk Deliverer | J.22.109438 | RPI | TCP-PERM-JOB | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-24 | 2022-08-05 |  | 2022-10-30 | 2022-12-15 23:59 |  | 2022-03-27 23:59 | APG TS | JEscudero | 2023-05-09 09:54 | MSwara |  | No |  |  |  |  | Yudha Swara |  | 0 | 1 |  |  |  | 75 | 33.3 | 0 | 100 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Wayne Wallis | TCP-Tubing-Conveyed Perforation
P.1002109 | O.1002109.01 | A.1002109.01.03 | TCP 3.5" Cr Guns / BDC-3-06 (A) | INPEX OPERATIONS AUSTRALIA PTY LTD | BDC-03-06 | Maersk Deliverer | J.22.109441 | RPI | TCP-PERM-JOB | Medium | Operationally Complete | Close - PSD |  | Not Required | Design Completed | In Progress |  | 2022-10-01 |  | 2023-03-15 | 2023-04-30 23:59 |  |  | APG TS | JEscudero | 2023-05-05 08:46 | MSwara |  | No |  |  |  |  | Yudha Swara |  | 112020 | 1 |  |  |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Evgeniy Kondratiev | TCP-Tubing-Conveyed Perforation
P.1002109 | O.1002109.01 | A.1002109.01.01 | 13Cr 3.5 HSD 6 spf / 4.72 HSD 5 spf | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Maersk Deliverer | J.21.108317 | RPI | TCP-SALE | Medium | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2021-06-26 |  | 2021-06-26 | 2021-07-25 |  |  | APG TS | RSteers | 2022-10-03 06:19 | FDPSystemUser |  | No |  |  |  |  | Jose Escudero |  | 0 | 1 |  |  |  | 33.3 | 33.3 | 100 | 50 | 45 |  | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TCP-Tubing-Conveyed Perforation
P.1002086 | O.1002086.01 | A.1002086.01.01 | Woodside Hg Analysis | WOODSIDE ENERGY LTD | JULIMAR CAMPAIGN, JULA02, JULA04 | Ocean Apex |  | RPE | FSA-SF-JOB | InComplete | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2019-11-01 |  | 2019-12-01 | 2020-07-30 |  |  | APG TS | RSteers | 2020-07-29 15:15 | VLakhsmi |  | No |  |  |  |  | Yagan Bibby |  | 1140669 | [10 empty] | 0 | [7 empty] | Richard Steers | TS Downhole Reservoir Testing
P.1002085 | O.1002085.01 | A.1002085.01.03 | Santos STIM - FV 503 | SANTOS LIMITED | Fairview 503 | ENTERPRISE | J.20.062304 | RPI | TCP-TEMP-JOB | InComplete | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-06-03 |  | 2020-06-03 | 2020-06-03 23:00 |  |  | APG TS | GRoxo | 2024-11-19 20:07 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 59779.08 |  |  |  |  | 50 | 16.7 | 0 | 37.5 | 31.3 |  | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TCP-Tubing-Conveyed Perforation
P.1002085 | O.1002085.01 | A.1002085.01.02 | Execution - TCP STIM Gun FV501 | SANTOS LIMITED | Fairview 501 | ENTERPRISE | J.20.062309 | RPI | TCP-TEMP-JOB | InComplete | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-05-20 |  | 2020-05-20 | 2020-07-26 |  |  | APG TS | MSwara | 2024-11-19 20:07 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 59779.08 |  |  |  |  | 50 | 16.7 | 0 | 37.5 | 31.3 |  | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TCP-Tubing-Conveyed Perforation
P.1002085 | O.1002085.01 | A.1002085.01.04 | Santos STIM FV 519 | SANTOS LIMITED | Fairview 519 | ENTERPRISE | J.20.062310 | RPI | TCP-TEMP-JOB | InComplete | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-06-03 |  | 2020-06-03 | 2020-06-07 23:59 |  |  | APG TS | GRoxo | 2024-11-19 20:07 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 56855.1 |  |  |  |  | 33.3 | 16.7 | 0 | 50 | 30 |  | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TCP-Tubing-Conveyed Perforation
P.1002085 | O.1002085.01 | A.1002085.01.05 | Santos STIM FV-17-19-1 | SANTOS LIMITED | FV17-19-1 | ENTERPRISE | J.20.062316 | RPI | TCP-TEMP-JOB | InComplete | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-06-01 |  | 2020-06-10 | 2020-06-18 23:59 |  |  | APG TS | GRoxo | 2024-11-19 20:07 | FDPSystemUser |  | No |  |  |  |  | Zhong Wei Gao |  | 59779.08 |  |  |  |  | 33.3 | 33.3 | 0 | 50 | 35 |  | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TCP-Tubing-Conveyed Perforation
P.1002085 | O.1002085.01 | A.1002085.01.01 | Design Phase - TCP STIM gun | SANTOS LIMITED | FV17-19-1, Fairview 501, FV17-19-2, Fairview 503, Fairview 519 | ENTERPRISE | J.20.062317 | RPI | TCP-TEMP-JOB | InComplete | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress |  | 2019-11-25 |  | 2020-03-28 | 2020-04-27 |  |  | APG TS | MSwara | 2024-11-19 20:07 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 413362.04 |  |  |  |  | 50 | 16.7 | 0 | 25 | 27.5 |  | 0 | [7 empty] | Richard Steers | TCP-Tubing-Conveyed Perforation
P.1002085 | O.1002085.01 | A.1002085.01.06 | Santos STIM FV-17-19-2 | SANTOS LIMITED | FV17-19-2 | ENTERPRISE | J.20.062319 | RPI | TCP-TEMP-JOB | InComplete | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-06-21 |  | 2020-06-22 | 2020-06-28 23:59 |  |  | APG TS | GRoxo | 2024-11-19 20:07 | FDPSystemUser |  | No |  |  |  |  | Zhong Wei Gao |  | 59779.08 |  |  |  |  | 33.3 | 16.7 | 0 | 37.5 | 26.3 |  | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TCP-Tubing-Conveyed Perforation
P.1002084 | O.1002084.01 | A.1002084.01.01 | 2019-012-Sapura-Pluto-LWI-Bleed Off | NORMAND SAPURA PTY LTD | PLA07, Wanaea-11, WANAEA 3 | SapuraKencana Constructor |  | RPI | TSWT-NOSEPNOVX-JOB | InComplete | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2019-10-11 |  | 2019-10-14 | 2019-11-30 |  |  | APG TS | AFrancis4 | 2020-06-22 14:03 | GRoxo |  | No |  |  |  |  | Josh Markowski |  | 0 | [10 empty] | 0 | [7 empty] | Richard Steers | TS Surface Testing
P.1002076 | O.1002076.04 | A.1002076.04.02 | Perof 3-3/8 | SANTOS LIMITED |  | WILD DESERT RIG 4 | J.24.096930 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-05-13 | 2024-05-11 | 2024-05-13 | 2024-05-13 | 2024-05-26 23:59 | 2024-05-27 | 2024-05-26 23:59 | Moomba WL | FShallal | 2024-05-23 15:21 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 5 |  | L0 - No RO |  | 83.3 | 50 | 0 | 0 | 40 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1002076 | O.1002076.04 | A.1002076.04.01 | Toobunyah 5 | SANTOS LIMITED | Well #31 | WILD DESERT RIG 4 | J.28.000010 | RPI | PS-WL-Ops | Low | Unconfirmed - 10% | Design - CEC |  | In Progress | Not Started | Not Started | 2028-05-20 13:00 | 2028-05-20 |  | 2028-05-20 13:00 | 2028-05-23 23:59 |  | 2028-05-23 23:59 | Moomba WL | FShallal | 2024-05-10 14:48 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 1 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.26 | Zeus 10 Plug Perf | SANTOS LIMITED | ZEUS 010, TENNAPERRA 5, ZEUS 15, MINOS 4 | WILD DESERT RIG 4 | J.24.100366 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-02-13 19:30 | 2024-05-15 |  | 2024-05-18 13:30 | 2024-09-04 13:29 |  | 2023-12-22 00:30 | Moomba WL | AJaved15 | 2024-08-29 08:08 | FShallal |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 12959.71 | 1 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 2 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.20 | Wellington 4 | SANTOS LIMITED | WELLINGTON 4 | WILD DESERT RIG 4 | J.23.104975 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-12 | 2023-07-10 | 2023-07-11 14:00 | 2023-07-12 | 2023-07-15 23:59 | 2023-07-16 | 2023-07-15 23:59 | Moomba WL | ADuong4 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.21 | Baryulah 6_USIT | SANTOS LIMITED | BARYULAH 6 | WILD DESERT RIG 4 | J.23.113738 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-22 12:00 | 2023-07-21 | 2023-07-22 | 2023-07-22 12:00 | 2023-08-05 11:59 | 2023-07-25 | 2023-07-24 11:59 | Moomba WL | eismail | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 1 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 75 | 75 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.22 | Baryulah 6 | SANTOS LIMITED | BARYULAH 6, MULBERRY 11, MULBERRY 42, MULBERRY 3 | WILD DESERT RIG 4 | J.23.114698 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-22 16:00 | 2023-07-22 12:00 | 2023-07-21 04:00 | 2023-07-22 16:00 | 2023-08-31 23:59 | 2023-09-01 | 2023-08-31 23:59 | Moomba WL | ADuong4 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.23 | Watkins North 1,2 | SANTOS LIMITED | BARYULAH 6, MULBERRY 11, MULBERRY 42, MULBERRY 3, WATKINS NORTH 1, WATKINS NORTH 2 | WILD DESERT RIG 4 | J.23.138822 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-09-26 16:00 | 2023-09-25 12:00 |  | 2023-09-26 16:00 | 2023-10-31 00:59 |  | 2023-10-31 00:59 | Moomba WL | ymoradi2 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 6288.5 | 1 |  | L0 - No RO |  | 100 | 100 | 0 | 100 | 90 |  | 1 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.24 | Toobunyah 5 | SANTOS LIMITED | TOOBUNYAH 5 | WILD DESERT RIG 4 | J.23.160206 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | Design Completed | Not Started | Not Started | 2023-10-29 13:00 | 2023-10-29 |  | 2023-10-29 13:00 | 2023-11-01 23:59 |  | 2023-11-01 23:59 | Moomba WL | ADuong4 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.25 | Hera 2 | SANTOS LIMITED | HERA 2 | WILD DESERT RIG 4 | J.24.038985 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-01-09 12:00 | 2024-01-08 12:00 |  | 2024-01-09 12:00 | 2024-01-11 23:59 |  | 2024-01-11 23:59 | Moomba WL | ADuong4 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 1 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Adel Mohammad Alhashemi | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.19 | Narcoonowie 8-Tubing Cut-Punch | SANTOS LIMITED | Narcoonowie 8 | WILD DESERT RIG 4 | J.22.110095 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-09-13 16:00 | 2022-09-13 09:00 |  | 2022-09-13 16:00 | 2022-09-14 10:00 |  | 2022-09-14 10:00 | Moomba WL | ymoradi2 | 2022-10-03 12:40 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 6686.16 | 1 |  |  |  | 50 | 66.7 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.18 | Tickalara 21 | SANTOS LIMITED | Tickalara 22 | WILD DESERT RIG 4 | J.21.108776 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-03 17:00 | 2021-11-03 09:00 | 2021-11-03 01:00 | 2021-11-03 16:00 | 2021-11-04 10:00 | 2021-11-05 01:00 | 2021-11-04 11:00 | Moomba WL | KKeese | 2022-10-03 11:40 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6686.16 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.17 | Wilson 6 | SANTOS LIMITED | BARYULAH 2 | WILD DESERT RIG 4 | J.21.108775 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-31 17:00 | 2021-10-31 09:00 | 2021-10-31 01:00 | 2021-10-31 16:00 | 2021-11-01 10:00 | 2021-11-02 01:00 | 2021-11-01 11:00 | Moomba WL | KKeese | 2022-10-03 11:40 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6686.16 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.16 | Baryulah 2- PowerCutter | SANTOS LIMITED | BARYULAH 2 | WILD DESERT RIG 4 | J.21.108737 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-07 16:00 | 2021-09-07 09:00 | 2021-09-07 | 2021-09-07 16:00 | 2021-09-08 10:00 | 2021-09-09 | 2021-09-08 10:00 | Moomba WL | DKitney | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6686.16 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.15 | Tickalara 22- Perf | SANTOS LIMITED | Tickalara 22 | WILD DESERT RIG 4 | J.21.108652 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-31 08:00 | 2021-07-30 17:00 | 2021-07-31 | 2021-07-31 08:00 | 2021-07-31 14:00 | 2021-08-01 | 2021-07-31 14:00 | Moomba WL | DKitney | 2022-10-03 11:26 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 10162.96 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.14 | Tickalara 16 | SANTOS LIMITED | Tickalara 16, Tickalara 22 | WILD DESERT RIG 4 | J.21.108550 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-03 06:00 | 2021-05-31 | 2021-06-02 | 2021-06-03 06:00 | 2021-06-11 15:00 | 2021-06-11 09:00 | 2021-06-11 15:00 | Moomba WL | KKeese | 2022-10-03 11:17 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 15369.38 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.03 | Seccante 3 Perforation | SANTOS LIMITED | Seccante 3 | WILD DESERT RIG 4 | J.20.062925 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-03-26 06:00 | 2020-03-23 |  | 2020-03-26 06:00 | 2020-03-29 06:00 |  | 2020-11-29 06:00 | Moomba WL | SGilbert | 2022-10-03 10:58 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 15369.38 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.10 | Psyche 2 | SANTOS LIMITED | Psyche 2 | WILD DESERT RIG 4 | J.20.062922 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-12-27 12:00 | 2020-09-11 |  | 2020-12-27 12:00 | 2021-01-01 11:59 |  | 2021-01-01 11:59 | Moomba WL | DKitney | 2022-10-03 10:57 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.02 | Munkah 7 | SANTOS LIMITED | Munkah 1 | WILD DESERT RIG 4 | J.20.062921 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-03-04 12:52 | 2020-03-03 |  | 2020-03-04 12:52 | 2020-03-07 12:52 |  | 2020-11-07 12:52 | Moomba WL | DParker16 | 2022-10-03 10:57 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6686.16 |  |  |  |  | 66.7 | 0 | 0 | 0 | 20 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.09 | Chookoo 3 | SANTOS LIMITED | Chookoo 1 | WILD DESERT RIG 4 | J.20.062920 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-08-15 | 2020-08-14 |  | 2020-08-15 | 2020-08-19 23:59 |  | 2020-08-19 23:59 | Moomba WL | KKeese | 2022-10-03 10:57 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 |  |  |  |  | 66.7 | 0 | 0 | 0 | 20 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.12 | Cook 27 | SANTOS LIMITED | Cook 27 | WILD DESERT RIG 4 | J.20.062918 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-09-30 06:00 | 2020-09-28 |  | 2020-09-30 06:00 | 2020-10-03 05:59 |  | 2020-10-03 05:59 | Moomba WL | KKeese | 2022-10-03 10:57 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.08 | Cooroo 7 | SANTOS LIMITED | Cooroo 7 (APP A) | WILD DESERT RIG 4 | J.20.062917 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-06-27 | 2020-06-12 |  | 2020-06-27 | 2020-06-28 23:59 |  | 2020-06-28 23:59 | Moomba WL | KKeese | 2022-10-03 10:57 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 9434.7 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.13 | Wilson 6 | SANTOS LIMITED | WILSON 6 | WILD DESERT RIG 4 | J.21.108416 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-23 10:00 | 2021-01-23 |  | 2021-01-23 10:00 | 2021-01-25 07:04 |  | 2021-01-25 07:04 | Moomba WL | DParker16 | 2022-10-03 10:56 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 27317.74 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.11 | Cocinero 10 | SANTOS LIMITED | Cocinero 11 | WILD DESERT RIG 4 | J.20.062911 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-09-26 | 2020-09-26 |  | 2020-09-26 | 2020-09-28 23:59 |  | 2020-09-28 23:59 | Moomba WL | KKeese | 2022-10-03 10:56 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.04 | Seccante 4 Perforation | SANTOS LIMITED | Seccante 4 | WILD DESERT RIG 4 | J.20.062910 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-03-30 12:00 | 2020-03-25 |  | 2020-03-30 12:00 | 2020-03-31 12:00 |  | 2020-12-03 12:00 | Moomba WL | SGilbert | 2022-10-03 10:56 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 13109.43 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.06 | Wackett 5-Packer Setting TCP | SANTOS LIMITED | Wackett 5 | WILD DESERT RIG 4 | J.20.062909 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-06-06 | 2020-06-04 |  | 2020-06-06 | 2020-06-10 23:59 |  | 2020-06-10 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:56 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.05 | Seccante 6 Perforations | SANTOS LIMITED | Seccante 6 | WILD DESERT RIG 4 | J.20.062908 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-04-05 20:30 | 2020-03-29 01:00 |  | 2020-04-06 06:00 | 2020-04-09 06:00 |  | 2020-12-09 20:30 | Moomba WL | SGilbert | 2022-10-03 10:56 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 13109.43 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.01 | Perforation | SANTOS LIMITED | Vega 6 | WILD DESERT RIG 4 | J.19.060531 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2019-12-24 17:00 | 2019-12-24 |  | 2019-12-25 | 2019-12-28 |  | 2019-12-28 | Moomba WL | ASetya | 2022-10-03 10:56 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1002076 | O.1002076.03 | A.1002076.03.07 | Coorooo NW5-Perfo | SANTOS LIMITED | Cooroo North West 5 | WILD DESERT RIG 4 | J.20.062906 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-06-27 12:00 | 2020-06-08 |  | 2020-06-27 12:00 | 2020-06-30 11:59 |  | 2020-06-30 11:59 | Moomba WL | ymoradi2 | 2022-10-03 10:56 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1002076 | O.1002076.02 | A.1002076.02.19 | Hector 1 | SANTOS LIMITED | HECTOR 1 | WILD DESERT RIG 4 | J.23.152393 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-10-15 22:00 | 2023-10-06 |  | 2024-10-12 22:00 | 2024-10-14 22:00 |  | 2025-01-12 21:59 | Moomba WL | FShallal | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 4824.56 | 1 |  | L0 - No RO |  | 83.3 | 50 | 0 | 50 | 55 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1002076 | O.1002076.02 | A.1002076.02.21 | Cocinero Perforation Campaign | SANTOS LIMITED | COCINERO 14, COCINERO 15, COCINERO 16, COCINERO 17 | WILD DESERT RIG 4 | J.24.055521 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2024-02-22 16:00 | 2024-02-20 |  | 2024-02-22 16:00 | 2024-03-27 15:59 |  | 2024-03-27 15:59 | Moomba WL | ymoradi2 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 6578.95 | 1 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Adel Mohammad Alhashemi | WL Production Services
P.1002076 | O.1002076.02 | A.1002076.02.20 | Jackson 56 plug & Perf | SANTOS LIMITED | JACKSON 56, COCINERO 14, COCINERO 15, ZEUS 14, TENNAPERRA 5 | WILD DESERT RIG 4 | J.24.045554 | RPI | PS-WL-NO | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2024-01-27 16:00 | 2024-01-25 |  | 2024-01-27 16:00 | 2024-07-11 15:59 |  | 2024-07-09 15:59 | Moomba WL | AJaved15 | 2024-08-07 19:47 | FShallal |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 6578.95 | 1 |  | L0 - No RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 1 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1002076 | O.1002076.02 | A.1002076.02.22 | Wackett 3-P&A Perf | SANTOS LIMITED | HECTOR 1, WACKETT 3 | WILD DESERT RIG 4 | J.24.083457 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-04-17 | 2024-04-13 | 2024-04-12 13:00 | 2024-04-14 | 2024-05-31 22:00 | 2024-10-15 | 2024-07-14 23:59 | Moomba WL | ymoradi2 | 2024-05-10 08:26 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 4824.56 | 1 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1002076 | O.1002076.02 | A.1002076.02.18 | Strzelecki 29 | SANTOS LIMITED | STRZELECKI 29, MOOMBA 93, BIG LAKE 85 | WILD DESERT RIG 4 | J.23.053545 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-07 | 2023-03-06 | 2023-03-05 15:00 | 2023-03-07 | 2023-06-03 23:59 | 2023-06-04 | 2023-06-03 23:59 | Moomba WL | ssultan | 2023-10-03 21:20 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1002076 | O.1002076.02 | A.1002076.02.16 | Calamia East 1 | SANTOS LIMITED | Calamia East 1, Seccante 1, STIMPEE 005, GIDGEALPA 25, MOOMBA 139 | WILD DESERT RIG 4 | J.22.110092 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-08-26 | 2022-08-25 |  | 2022-08-26 | 2023-02-01 23:59 |  | 2023-02-01 23:59 | Moomba WL | ADuong4 | 2023-02-10 09:37 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 14113.71 | 3 |  | L0 - No RO |  | 91.7 | 66.7 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1002076 | O.1002076.02 | A.1002076.02.17 | Merrimelia 49 | SANTOS LIMITED | MERRIMELIA 49 | WILD DESERT RIG 4 | J.22.116990 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-10-23 |  | 2022-10-23 | 2022-10-24 23:59 |  |  | Moomba WL | KKeese | 2022-10-22 09:31 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1002076 | O.1002076.02 | A.1002076.02.15 | Cooroo NW7-SCMT-Perf | SANTOS LIMITED | Cooroo North West 7 | WILD DESERT RIG 4 | J.22.109968 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-08-04 08:00 | 2022-08-04 |  | 2022-08-04 08:00 | 2022-08-07 07:59 |  | 2022-08-07 07:59 | Moomba WL | ymoradi2 | 2022-10-03 12:27 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1002076 | O.1002076.02 | A.1002076.02.14 | tostada 1 | SANTOS LIMITED | Tostada 1 | WILD DESERT RIG 4 | J.22.109937 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-06-19 | 2022-06-13 |  | 2022-06-19 | 2022-06-21 23:59 |  | 2022-06-21 23:59 | Moomba WL | ADuong4 | 2022-10-03 12:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1002076 | O.1002076.02 | A.1002076.02.13 | Wilson 5 | SANTOS LIMITED | Wilson 5 | WILD DESERT RIG 4 | J.22.109936 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-06-12 08:00 | 2022-06-11 |  | 2022-06-12 08:00 | 2022-06-15 07:59 |  | 2022-06-15 07:59 | Moomba WL | ADuong4 | 2022-10-03 12:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 9112.28 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1002076 | O.1002076.02 | A.1002076.02.12 | Ticklara 16 perforation | SANTOS LIMITED | Tickalara 16, Tickalara 25, Tickalara 23 | WILD DESERT RIG 4 | J.21.108642 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-10 10:00 | 2021-07-10 06:00 | 2021-07-10 | 2021-07-10 10:00 | 2021-07-10 16:00 | 2021-07-11 | 2021-07-10 16:00 | Moomba WL | ymoradi2 | 2022-10-03 11:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 11323.92 | 0 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1002076 | O.1002076.02 | A.1002076.02.11 | Ipundu 8- CBL | SANTOS LIMITED | Ipundu 8 | WILD DESERT RIG 4 | J.21.108538 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-04-25 10:00 | 2021-04-25 06:00 | 2021-04-25 | 2021-04-25 10:00 | 2021-04-25 16:00 | 2021-04-26 | 2021-04-25 16:00 | Moomba WL | DKitney | 2022-10-03 11:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 11323.92 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Owen Bass | WL Production Services
P.1002076 | O.1002076.02 | A.1002076.02.09 | Psyche 3-Packer set | SANTOS LIMITED | Psyche 3 | WILD DESERT RIG 4 | J.20.062924 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-12-20 13:00 | 2020-12-18 |  | 2020-12-20 12:00 | 2020-12-24 11:59 |  | 2020-12-24 12:59 | Moomba WL | ymoradi2 | 2022-10-03 10:58 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1002076 | O.1002076.02 | A.1002076.02.04 | McKinlay 11 | SANTOS LIMITED | McKinlay 11 | WILD DESERT RIG 4 | J.20.062923 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-07-12 10:00 | 2020-07-11 12:00 |  | 2020-07-12 10:00 | 2020-07-14 17:59 |  | 2020-07-13 12:00 | Moomba WL | MSchvartz | 2022-10-03 10:58 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1002076 | O.1002076.02 | A.1002076.02.01 | Vega 6 | SANTOS LIMITED | Vega 6 | WILD DESERT RIG 4 | J.19.060533 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2019-12-15 | 2019-12-15 |  | 2019-12-15 | 2019-12-19 |  | 2019-12-19 | Moomba WL | KKeese | 2022-10-03 10:57 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1002076 | O.1002076.02 | A.1002076.02.05 | Chookoo 3 | SANTOS LIMITED | Chookoo 3 | WILD DESERT RIG 4 | J.20.062919 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-08-20 11:17 | 2020-08-18 11:17 |  | 2020-08-20 11:17 | 2020-08-24 11:17 |  | 2020-08-24 11:17 | Moomba WL | DParker16 | 2022-10-03 10:57 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 9427.49 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1002076 | O.1002076.02 | A.1002076.02.03 | HSD Perfo | SANTOS LIMITED | Irtalie East 1 | WILD DESERT RIG 4 | J.20.062916 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-06-16 16:00 | 2020-06-16 12:00 |  | 2020-06-16 16:00 | 2020-06-18 23:59 |  | 2020-06-17 18:00 | Moomba WL | AHermawan | 2022-10-03 10:57 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1002076 | O.1002076.02 | A.1002076.02.06 | Psyche 2 Tubing Punch / [Contingent Tubing Cut] ; Perforate / Packer Set / Casing Patches ; | SANTOS LIMITED | PSYCHE 2 | WILD DESERT RIG 4 | J.20.062913 | RPI | PS-WL-Ops | Low | Confirmed | Prepare - Mob |  | In Progress | In Progress | In Progress | 2020-10-02 13:23 | 2020-09-22 |  | 2020-09-22 | 2020-10-09 00:59 |  | 2020-10-03 13:28 | Moomba WL | ymoradi2 | 2022-10-03 10:56 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 58.3 | 33.3 | 0 | 12.5 | 31.3 |  | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1002076 | O.1002076.02 | A.1002076.02.08 | Psyche 7 Reperforation / Set-A-Seat Plug / Packer Set ; | SANTOS LIMITED | Psyche 7 | WILD DESERT RIG 4 | J.20.062912 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-11-17 | 2020-11-16 |  | 2020-11-17 | 2020-11-21 23:59 |  | 2020-11-21 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:56 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1002076 | O.1002076.02 | A.1002076.02.07 | Psyche 7 | SANTOS LIMITED | Psyche 7 | WILD DESERT RIG 4 | J.20.062905 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-12-21 12:00 | 2020-12-20 |  | 2020-12-21 12:00 | 2020-12-25 11:59 |  | 2020-12-25 11:59 | Moomba WL | ymoradi2 | 2022-10-03 10:55 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1002076 | O.1002076.02 | A.1002076.02.02 | Lepard 2-Perfo, Packer setting | SANTOS LIMITED | Lepard 2 | WILD DESERT RIG 4 | J.20.062904 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-02-16 06:00 | 2020-02-01 12:00 |  | 2020-02-16 06:00 | 2020-02-18 06:00 |  | 2020-02-23 06:00 | Moomba WL | ymoradi2 | 2022-10-03 10:55 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1002076 | O.1002076.02 | A.1002076.02.10 | Patroclus 3- Perfo 4.5" HSD | SANTOS LIMITED | PATROCLUS 3 | WILD DESERT RIG 4 | J.21.108415 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-02 13:00 | 2021-01-31 |  | 2021-02-01 12:00 | 2021-03-03 11:59 |  | 2021-02-05 12:59 | Moomba WL | ymoradi2 | 2022-10-03 10:55 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1002076 | O.1002076.01 | A.1002076.01.12 | Carmina 2 | SANTOS LIMITED | CARMINA 2 | Wild Desert Rig 22 | J.23.062573 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-01 06:00 | 2023-03-17 06:00 |  | 2023-04-01 06:00 | 2023-04-05 17:00 |  | 2023-04-05 17:00 | Moomba WL | KKeese | 2023-04-01 11:18 | JDagdag |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 26497.84 | 1 |  | L3 - Full RO |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1002076 | O.1002076.01 | A.1002076.01.11 | Psyche 3- Perforation | SANTOS LIMITED | Psyche 3 | Wild Desert Rig 22 | J.20.062926 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-12-27 06:00 | 2020-12-12 06:00 |  | 2020-12-27 06:00 | 2020-12-31 18:00 |  | 2020-12-31 18:00 | Moomba WL | DKitney | 2022-10-03 10:58 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 13134.75 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1002076 | O.1002076.01 | A.1002076.01.03 | Cocinero 13 | SANTOS LIMITED | COCINERO 13 | Wild Desert Rig 22 | J.19.060535 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Design Completed | In Progress | 2019-11-12 17:47 | 2019-10-23 17:47 |  | 2019-11-12 17:47 | 2019-11-14 17:47 |  | 2019-11-17 16:25 | Moomba WL | DParker16 | 2022-10-03 10:58 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7143.11 |  |  | L0 - No RO |  | 58.3 | 16.7 | 0 | 25 | 30 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1002076 | O.1002076.01 | A.1002076.01.04 | Cocinero 11 | SANTOS LIMITED | Cocinero 11 | Wild Desert Rig 22 | J.19.060534 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2019-10-29 | 2019-10-28 |  | 2019-10-28 | 2019-10-30 |  | 2019-10-30 | Moomba WL | KKeese | 2022-10-03 10:57 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6074.85 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1002076 | O.1002076.01 | A.1002076.01.07 | Isoptera 3 | SANTOS LIMITED | ISOPTERA 003 | Wild Desert Rig 22 | J.20.062915 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-04-07 10:00 | 2020-04-08 |  | 2020-04-09 | 2020-04-13 10:21 |  | 2020-04-11 20:21 | Moomba WL | DParker16 | 2022-10-03 10:57 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 12105.97 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1002076 | O.1002076.01 | A.1002076.01.06 | Isoptera 1 | SANTOS LIMITED | Isoptera 1 | Wild Desert Rig 22 | J.20.062914 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-03-23 06:00 | 2020-03-21 |  | 2020-03-23 06:00 | 2020-03-26 06:00 |  | 2020-03-26 06:00 | Moomba WL | KKeese | 2022-10-03 10:57 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1002076 | O.1002076.01 | A.1002076.01.02 | Cocinero 10 | SANTOS LIMITED | Cocinero 10 (Dev E) Oil DXCFA | Wild Desert Rig 22 | J.19.060532 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2019-10-20 10:03 | 2019-10-20 08:03 |  | 2019-10-20 10:03 | 2019-10-22 10:03 |  | 2019-10-22 10:03 | Moomba WL | DParker16 | 2022-10-03 10:57 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 13942.17 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1002076 | O.1002076.01 | A.1002076.01.10 | Psyche 2 | SANTOS LIMITED | Psyche 2 | Wild Desert Rig 22 | J.20.062907 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-11-08 12:00 | 2020-11-08 06:00 |  | 2020-11-08 12:00 | 2020-11-13 |  | 2020-11-13 | Moomba WL | AHermawan | 2022-10-03 10:56 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1002076 | O.1002076.01 | A.1002076.01.01 | Wallis 1 | SANTOS LIMITED |  | Wild Desert Rig 22 | J.19.060530 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | In Progress | In Progress | In Progress | 2019-10-09 14:05 | 2019-10-09 10:05 |  | 2019-10-09 14:05 | 2019-10-11 14:05 |  | 2019-10-11 14:05 | Moomba WL | DParker16 | 2022-10-03 10:56 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 18656.24 |  |  | L0 - No RO |  | 50 | 16.7 | 0 | 0 | 20 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1002076 | O.1002076.01 | A.1002076.01.08 | Jena 24 | SANTOS LIMITED | Jena 24 | Wild Desert Rig 22 | J.20.062903 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-04-11 11:00 | 2020-04-11 18:01 |  | 2020-04-12 06:00 | 2020-04-14 15:02 |  | 2020-04-13 20:02 | Moomba WL | DParker16 | 2022-10-03 10:55 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 17617.08 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1002076 | O.1002076.01 | A.1002076.01.05 | Cocinero 12 | SANTOS LIMITED | Cocinero 12 | Wild Desert Rig 22 | J.19.060529 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2019-11-02 | 2019-11-02 |  | 2019-11-03 | 2019-11-03 |  | 2019-11-03 12:00 | Moomba WL | KKeese | 2022-10-03 10:55 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1002076 | O.1002076.01 | A.1002076.01.09 | Meranji South 1 | SANTOS LIMITED | Meranji South 1 | Wild Desert Rig 22 | J.20.062902 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-06-04 16:00 | 2020-05-24 |  | 2020-06-04 16:00 | 2020-06-06 15:59 |  | 2020-06-06 15:59 | Moomba WL | KKeese | 2022-10-03 10:55 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1002075 | O.1002075.01 | A.1002075.01.01 | TCP_DST_TDA_Gular-1 | AGR (AUSTRALIA) PTY LTD | GULAR-1 | Noble Tom Prosser | J.19.060366 | RPI | TCP-TEMP-JOB | InComplete | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress |  | 2019-11-15 12:17 |  | 2019-12-17 | 2020-01-18 |  |  | APG TS | MSwara | 2024-11-19 20:07 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 486726.35 |  |  |  |  | 58.3 | 16.7 | 0 | 25 | 30 |  | 0 | [7 empty] | Richard Steers | TCP-Tubing-Conveyed Perforation
P.1002075 | O.1002075.01 | A.1002075.01.02 | SWT-Gular-1 | AGR (AUSTRALIA) PTY LTD | GULAR-1 | Noble Tom Prosser | J.19.060368 | RPI | TSWT-FLOWBACK-JOB | InComplete | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2019-11-15 |  | 2019-12-02 | 2019-12-20 |  |  | APG TS | MSwara | 2022-10-03 06:20 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 0 | [10 empty] | 0 | [7 empty] | Richard Steers | TS Surface Testing
P.1002074 | O.1002074.01 | A.1002074.01.01 | Aztech - TCP | BEACH ENERGY LTD | Beharra Springs-North-01 | RIGLESS - AUSTRALIA | J.19.060367 | RPI | TCP-PERM-JOB | InComplete | Operationally Complete | Close - PSD |  | Not Started | In Progress | In Progress |  | 2019-11-01 |  | 2019-11-07 | 2019-11-21 |  |  | APG TS | RSteers | 2022-10-03 06:20 | FDPSystemUser |  | No |  |  |  |  | Wayne Wallis |  | 160340.92 | [10 empty] | 0 | [7 empty] | Richard Steers | TCP-Tubing-Conveyed Perforation
P.1002073 | O.1002073.01 | A.1002073.01.01 | Design Phase GS2 - 13Cr/iOX/HSD | CHEVRON APG ABU PERTH. |  | GSF Development Driller I | J.20.062318 | RPI | TCP-PERM-JOB | InComplete | Confirmed | Execute - PSD |  | Not Started | Not Started | In Progress |  | 2019-12-15 |  | 2020-02-15 | 2020-12-15 |  |  | APG TS | RSteers | 2022-10-03 06:20 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 6517332.23 | [10 empty] | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TCP-Tubing-Conveyed Perforation
P.1002073 | O.1002073.01 | A.1002073.01.07 | 6th Well - GOR-1B | CHEVRON APG ABU PERTH. | GOR-1B | GSF Development Driller I | J.20.062315 | RPI | TCP-PERM-JOB | High | Operationally Complete | Close - PSD |  | Not Started | In Progress | In Progress |  | 2020-09-07 |  | 2020-09-15 | 2020-10-07 |  |  | APG TS | MSwara | 2022-10-03 06:20 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 127359.04 | [10 empty] | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TCP-Tubing-Conveyed Perforation
P.1002073 | O.1002073.01 | A.1002073.01.06 | 5th Well - GOR-1A | CHEVRON APG ABU PERTH. | GOR-1A | GSF Development Driller I | J.20.062314 | RPI | TCP-PERM-JOB | High | Operationally Complete | Close - PSD |  | Not Started | In Progress | In Progress |  | 2020-08-11 06:45 |  | 2020-08-18 | 2020-09-27 |  |  | APG TS | MSwara | 2022-10-03 06:20 | FDPSystemUser |  | No |  | [AUJN-DST] - AU - Jandakot TST |  |  | Yudha Swara |  | 268471.37 | [10 empty] | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TCP-Tubing-Conveyed Perforation
P.1002073 | O.1002073.01 | A.1002073.01.02 | 1st Well - GOR-4C | CHEVRON APG ABU PERTH. | GOR-4C | GSF Development Driller I | J.20.062313 | RPI | TCP-PERM-JOB | InComplete | Operationally Complete | Close - PSD |  | Not Started | Design Completed | In Progress |  | 2020-05-10 |  | 2020-05-10 | 2020-07-16 |  |  | APG TS | MSwara | 2022-10-03 06:19 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 408382.27 | [10 empty] | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TCP-Tubing-Conveyed Perforation
P.1002073 | O.1002073.01 | A.1002073.01.08 | 7th Well - GOR-1GST | CHEVRON APG ABU PERTH. | GOR-1G ST1 | GSF Development Driller I | J.20.062308 | RPI | TCP-PERM-JOB | High | Operationally Complete | Close - PSD |  | Not Started | In Progress | In Progress |  | 2020-09-23 |  | 2020-10-01 | 2020-10-23 |  |  | APG TS | MSwara | 2022-10-03 06:19 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 518759.62 | [10 empty] | 0 | [7 empty] | Richard Steers | TCP-Tubing-Conveyed Perforation
P.1002073 | O.1002073.01 | A.1002073.01.05 | 4th Well - GOR-4F | CHEVRON APG ABU PERTH. | GOR-4F | GSF Development Driller I | J.20.062307 | RPI | TCP-PERM-JOB | High | Operationally Complete | Close - PSD |  | Not Started | In Progress | In Progress |  | 2020-07-31 |  | 2020-07-31 | 2020-08-31 |  |  | APG TS | MSwara | 2022-10-03 06:19 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 239224.15 | [10 empty] | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TCP-Tubing-Conveyed Perforation
P.1002073 | O.1002073.01 | A.1002073.01.04 | 3rd Well - GOR-4E | CHEVRON APG ABU PERTH. | GOR-4E | GSF Development Driller I | J.20.062306 | RPI | TCP-PERM-JOB | High | Operationally Complete | Close - PSD |  | Not Started | Design Completed | In Progress |  | 2020-07-04 |  | 2020-07-19 | 2020-08-17 |  |  | APG TS | MSwara | 2022-10-03 06:18 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 533655.2 | [10 empty] | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TCP-Tubing-Conveyed Perforation
P.1002073 | O.1002073.01 | A.1002073.01.03 | 2nd Well - GOR-4D | CHEVRON APG ABU PERTH. | GOR-4D | GSF Development Driller I | J.20.062305 | RPI | TCP-PERM-JOB | InComplete | Operationally Complete | Close - PSD |  | Not Started | Design Completed | In Progress |  | 2020-06-29 |  | 2020-06-29 | 2020-07-31 |  |  | APG TS | MSwara | 2022-10-03 06:18 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 524358 | [10 empty] | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TCP-Tubing-Conveyed Perforation
P.1002058 | O.1002058.01 | A.1002058.01.03 | Nangwarry- CH 7in section | OTWAY ENERGY PTY LTD | NANGWARRY-1 | Easternwell 106 | J.20.062901 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-01-20 12:00 | 2020-01-20 12:00 |  | 2020-01-20 12:00 | 2020-01-23 12:00 |  | 2020-02-16 12:00 | Moomba WL | ASinger2 | 2022-10-03 10:55 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1002058 | O.1002058.01 | A.1002058.01.02 | 12 1/4 Section | OTWAY ENERGY PTY LTD | NANGWARRY-1 | Easternwell 106 | J.20.062900 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-01-18 18:00 | 2019-12-11 |  | 2020-01-18 18:00 | 2020-01-24 18:00 |  | 2020-01-24 18:00 | Moomba WL | OBass | 2022-10-03 10:55 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 82812.22 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1002058 | O.1002058.01 | A.1002058.01.01 | Nangwarry-1 | OTWAY ENERGY PTY LTD | NANGWARRY-1 | Easternwell 106 | J.20.062899 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-01-09 | 2019-12-01 |  | 2020-01-09 | 2020-02-05 |  | 2020-02-05 | Moomba WL | AGamero | 2022-10-03 10:55 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1002044 | O.1002044.01 | A.1002044.01.04 | Snatcher North 3 | SENEX ENERGY LTD | SNATCHER NORTH-3 | Saxon Rig 185 | J.19.060528 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2019-11-11 12:00 | 2019-11-08 07:00 |  | 2019-11-11 12:00 | 2019-11-14 12:00 |  | 2019-11-14 12:00 | Moomba WL | AGamero | 2022-10-03 10:55 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1002044 | O.1002044.01 | A.1002044.01.01 | Snatcher 12 | SENEX ENERGY LTD | SNATCHER-12 | Saxon Rig 185 | J.19.060527 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2019-10-27 | 2019-10-27 |  | 2019-10-27 | 2019-10-30 |  | 2019-10-30 | Moomba WL | AGamero | 2022-10-03 10:55 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1002044 | O.1002044.01 | A.1002044.01.03 | Snatcher North 12-DW1 | SENEX ENERGY LTD | SNATCHER 012 | Saxon Rig 185 | J.19.060526 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2019-10-18 07:00 | 2019-11-01 07:00 |  | 2019-11-01 07:00 | 2019-11-04 07:00 |  | 2019-11-04 07:00 | Moomba WL | AGamero | 2022-10-03 10:55 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 25 | 20 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1002044 | O.1002044.01 | A.1002044.01.02 | Snatcher North-2 | SENEX ENERGY LTD | SNATCHER NORTH-2 | Saxon Rig 185 | J.19.060525 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2019-10-16 15:00 | 2019-10-15 19:00 |  | 2019-10-16 15:00 | 2019-10-19 15:00 |  | 2019-10-19 15:00 | Moomba WL | AGamero | 2022-10-03 10:54 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001911 | O.1001911.02 | A.1001911.02.01 | 2019-011-Jadestone-Stag-MPFM | CHEVRON APG ABU PERTH. |  | Rigless Australia - 1 | J.19.060365 | RPI | TSWT-VXONLY-JOB | InComplete | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2019-10-29 |  | 2019-10-29 | 2019-10-31 |  |  | APG TS | AFrancis4 | 2024-11-19 20:21 | FDPSystemUser |  | No |  |  |  |  | Allwyn Francis |  | 0 | [10 empty] | 0 | [7 empty] | Richard Steers | TS Surface Testing
P.1001911 | O.1001911.01 | A.1001911.01.01 | CVX_VX - Barrow Island | CHEVRON APG ABU PERTH. |  | Rigless Australia - 1 | J.21.108316 | RPI | TSWT-RENTAL | High | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-10-29 |  | 2021-10-31 | 2021-12-13 |  |  | APG TS | LSimaremare | 2022-10-03 06:18 | FDPSystemUser |  | No |  |  |  |  | Wayne Wallis |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Gabriela Soter Roxo Teckemeier | TS Surface Testing
P.1001906 | O.1001906.04 | A.1001906.04.05 | USIT-CBL Merrimelia 46 | SANTOS LIMITED | MERRIMELIA 46 | Wild Desert Rig 6 | J.23.126445 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-08-26 09:00 | 2023-08-26 06:00 | 2023-08-26 | 2023-08-26 11:00 | 2023-08-30 10:59 | 2023-08-31 | 2023-08-30 08:59 | Moomba WL | eismail | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Abu Dhabi | Mazhar Iqbal |  | 0 | 1 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001906 | O.1001906.04 | A.1001906.04.04 | Liger-1 Casing Patch | SANTOS LIMITED | LIGER 1 | Wild Desert Rig 6 | J.23.101966 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-06-11 13:00 | 2023-06-11 15:00 | 2023-06-10 04:00 | 2023-06-11 15:00 | 2023-06-18 14:59 | 2023-06-18 | 2023-06-18 13:59 | Moomba WL | eismail | 2023-10-03 21:19 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001906 | O.1001906.04 | A.1001906.04.03 | Moorari 6- SCMT-Plug-Packer set- Perfo | SANTOS LIMITED | MOORARI 5 | Wild Desert Rig 6 | J.21.108814 | RPI | PS-WL-Ops | Low | Confirmed | Design - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-30 | 2021-12-29 |  | 2021-12-30 | 2021-12-31 23:59 |  | 2021-12-31 23:59 | Moomba WL | ymoradi2 | 2022-10-03 11:53 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 50 | 0 | 0 | 40 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001906 | O.1001906.04 | A.1001906.04.02 | Mckinlay 24-SCMT | SANTOS LIMITED | McKinlay 24 | Wild Desert Rig 6 | J.21.108755 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-10-07 | 2021-10-06 | 2021-10-06 | 2021-10-07 | 2021-10-08 23:59 | 2021-10-09 | 2021-10-08 23:59 | Moomba WL | YLee25 | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.04 | A.1001906.04.01 | McKinlay 21-SCMT | SANTOS LIMITED | Mckinlay 21, McKinlay 23, McKinlay 24 | Wild Desert Rig 6 | J.21.108746 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-09-25 | 2021-09-24 | 2021-09-25 | 2021-09-25 | 2021-09-28 23:59 | 2021-09-29 | 2021-09-28 23:59 | Moomba WL | ymoradi2 | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001906 | O.1001906.03 | A.1001906.03.04 | Bugito 3 | SANTOS LIMITED | BUGITO 003 | Wild Desert Rig 6 | J.20.062898 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-04-08 05:00 | 2020-04-09 |  | 2020-04-09 | 2020-04-15 14:28 |  | 2020-04-14 19:28 | Moomba WL | DParker16 | 2022-10-03 10:54 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 8585.8 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.03 | A.1001906.03.06 | Fly Lake 4 | SANTOS LIMITED | Fly Lake 4 | Wild Desert Rig 6 | J.20.062895 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-04-17 23:50 | 2020-04-17 10:00 |  | 2020-04-18 18:50 | 2020-04-20 18:50 |  | 2020-04-19 23:50 | Moomba WL | DParker16 | 2022-10-03 10:54 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7087.33 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.03 | A.1001906.03.02 | CPST-Perfo | SANTOS LIMITED | STIMPEE 005 | Wild Desert Rig 6 | J.20.062893 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-02-20 06:00 | 2020-02-20 |  | 2020-02-20 06:00 | 2020-02-22 06:00 |  | 2020-02-27 06:00 | Moomba WL | ysaeedabadian | 2022-10-03 10:54 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 13830.8 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.03 | A.1001906.03.07 | Big Lake 93 | SANTOS LIMITED | Big Lake 93 | Wild Desert Rig 6 | J.20.062891 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-04-21 08:42 | 2020-04-21 06:30 |  | 2020-04-22 13:12 | 2020-05-04 07:18 |  | 2020-05-03 12:18 | Moomba WL | DParker16 | 2022-10-03 10:53 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 12506.3 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.03 | A.1001906.03.05 | Isoptera 2 | SANTOS LIMITED | Isoptera 2 | Wild Desert Rig 6 | J.20.062890 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-04-10 20:02 | 2020-04-11 14:02 |  | 2020-04-11 15:02 | 2020-04-14 19:52 |  | 2020-04-14 00:52 | Moomba WL | DParker16 | 2022-10-03 10:53 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 15325.84 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.03 | A.1001906.03.01 | Charo 15 | SANTOS LIMITED | Charo 15 | Wild Desert Rig 6 | J.20.062885 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-01-16 10:00 | 2020-01-05 08:00 |  | 2020-01-16 10:00 | 2020-01-17 12:00 |  | 2020-01-17 12:00 | Moomba WL | AHermawan | 2022-10-03 10:53 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001906 | O.1001906.03 | A.1001906.03.03 | 3-3/8" HSD Perforation | SANTOS LIMITED | ULANDI 16 | Wild Desert Rig 6 | J.20.062882 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-02-23 16:30 | 2020-02-23 |  | 2020-02-24 | 2020-02-27 |  | 2020-02-24 16:30 | Moomba WL | ysaeedabadian | 2022-10-03 10:53 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 14917.82 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.03 | A.1001906.03.08 | Gidgeapla 33 | SANTOS LIMITED | BUGITO 003 | Wild Desert Rig 6 | J.20.062880 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-04-23 10:00 | 2020-04-24 |  | 2020-04-24 06:00 | 2020-04-25 06:00 |  | 2020-04-24 10:00 | Moomba WL | KKeese | 2022-10-03 10:52 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.03 | A.1001906.03.09 | Sturt 5 | SANTOS LIMITED | Sturt 5 | Wild Desert Rig 6 | J.20.062879 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-10-28 17:00 | 2020-10-28 12:00 |  | 2020-10-28 17:00 | 2020-10-30 23:59 |  | 2020-10-30 23:59 | Moomba WL | AHermawan | 2022-10-03 10:52 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001906 | O.1001906.03 | A.1001906.03.10 | Alwyn North 2 | SANTOS LIMITED | Alwyn North 2 | Wild Desert Rig 6 | J.21.108414 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-18 12:00 | 2021-01-18 12:00 |  | 2021-01-18 12:00 | 2021-01-19 12:00 |  | 2021-01-19 12:00 | Moomba WL | AHermawan | 2022-10-03 10:52 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.29 | TCP_Dorodilllo 8 | SANTOS LIMITED | DORODILLO 8, STRZELECKI 14, MARABOOKA 4, NUNGEROO WEST 001, MOOMBA 139, BIG LAKE 85, GIDGEALPA 32 | Wild Desert Rig 6 | J.23.101578 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-06-14 16:00 | 2023-06-12 09:30 | 2023-06-11 02:00 | 2023-06-14 16:00 | 2023-12-31 17:00 | 2024-01-01 | 2023-12-31 17:00 | Moomba WL | eismail | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 11401.52 | 1 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.30 | Cuisinier 34-Perfo | SANTOS LIMITED | BARYULAH 8, ACRUS 1, CUISINIER 34 | Wild Desert Rig 6 | J.23.108127 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-07-07 15:00 | 2023-07-06 | 2023-07-06 23:00 | 2023-07-07 15:00 | 2023-07-10 14:59 | 2023-07-10 23:00 | 2023-07-10 14:59 | Moomba WL | ymoradi2 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 100 | 100 | 0 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Adel Mohammad Alhashemi | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.31 | Gidgealpa 32 | SANTOS LIMITED |  | Wild Desert Rig 6 | J.23.171201 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2023-11-26 |  | 2023-11-26 | 2023-12-31 23:59 |  |  | Moomba WL | FShallal | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 0 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 1 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.32 | Gidgealpa 32 | SANTOS LIMITED |  | Wild Desert Rig 6 | J.23.171266 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-11-28 | 2023-11-27 |  | 2023-11-28 | 2024-03-15 23:59 |  | 2024-03-15 23:59 | Moomba WL | FShallal | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 1 |  | L0 - No RO |  | 75 | 66.7 | 0 | 50 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.33 | Moomba 44 | SANTOS LIMITED | MOOMBA 44 | Wild Desert Rig 6 | J.24.086434 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-04-18 | 2024-04-17 |  | 2024-04-18 | 2024-04-20 23:59 |  | 2024-04-20 23:59 | Moomba WL | AJaved15 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 1 |  | L0 - No RO |  | 100 | 100 | 0 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.26 | Zeus Tennaperra campaign | SANTOS LIMITED | ZEUS 1, ZEUS 14, ZEUS 15, TENNAPERRA 11, MINOS 4 | Wild Desert Rig 6 | J.23.037872 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-02-11 15:00 | 2023-02-10 |  | 2023-02-11 15:00 | 2023-02-14 14:59 |  | 2023-02-14 14:59 | Moomba WL | ymoradi2 | 2023-12-04 17:24 | eismail |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.28 | TCP_Cook East 1 | SANTOS LIMITED | COOK EAST 1 | Wild Desert Rig 6 | J.23.086350 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-22 15:00 | 2023-05-20 10:00 |  | 2023-05-22 15:00 | 2023-05-24 16:00 |  | 2023-05-24 16:00 | Moomba WL | PLima7 | 2023-05-31 09:33 | PLima7 |  | No |  |  |  |  | Mazhar Iqbal |  | 6576.96 | 1 |  | L0 - No RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.27 | Bayulah 8- Perforation Patch | SANTOS LIMITED | BARYULAH 8, ACRUS 1 | Wild Desert Rig 6 | J.23.055836 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-03-15 15:00 | 2023-03-14 |  | 2023-03-15 15:00 | 2023-03-18 14:59 |  | 2023-03-18 14:59 | Moomba WL | ymoradi2 | 2023-04-14 16:16 | PLima7 |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.25 | Marabooka 1 | SANTOS LIMITED | MARABOOKA 1 | Wild Desert Rig 6 | J.23.034861 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-02-06 12:30 | 2023-02-04 |  | 2023-02-06 12:30 | 2023-02-17 12:29 |  | 2023-02-17 12:29 | Moomba WL | ADuong4 | 2023-02-22 06:14 | ymoradi2 |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.24 | Zeus 1 | SANTOS LIMITED | ZEUS 1 | Wild Desert Rig 6 | J.22.135994 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2022-12-26 15:00 | 2022-12-24 |  | 2022-12-26 15:00 | 2022-12-29 14:59 |  | 2022-12-29 14:59 | Moomba WL | ADuong4 | 2022-12-28 08:36 | ADuong4 |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.23 | Tantanna 2- Tubing Cut | SANTOS LIMITED | TANTANNA 12, TANTANNA 2 | Wild Desert Rig 6 | J.22.133277 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-12-17 | 2022-12-11 14:00 |  | 2022-12-16 14:00 | 2022-12-18 13:59 |  | 2022-12-18 23:59 | Moomba WL | ymoradi2 | 2022-12-16 18:08 | eismail |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 0 |  | L0 - No RO |  | 75 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.22 | Durham Downs North 1 | SANTOS LIMITED | DURHAM DOWNS NORTH 1 | Wild Desert Rig 6 | J.22.127964 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2022-11-22 | 2022-11-21 |  | 2022-11-22 | 2022-11-23 23:59 |  | 2022-11-23 23:59 | Moomba WL | ADuong4 | 2022-12-01 20:53 | ymoradi2 |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.21 | Yanda 9 St1 | SANTOS LIMITED | YANDA 9 ST1 | Wild Desert Rig 6 | J.22.110099 | RPI | PS-WL-NO | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2022-10-01 14:00 | 2022-10-01 |  | 2022-10-01 14:00 | 2022-10-02 23:59 |  | 2022-10-02 23:59 | Moomba WL | ADuong4 | 2022-11-12 09:57 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 100 | 100 | 50 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.20 | Charo 5- Perforation | SANTOS LIMITED | Charo 5 | Wild Desert Rig 6 | J.22.109954 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-07-10 12:00 | 2022-07-10 08:30 |  | 2022-07-10 12:00 | 2022-07-11 12:00 |  | 2022-07-11 12:00 | Moomba WL | DKitney | 2022-10-03 12:26 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 8585.8 | 1 |  |  |  | 91.7 | 83.3 | 0 | 50 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.19 | Big Lake 77- Perforation | SANTOS LIMITED | Big Lake 77 | Wild Desert Rig 6 | J.22.109825 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-05-28 14:00 | 2022-05-28 10:00 |  | 2022-05-28 14:00 | 2022-05-29 10:00 |  | 2022-05-29 10:00 | Moomba WL | DKitney | 2022-10-03 12:13 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 5820.14 | 1 |  |  |  | 66.7 | 66.7 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.18 | Dullingari 54- Tubing Cut | SANTOS LIMITED | Dullingari 54 | Wild Desert Rig 6 | J.22.109811 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-05-11 06:00 | 2022-05-09 06:00 |  | 2022-05-11 07:00 | 2022-05-12 23:59 |  | 2022-05-12 22:59 | Moomba WL | DKitney | 2022-10-03 12:12 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.17 | Kurunda 1- P&A | SANTOS LIMITED | KURUNDA 1 | Wild Desert Rig 6 | J.22.109631 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-02-15 | 2022-02-14 |  | 2022-02-15 | 2022-02-17 23:59 |  | 2022-02-17 23:59 | Moomba WL | DKitney | 2022-10-03 11:55 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 12164.35 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.16 | McKinlay-22, McKinlay 20-SCMT campaign | SANTOS LIMITED | McKinlay 22, McKinlay 20 | Wild Desert Rig 6 | J.21.108662 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-08-26 06:00 | 2021-08-25 06:00 | 2021-08-25 14:00 | 2021-08-26 06:00 | 2021-08-30 23:59 | 2021-09-01 | 2021-08-31 23:59 | Moomba WL | ymoradi2 | 2022-10-03 11:27 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.15 | Tirrawarra 16 Perforation | SANTOS LIMITED | Tirrawarra 16 | Wild Desert Rig 6 | J.21.108650 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-05 06:00 | 2021-08-04 06:00 | 2021-08-04 14:00 | 2021-08-05 06:00 | 2021-08-09 23:59 | 2021-08-11 | 2021-08-10 23:59 | Moomba WL | KKeese | 2022-10-03 11:26 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 91.7 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.14 | Tirrawarra 16 Tubing Cut and Perforation | SANTOS LIMITED | Tirrawarra 16 | Wild Desert Rig 6 | J.21.108648 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-26 06:00 | 2021-07-25 06:00 | 2021-07-25 | 2021-07-25 06:00 | 2021-07-26 23:59 | 2021-07-28 | 2021-07-27 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 11:26 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.13 | Tirrawarra 61 Tubing Cut | SANTOS LIMITED | Tirrawarra 61 | Wild Desert Rig 6 | J.21.108633 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-06-14 06:00 | 2021-06-12 06:00 | 2021-06-14 | 2021-06-14 07:00 | 2021-06-15 23:59 | 2021-06-16 | 2021-06-15 22:59 | Moomba WL | ymoradi2 | 2022-10-03 11:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  |  |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Owen Bass | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.11 | Sturt 5-Perfo 3 3/8" HSD | SANTOS LIMITED | Sturt 5 | Wild Desert Rig 6 | J.20.062897 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-10-26 07:00 | 2020-10-24 06:00 |  | 2020-10-26 07:00 | 2020-10-27 23:59 |  | 2020-10-27 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:54 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.06 | Merrimelia 60 | SANTOS LIMITED | Merrimelia 60 | Wild Desert Rig 6 | J.19.060524 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2019-11-22 13:00 | 2019-11-22 06:30 |  | 2019-11-22 13:00 | 2019-11-23 10:00 |  | 2019-11-23 10:00 | Moomba WL | DParker16 | 2022-10-03 10:54 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 17171.59 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.02 | Tennaperra 7 Perforation | SANTOS LIMITED | TENNAPERRA 7 | Wild Desert Rig 6 | J.19.060523 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Design Completed | In Progress | 2019-10-11 19:22 | 2019-10-11 07:00 |  | 2019-10-11 07:00 | 2019-10-13 23:00 |  | 2019-10-13 23:00 | Moomba WL | ymoradi2 | 2022-10-03 10:54 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 58.3 | 16.7 | 0 | 25 | 30 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.07 | Plug Setting and Perforation Merrimelia 49 | SANTOS LIMITED | Merrimelia 49 | Wild Desert Rig 6 | J.20.062892 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-01-29 08:00 | 2020-01-10 10:00 |  | 2020-01-29 15:00 | 2020-01-31 16:00 |  | 2020-01-31 16:00 | Moomba WL | ASetya | 2022-10-03 10:54 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.05 | Merrimelia 53 | SANTOS LIMITED | Merrimelia 53 | Wild Desert Rig 6 | J.19.060522 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2019-11-18 15:00 | 2019-11-18 09:00 |  | 2019-11-18 15:00 | 2019-11-19 10:00 |  | 2019-11-19 10:00 | Moomba WL | DParker16 | 2022-10-03 10:54 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 12352.96 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.10 | Mckinlay 1 | SANTOS LIMITED | Mckinlay 1 | Wild Desert Rig 6 | J.20.062888 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-10-03 06:00 | 2020-10-02 04:47 |  | 2020-10-03 06:00 | 2020-10-05 13:00 |  | 2020-10-05 13:00 | Moomba WL | DParker16 | 2022-10-03 10:53 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.09 | Tubing Cutter_2-3/8 in_Hackett 1 | SANTOS LIMITED | Hackett 1 | Wild Desert Rig 6 | J.20.062884 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-03-27 13:00 | 2020-03-21 10:00 |  | 2020-03-27 13:00 | 2020-03-31 18:00 |  | 2020-03-31 18:00 | Moomba WL | ASteinbach2 | 2022-10-03 10:53 | FDPSystemUser |  | No |  |  |  |  | Shannon Gilbert |  | 26744.64 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.12 | Alwyn 8 | SANTOS LIMITED | Alwyn 8 | Wild Desert Rig 6 | J.20.062881 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-23 | 2020-11-20 13:23 |  | 2020-12-23 | 2020-12-24 |  | 2020-12-24 | Moomba WL | DParker16 | 2022-10-03 10:53 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 8585.77 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.03 | Tennaperra 9 Perforations | SANTOS LIMITED | TENNAPERRA 9 (APP G) OIL DCFA | Wild Desert Rig 6 | J.19.060520 | RPI | PS-WL-NO | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2019-10-14 15:00 | 2019-10-14 14:00 |  | 2019-10-14 15:00 | 2019-10-15 09:00 |  | 2019-10-15 09:00 | Moomba WL | ymoradi2 | 2022-10-03 10:52 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.08 | Tubing Cutter 2-3/8" | SANTOS LIMITED |  | Wild Desert Rig 6 | J.20.062875 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2020-03-23 13:00 | 2020-03-23 10:00 |  | 2020-03-23 13:00 | 2020-03-24 18:00 |  | 2020-03-24 18:00 | Moomba WL | eismail | 2022-10-03 10:52 | FDPSystemUser |  | No |  |  |  |  | Shannon Gilbert |  | 0 |  |  | L0 - No RO |  | 33.3 | 16.7 | 0 | 0 | 15 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.04 | Watkins-1_HSD | SANTOS LIMITED | Watkins 1 | Wild Desert Rig 6 | J.19.060519 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2019-10-18 06:00 | 2019-10-17 16:00 |  | 2019-10-18 06:00 | 2019-10-18 13:00 |  | 2019-10-18 13:00 | Moomba WL | ymoradi2 | 2022-10-03 10:52 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001906 | O.1001906.02 | A.1001906.02.01 | Tennaperra-6_3-3/8-HSD | SANTOS LIMITED | Tennaperra 6 | Wild Desert Rig 6 |  | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2019-10-08 14:00 |  | 2019-10-08 18:00 | 2019-10-10 |  |  | Moomba WL | ymoradi2 | 2020-11-13 10:25 | JColeman |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001906 | O.1001906.01 | A.1001906.01.21 | Gidgealpa 69 | SANTOS LIMITED | GIDGEALPA 69 | Wild Desert Rig 6 | J.24.070255 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2024-03-12 08:00 | 2024-03-10 |  | 2024-03-12 08:00 | 2024-03-30 07:59 |  | 2024-03-30 07:59 | Moomba WL | FShallal | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 5 |  | L0 - No RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001906 | O.1001906.01 | A.1001906.01.20 | Della 8- Tubing Cut | SANTOS LIMITED | Della 8 | Wild Desert Rig 6 | J.22.110091 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-08-31 17:00 | 2022-08-31 |  | 2022-08-31 17:00 | 2022-09-02 07:59 |  | 2022-09-02 07:59 | Moomba WL | ymoradi2 | 2022-10-03 12:39 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 25268.91 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001906 | O.1001906.01 | A.1001906.01.19 | Bugito 1- Perf | SANTOS LIMITED | Bugito 1 | Wild Desert Rig 6 | J.22.109786 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-03 17:00 | 2022-04-02 07:00 |  | 2022-04-03 17:00 | 2022-04-05 07:59 |  | 2022-04-05 07:59 | Moomba WL | DKitney | 2022-10-03 12:09 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 25268.91 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001906 | O.1001906.01 | A.1001906.01.18 | Kanowana 7- Perf/Packer | SANTOS LIMITED | Kanowana 7 | Wild Desert Rig 6 | J.22.109618 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-09 10:00 | 2022-01-09 09:00 |  | 2022-01-09 10:00 | 2022-01-12 12:00 |  | 2022-01-12 12:00 | Moomba WL | DKitney | 2022-10-03 11:54 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 39980.21 | 10 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.01 | A.1001906.01.17 | Moorari 6 | SANTOS LIMITED | Moorari 5 | Wild Desert Rig 6 | J.21.108812 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-27 12:00 | 2021-12-26 07:00 |  | 2021-12-27 12:00 | 2021-12-28 00:01 |  | 2021-12-28 00:01 | Moomba WL | KKeese | 2022-10-03 11:53 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.01 | A.1001906.01.16 | Rakoona 1 SCMT | SANTOS LIMITED | RAKOONA 1 | Wild Desert Rig 6 | J.21.108763 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2021-10-19 | 2021-10-18 | 2021-10-18 | 2021-10-19 | 2021-10-20 23:59 | 2021-10-22 11:00 | 2021-10-20 23:59 | Moomba WL | YLee25 | 2022-10-03 11:39 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | 1 |  | L1 - Support RO |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.01 | A.1001906.01.15 | Rakoona 1- Tubing Cutter | SANTOS LIMITED | RAKOONA 1 | Wild Desert Rig 6 | J.21.108762 | RPI | PS-WL-NO | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-10-16 12:00 | 2021-10-15 07:00 | 2021-10-16 | 2021-10-16 12:00 | 2021-10-17 00:01 | 2021-10-18 | 2021-10-17 00:01 | Moomba WL | DKitney | 2022-10-03 11:39 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 91.7 | 50 | 100 | 75 | 75 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.01 | A.1001906.01.14 | Big Lake 30 | SANTOS LIMITED | Big Lake 30 | Wild Desert Rig 6 | J.21.108544 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-18 06:00 | 2021-05-17 12:00 | 2021-05-18 | 2021-05-18 06:00 | 2021-05-20 18:00 | 2021-05-21 | 2021-05-20 18:00 | Moomba WL | KKeese | 2022-10-03 11:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 4 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.01 | A.1001906.01.13 | Tarwonga 7 | SANTOS LIMITED | Tarwonga 7 | Wild Desert Rig 6 | J.21.108539 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-05-08 06:00 | 2021-05-07 12:00 | 2021-05-08 | 2021-05-08 06:00 | 2021-05-10 18:00 | 2021-05-11 | 2021-05-09 | Moomba WL | DKitney | 2022-10-03 11:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.01 | A.1001906.01.12 | Moomba 48 - ; Cut Tubing- SCMT | SANTOS LIMITED | Moomba 48 | Wild Desert Rig 6 | J.21.108529 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-04-08 | 2021-04-07 | 2021-04-07 23:00 | 2021-04-08 | 2021-04-10 23:59 | 2021-04-11 | 2021-04-10 23:59 | Moomba WL | ymoradi2 | 2022-10-03 11:14 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.01 | A.1001906.01.11 | Sturt 5 | SANTOS LIMITED | Mckinlay 1 | Wild Desert Rig 6 | J.20.062896 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-10-20 | 2020-10-19 |  | 2020-10-20 | 2020-10-22 23:59 |  | 2020-10-22 23:59 | Moomba WL | KKeese | 2022-10-03 10:54 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.01 | A.1001906.01.07 | Narcoonowie 2-4.5" HSD | SANTOS LIMITED | Narcoonowie 2 | Wild Desert Rig 6 | J.20.062894 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-07-04 | 2020-07-03 |  | 2020-07-04 | 2020-07-05 23:59 |  | 2020-07-05 23:59 | Moomba WL | KKeese | 2022-10-03 10:54 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.01 | A.1001906.01.06 | Narcoonowie 2- SCMT/CPST/HSD | SANTOS LIMITED | Narcoonowie 2 | Wild Desert Rig 6 | J.20.062889 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-06-06 | 2020-06-05 |  | 2020-06-06 | 2020-06-10 23:59 |  | 2020-06-10 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:53 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.01 | A.1001906.01.08 | Big Lake 67 | SANTOS LIMITED | Big Lake 67 | Wild Desert Rig 6 | J.20.062887 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress | 2020-08-09 06:00 | 2020-07-31 14:30 |  | 2020-08-09 06:00 | 2020-08-14 05:59 |  | 2020-08-14 05:59 | Moomba WL | DKitney | 2022-10-03 10:53 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001906 | O.1001906.01 | A.1001906.01.05 | Narcoonowie 2-Tubing Cutter | SANTOS LIMITED | Narcoonowie 2 | Wild Desert Rig 6 | J.20.062886 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-06-03 06:00 | 2020-05-31 14:30 |  | 2020-06-03 06:00 | 2020-06-08 05:59 |  | 2020-06-08 05:59 | Moomba WL | ymoradi2 | 2022-10-03 10:53 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.01 | A.1001906.01.09 | Big Lake 35 | SANTOS LIMITED | Big Lake 35 | Wild Desert Rig 6 | J.20.062883 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-08-20 | 2020-08-18 |  | 2020-08-20 | 2020-08-21 23:59 |  | 2020-08-21 23:59 | Moomba WL | KKeese | 2022-10-03 10:53 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.01 | A.1001906.01.01 | Dullingari 22 | SANTOS LIMITED | DULLINGARI NORTH 022 | Wild Desert Rig 6 | J.19.060521 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Design Completed | In Progress | 2019-09-30 | 2019-09-30 |  | 2019-09-30 | 2019-10-02 |  | 2019-10-02 | Moomba WL | KKeese | 2022-10-03 10:52 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001906 | O.1001906.01 | A.1001906.01.02 | Charo 10 | SANTOS LIMITED | Charo 10 | Wild Desert Rig 6 | J.20.062878 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-08-23 13:00 | 2020-03-14 |  | 2020-08-23 12:00 | 2020-08-25 12:00 |  | 2020-08-25 13:00 | Moomba WL | SGilbert | 2022-10-03 10:52 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 16205.69 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.01 | A.1001906.01.10 | Mckinlay 1 | SANTOS LIMITED | Mckinlay 1 | Wild Desert Rig 6 | J.20.062877 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-10-10 | 2020-10-09 |  | 2020-10-10 | 2020-10-12 23:59 |  | 2020-10-12 23:59 | Moomba WL | KKeese | 2022-10-03 10:52 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.01 | A.1001906.01.04 | Narcoonowie 4- Perfo 4.5" HSD | SANTOS LIMITED | NARCOONOWIE 4 | Wild Desert Rig 6 | J.20.062876 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-05-29 08:00 | 2020-05-29 |  | 2020-05-29 08:00 | 2020-05-31 23:59 |  | 2020-05-31 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:52 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001906 | O.1001906.01 | A.1001906.01.03 | Narcoonowie 4-Tubing Cut+Perfo | SANTOS LIMITED | NARCOONOWIE 4 | Wild Desert Rig 6 | J.20.062874 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-06-28 | 2020-05-25 |  | 2020-06-28 | 2020-07-01 14:59 |  | 2020-07-01 14:59 | Moomba WL | ymoradi2 | 2022-10-03 10:52 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001858 | O.1001858.01 | A.1001858.01.01 | CVX_TCP_GOR-1G | CHEVRON APG ABU PERTH. | GOR-1G | GSF Development Driller I | J.19.060364 | RPI | TCP-TEMP-JOB | InComplete | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2019-10-03 |  | 2019-10-03 | 2019-11-26 08:48 |  |  | APG TS | LSimaremare | 2024-11-19 20:07 | FDPSystemUser |  | No |  |  |  |  | Yudha Swara |  | 1959124 |  |  |  |  | 58.3 | 16.7 | 0 | 50 | 37.5 |  | 0 | [7 empty] | Gabriela Soter Roxo Teckemeier | TCP-Tubing-Conveyed Perforation
P.1001823 | O.1001823.01 | A.1001823.01.03 | Moomba 253- HT | SANTOS LIMITED | Moomba 253 | ENSIGN 970 | J.20.062873 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-04-02 20:00 | 2020-03-31 18:00 |  | 2020-04-02 23:00 | 2020-04-06 22:00 |  | 2020-04-06 19:00 | Moomba WL | OBass | 2022-10-03 10:51 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001823 | O.1001823.01 | A.1001823.01.02 | Moomba 251_QUADCOMBO | SANTOS LIMITED | Moomba 251 | ENSIGN 970 |  | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-21 18:00 |  | 2020-01-18 18:00 | 2020-01-19 07:00 |  |  | Moomba WL | ASteinbach2 | 2020-11-13 10:25 | JColeman |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001823 | O.1001823.01 | A.1001823.01.01 | ES Logging | SANTOS LIMITED | Cascade (WC A) | ENSIGN 970 |  | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2019-09-29 |  | 2019-09-29 12:00 | 2019-10-02 |  |  | Moomba WL | DSuitella | 2020-11-13 10:25 | JColeman |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001781 | O.1001781.03 | A.1001781.03.01 | 7in CH Section | BEACH ENERGY LTD | DOMBEY 001 | ENSIGN 931 | J.19.060516 | RPE | ES-CH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2019-10-24 20:00 | 2019-10-24 |  | 2019-10-26 20:00 | 2019-11-02 20:00 |  | 2019-12-02 20:00 | Moomba WL | DWatanabe | 2022-10-03 10:51 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 11695.91 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001781 | O.1001781.02 | A.1001781.02.01 | 8.5" OH TD Section | BEACH ENERGY LTD | Dombey-1 | ENSIGN 931 | J.19.060518 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2019-10-15 | 2019-10-12 |  | 2019-10-15 | 2019-10-27 |  | 2019-10-27 | Moomba WL | BAhmad | 2022-10-03 10:51 | FDPSystemUser |  | No |  |  |  |  | Bilal Ahmad |  | 42235.22 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001781 | O.1001781.01 | A.1001781.01.01 | 8.5" OH Logging | BEACH ENERGY LTD | DOMBEY 001 | ENSIGN 931 | J.19.060517 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-12 11:24 | 2019-09-23 |  | 2019-10-14 | 2019-10-17 23:00 |  | 2019-10-24 23:00 | Moomba WL | BAhmad | 2022-10-03 10:51 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Daigoro Watanabe |  | 0 |  |  | L1 - Support RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001744 | O.1001744.01 | A.1001744.01.04 | WAP repeat Operation for Feb, 20 | ORIGIN ENERGY RESOURCES LIMITED | Reedy Creek 115, Reedy Creek 146, Reedy Creek 174, Reedy Creek 143, Reedy Creek 145, Reedy Creek 172, Reedy Creek 173, Reedy Creek 203, Reedy Creek 171, Reedy Creek 201, Reedy Creek 170 | Rigless Australia - 1 | J.20.063353 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-02-03 |  | 2020-02-03 23:00 | 2020-02-23 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:51 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001744 | O.1001744.01 | A.1001744.01.03 | Origin Rigless WAP_JAN | ORIGIN ENERGY RESOURCES LIMITED | Reedy Creek 115, Reedy Creek 146, Reedy Creek 174, Reedy Creek 143, Reedy Creek 145, Reedy Creek 172, Reedy Creek 173, Reedy Creek 203, Reedy Creek 171, Reedy Creek 201, Reedy Creek 170 | Rigless Australia - 1 | J.20.063352 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-01-12 |  | 2020-01-12 23:00 | 2020-02-01 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:51 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 14067.58 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001744 | O.1001744.01 | A.1001744.01.01 | Origin Rigless WAP_OCT | ORIGIN ENERGY RESOURCES LIMITED | CONDABRI 266, CONDABRI 268, CONDABRI 296, CONDABRI 292 | Rigless Australia - 1 | J.19.060670 | RPI | PS-WL-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-18 | 2019-10-14 |  | 2019-10-18 | 2019-11-06 23:00 |  | 2019-11-06 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:51 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Anouk Suminar | WL Production Services
P.1001744 | O.1001744.01 | A.1001744.01.02 | Origin Rigless WAP_NOV | ORIGIN ENERGY RESOURCES LIMITED |  | Rigless Australia - 1 | J.19.060665 | RPI | PS-WL-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-18 | 2019-11-13 23:00 |  | 2019-11-17 23:00 | 2019-12-07 23:00 |  | 2019-11-06 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:51 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Anouk Suminar | WL Production Services
P.1001744 | O.1001744.01 | A.1001744.01.06 | WAP April,20 | ORIGIN ENERGY RESOURCES LIMITED | Reedy Creek 115, Reedy Creek 146, Reedy Creek 174, Reedy Creek 143, Reedy Creek 145, Reedy Creek 172, Reedy Creek 173, Reedy Creek 203, Reedy Creek 171, Reedy Creek 201, Reedy Creek 170 | Rigless Australia - 1 | J.20.063351 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-04-03 |  | 2020-04-03 23:00 | 2020-04-23 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:51 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001744 | O.1001744.01 | A.1001744.01.05 | WAP Perfo in March,20 | ORIGIN ENERGY RESOURCES LIMITED | Reedy Creek 115, Reedy Creek 146, Reedy Creek 174, Reedy Creek 143, Reedy Creek 145, Reedy Creek 172, Reedy Creek 173, Reedy Creek 203, Reedy Creek 171, Reedy Creek 201, Reedy Creek 170 | Rigless Australia - 1 | J.20.063350 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-02-29 |  | 2020-02-29 23:00 | 2020-03-20 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:51 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001742 | O.1001742.01 | A.1001742.01.04 | Peat 45 | ORIGIN ENERGY RESOURCES LIMITED | Peat 45 | Rigless Australia - 1 | J.19.060669 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-08 |  | 2019-12-08 04:00 | 2019-12-09 12:00 |  |  | Roma WL | JEsmeralda | 2022-10-03 13:51 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 7862.25 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001742 | O.1001742.01 | A.1001742.01.02 | Origin Rigless CBL_NOV | ORIGIN ENERGY RESOURCES LIMITED |  | Rigless Australia - 1 | J.19.060668 | RPI | PS-WL-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-11-13 23:00 | 2019-11-09 23:00 |  | 2019-11-13 23:00 | 2019-12-03 23:00 |  | 2019-12-03 22:00 | Roma WL | VOliveira5 | 2022-10-03 13:51 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Production Services
P.1001742 | O.1001742.01 | A.1001742.01.05 | CBL-IBC | ORIGIN ENERGY RESOURCES LIMITED | Condabri North Deep 27 | Rigless Australia - 1 | J.19.060667 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-19 10:00 |  | 2019-12-21 06:00 | 2019-12-24 18:00 |  |  | Roma WL | JAnderson60 | 2022-10-03 13:51 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 83800.91 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001742 | O.1001742.01 | A.1001742.01.03 | Origin Rigless CBL_DEC | ORIGIN ENERGY RESOURCES LIMITED | REEDY CREEK 115, REEDY CREEK 145, REEDY CREEK 174, REEDY CREEK 231, REEDY CREEK 261, REEDY CREEK 262, CONDABRI 178, CONDABRI SOUTH 167, LUCKY GULLY 22, LUCKY GULLY 280, REEDY CREEK 258, REEDY CREEK 227, REEDY CREEK 194, REEDY CREEK 193, REEDY CREEK 226, LUCKY GULLY 47, LUCKY GULLY 32, LUCKY GULLY 17, LUCKY GULLY 18, LUCKY GULLY 16 | Rigless Australia - 1 | J.19.060666 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2019-11-17 20:00 | 2019-12-09 23:00 |  | 2019-12-17 20:00 | 2020-01-02 20:00 |  | 2020-01-06 19:00 | Roma WL | VOliveira5 | 2022-10-03 13:51 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 8382.06 |  |  |  |  | 41.7 | 0 | 0 | 25 | 20 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001742 | O.1001742.01 | A.1001742.01.01 | Origin Rigless CBL_Vinh | ORIGIN ENERGY RESOURCES LIMITED | REEDY CREEK 138, REEDY CREEK 94, REEDY CREEK 22, REEDY CREEK 46, REEDY CREEK 66INJ-P, REEDY CREEK 11, REEDY CREEK 52, REEDY CREEK 12, REEDY CREEK 86, REEDY CREEK 32, REEDY CREEK 104, REEDY CREEK 134 | Rigless Australia - 1 | J.19.060664 | RPI | PS-WL-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-14 | 2019-10-10 |  | 2019-10-14 | 2019-11-02 23:00 |  | 2019-11-02 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:50 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 7862.25 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.07 | A.1001734.07.04 | Rigless SCMT_RM13-27-1 | SANTOS LIMITED | RM13-27-1 | Rigless Australia - 1 | J.23.115411 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-25 10:00 | 2023-07-24 10:00 | 2023-07-24 23:00 | 2023-07-25 10:00 | 2023-07-29 23:59 | 2023-07-29 23:00 | 2023-07-29 23:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 10337.23 | 5 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001734 | O.1001734.07 | A.1001734.07.05 | Rigless_FV06-55-1 | SANTOS LIMITED | RM13-27-1, FV06-55-1 | Rigless Australia - 1 | J.23.130612 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-08-28 10:00 | 2023-08-27 10:00 | 2023-08-27 23:00 | 2023-08-28 10:00 | 2023-09-01 23:59 | 2023-09-01 23:00 | 2023-09-01 23:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 10337.23 | 5 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001734 | O.1001734.07 | A.1001734.07.06 | Rigless CH CSG_Dedicated Oct23 | SANTOS LIMITED | RM13-27-1, FV06-55-1 | Rigless Australia - 1 | J.23.139522 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-25 10:00 | 2023-09-24 10:00 | 2023-09-24 23:00 | 2023-09-25 10:00 | 2023-09-29 23:59 | 2023-09-29 23:00 | 2023-09-29 23:59 | Roma WL | JEsmeralda | 2023-10-16 14:06 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 5 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001734 | O.1001734.07 | A.1001734.07.02 | Rigless Perforation | SANTOS LIMITED | FV11-70 21, FV13-29 1, FV12-42 1 | Rigless Australia - 1 | J.23.028765 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-01-21 10:00 | 2023-01-20 10:00 |  | 2023-01-21 10:00 | 2023-01-25 23:59 |  | 2023-01-25 23:59 | Roma WL | MRony2 | 2023-05-27 15:31 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 12709.55 | 4 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.07 | A.1001734.07.03 | Rigless_PMIT-SCMT | SANTOS LIMITED | RM09-82-1 | Rigless Australia - 1 | J.23.068076 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-06 10:00 | 2023-04-05 10:00 |  | 2023-04-06 10:00 | 2023-04-10 23:59 |  | 2023-04-10 23:59 | Roma WL | SAli63 | 2023-04-15 03:26 | handoko |  | No |  |  |  |  | Jon Lawrie |  | 10337.23 | 4 |  | L0 - No RO |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.07 | A.1001734.07.01 | Plug | SANTOS LIMITED | DALDOWIE 20, NORTH SCOTIA 5, NORTH SCOTIA 6 | Rigless Australia - 1 | J.22.126051 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-16 06:00 | 2022-11-15 10:00 |  | 2022-11-16 06:00 | 2022-11-18 23:59 |  | 2022-11-18 23:59 | Roma WL | MRony2 | 2023-03-01 20:06 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  |  |  | 75 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.06 | A.1001734.06.02 | SCMT and Perf | SANTOS LIMITED | RM42-07-1, RM42-11-1, FV12-116-1 | Rigless Australia - 1 | J.22.110384 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2022-07-13 15:00 |  | 2022-07-14 08:00 | 2022-07-19 23:59 |  |  | Roma WL | PLima7 | 2022-10-19 13:15 | MRony2 |  | No |  |  |  |  | Jon Lawrie |  | 25779.73 | 3 |  |  |  | 66.7 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.06 | A.1001734.06.01 | SLDTJune | SANTOS LIMITED | Daldowie 13, Daldowie 14, Daldowie 15, Daldowie 16, North Scotia 2, North Scotia 4, Collingwood 24, North Scotia 6, North Scotia 3, Collingwood 22, Collingwood 23, FV12-116-1 | Rigless Australia - 1 | J.22.110341 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-06-11 23:00 |  | 2022-06-12 12:00 | 2022-06-22 11:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:16 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 4467.19 | 12 |  |  |  | 50 | 50 | 0 | 75 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.05 | A.1001734.05.01 | Pre Foam-X PNX | SANTOS LIMITED | RM15-87-1 | Rigless Australia - 1 | J.22.110308 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-04-02 |  | 2022-04-02 | 2022-04-06 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 11046.13 | 2 |  |  |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.04 | A.1001734.04.02 | SLDT | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.110889 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-04-29 23:00 | 2022-04-28 23:00 |  | 2022-04-29 23:00 | 2022-05-09 22:59 |  | 2022-05-09 22:59 | Roma WL | MRony2 | 2022-10-03 14:59 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 8 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.04 | A.1001734.04.05 | SLDT April | SANTOS LIMITED | Daldowie 17, Daldowie 18, Daldowie 19, Glen Evis 8, Daldowie 16 | Rigless Australia - 1 | J.22.110323 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-04-07 23:00 |  | 2022-04-07 23:00 | 2022-04-17 22:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 4873.29 | 8 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.04 | A.1001734.04.04 | SCMT | SANTOS LIMITED | FV12-38-2 | Rigless Australia - 1 | J.22.110301 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-01-14 06:00 |  | 2022-01-15 06:00 | 2022-01-16 18:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 4132.55 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.04 | A.1001734.04.03 | SLDT March | SANTOS LIMITED | Cattle Creek 10, Cattle Creek 8, FV08-02 2, FV08-03 1, FV08-05 1, FV08-06 1, GLEN EVIS 6, Glen Evis 4, Glen Evis 7, Glen Evis 3, Glen Evis 5, Glen Evis 2 | Rigless Australia - 1 | J.22.110293 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-03-04 23:00 |  | 2022-03-05 23:00 | 2022-03-15 22:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 4873.29 | 12 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.04 | A.1001734.04.01 | SLDT December Campaign | SANTOS LIMITED | FV13-74-1, FV13-79-1, FV13-84-1, FV13-93-1, FV13-82-1, FV13-82-2, FV13-76-1, FV13-76-2, FV12-38-2, FV12-39-2 | Rigless Australia - 1 | J.21.109077 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2021-12-06 23:00 | 2021-12-05 23:00 |  | 2021-12-06 23:00 | 2022-01-06 22:59 |  | 2022-01-06 22:59 | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 12579.59 | 12 |  | L3 - Full RO |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.03 | A.1001734.03.05 | SLDT-SCMT | SANTOS LIMITED | Kelsall 24, Kelsall 25, KELSALL 26, FV13-90-1, FV13-90-2, FV12-118-1, FV17-63-1, FV17-64-1, FV13-92-1, FV18-01-3, the Rock 22 | Rigless Australia - 1 | J.21.109427 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-09-19 11:00 | 2021-09-19 |  | 2021-09-19 10:00 | 2021-09-30 23:59 |  | 2021-10-01 00:59 | Roma WL | MRony2 | 2022-10-03 14:59 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 7056.53 | 4 |  |  |  | 58.3 | 50 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.03 | A.1001734.03.02 | SLDT | SANTOS LIMITED | FV07-37-1, FV12-104-1, FV12-90-2 | Rigless Australia - 1 | J.21.109426 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-05-16 06:00 | 2021-05-15 12:00 |  | 2021-05-16 06:00 | 2021-05-20 19:59 |  | 2021-05-20 19:59 | Roma WL | MRony2 | 2022-10-03 14:59 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 3573.75 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.03 | A.1001734.03.09 | SCMT-EMIT | SANTOS LIMITED | Lowesby 1 | Rigless Australia - 1 | J.22.110298 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-01-25 |  | 2022-01-25 16:00 | 2022-01-29 15:59 |  |  | Roma WL | ysaeedabadian | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 21221.57 | 2 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.03 | A.1001734.03.08 | SLDT Sep2 | SANTOS LIMITED | Kelsall 21, Kelsall 22, AVALON 24, AVALON 28, KELSALL 23, AVALON 19 | Rigless Australia - 1 | J.21.109072 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-09-18 |  | 2021-09-19 10:00 | 2021-09-23 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 2 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.03 | A.1001734.03.07 | SLDT Dec | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.110268 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-04-21 01:00 |  | 2022-04-21 11:00 | 2022-04-29 00:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 8 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.03 | A.1001734.03.03 | SLDT | SANTOS LIMITED | Sunshine Ranch 2, VINCENT DOWNS 1 | Rigless Australia - 1 | J.21.108993 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-06-06 |  | 2021-06-06 10:00 | 2021-06-11 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 7706.3 | 4 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.03 | A.1001734.03.01 | SLDT Mar-2021 | SANTOS LIMITED | FV17-54-1, FV18-70-1, FV18-69-1, FV18-72-1, FV18-40-1 | Rigless Australia - 1 | J.21.108991 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-03-25 |  | 2021-03-25 10:00 | 2021-03-31 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 3573.75 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.03 | A.1001734.03.06 | SLDT_Nov2021 | SANTOS LIMITED | FV13-75-1, FV13-94-1, FV13-81-1, FV13-91-1, FV13-74-1, FV13-85-1, FV18-78-1, FV13-78-1, FV13-93-1, FV18-83-1 | Rigless Australia - 1 | J.21.108990 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-11-03 01:00 |  | 2021-11-03 11:00 | 2021-11-10 00:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 7706.3 | 8 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.03 | A.1001734.03.04 | SLDT Rigless_Sep 2021 | SANTOS LIMITED | Kelsall 21, Kelsall 22, AVALON 24, AVALON 28, KELSALL 23, AVALON 19 | Rigless Australia - 1 | J.21.108987 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-09-08 |  | 2021-09-09 10:00 | 2021-09-13 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:11 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 7706.3 | 2 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.02 | A.1001734.02.11 | SLDT February | SANTOS LIMITED | Mount Kingsley 37, Mount Kingsley 44, Mount Kingsley 38 | Rigless Australia - 1 | J.21.108926 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-02-13 |  | 2021-02-13 10:00 | 2021-02-18 10:59 |  |  | Roma WL | SClark17 | 2022-10-03 13:50 | FDPSystemUser |  | No |  |  |  |  | Samuel Clark |  | 9148.8 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.02 | A.1001734.02.02 | SLDT_June20 | SANTOS LIMITED | FV18-75-1, FV18-74-1, FV18-46-1, FV18-32-1, FV18-33-1, FV18-65-1, FV13-30-1 | Rigless Australia - 1 | J.20.063349 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-07 06:00 |  | 2020-06-07 12:00 | 2020-06-15 11:59 |  |  | Roma WL | ZWahid | 2022-10-03 13:50 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 3573.75 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.02 | A.1001734.02.01 | SLDT_rigless | SANTOS LIMITED | FV18-36-1, FV18-46-1, FV18-43-1, FV18-54-1, FV18-63-1, FV18-73-1, FV18-74-1, FV18-75-1, FV18-76-1 | Rigless Australia - 1 | J.20.063348 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-25 |  | 2020-05-26 | 2020-06-02 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:50 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 3573.75 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.02 | A.1001734.02.03 | SLDT_Oct20 | SANTOS LIMITED | FV18-75 1, FV18-74 1, FV18-46 1, FV18-32 1, FV18-33 1, FV18-65 1, FV13-30 1, THE ROCK 14, THE ROCK 15, THE ROCK 12 | Rigless Australia - 1 | J.20.063340 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2020-03-23 04:00 | 2020-10-02 06:00 |  | 2020-10-03 12:00 | 2020-10-14 12:59 |  | 2020-10-14 12:59 | Roma WL | ZWahid | 2022-10-03 13:49 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 3573.75 |  |  | L0 - No RO |  | 58.3 | 50 | 0 | 75 | 55 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.02 | A.1001734.02.10 | SLDT-SCMT | SANTOS LIMITED | AVALON 27, AVALON 20 | Rigless Australia - 1 | J.21.108925 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2020-07-18 01:00 | 2021-01-28 |  | 2021-01-28 10:00 | 2021-02-02 10:59 |  | 2021-02-02 10:59 | Roma WL | MRony2 | 2022-10-03 13:49 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 8969.46 |  |  | L1 - Support RO |  | 58.3 | 50 | 0 | 75 | 55 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.02 | A.1001734.02.07 | SLDT_December | SANTOS LIMITED | AVALON 19, AVALON 25, AVALON 23, AVALON 26, AVALON 27 | Rigless Australia - 1 | J.20.063334 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2020-06-16 03:00 | 2020-12-27 08:00 |  | 2020-12-27 12:00 | 2021-01-01 12:59 |  | 2021-01-01 12:59 | Roma WL | PLima7 | 2022-10-03 13:48 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 3573.75 |  |  | L0 - No RO |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.02 | A.1001734.02.08 | SLDT Phase 2 | SANTOS LIMITED | AVALON 19, AVALON 25, AVALON 23, AVALON 26, AVALON 27 | Rigless Australia - 1 | J.21.108922 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-01-05 08:00 |  | 2021-01-05 12:00 | 2021-01-10 12:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:47 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 3573.75 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.02 | A.1001734.02.04 | SLDT_Nov | SANTOS LIMITED | FV18-75-1, FV18-74-1, FV18-46-1, FV18-32-1, FV18-33-1, FV18-65-1, FV13-30-1, The Rock 14, The Rock 15, The Rock 12, The Rock 13, The Rock 16 | Rigless Australia - 1 | J.20.063325 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-10-29 06:00 |  | 2020-10-30 12:00 | 2020-11-04 12:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:47 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 3573.75 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.02 | A.1001734.02.09 | SLDT _ SCMT | SANTOS LIMITED | Avalon 21, Avalon 22 | Rigless Australia - 1 | J.21.108921 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-01-11 20:00 |  | 2021-01-12 | 2021-01-17 00:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:47 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 3573.75 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.02 | A.1001734.02.06 | SCMT_WHE | SANTOS LIMITED | FV18-75-1, FV18-74-1, FV18-46-1, FV18-32-1, FV18-33-1, FV18-65-1, FV13-30-1, The Rock 14, The Rock 15, The Rock 12 | Rigless Australia - 1 | J.20.063313 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-12-03 06:00 |  | 2020-12-04 12:00 | 2020-12-09 12:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:46 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.02 | A.1001734.02.05 | SLDT Dec | SANTOS LIMITED | FV18-75-1, FV18-74-1, FV18-46-1, FV18-32-1, FV18-33-1, FV18-65-1, FV13-30-1, The Rock 14, The Rock 15, The Rock 12, THE ROCK 17, THE ROCK 19, THE ROCK 18, THE ROCK 20 | Rigless Australia - 1 | J.20.063312 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-12-08 06:00 |  | 2020-12-09 12:00 | 2020-12-14 12:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:46 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 3573.75 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.01 | A.1001734.01.06 | Santos Rigless SLDT - repeat ops | SANTOS LIMITED | AC23-21-4, AC23-44-1, AC23-45 1, AC23-46 1, AC23-49-1, AC23-55 1, AC23-54 1, AC23-61-1, AC23-35-1, AC23-36-1, AC23-37 1, AC23-57-1, AC23-52 1, AC23-59-1 | Rigless Australia - 1 | J.20.063346 | RPE | ES-CH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-01-13 |  | 2020-01-13 12:00 | 2020-01-24 12:00 |  |  | Roma WL | MEketone | 2022-10-03 13:50 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 2923.98 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001734 | O.1001734.01 | A.1001734.01.01 | Santos Rigless SLDT/CBL - OCT | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.063345 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-06 23:00 |  | 2020-03-04 23:00 | 2020-03-24 22:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:50 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Production Services
P.1001734 | O.1001734.01 | A.1001734.01.09 | SLDT/CBL in May | SANTOS LIMITED | RM50-111-1, Sunnyholt 49 | Rigless Australia - 1 | J.21.108924 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-05-28 17:00 |  | 2021-05-30 21:00 | 2021-06-04 21:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:48 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.01 | A.1001734.01.04 | SLDT | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.063330 | RPE | ES-CH-Ops | InComplete | Cancelled | Close - PSD |  | Not Required | Not Started | In Progress |  | 2020-03-05 23:00 |  | 2020-03-06 23:00 | 2020-03-09 23:00 |  |  | Roma WL | WMcconkey | 2022-10-03 13:48 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001734 | O.1001734.01 | A.1001734.01.08 | SLDT/CBL in June | SANTOS LIMITED | RM50-111-1, Sunnyholt 49 | Rigless Australia - 1 | J.21.108923 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-02-20 17:00 |  | 2021-02-22 21:00 | 2021-02-27 21:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:48 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.01 | A.1001734.01.07 | SLDT_May_MM | SANTOS LIMITED | FV18-54-1, FV18-73-1, FV18-63-1 | Rigless Australia - 1 | J.20.063328 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-25 01:00 |  | 2020-05-26 12:00 | 2020-06-03 12:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:48 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 3573.75 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.01 | A.1001734.01.02 | Santos Rigless SLDT/CBL | SANTOS LIMITED | RM50-111-1, Sunnyholt 49 | Rigless Australia - 1 | J.20.063324 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2020-02-13 14:00 |  | 2020-02-13 18:00 | 2020-02-18 18:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:47 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 4223.52 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001734 | O.1001734.01 | A.1001734.01.05 | CBL - Jan | SANTOS LIMITED | AC23-32 1, BUNGAWARRA 1, BUNGAWARRA 2, FV15-26 1, FV16-62 1 | Rigless Australia - 1 | J.20.063311 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2020-01-05 07:00 | 2020-01-05 07:00 |  | 2020-01-05 07:00 | 2020-01-10 15:00 |  | 2020-01-12 09:51 | Roma WL | JAnderson60 | 2022-10-03 13:46 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Julia Elizabeth Anderson |  | 4132.55 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001734 | O.1001734.01 | A.1001734.01.03 | Santos Rigless SLDT - April MM | SANTOS LIMITED | FV07-35 1, FV17-55-1, FV18-50-1, FV18-59-1A, FV18-35-1, FV18-34-1, FV18-36-1, FV18-32-1, FV18-33-1, FV18-53-1, FV18-68-1, FV18-68-2 | Rigless Australia - 1 | J.20.063310 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-26 06:00 |  | 2020-04-26 13:00 | 2020-05-04 13:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:46 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 11371.02 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.02 | A.1001731.02.01 | Roller mob | SANTOS LIMITED | FAIRVIEW 280 | SAVANNA DRILLING #67 | J.20.063344 | RPI | PS-WL-NO | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-05-20 |  | 2020-05-20 | 2020-05-24 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:50 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 1752.11 |  |  | L0 - No RO |  | 50 | 33.3 | 100 | 75 | 57.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.18 | Perfo_FV16-61-1 | SANTOS LIMITED | FV16-61 1 | SAVANNA DRILLING #67 | J.20.063347 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-02-21 |  | 2020-02-22 | 2020-02-25 |  |  | Roma WL | MRony2 | 2022-10-03 13:50 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 17283.95 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.10 | Perfo | SANTOS LIMITED | FV17-57-1 | SAVANNA DRILLING #67 | J.19.060663 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2019-12-27 08:00 |  | 2019-12-27 22:00 | 2019-12-29 22:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:50 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.41 | Perfo Fairview 183 | SANTOS LIMITED | Fairview 183 | SAVANNA DRILLING #67 | J.20.063343 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-10-20 20:00 |  | 2020-10-22 | 2020-10-24 12:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:50 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 25367.12 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.30 | Perfo | SANTOS LIMITED | FV12-103-1 | SAVANNA DRILLING #67 | J.20.063342 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress |  | 2020-08-10 09:00 |  | 2020-08-10 11:00 | 2020-08-12 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:50 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 17283.95 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.15 | Perfo_FV16-62-1 | SANTOS LIMITED | FV16-62 1 | SAVANNA DRILLING #67 | J.20.063341 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-01-26 16:00 |  | 2020-01-26 16:00 | 2020-01-30 16:00 |  |  | Roma WL | MMclean3 | 2022-10-03 13:49 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.33 | Perforation FV11-31-6 | SANTOS LIMITED | FV11-31-6 | SAVANNA DRILLING #67 | J.20.063339 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-09-06 20:00 |  | 2020-09-07 | 2020-09-11 12:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:49 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 17283.95 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.29 | Perfo-FV15-12-1 | SANTOS LIMITED | FV15-12-1 | SAVANNA DRILLING #67 | J.20.063338 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-04-20 07:00 |  | 2020-04-21 11:00 | 2020-04-23 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:49 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 21442.5 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.04 | Perfo | SANTOS LIMITED |  | SAVANNA DRILLING #67 | J.19.060662 | RPI | PS-WL-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2019-10-23 23:00 | 2019-11-13 22:00 |  | 2019-11-13 22:00 | 2019-11-17 22:00 |  | 2019-10-27 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:49 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 0 |  |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Anouk Suminar | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.22 | Perfo_FV16-66-1 | SANTOS LIMITED | FV16-66-1 | SAVANNA DRILLING #67 | J.20.063337 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-03-15 |  | 2020-03-15 06:00 | 2020-03-18 06:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:49 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 17283.95 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.14 | Perfo | SANTOS LIMITED | FV15-27 1 | SAVANNA DRILLING #67 | J.20.063336 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-01-09 |  | 2020-01-10 | 2020-01-15 |  |  | Roma WL | VCao2 | 2022-10-03 13:49 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.11 | Pefro | SANTOS LIMITED | FV17-56-1 | SAVANNA DRILLING #67 | J.20.063335 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-01-01 22:00 |  | 2020-01-02 22:00 | 2020-01-06 22:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:49 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.05 | Perfo | SANTOS LIMITED |  | SAVANNA DRILLING #67 | J.19.060661 | RPI | PS-WL-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2019-10-23 23:00 | 2019-11-20 22:00 |  | 2019-11-20 22:00 | 2019-11-24 22:00 |  | 2019-10-27 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:49 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 0 |  |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Anouk Suminar | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.03 | Perfo | SANTOS LIMITED |  | SAVANNA DRILLING #67 | J.19.060660 | RPI | PS-WL-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2019-10-23 23:00 | 2019-11-06 22:00 |  | 2019-11-06 22:00 | 2019-11-10 22:00 |  | 2019-10-27 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:49 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 0 |  |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Anouk Suminar | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.34 | USIT-CBL | SANTOS LIMITED | Fairview 63 | SAVANNA DRILLING #67 | J.20.063333 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-10-27 17:00 |  | 2020-10-28 10:00 | 2020-10-30 22:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:48 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 20246.91 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.31 | Perfo FV12-102-1 | SANTOS LIMITED | FV12-102-1 | SAVANNA DRILLING #67 | J.20.063332 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-08-19 10:00 |  | 2020-08-20 | 2020-08-22 19:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:48 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 23261.86 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.12 | Perfo | SANTOS LIMITED | FV16-17-1 | SAVANNA DRILLING #67 | J.20.063331 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-01-05 18:00 |  | 2020-01-06 06:00 | 2020-01-10 06:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:48 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 19363.22 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.06 | Perfo | SANTOS LIMITED |  | SAVANNA DRILLING #67 | J.19.060659 | RPI | PS-WL-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2019-10-23 23:00 | 2019-11-27 22:00 |  | 2019-11-27 22:00 | 2019-12-01 22:00 |  | 2019-10-27 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:48 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 0 |  |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Anouk Suminar | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.32 | Perfo | SANTOS LIMITED | FV12-101-1 | SAVANNA DRILLING #67 | J.20.063329 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress |  | 2020-08-30 07:00 |  | 2020-08-31 10:00 | 2020-09-02 18:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:48 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 17283.95 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.38 | Perfo FV12-74-1 | SANTOS LIMITED | FV12-74-1 | SAVANNA DRILLING #67 | J.20.063327 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-10-04 21:00 |  | 2020-10-05 01:00 | 2020-10-09 13:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:48 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 30799.22 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.24 | Perfo_FV182 | SANTOS LIMITED | FV 182 | SAVANNA DRILLING #67 | J.20.063326 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-03-24 08:00 |  | 2020-03-24 08:00 | 2020-03-29 08:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:48 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 17283.95 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.36 | Perfo FV18-45-1 | SANTOS LIMITED | FV18-45-1 | SAVANNA DRILLING #67 | J.20.063323 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-09-22 20:00 |  | 2020-09-23 | 2020-09-27 12:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:47 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 17283.95 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.35 | Perfo FV13-31-1 | SANTOS LIMITED | FV13-31-1 | SAVANNA DRILLING #67 | J.20.063322 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-09-16 12:00 |  | 2020-09-16 12:00 | 2020-09-20 |  |  | Roma WL | MRony2 | 2022-10-03 13:47 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 17283.95 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.07 | Perfo | SANTOS LIMITED |  | SAVANNA DRILLING #67 | J.19.060658 | RPI | PS-WL-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2019-10-23 23:00 | 2019-12-04 22:00 |  | 2019-12-04 22:00 | 2019-12-08 22:00 |  | 2019-10-27 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:47 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 0 |  |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Anouk Suminar | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.21 | Perfo_Sav_FV16-64-1 | SANTOS LIMITED | FV16641 | SAVANNA DRILLING #67 | J.20.063321 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-03-08 05:30 |  | 2020-03-10 18:30 | 2020-03-14 00:50 |  |  | Roma WL | MRony2 | 2022-10-03 13:47 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 17283.95 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.02 | Perfo | SANTOS LIMITED |  | SAVANNA DRILLING #67 | J.19.060657 | RPI | PS-WL-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2019-10-23 23:00 | 2019-10-30 22:00 |  | 2019-10-30 22:00 | 2019-11-03 22:00 |  | 2019-10-27 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:47 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 3248.86 |  |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 | [7 empty] | Anouk Suminar | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.27 | Perfo_FV15-30-1 | SANTOS LIMITED | FV15-30 1 | SAVANNA DRILLING #67 | J.20.063320 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-04-09 |  | 2020-04-11 06:00 | 2020-04-13 18:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:47 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 21247.56 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.25 | Perfo_Fv15-28-1 | SANTOS LIMITED | FV 15-28-1 | SAVANNA DRILLING #67 | J.20.063319 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-03-31 |  | 2020-04-01 14:00 | 2020-04-04 14:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:47 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 18400.91 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.16 | Perfo_FV15-26-1 | SANTOS LIMITED | FV15-26 1 | SAVANNA DRILLING #67 | J.20.063318 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-02-01 |  | 2020-02-02 06:00 | 2020-02-05 06:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:46 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 33554.26 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.13 | Perfo FV15-25-1 | SANTOS LIMITED | FV15-25 1 | SAVANNA DRILLING #67 | J.20.063317 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-01-17 17:00 |  | 2020-01-17 22:00 | 2020-01-21 22:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:46 | FDPSystemUser |  | No |  |  |  |  | Mari-Clair McLean |  | 34048.08 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.08 | Perfo | SANTOS LIMITED |  | SAVANNA DRILLING #67 | J.19.060656 | RPI | PS-WL-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2019-10-23 23:00 | 2019-12-11 22:00 |  | 2019-12-11 22:00 | 2019-12-15 22:00 |  | 2019-10-27 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:46 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 0 |  |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Anouk Suminar | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.37 | Perfo - FV11-101-1 | SANTOS LIMITED | FV11-101-1 | SAVANNA DRILLING #67 | J.20.063316 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-09-29 06:00 |  | 2020-09-29 06:00 | 2020-10-01 18:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:46 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 17283.95 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.26 | Perfo_FV15-31-1 | SANTOS LIMITED | FV15-31 1 | SAVANNA DRILLING #67 | J.20.063315 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-04-04 07:00 |  | 2020-04-05 11:00 | 2020-04-07 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:46 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 21247.56 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.17 | Perfo_FV209 | SANTOS LIMITED | Fairview 209 | SAVANNA DRILLING #67 | J.20.063314 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-02-16 08:00 |  | 2020-02-16 12:00 | 2020-02-19 |  |  | Roma WL | MRony2 | 2022-10-03 13:46 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 17283.95 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.01 | Perfo_FV07-33-1 | SANTOS LIMITED | FV07-33 1, FV12-73 1 | SAVANNA DRILLING #67 | J.19.060655 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Design Completed | In Progress | 2019-10-11 23:00 | 2019-10-11 23:00 |  | 2019-10-11 23:00 | 2019-10-15 23:00 |  | 2019-10-15 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:46 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 28687.46 |  |  | L0 - No RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 | [7 empty] | Anouk Suminar | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.19 | Perfo_Sav 67_FV16-68-1 | SANTOS LIMITED | FV16-68-1 | SAVANNA DRILLING #67 | J.20.063309 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-02-28 |  | 2020-02-29 | 2020-03-03 |  |  | Roma WL | MRony2 | 2022-10-03 13:45 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 17283.95 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.09 | Perfo | SANTOS LIMITED |  | SAVANNA DRILLING #67 | J.19.060654 | RPI | PS-WL-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2019-10-23 23:00 | 2019-12-18 22:00 |  | 2019-12-18 22:00 | 2019-12-22 22:00 |  | 2019-10-27 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:45 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 0 |  |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Anouk Suminar | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.40 | Perforation FV11-38-2 | SANTOS LIMITED | FV11-38 2 | SAVANNA DRILLING #67 | J.20.063308 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | In Progress | In Progress | 2020-06-26 22:00 | 2020-10-16 20:00 |  | 2020-10-17 | 2020-10-19 12:00 |  | 2020-10-24 23:00 | Roma WL | MRony2 | 2022-10-03 13:45 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 17283.95 |  |  | L0 - No RO |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.39 | Perfo FV06-26-7 | SANTOS LIMITED | FV06-26-7 | SAVANNA DRILLING #67 | J.20.063307 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-10-11 13:00 |  | 2020-10-11 17:00 | 2020-10-14 05:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:45 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 20013 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.28 | Perfo_FV280 | SANTOS LIMITED | Fairview 280 | SAVANNA DRILLING #67 | J.20.063306 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-04-14 07:00 |  | 2020-04-15 11:00 | 2020-04-17 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:45 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 71998.05 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.23 | Perfo_FV16-67-1 | SANTOS LIMITED | FV16-67 1 | SAVANNA DRILLING #67 | J.20.063305 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-03-20 08:00 |  | 2020-03-20 08:00 | 2020-03-23 08:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:45 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 24236.52 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001731 | O.1001731.01 | A.1001731.01.20 | Perfo | SANTOS LIMITED | FV16651 | SAVANNA DRILLING #67 | J.20.063304 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-03-05 |  | 2020-03-05 | 2020-03-08 |  |  | Roma WL | MRony2 | 2022-10-03 13:45 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 17283.95 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001705 | O.1001705.02 | A.1001705.02.01 | PumpDownPerf | ORIGIN ENERGY RESOURCES LIMITED |  | ENSIGN 963 | J.20.063301 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-01 |  | 2020-04-04 | 2020-04-19 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:44 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Production Services
P.1001705 | O.1001705.01 | A.1001705.01.02 | Velkerri 76 S2-1/-1H | ORIGIN ENERGY RESOURCES LIMITED |  | ENSIGN 963 | J.19.060650 | RPE | ES-OH-Ops | High | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-31 | 2019-12-07 |  | 2019-12-10 | 2019-12-19 |  | 2019-11-09 | Roma WL | VOliveira5 | 2022-10-03 13:44 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001705 | O.1001705.01 | A.1001705.01.03 | USIT-CBL | ORIGIN ENERGY RESOURCES LIMITED | KYALLA 117 N2-1 | ENSIGN 963 | J.19.060649 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-10 |  | 2019-12-14 | 2019-12-20 |  |  | Roma WL | ysaeedabadian | 2022-10-03 13:44 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001705 | O.1001705.01 | A.1001705.01.01 | Kyalla 117 N2-1/1H | ORIGIN ENERGY RESOURCES LIMITED | KYALLA 117 N2-1 | ENSIGN 963 | J.19.060648 | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-10-28 |  | 2019-10-31 | 2019-11-26 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:44 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 41910.33 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001703 | O.1001703.01 | A.1001703.01.01 | Myall Creek North 1 | ARMOUR ENERGY (SURAT BASIN) PTY LTD | MYALL CREEK NORTH 1 | Silver City 20 | J.19.060653 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2019-10-11 15:00 |  | 2019-10-11 17:00 | 2019-10-15 17:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:45 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 113287.85 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001703 | O.1001703.01 | A.1001703.01.04 | Armour - PNX 2 - MC4 | ARMOUR ENERGY (SURAT BASIN) PTY LTD | Myall Creek 4 | Silver City 20 | J.20.063302 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-20 12:00 |  | 2020-04-21 | 2020-04-23 |  |  | Roma WL | ZWahid | 2022-10-03 13:45 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 29239.77 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001703 | O.1001703.01 | A.1001703.01.02 | Horseshoe 4 | ARMOUR ENERGY (SURAT BASIN) PTY LTD | Horse Shoe 4 | Silver City 20 | J.19.060652 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-11-08 |  | 2019-11-08 12:00 | 2019-11-12 12:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:45 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 116536.71 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001703 | O.1001703.01 | A.1001703.01.03 | Armour - PNX 1 - MC4 | ARMOUR ENERGY (SURAT BASIN) PTY LTD | Myall Creek 4 | Silver City 20 | J.20.063299 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-23 |  | 2020-03-25 17:00 | 2020-03-29 17:00 |  |  | Roma WL | ZWahid | 2022-10-03 13:44 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 37946.72 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001703 | O.1001703.01 | A.1001703.01.05 | Armour - PNX 3 | ARMOUR ENERGY (SURAT BASIN) PTY LTD |  | Silver City 20 | J.20.063298 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-10-23 |  | 2020-10-23 12:00 | 2020-10-27 12:00 |  |  | Roma WL | ZWahid | 2022-10-03 13:44 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Production Services
P.1001701 | O.1001701.04 | A.1001701.04.04 | Comet Ridge Mahalo East 1 | COMET RIDGE LIMITED | MAHALO NORTH 1, MAHALO EAST 1 | CONDOR RIG 1 | J.24.142281 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-10-15 12:00 | 2024-10-14 |  | 2024-10-15 12:00 | 2024-10-19 21:59 |  | 2024-10-19 21:59 | Roma WL | KKeese | 2024-10-31 14:22 | SNiang |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 176387.26 | 3 |  | L2 - Shift RO |  | 100 | 100 | 0 | 75 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001701 | O.1001701.04 | A.1001701.04.02 | Cometridge | COMET RIDGE LIMITED | Mahalo North 1 | CONDOR RIG 1 | J.22.110888 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-06 14:00 | 2023-06-06 |  | 2023-06-06 14:00 | 2023-06-10 23:59 |  | 2023-06-09 23:59 | Roma WL | MRony2 | 2023-02-20 16:37 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001701 | O.1001701.04 | A.1001701.04.03 | Cometridge | COMET RIDGE LIMITED | Mahalo North 1 | CONDOR RIG 1 | J.22.110416 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-05-18 14:00 | 2023-05-18 |  | 2023-05-18 14:00 | 2023-05-22 23:59 |  | 2023-05-21 23:59 | Roma WL | MRony2 | 2023-02-20 16:37 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001701 | O.1001701.04 | A.1001701.04.01 | Mahalo North 1 | COMET RIDGE LIMITED | Mahalo North 1 | CONDOR RIG 1 | J.21.109425 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-10-19 14:00 | 2021-10-19 |  | 2021-10-19 14:00 | 2021-10-23 23:59 |  | 2021-10-22 23:59 | Roma WL | MRony2 | 2022-10-03 14:59 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 79339.18 | 3 |  |  |  | 75 | 50 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001701 | O.1001701.03 | A.1001701.03.01 | MDT packer sell | COMET RIDGE LIMITED | ALBANY 2 | Ensign 932 | J.20.063300 | RPE | ES-OH-NO | InComplete | Unconfirmed - 90% | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-02-24 |  | 2020-02-24 | 2020-02-25 |  |  | Roma WL | MRony2 | 2022-10-03 13:44 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001701 | O.1001701.02 | A.1001701.02.01 | SIS processing | COMET RIDGE LIMITED | ALBANY 2 | Ensign 932 | J.20.063303 | RPE | ES-OH-NO | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2020-02-06 |  | 2020-02-06 | 2020-02-18 |  |  | Roma WL | MRony2 | 2022-10-03 13:45 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 1624.43 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001701 | O.1001701.01 | A.1001701.01.01 | S1 | COMET RIDGE LIMITED | ALBANY 1 | Ensign 932 | J.19.060651 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-16 | 2019-10-15 |  | 2019-10-16 | 2019-10-23 |  | 2019-10-23 | Roma WL | VOliveira5 | 2022-10-03 13:45 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001701 | O.1001701.01 | A.1001701.01.02 | S2 | COMET RIDGE LIMITED | ALBANY 1 | Ensign 932 | J.19.060647 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-16 | 2019-11-09 |  | 2019-11-10 | 2019-11-17 |  | 2019-11-17 | Roma WL | VOliveira5 | 2022-10-03 13:44 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001693 | O.1001693.04 | A.1001693.04.01 | Liger 1 | SANTOS LIMITED | MOOMBA 268 | ENSIGN 971 | J.24.000291 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-03-10 23:00 | 2024-03-11 | 2024-03-11 01:00 | 2024-03-11 | 2024-03-17 | 2024-03-18 | 2024-03-16 22:59 | Moomba WL | KKeese | 2023-10-28 17:01 | KKeese |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001693 | O.1001693.04 | A.1001693.04.16 | Moomba 288 | SANTOS LIMITED | MOOMBA 288 | ENSIGN 971 | J.22.127954 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-12-22 14:00 | 2023-01-11 15:00 |  | 2023-01-12 14:00 | 2023-01-18 14:00 |  | 2023-01-18 13:59 | Moomba WL | KKeese | 2023-01-21 08:23 | YPouryan |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 28369.69 | 2 |  | L2 - Shift RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.04 | A.1001693.04.15 | Moomba 293 | SANTOS LIMITED | Moomba 268 | ENSIGN 971 | J.23.011744 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2023-02-15 |  | 2023-02-15 | 2023-02-21 |  |  | Moomba WL | KKeese | 2022-10-30 18:25 | eismail |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.04 | A.1001693.04.14 | Moomba 277 | SANTOS LIMITED | Moomba 277 | ENSIGN 971 | J.22.110087 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-08-21 |  | 2022-08-21 | 2022-09-02 23:59 |  |  | Moomba WL | KKeese | 2022-10-06 10:28 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.04 | A.1001693.04.13 | Moomba 280 | SANTOS LIMITED | Moomba 280 | ENSIGN 971 | J.22.110002 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-09-28 | 2022-09-27 10:00 |  | 2022-09-27 12:00 | 2022-09-29 13:00 |  | 2022-10-03 11:59 | Moomba WL | KKeese | 2022-10-03 12:31 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 26967.51 | 4 |  |  |  | 66.7 | 83.3 | 0 | 25 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.04 | A.1001693.04.12 | Moomba 274 Quad Combo-MDT | SANTOS LIMITED | Moomba 274 | ENSIGN 971 | J.22.109820 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-05-24 | 2022-05-24 |  | 2022-05-24 | 2022-06-05 23:59 |  | 2022-06-05 23:59 | Moomba WL | YPouryan | 2022-10-03 12:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | 2 |  |  |  | 75 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.04 | A.1001693.04.11 | Moomba South Dev 1 AJ | SANTOS LIMITED | Moomba 268 | ENSIGN 971 | J.22.109776 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-10-27 01:00 | 2022-10-27 |  | 2022-10-27 | 2022-11-02 |  | 2022-11-02 00:59 | Moomba WL | KKeese | 2022-10-03 12:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.04 | A.1001693.04.10 | Moomba 282 | SANTOS LIMITED | MOOMBA 268 | ENSIGN 971 | J.22.109775 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-10-15 | 2022-10-15 |  | 2022-10-15 | 2022-10-21 |  | 2022-10-20 23:59 | Moomba WL | KKeese | 2022-10-03 12:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.04 | A.1001693.04.09 | Moomba 276 | SANTOS LIMITED | Moomba 268 | ENSIGN 971 | J.22.109774 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-08-18 | 2022-08-18 |  | 2022-08-18 | 2022-08-24 |  | 2022-08-23 23:59 | Moomba WL | KKeese | 2022-10-03 12:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.04 | A.1001693.04.08 | Santos OH | SANTOS LIMITED |  | ENSIGN 971 | J.22.109773 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-09-15 | 2022-09-15 |  | 2022-09-15 | 2022-09-21 |  | 2022-09-20 23:59 | Moomba WL | KKeese | 2022-10-03 12:08 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | 1 |  | L1 - Support RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.04 | A.1001693.04.07 | Moomba 277 | SANTOS LIMITED | MOOMBA 268 | ENSIGN 971 | J.22.109772 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-07-25 | 2022-07-25 |  | 2022-07-25 | 2022-07-31 |  | 2022-07-30 23:59 | Moomba WL | KKeese | 2022-10-03 12:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.04 | A.1001693.04.06 | Moomba 275 | SANTOS LIMITED | Moomba 275 | ENSIGN 971 | J.22.109771 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-07-30 | 2022-07-30 |  | 2022-07-30 | 2022-08-05 |  | 2022-08-04 23:59 | Moomba WL | KKeese | 2022-10-03 12:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.04 | A.1001693.04.05 | Moomba 268 | SANTOS LIMITED | Moomba 268 | ENSIGN 971 | J.22.109770 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-06-26 10:00 | 2022-06-26 08:00 |  | 2022-06-26 10:00 | 2022-07-02 10:00 |  | 2022-07-02 09:59 | Moomba WL | KKeese | 2022-10-03 12:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 35723.2 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.04 | A.1001693.04.04 | Moomba 266 | SANTOS LIMITED | MOOMBA 268 | ENSIGN 971 | J.22.109769 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-06-01 | 2022-06-01 |  | 2022-06-01 | 2022-06-07 |  | 2022-06-06 23:59 | Moomba WL | KKeese | 2022-10-03 12:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.04 | A.1001693.04.03 | Santos OH Logging # 2 | SANTOS LIMITED | MOOMBA 268 | ENSIGN 971 | J.22.109661 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-05-01 | 2022-05-01 |  | 2022-05-01 | 2022-05-07 |  | 2022-05-06 23:59 | Moomba WL | KKeese | 2022-10-03 11:57 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.04 | A.1001693.04.02 | Moomba 272_QC-HT, MDT Pressure | SANTOS LIMITED | Moomba 272 | ENSIGN 971 | J.22.109660 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-04-16 | 2022-04-16 |  | 2022-04-16 | 2022-04-20 |  | 2022-04-20 23:59 | Moomba WL | KKeese | 2022-10-03 11:57 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.03 | A.1001693.03.02 | Durham Downs North 10- CBL | SANTOS LIMITED | DURHAM DOWNS NORTH 10 | ENSIGN 971 | J.21.108661 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-08-25 18:00 | 2021-08-24 11:00 | 2021-08-25 | 2021-08-25 20:00 | 2021-08-26 08:00 | 2021-08-27 | 2021-08-26 06:00 | Moomba WL | DKitney | 2022-10-03 11:27 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 9919.08 | 1 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001693 | O.1001693.03 | A.1001693.03.01 | Durham Downs North 9- SCMT | SANTOS LIMITED | Durham Downs North 9 | ENSIGN 971 | J.21.108649 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-07-28 18:00 | 2021-07-27 09:00 | 2021-07-28 | 2021-07-28 18:00 | 2021-07-29 06:00 | 2021-07-30 | 2021-07-29 06:00 | Moomba WL | DKitney | 2022-10-03 11:26 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 9919.08 | 1 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001693 | O.1001693.02 | A.1001693.02.01 | Coolah-12_UBD-Packer-Setting | SANTOS LIMITED | Coolah 12 | ENSIGN 971 | J.19.060515 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2019-09-27 12:00 | 2019-09-21 |  | 2019-09-27 12:00 | 2019-10-02 18:00 |  | 2019-10-02 18:00 | Moomba WL | ymoradi2 | 2022-10-03 10:49 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 5847.95 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001693 | O.1001693.01 | A.1001693.01.38 | Moomba 306 | SANTOS LIMITED | MOOMBA 293 | ENSIGN 971 | J.23.041194 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-07-01 11:00 | 2023-07-01 10:00 |  | 2023-07-01 12:00 | 2023-07-07 11:59 |  | 2023-07-07 12:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.41 | Moomba South DA3 1 | SANTOS LIMITED | MOOMBA 293 | ENSIGN 971 | J.23.085645 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-12-12 11:00 | 2023-12-12 10:00 |  | 2023-12-12 12:00 | 2023-12-18 11:59 |  | 2023-12-18 12:59 | Moomba WL | KKeese | 2023-12-30 08:21 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.48 | Moomba 316 | SANTOS LIMITED | MOOMBA 301 | ENSIGN 971 | J.24.021438 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-01-16 11:00 | 2024-01-09 10:00 |  | 2024-01-16 12:00 | 2024-01-20 11:59 |  | 2024-01-20 12:59 | Moomba WL | KKeese | 2023-12-30 08:00 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.47 | Moomba 315 (SOUTH DA 3 DEV AI GAS) DCXF | SANTOS LIMITED | MOOMBA 301 | ENSIGN 971 | J.23.122636 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-01-01 11:00 | 2023-12-25 10:00 |  | 2024-01-01 12:00 | 2024-01-05 11:59 |  | 2024-01-05 12:59 | Moomba WL | KKeese | 2023-12-30 08:00 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 2 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.45 | Moomba 313 (SOUTH DA 3 DEV AT GAS) DCXF | SANTOS LIMITED | MOOMBA 301 | ENSIGN 971 | J.23.140545 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-30 11:00 | 2023-10-23 10:00 | 2023-10-26 13:00 | 2023-10-30 12:00 | 2023-11-08 11:59 | 2023-11-09 01:00 | 2023-11-08 12:59 | Moomba WL | KKeese | 2023-09-26 09:57 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.46 | Moomba 314 (SOUTH DA 3 DEV BB GAS) DCXF | SANTOS LIMITED | MOOMBA 301 | ENSIGN 971 | J.23.122635 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-11-14 11:00 | 2023-11-07 10:00 | 2023-11-10 13:00 | 2023-11-14 12:00 | 2023-11-23 11:59 | 2023-11-24 01:00 | 2023-11-23 12:59 | Moomba WL | KKeese | 2023-09-26 09:57 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.44 | Moomba 308 (SOUTH DA 6.3 DEV AI GAS) DCXF | SANTOS LIMITED | MOOMBA 301 | ENSIGN 971 | J.23.122634 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-13 11:00 | 2023-10-06 10:00 | 2023-10-09 13:00 | 2023-10-13 12:00 | 2023-10-22 11:59 | 2023-10-23 01:00 | 2023-10-22 12:59 | Moomba WL | KKeese | 2023-09-26 09:30 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.43 | Moomba 307 (SOUTH DA 6.3 DEV AE GAS) DCXF | SANTOS LIMITED | MOOMBA 301 | ENSIGN 971 | J.23.122633 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-01 11:00 | 2023-09-24 10:00 | 2023-09-27 12:00 | 2023-10-01 12:00 | 2023-10-10 11:59 | 2023-10-11 01:00 | 2023-10-10 12:59 | Moomba WL | KKeese | 2023-09-26 09:30 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.42 | Moomba South 3 DB 1 | SANTOS LIMITED | MOOMBA 293 | ENSIGN 971 | J.23.085646 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-12-23 11:00 | 2023-12-23 10:00 | 2023-12-19 13:00 | 2023-12-23 12:00 | 2023-12-29 11:59 | 2023-12-29 13:00 | 2023-12-29 12:59 | Moomba WL | KKeese | 2023-08-17 17:22 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.39 | Moomba 307 | SANTOS LIMITED | MOOMBA 293 | ENSIGN 971 | J.23.083623 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-16 11:00 | 2023-09-16 10:00 | 2023-09-12 12:00 | 2023-09-16 12:00 | 2023-09-22 11:59 | 2023-09-22 12:00 | 2023-09-22 12:59 | Moomba WL | KKeese | 2023-08-03 12:28 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.40 | Moomba 308 | SANTOS LIMITED | MOOMBA 293 | ENSIGN 971 | J.23.083624 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-24 11:00 | 2023-09-24 10:00 | 2023-09-20 12:00 | 2023-09-24 12:00 | 2023-09-30 11:59 | 2023-09-30 12:00 | 2023-09-30 12:59 | Moomba WL | KKeese | 2023-08-03 12:28 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.37 | Moomba 305 | SANTOS LIMITED | MOOMBA 293 | ENSIGN 971 | J.23.041193 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-17 11:00 | 2023-06-17 10:00 |  | 2023-06-17 12:00 | 2023-06-23 11:59 |  | 2023-06-23 12:59 | Moomba WL | KKeese | 2023-06-09 07:43 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.36 | Moomba 301 | SANTOS LIMITED | MOOMBA 301 | ENSIGN 971 | J.23.041192 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-31 11:00 | 2023-05-24 10:00 |  | 2023-05-31 12:00 | 2023-06-09 11:59 |  | 2023-06-09 12:59 | Moomba WL | KKeese | 2023-06-06 08:42 | DYanagawa |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 39787.68 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.34 | Moomba 300 | SANTOS LIMITED | MOOMBA 300 | ENSIGN 971 | J.23.021784 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-04-22 | 2023-05-05 |  | 2023-05-05 22:00 | 2023-05-08 21:59 |  | 2023-05-11 23:59 | Moomba WL | KKeese | 2023-05-07 17:00 | eismail |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 32179.88 | 2 |  | L3 - Full RO |  | 91.7 | 66.7 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.35 | Moomba 298 | SANTOS LIMITED | MOOMBA 298 | ENSIGN 971 | J.23.041191 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-03-31 10:00 | 2023-03-30 10:00 |  | 2023-03-31 12:00 | 2023-04-06 11:59 |  | 2023-04-06 11:59 | Moomba WL | KKeese | 2023-04-08 11:37 | HEstrella |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 28369.69 | 2 |  | L2 - Shift RO |  | 50 | 83.3 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.33 | Moomba 298 | SANTOS LIMITED |  | ENSIGN 971 | J.23.021783 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-04-07 | 2023-04-07 |  | 2023-04-07 | 2023-04-12 23:59 |  | 2023-04-13 01:59 | Moomba WL | KKeese | 2023-02-19 11:19 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.32 | Moomba 293_QC | SANTOS LIMITED | MOOMBA 293 | ENSIGN 971 | J.23.012002 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-02-13 11:00 | 2023-02-13 10:00 |  | 2023-02-13 12:00 | 2023-02-19 11:59 |  | 2023-02-19 12:59 | Moomba WL | eismail | 2023-02-16 08:02 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 28369.69 | 1 |  | L0 - No RO |  | 100 | 100 | 0 | 75 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.31 | Moomba 226 | SANTOS LIMITED | Moomba 226 (Dev B) | ENSIGN 971 | J.22.109748 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-03-06 22:00 | 2022-03-06 |  | 2022-03-06 22:00 | 2022-03-08 21:59 |  | 2022-03-08 23:00 | Moomba WL | KKeese | 2022-10-03 12:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 26770.63 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.30 | Beanbush 3 | SANTOS LIMITED | BEANBUSH 003 | ENSIGN 971 | J.22.109726 | RPE | ES-OH-NO | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2022-02-24 |  | 2022-02-24 | 2022-02-25 23:59 |  |  | Moomba WL | RTwigg | 2022-10-03 12:03 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 33.3 | 33.3 | 100 | 50 | 45 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.29 | Liger 1 | SANTOS LIMITED | LIGER 1 | ENSIGN 971 | J.21.108747 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-09-27 | 2021-09-27 | 2021-09-27 | 2021-09-27 | 2021-10-03 | 2021-10-04 | 2021-10-02 23:59 | Moomba WL | MAl-wakeel | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 66.7 | 33.3 | 0 | 75 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.22 | Moomba 225 | SANTOS LIMITED | MOOMBA 225 | ENSIGN 971 | J.20.062869 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-09-27 20:00 | 2020-09-27 19:00 |  | 2020-09-27 20:00 | 2020-09-30 20:00 |  | 2020-10-04 21:00 | Moomba WL | AGamero | 2022-10-03 10:51 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.19 | Well TBD | SANTOS LIMITED |  | ENSIGN 971 | J.20.062868 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-10-03 23:00 | 2020-10-04 |  | 2020-10-04 | 2020-10-07 |  | 2020-10-11 | Moomba WL | AGamero | 2022-10-03 10:51 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.20 | Well TBD | SANTOS LIMITED |  | ENSIGN 971 | J.20.062867 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-10-17 | 2020-10-17 |  | 2020-10-17 | 2020-10-20 |  | 2020-10-24 | Moomba WL | AGamero | 2022-10-03 10:51 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.27 | Yalcumma 3 PumpDown SWeTech | SANTOS LIMITED | YALCUMMA 3 DW1 | ENSIGN 971 | J.20.062866 | RPE | ES-CH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-26 18:00 | 2020-09-02 18:00 |  | 2020-12-27 12:00 | 2021-01-01 21:00 |  | 2021-01-04 03:00 | Moomba WL | DKitney | 2022-10-03 10:50 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.14 | Well TBD | SANTOS LIMITED |  | ENSIGN 971 | J.20.062864 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-07-22 23:00 | 2020-07-23 |  | 2020-07-23 | 2020-07-26 |  | 2020-07-29 23:00 | Moomba WL | AGamero | 2022-10-03 10:50 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.12 | Well TBD | SANTOS LIMITED |  | ENSIGN 971 | J.20.062863 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-06-26 23:00 | 2020-06-27 |  | 2020-06-27 | 2020-06-30 |  | 2020-07-03 23:00 | Moomba WL | AGamero | 2022-10-03 10:50 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.09 | Tarwonga 6 | SANTOS LIMITED | Tarwonga 6 | ENSIGN 971 | J.21.108412 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-04-04 23:00 | 2021-04-03 12:00 |  | 2021-04-04 23:00 | 2021-04-10 |  | 2021-04-10 | Moomba WL | AGamero | 2022-10-03 10:50 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.05 | Durham Downs North 8 | SANTOS LIMITED | DURHAM DOWNS NORTH 8 | ENSIGN 971 | J.20.062859 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-03-27 23:00 | 2020-03-27 12:00 |  | 2020-03-27 23:00 | 2020-03-29 14:00 |  | 2020-03-29 14:00 | Moomba WL | AGamero | 2022-10-03 10:50 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.10 | Moonanga 2 | SANTOS LIMITED | Moonanga 2 | ENSIGN 971 | J.21.108411 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-06-06 | 2021-06-06 |  | 2021-06-06 | 2021-06-12 |  | 2021-06-11 23:59 | Moomba WL | AGamero | 2022-10-03 10:50 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.21 | Moomba 263 | SANTOS LIMITED | Moomba 263 | ENSIGN 971 | J.20.062855 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-12-04 | 2020-12-04 |  | 2020-12-04 | 2020-12-07 |  | 2020-12-11 | Moomba WL | AGamero | 2022-10-03 10:49 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.07 | Moomba 252 | SANTOS LIMITED | Moomba 252 | ENSIGN 971 | J.20.062853 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-07-27 | 2020-07-26 |  | 2020-07-26 20:00 | 2020-07-30 20:00 |  | 2020-07-31 | Moomba WL | AGamero | 2022-10-03 10:49 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 69424.85 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.15 | Well TBD | SANTOS LIMITED |  | ENSIGN 971 | J.20.062851 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-08-05 23:00 | 2020-08-06 |  | 2020-08-06 | 2020-08-09 |  | 2020-08-12 23:00 | Moomba WL | AGamero | 2022-10-03 10:49 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.25 | Yalcumma 3 | SANTOS LIMITED | YALCUMMA 003 | ENSIGN 971 | J.20.062850 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-08-13 | 2020-08-13 |  | 2020-08-15 | 2020-08-18 |  | 2020-08-16 13:30 | Moomba WL | AGamero | 2022-10-03 10:49 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 69333.89 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.08 | Santos ¦ Moomba 259 ¦ Ensign 971 | SANTOS LIMITED | MOOMBA 259 | ENSIGN 971 | J.21.108409 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2020-10-04 09:00 | 2021-03-01 06:00 |  | 2021-03-01 10:00 | 2021-03-03 10:00 |  | 2021-03-08 09:00 | Moomba WL | AGamero | 2022-10-03 10:49 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  | L0 - No RO |  | 58.3 | 50 | 0 | 75 | 55 |  | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.03 | Barrolka North East 5 | SANTOS LIMITED | Barrolka North East 5 | ENSIGN 971 | J.20.062849 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-01-14 | 2020-01-14 |  | 2020-01-14 | 2020-01-17 |  | 2020-01-21 | Moomba WL | AGamero | 2022-10-03 10:48 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.26 | Yalcumma 3 DW1 - FPIT, Backoff | SANTOS LIMITED | YALCUMMA 003 DW1 | ENSIGN 971 | J.20.062848 | RPE | ES-CH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2020-09-02 12:00 | 2020-08-31 |  | 2020-09-02 12:00 | 2020-09-04 11:59 |  | 2020-09-07 11:59 | Moomba WL | AHermawan | 2022-10-03 10:48 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 |  |  | L0 - No RO |  | 58.3 | 16.7 | 0 | 37.5 | 33.8 |  | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.23 | Moomba 260 | SANTOS LIMITED | Moomba 260 | ENSIGN 971 | J.21.108408 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress | 2021-02-16 12:00 | 2021-02-16 12:00 |  | 2021-02-16 12:00 | 2021-02-19 12:00 |  | 2021-02-23 12:00 | Moomba WL | AGamero | 2022-10-03 10:48 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.17 | Well TBD | SANTOS LIMITED |  | ENSIGN 971 | J.20.062847 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-09-04 23:00 | 2020-09-05 |  | 2020-09-05 | 2020-09-08 |  | 2020-09-11 23:00 | Moomba WL | AGamero | 2022-10-03 10:48 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.13 | Well TBD | SANTOS LIMITED |  | ENSIGN 971 | J.20.062846 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-07-08 23:00 | 2020-07-09 |  | 2020-07-09 | 2020-07-12 |  | 2020-07-15 23:00 | Moomba WL | AGamero | 2022-10-03 10:48 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.28 | Moomba 261 | SANTOS LIMITED | Moomba 261 | ENSIGN 971 | J.21.108407 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-03-13 18:00 | 2021-03-13 12:00 |  | 2021-03-13 18:00 | 2021-03-18 18:00 |  | 2021-03-18 18:00 | Moomba WL | OBass | 2022-10-03 10:48 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.18 | Well TBD | SANTOS LIMITED |  | ENSIGN 971 | J.20.062845 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-09-19 23:00 | 2020-09-20 |  | 2020-09-20 | 2020-09-23 |  | 2020-09-26 23:00 | Moomba WL | AGamero | 2022-10-03 10:48 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.24 | Kowloon 1 | SANTOS LIMITED | Kowloon 1 | ENSIGN 971 | J.20.062843 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-12-30 06:00 | 2020-12-18 |  | 2020-12-30 06:00 | 2021-01-02 06:00 |  | 2021-01-06 06:00 | Moomba WL | AGamero | 2022-10-03 10:48 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.16 | Well TBD | SANTOS LIMITED |  | ENSIGN 971 | J.20.062842 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-08-22 23:00 | 2020-08-23 |  | 2020-08-23 | 2020-08-26 |  | 2020-08-29 23:00 | Moomba WL | AGamero | 2022-10-03 10:48 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.02 | Barrolka North East 4 | SANTOS LIMITED | Barrolka North East 4 | ENSIGN 971 | J.19.060514 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2019-12-25 | 2019-12-25 |  | 2019-12-25 | 2019-12-28 |  | 2020-01-01 | Moomba WL | AGamero | 2022-10-03 10:48 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.01 | Coolah 11 | SANTOS LIMITED | Coolah 11 | ENSIGN 971 | J.19.060513 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2019-12-13 | 2019-12-05 |  | 2019-12-13 | 2019-12-16 |  | 2019-12-20 | Moomba WL | AGamero | 2022-10-03 10:47 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 50 | 33.3 | 0 | 25 | 32.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.11 | Well TBD | SANTOS LIMITED |  | ENSIGN 971 | J.20.062839 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-06-10 23:00 | 2020-06-11 |  | 2020-06-11 | 2020-06-14 |  | 2020-06-17 23:00 | Moomba WL | AGamero | 2022-10-03 10:47 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.06 | Merupa | SANTOS LIMITED | Merupa | ENSIGN 971 |  | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-03 |  | 2020-04-03 | 2020-04-06 |  |  | Moomba WL | AGamero | 2020-11-13 10:25 | JColeman |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001693 | O.1001693.01 | A.1001693.01.04 | Durham Downs West 1 | SANTOS LIMITED | Durham Downs West | ENSIGN 971 |  | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-28 |  | 2020-01-29 18:00 | 2020-02-08 18:00 |  |  | Moomba WL | AGamero | 2020-11-13 10:25 | JColeman |  | No |  |  |  |  | Ihab Wahbi |  | 47713.71 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001689 | O.1001689.06 | A.1001689.06.01 | Moomba 45 | SANTOS LIMITED | Well #21 | Wild Desert Rig 16 | J.23.008527 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2023-03-08 19:00 |  | 2023-03-09 10:00 | 2023-03-15 09:59 |  |  | Moomba WL | FDPSystemUser | 2022-10-27 10:54 | KKeese |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  |  |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.05 | A.1001689.05.08 | Well # 1 | SANTOS LIMITED |  | Wild Desert Rig 16 | J.23.008556 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2023-11-08 16:00 |  | 2023-11-08 18:00 | 2023-11-10 18:00 |  |  | Moomba WL | MAlhashemi | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 16.7 | 0 | 0 | 0 | 5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001689 | O.1001689.05 | A.1001689.05.10 | WD16-(4.5)HSD-(7.5) Packer | SANTOS LIMITED | Toolachee | Wild Desert Rig 16 | J.22.110084 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-08-16 06:00 | 2022-08-15 08:00 |  | 2022-08-16 07:00 | 2022-08-18 06:59 |  | 2022-08-18 06:59 | Moomba WL | JMoraes2 | 2022-10-03 12:39 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001689 | O.1001689.05 | A.1001689.05.09 | Keleary 3 - Tubing Cut | SANTOS LIMITED | Keleary 3 | Wild Desert Rig 16 | J.22.109816 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-11-08 17:00 | 2022-05-15 12:00 |  | 2022-05-15 16:00 | 2022-05-17 06:59 |  | 2023-11-10 07:59 | Moomba WL | MAlhashemi | 2022-10-03 12:12 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7087.33 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001689 | O.1001689.05 | A.1001689.05.07 | Coonatie 10 Production Casing Perforation | SANTOS LIMITED | Coonatie 10 | Wild Desert Rig 16 | J.22.109813 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-11-05 02:00 | 2022-05-12 |  | 2022-05-12 | 2022-05-12 23:59 |  | 2023-11-06 01:59 | Moomba WL | SYalamanchi2 | 2022-10-03 12:12 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001689 | O.1001689.05 | A.1001689.05.06 | Correa 1- Tubing Cut | SANTOS LIMITED | Correa 1 | Wild Desert Rig 16 | J.22.109746 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-08-26 09:00 | 2022-03-02 08:00 |  | 2022-03-02 09:00 | 2022-03-03 23:59 |  | 2023-08-27 23:59 | Moomba WL | DKitney | 2022-10-03 12:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7087.33 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001689 | O.1001689.05 | A.1001689.05.05 | Kurunda 3- Tubing Cut | SANTOS LIMITED | Kurunda 3 | Wild Desert Rig 16 | J.21.108795 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-23 | 2021-11-26 |  | 2021-11-27 | 2021-11-28 23:59 |  | 2023-05-24 23:59 | Moomba WL | DKitney | 2022-10-03 11:51 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.05 | A.1001689.05.04 | Meranji 7 | SANTOS LIMITED | Meranji 7 | Wild Desert Rig 16 | J.21.108764 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-17 | 2021-10-21 | 2023-04-17 01:00 | 2021-10-22 | 2021-10-23 23:59 | 2023-04-19 01:00 | 2023-04-19 00:59 | Moomba WL | KKeese | 2022-10-03 11:39 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 79.2 | 8.3 | 0 | 0 | 26.3 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.05 | A.1001689.05.03 | Waukatanna 2 | SANTOS LIMITED | Waukatanna 2 | Wild Desert Rig 16 | J.21.108759 | RPI | PS-WL-NO | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-05-28 | 2021-12-01 | 2023-05-28 01:00 | 2021-12-02 | 2021-12-03 23:59 | 2023-05-30 01:00 | 2023-05-30 00:59 | Moomba WL | ymoradi2 | 2022-10-03 11:39 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 91.7 | 66.7 | 100 | 75 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001689 | O.1001689.05 | A.1001689.05.02 | Fly Lake 1 | SANTOS LIMITED | Fly Lake 1 | Wild Desert Rig 16 | J.21.108541 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-07 01:00 | 2021-05-13 | 2022-11-07 02:00 | 2021-05-14 | 2021-05-15 23:59 | 2022-11-09 02:00 | 2022-11-09 01:59 | Moomba WL | KKeese | 2022-10-03 11:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.05 | A.1001689.05.01 | Moomba 176 | SANTOS LIMITED | Moomba 176 | Wild Desert Rig 16 | J.21.108406 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-08-18 | 2021-02-21 |  | 2021-02-22 | 2021-02-23 23:59 |  | 2022-08-19 23:59 | Moomba WL | KKeese | 2022-10-03 10:47 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001689 | O.1001689.04 | A.1001689.04.03 | Gidgealpa 57 | SANTOS LIMITED | Gidgealpa 57 | Wild Desert Rig 16 | J.21.108413 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-01-21 18:00 | 2021-01-21 08:00 |  | 2021-01-21 18:00 | 2021-01-23 08:59 |  | 2021-01-23 08:59 | Moomba WL | AHermawan | 2022-10-03 10:51 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.04 | A.1001689.04.01 | TCP Correlation Big Lake 102 | SANTOS LIMITED | Big Lake 102 | Wild Desert Rig 16 | J.20.062865 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-03-02 09:00 | 2020-03-03 06:00 |  | 2020-03-03 06:00 | 2020-03-05 |  | 2020-03-04 03:00 | Moomba WL | ASetya | 2022-10-03 10:50 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.04 | A.1001689.04.02 | Muteroo 4 | SANTOS LIMITED | Muteroo 4 | Wild Desert Rig 16 | J.21.108410 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-01-11 09:00 | 2021-01-11 08:00 |  | 2021-01-11 09:00 | 2021-01-12 23:59 |  | 2021-01-12 23:59 | Moomba WL | AHermawan | 2022-10-03 10:49 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.29 | Marabooka 19 | SANTOS LIMITED | MARABOOKA 19, NUNGEROO WEST 001, STRZELECKI 36, STRZELECKI 35, HECTOR 1, MOOMBA 79, BIG LAKE 135 | Wild Desert Rig 16 | J.23.128291 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-08-30 12:00 | 2023-08-30 | 2023-08-28 18:00 | 2023-08-30 12:00 | 2024-05-01 23:59 | 2024-05-02 | 2024-05-01 23:59 | Moomba WL | ADuong4 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 8961.01 | 1 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.30 | Moomba 79_USIT | SANTOS LIMITED | MOOMBA 79, MOOMBA 43 | Wild Desert Rig 16 | J.23.168986 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-11-20 20:00 | 2023-11-20 18:00 |  | 2023-11-20 20:00 | 2024-02-21 06:59 |  | 2024-02-21 06:59 | Moomba WL | ASamokhin | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 24603.64 | 5 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Adel Mohammad Alhashemi | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.31 | Tallalia 2 USIT_CBL | SANTOS LIMITED | TALLALIA 2 | Wild Desert Rig 16 | J.23.172430 | RPI | PS-WL-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-12-09 20:00 | 2023-12-05 18:00 |  | 2023-12-09 20:00 | 2024-03-11 06:59 |  | 2024-03-11 06:59 | Moomba WL | AKavooris | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.32 | Moomba 79 Perforation | SANTOS LIMITED | MOOMBA 79 | Wild Desert Rig 16 | J.23.173496 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-12-10 20:00 | 2023-12-10 18:00 |  | 2023-12-10 20:00 | 2024-03-12 06:59 |  | 2024-03-12 06:59 | Moomba WL | ymoradi2 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 4136.45 | 1 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.33 | Big Lake 135 | SANTOS LIMITED | MARABOOKA 19, NUNGEROO WEST 001, STRZELECKI 36, STRZELECKI 35, HECTOR 1, MOOMBA 79, BIG LAKE 135, TOOLACHEE 16, WACKETT 7, KARRI SOUTH 1 | Wild Desert Rig 16 | J.24.074274 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-03-27 15:00 | 2024-03-22 |  | 2024-03-23 12:00 | 2024-07-05 23:59 |  | 2024-11-14 03:59 | Moomba WL | FShallal | 2024-08-13 16:28 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 3 |  | L0 - No RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 1 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.28 | Merrimelia 12 | SANTOS LIMITED | BURLEY 3 | Wild Desert Rig 16 | J.23.077771 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-03 20:00 | 2023-04-29 |  | 2023-05-03 20:00 | 2023-05-08 19:59 |  | 2023-05-08 19:59 | Moomba WL | ymoradi2 | 2023-05-07 17:57 | eismail |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 75 | 50 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.27 | Burley 3 | SANTOS LIMITED | Burley 3 | Wild Desert Rig 16 | J.22.109939 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-06-13 20:00 | 2022-06-11 |  | 2022-06-13 20:00 | 2022-06-18 19:59 |  | 2022-06-18 19:59 | Moomba WL | YPouryan | 2022-10-03 12:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.26 | Meranji 15 | SANTOS LIMITED | Meranji 15 | Wild Desert Rig 16 | J.22.109789 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-08 10:00 | 2022-04-07 |  | 2022-04-08 10:00 | 2022-04-09 23:59 |  | 2022-04-09 23:59 | Moomba WL | ADuong4 | 2022-10-03 12:10 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7087.33 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.25 | Meranji 2 | SANTOS LIMITED | Meranji 2 | Wild Desert Rig 16 | J.21.108738 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-09 12:00 | 2021-09-09 15:00 | 2021-09-09 14:00 | 2021-09-10 06:00 | 2021-09-16 05:59 | 2021-09-17 | 2021-09-15 13:59 | Moomba WL | KKeese | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.24 | Daralingie 11, Meranji 2 Tubing Cut, | SANTOS LIMITED | DARALINGIE 11, MERANJI 2 | Wild Desert Rig 16 | J.21.108664 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | In Progress | In Progress | 2021-08-27 14:38 | 2021-08-27 15:00 | 2021-08-27 14:00 | 2021-08-28 06:00 | 2021-09-03 05:59 | 2021-09-04 | 2021-09-03 09:59 | Moomba WL | ymoradi2 | 2022-10-03 11:27 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.23 | Moomba 136 SwETech | SANTOS LIMITED | Moomba 136 | Wild Desert Rig 16 | J.21.108651 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-28 12:00 | 2021-07-28 15:00 | 2021-07-28 14:00 | 2021-07-29 06:00 | 2021-08-04 05:59 | 2021-08-05 | 2021-08-03 13:59 | Moomba WL | KKeese | 2022-10-03 11:26 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.22 | Moomba 136 Tubing Cutter | SANTOS LIMITED | Moomba 136 | Wild Desert Rig 16 | J.21.108646 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-07-24 12:00 | 2021-07-24 15:00 | 2021-07-24 14:00 | 2021-07-25 06:00 | 2021-07-31 05:59 | 2021-08-01 | 2021-07-30 13:59 | Moomba WL | SYalamanchi2 | 2022-10-03 11:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.21 | Moomba 45 | SANTOS LIMITED | Moomba 45 | Wild Desert Rig 16 | J.21.108635 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-20 12:00 | 2021-06-19 21:00 | 2021-06-19 14:00 | 2021-06-20 12:00 | 2021-06-26 11:59 | 2021-06-27 | 2021-06-26 13:59 | Moomba WL | KKeese | 2022-10-03 11:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.20 | Fly Lake 1 ;Goyder 6, Set CIBP & Perforate ; Packer Set, Casing patch | SANTOS LIMITED | Fly Lake 1, Goyder 6, Fly Lake 24 | Wild Desert Rig 16 | J.21.108545 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-20 | 2021-05-19 | 2021-05-20 | 2021-05-20 | 2021-05-22 23:59 | 2021-05-23 | 2021-05-22 23:59 | Moomba WL | ymoradi2 | 2022-10-03 11:15 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | 2 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.19 | Munkah 4 Tubing Cut Long String | SANTOS LIMITED | MUNKAH 4 | Wild Desert Rig 16 | J.21.108528 | RPI | PS-WL-NO | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-06 13:00 | 2021-04-05 21:00 | 2021-04-06 | 2021-04-06 12:00 | 2021-04-10 11:59 | 2021-04-11 | 2021-04-10 15:59 | Moomba WL | KKeese | 2022-10-03 11:14 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 91.7 | 66.7 | 100 | 75 | 80 |  | 0 |  |  |  | 0 |  |  |  | Owen Bass | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.18 | Munkah 4 ; Tubing Cut [Short String / Long String] | SANTOS LIMITED | Munkah 4 | Wild Desert Rig 16 | J.21.108524 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-03-15 15:00 | 2021-03-14 21:00 | 2021-03-15 | 2021-03-15 12:00 | 2021-03-19 11:59 | 2021-03-20 | 2021-03-19 14:59 | Moomba WL | ymoradi2 | 2022-10-03 11:13 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.17 | Moomba 32- Cuttter/SCMT | SANTOS LIMITED | Moomba 32 | Wild Desert Rig 16 | J.21.108424 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-27 12:00 | 2021-02-26 21:00 | 2021-02-27 | 2021-02-27 12:00 | 2021-03-03 11:59 | 2021-03-04 | 2021-03-03 14:59 | Moomba WL | DKitney | 2022-10-03 11:03 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.14 | Kerna 2A- Circ Perf | SANTOS LIMITED | Kerna 2 | Wild Desert Rig 16 | J.20.062872 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-10-28 22:56 | 2020-10-21 20:50 |  | 2020-10-28 23:50 | 2020-11-02 00:53 |  | 2020-11-01 23:59 | Moomba WL | DKitney | 2022-10-03 10:51 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 4049.9 |  |  |  |  | 66.7 | 50 | 0 | 62.5 | 53.8 |  | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.12 | Kerna 2 - 3-3/8'' HSD | SANTOS LIMITED | Kerna 2 | Wild Desert Rig 16 | J.20.062871 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-10-17 07:14 | 2020-10-17 00:15 |  | 2020-10-17 07:14 | 2020-10-20 09:14 |  | 2020-10-20 09:14 | Moomba WL | DParker16 | 2022-10-03 10:51 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.06 | Moorari 5 | SANTOS LIMITED | Moorari 5 | Wild Desert Rig 16 | J.20.062870 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-07-10 12:00 | 2020-07-10 11:00 |  | 2020-07-10 12:00 | 2020-07-11 14:00 |  | 2020-07-11 14:00 | Moomba WL | MSchvartz | 2022-10-03 10:51 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.09 | Tirrawarra 14; puncher, cutter; Reperforate / Set Packer | SANTOS LIMITED | Tirrawarra 14 | Wild Desert Rig 16 | J.20.062862 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress | 2020-12-27 12:00 | 2020-09-17 |  | 2020-12-27 12:00 | 2021-01-01 04:59 |  | 2021-01-01 04:59 | Moomba WL | ymoradi2 | 2022-10-03 10:50 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.04 | Moomba 51 PJ 4505 and Packer Setting | SANTOS LIMITED | Moomba51 | Wild Desert Rig 16 | J.20.062860 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-12-29 10:00 | 2020-09-11 20:00 |  | 2020-12-29 12:00 | 2020-12-31 06:00 |  | 2020-12-31 23:00 | Moomba WL | ASetya | 2022-10-03 10:50 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6429.6 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.05 | Cooba-2_Puncher_Tubing Cutter | SANTOS LIMITED | Cooba 2 | Wild Desert Rig 16 | J.20.062858 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-06-22 17:00 | 2020-06-22 11:00 |  | 2020-06-22 17:00 | 2020-06-23 19:00 |  | 2020-06-23 19:00 | Moomba WL | AHermawan | 2022-10-03 10:50 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.03 | Chiron 1 | SANTOS LIMITED | Chiron 1 | Wild Desert Rig 16 | J.20.062857 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-08-05 06:02 | 2020-07-06 18:00 |  | 2020-08-05 06:02 | 2020-08-06 18:00 |  | 2020-08-06 18:00 | Moomba WL | DParker16 | 2022-10-03 10:49 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 14174.66 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.02 | Burke 4- Tubing Cutter | SANTOS LIMITED | Burke 3 | Wild Desert Rig 16 | J.20.062856 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-20 06:00 | 2020-12-20 |  | 2020-12-20 06:00 | 2020-12-22 12:00 |  | 2020-12-21 13:00 | Moomba WL | ymoradi2 | 2022-10-03 10:49 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.08 | Pira 1 Perfo Packer | SANTOS LIMITED | Pira 1 | Wild Desert Rig 16 | J.20.062854 | RPI | PS-WL-Ops | Low | Operationally Complete | Design - PSD |  | In Progress | In Progress | In Progress | 2020-10-08 07:00 | 2020-10-08 |  | 2020-10-08 07:00 | 2020-10-12 23:59 |  | 2020-10-12 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:49 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  |  |  | 58.3 | 16.7 | 0 | 62.5 | 41.3 |  | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.13 | Toolachee 12 - P&A ; Perforate [20ft 3-3/8" Power Jet] | SANTOS LIMITED | Toolachee 12 | Wild Desert Rig 16 | J.20.062852 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-10-24 | 2020-10-23 |  | 2020-10-24 | 2020-10-25 23:59 |  | 2020-10-25 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:49 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  |  |  | 66.7 | 16.7 | 0 | 0 | 25 |  | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.16 | Sturt East 1 | SANTOS LIMITED | Sturt East 1 | Wild Desert Rig 16 | J.20.062844 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-11-21 13:18 | 2020-11-20 13:18 |  | 2020-11-21 13:18 | 2020-11-23 13:18 |  | 2020-11-23 13:18 | Moomba WL | DParker16 | 2022-10-03 10:48 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 5806.89 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.01 | TubingCut-CBL-TailpipeSetting-Plug Setting | SANTOS LIMITED | Strzelecki 8 | Wild Desert Rig 16 | J.20.062840 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-08-10 06:00 | 2020-07-20 06:00 |  | 2020-08-10 06:00 | 2020-08-12 19:00 |  | 2020-08-12 19:00 | Moomba WL | ymoradi2 | 2022-10-03 10:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.11 | Kerna 2 | SANTOS LIMITED | Kerna 2 | Wild Desert Rig 16 | J.20.062838 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-10-14 11:45 | 2020-10-13 11:45 |  | 2020-10-14 11:45 | 2020-10-18 11:45 |  | 2020-10-18 11:45 | Moomba WL | DParker16 | 2022-10-03 10:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6966.34 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.15 | Sturt East 1 - P&A ; Cement Evaluation Log | SANTOS LIMITED | STURT EAST 1 | Wild Desert Rig 16 | J.20.062837 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2020-11-15 15:00 | 2020-11-15 |  | 2020-11-15 15:00 | 2020-11-19 14:59 |  | 2020-11-19 14:59 | Moomba WL | ymoradi2 | 2022-10-03 10:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 75 | 50 | 0 | 75 | 60 |  | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.10 | Kerna 2A | SANTOS LIMITED | Kerna 2 | Wild Desert Rig 16 | J.20.062836 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-10-10 22:56 | 2020-10-06 19:56 |  | 2020-10-10 22:56 | 2020-10-14 23:59 |  | 2020-10-14 23:59 | Moomba WL | DParker16 | 2022-10-03 10:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.03 | A.1001689.03.07 | Della 19 | SANTOS LIMITED | Della 19 | Wild Desert Rig 16 | J.20.062835 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-08-12 14:16 | 2020-08-11 14:16 |  | 2020-08-12 14:16 | 2020-08-15 14:16 |  | 2020-08-15 14:16 | Moomba WL | DParker16 | 2022-10-03 10:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.25 | Marabooka 4-CBL-USIT-CPST | SANTOS LIMITED | DULLINGARI 35, MARABOOKA 4 | Wild Desert Rig 16 | J.23.108134 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-07-11 12:00 | 2023-07-10 | 2023-07-11 | 2023-07-11 12:00 | 2023-07-13 11:59 | 2023-07-14 | 2023-07-13 11:59 | Moomba WL | ymoradi2 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 1 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Adel Mohammad Alhashemi | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.26 | Gidgealpa 27 | SANTOS LIMITED | GIDGEALPA 25, STRZELECKI 34, TALOOLA 2, DARALINGIE 16 | Wild Desert Rig 16 | J.23.117746 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-07-30 15:00 | 2023-07-29 12:00 | 2023-07-29 04:00 | 2023-07-30 15:00 | 2023-10-31 23:59 | 2023-11-01 | 2023-10-31 23:59 | Moomba WL | ADuong4 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 97509.63 | 1 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.27 | Moomba 43 String Shot | SANTOS LIMITED | MOOMBA 41, MOOMBA 43 | Wild Desert Rig 16 | J.24.041847 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-01-17 | 2024-01-16 23:00 |  | 2024-01-17 | 2024-01-18 23:59 |  | 2024-01-18 23:59 | Moomba WL | ADuong4 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 2 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Adel Mohammad Alhashemi | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.28 | Toolachee 16 | SANTOS LIMITED | TOOLACHEE 16 | Wild Desert Rig 16 | J.24.076770 | RPI | PS-WL-NO | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2024-03-28 | 2024-03-27 |  | 2024-03-27 | 2024-04-18 23:59 |  | 2024-04-18 23:59 | Moomba WL | ssultan | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 18201.43 | 1 |  | L3 - Full RO |  | 75 | 50 | 100 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.30 | Monte 1 | SANTOS LIMITED | MONTE 1, KURUNDA 5 | Wild Desert Rig 16 | J.24.114722 | RPI | PS-WL-NO | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-06-12 | 2024-06-07 |  | 2024-06-07 | 2024-06-09 23:59 |  | 2024-06-09 23:59 | Moomba WL | HEstrella | 2024-08-16 09:59 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 1 |  | L0 - No RO |  | 100 | 83.3 | 100 | 75 | 87.5 |  | 2 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.31 | Tantanna 13 | SANTOS LIMITED | TANTANNA 13, DARALINGIE 7 | Wild Desert Rig 16 | J.24.131315 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-07-22 15:00 | 2024-07-22 |  | 2024-07-22 15:00 | 2024-07-28 23:59 |  | 2024-07-28 23:59 | Moomba WL | ADuong4 | 2024-08-13 16:29 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 1 |  | L0 - No RO |  | 100 | 100 | 0 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.29 | Dampierre 1 casing cut | SANTOS LIMITED | DAMPIERRE 1, MONTE 1 | Wild Desert Rig 16 | J.24.101138 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-05-21 | 2024-05-20 |  | 2024-05-21 | 2024-07-06 23:59 |  | 2024-07-06 23:59 | Moomba WL | AJaved15 | 2024-08-13 16:28 | KKeese |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 1 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.24 | Dullingari 35 | SANTOS LIMITED | DULLINGARI 35 | Wild Desert Rig 16 | J.23.100090 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-10 12:00 | 2023-06-09 |  | 2023-06-10 12:00 | 2023-06-12 11:59 |  | 2023-06-12 11:59 | Moomba WL | ADuong4 | 2023-06-13 08:33 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.23 | STRZLECKI 24 USIT | SANTOS LIMITED | STRZELECKI 24 | Wild Desert Rig 16 | J.23.091911 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2023-05-28 06:00 | 2023-05-28 04:00 |  | 2023-05-28 06:00 | 2023-05-31 11:00 |  | 2023-05-31 11:00 | Moomba WL | PLima7 | 2023-05-31 08:43 | PLima7 |  | No |  |  |  |  | Mazhar Iqbal |  | 7094.02 | 3 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.17 | Marabooka 1 Tubing Cutter | SANTOS LIMITED | MARABOOKA 1 | Wild Desert Rig 16 | J.23.037809 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2023-02-11 06:00 | 2023-02-11 04:00 |  | 2023-02-11 06:00 | 2023-02-15 11:00 |  | 2023-02-15 11:00 | Moomba WL | ymoradi2 | 2023-05-27 15:31 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 7094.02 | 1 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.22 | Merrimelia 11 | SANTOS LIMITED | MERRIMELIA 11, STRZELECKI 24 | Wild Desert Rig 16 | J.23.080781 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-05-07 17:00 | 2023-05-06 |  | 2023-05-07 17:00 | 2023-05-25 16:59 |  | 2023-05-25 16:59 | Moomba WL | ADuong4 | 2023-05-27 14:53 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 14188.03 | 4 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.21 | Strzelecki 8 | SANTOS LIMITED | STRZELECKI 8 | Wild Desert Rig 16 | J.23.062404 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-04-12 06:00 | 2023-04-12 04:00 |  | 2023-04-12 06:00 | 2023-04-26 11:00 |  | 2023-04-26 11:00 | Moomba WL | PLima7 | 2023-04-26 19:14 | eismail |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 7094.02 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.20 | Marabooka 2 | SANTOS LIMITED | MARABOOKA 2 | Wild Desert Rig 16 | J.23.060388 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-03-28 18:00 | 2023-03-25 |  | 2023-03-28 18:00 | 2023-03-30 17:59 |  | 2023-03-30 17:59 | Moomba WL | ADuong4 | 2023-04-01 09:05 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 6080.58 | 1 |  | L0 - No RO |  | 91.7 | 66.7 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.19 | Marabooka 2_Cutter | SANTOS LIMITED | MARABOOKA 2 | Wild Desert Rig 16 | J.23.053647 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2023-03-07 06:00 | 2023-03-07 04:00 |  | 2023-03-07 06:00 | 2023-03-11 11:00 |  | 2023-03-11 11:00 | Moomba WL | PLima7 | 2023-03-09 08:12 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 7094.02 | 1 |  | L0 - No RO |  | 75 | 50 | 0 | 25 | 45 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.15 | Marabooka 1 | SANTOS LIMITED | MARABOOKA 1 | Wild Desert Rig 16 | J.23.029148 | RPI | PS-WL-Ops | Medium | Confirmed | Prepare - Mob |  | Design Completed | In Progress | In Progress | 2023-01-20 06:00 | 2023-01-20 04:00 |  | 2023-01-20 06:00 | 2023-03-01 11:00 |  | 2023-03-01 10:00 | Moomba WL | KKeese | 2023-02-27 17:14 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 7094.02 | 1 |  | L0 - No RO |  | 66.7 | 0 | 0 | 50 | 35 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.18 | Marabooka 1 USIT | SANTOS LIMITED | MARABOOKA 1 | Wild Desert Rig 16 | J.23.040898 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-02-19 | 2023-02-18 |  | 2023-02-19 | 2023-02-20 23:59 |  | 2023-02-20 23:59 | Moomba WL | ADuong4 | 2023-02-20 13:27 | ADuong4 |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.14 | Dulingari North 8- Tubing Cut | SANTOS LIMITED | DULLINGARI NORTH 8, STREZLECKI 17, STRZELECKI 14 | Wild Desert Rig 16 | J.22.122235 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-01 06:00 | 2022-11-01 04:00 |  | 2022-11-01 06:00 | 2023-02-01 11:00 |  | 2023-02-01 11:00 | Moomba WL | DKitney | 2023-02-12 15:34 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 14188.04 | 1 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.16 | Strrzelecki 5 SCMT | SANTOS LIMITED | STRZELECKI 5 | Wild Desert Rig 16 | J.23.030256 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Required | In Progress | 2023-01-24 06:00 | 2023-01-24 04:00 |  | 2023-01-24 06:00 | 2023-02-03 11:00 |  | 2023-02-06 | Moomba WL | YPouryan | 2023-02-10 09:50 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 7094.02 | 1 |  | L3 - Full RO |  | 75 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.13 | Dullingari 20 tubing cut | SANTOS LIMITED | Dullingari 20 | Wild Desert Rig 16 | J.22.110094 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-08-30 11:00 | 2022-08-30 09:00 |  | 2022-08-30 12:00 | 2022-08-31 09:00 |  | 2022-08-31 08:00 | Moomba WL | ymoradi2 | 2022-10-03 12:40 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 8585.8 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.12 | Kurunda 4- Split Shot | SANTOS LIMITED | Kurunda 4 | Wild Desert Rig 16 | J.21.108804 | RPI | PS-WL-NO | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-14 19:00 | 2021-12-14 18:00 |  | 2021-12-14 19:00 | 2021-12-15 16:00 |  | 2021-12-15 16:00 | Moomba WL | DKitney | 2022-10-03 11:52 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 485.99 | 0 |  |  |  | 91.7 | 66.7 | 100 | 75 | 80 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.11 | Kurunda 4 | SANTOS LIMITED | Kurunda 4 | Wild Desert Rig 16 | J.21.108800 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-12-11 12:00 | 2021-12-11 09:00 |  | 2021-12-11 12:00 | 2021-12-12 09:00 |  | 2021-12-12 09:00 | Moomba WL | KKeese | 2022-10-03 11:52 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 8585.8 | 0 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.09 | Toolachee 12 Circ Perf | SANTOS LIMITED | Toolachee 12 | Wild Desert Rig 16 | J.20.062861 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2020-11-02 12:00 | 2020-11-02 09:00 |  | 2020-11-02 12:00 | 2020-11-03 09:00 |  | 2020-11-03 09:00 | Moomba WL | DKitney | 2022-10-03 10:50 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 8585.8 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.10 | Muteroo 4-Tubing Cut | SANTOS LIMITED | MUTEROO 4 | Wild Desert Rig 16 | J.20.062841 | RPI | PS-WL-NO | Medium | Confirmed | Prepare - Mob |  | Design Completed | In Progress | In Progress | 2020-12-30 07:00 | 2020-12-30 |  | 2020-12-30 07:00 | 2021-01-01 23:59 |  | 2021-01-01 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:48 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 75 | 66.7 | 100 | 50 | 67.5 |  | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.06 | Dullingari 24 Tubing cutters | SANTOS LIMITED | Dullinagri 24 | Wild Desert Rig 16 | J.20.062834 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-07-03 01:30 | 2020-05-02 06:00 |  | 2020-07-03 12:00 | 2020-07-09 23:00 |  | 2020-07-09 12:30 | Moomba WL | SGilbert | 2022-10-03 10:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.05 | Munkarie 1 Tubing Cutter | SANTOS LIMITED | Munkarie 1 | Wild Desert Rig 16 | J.20.062833 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-04-21 06:00 | 2020-04-21 06:00 |  | 2020-04-21 07:00 | 2020-04-27 18:00 |  | 2020-04-27 17:00 | Moomba WL | SGilbert | 2022-10-03 10:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.07 | Merrimelia 43-Packer Setting TCP | SANTOS LIMITED | Merrimelia 43 | Wild Desert Rig 16 | J.20.062820 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-06-05 06:00 | 2020-06-02 |  | 2020-06-05 06:00 | 2020-06-09 05:59 |  | 2020-06-09 05:59 | Moomba WL | ymoradi2 | 2022-10-03 10:45 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  |  |  | 66.7 | 16.7 | 0 | 0 | 25 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.02 | U420 Toolachee Nth 1 PowerCutter | SANTOS LIMITED | Toolachee North 1 | Wild Desert Rig 16 | J.19.060509 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2019-10-18 16:00 | 2019-10-18 06:00 |  | 2019-10-18 16:00 | 2019-10-25 18:00 |  | 2019-10-25 18:00 | Moomba WL | JAnnear | 2022-10-03 10:44 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 11380.23 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.08 | Cooba 2 | SANTOS LIMITED | Cooba 2 | Wild Desert Rig 16 | J.20.062806 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-07-06 | 2020-07-03 |  | 2020-07-06 | 2020-07-10 23:59 |  | 2020-07-10 23:59 | Moomba WL | KKeese | 2022-10-03 10:43 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.03 | Tubing Cutter Pira 1 | SANTOS LIMITED | Pira 1 | Wild Desert Rig 16 | J.19.060501 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2019-11-16 07:00 | 2019-11-16 06:00 |  | 2019-11-16 07:00 | 2019-11-22 18:00 |  | 2019-11-22 18:00 | Moomba WL | ymoradi2 | 2022-10-03 10:41 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.01 | Dullingari 22 PowerCutter | SANTOS LIMITED | DULLINGARI 22 | Wild Desert Rig 16 | J.19.060500 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2019-10-11 | 2019-10-09 |  | 2019-10-11 | 2019-10-15 |  | 2019-10-15 | Moomba WL | JAnnear | 2022-10-03 10:41 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001689 | O.1001689.02 | A.1001689.02.04 | Dullingari North 1 Tubing cutter | SANTOS LIMITED | Dullingari North 1 | Wild Desert Rig 16 | J.20.062777 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-04-10 06:00 | 2020-04-10 06:00 |  | 2020-04-10 07:00 | 2020-04-16 18:00 |  | 2020-04-16 17:00 | Moomba WL | SGilbert | 2022-10-03 10:38 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  |  |  | 58.3 | 16.7 | 0 | 50 | 37.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.01 | A.1001689.01.13 | A.1001698.01.01 | SANTOS LIMITED | Moomba 136 | Wild Desert Rig 16 | J.21.108645 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-07-21 | 2021-07-20 | 2021-07-21 | 2021-07-21 | 2021-07-25 23:59 | 2021-07-26 | 2021-07-25 23:59 | Moomba WL | YLee25 | 2022-10-03 11:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 5590.03 | 0 |  |  |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.01 | A.1001689.01.10 | BigLake102-Rigless-TubingCutter | SANTOS LIMITED | BIG LAKE 102 | Wild Desert Rig 16 | J.20.062832 | RPI | PS-WL-Ops | Low | Confirmed | Prepare - Mob |  | In Progress | Design Completed | In Progress | 2020-03-10 16:00 | 2020-03-10 15:00 |  | 2020-03-10 16:00 | 2020-03-12 |  | 2020-03-12 | Moomba WL | ymoradi2 | 2022-10-03 10:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.01 | A.1001689.01.11 | Dullingari 24 | SANTOS LIMITED | Baryulah 4 | Wild Desert Rig 16 | J.20.062827 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-04-27 04:00 | 2020-04-27 |  | 2020-04-28 | 2020-04-30 |  | 2020-04-29 04:00 | Moomba WL | KKeese | 2022-10-03 10:46 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  |  |  | 75 | 8.3 | 0 | 0 | 25 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.01 | A.1001689.01.04 | Toolachee North 1 | SANTOS LIMITED |  | Wild Desert Rig 16 | J.19.060511 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-29 20:24 | 2019-10-29 |  | 2019-10-29 | 2019-10-31 |  | 2019-10-31 | Moomba WL | KKeese | 2022-10-03 10:45 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001689 | O.1001689.01 | A.1001689.01.12 | Merrimelia 43 | SANTOS LIMITED | Merrimelia 43 | Wild Desert Rig 16 | J.20.062819 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-06-18 08:38 | 2020-06-17 15:08 |  | 2020-06-18 08:38 | 2020-06-19 08:38 |  | 2020-06-19 08:38 | Moomba WL | DParker16 | 2022-10-03 10:45 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 3374.92 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001689 | O.1001689.01 | A.1001689.01.02 | Moomba 34 | SANTOS LIMITED | MOOMBA 34 | Wild Desert Rig 16 | J.19.060508 | RPI | PS-WL-Ops | High | Unconfirmed - 90% | Design - CEC |  | In Progress | Design Completed | In Progress | 2019-11-10 | 2019-10-03 |  | 2019-11-10 | 2019-11-13 23:00 |  | 2019-11-12 23:00 | Moomba WL | KKeese | 2022-10-03 10:44 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 7087.33 |  |  | L0 - No RO |  | 58.3 | 16.7 | 0 | 25 | 30 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001689 | O.1001689.01 | A.1001689.01.09 | BigLake102-TubingCutterTCP-Correlation | SANTOS LIMITED | BIG LAKE 102 | Wild Desert Rig 16 | J.20.062810 | RPI | PS-WL-NO | Medium | Confirmed | Execute - PSD |  | In Progress | Design Completed | In Progress | 2020-02-27 03:00 | 2020-02-28 |  | 2020-02-28 | 2020-03-04 |  | 2020-03-03 03:00 | Moomba WL | ymoradi2 | 2022-10-03 10:43 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.01 | A.1001689.01.07 | Moomba 51 | SANTOS LIMITED | Moomba51 | Wild Desert Rig 16 | J.19.060502 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2019-12-30 16:00 | 2019-12-30 12:00 |  | 2019-12-30 16:00 | 2019-12-31 13:00 |  | 2019-12-31 13:00 | Moomba WL | DParker16 | 2022-10-03 10:42 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6686.16 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001689 | O.1001689.01 | A.1001689.01.01 | Perforation & CPST | SANTOS LIMITED | Baryulah 4 | Wild Desert Rig 16 | J.19.060499 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2019-09-21 | 2019-09-21 |  | 2019-09-21 | 2019-09-24 |  | 2019-09-24 | Moomba WL | AGamero | 2022-10-03 10:41 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 580.73 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001689 | O.1001689.01 | A.1001689.01.03 | Toolachee North 1 | SANTOS LIMITED | Toolachee North 1 | Wild Desert Rig 16 | J.19.060496 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2019-10-30 | 2019-10-30 |  | 2019-10-30 | 2019-10-31 |  | 2019-10-31 | Moomba WL | KKeese | 2022-10-03 10:40 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 8336.05 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001689 | O.1001689.01 | A.1001689.01.08 | Big Lake 35 | SANTOS LIMITED | Big Lake 35 | Wild Desert Rig 16 | J.20.062784 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-01-24 10:00 | 2020-01-24 09:00 |  | 2020-01-24 10:00 | 2020-01-25 |  | 2020-01-25 | Moomba WL | ymoradi2 | 2022-10-03 10:39 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  |  |  | 66.7 | 16.7 | 0 | 0 | 25 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001689 | O.1001689.01 | A.1001689.01.05 | Napowie 1 SCMT TCP correlation | SANTOS LIMITED | Napowie 2 | Wild Desert Rig 16 | J.19.060494 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2019-12-13 07:00 | 2019-12-13 06:00 |  | 2019-12-13 07:00 | 2019-12-14 14:00 |  | 2019-12-14 14:00 | Moomba WL | ymoradi2 | 2022-10-03 10:39 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001689 | O.1001689.01 | A.1001689.01.06 | Stokes 3-Tubing Cutter-Contingent | SANTOS LIMITED | STOKES 3 | Wild Desert Rig 16 | J.19.060493 | RPI | PS-WL-Ops | High | Confirmed | Execute - PSD |  | In Progress | Design Completed | In Progress | 2019-12-25 21:00 | 2019-12-25 06:00 |  | 2019-12-25 21:00 | 2019-12-25 23:00 |  | 2019-12-27 21:00 | Moomba WL | ymoradi2 | 2022-10-03 10:38 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 58.3 | 16.7 | 0 | 25 | 30 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001688 | O.1001688.04 | A.1001688.04.27 | Coloy 2 | SANTOS LIMITED | COLOY 2 | ENSIGN 967 | J.24.058782 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2024-02-24 23:00 | 2024-02-25 02:00 |  | 2024-02-25 02:00 | 2024-02-28 01:59 |  | 2024-05-23 01:00 | Moomba WL | HChapman3 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Jakarta | Shameer Mumtaz Ali |  | 45701.3 | 2 |  | L2 - Shift RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.21 | Coloy 1 | SANTOS LIMITED | COLOY 1 | ENSIGN 967 | J.23.038912 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-03-18 22:00 | 2023-03-19 01:00 | 2023-03-18 | 2023-03-19 01:00 | 2023-03-22 00:59 | 2023-03-24 | 2023-06-15 | Moomba WL | KKeese | 2023-08-06 13:35 | JDagdag |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 45701.3 | 2 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.23 | Cuisiner 33 | SANTOS LIMITED | CUISINIER 33 | ENSIGN 967 | J.23.041189 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-13 03:00 | 2023-04-13 01:00 |  | 2023-04-13 06:00 | 2023-04-20 05:59 |  | 2023-04-20 06:59 | Moomba WL | KKeese | 2023-06-13 09:41 | DYanagawa |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 45540.68 | 2 |  | L2 - Shift RO |  | 83.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.26 | Tigon 1 | SANTOS LIMITED | TIGON 1 | ENSIGN 967 | J.23.068395 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | Design Completed | 2023-05-15 12:00 | 2023-05-15 01:00 |  | 2023-05-16 01:00 | 2023-05-23 00:59 |  | 2023-05-22 15:59 | Moomba WL | KKeese | 2023-05-17 11:18 | YPouryan |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 27087.07 | 2 |  | L3 - Full RO |  | 91.7 | 66.7 | 0 | 0 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.25 | Cuisinier 32 | SANTOS LIMITED | CUISINIER 32 | ENSIGN 967 | J.23.068394 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-04 22:00 | 2023-05-04 01:00 |  | 2023-05-05 01:00 | 2023-05-08 00:59 |  | 2023-05-08 01:59 | Moomba WL | KKeese | 2023-05-07 18:03 | eismail |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.24 | Cuisiner 34 | SANTOS LIMITED | CUISINIER 34 | ENSIGN 967 | J.23.041190 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-25 22:00 | 2023-04-25 01:00 |  | 2023-04-26 01:00 | 2023-04-29 00:59 |  | 2023-04-29 01:59 | Moomba WL | KKeese | 2023-04-26 23:31 | ASamokhin |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 27087.07 | 2 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.22 | Cuisiner 31 | SANTOS LIMITED | CUISINIER 31 | ENSIGN 967 | J.23.041188 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-03-30 22:00 | 2023-03-30 01:00 |  | 2023-03-31 01:00 | 2023-04-07 00:59 |  | 2023-04-07 00:59 | Moomba WL | KKeese | 2023-04-06 16:10 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 45701.3 | 2 |  | L2 - Shift RO |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.20 | Wackett South 2 | SANTOS LIMITED | ULANDI 17 | ENSIGN 967 | J.23.038911 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-26 22:00 | 2023-03-26 01:00 |  | 2023-03-27 01:00 | 2023-03-30 00:59 |  | 2023-03-30 01:59 | Moomba WL | KKeese | 2023-03-17 06:39 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.19 | Maya 2 | SANTOS LIMITED | MAYA 2 | ENSIGN 967 | J.23.027210 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-02-24 22:00 | 2023-02-25 01:00 |  | 2023-02-25 01:00 | 2023-03-04 00:59 |  | 2023-03-04 01:59 | Moomba WL | KKeese | 2023-03-01 16:16 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 45701.3 | 2 |  | L3 - Full RO |  | 91.7 | 58.3 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.18 | Dampierre 1 | SANTOS LIMITED | DAMPIERRE 1 | ENSIGN 967 | J.23.027209 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-02-11 05:00 | 2023-02-11 01:00 |  | 2023-02-11 08:00 | 2023-02-14 07:59 |  | 2023-02-14 08:59 | Moomba WL | KKeese | 2023-02-16 15:29 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 45701.3 | 2 |  | L3 - Full RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.17 | Indigo 1 | SANTOS LIMITED | INDIGO 1 | ENSIGN 967 | J.23.027208 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-01-30 22:00 | 2023-01-30 01:00 |  | 2023-01-31 01:00 | 2023-02-03 00:59 |  | 2023-02-03 01:59 | Moomba WL | KKeese | 2023-02-13 21:24 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 3 |  | L3 - Full RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.16 | Tequila 2 | SANTOS LIMITED | TEQUILA 2 | ENSIGN 967 | J.23.022165 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-01-16 15:00 | 2023-01-15 01:00 |  | 2023-01-16 17:00 | 2023-01-19 16:59 |  | 2023-01-19 14:59 | Moomba WL | KKeese | 2023-01-21 11:17 | YPouryan |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 3 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.15 | Minos 4 | SANTOS LIMITED | MINOS 4 | ENSIGN 967 | J.23.018732 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-01-06 23:00 | 2023-01-04 01:00 |  | 2023-01-07 01:00 | 2023-01-10 00:59 |  | 2023-01-09 22:59 | Moomba WL | KKeese | 2023-01-11 14:48 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L2 - Shift RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.14 | Zeus 15 | SANTOS LIMITED | ULANDI 17, ZEUS 15 | ENSIGN 967 | J.22.127953 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-12-30 23:00 | 2022-12-30 01:00 |  | 2022-12-31 01:00 | 2023-01-03 00:59 |  | 2023-01-02 22:59 | Moomba WL | KKeese | 2023-01-03 11:11 | JDagdag |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.13 | Zeus 14 | SANTOS LIMITED | ZEUS 14 | ENSIGN 967 | J.22.127952 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-12-26 12:00 | 2022-12-26 06:00 |  | 2022-12-26 14:00 | 2022-12-29 13:59 |  | 2022-12-29 11:59 | Moomba WL | KKeese | 2022-12-26 14:09 | eismail |  | No |  |  |  |  | Mazhar Iqbal |  | 42962.9 | 2 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.12 | Zeus 13 | SANTOS LIMITED | ZEUS 13 | ENSIGN 967 | J.22.127951 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-12-16 15:00 | 2022-12-11 01:00 |  | 2022-12-16 17:00 | 2022-12-21 16:59 |  | 2022-12-21 14:59 | Moomba WL | KKeese | 2022-12-18 15:07 | YPouryan |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L2 - Shift RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.11 | Tennaperra 11 | SANTOS LIMITED | TENNAPERRA 11 | ENSIGN 967 | J.22.127950 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-12-07 23:00 | 2022-12-07 01:00 |  | 2022-12-08 01:00 | 2022-12-11 00:59 |  | 2022-12-10 22:59 | Moomba WL | KKeese | 2022-12-17 16:13 | eismail |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO | [7 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.10 | Alwyn 9 | SANTOS LIMITED | ULANDI 17, ALWYN 9 | ENSIGN 967 | J.22.127949 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-26 23:00 | 2022-11-26 01:00 |  | 2022-11-27 01:00 | 2022-11-30 00:59 |  | 2022-11-29 22:59 | Moomba WL | KKeese | 2022-12-03 08:23 | YPouryan |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.08 | Isoptera 6 | SANTOS LIMITED | ISOPTERA 6 | ENSIGN 967 | J.22.127029 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-15 23:00 | 2022-11-15 01:00 |  | 2022-11-16 01:00 | 2022-11-19 00:59 |  | 2022-11-18 22:59 | Moomba WL | NBortkevich | 2022-12-01 17:48 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.09 | Ulandi 17 | SANTOS LIMITED | ULANDI 17 | ENSIGN 967 | J.22.127942 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-19 23:00 | 2022-11-19 01:00 |  | 2022-11-20 01:00 | 2022-11-23 00:59 |  | 2022-11-22 22:59 | Moomba WL | KKeese | 2022-11-24 08:43 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  |  |  | 75 | 66.7 | 0 | 50 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.07 | Isoptera 7 | SANTOS LIMITED | ISOPTERA 7 | ENSIGN 967 | J.22.126218 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-11-12 |  | 2022-11-13 | 2022-11-15 23:59 |  |  | Moomba WL | KKeese | 2022-11-16 21:10 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 77175.16 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.06 | Bugito 4 | SANTOS LIMITED | BUGITO 4 | ENSIGN 967 | J.22.125997 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-10-31 22:00 |  | 2022-11-05 22:00 | 2022-11-08 21:59 |  |  | Moomba WL | eismail | 2022-11-11 07:50 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  |  |  | 66.7 | 66.7 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.05 | Isoptera 4 | SANTOS LIMITED | ISOPTERA 4 | ENSIGN 967 | J.22.121296 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-10-26 |  | 2022-10-31 | 2022-11-07 23:59 |  |  | Moomba WL | YPouryan | 2022-11-02 15:08 | YPouryan |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  |  |  | 66.7 | 66.7 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.04 | Isoptera 5 QC-XPT | SANTOS LIMITED | ISOPTERA 5 | ENSIGN 967 | J.22.119766 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-10-23 |  | 2022-10-25 | 2022-10-25 00:30 |  |  | Moomba WL | YPouryan | 2022-10-27 13:48 | YPouryan |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.02 | Wallace 2_QC_XPT | SANTOS LIMITED | WALLACE 2 | ENSIGN 967 | J.22.115007 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-10-12 |  | 2022-10-12 | 2022-10-19 23:59 |  |  | Moomba WL | YPouryan | 2022-10-19 09:02 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.03 | Quadcombo XPT | SANTOS LIMITED | SECCANTE 9 | ENSIGN 967 | J.22.115406 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-10-17 |  | 2022-10-17 | 2022-10-18 23:59 |  |  | Moomba WL | PLima7 | 2022-10-18 06:34 | PLima7 |  | No |  |  |  |  | Mazhar Iqbal |  | 40805.72 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.04 | A.1001688.04.01 | Seccante 8_QC_XPT | SANTOS LIMITED | SECCANTE 8 | ENSIGN 967 | J.22.114985 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-10-11 10:00 |  | 2022-10-11 12:00 | 2022-10-12 23:59 |  |  | Moomba WL | MAlhashemi | 2022-10-11 07:20 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 128888.7 | 2 |  |  |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.95 | Bugito 5 | SANTOS LIMITED |  | ENSIGN 967 | J.24.120526 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-06-22 21:00 | 2024-06-22 |  | 2024-06-23 | 2024-06-25 23:59 |  | 2024-06-26 00:59 | Moomba WL | SMccauley | 2024-06-26 14:55 | KKeese |  | No |  |  |  | ROE WL Abu Dhabi | Elsamawal Mohamedelhassan Awadalla Ismail |  | 0 | 2 |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.86 | Tenaperra 11 | SANTOS LIMITED |  | ENSIGN 967 | J.22.110025 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-12-09 |  | 2022-12-09 | 2022-12-11 23:59 |  |  | Moomba WL | KKeese | 2022-11-19 10:20 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.93 | Minos 4 | SANTOS LIMITED |  | ENSIGN 967 | J.23.011745 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2023-01-09 |  | 2023-01-09 | 2023-01-11 23:59 |  |  | Moomba WL | KKeese | 2022-11-18 06:11 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.92 | Zeus 15 | SANTOS LIMITED |  | ENSIGN 967 | J.22.121238 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2023-01-01 |  | 2023-01-01 | 2023-01-03 23:59 |  |  | Moomba WL | KKeese | 2022-11-18 06:11 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.91 | Zeus 14 | SANTOS LIMITED |  | ENSIGN 967 | J.22.121230 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-12-25 |  | 2022-12-25 | 2022-12-27 23:59 |  |  | Moomba WL | KKeese | 2022-11-18 06:11 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.87 | Zeus 13 | SANTOS LIMITED |  | ENSIGN 967 | J.22.110026 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-12-17 |  | 2022-12-17 | 2022-12-19 23:59 |  |  | Moomba WL | KKeese | 2022-11-18 06:11 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.94 | Isoptera 6 | SANTOS LIMITED |  | ENSIGN 967 | J.22.121239 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-11-16 |  | 2022-11-16 | 2022-11-18 23:59 |  |  | Moomba WL | KKeese | 2022-11-18 06:11 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.85 | Alwyn 9 | SANTOS LIMITED |  | ENSIGN 967 | J.22.110024 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-11-26 |  | 2022-11-26 | 2022-11-28 23:59 |  |  | Moomba WL | KKeese | 2022-11-18 06:11 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.84 | Ulandi 17 | SANTOS LIMITED |  | ENSIGN 967 | J.22.110023 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-11-21 |  | 2022-11-21 | 2022-11-23 23:59 |  |  | Moomba WL | KKeese | 2022-11-18 06:11 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.83 | Isoptera 7 | SANTOS LIMITED |  | ENSIGN 967 | J.22.110022 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2022-11-10 21:00 | 2022-11-10 |  | 2022-11-11 | 2022-11-13 23:59 |  | 2022-11-14 00:59 | Moomba WL | KKeese | 2022-11-10 09:29 | eismail |  | No |  |  |  | ROE WL Abu Dhabi | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 66.7 | 83.3 | 0 | 0 | 45 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.82 | Bugito 4 | SANTOS LIMITED |  | ENSIGN 967 | J.22.110021 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-11-05 |  | 2022-11-05 | 2022-11-07 23:59 |  |  | Moomba WL | KKeese | 2022-11-05 22:02 | eismail |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.81 | Isoptera 4 | SANTOS LIMITED |  | ENSIGN 967 | J.22.110020 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-10-31 |  | 2022-10-31 | 2022-11-02 23:59 |  |  | Moomba WL | KKeese | 2022-10-30 11:12 | eismail |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.90 | Isoptera 5 QC-XPT | SANTOS LIMITED |  | ENSIGN 967 | J.22.119760 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2022-10-22 |  | 2022-10-23 | 2022-10-24 23:59 |  |  | Moomba WL | YPouryan | 2022-10-27 08:27 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 0 |  | L2 - Shift RO | [7 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.78 | Isoptera 5 | SANTOS LIMITED |  | ENSIGN 967 | J.22.110017 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-10-22 |  | 2022-10-23 | 2022-10-31 23:59 |  |  | Moomba WL | KKeese | 2022-10-27 08:22 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.76 | Seccante 8 | SANTOS LIMITED |  | ENSIGN 967 | J.22.110015 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2022-10-07 22:00 | 2022-10-08 |  | 2022-10-08 | 2022-10-12 23:59 |  | 2022-10-13 00:59 | Moomba WL | KKeese | 2022-10-08 16:30 | MAlhashemi |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L2 - Shift RO |  | 75 | 83.3 | 0 | 0 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.77 | Rango 4 | SANTOS LIMITED | RAGNO 4 | ENSIGN 967 | J.22.110016 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-10-02 10:00 |  | 2022-10-02 14:00 | 2022-10-03 13:59 |  |  | Moomba WL | KKeese | 2022-10-08 16:27 | MAlhashemi |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 42962.9 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.89 | Ragno 3 | SANTOS LIMITED | Ragno 3 | ENSIGN 967 | J.22.110097 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-09-26 22:00 | 2022-09-07 |  | 2022-09-26 | 2022-09-30 23:59 |  | 2022-09-30 21:59 | Moomba WL | eismail | 2022-10-03 12:40 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 42388.98 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.88 | Nungeroo West 1 | SANTOS LIMITED | Nungeroo West 1 | ENSIGN 967 | J.22.110090 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-08-27 | 2022-08-27 |  | 2022-08-27 | 2022-08-30 23:59 |  | 2022-08-30 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 12:39 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  |  |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.80 | Bugito 4 | SANTOS LIMITED |  | ENSIGN 967 | J.22.110019 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-10-20 21:00 | 2022-10-21 |  | 2022-10-21 | 2022-10-23 23:59 |  | 2022-10-24 00:59 | Moomba WL | KKeese | 2022-10-03 12:32 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.79 | Isoptera 4 | SANTOS LIMITED |  | ENSIGN 967 | J.22.110018 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-10-10 21:00 | 2022-10-11 |  | 2022-10-11 | 2022-10-13 23:59 |  | 2022-10-14 00:59 | Moomba WL | KKeese | 2022-10-03 12:32 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.75 | Wallace 2 | SANTOS LIMITED |  | ENSIGN 967 | J.22.110014 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-09-22 22:00 | 2022-09-23 |  | 2022-09-25 | 2022-09-27 23:59 |  | 2022-09-28 01:59 | Moomba WL | KKeese | 2022-10-03 12:32 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.74 | Narcoonowie 11 quadcombo,XPT | SANTOS LIMITED | Narcoonowie 11 | ENSIGN 967 | J.22.109959 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-07-27 19:30 | 2022-07-22 |  | 2022-07-27 19:30 | 2022-08-05 19:29 |  | 2022-08-05 19:29 | Moomba WL | YPouryan | 2022-10-03 12:26 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.73 | Cooroo North West 7 | SANTOS LIMITED | Cooroo North West 7 | ENSIGN 967 | J.22.109951 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-07-02 | 2022-07-01 |  | 2022-07-02 | 2022-07-07 23:59 |  | 2022-07-07 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 12:26 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.72 | Barrolka 26 | SANTOS LIMITED | Barrolka 26 | ENSIGN 967 | J.22.109934 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-06-06 | 2022-06-06 |  | 2022-06-06 | 2022-06-10 23:59 |  | 2022-06-10 23:59 | Moomba WL | YLee25 | 2022-10-03 12:24 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 68660.7 | 4 |  |  |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.71 | QC/XPT Q3 Well 12 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109917 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-09-20 22:00 | 2022-09-21 |  | 2022-09-21 | 2022-09-25 23:59 |  | 2022-09-26 01:59 | Moomba WL | KKeese | 2022-10-03 12:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.70 | QC/XPT Q3 Well 11 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109916 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-09-15 22:00 | 2022-09-16 |  | 2022-09-16 | 2022-09-20 23:59 |  | 2022-09-21 01:59 | Moomba WL | KKeese | 2022-10-03 12:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.69 | Jena 29 | SANTOS LIMITED | Jena 029 | ENSIGN 967 | J.22.109915 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-09-14 18:00 | 2022-09-11 |  | 2022-09-14 20:00 | 2022-09-22 19:59 |  | 2022-09-22 17:59 | Moomba WL | KKeese | 2022-10-03 12:22 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 43254.06 | 2 |  |  |  | 66.7 | 33.3 | 0 | 75 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.68 | Ragno 2 | SANTOS LIMITED | Ragno 002 | ENSIGN 967 | J.22.109914 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-09-20 22:00 | 2022-09-02 |  | 2022-09-21 | 2022-09-25 23:59 |  | 2022-09-25 21:59 | Moomba WL | KKeese | 2022-10-03 12:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 42388.98 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.67 | QC/XPT Q3 Well 8 | SANTOS LIMITED | Odonata 3 | ENSIGN 967 | J.22.109913 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-09-06 22:00 | 2022-09-06 |  | 2022-09-07 | 2022-09-11 23:59 |  | 2022-09-11 21:59 | Moomba WL | KKeese | 2022-10-03 12:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 43254.06 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.66 | QC/XPT Q3 Well 7 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109912 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-08-21 22:00 | 2022-08-22 |  | 2022-08-22 | 2022-08-26 23:59 |  | 2022-08-27 01:59 | Moomba WL | KKeese | 2022-10-03 12:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.65 | QC/XPT Q3 Well 6 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109911 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-08-15 22:00 | 2022-08-16 |  | 2022-08-16 | 2022-08-20 23:59 |  | 2022-08-21 01:59 | Moomba WL | KKeese | 2022-10-03 12:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.64 | Narcoonowie 13_QC/XPT | SANTOS LIMITED | NARCOONOWIE 013 | ENSIGN 967 | J.22.109909 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2022-08-15 22:00 | 2022-08-16 |  | 2022-08-16 | 2022-08-20 23:59 |  | 2022-08-20 23:59 | Moomba WL | KKeese | 2022-10-03 12:22 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L2 - Shift RO |  | 66.7 | 83.3 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.63 | Narcoonowie 12- Quad Combo/XPT | SANTOS LIMITED | Narcoonowie 12 | ENSIGN 967 | J.22.109908 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-08-06 10:00 | 2022-08-06 06:00 |  | 2022-08-06 12:00 | 2022-08-11 11:59 |  | 2022-08-11 09:59 | Moomba WL | KKeese | 2022-10-03 12:22 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  |  |  | 75 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.62 | QC/XPT Q3 Well 3 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109907 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-07-16 22:00 | 2022-07-17 |  | 2022-07-17 | 2022-07-21 23:59 |  | 2022-07-22 01:59 | Moomba WL | KKeese | 2022-10-03 12:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.61 | QC/XPT Q3 Well 2 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109906 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-07-05 22:00 | 2022-07-06 |  | 2022-07-06 | 2022-07-10 23:59 |  | 2022-07-11 01:59 | Moomba WL | KKeese | 2022-10-03 12:21 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.60 | QC Q3 Well 1 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109905 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-06-24 22:00 | 2022-06-25 |  | 2022-06-25 | 2022-06-29 23:59 |  | 2022-06-30 01:59 | Moomba WL | KKeese | 2022-10-03 12:21 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.59 | Bolah 10 | SANTOS LIMITED | Bolah 10 | ENSIGN 967 | J.22.109807 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-05-04 | 2022-05-02 18:00 |  | 2022-05-03 18:00 | 2022-05-07 17:59 |  | 2022-05-07 23:59 | Moomba WL | eismail | 2022-10-03 12:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.58 | Bolah 9 | SANTOS LIMITED | Bolah 9 | ENSIGN 967 | J.22.109797 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-04-13 | 2022-04-12 |  | 2022-04-13 | 2022-04-16 23:59 |  | 2022-04-16 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 12:10 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.57 | Bolah 8 | SANTOS LIMITED | Bolah 8 | ENSIGN 967 | J.22.109785 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-03-29 | 2022-03-28 |  | 2022-03-29 | 2022-04-02 23:59 |  | 2022-04-02 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 12:09 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.56 | Santos OH Logging # 24 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109651 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-06-18 22:00 | 2022-06-19 |  | 2022-06-19 | 2022-06-23 23:59 |  | 2022-06-24 01:59 | Moomba WL | KKeese | 2022-10-03 11:57 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.55 | Santos OH Logging # 23 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109650 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-06-08 22:00 | 2022-06-09 |  | 2022-06-09 | 2022-06-13 23:59 |  | 2022-06-14 01:59 | Moomba WL | KKeese | 2022-10-03 11:56 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.54 | Santos OH Logging #22 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109649 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-05-30 22:00 | 2022-05-31 |  | 2022-05-31 | 2022-06-04 23:59 |  | 2022-06-05 01:59 | Moomba WL | KKeese | 2022-10-03 11:56 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.53 | Barrolka 25 | SANTOS LIMITED | Barrolka 25 | ENSIGN 967 | J.22.109648 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-05-17 22:00 | 2022-05-18 |  | 2022-05-18 | 2022-05-23 23:59 |  | 2022-05-23 21:59 | Moomba WL | KKeese | 2022-10-03 11:56 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 68660.7 | 3 |  |  |  | 66.7 | 83.3 | 0 | 50 | 60 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.52 | Santos OH Logging # 20 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109647 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-05-04 22:00 | 2022-05-05 |  | 2022-05-05 | 2022-05-09 23:59 |  | 2022-05-10 01:59 | Moomba WL | KKeese | 2022-10-03 11:56 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.51 | Santos OH Logging #19 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109646 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-04-24 22:00 | 2022-04-25 |  | 2022-04-25 | 2022-04-29 23:59 |  | 2022-04-30 01:59 | Moomba WL | KKeese | 2022-10-03 11:56 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.50 | Santos OH Logging | SANTOS LIMITED |  | ENSIGN 967 | J.22.109645 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-04-15 22:00 | 2022-04-16 |  | 2022-04-16 | 2022-04-20 23:59 |  | 2022-04-21 01:59 | Moomba WL | KKeese | 2022-10-03 11:56 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.49 | Santos OH Logging # 17 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109644 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-04-06 22:00 | 2022-04-07 |  | 2022-04-07 | 2022-04-11 23:59 |  | 2022-04-12 01:59 | Moomba WL | KKeese | 2022-10-03 11:56 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.48 | Pelican 14 | SANTOS LIMITED | Pelican 14 | ENSIGN 967 | J.22.109630 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-02-21 | 2022-02-21 |  | 2022-02-21 | 2022-02-26 23:59 |  | 2022-02-26 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 11:55 | FDPSystemUser |  | No |  |  |  | ROE WL Jakarta | Rob Twigg |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.47 | Santos OH Logging #16 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109604 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-03-17 23:00 | 2022-03-18 |  | 2022-03-18 | 2022-03-22 23:59 |  | 2022-03-23 00:59 | Moomba WL | IWahbi | 2022-10-03 11:50 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.46 | Santos OH Logging #15 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109603 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-03-12 23:00 | 2022-03-13 |  | 2022-03-13 | 2022-03-17 23:59 |  | 2022-03-18 00:59 | Moomba WL | IWahbi | 2022-10-03 11:49 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.45 | Santos OH Logging #14 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109602 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-03-07 23:00 | 2022-03-08 |  | 2022-03-08 | 2022-03-12 23:59 |  | 2022-03-13 00:59 | Moomba WL | IWahbi | 2022-10-03 11:49 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.44 | Santos OH Logging #13 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109601 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-03-02 23:00 | 2022-03-03 |  | 2022-03-03 | 2022-03-07 23:59 |  | 2022-03-08 00:59 | Moomba WL | IWahbi | 2022-10-03 11:49 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.43 | Meranji 24_QC, XPT | SANTOS LIMITED | Meranji 24 | ENSIGN 967 | J.22.109600 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-03-07 23:00 | 2022-03-08 |  | 2022-03-08 | 2022-03-12 23:59 |  | 2022-03-12 22:59 | Moomba WL | IWahbi | 2022-10-03 11:49 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.42 | Santos OH Logging #11 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109599 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-02-20 23:00 | 2022-02-21 |  | 2022-02-21 | 2022-02-25 23:59 |  | 2022-02-26 00:59 | Moomba WL | IWahbi | 2022-10-03 11:49 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.41 | Santos OH Logging #10 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109598 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-02-15 23:00 | 2022-02-16 |  | 2022-02-16 | 2022-02-20 23:59 |  | 2022-02-21 00:59 | Moomba WL | IWahbi | 2022-10-03 11:49 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.40 | Santos OH Logging #9 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109597 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-02-10 23:00 | 2022-02-11 |  | 2022-02-11 | 2022-02-15 23:59 |  | 2022-02-16 00:59 | Moomba WL | IWahbi | 2022-10-03 11:49 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.39 | Santos OH Logging #8 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109596 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-02-05 23:00 | 2022-02-06 |  | 2022-02-06 | 2022-02-10 23:59 |  | 2022-02-11 00:59 | Moomba WL | IWahbi | 2022-10-03 11:49 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.38 | Santos OH Logging #7 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109595 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-01-31 23:00 | 2022-02-01 |  | 2022-02-01 | 2022-02-05 23:59 |  | 2022-02-06 00:59 | Moomba WL | IWahbi | 2022-10-03 11:49 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.37 | Santos OH Logging #6 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109594 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-01-26 23:00 | 2022-01-27 |  | 2022-01-27 | 2022-01-31 23:59 |  | 2022-02-01 00:59 | Moomba WL | IWahbi | 2022-10-03 11:49 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.36 | Santos OH Logging #5 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109593 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-01-21 23:00 | 2022-01-22 |  | 2022-01-22 | 2022-01-26 23:59 |  | 2022-01-27 00:59 | Moomba WL | IWahbi | 2022-10-03 11:49 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.35 | Santos OH Logging #4 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109592 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-01-16 23:00 | 2022-01-17 |  | 2022-01-17 | 2022-01-21 23:59 |  | 2022-01-27 23:00 | Moomba WL | IWahbi | 2022-10-03 11:49 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.34 | Santos OH Logging #3 | SANTOS LIMITED |  | ENSIGN 967 | J.22.109591 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-01-11 23:00 | 2022-01-12 |  | 2022-01-12 | 2022-01-16 23:59 |  | 2022-01-17 00:59 | Moomba WL | IWahbi | 2022-10-03 11:48 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.33 | Hector South East 2 QC/MDT-Sampling | SANTOS LIMITED | Hector South East 2 | ENSIGN 967 | J.22.109590 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-06-24 09:00 | 2022-06-24 08:00 |  | 2022-06-24 10:00 | 2022-06-29 09:59 |  | 2022-06-29 08:59 | Moomba WL | IWahbi | 2022-10-03 11:48 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  |  |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.32 | Kappa 2 | SANTOS LIMITED | Kappa 2 | ENSIGN 967 | J.22.109589 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-01-15 12:00 | 2022-01-15 |  | 2022-01-15 13:00 | 2022-01-20 12:59 |  | 2022-01-20 11:59 | Moomba WL | IWahbi | 2022-10-03 11:48 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 44211.44 | 2 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.31 | Chimera 1 | SANTOS LIMITED |  | ENSIGN 967 | J.21.108782 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress | 2021-11-05 | 2021-11-05 | 2021-11-05 | 2021-11-05 | 2021-11-11 23:59 | 2021-11-12 | 2021-11-11 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 11:41 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | 2 |  | L1 - Support RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.30 | Merlin 1 | SANTOS LIMITED |  | ENSIGN 967 | J.21.108748 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2021-09-26 | 2021-09-23 | 2021-09-26 | 2021-09-26 | 2021-09-29 23:59 | 2021-09-30 | 2021-09-29 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.29 | Vega 8 | SANTOS LIMITED |  | ENSIGN 967 | J.21.108733 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2021-12-23 23:00 | 2021-12-24 | 2021-12-24 | 2021-12-24 | 2021-12-28 23:59 | 2021-12-29 | 2021-12-29 00:59 | Moomba WL | IWahbi | 2022-10-03 11:33 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.28 | Chef 1 | SANTOS LIMITED | Chef 1 | ENSIGN 967 | J.21.108732 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-12-25 23:00 | 2021-12-25 | 2021-12-25 | 2021-12-26 | 2021-12-30 23:59 | 2021-12-31 | 2021-12-30 22:59 | Moomba WL | IWahbi | 2022-10-03 11:33 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  |  |  | 83.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.27 | Cook East 1 | SANTOS LIMITED | Cook East 1 | ENSIGN 967 | J.21.108731 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-12-12 23:00 | 2021-12-12 | 2021-12-09 13:00 | 2021-12-13 | 2021-12-18 23:59 | 2021-12-19 | 2021-12-18 22:59 | Moomba WL | IWahbi | 2022-10-03 11:33 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | 0 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.26 | Llama 1 | SANTOS LIMITED | Llama 1 | ENSIGN 967 | J.21.108730 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-10-26 23:00 | 2021-10-22 | 2021-10-27 | 2021-10-27 | 2021-10-31 23:59 | 2021-11-15 | 2021-10-31 22:59 | Moomba WL | IWahbi | 2022-10-03 11:33 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 37964.65 | 0 |  |  |  | 75 | 33.3 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.25 | Kanook South 1 | SANTOS LIMITED | Kanook South 1 | ENSIGN 967 | J.21.108729 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-11-23 23:00 | 2021-10-29 | 2021-11-23 | 2021-11-23 | 2021-11-27 23:59 | 2021-12-23 | 2021-12-01 23:00 | Moomba WL | IWahbi | 2022-10-03 11:33 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 48995.54 | 2 |  |  |  | 75 | 33.3 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.24 | Chimera 1 | SANTOS LIMITED | Chimera 1 | ENSIGN 967 | J.21.108728 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-11-05 23:00 | 2021-11-06 | 2021-11-05 13:00 | 2021-11-06 | 2021-11-12 23:59 | 2021-11-13 | 2021-11-12 22:59 | Moomba WL | IWahbi | 2022-10-03 11:33 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | 0 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.23 | Legbar 1 | SANTOS LIMITED | Legbar 1 | ENSIGN 967 | J.21.108727 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-10-13 11:00 | 2021-10-13 | 2021-10-12 | 2021-10-13 12:00 | 2021-10-18 11:59 | 2021-10-18 | 2021-10-18 10:59 | Moomba WL | IWahbi | 2022-10-03 11:33 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 44211.44 | 0 |  |  |  | 75 | 33.3 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.22 | Merlin 1 | SANTOS LIMITED | Merlin 1 | ENSIGN 967 | J.21.108726 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-09-25 22:00 | 2021-09-23 | 2021-09-25 23:00 | 2021-09-26 | 2021-09-30 23:59 | 2021-10-01 | 2021-09-30 21:59 | Moomba WL | IWahbi | 2022-10-03 11:33 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 44211.44 | 0 |  |  |  | 66.7 | 33.3 | 0 | 75 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.21 | Cherokee 2 | SANTOS LIMITED | Cherokee 2 | ENSIGN 967 | J.21.108663 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-08-26 22:00 | 2021-08-26 21:00 | 2021-08-26 | 2021-08-26 22:00 | 2021-08-31 23:59 | 2021-09-01 | 2021-08-31 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 11:27 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.20 | Cherokee 3 | SANTOS LIMITED | Cherokee 3 | ENSIGN 967 | J.21.108657 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-08-13 | 2021-08-13 | 2021-08-13 | 2021-08-13 | 2021-08-17 23:59 | 2021-08-24 | 2021-08-17 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 11:26 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | 2 |  |  |  | 83.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.19 | Leghorn 2 | SANTOS LIMITED | Leghorn 2 | ENSIGN 967 | J.21.108653 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-08-02 07:00 | 2021-08-01 15:00 | 2021-08-02 | 2021-08-02 08:00 | 2021-08-06 07:59 | 2021-08-07 | 2021-08-07 06:59 | Moomba WL | KKeese | 2022-10-03 11:26 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 42388.98 | 2 |  |  |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.18 | Quad Combo + XPT | SANTOS LIMITED | Boongala 3 | ENSIGN 967 | J.21.108638 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-06-30 23:00 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 2021-07-03 23:59 | 2021-07-05 | 2021-07-04 22:59 | Moomba WL | ADuong4 | 2022-10-03 11:25 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 42388.98 | 2 |  |  |  | 66.7 | 33.3 | 0 | 75 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.17 | Bearcat 2 | SANTOS LIMITED | BEARCAT 2 | ENSIGN 967 | J.21.108555 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-09-06 23:00 | 2021-09-07 | 2021-09-07 | 2021-09-07 | 2021-09-16 23:59 | 2021-09-29 | 2021-09-16 22:59 | Moomba WL | IWahbi | 2022-10-03 11:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 44211.44 | 0 |  |  |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.16 | Legbar 1 | SANTOS LIMITED |  | ENSIGN 967 | J.21.108554 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2021-09-18 23:00 | 2021-09-19 | 2021-09-19 | 2021-09-19 | 2021-09-23 23:59 | 2021-09-24 | 2021-09-23 22:59 | Moomba WL | IWahbi | 2022-10-03 11:17 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.15 | Llama 1 | SANTOS LIMITED |  | ENSIGN 967 | J.21.108553 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2021-09-06 23:00 | 2021-09-07 | 2021-09-07 | 2021-09-07 | 2021-09-11 23:59 | 2021-09-12 | 2021-09-11 22:59 | Moomba WL | IWahbi | 2022-10-03 11:17 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.14 | Merlin 1 | SANTOS LIMITED |  | ENSIGN 967 | J.21.108552 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2021-08-25 23:00 | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-08-30 23:59 | 2021-08-31 | 2021-08-30 22:59 | Moomba WL | IWahbi | 2022-10-03 11:17 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.13 | Cherooke 2 | SANTOS LIMITED |  | ENSIGN 967 | J.21.108551 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-08-13 23:00 | 2021-08-14 | 2021-08-14 | 2021-08-14 | 2021-08-18 23:59 | 2021-08-19 | 2021-08-18 22:59 | Moomba WL | IWahbi | 2022-10-03 11:17 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.12 | Bolah 5- QC/XPT | SANTOS LIMITED | Bolah 5 | ENSIGN 967 | J.21.108405 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-02-14 12:00 | 2021-02-15 06:00 |  | 2021-02-15 06:00 | 2021-02-20 05:59 |  | 2021-02-19 11:59 | Moomba WL | DKitney | 2022-10-03 10:46 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 49354.68 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.11 | Bolah 7 | SANTOS LIMITED | Bolah 7 | ENSIGN 967 | J.21.108404 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-01-30 12:00 | 2021-01-30 12:00 |  | 2021-01-30 12:00 | 2021-02-04 11:59 |  | 2021-02-04 11:59 | Moomba WL | AHermawan | 2022-10-03 10:45 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 44211.44 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.10 | Cherokee 3 | SANTOS LIMITED |  | ENSIGN 967 | J.21.108403 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2021-08-02 23:00 | 2021-08-03 |  | 2021-08-03 | 2021-08-07 23:59 |  | 2021-08-07 22:59 | Moomba WL | OBass | 2022-10-03 10:44 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.09 | Leghorn 2 | SANTOS LIMITED |  | ENSIGN 967 | J.21.108402 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2021-07-22 23:00 | 2021-07-23 |  | 2021-07-23 | 2021-07-27 23:59 |  | 2021-07-27 22:59 | Moomba WL | OBass | 2022-10-03 10:44 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.04 | Anna North 4 | SANTOS LIMITED | Anna North 4 | ENSIGN 967 | J.21.108401 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-04-20 23:00 | 2021-04-20 23:00 |  | 2021-04-20 23:00 | 2021-04-25 22:59 |  | 2021-04-26 22:59 | Moomba WL | OBass | 2022-10-03 10:44 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 44211.44 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.02 | Anna North 2 | SANTOS LIMITED | Anna North 2 | ENSIGN 967 | J.21.108400 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-03-22 | 2021-03-20 18:00 |  | 2021-03-22 | 2021-03-24 23:59 |  | 2021-03-27 23:59 | Moomba WL | OBass | 2022-10-03 10:43 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 44211.44 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.07 | Dilchee 5 | SANTOS LIMITED | Dilchee 5 | ENSIGN 967 | J.21.108399 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-06-17 23:00 | 2021-06-17 |  | 2021-06-17 | 2021-06-21 23:59 |  | 2021-06-21 22:59 | Moomba WL | OBass | 2022-10-03 10:43 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 44211.44 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.01 | Annabella 1 | SANTOS LIMITED | Annabella 1 | ENSIGN 967 | J.21.108398 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-03-07 18:00 | 2021-03-05 18:00 |  | 2021-03-07 18:00 | 2021-03-12 17:59 |  | 2021-03-12 17:59 | Moomba WL | OBass | 2022-10-03 10:43 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 44211.44 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.03 | Anna North 3 | SANTOS LIMITED | Anna North 3 | ENSIGN 967 | J.21.108397 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-04-06 06:00 | 2021-04-05 17:00 |  | 2021-04-06 06:00 | 2021-04-11 05:59 |  | 2021-04-12 05:59 | Moomba WL | OBass | 2022-10-03 10:41 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 44211.44 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.05 | Viper (NFE A) | SANTOS LIMITED | Viper 1 | ENSIGN 967 | J.21.108395 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-06-01 11:00 | 2021-05-30 |  | 2021-06-01 12:00 | 2021-06-06 11:59 |  | 2021-06-07 10:59 | Moomba WL | OBass | 2022-10-03 10:41 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 135435.66 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.08 | Boongala 3 | SANTOS LIMITED |  | ENSIGN 967 | J.21.108394 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-06-29 23:00 | 2021-06-30 |  | 2021-06-30 | 2021-07-04 23:59 |  | 2021-07-04 22:59 | Moomba WL | OBass | 2022-10-03 10:41 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.03 | A.1001688.03.06 | Houby (NFE A) | SANTOS LIMITED | Houby 1 | ENSIGN 967 | J.21.108393 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-05-14 23:00 | 2021-05-15 |  | 2021-05-15 | 2021-05-19 23:59 |  | 2021-05-20 22:59 | Moomba WL | OBass | 2022-10-03 10:39 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 44211.44 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.02 | A.1001688.02.01 | Amyema 2- CBL | SANTOS LIMITED | Amyema 2 | ENSIGN 967 | J.20.062801 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2020-12-03 07:00 | 2020-12-01 06:00 |  | 2020-12-03 07:00 | 2020-12-03 18:00 |  | 2020-12-03 18:00 | Moomba WL | DKitney | 2022-10-03 10:42 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 5806.89 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001688 | O.1001688.01 | A.1001688.01.29 | Alwyn North 2 | SANTOS LIMITED | ALWYN NORTH 002 | ENSIGN 967 | J.20.062831 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2020-04-21 11:00 | 2020-10-30 04:00 |  | 2020-12-20 12:00 | 2020-12-24 12:00 |  | 2020-12-19 22:12 | Moomba WL | AGamero | 2022-10-03 10:46 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  | L0 - No RO |  | 75 | 50 | 0 | 75 | 60 |  | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.28 | Yanda South 1 | SANTOS LIMITED | Yanda South 1 | ENSIGN 967 | J.20.062826 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2020-10-05 23:00 | 2020-10-04 12:00 |  | 2020-10-05 23:00 | 2020-10-09 23:00 |  | 2020-10-09 23:00 | Moomba WL | AGamero | 2022-10-03 10:46 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.26 | Okotoko North 2 | SANTOS LIMITED | Okotoko North 2 | ENSIGN 967 | J.20.062825 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress | 2020-09-02 17:00 | 2020-09-02 04:00 |  | 2020-09-02 18:00 | 2020-09-06 18:00 |  | 2020-09-06 17:00 | Moomba WL | AGamero | 2022-10-03 10:46 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.19 | Toolachee 56 | SANTOS LIMITED | Toolachee 56 | ENSIGN 967 | J.20.062824 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-06-25 03:00 | 2020-06-25 04:00 |  | 2020-06-25 04:00 | 2020-06-29 04:00 |  | 2020-06-29 03:00 | Moomba WL | AGamero | 2022-10-03 10:46 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.35 | Pondrinie 20 | SANTOS LIMITED | Pondrinie 20 | ENSIGN 967 | J.20.062818 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-04-27 09:00 | 2020-04-28 04:00 |  | 2020-04-28 04:00 | 2020-05-03 03:00 |  | 2020-04-30 18:30 | Moomba WL | OBass | 2022-10-03 10:45 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 53437.3 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.21 | Inglewood 1 | SANTOS LIMITED | Inglewood 1 | ENSIGN 967 | J.20.062817 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress | 2020-07-17 15:00 | 2020-07-17 16:00 |  | 2020-07-17 16:00 | 2020-07-24 16:00 |  | 2020-07-24 15:00 | Moomba WL | AGamero | 2022-10-03 10:45 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.14 | Wippo South 2 | SANTOS LIMITED |  | ENSIGN 967 | J.20.062816 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-04-11 18:00 | 2020-04-11 18:00 |  | 2020-04-11 18:00 | 2020-04-15 19:00 |  | 2020-04-16 06:00 | Moomba WL | AGamero | 2022-10-03 10:45 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.36 | Moon North West 1 | SANTOS LIMITED | MOON NORTH WEST 1 | ENSIGN 967 | J.20.062814 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2020-12-29 14:00 | 2020-12-29 18:00 |  | 2020-12-31 08:00 | 2021-01-04 08:00 |  | 2021-01-02 16:00 | Moomba WL | OBass | 2022-10-03 10:44 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.31 | Warumpi 2 | SANTOS LIMITED | Warumpi 2 | ENSIGN 967 | J.20.062813 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-10-21 04:00 | 2020-10-19 04:00 |  | 2020-10-21 04:00 | 2020-10-25 04:00 |  | 2020-10-25 04:00 | Moomba WL | AGamero | 2022-10-03 10:44 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.01 | ES Logging | SANTOS LIMITED | Vega 6 | ENSIGN 967 | J.19.060507 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2019-10-15 | 2019-10-15 |  | 2019-10-15 | 2019-10-25 |  | 2019-10-24 23:00 | Moomba WL | AGamero | 2022-10-03 10:44 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.11 | Hera 5 | SANTOS LIMITED | Hera 5 | ENSIGN 967 | J.20.062809 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-02-20 01:00 | 2020-02-20 |  | 2020-02-20 01:00 | 2020-02-25 16:00 |  | 2020-02-25 16:00 | Moomba WL | AGamero | 2022-10-03 10:43 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.33 | Alwyn 8 | SANTOS LIMITED | Alwyn 8 | ENSIGN 967 | J.20.062805 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-10-27 04:00 | 2020-10-27 04:00 |  | 2020-10-27 04:00 | 2020-10-30 04:00 |  | 2020-10-30 04:00 | Moomba WL | AGamero | 2022-10-03 10:43 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.32 | Brumby 14 | SANTOS LIMITED | Brumby 14 | ENSIGN 967 | J.20.062804 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-12-12 04:00 | 2020-12-07 04:00 |  | 2020-12-12 04:00 | 2020-12-15 04:00 |  | 2020-12-15 04:00 | Moomba WL | AGamero | 2022-10-03 10:43 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.34 | Pondrinie 18 | SANTOS LIMITED | Pondrinie 18 | ENSIGN 967 | J.20.062803 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-04-16 12:30 | 2020-04-18 12:00 |  | 2020-04-18 12:00 | 2020-04-20 11:00 |  | 2020-04-19 12:30 | Moomba WL | OBass | 2022-10-03 10:42 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 41417.26 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.27 | Maverick 1 | SANTOS LIMITED | Maverick 1 | ENSIGN 967 | J.20.062800 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress | 2020-12-29 11:00 | 2020-09-22 05:00 |  | 2020-12-27 12:00 | 2021-01-01 12:00 |  | 2021-01-03 10:00 | Moomba WL | AGamero | 2022-10-03 10:42 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.22 | Brompton 1 | SANTOS LIMITED | Brompton 1 | ENSIGN 967 | J.20.062799 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-08-23 11:00 | 2020-08-01 14:00 |  | 2020-08-23 12:00 | 2020-08-25 12:00 |  | 2020-09-02 11:00 | Moomba WL | AGamero | 2022-10-03 10:42 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 128418.53 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.38 | Bolah 7 | SANTOS LIMITED |  | ENSIGN 967 | J.21.108396 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2021-01-27 11:00 | 2021-01-27 12:00 |  | 2021-01-27 12:00 | 2021-01-31 12:00 |  | 2021-01-31 11:00 | Moomba WL | OBass | 2022-10-03 10:41 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.25 | Wippo South 2 | SANTOS LIMITED | Wippo South 2 | ENSIGN 967 | J.20.062797 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-09-12 11:00 | 2020-09-12 04:00 |  | 2020-09-12 12:00 | 2020-09-16 12:00 |  | 2020-09-03 11:00 | Moomba WL | AGamero | 2022-10-03 10:41 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.18 | Moon 5 | SANTOS LIMITED | Moon 5 | ENSIGN 967 | J.20.062793 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress | 2020-06-26 23:00 | 2020-06-04 04:00 |  | 2020-06-27 | 2020-07-01 |  | 2020-06-30 23:00 | Moomba WL | AGamero | 2022-10-03 10:40 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.16 | Gidgealpa South 1 | SANTOS LIMITED | GIDGEALPA SOUTH 001 | ENSIGN 967 | J.20.062792 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-05-09 11:00 | 2020-05-09 12:00 |  | 2020-05-09 12:00 | 2020-05-13 |  | 2020-04-30 11:00 | Moomba WL | AGamero | 2022-10-03 10:40 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.10 | Jarrar 8 | SANTOS LIMITED | Jarrar 8 | ENSIGN 967 | J.20.062791 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-02-12 09:00 | 2020-02-12 08:00 |  | 2020-02-12 08:00 | 2020-02-16 07:00 |  | 2020-02-22 08:00 | Moomba WL | AGamero | 2022-10-03 10:40 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 24515.92 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.02 | ES Logging | SANTOS LIMITED | Vega 7 | ENSIGN 967 | J.19.060498 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2019-11-20 01:00 | 2019-11-02 |  | 2019-11-20 | 2019-11-23 23:00 |  | 2019-11-23 | Moomba WL | AGamero | 2022-10-03 10:40 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.30 | Amyema 2 | SANTOS LIMITED | Amyema 2 | ENSIGN 967 | J.20.062787 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-11-29 06:00 | 2020-11-24 04:00 |  | 2020-11-29 06:00 | 2020-12-03 06:00 |  | 2020-12-03 06:00 | Moomba WL | AGamero | 2022-10-03 10:39 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.17 | Moon 4 | SANTOS LIMITED | Moon 4 | ENSIGN 967 | J.20.062786 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress | 2020-05-25 05:00 | 2020-05-23 04:00 |  | 2020-05-25 06:00 | 2020-05-29 06:00 |  | 2020-05-16 05:00 | Moomba WL | AGamero | 2022-10-03 10:39 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.12 | Hera 6 | SANTOS LIMITED | Hera 6 | ENSIGN 967 | J.20.062785 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-03-09 18:00 | 2020-02-29 18:00 |  | 2020-03-09 18:00 | 2020-03-24 18:00 |  | 2020-04-17 17:00 | Moomba WL | AGamero | 2022-10-03 10:39 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 42560.1 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.37 | Test test | SANTOS LIMITED |  | ENSIGN 967 | J.20.062783 | RPE | ES-OH-NO | High | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-11-26 | 2020-11-20 |  | 2020-11-26 | 2020-11-27 23:59 |  | 2020-11-27 23:59 | Moomba WL | WXu13 | 2022-10-03 10:39 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.23 | Ruby 3 | SANTOS LIMITED | RUBY 3 | ENSIGN 967 | J.21.108392 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-01-15 11:00 | 2021-01-15 12:00 |  | 2021-01-15 12:00 | 2021-01-19 12:00 |  | 2021-01-19 11:00 | Moomba WL | AGamero | 2022-10-03 10:39 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.13 | Cooroo North West 4 | SANTOS LIMITED | Cooroo North West 4 | ENSIGN 967 | J.20.062781 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress | 2020-04-09 | 2020-03-22 18:00 |  | 2020-04-09 | 2020-04-11 19:00 |  | 2020-04-24 13:00 | Moomba WL | AGamero | 2022-10-03 10:39 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 59809.93 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.08 | Jarrar 6 | SANTOS LIMITED | Jarrar 6 | ENSIGN 967 | J.20.062780 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-01-20 19:00 | 2020-01-14 |  | 2020-01-20 18:00 | 2020-01-24 17:00 |  | 2020-01-30 18:00 | Moomba WL | AGamero | 2022-10-03 10:38 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.24 | Goose 1 | SANTOS LIMITED | Goose 1 | ENSIGN 967 | J.20.062776 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress | 2020-08-22 23:00 | 2020-08-23 |  | 2020-08-23 | 2020-08-30 |  | 2020-08-29 23:00 | Moomba WL | AGamero | 2022-10-03 10:38 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.15 | Pondrinie 19 | SANTOS LIMITED | Pondrinie 19 | ENSIGN 967 | J.20.062775 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-04-07 18:00 | 2020-04-04 18:00 |  | 2020-04-07 18:00 | 2020-04-12 16:00 |  | 2020-04-11 18:00 | Moomba WL | AGamero | 2022-10-03 10:38 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 53437.3 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.09 | Jarrar 7 | SANTOS LIMITED | Jarrar 7 | ENSIGN 967 | J.20.062774 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-01-31 23:00 | 2020-01-29 18:00 |  | 2020-01-31 22:00 | 2020-02-06 18:00 |  | 2020-02-15 22:00 | Moomba WL | AGamero | 2022-10-03 10:38 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.05 | Cherokee 1 | SANTOS LIMITED | Cherokee (NFE) | ENSIGN 967 |  | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-16 01:00 |  | 2020-01-18 18:00 | 2020-01-22 17:00 |  |  | Moomba WL | AGamero | 2022-09-03 07:59 | walfaro |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.04 | Piute 1 | SANTOS LIMITED | Piute (NFE) | ENSIGN 967 |  | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-04 |  | 2019-12-04 | 2019-12-07 23:00 |  |  | Moomba WL | AGamero | 2022-09-03 07:59 | walfaro |  | No |  |  |  |  | Rob Twigg |  | 41708.9 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.20 | Hector SE 1 | SANTOS LIMITED | HECTOR SE NFE A | ENSIGN 967 |  | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-07-04 04:00 |  | 2020-07-08 14:00 | 2020-07-12 14:00 |  |  | Moomba WL | AGamero | 2022-09-03 07:59 | walfaro |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.07 | Toltec 1 | SANTOS LIMITED | Toltec (NFE) | ENSIGN 967 |  | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-08 18:00 |  | 2020-01-14 | 2020-01-17 23:00 |  |  | Moomba WL | AGamero | 2022-09-03 07:59 | walfaro |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.03 | Leghorn 1 | SANTOS LIMITED | Leghorn (NFE) | ENSIGN 967 |  | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-11-19 |  | 2019-11-20 | 2019-11-20 23:00 |  |  | Moomba WL | AGamero | 2022-09-03 07:59 | walfaro |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001688 | O.1001688.01 | A.1001688.01.06 | Ute 1 | SANTOS LIMITED | Ute (NFE) | ENSIGN 967 |  | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-30 |  | 2019-12-30 12:00 | 2020-01-03 11:00 |  |  | Moomba WL | AGamero | 2022-09-03 07:59 | walfaro |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.28 | Cooroo North West 6 | SANTOS LIMITED | Cooroo North West 6 | Ensign 950 | J.20.062830 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-04-26 15:00 | 2020-04-27 21:00 |  | 2020-04-27 21:00 | 2020-05-01 21:00 |  | 2020-05-04 01:00 | Moomba WL | OBass | 2022-10-03 10:46 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 39034.44 |  |  |  |  | 58.3 | 50 | 0 | 62.5 | 51.2 |  | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.20 | Isoptera 2 | SANTOS LIMITED | ISOPTERA 002 | Ensign 950 | J.20.062829 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-02-04 22:00 | 2020-02-02 21:00 |  | 2020-02-04 21:00 | 2020-02-08 21:00 |  | 2020-02-11 22:00 | Moomba WL | AGamero | 2022-10-03 10:46 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 39989.6 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.19 | Bugito 3 | SANTOS LIMITED | BUGITO 003 | Ensign 950 | J.20.062828 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-01-31 22:00 | 2020-01-31 21:00 |  | 2020-01-31 21:00 | 2020-02-04 21:00 |  | 2020-02-07 22:00 | Moomba WL | AGamero | 2022-10-03 10:46 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 40305.39 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.31 | Kooroopa North (App A) | SANTOS LIMITED |  | Ensign 950 | J.20.062823 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-05-29 21:00 | 2020-05-29 21:00 |  | 2020-05-29 21:00 | 2020-06-02 21:00 |  | 2020-06-05 21:00 | Moomba WL | OBass | 2022-10-03 10:46 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.13 | Thungo North 1 | SANTOS LIMITED | Thungo North 1 | Ensign 950 | J.19.060512 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2019-12-17 12:00 | 2019-12-17 07:00 |  | 2019-12-17 11:00 | 2019-12-21 11:00 |  | 2019-12-24 12:00 | Moomba WL | AGamero | 2022-10-03 10:45 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.23 | Seccante 5 | SANTOS LIMITED | Seccante 5 | Ensign 950 | J.20.062822 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress | 2020-02-27 17:00 | 2020-02-27 10:30 |  | 2020-02-28 13:00 | 2020-03-03 13:00 |  | 2020-03-06 03:30 | Moomba WL | AGamero | 2022-10-03 10:45 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.18 | Seccante 7 | SANTOS LIMITED | Seccante 7 | Ensign 950 | J.20.062821 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-01-20 22:00 | 2020-01-19 21:00 |  | 2020-01-20 21:00 | 2020-01-24 21:00 |  | 2020-01-27 22:00 | Moomba WL | AGamero | 2022-10-03 10:45 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 42388.98 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.34 | Kooroopa (App A) | SANTOS LIMITED |  | Ensign 950 | J.20.062815 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-06-19 21:00 | 2020-06-19 21:00 |  | 2020-06-19 21:00 | 2020-06-23 21:00 |  | 2020-06-26 21:00 | Moomba WL | OBass | 2022-10-03 10:45 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.05 | ES Logging | SANTOS LIMITED | WACKETT 19 | Ensign 950 | J.19.060510 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2019-10-16 11:00 | 2019-10-14 |  | 2019-10-16 11:00 | 2019-10-17 11:00 |  | 2019-10-18 11:00 | Moomba WL | AGamero | 2022-10-03 10:44 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 46586.61 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.24 | Cooroo North West 3 | SANTOS LIMITED | Cooroo North West 3 | Ensign 950 | J.20.062812 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-03-31 | 2020-03-30 06:00 |  | 2020-03-30 23:00 | 2020-04-03 23:00 |  | 2020-04-06 23:00 | Moomba WL | AGamero | 2022-10-03 10:44 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 87767.31 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.22 | Jena 24_Quad Combo, XPT | SANTOS LIMITED | Jena 24 | Ensign 950 | J.20.062811 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-02-24 22:00 | 2020-02-23 21:00 |  | 2020-02-24 21:00 | 2020-02-28 21:00 |  | 2020-03-02 22:00 | Moomba WL | AGamero | 2022-10-03 10:44 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.29 | Cooroo 7 | SANTOS LIMITED | Cooroo 7 (APP A) | Ensign 950 | J.20.062808 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-04-12 02:30 | 2020-04-10 21:00 |  | 2020-04-12 12:00 | 2020-04-14 12:00 |  | 2020-04-19 02:30 | Moomba WL | OBass | 2022-10-03 10:43 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 44509.42 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.15 | Seccante 3 | SANTOS LIMITED | Seccante 3 | Ensign 950 | J.20.062807 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-01-14 01:00 | 2020-01-02 07:00 |  | 2020-01-14 | 2020-01-18 |  | 2020-01-21 01:00 | Moomba WL | AGamero | 2022-10-03 10:43 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 50 | 33.3 | 0 | 25 | 32.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.06 | Wackett 20 | SANTOS LIMITED | WACKETT 20 | Ensign 950 | J.19.060506 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-11-10 13:00 | 2019-10-23 12:00 |  | 2019-11-10 12:00 | 2019-11-13 12:00 |  | 2019-11-13 13:00 | Moomba WL | AGamero | 2022-10-03 10:43 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 25 | 20 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.25 | Isoptera 3 | SANTOS LIMITED | Isoptera 3 | Ensign 950 | J.20.062802 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-02-12 07:00 | 2020-02-07 21:00 |  | 2020-02-12 06:00 | 2020-02-18 06:00 |  | 2020-02-21 07:00 | Moomba WL | AGamero | 2022-10-03 10:42 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 39989.6 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.07 | Wackett 21 Quad Combo + MDT Sampling | SANTOS LIMITED | WACKETT 21 | Ensign 950 | J.19.060505 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2019-10-31 08:00 | 2019-10-31 07:00 |  | 2019-10-31 07:00 | 2019-11-03 07:00 |  | 2019-11-03 08:00 | Moomba WL | AGamero | 2022-10-03 10:42 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.01 | ES Logging | SANTOS LIMITED |  | Ensign 950 | J.19.060504 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2019-10-06 | 2019-10-06 |  | 2019-10-06 | 2019-10-12 |  | 2019-10-12 | Moomba WL | AGamero | 2022-10-03 10:42 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.21 | Ulandi 11 | SANTOS LIMITED | ULANDI 011 | Ensign 950 | J.20.062798 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-02-20 22:00 | 2020-02-19 21:00 |  | 2020-02-20 21:00 | 2020-02-24 21:00 |  | 2020-02-27 22:00 | Moomba WL | AGamero | 2022-10-03 10:42 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.12 | Dilkera 8_Quad Combo | SANTOS LIMITED | Dilkera 8 | Ensign 950 | J.19.060503 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2019-12-11 08:00 | 2019-12-11 07:00 |  | 2019-12-11 07:00 | 2019-12-15 07:00 |  | 2019-12-18 08:00 | Moomba WL | AGamero | 2022-10-03 10:42 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.27 | Cooroo North West 5 | SANTOS LIMITED | Cooroo North West 5 | Ensign 950 | J.20.062796 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-05-09 15:30 | 2020-04-20 18:00 |  | 2020-05-10 | 2020-05-14 |  | 2020-05-17 01:00 | Moomba WL | OBass | 2022-10-03 10:41 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 44509.42 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.26 | Cooroo North West (App D) | SANTOS LIMITED |  | Ensign 950 | J.20.062795 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-04-03 22:00 | 2020-04-03 21:00 |  | 2020-04-03 21:00 | 2020-04-07 21:00 |  | 2020-04-10 21:00 | Moomba WL | OBass | 2022-10-03 10:41 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.30 | Wolgolla West (NFEA) | SANTOS LIMITED |  | Ensign 950 | J.20.062794 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-05-17 21:00 | 2020-05-17 21:00 |  | 2020-05-17 21:00 | 2020-05-21 21:00 |  | 2020-05-24 21:00 | Moomba WL | OBass | 2022-10-03 10:41 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.33 | Kooroopa North (App E) | SANTOS LIMITED |  | Ensign 950 | J.20.062790 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-06-12 21:00 | 2020-06-12 21:00 |  | 2020-06-12 21:00 | 2020-06-16 21:00 |  | 2020-06-19 21:00 | Moomba WL | OBass | 2022-10-03 10:40 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.16 | Seccante 6 | SANTOS LIMITED | Seccante 6 | Ensign 950 | J.20.062789 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-01-18 22:00 | 2020-01-10 21:00 |  | 2020-01-18 21:00 | 2020-01-22 21:00 |  | 2020-01-25 22:00 | Moomba WL | AGamero | 2022-10-03 10:40 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.14 | McKinlay 19 | SANTOS LIMITED | Mckinlay 19 | Ensign 950 | J.20.062788 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-01-18 19:00 | 2019-12-29 07:00 |  | 2020-01-18 18:00 | 2020-01-22 18:00 |  | 2020-01-25 19:00 | Moomba WL | AGamero | 2022-10-03 10:40 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.09 | Dilkera 5 | SANTOS LIMITED | DILKERA 5 | Ensign 950 | J.19.060497 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2019-11-27 08:00 | 2019-11-26 07:00 |  | 2019-11-27 07:00 | 2019-11-30 07:00 |  | 2019-12-04 08:00 | Moomba WL | AGamero | 2022-10-03 10:40 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 39989.6 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.08 | Dilkera 4 | SANTOS LIMITED | Dilkera 4 | Ensign 950 | J.19.060495 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2019-11-20 08:00 | 2019-11-20 07:00 |  | 2019-11-20 07:00 | 2019-11-25 07:00 |  | 2019-11-28 08:00 | Moomba WL | AGamero | 2022-10-03 10:39 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 39989.6 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.32 | Kooroopa North (App C) | SANTOS LIMITED |  | Ensign 950 | J.20.062782 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-06-05 21:00 | 2020-06-05 21:00 |  | 2020-06-05 21:00 | 2020-06-09 21:00 |  | 2020-06-12 21:00 | Moomba WL | OBass | 2022-10-03 10:39 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.17 | Seccante 4 | SANTOS LIMITED | Seccante 4 | Ensign 950 | J.20.062779 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-01-18 22:00 | 2020-01-15 21:00 |  | 2020-01-18 21:00 | 2020-01-22 21:00 |  | 2020-01-25 22:00 | Moomba WL | AGamero | 2022-10-03 10:38 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 24515.92 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.10 | Dilkera 6 | SANTOS LIMITED | Dilkera 6 | Ensign 950 | J.20.062778 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-01-19 19:00 | 2019-12-01 07:00 |  | 2020-01-19 18:00 | 2020-01-23 18:00 |  | 2020-01-26 19:00 | Moomba WL | AGamero | 2022-10-03 10:38 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 30946.09 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.11 | Dilkera 7 | SANTOS LIMITED | Dilkera 7 | Ensign 950 | J.19.060492 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2019-12-13 21:00 | 2019-12-07 07:00 |  | 2019-12-13 20:00 | 2019-12-20 20:00 |  | 2019-12-20 21:00 | Moomba WL | AGamero | 2022-10-03 10:38 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 50 | 33.3 | 0 | 25 | 32.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.04 | ES Logging | SANTOS LIMITED | Wackett East (NFE) | Ensign 950 |  | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-09-27 |  | 2019-09-27 | 2019-10-04 |  |  | Moomba WL | AGamero | 2020-11-13 10:25 | JColeman |  | No |  |  |  |  | Ihab Wahbi |  | 39989.6 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.03 | ES Logging | SANTOS LIMITED | Wackett South (App) | Ensign 950 |  | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2019-09-18 |  | 2019-09-18 | 2019-09-25 |  |  | Moomba WL | AGamero | 2020-11-13 10:25 | JColeman |  | No |  |  |  |  | Ihab Wahbi |  | 46586.61 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001674 | O.1001674.01 | A.1001674.01.02 | ES Logging | SANTOS LIMITED | Wackett East (NFE) | Ensign 950 |  | RPE | ES-OH-Ops | InComplete | Cancelled | Close - PSD |  | Not Required | Not Started | In Progress |  | 2019-09-27 |  | 2019-09-27 | 2019-10-04 |  |  | Moomba WL | AGamero | 2020-11-13 10:25 | JColeman |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001664 | O.1001664.05 | A.1001664.05.03 | Arrow Q1 2025 Mar | ARROW ENERGY LTD |  | Saxon Rig 167 | J.25.008348 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2025-07-02 01:00 | 2025-07-03 | 2025-07-03 01:00 | 2025-07-03 | 2025-07-06 23:59 | 2025-07-07 01:00 | 2025-08-03 00:59 | Roma WL | KKeese | 2025-05-18 13:31 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 0 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 3 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001664 | O.1001664.05 | A.1001664.05.02 | Arrow Q1 2025 Feb | ARROW ENERGY LTD |  | Saxon Rig 167 | J.25.008347 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2023-05-04 10:00 | 2025-02-01 |  | 2025-02-01 | 2025-02-28 23:59 |  | 2025-02-28 23:59 | Roma WL | KKeese | 2024-10-29 11:48 | KKeese |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 3 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001664 | O.1001664.05 | A.1001664.05.01 | Arrow Q1 2025 | ARROW ENERGY LTD |  | Saxon Rig 167 | J.24.142259 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2023-05-04 10:00 | 2025-01-01 |  | 2025-01-01 | 2025-01-31 23:59 |  | 2025-01-31 23:59 | Roma WL | KKeese | 2024-10-29 11:42 | KKeese |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 3 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001664 | O.1001664.04 | A.1001664.04.04 | MPK6_USIT-CBL | ARROW ENERGY LTD |  | SAVANNA DRILLING #406 | J.23.073841 | RPE | ES-CH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | Not Started | 2023-07-11 | 2023-07-10 |  | 2023-07-11 | 2023-07-12 23:59 |  | 2023-07-12 23:59 | Roma WL | SAli63 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 1 |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001664 | O.1001664.04 | A.1001664.04.06 | Arrow OH June | ARROW ENERGY LTD | TIPTON 241 | SAVANNA DRILLING #406 | J.23.100109 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-06-12 18:00 | 2024-06-11 06:00 | 2024-06-11 23:00 | 2024-06-12 18:00 | 2024-06-15 18:59 | 2024-06-15 23:00 | 2025-01-17 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 2 |  | L3 - Full RO |  | 66.7 | 50 | 0 | 0 | 35 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001664 | O.1001664.04 | A.1001664.04.11 | Aarow Energy 3 | ARROW ENERGY LTD | TIPTON 241 | SAVANNA DRILLING #406 | J.24.022194 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-03-24 18:00 | 2024-03-24 06:00 |  | 2024-03-24 18:00 | 2024-03-27 18:59 |  | 2024-03-27 18:59 | Roma WL | KKeese | 2024-01-10 16:28 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001664 | O.1001664.04 | A.1001664.04.10 | Aarow Energy 2 | ARROW ENERGY LTD | TIPTON 241 | SAVANNA DRILLING #406 | J.24.022193 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-02-25 18:00 | 2024-02-25 06:00 |  | 2024-02-25 18:00 | 2024-02-28 18:59 |  | 2024-02-28 18:59 | Roma WL | KKeese | 2024-01-10 16:17 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001664 | O.1001664.04 | A.1001664.04.09 | Aarow Energy 1 | ARROW ENERGY LTD | TIPTON 241 | SAVANNA DRILLING #406 | J.24.022192 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-01-28 18:00 | 2024-01-28 06:00 |  | 2024-01-28 18:00 | 2024-02-10 18:59 |  | 2024-02-10 18:59 | Roma WL | KKeese | 2024-01-05 11:10 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 1 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001664 | O.1001664.04 | A.1001664.04.08 | Arrow Advanced OH 2 | ARROW ENERGY LTD | TIPTON 241 | SAVANNA DRILLING #406 | J.23.119062 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-23 18:00 | 2023-10-22 06:00 | 2023-10-23 | 2023-10-23 18:00 | 2023-10-26 18:59 | 2023-10-27 | 2023-10-26 18:59 | Roma WL | KKeese | 2023-08-28 16:37 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001664 | O.1001664.04 | A.1001664.04.07 | Arrow Advanced OH 1 | ARROW ENERGY LTD | TIPTON 241 | SAVANNA DRILLING #406 | J.23.119061 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-09 18:00 | 2023-10-08 06:00 | 2023-10-09 | 2023-10-09 18:00 | 2023-10-12 18:59 | 2023-10-13 | 2023-10-12 18:59 | Roma WL | KKeese | 2023-08-28 16:37 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001664 | O.1001664.04 | A.1001664.04.05 | Arrow_May | ARROW ENERGY LTD | TIPTON 241 | SAVANNA DRILLING #406 | J.23.092185 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-31 18:00 | 2023-05-31 06:00 |  | 2023-05-31 18:00 | 2023-06-03 18:59 |  | 2023-06-03 18:59 | Roma WL | KKeese | 2023-06-04 09:00 | NMoore2 |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 17154 | 2 |  | L3 - Full RO |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001664 | O.1001664.04 | A.1001664.04.03 | Quad Combo_FMI | ARROW ENERGY LTD |  | SAVANNA DRILLING #406 | J.23.052649 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2023-03-14 18:00 | 2023-03-14 06:00 |  | 2023-03-14 18:00 | 2023-03-17 18:59 |  | 2023-03-17 18:59 | Roma WL | SAli63 | 2023-03-10 11:06 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001664 | O.1001664.04 | A.1001664.04.02 | CB22 | ARROW ENERGY LTD | CARN BREA 22 | SAVANNA DRILLING #406 | J.23.035788 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-02-07 18:00 | 2023-02-07 06:00 |  | 2023-02-07 18:00 | 2023-02-10 18:59 |  | 2023-02-10 18:59 | Roma WL | MRony2 | 2023-02-19 10:55 | ysaeedabadian |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 34224.17 | 3 |  | L2 - Shift RO |  | 75 | 83.3 | 100 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001664 | O.1001664.04 | A.1001664.04.01 | Barkula 2 | ARROW ENERGY LTD | BARAKULA 2 | SAVANNA DRILLING #406 | J.22.125142 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-11-08 16:00 |  | 2022-11-09 06:00 | 2022-11-10 06:59 |  |  | Roma WL | MRony2 | 2022-11-16 11:27 | RDell |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 33073.42 | 3 |  |  |  | 66.7 | 66.7 | 0 | 50 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001664 | O.1001664.03 | A.1001664.03.09 | May Ops _ Arrow | ARROW ENERGY LTD | Red Hill 41 | Saxon Rig 165 | J.22.110887 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-07-08 23:00 | 2022-07-08 |  | 2022-07-09 | 2022-07-12 23:59 |  | 2022-07-12 23:00 | Roma WL | MRony2 | 2022-10-03 14:59 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001664 | O.1001664.03 | A.1001664.03.08 | May Ops | ARROW ENERGY LTD | Red Hill 41 | Saxon Rig 165 | J.22.110886 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-06-13 23:00 | 2022-06-13 |  | 2022-06-14 | 2022-06-17 23:59 |  | 2022-06-17 23:00 | Roma WL | MRony2 | 2022-10-03 14:59 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001664 | O.1001664.03 | A.1001664.03.01 | Well 1 | ARROW ENERGY LTD | Moranbah 258V, Moranbah 257V | Saxon Rig 165 | J.21.109424 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-11-20 | 2021-11-20 |  | 2021-11-20 | 2021-11-27 23:59 |  | 2021-11-27 23:59 | Roma WL | MRony2 | 2022-10-03 14:59 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 10493.83 | 2 |  |  |  | 75 | 33.3 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001664 | O.1001664.03 | A.1001664.03.05 | Red Hill 41 | ARROW ENERGY LTD | Red Hill 41 | Saxon Rig 165 | J.22.110273 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-03-10 |  | 2022-03-10 | 2022-03-13 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 17673.81 | 2 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001664 | O.1001664.03 | A.1001664.03.06 | Red Hill 40 | ARROW ENERGY LTD | Red Hill 40 | Saxon Rig 165 | J.22.110272 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-03-21 |  | 2022-03-24 | 2022-03-26 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 17673.81 | 2 |  |  |  | 75 | 50 | 0 | 50 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001664 | O.1001664.03 | A.1001664.03.02 | Well 2 | ARROW ENERGY LTD | Moranbah 257V | Saxon Rig 165 | J.21.109075 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-12-06 |  | 2021-12-06 | 2021-12-08 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 10493.83 | 2 |  |  |  | 83.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001664 | O.1001664.03 | A.1001664.03.04 | Mavis Downs 10 | ARROW ENERGY LTD | Mavis Downs 10 | Saxon Rig 165 | J.22.110270 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-03-16 |  | 2022-03-16 | 2022-03-21 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 17673.81 | 2 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001664 | O.1001664.03 | A.1001664.03.07 | Well 7 | ARROW ENERGY LTD | Kemmis Creek 5 | Saxon Rig 165 | J.22.110269 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-03-29 |  | 2022-03-30 | 2022-04-01 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 17089.02 | 2 |  |  |  | 75 | 33.3 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001664 | O.1001664.03 | A.1001664.03.03 | Well 3 | ARROW ENERGY LTD | Kimmis Creek 6 | Saxon Rig 165 | J.21.109074 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-12-13 13:00 |  | 2021-12-13 20:00 | 2021-12-16 19:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 12865.5 | 2 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001664 | O.1001664.02 | A.1001664.02.01 | MDT | ARROW ENERGY LTD |  | Saxon Rig 167 | J.19.060646 | RPE | ES-OH-Ops | Low | Unconfirmed - 50% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-11-07 23:00 | 2019-11-06 23:00 |  | 2019-11-07 23:00 | 2019-11-11 23:00 |  | 2019-11-11 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:44 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001664 | O.1001664.02 | A.1001664.02.02 | Advance services and MDT | ARROW ENERGY LTD |  | Saxon Rig 167 | J.19.060634 | RPE | ES-OH-Ops | Low | Unconfirmed - 50% | Design - PSD |  | In Progress | Not Started | In Progress | 2019-11-11 06:00 | 2019-12-10 15:00 |  | 2019-12-11 06:00 | 2019-12-15 06:00 |  | 2019-11-15 06:00 | Roma WL | VOliveira5 | 2022-10-03 13:37 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 |  |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001664 | O.1001664.01 | A.1001664.01.13 | Advance and CMR | ARROW ENERGY LTD | Tipton 200 | Saxon Rig 167 | J.22.110885 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-01-06 08:00 | 2022-01-05 12:00 |  | 2022-01-06 08:00 | 2022-01-08 07:59 |  | 2022-01-08 07:59 | Roma WL | MRony2 | 2022-10-03 14:59 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001664 | O.1001664.01 | A.1001664.01.05 | ADV_SUITE | ARROW ENERGY LTD |  | Saxon Rig 167 | J.19.060645 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-22 | 2019-11-18 23:00 |  | 2019-11-18 23:00 | 2019-11-21 23:00 |  | 2019-10-25 | Roma WL | VOliveira5 | 2022-10-03 13:44 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001664 | O.1001664.01 | A.1001664.01.08 | ADV_SUITE | ARROW ENERGY LTD |  | Saxon Rig 167 | J.19.060644 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-09 23:00 |  | 2019-12-09 23:00 | 2019-12-12 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:43 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001664 | O.1001664.01 | A.1001664.01.11 | ADV_SUITE | ARROW ENERGY LTD |  | Saxon Rig 167 | J.19.060643 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-29 23:00 |  | 2019-12-29 23:00 | 2020-01-01 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:43 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001664 | O.1001664.01 | A.1001664.01.04 | ADV_SUITE | ARROW ENERGY LTD |  | Saxon Rig 167 | J.19.060642 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2019-11-10 23:00 |  | 2019-11-10 23:00 | 2019-11-13 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:42 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | 0 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Anouk Suminar | WL Evaluation Services
P.1001664 | O.1001664.01 | A.1001664.01.02 | ADV_SUITE | ARROW ENERGY LTD |  | Saxon Rig 167 | J.19.060641 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-17 23:00 | 2019-10-21 23:00 |  | 2019-10-21 23:00 | 2019-10-24 23:00 |  | 2019-10-20 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:42 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001664 | O.1001664.01 | A.1001664.01.09 | ADV_SUITE | ARROW ENERGY LTD |  | Saxon Rig 167 | J.19.060637 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-22 | 2019-12-15 23:00 |  | 2019-12-15 23:00 | 2019-12-18 23:00 |  | 2019-10-25 | Roma WL | VOliveira5 | 2022-10-03 13:39 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001664 | O.1001664.01 | A.1001664.01.07 | ADV_SUITE | ARROW ENERGY LTD |  | Saxon Rig 167 | J.19.060636 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-22 | 2019-12-02 23:00 |  | 2019-12-02 23:00 | 2019-12-05 23:00 |  | 2019-10-25 | Roma WL | VOliveira5 | 2022-10-03 13:38 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001664 | O.1001664.01 | A.1001664.01.01 | ADV_SUITE | ARROW ENERGY LTD |  | Saxon Rig 167 | J.19.060635 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-15 | 2019-10-15 |  | 2019-10-15 | 2019-10-18 |  | 2019-10-18 | Roma WL | VOliveira5 | 2022-10-03 13:38 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001664 | O.1001664.01 | A.1001664.01.03 | ADV_SUITE | ARROW ENERGY LTD |  | Saxon Rig 167 | J.19.060633 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-22 | 2019-10-28 23:00 |  | 2019-10-28 23:00 | 2019-10-31 23:00 |  | 2019-10-25 | Roma WL | VOliveira5 | 2022-10-03 13:37 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001664 | O.1001664.01 | A.1001664.01.12 | ADV_SUITE | ARROW ENERGY LTD |  | Saxon Rig 167 | J.20.063238 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-06 23:00 |  | 2020-01-06 23:00 | 2020-01-09 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:36 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001664 | O.1001664.01 | A.1001664.01.10 | ADV_SUITE | ARROW ENERGY LTD |  | Saxon Rig 167 | J.19.060632 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-22 23:00 |  | 2019-12-22 23:00 | 2019-12-25 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:36 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 58851.2 |  |  |  |  | 50 | 0 | 0 | 0 | 15 |  | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001664 | O.1001664.01 | A.1001664.01.06 | ADV_SUITE | ARROW ENERGY LTD |  | Saxon Rig 167 | J.19.060631 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-22 | 2019-11-25 23:00 |  | 2019-11-25 23:00 | 2019-11-28 23:00 |  | 2019-10-25 | Roma WL | VOliveira5 | 2022-10-03 13:35 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001663 | O.1001663.04 | A.1001663.04.12 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.22.110226 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-02-08 02:00 |  | 2022-02-08 12:00 | 2022-02-08 22:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:44 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.04 | A.1001663.04.06 | RM68-115-1 | SANTOS LIMITED | RM68-115-1 | SAVANNA DRILLING #407 | J.20.063292 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-09-20 |  | 2020-09-21 | 2020-09-22 10:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:43 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.04 | A.1001663.04.10 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.22.110223 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-02-02 02:00 |  | 2022-02-02 12:00 | 2022-02-02 22:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:42 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.04 | A.1001663.04.04 | RM15-28-1 | SANTOS LIMITED | RM15-28-1 | SAVANNA DRILLING #407 | J.20.063277 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-09-13 |  | 2020-09-15 20:00 | 2020-09-16 06:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:41 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.04 | A.1001663.04.03 | RM09-81-1 | SANTOS LIMITED | RM09-81-1 | SAVANNA DRILLING #407 | J.20.063276 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-11 |  | 2020-09-12 10:00 | 2020-09-13 20:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:41 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.04 | A.1001663.04.01 | RM68-14-1 Quad Combo | SANTOS LIMITED | RM68-14-1 | SAVANNA DRILLING #407 | J.20.063264 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-08 06:00 |  | 2020-09-08 06:00 | 2020-09-08 16:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:40 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.04 | A.1001663.04.11 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.22.110218 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-02-05 02:00 |  | 2022-02-05 12:00 | 2022-02-05 22:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:39 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.04 | A.1001663.04.07 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.21.108920 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-06-15 16:00 |  | 2021-06-16 20:00 | 2021-06-17 06:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:38 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.04 | A.1001663.04.02 | RM13-62-1 Quad combo | SANTOS LIMITED | RM13-62-1 | SAVANNA DRILLING #407 | J.20.063249 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-10 22:00 |  | 2020-09-10 22:00 | 2020-09-11 08:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:38 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.04 | A.1001663.04.09 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.22.110214 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-01-31 02:00 |  | 2022-01-31 12:00 | 2022-01-31 22:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:37 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.04 | A.1001663.04.08 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.22.110212 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-01-28 02:00 |  | 2022-01-28 12:00 | 2022-01-28 22:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:36 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.04 | A.1001663.04.05 | RM15-37-1 | SANTOS LIMITED | RM15-37-1 | SAVANNA DRILLING #407 | J.20.063216 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-09-17 |  | 2020-09-18 18:00 | 2020-09-19 18:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:33 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.27 | RM28-24-1 | SANTOS LIMITED | RM28-24-1 | SAVANNA DRILLING #407 | J.20.063297 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-23 18:00 |  | 2020-07-23 20:00 | 2020-07-24 20:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:44 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.12 | RM28-18-1 | SANTOS LIMITED | RM28-18 | SAVANNA DRILLING #407 | J.20.063296 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-05-31 17:00 |  | 2020-06-01 18:00 | 2020-06-02 18:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:43 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.05 | QC | SANTOS LIMITED | RM90-31-1 | SAVANNA DRILLING #407 | J.20.063295 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-07 09:00 |  | 2020-05-08 13:00 | 2020-05-09 13:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:43 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 |  |  |  |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.04 | QC | SANTOS LIMITED | RM90-09-1 | SAVANNA DRILLING #407 | J.20.063291 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-17 02:00 |  | 2020-09-18 03:00 | 2020-09-19 03:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:43 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.34 | RM68-67-1 | SANTOS LIMITED | RM68-67-1 | SAVANNA DRILLING #407 | J.20.063288 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-10 11:00 |  | 2020-08-10 18:00 | 2020-08-11 18:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:42 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.19 | RM68-104-1 | SANTOS LIMITED | RM68-104-1 | SAVANNA DRILLING #407 | J.20.063287 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-26 |  | 2020-06-26 | 2020-06-27 |  |  | Roma WL | MRony2 | 2022-10-03 13:42 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.38 | RM68-69-1 | SANTOS LIMITED | RM68-69-1 | SAVANNA DRILLING #407 | J.20.063285 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-19 02:00 |  | 2020-08-20 03:00 | 2020-08-22 03:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:42 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.28 | RM68-70-1 | SANTOS LIMITED | RM68-70-1 | SAVANNA DRILLING #407 | J.20.063284 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-26 |  | 2020-07-26 | 2020-07-27 |  |  | Roma WL | MRony2 | 2022-10-03 13:42 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.25 | RM28-23-1 | SANTOS LIMITED | RM28-23-1 | SAVANNA DRILLING #407 | J.20.063283 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-17 11:00 |  | 2020-07-17 12:00 | 2020-07-18 12:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:42 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.23 | RM28-20-1 | SANTOS LIMITED | RM28-20-1 | SAVANNA DRILLING #407 | J.20.063282 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-05 22:00 |  | 2020-07-06 23:00 | 2020-07-07 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:42 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.20 | RM68-105-1 BHC-HRLA-PEX-GR-SP | SANTOS LIMITED | RM68-105-1 | SAVANNA DRILLING #407 | J.20.063281 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-29 |  | 2020-07-29 | 2020-07-30 |  |  | Roma WL | MRony2 | 2022-10-03 13:41 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.15 | Wyena 7 | SANTOS LIMITED | Wyena 7 | SAVANNA DRILLING #407 | J.20.063280 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-09 22:00 |  | 2020-06-11 23:00 | 2020-06-14 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:41 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.32 | RM68-50-1 Quad Combo | SANTOS LIMITED | RM68-50-1 | SAVANNA DRILLING #407 | J.20.063275 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-04 |  | 2020-08-04 | 2020-08-05 |  |  | Roma WL | MRony2 | 2022-10-03 13:41 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.22 | RM68-107-1 BHC_HRLA-PEX-GR-SP | SANTOS LIMITED | RM68-107-1 | SAVANNA DRILLING #407 | J.20.063274 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-03 06:00 |  | 2020-07-03 06:00 | 2020-07-04 06:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:41 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.17 | RM68-102-1 BHC-HRLA-PEX-GR-SP | SANTOS LIMITED | RM68-102-1 | SAVANNA DRILLING #407 | J.20.063273 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-20 12:00 |  | 2020-06-20 12:00 | 2020-06-21 12:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:41 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.16 | Wyena 8 | SANTOS LIMITED | Wyena 8 | SAVANNA DRILLING #407 | J.20.063272 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-17 18:00 |  | 2020-06-17 18:00 | 2020-06-19 18:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:41 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 15920.73 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.02 | RM90-20-1 | SANTOS LIMITED | RM90-20-1 | SAVANNA DRILLING #407 | J.20.063271 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-02 09:00 |  | 2020-05-04 01:00 | 2020-05-05 01:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:40 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.06 | RM90-32-1 | SANTOS LIMITED | RM90-32-1 | SAVANNA DRILLING #407 | J.20.063268 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2019-12-19 20:00 | 2020-05-11 17:00 |  | 2020-05-11 18:00 | 2020-05-12 18:00 |  | 2019-12-20 20:00 | Roma WL | MRony2 | 2022-10-03 13:40 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 |  |  | L3 - Full RO |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.37 | RM14-06-1 | SANTOS LIMITED | RM14-06-1 | SAVANNA DRILLING #407 | J.20.063263 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-16 02:00 |  | 2020-08-17 03:00 | 2020-08-18 03:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:40 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.36 | RM68-78-1 | SANTOS LIMITED | RM68-78-1 | SAVANNA DRILLING #407 | J.20.063262 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-15 13:00 |  | 2020-08-15 15:00 | 2020-08-16 15:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:40 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.30 | RM68-49-1 Quad Combo | SANTOS LIMITED | RM68-49-1 | SAVANNA DRILLING #407 | J.20.063257 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-30 18:00 |  | 2020-07-30 18:00 | 2020-07-31 18:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:39 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.07 | RM90-43-1 | SANTOS LIMITED | RM90-43-1 | SAVANNA DRILLING #407 | J.20.063255 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-13 09:00 |  | 2020-05-15 10:00 | 2020-05-16 10:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:38 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 |  |  |  |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.31 | RM68-38-1 | SANTOS LIMITED | RM68-38-1 | SAVANNA DRILLING #407 | J.20.063248 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-02 18:00 |  | 2020-08-02 18:00 | 2020-08-03 18:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:37 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.14 | Wyena 6 | SANTOS LIMITED | Wyena 6 | SAVANNA DRILLING #407 | J.20.063247 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-06 22:00 |  | 2020-06-08 23:00 | 2020-06-10 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:37 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.10 | RM90-53-1 BHC-PEX-HRLA-SP | SANTOS LIMITED | RM90-53-1 | SAVANNA DRILLING #407 | J.20.063246 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-26 18:00 |  | 2020-05-26 18:00 | 2020-05-27 18:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:37 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.35 | RM68-68-1 | SANTOS LIMITED | RM68-68-1 | SAVANNA DRILLING #407 | J.20.063242 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-13 02:00 |  | 2020-08-13 03:00 | 2020-08-14 03:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:36 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 9493.18 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.09 | RM90-42-1-BHC-HRLA-PEX | SANTOS LIMITED | RM90-42-1 | SAVANNA DRILLING #407 | J.20.063241 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2019-12-29 20:00 | 2020-05-30 18:00 |  | 2020-05-30 18:00 | 2020-05-31 18:00 |  | 2019-12-30 20:00 | Roma WL | MRony2 | 2022-10-03 13:36 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 |  |  | L3 - Full RO |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.24 | RM28-21-1 | SANTOS LIMITED | RM28-21-1 | SAVANNA DRILLING #407 | J.20.063237 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-08 22:00 |  | 2020-07-09 23:00 | 2020-07-11 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:36 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 21281.35 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.40 | RM09-66-1 Quad Combo | SANTOS LIMITED | RM09-66-1 | SAVANNA DRILLING #407 | J.20.063234 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-09-04 23:00 |  | 2020-09-04 23:00 | 2020-09-05 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:35 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 |  |  |  |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.29 | RM68-60-1 Quad Combo | SANTOS LIMITED | RM68-60-1 | SAVANNA DRILLING #407 | J.20.063233 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-29 03:00 |  | 2020-07-29 03:00 | 2020-07-30 03:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:35 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.11 | RM28-17-1 | SANTOS LIMITED | RM28-17-1 | SAVANNA DRILLING #407 | J.20.063232 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-28 17:00 |  | 2020-05-29 18:00 | 2020-05-30 18:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:35 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.03 | RM90-21-1 | SANTOS LIMITED | RM90-21-1 | SAVANNA DRILLING #407 | J.20.063231 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-05 09:00 |  | 2020-05-06 10:00 | 2020-05-07 10:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:35 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 |  |  |  |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.01 | RM90-09-1 | SANTOS LIMITED | RM90-09-1 | SAVANNA DRILLING #407 | J.20.063230 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-30 05:00 |  | 2020-05-01 06:00 | 2020-05-02 06:00 |  |  | Roma WL | MEketone | 2022-10-03 13:35 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.39 | RM09-67-1 QC | SANTOS LIMITED | RM09-67-1 | SAVANNA DRILLING #407 | J.20.063223 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-03 |  | 2020-09-03 | 2020-09-04 |  |  | Roma WL | MRony2 | 2022-10-03 13:34 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.33 | RM68-61-1 | SANTOS LIMITED | RM68-61-1 | SAVANNA DRILLING #407 | J.20.063222 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-05 02:00 |  | 2020-08-06 18:00 | 2020-08-07 18:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:34 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.21 | RM68-106-1 BHC-HRLA-PEX-GR-SP | SANTOS LIMITED | RM68-106-1 | SAVANNA DRILLING #407 | J.20.063221 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-30 06:00 |  | 2020-06-30 06:00 | 2020-07-01 06:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:34 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.18 | RM68-103-1 BHC-HRLA-PEX | SANTOS LIMITED | RM68-103-1 | SAVANNA DRILLING #407 | J.20.063220 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-23 12:00 |  | 2020-06-23 12:00 | 2020-06-24 12:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:34 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.13 | RM28-19-1_QC-MDT | SANTOS LIMITED | RM28-19 | SAVANNA DRILLING #407 | J.20.063219 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-04 17:00 |  | 2020-06-05 10:00 | 2020-06-06 10:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:34 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 72261.21 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.08 | Santos ¦ BHC-HRLA-PEX-SP | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.20.063218 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-05-30 15:00 |  | 2020-05-30 15:00 | 2020-05-31 15:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:34 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 |  |  |  |  | 50 | 16.7 | 0 | 25 | 27.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.03 | A.1001663.03.26 | RM28-25-1 | SANTOS LIMITED | RM28-25-1 | SAVANNA DRILLING #407 | J.20.063215 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Required | In Progress |  | 2020-07-19 02:00 |  | 2020-07-20 03:00 | 2020-07-21 03:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:33 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.02 | A.1001663.02.01 | QC_MDT_RM21-17-1 | SANTOS LIMITED | RM21-17-1 | SAVANNA DRILLING #407 | J.20.063290 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-11 18:00 |  | 2020-01-12 12:00 | 2020-01-16 12:00 |  |  | Roma WL | JEsmeralda | 2022-10-03 13:43 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.53 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.22.110225 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-03-22 06:00 |  | 2022-03-22 06:00 | 2022-03-23 06:00 |  |  | Roma WL | EDelange | 2022-10-03 13:43 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.36 | RM50-151-1 | SANTOS LIMITED | RM50-151-1 | SAVANNA DRILLING #407 | J.20.063294 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2020-01-20 01:00 | 2020-04-12 |  | 2020-04-14 23:00 | 2020-04-17 23:00 |  | 2020-01-23 01:00 | Roma WL | EDelange | 2022-10-03 13:43 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.20 | Santos ¦ RM50-137-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM50-137-1 | SAVANNA DRILLING #407 | J.20.063293 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-30 08:00 |  | 2020-04-01 14:00 | 2020-04-02 14:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:43 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.34 | PEX_RM21-20-1 | SANTOS LIMITED | RM21-20-1 | SAVANNA DRILLING #407 | J.20.063289 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-05 12:00 |  | 2020-01-05 14:00 | 2020-01-06 |  |  | Roma WL | LVaiciulyte | 2022-10-03 13:43 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Laura Vaiciulyte |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.58 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.22.110224 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-04-06 05:00 |  | 2022-04-06 05:00 | 2022-04-07 05:00 |  |  | Roma WL | EDelange | 2022-10-03 13:42 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.22 | QC | SANTOS LIMITED | RM50-138-1 | SAVANNA DRILLING #407 | J.20.063286 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-04 08:00 |  | 2020-04-04 10:00 | 2020-04-05 10:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:42 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.59 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.22.110222 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-04-09 05:00 |  | 2022-04-09 05:00 | 2022-04-10 05:00 |  |  | Roma WL | EDelange | 2022-10-03 13:41 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.48 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.22.110221 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-03-06 06:00 |  | 2022-03-06 06:00 | 2022-03-07 06:00 |  |  | Roma WL | EDelange | 2022-10-03 13:41 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.21 | Santos ¦ RM50-127-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM50-127-1 | SAVANNA DRILLING #407 | J.20.063279 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-02 08:00 |  | 2020-04-04 13:00 | 2020-04-05 13:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:41 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.18 | Santos ¦ RM90-14-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM90-14-1 | SAVANNA DRILLING #407 | J.20.063278 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-24 08:00 |  | 2020-03-24 09:00 | 2020-03-25 09:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:41 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.54 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.22.110220 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-03-25 06:00 |  | 2022-03-25 06:00 | 2022-03-26 06:00 |  |  | Roma WL | EDelange | 2022-10-03 13:40 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.42 | QC - MDT | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.20.063270 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2020-04-27 07:00 | 2020-04-27 06:00 |  | 2020-04-27 06:00 | 2020-04-28 06:00 |  | 2020-04-29 19:00 | Roma WL | EDelange | 2022-10-03 13:40 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 |  |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.10 | Santos ¦ BHC-HRLA-PEX ¦ RM49-148-1 | SANTOS LIMITED | RM49-148-1 | SAVANNA DRILLING #407 | J.20.063269 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-12 14:00 |  | 2020-02-12 14:00 | 2020-02-13 14:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:40 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.29 | RM50-151-1 BHC-PEX-HRLA-GR-SP | SANTOS LIMITED | RM50-151-1 | SAVANNA DRILLING #407 | J.20.063267 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2020-01-21 09:00 | 2020-04-14 07:00 |  | 2020-04-14 07:00 | 2020-04-15 07:00 |  | 2020-01-22 09:00 | Roma WL | VOliveira5 | 2022-10-03 13:40 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.15 | Santos ¦ RM90-33-1 ¦ BHC-HRLA-PEX-SP | SANTOS LIMITED | RM90-33 1 | SAVANNA DRILLING #407 | J.20.063266 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-14 08:00 |  | 2020-03-14 08:00 | 2020-03-15 08:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:40 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.07 | Santos ¦ RM90-10-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM90-10-1 | SAVANNA DRILLING #407 | J.20.063265 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-21 22:00 |  | 2020-01-31 20:00 | 2020-02-01 20:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:40 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.41 | RM50-154-1 | SANTOS LIMITED | RM50-154-1 | SAVANNA DRILLING #407 | J.20.063261 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-25 06:00 |  | 2020-04-25 06:00 | 2020-04-26 06:00 |  |  | Roma WL | EDelange | 2022-10-03 13:39 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.26 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.20.063260 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-14 |  | 2020-04-14 | 2020-04-15 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:39 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 5360.62 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.19 | Santos ¦ RM50-115-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM50-115-1 | SAVANNA DRILLING #407 | J.20.063259 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-26 08:00 |  | 2020-03-26 11:00 | 2020-03-27 11:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:39 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.17 | Santos ¦ BHC-HRLA-PEX ¦ RM90-22-1 | SANTOS LIMITED | RM90-22-1 | SAVANNA DRILLING #407 | J.20.063258 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-20 08:00 |  | 2020-03-20 08:00 | 2020-03-21 08:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:39 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.02 | QC | SANTOS LIMITED | RM21-11 1 | SAVANNA DRILLING #407 | J.19.060640 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-12-19 | 2019-12-22 |  | 2019-12-22 | 2019-12-23 |  | 2019-12-20 | Roma WL | VOliveira5 | 2022-10-03 13:39 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 0 |  |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.47 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.22.110219 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-03-03 06:00 |  | 2022-03-03 06:00 | 2022-03-04 06:00 |  |  | Roma WL | EDelange | 2022-10-03 13:39 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.35 | PEX_RM21-21-1 | SANTOS LIMITED | RM21-21-1 | SAVANNA DRILLING #407 | J.20.063256 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-09 12:00 |  | 2020-01-09 13:00 | 2020-01-10 |  |  | Roma WL | LVaiciulyte | 2022-10-03 13:39 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Laura Vaiciulyte |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.33 | QC/MDT | SANTOS LIMITED | RM21-18-1 | SAVANNA DRILLING #407 | J.19.060639 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2019-12-30 12:00 |  | 2019-12-31 09:00 | 2020-01-03 |  |  | Roma WL | LVaiciulyte | 2022-10-03 13:39 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Laura Vaiciulyte |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.01 | QC | SANTOS LIMITED | RM21-10 1 | SAVANNA DRILLING #407 | J.19.060638 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2019-12-21 12:00 |  | 2019-12-21 15:00 | 2019-12-22 15:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:39 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.55 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.22.110217 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-03-28 06:00 |  | 2022-03-28 06:00 | 2022-03-29 06:00 |  |  | Roma WL | EDelange | 2022-10-03 13:38 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.38 | RM50-152-1 BHC-PEX-HRLA | SANTOS LIMITED | RM50-152-1 | SAVANNA DRILLING #407 | J.20.063254 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-18 |  | 2020-04-18 | 2020-04-19 |  |  | Roma WL | EDelange | 2022-10-03 13:38 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.30 | PEX_RM90-46-1 | SANTOS LIMITED | RM90-46 1 | SAVANNA DRILLING #407 | J.20.063253 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-14 22:00 |  | 2020-01-15 22:00 | 2020-01-16 22:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:38 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.23 | Santos ¦ RM50-128-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM50-128-1 | SAVANNA DRILLING #407 | J.20.063252 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-06 07:00 |  | 2020-04-06 12:00 | 2020-04-07 12:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:38 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.13 | QC | SANTOS LIMITED | RM90-25-1 | SAVANNA DRILLING #407 | J.20.063251 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-22 10:00 |  | 2020-02-22 10:00 | 2020-03-04 15:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:38 | FDPSystemUser |  | No |  |  |  |  | Lisa Delange |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.11 | QC - RM49-160-1 - Sav407 | SANTOS LIMITED | RM49-160-1 | SAVANNA DRILLING #407 | J.20.063250 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-15 |  | 2020-02-15 23:00 | 2020-02-16 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:38 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.60 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.22.110216 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-04-12 05:00 |  | 2022-04-12 05:00 | 2022-04-13 05:00 |  |  | Roma WL | EDelange | 2022-10-03 13:37 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.56 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.22.110215 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-03-31 06:00 |  | 2022-03-31 06:00 | 2022-04-01 06:00 |  |  | Roma WL | EDelange | 2022-10-03 13:37 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.27 | Rm50-140-1 BHC-PEX-HRLA-GR-SP | SANTOS LIMITED | RM50-140-1 | SAVANNA DRILLING #407 | J.20.063245 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-11 09:00 |  | 2020-04-11 09:00 | 2020-04-12 09:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:37 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.16 | Santos ¦ RM90-23-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM90231 | SAVANNA DRILLING #407 | J.20.063244 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-17 08:00 |  | 2020-03-17 08:00 | 2020-03-18 08:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:37 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.05 | Santos ¦ RM90-24-1¦ BHC-HRLA-PEX | SANTOS LIMITED | RM90-24-1 | SAVANNA DRILLING #407 | J.20.063243 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2020-01-12 21:00 | 2020-01-24 08:00 |  | 2020-01-24 20:00 | 2020-01-25 20:00 |  | 2020-02-15 10:42 | Roma WL | VOliveira5 | 2022-10-03 13:37 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 5360.62 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 25 | 20 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.49 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.22.110213 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-03-09 06:00 |  | 2022-03-09 06:00 | 2022-03-10 06:00 |  |  | Roma WL | EDelange | 2022-10-03 13:36 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.28 | RM50-151-1 BHC-HRLA-PEX-GR-SP | SANTOS LIMITED | RM50-155-1 | SAVANNA DRILLING #407 | J.20.063240 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2020-01-24 02:00 | 2020-04-14 |  | 2020-04-14 | 2020-04-15 |  | 2020-01-25 02:00 | Roma WL | VOliveira5 | 2022-10-03 13:36 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.24 | RM50-139-1 | SANTOS LIMITED | RM50-139-1 | SAVANNA DRILLING #407 | J.20.063239 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-09 |  | 2020-04-09 15:00 | 2020-04-10 15:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:36 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.57 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.22.110211 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-04-03 05:00 |  | 2022-04-03 05:00 | 2022-04-04 05:00 |  |  | Roma WL | EDelange | 2022-10-03 13:36 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.40 | RM50-153-1 | SANTOS LIMITED | RM50-153-1 | SAVANNA DRILLING #407 | J.20.063236 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Execute - PSD |  | In Progress | Not Started | In Progress | 2020-01-19 02:00 | 2020-04-21 14:00 |  | 2020-04-22 | 2020-04-23 10:00 |  | 2020-01-20 12:00 | Roma WL | EDelange | 2022-10-03 13:36 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.03 | QC | SANTOS LIMITED | RM21-19 1 | SAVANNA DRILLING #407 | J.20.063235 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2019-12-28 23:00 | 2020-01-02 22:00 |  | 2020-01-03 22:00 | 2020-01-04 22:00 |  | 2020-01-04 22:00 | Roma WL | VOliveira5 | 2022-10-03 13:36 | FDPSystemUser |  | No |  |  |  |  | Mohammad Rashed Al Rony |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 25 | 20 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.52 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.22.110210 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-03-19 06:00 |  | 2022-03-19 06:00 | 2022-03-20 06:00 |  |  | Roma WL | EDelange | 2022-10-03 13:35 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.43 | RM90-08-1 | SANTOS LIMITED | RM90-08-1 | SAVANNA DRILLING #407 | J.20.063229 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-27 06:00 |  | 2020-04-27 06:00 | 2020-04-29 18:00 |  |  | Roma WL | EDelange | 2022-10-03 13:35 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.39 | QC-No RO | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.20.063228 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2020-01-19 02:00 | 2020-04-22 |  | 2020-04-22 | 2020-04-23 |  | 2020-01-20 02:00 | Roma WL | EDelange | 2022-10-03 13:35 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 |  |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.14 | QC_RM90-34-1 | SANTOS LIMITED | RM90341 | SAVANNA DRILLING #407 | J.20.063227 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-08 12:00 |  | 2020-03-08 14:00 | 2020-03-09 14:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:35 | FDPSystemUser |  | No |  |  |  |  | Lisa Delange |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.12 | Santos ¦ RM90-13-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM90-13-1 | SAVANNA DRILLING #407 | J.20.063226 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-18 09:00 |  | 2020-02-18 20:00 | 2020-02-19 20:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:35 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.09 | Santos ¦ RM49-137-1 ¦ BHC-RLA-PEX | SANTOS LIMITED | RM49-137-1 | SAVANNA DRILLING #407 | J.20.063225 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-03 |  | 2020-02-10 03:00 | 2020-02-11 03:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:34 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.06 | Santos ¦ RM90-35-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM90-35-1 | SAVANNA DRILLING #407 | J.20.063224 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-27 22:00 |  | 2020-01-28 08:00 | 2020-01-29 08:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:34 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.51 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.22.110209 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-03-16 06:00 |  | 2022-03-16 06:00 | 2022-03-17 06:00 |  |  | Roma WL | EDelange | 2022-10-03 13:34 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.46 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.22.110208 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-02-28 06:00 |  | 2022-02-28 06:00 | 2022-03-01 06:00 |  |  | Roma WL | EDelange | 2022-10-03 13:34 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.45 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.22.110207 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-02-25 06:00 |  | 2022-02-25 06:00 | 2022-02-26 06:00 |  |  | Roma WL | EDelange | 2022-10-03 13:34 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.31 | PEX-HRLA-BHC/TLD-CCL | SANTOS LIMITED | RM21-15 1 | SAVANNA DRILLING #407 | J.19.060630 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-26 08:30 |  | 2019-12-26 10:00 | 2019-12-26 22:49 |  |  | Roma WL | LVaiciulyte | 2022-10-03 13:33 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Laura Vaiciulyte |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.25 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.20.063217 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-11 |  | 2020-04-11 | 2020-04-12 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:33 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 10721.24 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.50 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.22.110206 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-03-13 06:00 |  | 2022-03-13 06:00 | 2022-03-14 06:00 |  |  | Roma WL | EDelange | 2022-10-03 13:33 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.44 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #407 | J.20.063214 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2020-01-13 08:00 | 2020-04-30 06:00 |  | 2020-04-30 06:00 | 2020-05-01 06:00 |  | 2020-01-14 08:00 | Roma WL | EDelange | 2022-10-03 13:33 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 |  |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.37 | RM50-141-1 BHC-PEX-HRLA | SANTOS LIMITED | RM50-141-1 | SAVANNA DRILLING #407 | J.20.063213 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-15 01:30 |  | 2020-04-15 01:30 | 2020-04-16 01:30 |  |  | Roma WL | EDelange | 2022-10-03 13:33 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.32 | QC-RM21-16-1 | SANTOS LIMITED | RM21-16-1 | SAVANNA DRILLING #407 | J.19.060629 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2019-12-28 17:00 |  | 2019-12-28 18:00 | 2019-12-29 |  |  | Roma WL | LVaiciulyte | 2022-10-03 13:33 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Laura Vaiciulyte |  | 10389.86 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.08 | Santos ¦ RM49-146-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM49-146-1 | SAVANNA DRILLING #407 | J.20.063212 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2020-01-19 13:00 | 2020-01-28 |  | 2020-02-09 12:00 | 2020-02-10 12:00 |  | 2020-02-10 13:00 | Roma WL | VOliveira5 | 2022-10-03 13:33 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 50 | 27.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001663 | O.1001663.01 | A.1001663.01.04 | Santos ¦ RM90-57-1 ¦ BHC-HRLA-PEX-SP | SANTOS LIMITED | RM90-57 1 | SAVANNA DRILLING #407 | J.20.063211 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-18 08:00 |  | 2020-01-18 23:00 | 2020-01-19 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:33 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001643 | O.1001643.02 | A.1001643.02.02 | FMI-SSCAN | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.19.060624 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-11-02 22:00 | 2019-11-16 22:00 |  | 2019-11-16 22:00 | 2019-11-18 22:00 |  | 2019-11-04 22:00 | Roma WL | VOliveira5 | 2022-10-03 13:31 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001643 | O.1001643.02 | A.1001643.02.01 | FMI-SSCAN | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.19.060623 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-11-02 22:00 | 2019-11-02 22:00 |  | 2019-11-02 22:00 | 2019-11-04 22:00 |  | 2019-11-04 22:00 | Roma WL | VOliveira5 | 2022-10-03 13:31 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001643 | O.1001643.02 | A.1001643.02.05 | FMI-SSCAN | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.20.063187 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-04 22:00 |  | 2020-04-04 22:00 | 2020-04-06 22:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:28 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001643 | O.1001643.02 | A.1001643.02.03 | FMI-SSCAN | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.19.060614 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-11-02 22:00 | 2019-11-30 22:00 |  | 2019-11-30 22:00 | 2019-12-02 22:00 |  | 2019-11-04 22:00 | Roma WL | VOliveira5 | 2022-10-03 13:27 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001643 | O.1001643.02 | A.1001643.02.04 | FMI-SSCAN | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.20.063121 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-21 22:00 |  | 2020-01-21 22:00 | 2020-01-23 22:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:18 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.23 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.20.063210 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-12 22:00 |  | 2020-02-12 22:00 | 2020-02-13 22:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:33 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.12 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.19.060628 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-26 23:00 | 2019-12-02 22:00 |  | 2019-12-02 22:00 | 2019-12-03 22:00 |  | 2019-10-27 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:33 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.05 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.19.060627 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-26 23:00 | 2019-11-08 22:00 |  | 2019-11-08 22:00 | 2019-11-09 22:00 |  | 2019-10-27 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:32 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.08 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.19.060622 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-26 23:00 | 2019-11-19 22:00 |  | 2019-11-19 22:00 | 2019-11-20 22:00 |  | 2019-10-27 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:31 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.02 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.19.060618 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-26 23:00 | 2019-10-29 23:00 |  | 2019-10-29 23:00 | 2019-10-30 23:00 |  | 2019-10-27 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:28 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.15 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.19.060613 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-26 23:00 | 2019-12-13 22:00 |  | 2019-12-13 22:00 | 2019-12-14 22:00 |  | 2019-10-27 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:27 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.18 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED | Orana 298 | SAVANNA DRILLING #449 | J.20.063174 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2020-01-27 12:00 |  | 2020-01-27 14:00 | 2020-01-28 14:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:26 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.06 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.19.060607 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-26 23:00 | 2019-11-12 22:00 |  | 2019-11-12 22:00 | 2019-11-13 22:00 |  | 2019-10-27 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:24 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.03 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.19.060606 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-26 23:00 | 2019-11-01 22:00 |  | 2019-11-01 22:00 | 2019-11-02 22:00 |  | 2019-10-27 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:24 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.14 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.19.060603 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-26 23:00 | 2019-12-09 22:00 |  | 2019-12-09 22:00 | 2019-12-10 22:00 |  | 2019-10-27 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:23 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.10 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.19.060602 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-26 23:00 | 2019-11-26 22:00 |  | 2019-11-26 22:00 | 2019-11-27 22:00 |  | 2019-10-27 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:23 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.07 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.19.060601 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-26 23:00 | 2019-11-16 22:00 |  | 2019-11-16 22:00 | 2019-11-17 22:00 |  | 2019-10-27 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:23 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.17 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED | Orana 305 | SAVANNA DRILLING #449 | J.20.063140 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-24 22:00 |  | 2020-01-25 06:00 | 2020-01-26 06:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:21 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.09 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.19.060593 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-26 23:00 | 2019-11-23 22:00 |  | 2019-11-23 22:00 | 2019-11-24 22:00 |  | 2019-10-27 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:19 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.24 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.20.063104 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-16 22:00 |  | 2020-02-16 22:00 | 2020-02-17 22:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.21 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.20.063103 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-04 22:00 |  | 2020-02-04 22:00 | 2020-02-05 22:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.16 | PEX-AIT-GPIT_Sav449 | ORIGIN ENERGY RESOURCES LIMITED | ORANA NORTH 312 | SAVANNA DRILLING #449 | J.20.063094 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2020-01-22 13:00 | 2020-01-19 06:00 |  | 2020-01-22 12:00 | 2020-01-24 18:00 |  | 2020-01-28 19:00 | Roma WL | VOliveira5 | 2022-10-03 13:14 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 4320.99 |  |  | L0 - No RO |  | 50 | 0 | 0 | 25 | 22.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.04 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.19.060584 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-26 23:00 | 2019-11-04 22:00 |  | 2019-11-04 22:00 | 2019-11-05 22:00 |  | 2019-10-27 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.11 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.19.060579 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-26 23:00 | 2019-11-29 22:00 |  | 2019-11-29 22:00 | 2019-11-30 22:00 |  | 2019-10-27 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:11 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.20 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED | Talinga 291 | SAVANNA DRILLING #449 | J.20.063069 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2020-02-03 08:00 |  | 2020-02-03 20:00 | 2020-02-04 20:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:10 | FDPSystemUser |  | No |  |  |  |  | Lisa Delange |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.01 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.19.060577 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-26 23:00 | 2019-10-26 23:00 |  | 2019-10-26 23:00 | 2019-10-27 23:00 |  | 2019-10-27 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.19 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED | Orana 291 | SAVANNA DRILLING #449 | J.20.063063 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-31 14:00 |  | 2020-02-01 14:00 | 2020-02-02 14:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:09 | FDPSystemUser |  | No |  |  |  |  | Lisa Delange |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.13 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.19.060572 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-26 23:00 | 2019-12-05 22:00 |  | 2019-12-05 22:00 | 2019-12-06 22:00 |  | 2019-10-27 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:09 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.25 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.20.063053 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-19 22:00 |  | 2020-02-19 22:00 | 2020-02-20 22:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:07 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001643 | O.1001643.01 | A.1001643.01.22 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #449 | J.20.063052 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-08 22:00 |  | 2020-02-08 22:00 | 2020-02-09 22:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:07 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001642 | O.1001642.02 | A.1001642.02.02 | MDT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #408 | J.20.063203 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-16 23:00 |  | 2020-01-17 23:00 | 2020-01-19 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:31 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001642 | O.1001642.02 | A.1001642.02.01 | MDT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #408 | J.19.060605 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-19 | 2019-10-18 |  | 2019-10-19 | 2019-10-20 23:00 |  | 2019-10-20 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:24 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001642 | O.1001642.01 | A.1001642.01.14 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #408 | J.19.060626 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-28 23:00 | 2019-12-09 22:00 |  | 2019-12-09 22:00 | 2019-12-10 22:00 |  | 2019-10-29 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:32 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001642 | O.1001642.01 | A.1001642.01.18 | PEX-AIT-GPIT - Combabula 380 | ORIGIN ENERGY RESOURCES LIMITED | Combabula380 | SAVANNA DRILLING #408 | J.20.063186 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-21 20:00 |  | 2020-01-21 20:00 | 2020-01-22 20:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:28 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001642 | O.1001642.01 | A.1001642.01.07 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #408 | J.19.060617 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-28 23:00 | 2019-11-16 22:00 |  | 2019-11-16 22:00 | 2019-11-17 22:00 |  | 2019-10-29 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:28 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001642 | O.1001642.01 | A.1001642.01.22 | PEX-AIT-GPIT Reedy Creek 075 | ORIGIN ENERGY RESOURCES LIMITED | Reedy Creek 75 | SAVANNA DRILLING #408 | J.20.063173 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-01 22:00 |  | 2020-02-02 23:00 | 2020-02-03 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:25 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001642 | O.1001642.01 | A.1001642.01.21 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED | Reedy Creek 71 | SAVANNA DRILLING #408 | J.20.063155 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-29 22:00 |  | 2020-01-30 22:00 | 2020-01-31 22:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:22 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001642 | O.1001642.01 | A.1001642.01.20 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED | Reedy Creek 72 | SAVANNA DRILLING #408 | J.20.063154 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-25 13:00 |  | 2020-01-28 12:00 | 2020-01-29 12:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:22 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001642 | O.1001642.01 | A.1001642.01.13 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #408 | J.19.060600 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-28 23:00 | 2019-12-05 22:00 |  | 2019-12-05 22:00 | 2019-12-06 22:00 |  | 2019-10-29 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:22 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001642 | O.1001642.01 | A.1001642.01.04 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #408 | J.19.060599 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-28 23:00 | 2019-11-04 22:00 |  | 2019-11-04 22:00 | 2019-11-05 22:00 |  | 2019-10-29 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:22 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001642 | O.1001642.01 | A.1001642.01.01 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #408 | J.19.060598 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-14 | 2019-10-26 23:00 |  | 2019-10-26 23:00 | 2019-10-27 23:00 |  | 2019-10-15 | Roma WL | VOliveira5 | 2022-10-03 13:22 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001642 | O.1001642.01 | A.1001642.01.17 | PEX-AIT-GPIT - Combabula 376 | ORIGIN ENERGY RESOURCES LIMITED | Combabula376 | SAVANNA DRILLING #408 | J.20.063127 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-19 22:00 |  | 2020-01-20 12:00 | 2020-01-21 12:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:19 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001642 | O.1001642.01 | A.1001642.01.24 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #408 | J.20.063120 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-15 22:00 |  | 2020-02-15 22:00 | 2020-02-16 22:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:18 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001642 | O.1001642.01 | A.1001642.01.16 | PEX-AIT-GPIT - Combabula 375 | ORIGIN ENERGY RESOURCES LIMITED | Combabula375 | SAVANNA DRILLING #408 | J.20.063102 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-16 22:00 |  | 2020-01-16 22:00 | 2020-01-17 22:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:15 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001642 | O.1001642.01 | A.1001642.01.08 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #408 | J.19.060587 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-28 23:00 | 2019-11-19 22:00 |  | 2019-11-19 22:00 | 2019-11-20 22:00 |  | 2019-10-29 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001642 | O.1001642.01 | A.1001642.01.12 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #408 | J.19.060583 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-28 23:00 | 2019-12-02 22:00 |  | 2019-12-02 22:00 | 2019-12-03 22:00 |  | 2019-10-29 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001642 | O.1001642.01 | A.1001642.01.06 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #408 | J.19.060582 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-28 23:00 | 2019-11-12 22:00 |  | 2019-11-12 22:00 | 2019-11-13 22:00 |  | 2019-10-29 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001642 | O.1001642.01 | A.1001642.01.05 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #408 | J.19.060581 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-28 23:00 | 2019-11-08 22:00 |  | 2019-11-08 22:00 | 2019-11-09 22:00 |  | 2019-10-29 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001642 | O.1001642.01 | A.1001642.01.19 | PEX-AIT-GPIT - Reedy Creek 105 | ORIGIN ENERGY RESOURCES LIMITED | Reedy Creek 105 | SAVANNA DRILLING #408 | J.20.063080 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-24 06:00 |  | 2020-01-24 06:00 | 2020-01-25 06:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:11 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001642 | O.1001642.01 | A.1001642.01.02 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #408 | J.19.060578 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-28 23:00 | 2019-10-29 23:00 |  | 2019-10-29 23:00 | 2019-10-30 23:00 |  | 2019-10-29 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:11 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001642 | O.1001642.01 | A.1001642.01.15 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #408 | J.19.060576 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-11-01 23:00 | 2019-12-13 22:00 |  | 2019-12-13 22:00 | 2019-12-14 22:00 |  | 2019-11-02 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001642 | O.1001642.01 | A.1001642.01.11 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #408 | J.19.060575 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-16 | 2019-11-29 22:00 |  | 2019-11-29 22:00 | 2019-11-30 22:00 |  | 2019-10-17 | Roma WL | VOliveira5 | 2022-10-03 13:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001642 | O.1001642.01 | A.1001642.01.09 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #408 | J.19.060574 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-28 23:00 | 2019-11-23 22:00 |  | 2019-11-23 22:00 | 2019-11-24 22:00 |  | 2019-10-29 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001642 | O.1001642.01 | A.1001642.01.23 | PEX-AIT-GPIT - RCK286 | ORIGIN ENERGY RESOURCES LIMITED | Reedy Creek 286 | SAVANNA DRILLING #408 | J.20.063051 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-03 22:00 |  | 2020-02-04 23:00 | 2020-02-05 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:07 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5068.23 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001642 | O.1001642.01 | A.1001642.01.10 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #408 | J.19.060569 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-28 23:00 | 2019-11-26 22:00 |  | 2019-11-26 22:00 | 2019-11-27 22:00 |  | 2019-10-29 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:07 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001642 | O.1001642.01 | A.1001642.01.03 | PEX-AIT-GPIT | ORIGIN ENERGY RESOURCES LIMITED |  | SAVANNA DRILLING #408 | J.19.060568 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-28 23:00 | 2019-11-01 22:00 |  | 2019-11-01 22:00 | 2019-11-02 22:00 |  | 2019-10-29 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:07 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001641 | O.1001641.02 | A.1001641.02.03 | FMI-SSCAN | SANTOS LIMITED |  | Ensign 968 | J.19.060621 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-11-04 23:00 | 2019-12-02 23:00 |  | 2019-12-02 23:00 | 2019-12-05 23:00 |  | 2019-11-07 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:31 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001641 | O.1001641.02 | A.1001641.02.01 | FMI-SSCAN | SANTOS LIMITED |  | Ensign 968 | J.19.060612 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-11-04 23:00 | 2019-11-04 23:00 |  | 2019-11-04 23:00 | 2019-11-07 23:00 |  | 2019-11-07 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:27 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001641 | O.1001641.02 | A.1001641.02.04 | FMI-SSCAN | SANTOS LIMITED |  | Ensign 968 | J.19.060609 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-23 23:00 |  | 2019-12-23 23:00 | 2019-12-26 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:25 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001641 | O.1001641.02 | A.1001641.02.05 | FMI-SSCAN | SANTOS LIMITED |  | Ensign 968 | J.20.063153 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-02 23:00 |  | 2020-01-02 23:00 | 2020-01-05 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:22 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001641 | O.1001641.02 | A.1001641.02.02 | FMI-SSCAN | SANTOS LIMITED |  | Ensign 968 | J.19.060580 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-11-04 23:00 | 2019-11-18 23:00 |  | 2019-11-18 23:00 | 2019-11-21 23:00 |  | 2019-11-07 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.39 | FV07-01-4_QC | SANTOS LIMITED | FV07-01-4 | Ensign 968 | J.23.088121 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-08-02 10:00 | 2023-08-01 | 2023-08-02 | 2023-08-02 10:00 | 2023-08-03 10:00 | 2023-08-04 | 2023-08-03 10:00 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 3 |  | L2 - Shift RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.42 | FV17-79-1_QC | SANTOS LIMITED | FV17-79-1, FV07-40-1 | Ensign 968 | J.23.137228 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-09-17 10:00 | 2023-09-16 | 2023-09-16 14:00 | 2023-09-17 10:00 | 2024-02-28 10:00 | 2024-02-29 | 2024-02-28 10:00 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 7764.78 | 3 |  | L2 - Shift RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.43 | Longvale 1 | SANTOS LIMITED | FV17-79-1, FV07-40-1 | Ensign 968 | J.24.035870 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2024-01-04 10:00 | 2024-01-03 |  | 2024-01-04 10:00 | 2024-02-24 10:00 |  | 2024-02-24 10:00 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 66.7 | 33.3 | 0 | 0 | 30 |  | 2 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.44 | Hardenley 14 SC-MDT | SANTOS LIMITED | HARDENLEY 14 | Ensign 968 | J.24.131364 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-12-17 08:00 | 2024-07-25 |  | 2024-07-27 | 2024-07-31 23:59 |  | 2024-07-31 23:59 | Roma WL | JEsmeralda | 2024-08-15 | SNiang |  | No |  |  |  | ROE WL Jakarta | Shameer Mumtaz Ali |  | 0 | 2 |  | L2 - Shift RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.41 | MDT Late October | SANTOS LIMITED |  | Ensign 968 | J.23.088123 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-23 10:00 | 2023-10-22 | 2023-10-23 01:00 | 2023-10-23 10:00 | 2023-10-24 10:00 | 2023-10-25 01:00 | 2023-10-24 10:00 | Roma WL | KKeese | 2023-08-29 11:19 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 3 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.40 | MDT Early October | SANTOS LIMITED |  | Ensign 968 | J.23.088122 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-09 10:00 | 2023-10-08 | 2023-10-09 01:00 | 2023-10-09 10:00 | 2023-10-10 10:00 | 2023-10-11 01:00 | 2023-10-10 10:00 | Roma WL | KKeese | 2023-08-29 11:19 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 3 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.33 | QC and MDT on Dulacca West 1 Corehole | SANTOS LIMITED |  | Ensign 968 | J.23.041214 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-09-25 10:00 | 2023-09-24 | 2023-09-25 | 2023-09-25 10:00 | 2023-09-26 10:00 | 2023-09-27 | 2023-09-26 10:00 | Roma WL | SAli63 | 2023-08-29 11:19 | KKeese |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.34 | QC and MDT on Bundaleer-1 | SANTOS LIMITED |  | Ensign 968 | J.23.041215 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-06-03 10:00 | 2023-06-02 |  | 2023-06-03 10:00 | 2023-06-04 10:00 |  | 2023-06-04 10:00 | Roma WL | SAli63 | 2023-06-13 14:45 | KKeese |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  | L2 - Shift RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.38 | Quad Combo | SANTOS LIMITED | FV06-55-1, FV06-60-1 | Ensign 968 | J.23.074863 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-01 10:00 | 2023-04-30 |  | 2023-05-01 10:00 | 2023-05-05 10:00 |  | 2023-05-05 10:00 | Roma WL | SAli63 | 2023-05-09 10:29 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 5 |  | L3 - Full RO |  | 83.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.36 | 3.5in SCMT | SANTOS LIMITED | FV07-51-1 | Ensign 968 | J.23.071805 | RPE | ES-CH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-04-16 18:00 | 2023-04-16 |  | 2023-04-16 18:00 | 2023-04-18 23:59 |  | 2023-04-18 23:59 | Roma WL | SAli63 | 2023-04-24 18:32 | MEketone |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 1 |  | L3 - Full RO |  | 91.7 | 50 | 0 | 50 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.37 | QC_FMI_FV06-57-1 | SANTOS LIMITED | FV06-57-1 | Ensign 968 | J.23.072641 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-04-22 10:00 | 2023-04-21 |  | 2023-04-22 10:00 | 2023-04-26 10:00 |  | 2023-04-26 10:00 | Roma WL | SAli63 | 2023-04-24 18:09 | MEketone |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 13460.04 | 2 |  | L3 - Full RO |  | 91.7 | 50 | 0 | 50 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.35 | Quad Combo | SANTOS LIMITED | FV07-54-1 | Ensign 968 | J.23.049250 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-03-03 18:00 | 2023-03-02 10:00 |  | 2023-03-03 18:00 | 2023-03-04 10:00 |  | 2023-03-04 08:00 | Roma WL | MRony2 | 2023-03-09 17:13 | handoko |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  | L3 - Full RO |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.32 | Quad Combo | SANTOS LIMITED | FV07-07-5, FV07-52-01 | Ensign 968 | J.23.039474 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-02-16 18:00 | 2023-02-15 10:00 |  | 2023-02-16 18:00 | 2023-02-27 10:00 |  | 2023-02-27 10:00 | Roma WL | ysaeedabadian | 2023-03-02 12:52 | MRony2 |  | No |  |  |  |  | Jon Lawrie |  | 19210.53 | 1 |  | L0 - No RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.31 | FV07-39-1 | SANTOS LIMITED | FV07-39-1 | Ensign 968 | J.23.027230 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-01-16 | 2023-01-14 12:00 |  | 2023-01-16 | 2023-01-17 |  | 2023-01-19 | Roma WL | MRony2 | 2023-01-18 15:24 | JEsmeralda |  | No |  |  |  |  | Jon Lawrie |  | 19210.53 | 2 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.30 | Ens968_Dec | SANTOS LIMITED | FV07-04-5 | Ensign 968 | J.22.110425 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-23 | 2022-11-21 12:00 |  | 2022-11-23 | 2022-11-24 |  | 2022-11-26 | Roma WL | MRony2 | 2022-11-26 16:57 | JEsmeralda |  | No |  |  |  |  | Jon Lawrie |  | 0 | 2 |  |  |  | 75 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.28 | ENS968_Oct | SANTOS LIMITED | FV12-112-1 | Ensign 968 | J.22.110424 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-10-21 12:00 |  | 2022-10-21 12:00 | 2022-10-22 12:00 |  |  | Roma WL | MRony2 | 2022-10-23 12:40 | KKeese |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.29 | Ens968_Nov | SANTOS LIMITED | FV12-112-1 | Ensign 968 | J.22.110426 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-11-15 12:00 |  | 2022-11-15 12:00 | 2022-11-16 12:00 |  |  | Roma WL | MRony2 | 2022-10-23 12:40 | KKeese |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.27 | QC | SANTOS LIMITED | FV12-112-1 | Ensign 968 | J.22.110403 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-08-05 12:00 |  | 2022-08-05 12:00 | 2022-08-06 12:00 |  |  | Roma WL | MRony2 | 2022-10-19 15:07 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  |  |  | 66.7 | 83.3 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.21 | QC _ Kelsall 18 | SANTOS LIMITED | Kelsall 18 | Ensign 968 | J.21.109423 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-10-01 18:00 | 2021-10-01 08:00 |  | 2021-10-01 18:00 | 2021-10-02 23:59 |  | 2021-10-02 23:59 | Roma WL | MRony2 | 2022-10-03 14:59 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 1 |  |  |  | 66.7 | 33.3 | 0 | 75 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.17 | Vincent Downs 1_QC-SScan | SANTOS LIMITED | VINCENT DOWNS 1 | Ensign 968 | J.21.109422 | RPE | ES-OH-NO | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-05-18 17:00 | 2021-05-18 |  | 2021-05-18 12:00 | 2021-05-20 12:00 |  | 2021-05-20 17:00 | Roma WL | EDelange | 2022-10-03 14:58 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 0 |  |  |  | 91.7 | 50 | 100 | 75 | 75 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.26 | Cattle creek | SANTOS LIMITED | Cattle Creek 7 | Ensign 968 | J.22.110338 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-05-17 |  | 2022-05-17 19:00 | 2022-05-20 19:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:16 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  |  |  | 41.7 | 0 | 0 | 25 | 20 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.25 | Quad combo | SANTOS LIMITED | Cattle Creek 7 | Ensign 968 | J.22.110304 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-02-08 |  | 2022-02-08 19:00 | 2022-02-11 19:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.23 | Super Combo_Cattle Creek 8 | SANTOS LIMITED | Cattle Creek 8 | Ensign 968 | J.22.110286 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-01-30 |  | 2022-01-31 19:00 | 2022-02-03 19:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 18458.09 | 2 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.24 | Super Combo and MDT | SANTOS LIMITED | Cattle Creek 6 | Ensign 968 | J.22.110280 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-02-13 12:00 |  | 2022-02-13 12:00 | 2022-02-16 12:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 18458.09 | 4 |  |  |  | 83.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.22 | Quad Combo | SANTOS LIMITED | Bottle Tree 9 | Ensign 968 | J.22.110279 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-01-15 |  | 2022-01-15 19:00 | 2022-01-18 19:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 5360.62 | 2 |  |  |  | 91.7 | 50 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.20 | QC+MDT | SANTOS LIMITED | Yoorooga East 2 | Ensign 968 | J.21.109066 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-10-13 |  | 2021-10-13 19:00 | 2021-10-16 19:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 60071.47 | 3 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.18 | Sunshine Ranch 2_QC_PPC | SANTOS LIMITED | SUNSHINE RANCH 2 | Ensign 968 | J.21.109053 | RPE | ES-OH-NO | Low | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2021-03-11 13:00 | 2021-05-31 02:00 |  | 2021-05-31 14:00 | 2021-06-02 14:00 |  | 2021-06-02 17:00 | Roma WL | EDelange | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 0 |  | L3 - Full RO |  | 75 | 50 | 100 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.19 | CBL | SANTOS LIMITED | Sunshine Ranch 3 | Ensign 968 | J.21.109000 | RPE | ES-CH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-06-29 08:00 |  | 2021-06-29 18:00 | 2021-06-30 23:59 |  |  | Roma WL | EDelange | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 50 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.04 | QC | SANTOS LIMITED | FV13-32-1 | Ensign 968 | J.19.060625 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-29 23:00 |  | 2019-12-30 23:00 | 2020-01-01 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:32 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.09 | FV08-06-1 | SANTOS LIMITED | FV08-06 1 | Ensign 968 | J.20.063202 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-26 |  | 2020-04-04 18:00 | 2020-04-06 18:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 13:30 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.08 | FMI-SS-HRLA-PEX | SANTOS LIMITED | FV06-49-1 | Ensign 968 | J.20.063201 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-07-19 19:00 |  | 2020-07-21 19:00 | 2020-07-23 19:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:30 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.07 | Supercombo | SANTOS LIMITED | FV08-02 2 | Ensign 968 | J.20.063200 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-16 18:00 |  | 2020-03-17 22:00 | 2020-03-20 22:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:30 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 7595.84 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.06 | Supercombo | SANTOS LIMITED | FV13-32-1 | Ensign 968 | J.20.063199 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-12 |  | 2020-02-13 | 2020-02-15 |  |  | Roma WL | MRony2 | 2022-10-03 13:30 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 9916.83 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.14 | QC-FMI-SS | SANTOS LIMITED | Mount Kingsley 38 | Ensign 968 | J.21.108912 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-02-09 |  | 2021-02-09 19:00 | 2021-02-11 19:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:28 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.01 | QC | SANTOS LIMITED |  | Ensign 968 | J.19.060597 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-30 | 2019-10-29 |  | 2019-10-30 | 2019-11-01 |  | 2019-11-01 | Roma WL | VOliveira5 | 2022-10-03 13:22 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.03 | QC | SANTOS LIMITED |  | Ensign 968 | J.19.060596 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-30 | 2019-12-11 23:00 |  | 2019-12-12 23:00 | 2019-12-14 23:00 |  | 2019-11-01 | Roma WL | VOliveira5 | 2022-10-03 13:21 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.15 | Mount Kingsley 40 | SANTOS LIMITED | The Rock 13, Mount Kingsley 40 | Ensign 968 | J.21.108901 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-02-15 19:00 |  | 2021-02-15 19:00 | 2021-02-17 19:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 8625.73 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.02 | QC | SANTOS LIMITED |  | Ensign 968 | J.19.060586 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-30 | 2019-11-20 23:00 |  | 2019-11-21 23:00 | 2019-11-23 23:00 |  | 2019-11-01 | Roma WL | VOliveira5 | 2022-10-03 13:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.05 | FV13-65 | SANTOS LIMITED | FV13-65-1 | Ensign 968 | J.20.063093 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-09 |  | 2020-07-13 | 2020-07-15 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.13 | The Rock 13 | SANTOS LIMITED | The Rock 13 | Ensign 968 | J.20.063079 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-21 19:00 |  | 2020-09-22 19:00 | 2020-09-24 19:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:11 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.12 | SAV968 | SANTOS LIMITED | The Rock 16 | Ensign 968 | J.20.063062 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-05 17:00 |  | 2020-09-05 19:00 | 2020-09-07 19:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 13:08 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.10 | Santos ¦ FV08-19-1 ¦ FMI-SSCAN-HRLA-PEX-SP | SANTOS LIMITED | FV08-19-1 | Ensign 968 | J.20.063061 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-17 16:00 |  | 2020-05-17 16:00 | 2020-05-19 16:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 13:08 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 18458.09 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.16 | Mount Kingsley 42 | SANTOS LIMITED | Mount Kingsley 42 | Ensign 968 | J.21.108888 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-02-20 06:00 |  | 2021-02-20 18:00 | 2021-02-22 18:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:07 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 8625.73 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001641 | O.1001641.01 | A.1001641.01.11 | SAV968 | SANTOS LIMITED | The Rock 12 | Ensign 968 | J.20.063050 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-10-03 19:00 |  | 2020-10-03 20:00 | 2020-10-06 20:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 13:07 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.04 | A.1001640.04.01 | Warrinnila 7 Corehole | SANTOS LIMITED |  | SAVANNA 165 | J.25.025343 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | Not Started | 2025-08-31 01:00 | 2025-09-01 |  | 2025-09-01 | 2025-09-08 23:59 |  | 2025-09-10 00:59 | Roma WL | JEsmeralda | 2025-09-26 16:41 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 3 |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001640 | O.1001640.04 | A.1001640.04.02 | FV13-100-1 | SANTOS LIMITED | FV13-100-1, FV08-36-2, FV13-96-1 | SAVANNA 165 | J.25.088426 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-04-29 | 2025-04-27 | 2025-04-28 | 2025-04-28 | 2025-04-30 23:59 | 2025-05-01 | 2025-04-30 23:59 | Roma WL | JEsmeralda | 2025-06-09 15:06 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 1 |  | L3 - Full RO |  | 100 | 83.3 | 100 | 83.3 | 90 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001640 | O.1001640.03 | A.1001640.03.02 | Sunnyholt 46 PEX-HRLA-BHC | SANTOS LIMITED | Sunnyholt 49 | Ensign 966 | J.20.063179 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-07 10:00 |  | 2020-02-07 10:00 | 2020-02-08 23:00 |  |  | Roma WL | LVaiciulyte | 2022-10-03 13:27 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Laura Vaiciulyte |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.03 | A.1001640.03.01 | RM49-156-1 / PEX-HRLA-BHC | SANTOS LIMITED | RM49-156 1 | Ensign 966 | J.20.063078 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-08 01:00 |  | 2020-01-08 02:00 | 2020-01-08 11:00 |  |  | Roma WL | LVaiciulyte | 2022-10-03 13:11 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Laura Vaiciulyte |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.02 | A.1001640.02.01 | MDT | SANTOS LIMITED |  | Ensign 966 | J.19.060608 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-11-12 23:00 | 2019-11-11 23:00 |  | 2019-11-12 23:00 | 2019-11-14 23:00 |  | 2019-11-14 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:25 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001640 | O.1001640.02 | A.1001640.02.02 | MDT | SANTOS LIMITED |  | Ensign 966 | J.19.060592 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-11-12 23:00 | 2019-11-26 23:00 |  | 2019-11-27 23:00 | 2019-11-29 23:00 |  | 2019-11-14 23:00 | Roma WL | VOliveira5 | 2022-10-03 13:19 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.32 | Warrinilla 12 Corehole | SANTOS LIMITED |  | Ensign 966 | J.24.180172 | RPE | ES-CH-Ops | Low | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2025-09-01 01:00 | 2025-09-01 |  | 2025-09-01 | 2025-09-07 23:59 |  | 2025-09-08 00:59 | Roma WL | JEsmeralda | 2025-02-22 15:35 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 0 | 3 |  | L3 - Full RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 2 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.31 | Glen Evis 13 | SANTOS LIMITED | GLEN EVIS 13, GLEN EVIS 12 | Ensign 966 | J.24.175858 | RPE | ES-CH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2024-10-30 | 2024-10-29 |  | 2024-10-30 | 2024-11-07 23:59 |  | 2024-11-07 23:59 | Roma WL | KKeese | 2024-11-16 14:17 | JEsmeralda |  | No |  |  |  | ROE WL Mumbai | Irwan Wongso |  | 13460.04 | 3 |  | L3 - Full RO |  | 100 | 100 | 100 | 100 | 100 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.28 | FV18-104-1 | SANTOS LIMITED | FV17-65-1 | Ensign 966 | J.24.035861 | RPE | ES-CH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2024-01-02 | 2024-01-02 |  | 2024-01-02 | 2024-01-04 23:59 |  | 2024-01-04 23:59 | Roma WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 75 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.29 | Dedicated 966_SC_Feb24 | SANTOS LIMITED | MOUNT KINGSLEY 53, MOUNT KINGSLEY 53A, MOUNT KINGSLEY 57, MOUNT KINGSLEY 55 | Ensign 966 | J.24.043684 | RPE | ES-CH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2024-01-25 | 2024-01-24 |  | 2024-01-25 | 2024-02-29 23:59 |  | 2024-02-29 23:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 13460.04 | 1 |  | L3 - Full RO |  | 91.7 | 83.3 | 100 | 100 | 92.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.30 | Dedicated 966_QC_Mar24 | SANTOS LIMITED | MOUNT KINGSLEY 53, MOUNT KINGSLEY 53A, MOUNT KINGSLEY 57, MOUNT KINGSLEY 55, MOUNT KINGSLEY 59, MOUNT KINGSLEY 51 | Ensign 966 | J.24.060086 | RPE | ES-CH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-03-01 | 2024-02-29 |  | 2024-03-01 | 2024-04-05 23:59 |  | 2024-04-05 23:59 | Roma WL | JEsmeralda | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 13460.04 | 1 |  | L3 - Full RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.27 | CBL in 9 5/8 | SANTOS LIMITED | FV17-65-1 | Ensign 966 | J.23.080930 | RPE | ES-CH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-08 | 2023-05-08 |  | 2023-05-08 | 2023-05-10 23:59 |  | 2023-05-10 23:59 | Roma WL | SAli63 | 2023-05-09 14:00 | JEsmeralda |  | No |  |  |  |  | Jon Lawrie |  | 0 | 1 |  | L0 - No RO |  | 83.3 | 16.7 | 0 | 100 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.26 | QC | SANTOS LIMITED | Woodroyd 7, FV07-50-1, FV07-39-1, FV07-56-1 | Ensign 966 | J.23.041219 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-02-21 16:00 | 2023-02-20 15:00 |  | 2023-02-21 16:00 | 2023-02-22 16:00 |  | 2023-02-22 16:00 | Roma WL | MRony2 | 2023-02-23 16:55 | ysaeedabadian |  | No |  |  |  |  | Jon Lawrie |  | 11825.86 | 1 |  | L0 - No RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.25 | FV07-50-1 | SANTOS LIMITED | Woodroyd 7, FV07-50-1 | Ensign 966 | J.22.123679 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-05 09:00 | 2022-11-02 15:00 |  | 2022-11-04 16:00 | 2022-11-05 16:00 |  | 2022-11-14 09:00 | Roma WL | MRony2 | 2022-12-05 14:03 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 11825.86 | 2 |  |  |  | 50 | 66.7 | 0 | 50 | 50 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.24 | QC | SANTOS LIMITED | Woodroyd 7 | Ensign 966 | J.22.110402 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-08-15 19:00 |  | 2022-08-18 20:00 | 2022-08-21 20:00 |  |  | Roma WL | MRony2 | 2022-10-19 20:59 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 3992.85 | 1 |  |  |  | 66.7 | 66.7 | 0 | 50 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.19 | North Scotia 1 | SANTOS LIMITED | FV12-38-1, FV12-39-1, FV12-39-2 | Ensign 966 | J.22.110884 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-04-27 08:00 | 2022-04-27 07:00 |  | 2022-04-27 08:00 | 2022-04-29 08:00 |  | 2022-05-05 08:00 | Roma WL | MRony2 | 2022-10-03 14:58 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.18 | Glen Evis 4 | SANTOS LIMITED | Glen Evis 4 | Ensign 966 | J.22.110883 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-02-22 09:00 | 2022-02-22 07:00 |  | 2022-02-22 08:00 | 2022-02-24 08:00 |  | 2022-03-02 09:00 | Roma WL | MRony2 | 2022-10-03 14:58 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.17 | Glen Evis 6 | SANTOS LIMITED | GLEN EVIS 6 | Ensign 966 | J.22.110882 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-02-18 09:00 | 2022-02-17 07:00 |  | 2022-02-18 08:00 | 2022-02-20 08:00 |  | 2022-03-04 09:00 | Roma WL | MRony2 | 2022-10-03 14:58 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.23 | North Scotia 1 | SANTOS LIMITED | North Scotia 1 | Ensign 966 | J.22.110342 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-04-23 |  | 2022-04-24 03:00 | 2022-04-26 03:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:16 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 14814.81 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.22 | Daldowie 17 | SANTOS LIMITED | Daldowie 17 | Ensign 966 | J.22.110325 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-03-30 07:00 |  | 2022-04-01 08:00 | 2022-04-03 08:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.21 | Daldowie 19 | SANTOS LIMITED | Daldowie 19, Daldowie 18 | Ensign 966 | J.22.110314 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-03-21 07:00 |  | 2022-03-21 08:00 | 2022-03-28 08:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.20 | North Scotia 6 | SANTOS LIMITED | North Scotia 1 | Ensign 966 | J.22.110307 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed |  | 2022-05-24 07:00 |  | 2022-05-27 08:00 | 2022-05-29 08:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 18908.38 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.16 | Quad Combo | SANTOS LIMITED | FV12-38-1, FV12-39-1, FV12-39-2 | Ensign 966 | J.21.109079 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-12-22 07:00 |  | 2021-12-22 08:00 | 2021-12-30 08:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 1 |  |  |  | 83.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.15 | FV13-76-2 | SANTOS LIMITED | FV13-76-2 | Ensign 966 | J.21.109078 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2021-03-10 09:00 | 2021-12-11 15:00 |  | 2021-12-12 08:00 | 2021-12-13 08:00 |  | 2021-12-13 09:00 | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 5750.49 | 1 |  | L0 - No RO |  | 91.7 | 50 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.14 | Santos ¦ FV18-81-1 ¦ BHC-HRLA-PEX-SP-GR | SANTOS LIMITED | FV11-81-1 | Ensign 966 | J.21.108919 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-10-08 15:00 |  | 2021-10-09 04:00 | 2021-10-10 04:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:32 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.11 | Santos ¦ FV13-64-1 ¦ BHC-HRLA-PEX-SP | SANTOS LIMITED | FV13-64-1 | Ensign 966 | J.20.063198 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-01 |  | 2020-06-17 | 2020-06-19 |  |  | Roma WL | MRony2 | 2022-10-03 13:30 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.02 | QC | SANTOS LIMITED | FV18-26-1 | Ensign 966 | J.20.063197 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-14 10:00 |  | 2020-04-21 23:00 | 2021-12-22 19:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:30 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.03 | QC | SANTOS LIMITED |  | Ensign 966 | J.19.060611 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-30 | 2019-12-11 23:00 |  | 2019-12-12 23:00 | 2019-12-14 23:00 |  | 2019-11-01 | Roma WL | VOliveira5 | 2022-10-03 13:26 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.09 | Santos ¦ FV18-76-1 ¦ PPC-BHC-GPIT-HRLA-PEX-SP | SANTOS LIMITED | FV18-76-1 | Ensign 966 | J.20.063152 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-21 10:00 |  | 2020-04-21 13:00 | 2020-04-23 13:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:22 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.08 | QC | SANTOS LIMITED |  | Ensign 966 | J.20.063151 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-05 01:00 |  | 2020-04-06 | 2020-04-08 |  |  | Roma WL | MRony2 | 2022-10-03 13:22 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.01 | QC | SANTOS LIMITED | RM90-12 1 | Ensign 966 | J.20.063150 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-03 |  | 2020-01-03 21:15 | 2020-01-04 05:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:22 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.06 | Santos ¦ Sunnyholt 50 ¦ BHC-HRLA-PEX-SP | SANTOS LIMITED | Sunnyholt 50 | Ensign 966 | J.20.063126 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-02 20:00 |  | 2020-02-03 08:00 | 2020-02-05 08:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:18 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.07 | Sunnyholt49 | SANTOS LIMITED |  | Ensign 966 | J.20.063119 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-06 23:00 |  | 2020-02-07 23:00 | 2020-02-09 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.05 | QC | SANTOS LIMITED |  | Ensign 966 | J.20.063118 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-18 23:00 |  | 2020-01-19 23:00 | 2020-01-21 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.12 | Kia Ora 2 ¦ FMI-SSCAN-HRLA-PEX-HNGS-GR ¦ MDT-GR | SANTOS LIMITED | Kia Ora 2 | Ensign 966 | J.20.063060 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2020-10-28 |  | 2020-10-29 | 2020-10-31 |  |  | Roma WL | MRony2 | 2022-10-03 13:08 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 62444.44 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.04 | QC | SANTOS LIMITED |  | Ensign 966 | J.19.060571 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-29 23:00 |  | 2019-12-30 23:00 | 2020-01-01 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:08 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.10 | Santos ¦ FV18-75-1 ¦ PEX-HRLA-BHC | SANTOS LIMITED | FV18-75-1 | Ensign 966 | J.20.063049 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-16 |  | 2020-05-16 14:00 | 2020-05-18 14:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:07 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 |  |  |  |  | 50 | 8.3 | 0 | 0 | 17.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001640 | O.1001640.01 | A.1001640.01.13 | QC-FMI_MDT_Warrinilla11 | SANTOS LIMITED | WARRANILLA 9 | Ensign 966 |  | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-08-05 23:00 |  | 2021-08-06 23:00 | 2021-08-10 23:00 |  |  | Roma WL | MRony2 | 2022-09-03 07:59 | walfaro |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 85212.48 | 4 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.11 | A.1001639.11.02 | Sav 409 Quad Combo 16 June- 30 June | SANTOS LIMITED | RM68-44-1, RM68-63-1, RM68-37-1, RM68-06-1, RM68-154-1, OBGML 01 | SAVANNA DRILLING #409 | J.23.101176 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-16 | 2023-06-16 | 2023-06-15 14:00 | 2023-06-16 | 2023-07-04 23:59 | 2023-07-05 | 2023-07-04 23:59 | Roma WL | RDell | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 4 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001639 | O.1001639.11 | A.1001639.11.01 | Sav 409 Jun 1-15 | SANTOS LIMITED | RM07-90-1, RM08-105-1, RM09-50-1, RM68-77-1, RM68-36-1 | SAVANNA DRILLING #409 | J.23.095609 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-06-04 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-15 23:59 | 2023-06-16 | 2023-06-15 23:59 | Roma WL | KKeese | 2023-10-17 16:43 | DJunuskaliyeva |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001639 | O.1001639.10 | A.1001639.10.11 | Quad Combo May15-31 | SANTOS LIMITED | RM13-89-1, RM13-85-1, RM13-86-1, RM14-36-1, RM08-41-1 | SAVANNA DRILLING #409 | J.23.081880 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-05-15 12:00 | 2023-05-15 |  | 2023-05-15 12:00 | 2023-05-29 01:00 |  | 2023-05-29 02:00 | Roma WL | SAli63 | 2023-06-05 17:16 | NSchwenke |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 14 |  | L3 - Full RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.10 | A.1001639.10.14 | Quad Combo_Jul1-15 | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.23.084124 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | Design Completed | 2023-07-01 12:00 | 2023-07-01 |  | 2023-07-01 12:00 | 2023-07-15 01:00 |  | 2023-07-15 02:00 | Roma WL | SAli63 | 2023-05-15 17:20 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 14 |  | L3 - Full RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.10 | A.1001639.10.10 | Quad Combo_May1-15 | SANTOS LIMITED | RM13-32-1, RM13-38-1, RM13-37-1, RM13-46-1, RM13-36-1, RM13-44-1 | SAVANNA DRILLING #409 | J.23.079425 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-05-01 12:00 | 2023-05-01 |  | 2023-05-01 12:00 | 2023-05-15 01:00 |  | 2023-05-15 02:00 | Roma WL | SAli63 | 2023-05-15 12:11 | RDell |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 14 |  | L3 - Full RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.10 | A.1001639.10.09 | Quad Combo_Apr15-Apr30 | SANTOS LIMITED | RM13-31-1, RM13-27-1, RM13-26-1, RM13-28-1, RM13-33-1, RM13-32-1 | SAVANNA DRILLING #409 | J.23.071814 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-04-16 15:00 | 2023-04-16 |  | 2023-04-16 15:00 | 2023-05-01 04:00 |  | 2023-05-01 05:00 | Roma WL | SAli63 | 2023-05-02 08:32 | NMoore2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 14 |  | L3 - Full RO |  | 91.7 | 50 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.10 | A.1001639.10.08 | Quad Combo_Apr1-15 | SANTOS LIMITED | RM12-66-1, RM17-12-1, RM12-67-1, RM12-56-1, RM12-57-1, RM13-25-1 | SAVANNA DRILLING #409 | J.23.063527 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-01 12:00 | 2023-04-01 |  | 2023-04-01 12:00 | 2023-04-15 01:00 |  | 2023-04-15 01:00 | Roma WL | SAli63 | 2023-04-18 03:15 | NSchwenke |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 14 |  | L3 - Full RO |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.10 | A.1001639.10.04 | Quad Combo_Mar2 | SANTOS LIMITED | RM12-55-1, RM12-46-1, RM12-54-1, RM12-53-1, RM12-64-1, RM12-65-1 | SAVANNA DRILLING #409 | J.23.016492 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-03-15 22:00 | 2023-03-14 22:00 |  | 2023-03-15 22:00 | 2023-04-02 21:59 |  | 2023-04-02 21:59 | Roma WL | MRony2 | 2023-04-01 08:24 | NMoore2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 14 |  | L3 - Full RO |  | 91.7 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.10 | A.1001639.10.03 | Quad Combo | SANTOS LIMITED | RM13-76-1, RM13-81-1, RM13-80-1, RM13-75-1, RM13-72-1 | SAVANNA DRILLING #409 | J.23.016494 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-03-07 | 2023-03-01 |  | 2023-03-01 22:00 | 2023-03-20 |  | 2023-03-20 | Roma WL | MRony2 | 2023-03-24 17:15 | SSabatini |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 14 |  | L3 - Full RO |  | 91.7 | 66.7 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.10 | A.1001639.10.13 | Quad Combo_Jun15-30 | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.23.055488 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | Design Completed | Not Started | Design Completed | 2023-06-15 12:00 | 2023-06-15 |  | 2023-06-15 12:00 | 2023-06-29 01:00 |  | 2023-06-29 02:00 | Roma WL | SAli63 | 2023-03-09 21:32 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 14 |  | L3 - Full RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.10 | A.1001639.10.12 | Quad Combo Jun1-15 | SANTOS LIMITED |  | SAVANNA DRILLING #409 |  | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | Design Completed | Not Started | Design Completed | 2023-06-01 12:00 | 2023-06-01 |  | 2023-06-01 12:00 | 2023-06-15 01:00 |  | 2023-06-15 02:00 | Roma WL | SAli63 | 2023-03-05 16:45 | SAli63 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 14 |  | L3 - Full RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.10 | A.1001639.10.07 | Quad Combo | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.23.016502 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-04-15 | 2023-04-13 22:00 |  | 2023-04-14 22:00 | 2023-04-22 21:59 |  | 2023-04-22 23:59 | Roma WL | MRony2 | 2023-03-05 16:11 | SAli63 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 4 |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.10 | A.1001639.10.06 | Quad Combo | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.23.016501 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-04-04 22:00 | 2023-04-03 22:00 |  | 2023-04-04 22:00 | 2023-04-12 21:59 |  | 2023-04-12 21:59 | Roma WL | MRony2 | 2023-03-05 16:11 | SAli63 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.10 | A.1001639.10.05 | Quad Combo_Apr1 | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.23.016500 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-25 22:00 | 2023-03-24 22:00 |  | 2023-03-25 22:00 | 2023-04-02 21:59 |  | 2023-04-02 21:59 | Roma WL | MRony2 | 2023-03-05 16:00 | SAli63 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.10 | A.1001639.10.02 | QuadCombo | SANTOS LIMITED | RM13-87-1, RM14-58-1, RM13-82-1, RM13-73-1, RM13-77-1 | SAVANNA DRILLING #409 | J.23.016493 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-02-14 23:00 | 2023-02-13 22:00 |  | 2023-02-14 22:00 | 2023-03-01 21:59 |  | 2023-03-01 22:59 | Roma WL | MRony2 | 2023-02-28 10:03 | RDell |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 4 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.10 | A.1001639.10.01 | QuadCombo | SANTOS LIMITED | RM13-87-1 | SAVANNA DRILLING #409 | J.23.016491 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-02-04 23:00 | 2023-02-02 22:00 |  | 2023-02-04 22:00 | 2023-02-12 21:59 |  | 2023-02-19 | Roma WL | MRony2 | 2023-02-23 17:59 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 4 |  | L3 - Full RO |  | 54.2 | 0 | 0 | 0 | 16.3 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.09 | A.1001639.09.10 | Quad Combo | SANTOS LIMITED | RM12-34-1, RM12-38-1, RM12-35-1, RM12-39-1, RM14-32-1 | SAVANNA DRILLING #409 | J.23.016490 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-02-01 | 2023-02-01 |  | 2023-02-01 | 2023-02-22 23:59 |  | 2023-02-22 23:59 | Roma WL | MRony2 | 2023-02-17 12:00 | NSchwenke |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 4 |  | L3 - Full RO |  | 83.3 | 50 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.09 | A.1001639.09.01 | QuadCombo | SANTOS LIMITED | RM08-95-1, RM12-30-1, RM08-96-1, RM08-74-1, RM08-75-1 | SAVANNA DRILLING #409 | J.22.110412 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2022-10-27 | 2022-10-26 |  | 2022-10-27 | 2022-11-08 23:59 |  | 2022-11-08 23:59 | Roma WL | MRony2 | 2023-02-10 01:38 | NSchwenke |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 4 |  | L3 - Full RO |  | 75 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.09 | A.1001639.09.04 | QuadCombo | SANTOS LIMITED | RM15-120-1, RM49-172-1, RM49-173-1, RM15-121-1, RM13-92-1 | SAVANNA DRILLING #409 | J.22.110415 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-20 | 2022-11-19 |  | 2022-11-20 | 2022-12-13 23:59 |  | 2022-12-13 23:59 | Roma WL | MRony2 | 2023-02-04 14:26 | SSabatini |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 4 |  | L3 - Full RO |  | 66.7 | 83.3 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.09 | A.1001639.09.09 | Quad Combo | SANTOS LIMITED | RM07-97-1, RM08-50-1, RM08-46-1, RM07-98-1, RM07-93-1, RM08-39-1A | SAVANNA DRILLING #409 | J.23.016488 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-01-18 | 2023-01-17 |  | 2023-01-18 | 2023-01-31 23:59 |  | 2023-01-25 23:59 | Roma WL | MRony2 | 2023-01-31 17:53 | RDell |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 4 |  | L3 - Full RO |  | 66.7 | 66.7 | 0 | 100 | 70 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.09 | A.1001639.09.07 | QuadCombo | SANTOS LIMITED | RM08-48-1, RM08-49-1, RM07-78-1, RM07-81-1, RM07-92-1 | SAVANNA DRILLING #409 | J.22.110421 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-01-11 | 2023-01-11 |  | 2023-01-11 | 2023-01-20 23:59 |  | 2023-01-29 23:59 | Roma WL | MRony2 | 2023-01-17 12:49 | NMoore2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 4 |  | L3 - Full RO |  | 75 | 66.7 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.09 | A.1001639.09.08 | QuadCombo | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.22.110429 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-01-11 | 2023-01-10 |  | 2023-01-11 | 2023-01-18 23:59 |  | 2023-01-18 23:59 | Roma WL | MRony2 | 2023-01-04 23:30 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 4 |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.09 | A.1001639.09.05 | QuadCombo | SANTOS LIMITED | RM07-73-1, RM07-82-1, RM07-101-1, RM07-86-1, RM07-87-1, RM07-91-1, RM07-85-1, RM07-84-1 | SAVANNA DRILLING #409 | J.22.110880 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-12-11 | 2022-12-10 |  | 2022-12-11 | 2022-12-31 23:59 |  | 2022-12-31 23:59 | Roma WL | MRony2 | 2023-01-03 06:55 | NSchwenke |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 4 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.09 | A.1001639.09.06 | QuadCombo | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.22.110881 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-20 | 2022-12-19 |  | 2022-12-20 | 2022-12-27 23:59 |  | 2022-12-27 23:59 | Roma WL | MRony2 | 2022-12-29 03:48 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 4 |  | L3 - Full RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.09 | A.1001639.09.03 | QuadCombo | SANTOS LIMITED | RM08-75-1, RM08-67-1, RM12-76-1, RM15-122-1 | SAVANNA DRILLING #409 | J.22.110427 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-09 | 2022-11-08 |  | 2022-11-09 | 2022-11-16 23:59 |  | 2022-11-16 23:59 | Roma WL | MRony2 | 2022-12-11 02:59 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 4 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.09 | A.1001639.09.02 | Qaudcombo | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.22.110428 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-10-18 |  | 2022-10-19 | 2022-10-26 23:59 |  |  | Roma WL | MRony2 | 2022-10-05 21:47 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 4 |  |  |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.18 | HILLTOP 22 | SANTOS LIMITED | BOTTLE TREE 10 | SAVANNA DRILLING #409 | J.23.008586 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-05-04 23:05 | 2023-05-04 |  | 2023-05-04 | 2023-05-07 23:59 |  | 2023-05-08 02:59 | Roma WL | MRony2 | 2023-05-06 14:55 | SAli63 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 |  | L2 - Shift RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.27 | Quadcombo | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.22.114262 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2022-11-15 |  | 2022-11-15 | 2022-11-16 23:59 |  |  | Roma WL | PLima7 | 2022-11-06 13:33 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.19 | LONESOME HOLDING 7 | SANTOS LIMITED | Bottle Tree 10 | SAVANNA DRILLING #409 | J.23.008584 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2023-01-27 |  | 2023-01-27 | 2023-01-30 23:59 |  |  | Roma WL | MRony2 | 2022-11-06 12:28 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.17 | HILLTOP 9 | SANTOS LIMITED | Bottle Tree 10 | SAVANNA DRILLING #409 | J.23.008585 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2023-01-23 |  | 2023-01-23 | 2023-01-26 23:59 |  |  | Roma WL | MRony2 | 2022-11-06 12:28 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.26 | Quad Combo | SANTOS LIMITED | Kaimanna 33 | SAVANNA DRILLING #409 | J.22.111871 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-10-05 05:30 |  | 2022-10-05 23:30 | 2022-10-07 06:29 |  |  | Roma WL | MRony2 | 2022-10-19 21:10 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.25 | Kaimanna 39 | SANTOS LIMITED | Kaimanna 39 | SAVANNA DRILLING #409 | J.22.110406 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-09-11 14:00 |  | 2022-09-12 21:00 | 2022-09-13 20:59 |  |  | Roma WL | MRony2 | 2022-10-19 20:52 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.16 | Kaimanna 17 | SANTOS LIMITED | KAIMANNA 17 | SAVANNA DRILLING #409 | J.22.110357 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-10-15 |  | 2022-10-15 | 2022-10-18 23:59 |  |  | Roma WL | MRony2 | 2022-10-19 20:41 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 60071.47 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.13 | Quad Combo MDT | SANTOS LIMITED | Kaimanna 44 | SAVANNA DRILLING #409 | J.22.110875 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-09-17 |  | 2022-09-18 10:00 | 2022-09-20 09:59 |  |  | Roma WL | MRony2 | 2022-10-19 20:38 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 60071.47 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.22 | QC | SANTOS LIMITED | Kaimanna 61 | SAVANNA DRILLING #409 | J.22.110878 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-08-09 14:00 |  | 2022-08-10 08:00 | 2022-08-14 07:59 |  |  | Roma WL | MRony2 | 2022-10-19 14:06 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 1 |  |  |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.28 | Quadcombo | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.22.114762 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-10-19 |  | 2022-10-19 | 2022-10-20 23:59 |  |  | Roma WL | PLima7 | 2022-10-10 12:33 | MRony2 |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.24 | Kaimanna 33 | SANTOS LIMITED | Kaimanna 33 | SAVANNA DRILLING #409 | J.22.110879 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-09-06 08:00 | 2022-09-05 14:00 |  | 2022-09-06 08:00 | 2022-09-08 07:59 |  | 2022-09-08 07:59 | Roma WL | MRony2 | 2022-10-03 14:58 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 5750.49 | 1 |  |  |  | 75 | 83.3 | 0 | 50 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.21 | Bumbey 34 | SANTOS LIMITED | Bottle Tree 10 | SAVANNA DRILLING #409 | J.22.110877 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-09-01 23:00 | 2022-09-02 |  | 2022-09-02 | 2022-09-05 23:59 |  | 2022-09-05 22:59 | Roma WL | MRony2 | 2022-10-03 14:58 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.20 | LONESOME HOLDING 4 | SANTOS LIMITED | Bottle Tree 10 | SAVANNA DRILLING #409 | J.22.110876 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-11-22 | 2022-11-22 |  | 2022-11-22 | 2022-11-25 23:59 |  | 2022-11-25 23:59 | Roma WL | MRony2 | 2022-10-03 14:58 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.12 | KAIMANNA 62 | SANTOS LIMITED | Kaimanna 62 | SAVANNA DRILLING #409 | J.22.110874 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-07-22 15:00 | 2022-07-22 |  | 2022-07-22 16:00 | 2022-07-24 15:59 |  | 2022-07-24 14:59 | Roma WL | MRony2 | 2022-10-03 14:58 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 62930.47 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.05 | CASTLE HILL 51 | SANTOS LIMITED | Castle Hill 51 | SAVANNA DRILLING #409 | J.22.110873 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-03-09 | 2022-03-08 |  | 2022-03-08 23:00 | 2022-03-11 22:59 |  | 2022-03-11 23:59 | Roma WL | MRony2 | 2022-10-03 14:57 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.04 | AC23-64-1 | SANTOS LIMITED | RM13-94-1, RM14-48-1, RM14-57-1, RM22-17-2, AC23-64-1 | SAVANNA DRILLING #409 | J.22.110872 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-02-27 | 2022-02-25 |  | 2022-02-26 23:00 | 2022-03-01 22:59 |  | 2022-03-01 23:59 | Roma WL | MRony2 | 2022-10-03 14:57 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.03 | Bottle Tree_10 MDT | SANTOS LIMITED | Bottle Tree 10 | SAVANNA DRILLING #409 | J.22.110871 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-02-09 | 2022-02-09 |  | 2022-02-09 | 2022-02-12 23:59 |  | 2022-02-12 23:59 | Roma WL | MRony2 | 2022-10-03 14:57 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 111176.09 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.23 | Kaimanna 33 | SANTOS LIMITED | Kaimanna 56 | SAVANNA DRILLING #409 | J.22.110395 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-09-01 14:00 |  | 2022-09-02 08:00 | 2022-09-03 07:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.15 | Kaimanna 2 PEX MDT | SANTOS LIMITED | Kaimanna 10, Kaimanna 2 | SAVANNA DRILLING #409 | J.22.110339 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-06-04 |  | 2022-06-04 | 2022-06-07 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:16 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 2 |  |  |  | 75 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.11 | KAIMANNA 56 | SANTOS LIMITED | Kaimanna 56 | SAVANNA DRILLING #409 | J.22.110332 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-06-28 14:00 |  | 2022-06-29 08:00 | 2022-06-30 07:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.14 | CASTLE HILL 81 | SANTOS LIMITED | Castle Hill 81 | SAVANNA DRILLING #409 | J.22.110329 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-04-17 |  | 2022-04-17 | 2022-04-20 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 118973.36 | 2 |  |  |  | 50 | 33.3 | 0 | 100 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.10 | KAIMANNA 21 QC | SANTOS LIMITED | Kaimanna 21 | SAVANNA DRILLING #409 | J.22.110318 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-06-11 |  | 2022-06-12 23:00 | 2022-06-15 22:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.07 | CASTLE HILL 87 | SANTOS LIMITED | RM13-94-1, RM14-48-1, RM14-57-1, RM22-17-2, AC23-64-1, Castle Hill 87 | SAVANNA DRILLING #409 | J.22.110316 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-04-11 |  | 2022-04-12 23:00 | 2022-04-15 22:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.08 | CASTLE HILL 61 | SANTOS LIMITED | Castle Hill 61 | SAVANNA DRILLING #409 | J.22.110315 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-04-19 |  | 2022-04-20 10:00 | 2022-04-23 10:00 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.09 | KAIMANNA 10 | SANTOS LIMITED | RM13-94-1, RM14-48-1, RM14-57-1, RM22-17-2, AC23-64-1, Kaimanna 10 | SAVANNA DRILLING #409 | J.22.110312 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed |  | 2022-05-05 |  | 2022-05-05 23:00 | 2022-05-06 22:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.06 | LINGA LONGA 6 | SANTOS LIMITED | RM13-94-1, RM14-48-1, RM14-57-1, RM22-17-2, Linga Longa 6 | SAVANNA DRILLING #409 | J.22.110310 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-03-22 |  | 2022-03-22 23:00 | 2022-03-25 22:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:15 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 5360.62 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.02 | QC | SANTOS LIMITED | RM13-94-1, RM14-48-1, RM14-57-1, RM22-17-2 | SAVANNA DRILLING #409 | J.22.110287 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-01-26 |  | 2022-01-26 23:00 | 2022-02-04 22:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | 3 |  |  |  | 75 | 33.3 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.08 | A.1001639.08.01 | QC_Multi well | SANTOS LIMITED | RM13-99-1, RM22-33-1, RM13-93-1 | SAVANNA DRILLING #409 | J.22.110271 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-01-17 |  | 2022-01-18 23:00 | 2022-01-26 22:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | 3 |  |  |  | 75 | 33.3 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.07 | A.1001639.07.06 | QC | SANTOS LIMITED | RM14-54-1, RM14-56-1, RM22-21-1, RM22-26-1, RM22-20-1, RM22-27-1, RM22-32-1 | SAVANNA DRILLING #409 | J.21.109421 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-12-14 23:00 | 2021-12-14 12:00 |  | 2021-12-14 23:00 | 2021-12-28 22:59 |  | 2021-12-28 22:59 | Roma WL | MRony2 | 2022-10-03 14:57 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.07 | A.1001639.07.11 | Santos MDT | SANTOS LIMITED | Reuben Downs 1 | SAVANNA DRILLING #409 | J.21.109076 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-12-08 22:00 |  | 2021-12-09 22:00 | 2021-12-13 21:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 90777.86 | 2 |  |  |  | 83.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.07 | A.1001639.07.10 | QC | SANTOS LIMITED | RM22-23-1, RM22-28-1, RM22-34-1 | SAVANNA DRILLING #409 | J.22.110267 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2022-01-11 |  | 2022-01-12 | 2022-01-26 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | 2 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.07 | A.1001639.07.09 | QC | SANTOS LIMITED | RM22-25-1, RM22-30-1, RM22-31-1 | SAVANNA DRILLING #409 | J.22.110265 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2022-01-05 22:00 | 2022-01-04 |  | 2022-01-05 22:00 | 2022-01-13 21:59 |  | 2022-01-13 21:59 | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 10721.24 | 2 |  | L3 - Full RO |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.07 | A.1001639.07.08 | QC | SANTOS LIMITED | RM22-20-1, RM13-83-1, RM13-84-1, RM22-31-1 | SAVANNA DRILLING #409 | J.21.109065 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2021-12-28 02:00 | 2021-12-28 |  | 2021-12-28 02:00 | 2022-01-05 01:59 |  | 2022-01-05 01:59 | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 10721.24 | 3 |  | L3 - Full RO |  | 75 | 33.3 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.07 | A.1001639.07.07 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.21.109060 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-12-21 |  | 2021-12-22 | 2021-12-29 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 1 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.07 | A.1001639.07.05 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.21.109055 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-11-25 |  | 2021-11-26 | 2021-12-03 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.07 | A.1001639.07.04 | QC | SANTOS LIMITED | RM15-95-1, RM09-29-1, RM15-56-1 | SAVANNA DRILLING #409 | J.21.109051 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2021-11-16 | 2021-11-15 |  | 2021-11-16 | 2021-11-23 23:59 |  | 2021-11-29 08:46 | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 1 |  | L3 - Full RO |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.07 | A.1001639.07.03 | QC | SANTOS LIMITED | RM15-70-1, RM15-69-1, RM15-79-1, RM15-78-1, RM15-86-1 | SAVANNA DRILLING #409 | J.21.109046 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-11-01 |  | 2021-11-02 | 2021-11-18 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 11500.98 | 3 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.07 | A.1001639.07.02 | QC-Santos | SANTOS LIMITED | RM49-127-1, RM08-88-1, BGDGWG01, BGDML01 | SAVANNA DRILLING #409 | J.21.109041 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-10-24 |  | 2021-10-24 12:00 | 2021-11-01 11:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 2 |  |  |  | 75 | 33.3 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.07 | A.1001639.07.01 | QC_Multi well | SANTOS LIMITED | RM14-26-1, RM14-28-1, RM22-22-1, RM22-24-1, RM50-158-1 | SAVANNA DRILLING #409 | J.21.109036 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-10-07 |  | 2021-10-08 | 2021-10-23 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 1 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.06 | A.1001639.06.11 | Multi Well Operation Sep 16-23 | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.21.109420 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-10-06 20:00 | 2021-10-06 21:00 |  | 2021-10-06 21:00 | 2021-10-13 20:59 |  | 2021-10-14 00:59 | Roma WL | EDelange | 2022-10-03 14:57 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.06 | A.1001639.06.08 | Multi Well Operation 3rd week of Sep | SANTOS LIMITED | RM15-60-1, RM14-39-1, RM14-46-1 | SAVANNA DRILLING #409 | J.21.109419 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-09-15 19:00 | 2021-09-15 20:00 |  | 2021-09-15 20:00 | 2021-09-23 19:59 |  | 2021-09-23 23:59 | Roma WL | EDelange | 2022-10-03 14:57 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 5750.49 | 3 |  |  |  | 66.7 | 33.3 | 0 | 75 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.06 | A.1001639.06.07 | Multi Well Operation Aug 2nd week of Sep | SANTOS LIMITED | RM14-43-1, RM14-44-1, RM14-42-1, RM15-60-1, RM14-39-1 | SAVANNA DRILLING #409 | J.21.109418 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-09-08 19:00 | 2021-09-08 20:00 |  | 2021-09-08 20:00 | 2021-09-20 19:59 |  | 2021-09-26 23:59 | Roma WL | EDelange | 2022-10-03 14:57 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 3 |  |  |  | 58.3 | 50 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.06 | A.1001639.06.05 | Multi Well Operations Aug 5-12 | SANTOS LIMITED | RM15-87-1, RM15-96-1, RM15-114-1 | SAVANNA DRILLING #409 | J.21.109417 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-08-17 19:00 | 2021-08-16 20:00 |  | 2021-08-17 20:00 | 2021-08-26 19:59 |  | 2021-08-24 23:59 | Roma WL | EDelange | 2022-10-03 14:57 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 3 |  |  |  | 58.3 | 50 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.06 | A.1001639.06.04 | Multi Well Operations Jul 29-Aug 5 | SANTOS LIMITED | RM15-102-1, RM15-104-1, RM15-94-1 | SAVANNA DRILLING #409 | J.21.109416 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-08-09 19:00 | 2021-08-08 20:00 |  | 2021-08-09 20:00 | 2021-08-16 19:59 |  | 2021-08-16 23:59 | Roma WL | EDelange | 2022-10-03 14:57 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 0 |  |  |  | 58.3 | 50 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.06 | A.1001639.06.06 | Multi Well Operation Aug 12-19 | SANTOS LIMITED | RM15-116-1, RM15-106-1, RM15-105-1, RM15-115-1, RM14-41-1 | SAVANNA DRILLING #409 | J.21.109064 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-08-26 20:00 |  | 2021-08-27 20:00 | 2021-09-06 19:59 |  |  | Roma WL | EDelange | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 3 |  |  |  | 58.3 | 50 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.06 | A.1001639.06.09 | Multi Well Operation 23rd Sep | SANTOS LIMITED | RM14-47-1, RM15-88-1, RM14-45-1, RM14-53-1 | SAVANNA DRILLING #409 | J.21.109063 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-09-24 20:00 |  | 2021-09-24 20:00 | 2021-10-01 19:59 |  |  | Roma WL | EDelange | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.06 | A.1001639.06.10 | Multi Well Operation Oct 01-07 | SANTOS LIMITED | RM15-44-1, RM15-43-1, RM15-34-1 | SAVANNA DRILLING #409 | J.21.109062 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-10-01 20:00 |  | 2021-10-01 20:00 | 2021-10-08 20:59 |  |  | Roma WL | EDelange | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.06 | A.1001639.06.03 | Multi Well Operations Jul 22-29 | SANTOS LIMITED | RM15-77-1, RM15-93-1, RM15-83-1 | SAVANNA DRILLING #409 | J.21.109061 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-07-29 20:00 |  | 2021-08-01 20:00 | 2021-08-08 19:59 |  |  | Roma WL | EDelange | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 2 |  |  |  | 58.3 | 50 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.06 | A.1001639.06.01 | Multi Well Operations Jul 8-15 | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.21.109058 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-07-14 20:00 |  | 2021-07-14 20:00 | 2021-07-21 19:59 |  |  | Roma WL | EDelange | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 0 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.06 | A.1001639.06.02 | Multi Well Operations July 15-22 | SANTOS LIMITED | RM15-67-1, RM15-113-1, RM15-103-1, RM15-84-1, RM15-85-1 | SAVANNA DRILLING #409 | J.21.109057 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-07-15 19:30 |  | 2021-07-15 20:00 | 2021-07-31 19:59 |  |  | Roma WL | EDelange | 2022-10-03 14:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 0 |  |  |  | 58.3 | 50 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.06 | A.1001639.06.12 | Multi Well Operation Sep 23-30 | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.21.108962 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-10-13 21:00 |  | 2021-10-13 21:00 | 2021-10-20 20:59 |  |  | Roma WL | EDelange | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 3 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.05 | A.1001639.05.11 | Quad Combo Multi Well | SANTOS LIMITED | RM50-157-1, RM49-169-1, RM49-166-1, RM15-75-1 | SAVANNA DRILLING #409 | J.21.109033 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-07-06 20:00 |  | 2021-07-06 20:00 | 2021-07-16 19:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.05 | A.1001639.05.10 | Multi Well Operations June 23-30 | SANTOS LIMITED | RM49-171-1, RM15-75-1, RM15-67-1, RM49-170-1 | SAVANNA DRILLING #409 | J.21.109029 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-06-24 20:00 |  | 2021-06-24 20:00 | 2021-07-01 19:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 22061.08 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.05 | A.1001639.05.09 | Multi Well Operations Jun 14-21 | SANTOS LIMITED | RM01-05-5, RM49-168-1, RM49-171-1, RM50-151-1, RM49-167-1 | SAVANNA DRILLING #409 | J.21.109026 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-06-14 20:00 |  | 2021-06-14 20:00 | 2021-06-24 19:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.05 | A.1001639.05.08 | QC_GPIT | SANTOS LIMITED | RM01-05-5, RM09-30-2, RM12-78-1 | SAVANNA DRILLING #409 | J.21.109024 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-06-06 20:00 |  | 2021-06-06 20:00 | 2021-06-15 19:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 11500.98 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.05 | A.1001639.05.07 | QUAD COMBO_GPIT_REPEAT OPS | SANTOS LIMITED | RM15-90-1, RM15-111-1, RM15-91-1, RM15-92-1 | SAVANNA DRILLING #409 | J.21.109021 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2021-06-01 21:00 | 2021-05-26 20:00 |  | 2021-06-01 20:00 | 2021-06-07 19:59 |  | 2021-08-05 20:59 | Roma WL | MRony2 | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 0 |  | L3 - Full RO |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.05 | A.1001639.05.06 | 409 Multi Well May 12-19 | SANTOS LIMITED | RM15-62-1, RM15-109-1, RM15-100-1, RM15-110-1, RM15-101-1 | SAVANNA DRILLING #409 | J.21.109017 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-05-08 20:00 |  | 2021-05-12 20:00 | 2021-05-25 19:59 |  |  | Roma WL | EDelange | 2022-10-03 14:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.05 | A.1001639.05.05 | 409 Multi Well May 2-May 9 | SANTOS LIMITED | RM15-80-1, RM15-71-1, RM15-72-1, RM15-61-1 | SAVANNA DRILLING #409 | J.21.109014 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-05-01 20:00 |  | 2021-05-01 20:00 | 2021-05-13 19:59 |  |  | Roma WL | EDelange | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.05 | A.1001639.05.04 | 409 Multi Well Apr 22-29 | SANTOS LIMITED | RM15-50-1, RM15-108-1, RM15-89-1, RM15-98-1 | SAVANNA DRILLING #409 | J.21.109012 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-04-22 20:00 |  | 2021-04-23 16:00 | 2021-05-01 15:59 |  |  | Roma WL | EDelange | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.05 | A.1001639.05.03 | 409 Multi Well Apr 15-22 | SANTOS LIMITED | RM15-21-1, RM15-57-1, RM15-58-1, RM15-59-1 | SAVANNA DRILLING #409 | J.21.109011 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-04-14 20:00 |  | 2021-04-14 20:00 | 2021-04-22 19:59 |  |  | Roma WL | EDelange | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.05 | A.1001639.05.02 | 409 Multi well Apr 8-15 | SANTOS LIMITED | RM13-54-1, RM15-23-1, RM15-21-1 | SAVANNA DRILLING #409 | J.21.109008 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-04-08 04:00 |  | 2021-04-08 04:00 | 2021-04-15 03:59 |  |  | Roma WL | EDelange | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.05 | A.1001639.05.01 | QC Multi well | SANTOS LIMITED | RM13-13-1, RM13-51-1, RM13-52-1 | SAVANNA DRILLING #409 | J.21.109004 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-03-31 20:00 |  | 2021-03-31 20:00 | 2021-04-07 19:59 |  |  | Roma WL | FDPSystemUser | 2022-10-03 14:12 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.25 | QC | SANTOS LIMITED | RM09-80-1 | SAVANNA DRILLING #409 | J.21.108976 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-06-21 09:00 |  | 2021-06-21 19:00 | 2021-06-27 04:59 |  |  | Roma WL | MRony2 | 2022-10-03 14:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.22 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.21.108918 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-05-31 09:00 |  | 2021-05-31 19:00 | 2021-06-06 14:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:32 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.15 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.21.108917 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-04-06 09:00 |  | 2021-04-06 19:00 | 2021-04-13 09:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:32 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.10 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.21.108916 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-05-10 09:00 |  | 2021-07-06 19:00 | 2021-07-11 08:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:32 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.06 | Repeat Ops (27 Jan) | SANTOS LIMITED | RM15-38-1, RM15-30-1, RM15-31-1, RM15-39-1, RM15-40-1 | SAVANNA DRILLING #409 | J.21.108915 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-01-31 14:00 |  | 2021-01-31 16:00 | 2021-02-10 05:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:32 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 10721.24 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.01 | RM09-80-1 | SANTOS LIMITED | RM09-80-1 | SAVANNA DRILLING #409 | J.20.063209 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-12-05 18:00 |  | 2020-12-06 20:00 | 2020-12-08 19:59 |  |  | Roma WL | FDPSystemUser | 2022-10-03 13:32 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.07 | QC | SANTOS LIMITED | RM15-46-1, RM15-47-1 | SAVANNA DRILLING #409 | J.21.108914 | RPE | ES-OH-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-01-29 00:16 |  | 2021-01-29 10:16 | 2021-02-05 00:15 |  |  | Roma WL | MRony2 | 2022-10-03 13:30 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.03 | QC | SANTOS LIMITED | RM14-24-1, RM15-25-1, RM12-13-5, RM68-146-1 | SAVANNA DRILLING #409 | J.20.063196 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-12-11 10:00 |  | 2020-12-11 18:00 | 2020-12-23 07:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:30 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 7595.84 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.17 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.21.108911 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-04-21 09:00 |  | 2021-04-21 19:00 | 2021-04-29 08:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:28 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.13 | Repeat ops 409 | SANTOS LIMITED | RM68-147-1, RM15-23-1, RM13-53-1 | SAVANNA DRILLING #409 | J.21.108910 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-03-17 10:00 |  | 2021-03-22 20:00 | 2021-03-30 09:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:28 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.12 | QC | SANTOS LIMITED | RM15-20-1, RM68-149-1, RM68-147-1 | SAVANNA DRILLING #409 | J.21.108909 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-03-11 18:00 |  | 2021-03-12 10:00 | 2021-03-17 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:26 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.05 | Repeat ops continue | SANTOS LIMITED | RM15-18-1, RM15-74-1, RM14-27-1, RM15-64-1, RM15-55-1 | SAVANNA DRILLING #409 | J.21.108908 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-01-07 |  | 2021-01-10 18:00 | 2021-01-27 07:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:26 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 11500.98 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.14 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.21.108906 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-03-31 10:00 |  | 2021-03-31 20:00 | 2021-04-05 08:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:24 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.02 | RM14-25-1 QC | SANTOS LIMITED | RM14-25-1 | SAVANNA DRILLING #409 | J.20.063149 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-12-09 18:00 |  | 2020-12-09 18:00 | 2020-12-10 07:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:22 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.21 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.21.108905 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-05-25 09:00 |  | 2021-05-25 19:00 | 2021-05-30 08:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:20 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.18 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.21.108904 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-05-01 09:00 |  | 2021-05-01 19:00 | 2021-05-09 08:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:20 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.08 | Repeats ops 409 | SANTOS LIMITED | RM15-48-1, RM15-81-1, RM15-22-1, RM15-32-1, RM15-42-1 | SAVANNA DRILLING #409 | J.21.108903 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-02-11 18:00 |  | 2021-02-11 20:00 | 2021-02-25 09:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:20 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.09 | repeat ops 409 | SANTOS LIMITED | RM15-33-1, RM15-41-1, RM15-49-1, RM15-99-1, RM15-97-1 | SAVANNA DRILLING #409 | J.21.108902 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-02-23 10:00 |  | 2021-02-23 20:00 | 2021-03-01 09:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:18 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5750.49 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.04 | 409 repeat ops | SANTOS LIMITED | RM68-134-1, RM68-133-1, RM68-144-1, RM68-137-1, RM68-145-1 | SAVANNA DRILLING #409 | J.20.063125 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-12-28 |  | 2020-12-28 18:00 | 2021-01-10 |  |  | Roma WL | MRony2 | 2022-10-03 13:18 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 11111.11 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.23 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.21.108899 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-06-07 09:00 |  | 2021-06-07 19:00 | 2021-06-13 14:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.24 | QC | SANTOS LIMITED | RM09-80-1 | SAVANNA DRILLING #409 | J.21.108894 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-06-14 09:00 |  | 2021-06-14 19:00 | 2021-06-20 04:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.19 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.21.108893 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-05-10 09:00 |  | 2021-05-10 19:00 | 2021-05-16 08:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.16 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.21.108892 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-04-10 09:00 |  | 2021-04-14 19:00 | 2021-04-19 08:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:09 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.20 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.21.108891 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-05-17 09:00 |  | 2021-05-17 19:00 | 2021-05-24 08:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:08 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.04 | A.1001639.04.11 | QC | SANTOS LIMITED | RM15-99-1, RM68-148-1, RM15-19-1, RM15-97-1 | SAVANNA DRILLING #409 | J.21.108890 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-03-01 18:00 |  | 2021-03-01 20:00 | 2021-03-10 09:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:08 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.23 | RM68-125-1 | SANTOS LIMITED | RM68-125-1 | SAVANNA DRILLING #409 | J.20.063208 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-11-01 |  | 2020-11-01 01:00 | 2020-11-02 00:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:32 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.36 | Test | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.20.063195 | RPE | ES-OH-NO | Medium | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-11-11 |  | 2020-11-11 | 2020-11-12 23:59 |  |  | Roma WL | WXu13 | 2022-10-03 13:30 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.24 | RM68-126-1 | SANTOS LIMITED | RM68-126-1 | SAVANNA DRILLING #409 | J.20.063194 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-11-01 16:00 |  | 2020-11-01 18:00 | 2020-11-03 17:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:30 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.12 | RM23-14-1_QC-MDT | SANTOS LIMITED | RM23-14-1 | SAVANNA DRILLING #409 | J.20.063193 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-09-29 21:00 |  | 2020-09-29 23:00 | 2020-10-01 22:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:30 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 59681.61 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.10 | RM23-18-1 | SANTOS LIMITED | RM23-18-1 | SAVANNA DRILLING #409 | J.20.063192 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-09-24 22:00 |  | 2020-09-25 | 2020-09-26 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:29 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.02 | RM15-51-1 Qaud Combo | SANTOS LIMITED | RM15-51-1 | SAVANNA DRILLING #409 | J.20.063191 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-09-02 06:00 |  | 2020-09-02 06:00 | 2020-09-03 05:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:29 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.35 | RM09-78-1 | SANTOS LIMITED | RM09-78-1 | SAVANNA DRILLING #409 | J.20.063185 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-12-04 06:00 |  | 2020-12-04 18:00 | 2020-12-05 17:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:28 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.33 | QC | SANTOS LIMITED | RM09-71-1 | SAVANNA DRILLING #409 | J.20.063178 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-11-29 10:00 |  | 2020-11-29 12:00 | 2020-11-30 11:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:26 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.15 | Santos ¦ RM23-09-1 ¦ 8.75 in ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM23-09 1 | SAVANNA DRILLING #409 | J.20.063177 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2020-10-08 06:33 | 2020-10-08 10:00 |  | 2020-10-08 14:00 | 2020-10-09 13:59 |  | 2020-10-09 13:59 | Roma WL | MRony2 | 2022-10-03 13:26 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 |  |  | L0 - No RO |  | 58.3 | 50 | 0 | 62.5 | 51.2 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.14 | Santos ¦ RM22-16-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM22-16-1 | SAVANNA DRILLING #409 | J.20.063176 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-10-05 12:00 |  | 2020-10-06 02:00 | 2020-10-07 01:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:26 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.26 | RM68-128-1 QC | SANTOS LIMITED | RM68-128-1 | SAVANNA DRILLING #409 | J.20.063172 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-11-06 12:00 |  | 2020-11-06 12:00 | 2020-11-07 11:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:25 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.06 | RM15-52-1 | SANTOS LIMITED | RM15-52-1 | SAVANNA DRILLING #409 | J.20.063171 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-12 22:00 |  | 2020-09-13 22:00 | 2020-09-14 21:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:25 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.22 | RM68-114-1 | SANTOS LIMITED | RM68-114-1 | SAVANNA DRILLING #409 | J.20.063166 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-10-29 18:00 |  | 2020-10-29 23:00 | 2020-10-31 22:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:24 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.11 | RM23-17-1 | SANTOS LIMITED | RM23-17-1 | SAVANNA DRILLING #409 | J.20.063165 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-26 22:00 |  | 2020-09-27 12:00 | 2020-09-28 11:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:24 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.01 | RM13-65-1 Quad Combo | SANTOS LIMITED | RM13-65-1 | SAVANNA DRILLING #409 | J.20.063164 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-31 03:00 |  | 2020-08-31 03:00 | 2020-09-02 02:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:24 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 10721.24 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.25 | RM68-127-1 | SANTOS LIMITED | RM68-127-1 | SAVANNA DRILLING #409 | J.20.063148 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-11-03 06:00 |  | 2020-11-04 18:00 | 2020-11-06 17:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:21 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.29 | RM13-50-1 QC | SANTOS LIMITED | RM13-50-1 | SAVANNA DRILLING #409 | J.20.063139 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-11-13 12:00 |  | 2020-11-13 12:00 | 2020-11-14 11:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:20 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.17 | RM23-12-1_QC-MDT | SANTOS LIMITED | RM23-12-1 | SAVANNA DRILLING #409 | J.20.063138 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2020-10-13 16:00 |  | 2020-10-13 18:00 | 2020-10-15 17:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:20 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 59681.61 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.09 | RM15-16-1 | SANTOS LIMITED | RM15-16-1 | SAVANNA DRILLING #409 | J.20.063137 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-09-20 22:00 |  | 2020-09-21 | 2020-09-23 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:20 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.20 | RM23-16-1 | SANTOS LIMITED | RM23-16 1 | SAVANNA DRILLING #409 | J.20.063124 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2020-10-23 18:00 | 2020-10-22 16:00 |  | 2020-10-23 18:00 | 2020-10-26 17:59 |  | 2020-10-26 17:59 | Roma WL | MRony2 | 2022-10-03 13:18 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 |  |  | L3 - Full RO |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.04 | RM15-45-1 Quad Combo | SANTOS LIMITED | RM15-45-1 | SAVANNA DRILLING #409 | J.20.063117 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2020-09-08 | 2020-09-08 |  | 2020-09-08 | 2020-09-08 23:59 |  | 2020-09-08 23:59 | Roma WL | MRony2 | 2022-10-03 13:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 16081.86 |  |  | L3 - Full RO |  | 58.3 | 50 | 0 | 75 | 55 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.16 | QC | SANTOS LIMITED | RM23-10-1 | SAVANNA DRILLING #409 | J.20.063101 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-10-11 15:00 |  | 2020-10-11 18:00 | 2020-10-12 17:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:15 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.03 | RM15-54-1 Quad Combo | SANTOS LIMITED | RM15-54-1 | SAVANNA DRILLING #409 | J.20.063100 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-09-05 |  | 2020-09-05 | 2020-09-05 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.27 | RM68-136-1_QC | SANTOS LIMITED | RM68-136-1 | SAVANNA DRILLING #409 | J.20.063092 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2020-11-08 16:00 |  | 2020-11-09 04:00 | 2020-11-10 03:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:13 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.13 | RM22-18-1 QC | SANTOS LIMITED | RM22-18-1 | SAVANNA DRILLING #409 | J.20.063091 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-10-03 06:00 |  | 2020-10-03 06:00 | 2020-10-04 06:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.28 | RM68-135-1 QC | SANTOS LIMITED | RM68-135-1 | SAVANNA DRILLING #409 | J.20.063077 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-11-11 06:00 |  | 2020-11-11 06:00 | 2020-11-12 05:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:11 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.08 | RM15-35-1 | SANTOS LIMITED | RM15-35 1 | SAVANNA DRILLING #409 | J.20.063076 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2020-09-19 12:00 | 2020-09-18 22:00 |  | 2020-09-19 12:00 | 2020-09-20 11:59 |  | 2020-09-20 11:59 | Roma WL | MRony2 | 2022-10-03 13:11 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 |  |  | L3 - Full RO |  | 58.3 | 16.7 | 0 | 62.5 | 41.3 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.07 | RM15-53-1 | SANTOS LIMITED | RM15-53-1 | SAVANNA DRILLING #409 | J.20.063075 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-15 22:00 |  | 2020-09-16 18:00 | 2020-09-17 17:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:11 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.05 | RM15-27-1 Quad Combo | SANTOS LIMITED | RM15-27-1 | SAVANNA DRILLING #409 | J.20.063074 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-10 |  | 2020-09-10 | 2020-09-10 23:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:11 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.30 | RM09-70-1 QC | SANTOS LIMITED | RM09-70-1 | SAVANNA DRILLING #409 | J.20.063068 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-11-15 21:00 |  | 2020-11-15 21:00 | 2020-11-16 20:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:09 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.19 | RM23-15-1 | SANTOS LIMITED | RM23-15-1 | SAVANNA DRILLING #409 | J.20.063067 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-10-18 16:00 |  | 2020-10-18 18:00 | 2020-10-20 17:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:09 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.32 | RM09-72-1_QC | SANTOS LIMITED | RM09-72 1 | SAVANNA DRILLING #409 | J.20.063059 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2020-12-01 12:00 | 2020-12-01 10:00 |  | 2020-12-01 12:00 | 2020-12-02 11:59 |  | 2020-12-02 11:59 | Roma WL | MRony2 | 2022-10-03 13:08 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 10721.24 |  |  | L0 - No RO |  | 75 | 50 | 0 | 75 | 60 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.31 | Alrush 1 QC_MDT | SANTOS LIMITED | ALRUSH 1 | SAVANNA DRILLING #409 | J.20.063058 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2020-11-23 10:00 |  | 2020-11-23 18:00 | 2020-11-26 17:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:08 | FDPSystemUser |  | No |  |  |  |  | Jon Lawrie |  | 76900.58 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.34 | RM09-73-1_QC | SANTOS LIMITED | RM09-73-1 | SAVANNA DRILLING #409 | J.20.063048 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-12-02 06:00 |  | 2020-12-02 08:00 | 2020-12-03 07:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:06 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Jon Lawrie |  | 5360.62 |  |  |  |  | 58.3 | 33.3 | 0 | 50 | 42.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.21 | RM23-13-1 | SANTOS LIMITED | RM23-13-1 | SAVANNA DRILLING #409 | J.20.063047 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-10-27 |  | 2020-10-27 12:00 | 2020-10-28 11:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:06 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.03 | A.1001639.03.18 | RM23-11-1 | SANTOS LIMITED | RM23-11-1 | SAVANNA DRILLING #409 | J.20.063046 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-10-16 16:00 |  | 2020-10-16 18:00 | 2020-10-17 17:59 |  |  | Roma WL | MRony2 | 2022-10-03 13:06 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.24 | QC | SANTOS LIMITED | RM68-79-1 | SAVANNA DRILLING #409 | J.20.063207 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-26 12:00 |  | 2020-07-26 12:00 | 2020-07-27 02:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:31 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.10 | RM08-91-1 BHC-HRLA-PEX-GR-SP | SANTOS LIMITED | RM08-91-1 | SAVANNA DRILLING #409 | J.20.063206 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-22 |  | 2020-06-22 | 2020-06-22 14:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:31 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.04 | RM40-09-1 | SANTOS LIMITED | RM40-09-1 | SAVANNA DRILLING #409 | J.20.063205 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-01 12:00 |  | 2020-06-02 | 2020-06-04 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:31 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.19 | RM68-97-1_QC | SANTOS LIMITED | RM68-97-1 | SAVANNA DRILLING #409 | J.20.063190 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-13 16:00 |  | 2020-07-14 04:00 | 2020-07-14 18:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:29 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.37 | RM13-68-1 | SANTOS LIMITED | RM13-68-2 | SAVANNA DRILLING #409 | J.20.063184 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-23 16:00 |  | 2020-08-24 18:00 | 2020-08-25 08:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:28 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.36 | RM13-78-1 | SANTOS LIMITED | RM13-78-1 | SAVANNA DRILLING #409 | J.20.063183 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-19 16:00 |  | 2020-08-20 18:00 | 2020-08-23 08:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:28 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.26 | RM68-91-1 Quad Combo | SANTOS LIMITED | RM68-91-1 | SAVANNA DRILLING #409 | J.20.063182 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-31 |  | 2020-07-31 | 2020-07-31 14:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:27 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.14 | RM68-96-1 BHC-HRLA-PEX-GR-SP | SANTOS LIMITED | RM68-96-1 | SAVANNA DRILLING #409 | J.20.063181 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-01 18:00 |  | 2020-07-01 18:00 | 2020-07-02 08:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:27 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.45 | qc | SANTOS LIMITED | RM40-16-1 | SAVANNA DRILLING #409 | J.21.108907 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-07-27 |  | 2021-07-27 12:00 | 2021-07-28 02:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:26 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.34 | RM68-40-1 | SANTOS LIMITED | RM68-40-1 | SAVANNA DRILLING #409 | J.20.063170 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-15 16:00 |  | 2020-08-16 18:00 | 2020-08-17 08:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:25 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.32 | RM68-41-1 | SANTOS LIMITED | RM68-41-1 | SAVANNA DRILLING #409 | J.20.063169 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-11 16:00 |  | 2020-08-12 18:00 | 2020-08-13 08:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:25 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.12 | RM68-83-1 | SANTOS LIMITED | RM68-83-1 | SAVANNA DRILLING #409 | J.20.063168 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-27 12:00 |  | 2020-06-27 12:00 | 2020-06-28 02:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:25 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Laura Vaiciulyte |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.08 | RM02-66-1 | SANTOS LIMITED | RM02-66-1 | SAVANNA DRILLING #409 | J.20.063167 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-14 12:00 |  | 2020-06-15 | 2020-06-17 14:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:25 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.39 | RM13-66-1 QC | SANTOS LIMITED | RM13-66-1 | SAVANNA DRILLING #409 | J.20.063163 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-18 18:00 |  | 2020-08-28 18:00 | 2020-08-29 08:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:24 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.23 | RM68-80-1 BHC-HRLA-PEX-GR-SP | SANTOS LIMITED | RM68-80-1 | SAVANNA DRILLING #409 | J.20.063162 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-24 |  | 2020-07-24 | 2020-07-24 14:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:24 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.17 | RM68-81-1 | SANTOS LIMITED | RM68-81-1 | SAVANNA DRILLING #409 | J.20.063161 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-08 12:00 |  | 2020-07-09 | 2020-07-10 14:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:24 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.16 | RM68-92-1 | SANTOS LIMITED | RM68-92-1 | SAVANNA DRILLING #409 | J.20.063160 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-07 12:00 |  | 2020-07-08 | 2020-07-08 14:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:23 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.06 | Santos ¦ RM09-76-1 ¦ 8.75in Section ¦ BHC-HRLA-PEX-SP | SANTOS LIMITED | RM09-76-1 | SAVANNA DRILLING #409 | J.20.063159 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-07 12:00 |  | 2020-06-08 | 2020-06-10 14:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:23 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.05 | Santos ¦ RM40-10-1 ¦ DT-HRLA-PEX-SP-GR | SANTOS LIMITED | RM40-10-1 | SAVANNA DRILLING #409 | J.20.063158 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-05 15:00 |  | 2020-06-05 21:00 | 2020-06-06 11:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:23 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.02 | RM50-150-01 | SANTOS LIMITED | RM50-150-1 | SAVANNA DRILLING #409 | J.20.063157 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2020-02-26 12:00 | 2020-05-26 01:00 |  | 2020-05-27 01:00 | 2020-05-29 21:00 |  | 2020-03-15 18:00 | Roma WL | MRony2 | 2022-10-03 13:23 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 |  |  | L3 - Full RO |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.29 | Quad Combo | SANTOS LIMITED | RM68-53-1 | SAVANNA DRILLING #409 | J.20.063147 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-04 06:00 |  | 2020-08-05 18:00 | 2020-08-06 08:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:21 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.21 | RM68-94-1 | SANTOS LIMITED | RM68-94-1 | SAVANNA DRILLING #409 | J.20.063146 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-18 16:00 |  | 2020-07-18 20:00 | 2020-07-20 10:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:21 | FDPSystemUser |  | No |  |  |  |  | Laura Vaiciulyte |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.35 | RM68-59-1 | SANTOS LIMITED | RM68-59-1 | SAVANNA DRILLING #409 | J.20.063136 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-17 16:00 |  | 2020-08-18 16:00 | 2020-08-19 06:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:20 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.18 | RM68-71-1 | SANTOS LIMITED | RM68-71-1 | SAVANNA DRILLING #409 | J.20.063135 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-10 12:00 |  | 2020-07-11 | 2020-07-12 14:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:20 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.03 | RM40-08-1 | SANTOS LIMITED | RM40-08-1 | SAVANNA DRILLING #409 | J.20.063134 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-30 12:00 |  | 2020-05-31 | 2020-06-01 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:20 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.13 | RM68-95-1 BHC-HRLA-PEX-GR-SP | SANTOS LIMITED | RM68-95-1 | SAVANNA DRILLING #409 | J.20.063123 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-29 23:00 |  | 2020-06-29 23:00 | 2020-06-30 13:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:18 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.44 | qc | SANTOS LIMITED | RM40-16-1 | SAVANNA DRILLING #409 | J.21.108900 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-07-24 |  | 2021-07-24 12:00 | 2021-07-25 02:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:17 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.38 | RM68-26-1 | SANTOS LIMITED | RM13-68-2 | SAVANNA DRILLING #409 | J.20.063116 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-26 04:00 |  | 2020-08-26 16:00 | 2020-08-27 06:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.30 | RM68-54-1 | SANTOS LIMITED | RM68-54-1 | SAVANNA DRILLING #409 | J.20.063115 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-05 16:00 |  | 2020-08-07 04:00 | 2020-08-09 18:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.27 | RM68-62-1 Quad Combo | SANTOS LIMITED | RM68-62-1 | SAVANNA DRILLING #409 | J.20.063114 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-08-02 04:00 |  | 2020-12-02 04:00 | 2020-12-02 18:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 |  |  |  |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.22 | RM68-82-1 | SANTOS LIMITED | RM68-82-1 | SAVANNA DRILLING #409 | J.20.063113 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-21 08:00 |  | 2020-07-21 10:00 | 2020-07-22 |  |  | Roma WL | MRony2 | 2022-10-03 13:17 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.11 | RM68-84-1 BHC-HRLA-PEX-GR-SP | SANTOS LIMITED | RM68-84-1 | SAVANNA DRILLING #409 | J.20.063112 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-25 |  | 2020-06-25 | 2020-06-25 14:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:17 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.20 | RM68-85-1 | SANTOS LIMITED | RM68-85-1 | SAVANNA DRILLING #409 | J.20.063099 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-15 20:00 |  | 2020-07-16 04:00 | 2020-07-18 18:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.01 | RM50-149-1 BHC-HRLA-PEX-SP | SANTOS LIMITED | RM50-149-1 | SAVANNA DRILLING #409 | J.20.063098 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-24 18:00 |  | 2020-05-24 18:00 | 2020-05-25 08:00 |  |  | Roma WL | FDPSystemUser | 2022-10-03 13:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.42 | qc | SANTOS LIMITED | RM40-16-1 | SAVANNA DRILLING #409 | J.21.108898 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-07-18 |  | 2021-07-18 12:00 | 2021-07-19 02:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:13 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.40 | qc | SANTOS LIMITED | RM40-16-1 | SAVANNA DRILLING #409 | J.20.063090 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-09-01 04:00 |  | 2020-09-01 16:00 | 2020-09-02 06:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:13 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.33 | RM68-51-1 | SANTOS LIMITED | RM68-51-1 | SAVANNA DRILLING #409 | J.20.063089 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-13 16:00 |  | 2020-08-14 18:00 | 2020-08-15 08:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.31 | RM68-39-1 | SANTOS LIMITED | RM68-39-1 | SAVANNA DRILLING #409 | J.20.063088 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-09 16:00 |  | 2020-08-10 18:00 | 2020-08-11 08:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.15 | RM68-93-1 Quad Combo | SANTOS LIMITED | RM68-93-1 | SAVANNA DRILLING #409 | J.20.063087 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-04 12:00 |  | 2020-07-05 | 2020-07-05 14:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:12 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.43 | qc | SANTOS LIMITED | RM40-16-1 | SAVANNA DRILLING #409 | J.21.108895 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-07-21 |  | 2021-07-21 12:00 | 2021-07-22 02:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:11 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.25 | RM68-90-1 Quad Combo | SANTOS LIMITED | RM68-90-1 | SAVANNA DRILLING #409 | J.20.063073 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-29 |  | 2020-07-29 | 2020-07-29 14:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:11 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.09 | RM08-102-1 BHC-HRLA-PEX-SP-GR | SANTOS LIMITED | RM08-102-1 | SAVANNA DRILLING #409 | J.20.063072 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-20 06:00 |  | 2020-06-20 06:00 | 2020-06-20 20:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 |  |  |  |  | 50 | 50 | 0 | 62.5 | 48.8 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.28 | RM68-52-1 Quad Combo | SANTOS LIMITED | RM68-52-1 | SAVANNA DRILLING #409 | J.20.063066 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-02 18:00 |  | 2020-08-02 18:00 | 2020-08-03 08:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:09 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.41 | qc | SANTOS LIMITED | RM40-16-1 | SAVANNA DRILLING #409 | J.21.108889 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-07-15 |  | 2021-07-15 12:00 | 2021-07-16 02:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:08 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.02 | A.1001639.02.07 | Santos ¦ RM07-108-1 ¦ 8.75in Section ¦ BHC-HRLA-PEX-SP | SANTOS LIMITED | RM07-108-1 | SAVANNA DRILLING #409 | J.20.063057 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-10 12:00 |  | 2020-06-11 | 2020-06-13 14:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:08 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.73 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.22.110205 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-02-01 17:00 |  | 2022-02-01 18:00 | 2022-02-02 18:00 |  |  | Roma WL | EDelange | 2022-10-03 13:31 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.67 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.22.110204 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-01-17 17:00 |  | 2022-01-17 18:00 | 2022-01-18 18:00 |  |  | Roma WL | EDelange | 2022-10-03 13:31 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.06 | Santos ¦ RM50-120-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM50-120-1 | SAVANNA DRILLING #409 | J.20.063204 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-10-31 23:00 |  | 2020-02-02 01:00 | 2020-02-03 01:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:31 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.76 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.22.110203 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-02-10 17:00 |  | 2022-02-10 18:00 | 2022-02-11 18:00 |  |  | Roma WL | EDelange | 2022-10-03 13:29 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.71 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.22.110202 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-01-25 17:00 |  | 2022-01-25 18:00 | 2022-01-26 18:00 |  |  | Roma WL | EDelange | 2022-10-03 13:29 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.64 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.21.108913 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-09-25 16:00 |  | 2021-09-25 17:00 | 2021-09-26 17:00 |  |  | Roma WL | EDelange | 2022-10-03 13:29 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.43 | Santos ¦ BHC-HRLA-PEX ¦ RM40-11-1 | SANTOS LIMITED | RM40111 | SAVANNA DRILLING #409 | J.20.063189 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-16 22:00 |  | 2020-03-19 12:00 | 2020-03-20 12:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:29 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.18 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.19.060620 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-16 | 2019-12-05 23:00 |  | 2019-12-05 23:00 | 2019-12-06 23:00 |  | 2019-10-17 | Roma WL | VOliveira5 | 2022-10-03 13:29 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.17 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.19.060619 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-16 | 2019-12-02 23:00 |  | 2019-12-02 23:00 | 2019-12-03 23:00 |  | 2019-10-17 | Roma WL | VOliveira5 | 2022-10-03 13:29 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.03 | Santos ¦ RM50-111-1 ¦ BHC-HRLA-PEX-SP | SANTOS LIMITED | RM50-111-1 | SAVANNA DRILLING #409 | J.20.063188 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-24 18:00 |  | 2020-01-25 | 2020-01-26 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:29 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.55 | RM40-06-1 | SANTOS LIMITED | RM40-06-1 | SAVANNA DRILLING #409 | J.20.063180 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-29 06:00 |  | 2020-04-30 | 2020-05-01 06:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 13:27 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.22 | QC | SANTOS LIMITED | AC23-115-1 | SAVANNA DRILLING #409 | J.19.060616 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-24 23:00 |  | 2019-12-25 11:00 | 2020-01-01 11:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:27 | FDPSystemUser |  | No |  |  |  |  | Yazdan Saeedabadian |  | 10721.24 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.10 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.19.060615 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-16 | 2019-11-11 23:00 |  | 2019-11-11 23:00 | 2019-11-12 23:00 |  | 2019-10-17 | Roma WL | VOliveira5 | 2022-10-03 13:27 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.78 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.22.110200 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-02-16 17:00 |  | 2022-02-16 18:00 | 2022-02-17 18:00 |  |  | Roma WL | EDelange | 2022-10-03 13:26 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.29 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.20.063175 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-07 23:00 |  | 2020-01-07 23:00 | 2020-01-08 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:26 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.11 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.19.060610 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-16 | 2019-11-14 23:00 |  | 2019-11-14 23:00 | 2019-11-15 23:00 |  | 2019-10-17 | Roma WL | VOliveira5 | 2022-10-03 13:26 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.70 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.22.110199 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-09-13 16:00 |  | 2022-09-13 17:00 | 2022-09-14 17:00 |  |  | Roma WL | EDelange | 2022-10-03 13:23 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.42 | Santos ¦ RM50-155-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM501551 | SAVANNA DRILLING #409 | J.20.063156 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-14 22:00 |  | 2020-03-16 11:00 | 2020-03-17 11:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:23 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.23 | QC | SANTOS LIMITED | AC23-37-1 | SAVANNA DRILLING #409 | J.19.060604 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-25 23:00 |  | 2019-12-26 23:00 | 2019-12-27 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:23 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.62 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.22.110198 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-08-24 17:00 |  | 2022-08-24 18:00 | 2022-08-25 18:00 |  |  | Roma WL | EDelange | 2022-10-03 13:21 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.37 | RM50-132-1_QC | SANTOS LIMITED | RM50-142-1 | SAVANNA DRILLING #409 | J.20.063145 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-18 |  | 2020-02-19 01:00 | 2020-02-20 01:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:21 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.36 | RM50-133-1_QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.20.063144 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-19 |  | 2020-02-21 01:00 | 2020-02-22 01:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:21 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.33 | Santos ¦ RM50-122-1 ¦ BHC-HRLA=PEX | SANTOS LIMITED | RM50-122-1 | SAVANNA DRILLING #409 | J.20.063143 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-01 |  | 2020-02-11 01:00 | 2020-02-12 01:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:21 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.56 | RM40-05-1 | SANTOS LIMITED | RM40-05-1 | SAVANNA DRILLING #409 | J.20.063142 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-02 05:00 |  | 2020-05-03 06:00 | 2020-05-04 06:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 13:21 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 |  |  |  |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.30 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.20.063141 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-10 23:00 |  | 2020-01-10 23:00 | 2020-01-11 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:21 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.74 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.22.110196 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-02-04 17:00 |  | 2022-02-04 18:00 | 2022-02-05 18:00 |  |  | Roma WL | EDelange | 2022-10-03 13:20 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.69 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.22.110195 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-01-23 17:00 |  | 2022-01-23 18:00 | 2022-01-24 18:00 |  |  | Roma WL | EDelange | 2022-10-03 13:20 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.59 | Santos ¦ RM40-14-1A ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM40-14-1A | SAVANNA DRILLING #409 | J.20.063133 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-05-07 17:00 |  | 2020-05-13 18:00 | 2020-05-14 18:00 |  |  | Roma WL | EDelange | 2022-10-03 13:19 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.57 | RM40-04-1 | SANTOS LIMITED | RM40-04-1 | SAVANNA DRILLING #409 | J.20.063132 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-01 05:00 |  | 2020-05-07 06:00 | 2020-05-08 06:00 |  |  | Roma WL | EDelange | 2022-10-03 13:19 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 |  |  |  |  | 33.3 | 50 | 0 | 50 | 40 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.46 | Santos ¦ RM50-102-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM50-102-1 | SAVANNA DRILLING #409 | J.20.063131 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-26 22:00 |  | 2020-03-28 09:00 | 2020-03-29 09:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:19 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.40 | RM50-144-1_QC | SANTOS LIMITED | RM50-144-1 | SAVANNA DRILLING #409 | J.20.063130 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2020-03-08 12:00 | 2020-03-07 11:00 |  | 2020-03-08 12:00 | 2020-03-09 12:00 |  | 2020-03-09 12:00 | Roma WL | MRony2 | 2022-10-03 13:19 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 25 | 20 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.25 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.19.060595 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-29 23:00 |  | 2019-12-29 23:00 | 2019-12-30 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:19 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.13 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.19.060594 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-16 | 2019-11-20 23:00 |  | 2019-11-20 23:00 | 2019-11-21 23:00 |  | 2019-10-17 | Roma WL | VOliveira5 | 2022-10-03 13:19 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.04 | Santos ¦ RM50-110-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM50-110-1 | SAVANNA DRILLING #409 | J.20.063129 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-10-25 23:00 |  | 2020-01-26 22:00 | 2020-01-27 22:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:19 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.02 | Santos ¦ AC23-56-1 ¦ BHC-HRLA-PEX-SP ¦ MDT-GR | SANTOS LIMITED | AC23-56 1 | SAVANNA DRILLING #409 | J.20.063128 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-18 12:00 |  | 2020-01-20 01:00 | 2020-01-22 01:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:19 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 59681.61 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.81 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.22.110194 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-02-25 17:00 |  | 2022-02-25 18:00 | 2022-02-26 18:00 |  |  | Roma WL | EDelange | 2022-10-03 13:18 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.66 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.22.110193 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-01-14 17:00 |  | 2022-01-14 18:00 | 2022-01-15 18:00 |  |  | Roma WL | EDelange | 2022-10-03 13:18 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.35 | Santos ¦ RM50-132-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM50-132-1 | SAVANNA DRILLING #409 | J.20.063122 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2020-01-26 13:00 | 2020-02-10 |  | 2020-02-16 12:00 | 2020-02-17 12:00 |  | 2020-02-17 12:00 | Roma WL | MRony2 | 2022-10-03 13:18 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.15 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.19.060591 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-16 | 2019-11-26 23:00 |  | 2019-11-26 23:00 | 2019-11-27 23:00 |  | 2019-10-17 | Roma WL | VOliveira5 | 2022-10-03 13:18 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.60 | Santos ¦ RM50-148-1 ¦ BHC-HRLA-PEX-SP | SANTOS LIMITED | RM50-148-1 | SAVANNA DRILLING #409 | J.20.063111 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-20 18:00 |  | 2020-05-21 06:00 | 2020-05-22 06:00 |  |  | Roma WL | EDelange | 2022-10-03 13:16 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.51 | RM40-27-1 BHC-HRLA-PEX-GR-SP | SANTOS LIMITED | RM40-27-1 | SAVANNA DRILLING #409 | J.20.063110 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-12 |  | 2020-04-12 | 2020-04-14 |  |  | Roma WL | SAndersen6 | 2022-10-03 13:16 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.50 | RM40-28-1 | SANTOS LIMITED | RM40-18-1 | SAVANNA DRILLING #409 | J.20.063109 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2020-04-09 12:00 | 2020-04-09 12:00 |  | 2020-04-09 12:00 | 2020-04-10 12:00 |  | 2020-04-10 12:00 | Roma WL | SAndersen6 | 2022-10-03 13:16 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.48 | Santos ¦ RM40-29-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM40-29-1 | SAVANNA DRILLING #409 | J.20.063108 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-02 22:00 |  | 2020-04-03 02:00 | 2020-04-04 02:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 13:16 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.45 | SANTOS ¦ RM50-101-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM50-101-1 | SAVANNA DRILLING #409 | J.20.063107 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-21 22:00 |  | 2020-03-24 23:00 | 2020-03-25 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:16 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.28 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.20.063106 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-04 23:00 |  | 2020-01-04 23:00 | 2020-01-05 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:16 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.21 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.19.060590 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-16 | 2019-12-14 23:00 |  | 2019-12-14 23:00 | 2019-12-15 23:00 |  | 2019-10-17 | Roma WL | VOliveira5 | 2022-10-03 13:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.19 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.19.060589 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-16 | 2019-12-08 23:00 |  | 2019-12-08 23:00 | 2019-12-09 23:00 |  | 2019-10-17 | Roma WL | VOliveira5 | 2022-10-03 13:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.16 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.19.060588 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-16 | 2019-11-29 23:00 |  | 2019-11-29 23:00 | 2019-11-30 23:00 |  | 2019-10-17 | Roma WL | VOliveira5 | 2022-10-03 13:15 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.07 | Santos ¦ RM50-123-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM50-123-1 | SAVANNA DRILLING #409 | J.20.063105 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-11-03 23:00 |  | 2020-02-04 08:00 | 2020-02-05 08:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:15 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.79 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.22.110192 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-02-19 17:00 |  | 2022-02-19 18:00 | 2022-02-20 18:00 |  |  | Roma WL | EDelange | 2022-10-03 13:14 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.68 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.22.110191 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-01-20 17:00 |  | 2022-01-20 18:00 | 2022-01-21 18:00 |  |  | Roma WL | EDelange | 2022-10-03 13:14 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.58 | QC | SANTOS LIMITED | RM40-16-1 | SAVANNA DRILLING #409 | J.20.063097 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-04 05:00 |  | 2020-05-10 06:00 | 2020-05-11 06:00 |  |  | Roma WL | EDelange | 2022-10-03 13:14 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 |  |  |  |  | 58.3 | 50 | 0 | 50 | 47.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.39 | RM50-134-1_QC | SANTOS LIMITED | RM50-134-1 | SAVANNA DRILLING #409 | J.20.063096 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-04 11:00 |  | 2020-03-05 12:00 | 2020-03-06 12:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:14 | FDPSystemUser |  | No |  |  |  |  | Lisa Delange |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.12 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.19.060585 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-16 | 2019-11-17 23:00 |  | 2019-11-17 23:00 | 2019-11-18 23:00 |  | 2019-10-17 | Roma WL | VOliveira5 | 2022-10-03 13:14 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.09 | Santos ¦ RM50-145-1 ¦ BHC-HRLA-PEX-SP | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.20.063095 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-14 05:00 |  | 2020-03-14 13:00 | 2020-03-15 13:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:14 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.77 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.22.110190 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-02-13 17:00 |  | 2022-02-13 18:00 | 2022-02-14 18:00 |  |  | Roma WL | EDelange | 2022-10-03 13:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.75 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.22.110189 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-02-07 17:00 |  | 2022-02-07 18:00 | 2022-02-08 18:00 |  |  | Roma WL | EDelange | 2022-10-03 13:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.65 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.21.108897 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-09-28 16:00 |  | 2021-09-28 17:00 | 2021-09-29 17:00 |  |  | Roma WL | EDelange | 2022-10-03 13:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.63 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.21.108896 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2021-06-23 17:00 |  | 2021-06-23 18:00 | 2021-06-24 18:00 |  |  | Roma WL | EDelange | 2022-10-03 13:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.53 | RM40-07-1 | SANTOS LIMITED | RM40-07-1 | SAVANNA DRILLING #409 | J.20.063086 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-29 06:00 |  | 2020-04-29 19:00 | 2020-04-30 19:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 13:12 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 |  |  |  |  | 50 | 0 | 0 | 25 | 22.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.52 | RM40-18-1 BHC-PEX-HRLA-GR-SP | SANTOS LIMITED | RM40-18-1 | SAVANNA DRILLING #409 | J.20.063085 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-14 |  | 2020-04-14 | 2020-04-15 |  |  | Roma WL | SAndersen6 | 2022-10-03 13:12 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.49 | Santos ¦ RM40-19-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM40-19-1 | SAVANNA DRILLING #409 | J.20.063084 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-06 22:00 |  | 2020-04-06 23:00 | 2020-04-07 23:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 13:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.44 | Santos ¦ RM40-20-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM40-20-1 | SAVANNA DRILLING #409 | J.20.063083 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-19 22:00 |  | 2020-03-21 23:00 | 2020-03-22 23:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.34 | Santos ¦ RM50-133-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM50-133-1 | SAVANNA DRILLING #409 | J.20.063082 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-07 |  | 2020-02-13 01:00 | 2020-02-14 01:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.05 | Santos ¦ RM50-121-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM50-121-1 | SAVANNA DRILLING #409 | J.20.063081 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-10-28 23:00 |  | 2020-01-29 15:00 | 2020-01-30 15:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:12 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.82 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.22.110188 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-02-28 17:00 |  | 2022-02-28 18:00 | 2022-03-01 18:00 |  |  | Roma WL | EDelange | 2022-10-03 13:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.80 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.22.110187 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-02-22 17:00 |  | 2022-02-22 18:00 | 2022-02-23 18:00 |  |  | Roma WL | EDelange | 2022-10-03 13:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.54 | RM40-17-1 | SANTOS LIMITED | RM40-17-1 | SAVANNA DRILLING #409 | J.20.063071 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-25 05:00 |  | 2020-04-26 06:00 | 2020-04-27 06:00 |  |  | Roma WL | SAndersen6 | 2022-10-03 13:10 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.32 | Santos ¦ RM50-112-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM50-112-1 | SAVANNA DRILLING #409 | J.20.063070 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-04 |  | 2020-02-08 01:00 | 2020-02-09 01:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:10 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.72 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.22.110186 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-01-28 17:00 |  | 2022-01-28 18:00 | 2022-01-29 18:00 |  |  | Roma WL | EDelange | 2022-10-03 13:09 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.61 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.20.063065 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2020-02-26 19:00 | 2020-05-24 18:00 |  | 2020-05-24 18:00 | 2020-05-25 18:00 |  | 2020-03-13 19:00 | Roma WL | EDelange | 2022-10-03 13:09 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Zaid Wahid |  | 0 |  |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.47 | Santos ¦ RM40-12-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM40-12-1 | SAVANNA DRILLING #409 | J.20.063064 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-31 02:00 |  | 2020-04-04 15:00 | 2020-04-05 15:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:09 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.20 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.19.060573 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-16 | 2019-12-11 23:00 |  | 2019-12-11 23:00 | 2019-12-12 23:00 |  | 2019-10-17 | Roma WL | VOliveira5 | 2022-10-03 13:09 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.41 | Santos ¦ RM50-145-1 ¦ BHC-HRLA-PEX-SP | SANTOS LIMITED | RM501451 | SAVANNA DRILLING #409 | J.20.063056 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-11 22:00 |  | 2020-03-13 02:00 | 2020-03-13 12:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:08 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.31 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.20.063055 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-23 18:00 |  | 2020-04-26 23:00 | 2020-04-27 23:00 |  |  | Roma WL | PLima7 | 2022-10-03 13:07 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.27 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.20.063054 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-01 23:00 |  | 2020-01-01 23:00 | 2020-01-02 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:07 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.01 | QC- Yazdan | SANTOS LIMITED | RM49-106-1 | SAVANNA DRILLING #409 | J.19.060570 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-25 16:00 |  | 2019-12-26 08:00 | 2019-12-29 08:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:07 | FDPSystemUser |  | No |  |  |  |  | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.38 | RM50-143-1_QC | SANTOS LIMITED | RM50-143-1 | SAVANNA DRILLING #409 | J.20.063045 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-20 19:00 |  | 2020-02-21 20:00 | 2020-02-22 20:00 |  |  | Roma WL | MRony2 | 2022-10-03 13:06 | FDPSystemUser |  | No |  |  |  |  | Lisa Delange |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.26 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.19.060567 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-26 23:00 |  | 2019-12-26 23:00 | 2019-12-27 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:06 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 | [10 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.24 | QC | SANTOS LIMITED | AC23-62-1 | SAVANNA DRILLING #409 | J.20.063044 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-04 23:00 |  | 2020-01-04 23:00 | 2020-01-06 23:00 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:06 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 5360.62 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.08 | Santos ¦ RM50-112-1 ¦ BHC-HRLA-PEX | SANTOS LIMITED | RM50-112-1 | SAVANNA DRILLING #409 | J.20.063043 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-11-05 23:00 |  | 2020-02-07 | 2020-02-08 |  |  | Roma WL | VOliveira5 | 2022-10-03 13:06 | FDPSystemUser |  | No |  |  |  |  | Zaid Wahid |  | 0 | [10 empty] | 0 | [7 empty] | Mohammad Rashed Al Rony | WL Evaluation Services
P.1001639 | O.1001639.01 | A.1001639.01.14 | QC | SANTOS LIMITED |  | SAVANNA DRILLING #409 | J.19.060566 | RPE | ES-OH-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-16 | 2019-11-23 23:00 |  | 2019-11-23 23:00 | 2019-11-24 23:00 |  | 2019-10-17 | Roma WL | VOliveira5 | 2022-10-03 13:06 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Victor Oliveira |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Anouk Suminar | WL Evaluation Services
P.1001578 | O.1001578.08 | A.1001578.08.01 | Monthly pro-rate Australind-1 | CHEVRON APG ABU PERTH. | Australind-1 | ENSCO 107 | J.20.062971 | RPI | PS-WL-NO | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-03-24 | 2020-03-19 |  | 2020-03-24 | 2020-03-29 |  | 2020-03-29 | New Burn WL | JCade | 2022-10-03 09:41 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 84434.55 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1001578 | O.1001578.07 | A.1001578.07.02 | March Reimbursable | CHEVRON APG ABU PERTH. | Yammaderry-2 | ENSCO 107 | J.20.062980 | RPI | PS-WL-NO | InComplete | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-03-15 |  | 2020-03-15 | 2020-03-25 |  |  | New Burn WL | frosa2 | 2022-10-03 09:42 | FDPSystemUser |  | No |  |  |  |  | James Cade |  | 66833.4 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1001578 | O.1001578.07 | A.1001578.07.03 | March PTU reimbursables - rev2 | CHEVRON APG ABU PERTH. | Yammaderry-2 | ENSCO 107 | J.20.062978 | RPI | PS-WL-NO | InComplete | Operationally Complete | Close - PSD |  | Not Started | Not Started | In Progress |  | 2020-03-16 |  | 2020-03-16 | 2020-03-25 |  |  | New Burn WL | JCade | 2022-10-03 09:42 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Felipe Donizeti Rosa |  | 10560 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1001578 | O.1001578.07 | A.1001578.07.01 | SCT BISN | CHEVRON APG ABU PERTH. | Yammaderry-2 | ENSCO 107 | J.20.062970 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-02-28 20:00 | 2020-02-26 |  | 2020-02-29 04:00 | 2020-03-09 04:00 |  | 2020-03-08 20:00 | New Burn WL | RTokabayev | 2022-10-03 09:41 | FDPSystemUser |  | No |  |  |  |  | James Cade |  | 128550 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1001578 | O.1001578.06 | A.1001578.06.04 | Ensco 107 TVI May | CHEVRON APG ABU PERTH. | Cowle-4 | ENSCO 107 | J.20.062977 | RPI | PS-WL-NO | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-04-26 | 2020-04-24 |  | 2020-04-26 | 2020-05-10 |  | 2020-05-10 | New Burn WL | LParedes | 2022-10-03 09:41 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1001578 | O.1001578.06 | A.1001578.06.03 | Ensco-107 TVI Apr | CHEVRON APG ABU PERTH. | Cowle-4 | ENSCO 107 | J.20.062976 | RPI | PS-WL-NO | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-03-26 | 2020-03-24 |  | 2020-03-26 | 2020-04-25 |  | 2020-04-25 | New Burn WL | LParedes | 2022-10-03 09:41 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1001578 | O.1001578.06 | A.1001578.06.02 | Ensco-107 TVI Mar | CHEVRON APG ABU PERTH. | Cowle-4 | ENSCO 107 | J.20.062975 | RPI | PS-WL-NO | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-02-26 | 2020-02-24 |  | 2020-02-26 | 2020-03-25 |  | 2020-03-25 | New Burn WL | LParedes | 2022-10-03 09:41 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1001578 | O.1001578.06 | A.1001578.06.01 | BISN Setting | CHEVRON APG ABU PERTH. | Cowle-4 | ENSCO 107 | J.20.062972 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-02-21 | 2020-02-19 |  | 2020-02-21 | 2020-02-27 |  | 2020-02-27 | New Burn WL | RTokabayev | 2022-10-03 09:41 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1001578 | O.1001578.05 | A.1001578.05.01 | MXD/STC BISN | CHEVRON APG ABU PERTH. | Roller-11 | ENSCO 107 | J.20.062969 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-02-01 | 2020-02-01 |  | 2020-02-01 | 2020-02-15 |  | 2020-02-15 | New Burn WL | RTokabayev | 2022-10-03 09:41 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1001578 | O.1001578.04 | A.1001578.04.01 | MXD/STC BISN | CHEVRON APG ABU PERTH. | Roller-10 | ENSCO 107 | J.20.062974 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress | 2020-02-15 | 2020-02-11 |  | 2020-02-15 | 2020-02-21 |  | 2020-02-21 | New Burn WL | RTokabayev | 2022-10-03 09:41 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1001578 | O.1001578.03 | A.1001578.03.01 | BISN | CHEVRON APG ABU PERTH. | Roller-8 | ENSCO 107 | J.20.062973 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-01-23 | 2020-01-23 |  | 2020-01-23 | 2020-01-30 |  | 2020-03-01 | New Burn WL | RTokabayev | 2022-10-03 09:41 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1001578 | O.1001578.02 | A.1001578.02.01 | BISN | CHEVRON APG ABU PERTH. | Roller-7 | ENSCO 107 | J.20.062979 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-01-19 21:00 | 2020-01-17 |  | 2020-01-19 21:00 | 2020-01-22 21:00 |  | 2020-01-22 21:00 | New Burn WL | RTokabayev | 2022-10-03 09:42 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1001578 | O.1001578.01 | A.1001578.01.04 | CVX_TVI_Saladin-B_Saladin-17 | CHEVRON APG ABU PERTH. |  | ENSCO 107 | J.19.060550 | RPI | PS-WL-Ops | InComplete | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2019-10-15 |  | 2019-10-20 | 2019-10-27 |  |  | New Burn WL | RTokabayev | 2022-10-03 09:42 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Production Services
P.1001578 | O.1001578.01 | A.1001578.01.01 | TVI Rental Oct-2019 | CHEVRON APG ABU PERTH. |  | ENSCO 107 | J.19.060549 | RPE | ES-OH-NO | InComplete | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2019-10-01 |  | 2019-10-01 | 2019-10-31 |  |  | New Burn WL | frosa2 | 2022-10-03 09:42 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1001578 | O.1001578.01 | A.1001578.01.02 | TVI Rental Nov-2019 | CHEVRON APG ABU PERTH. |  | ENSCO 107 | J.19.060548 | RPE | ES-OH-NO | Low | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress | 2019-11-01 | 2019-11-01 |  | 2019-11-01 | 2019-12-01 |  | 2019-12-01 | New Burn WL | frosa2 | 2022-10-03 09:41 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1001578 | O.1001578.01 | A.1001578.01.03 | TVI Rental Dec-2019 | CHEVRON APG ABU PERTH. |  | ENSCO 107 | J.19.060547 | RPE | ES-OH-NO | InComplete | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2019-12-01 |  | 2019-12-01 | 2019-12-31 |  |  | New Burn WL | frosa2 | 2022-10-03 09:41 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1001576 | O.1001576.01 | A.1001576.01.02 | Rental Nov-2019 | SANTOS WESTERN AUSTRALIA |  | Noble Tom Prosser | J.19.060545 | RPE | ES-OH-NO | InComplete | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2019-11-01 |  | 2019-11-01 | 2019-12-01 |  |  | New Burn WL | frosa2 | 2022-10-03 09:40 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1001576 | O.1001576.01 | A.1001576.01.01 | Rental Oct-2019 | SANTOS WESTERN AUSTRALIA |  | Noble Tom Prosser | J.19.060543 | RPE | ES-OH-NO | InComplete | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2019-10-01 |  | 2019-10-01 | 2019-10-31 |  |  | New Burn WL | frosa2 | 2022-10-03 09:40 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1001575 | O.1001575.01 | A.1001575.01.01 | RENTAL OCT 2019 | INPEX OPERATIONS AUSTRALIA PTY LTD |  | Ensco 5006 | J.19.060542 | RPE | ES-OH-NO | InComplete | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2019-10-01 |  | 2019-10-01 | 2019-10-31 |  |  | New Burn WL | frosa2 | 2022-10-03 09:40 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1001574 | O.1001574.01 | A.1001574.01.01 | Rental TIcket Oct-2019 | ESSO AUSTRALIA LTD | Sculpin-1 | Ocean Monarch | J.19.060546 | RPE | ES-OH-NO | InComplete | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2019-10-01 |  | 2019-10-01 | 2019-10-31 |  |  | New Burn WL | frosa2 | 2022-10-03 09:40 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1001574 | O.1001574.01 | A.1001574.01.02 | RENTAL NOVEMBER | ESSO AUSTRALIA LTD | Sculpin-1 | Ocean Monarch | J.19.060544 | RPE | ES-OH-NO | InComplete | Cancelled | Close - PSD |  | Not Started | Not Started | In Progress |  | 2019-11-01 |  | 2019-11-01 | 2019-12-01 |  |  | New Burn WL | frosa2 | 2022-10-03 09:40 | FDPSystemUser |  | No |  |  |  |  | Felipe Donizeti Rosa |  | 0 | [10 empty] | 0 | [7 empty] | Luis Cardenas | WL Evaluation Services
P.1001570 | O.1001570.07 | A.1001570.07.40 | Montegue 1 | SANTOS LIMITED | Montegue 1 | Rigless Australia - 1 | J.22.109817 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-05-17 10:00 | 2022-05-17 08:00 |  | 2022-05-17 10:00 | 2022-05-18 18:00 |  | 2022-05-18 18:00 | Moomba WL | DKitney | 2022-10-03 12:12 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 12443.9 | 5 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.39 | Pira 4- Links | SANTOS LIMITED | Pira 4, Dullingari 18, Tellus 1 | Rigless Australia - 1 | J.22.109812 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-05-11 12:00 | 2022-05-11 09:00 |  | 2022-05-11 12:00 | 2022-05-13 12:00 |  | 2022-05-13 12:00 | Moomba WL | DKitney | 2022-10-03 12:12 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 26573.35 | 5 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.38 | Meranji 19 | SANTOS LIMITED | Meranji 19 | Rigless Australia - 1 | J.22.109805 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-05-02 | 2022-05-01 |  | 2022-05-02 | 2022-05-04 23:59 |  | 2022-05-04 23:59 | Moomba WL | ADuong4 | 2022-10-03 12:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6138.53 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.37 | Tickalara 4 | SANTOS LIMITED | Tickalara 4 | Rigless Australia - 1 | J.22.109803 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-30 06:00 | 2022-04-26 13:00 |  | 2022-04-30 06:00 | 2022-05-02 19:59 |  | 2022-05-02 19:59 | Moomba WL | ADuong4 | 2022-10-03 12:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.36 | Meranji 19 | SANTOS LIMITED | PELICAN 10 | Rigless Australia - 1 | J.22.109801 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-04-24 10:00 | 2022-04-23 12:00 |  | 2022-04-24 10:00 | 2022-04-27 23:59 |  | 2022-04-27 23:59 | Moomba WL | ADuong4 | 2022-10-03 12:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 10435.5 | 4 |  | L0 - No RO |  | 91.7 | 100 | 0 | 0 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.35 | Wackett South 1 | SANTOS LIMITED | WACKETT SOUTH 1, HECTOR SOUTH EAST 1, RAFFLE 1 | Rigless Australia - 1 | J.22.109798 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-16 12:00 | 2022-04-15 15:00 |  | 2022-04-16 12:00 | 2022-04-18 23:59 |  | 2022-04-18 23:59 | Moomba WL | ADuong4 | 2022-10-03 12:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 4 |  | L0 - No RO |  | 75 | 100 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.34 | Well # 158 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109756 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-26 22:00 | 2022-06-26 23:00 |  | 2022-06-26 23:00 | 2022-06-29 22:59 |  | 2022-06-30 00:59 | Moomba WL | KKeese | 2022-10-03 12:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.33 | Well # 157 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109755 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-26 22:00 | 2022-06-26 23:00 |  | 2022-06-26 23:00 | 2022-06-29 22:59 |  | 2022-06-30 00:59 | Moomba WL | KKeese | 2022-10-03 12:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.32 | Well # 156 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109754 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-23 22:00 | 2022-06-23 23:00 |  | 2022-06-23 23:00 | 2022-06-26 22:59 |  | 2022-06-27 00:59 | Moomba WL | KKeese | 2022-10-03 12:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.31 | Well # 158 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109725 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-04-05 22:00 | 2022-04-05 23:00 |  | 2022-04-05 23:00 | 2022-04-08 22:59 |  | 2022-04-09 00:59 | Moomba WL | KKeese | 2022-10-03 12:03 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.30 | Well # 157 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109724 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-04-02 22:00 | 2022-04-02 23:00 |  | 2022-04-02 23:00 | 2022-04-05 21:59 |  | 2022-04-05 23:59 | Moomba WL | KKeese | 2022-10-03 12:03 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.29 | U 418_SWQ Campaign Mar-2022 | SANTOS LIMITED | BARYULAH 8, Yanda South 1, Baryulah 6, TIRRAWARRA 93, Mt Howitt 2, Barrolka 21, Kappa 2, Roti 2, LIGER 1 | Rigless Australia - 1 | J.22.109723 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-30 22:00 | 2022-03-30 23:00 |  | 2022-03-30 23:00 | 2022-04-02 22:59 |  | 2022-04-02 21:59 | Moomba WL | KKeese | 2022-10-03 12:03 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.28 | Well # 155 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109722 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-20 22:00 | 2022-06-20 23:00 |  | 2022-06-20 23:00 | 2022-06-23 22:59 |  | 2022-06-24 00:59 | Moomba WL | KKeese | 2022-10-03 12:03 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.27 | Well # 154 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109721 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-17 22:00 | 2022-06-17 23:00 |  | 2022-06-17 23:00 | 2022-06-20 22:59 |  | 2022-06-21 00:59 | Moomba WL | KKeese | 2022-10-03 12:03 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.26 | Well # 153 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109720 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-14 22:00 | 2022-06-14 23:00 |  | 2022-06-14 23:00 | 2022-06-17 22:59 |  | 2022-06-18 00:59 | Moomba WL | KKeese | 2022-10-03 12:03 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.25 | Well #152 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109719 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-11 22:00 | 2022-06-11 23:00 |  | 2022-06-11 23:00 | 2022-06-14 22:59 |  | 2022-06-15 00:59 | Moomba WL | KKeese | 2022-10-03 12:03 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.24 | Well # 151 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109718 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-08 22:00 | 2022-06-08 23:00 |  | 2022-06-08 23:00 | 2022-06-11 22:59 |  | 2022-06-12 00:59 | Moomba WL | KKeese | 2022-10-03 12:03 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.23 | Well # 150 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109717 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-05 22:00 | 2022-06-05 23:00 |  | 2022-06-05 23:00 | 2022-06-08 22:59 |  | 2022-06-09 00:59 | Moomba WL | KKeese | 2022-10-03 12:03 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.22 | Well # 149 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109716 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-02 22:00 | 2022-06-02 23:00 |  | 2022-06-02 23:00 | 2022-06-05 22:59 |  | 2022-06-06 00:59 | Moomba WL | KKeese | 2022-10-03 12:02 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.21 | Well # 148 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109715 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-05-30 22:00 | 2022-05-30 23:00 |  | 2022-05-30 23:00 | 2022-06-02 22:59 |  | 2022-06-03 00:59 | Moomba WL | KKeese | 2022-10-03 12:02 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.20 | Well # 147 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109714 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-05-27 22:00 | 2022-05-27 23:00 |  | 2022-05-27 23:00 | 2022-05-30 22:59 |  | 2022-05-31 00:59 | Moomba WL | KKeese | 2022-10-03 12:02 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.19 | Well # 146 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109713 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-05-24 22:00 | 2022-05-24 23:00 |  | 2022-05-24 23:00 | 2022-05-27 22:59 |  | 2022-05-28 00:59 | Moomba WL | KKeese | 2022-10-03 12:02 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.18 | Well # 145 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109712 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-05-21 22:00 | 2022-05-21 23:00 |  | 2022-05-21 23:00 | 2022-05-24 22:59 |  | 2022-05-25 00:59 | Moomba WL | KKeese | 2022-10-03 12:02 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.17 | Well # 144 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109711 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-05-18 22:00 | 2022-05-18 23:00 |  | 2022-05-18 23:00 | 2022-05-21 22:59 |  | 2022-05-22 00:59 | Moomba WL | KKeese | 2022-10-03 12:02 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.16 | Well # 143 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109710 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-05-15 22:00 | 2022-05-15 23:00 |  | 2022-05-15 23:00 | 2022-05-18 22:59 |  | 2022-05-19 00:59 | Moomba WL | KKeese | 2022-10-03 12:02 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.15 | Well # 142 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109709 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-05-12 22:00 | 2022-05-12 23:00 |  | 2022-05-12 23:00 | 2022-05-15 22:59 |  | 2022-05-16 00:59 | Moomba WL | KKeese | 2022-10-03 12:02 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.14 | Well # 141 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109708 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-05-09 22:00 | 2022-05-09 23:00 |  | 2022-05-09 23:00 | 2022-05-12 22:59 |  | 2022-05-13 00:59 | Moomba WL | KKeese | 2022-10-03 12:02 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.13 | Well # 140 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109707 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-05-06 22:00 | 2022-05-06 23:00 |  | 2022-05-06 23:00 | 2022-05-09 22:59 |  | 2022-05-10 00:59 | Moomba WL | KKeese | 2022-10-03 12:01 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.12 | Well # 139 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109706 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-05-03 22:00 | 2022-05-03 23:00 |  | 2022-05-03 23:00 | 2022-05-06 22:59 |  | 2022-05-07 00:59 | Moomba WL | KKeese | 2022-10-03 12:01 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.11 | Well # 138 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109705 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-04-30 22:00 | 2022-04-30 23:00 |  | 2022-04-30 23:00 | 2022-05-03 22:59 |  | 2022-05-04 00:59 | Moomba WL | KKeese | 2022-10-03 12:01 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.10 | Well # 137 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109704 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-04-27 22:00 | 2022-04-27 23:00 |  | 2022-04-27 23:00 | 2022-04-30 22:59 |  | 2022-05-01 00:59 | Moomba WL | KKeese | 2022-10-03 12:01 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.09 | Links Campaign | SANTOS LIMITED | BIG LAKE 150, Dullingari 18, Merrimelia 10 | Rigless Australia - 1 | J.22.109703 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-06-24 22:00 | 2022-06-24 23:00 |  | 2022-06-24 23:00 | 2022-06-27 22:59 |  | 2022-06-27 21:59 | Moomba WL | KKeese | 2022-10-03 12:01 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 34997.27 | 1 |  |  |  | 75 | 50 | 0 | 100 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.08 | Moomba CBL HT Wells (273/274) | SANTOS LIMITED | Moomba 273, Moomba 274 | Rigless Australia - 1 | J.22.109702 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-06-23 22:00 | 2022-06-23 23:00 |  | 2022-06-23 23:00 | 2022-06-26 22:59 |  | 2022-06-26 21:59 | Moomba WL | KKeese | 2022-10-03 12:01 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 10872.33 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.07 | Tiirawarra Links Campaign (Kanowana 1, Kanowana 7, Cowralli 10, Merrimelia 10) | SANTOS LIMITED | COWRALLI 10, MERRIMELIA 10, KANOWANA 1, KANOWANA 7 | Rigless Australia - 1 | J.22.109701 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-07-09 17:20 | 2022-05-29 13:00 |  | 2022-05-30 06:00 | 2022-06-02 05:59 |  | 2022-07-10 17:22 | Moomba WL | KKeese | 2022-10-03 12:01 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 43262.64 | 1 |  | L0 - No RO |  | 50 | 83.3 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.06 | Moorari3- Tubing Punchx2 | SANTOS LIMITED | MOORARI 3 | Rigless Australia - 1 | J.22.109700 | RPI | PS-WL-NO | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-05-19 12:47 | 2022-04-15 23:00 |  | 2022-04-15 23:00 | 2022-04-18 22:59 |  | 2022-05-20 12:50 | Moomba WL | KKeese | 2022-10-03 12:01 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 15728.4 | 1 |  | L0 - No RO |  | 91.7 | 33.3 | 100 | 50 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.05 | Liger 1 | SANTOS LIMITED | LIGER 1 | Rigless Australia - 1 | J.22.109699 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-10 22:00 | 2022-03-09 23:00 |  | 2022-03-10 23:00 | 2022-03-13 22:59 |  | 2022-03-13 21:59 | Moomba WL | KKeese | 2022-10-03 12:01 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 8099.81 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.04 | SANTOS CBL/PNX Campaign | SANTOS LIMITED | Roti 2, Chimera 1, Barrolka 24, Karmona 6 | Rigless Australia - 1 | J.22.109698 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-03-03 22:00 | 2022-03-03 23:00 |  | 2022-03-03 23:00 | 2022-03-09 22:59 |  | 2022-03-09 21:59 | Moomba WL | KKeese | 2022-10-03 12:01 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 42833.62 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.03 | Big Lake 77 | SANTOS LIMITED | Big Lake 77 | Rigless Australia - 1 | J.22.109697 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-02-26 05:00 | 2022-02-24 10:00 |  | 2022-02-26 06:00 | 2022-03-01 05:59 |  | 2022-03-01 04:59 | Moomba WL | KKeese | 2022-10-03 12:00 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 33048.73 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.02 | Amyema 2- Casing Patch | SANTOS LIMITED | Amyema 2 | Rigless Australia - 1 | J.22.109696 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-02-22 07:00 | 2022-02-22 07:00 |  | 2022-02-22 08:00 | 2022-02-25 07:59 |  | 2022-02-25 06:59 | Moomba WL | KKeese | 2022-10-03 12:00 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 8596.49 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001570 | O.1001570.07 | A.1001570.07.01 | Kappa 2- SCMT | SANTOS LIMITED | Kappa 2 | Rigless Australia - 1 | J.22.109695 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-02-20 07:00 | 2022-02-19 12:00 |  | 2022-02-20 07:00 | 2022-02-23 06:59 |  | 2022-02-23 05:59 | Moomba WL | KKeese | 2022-10-03 12:00 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 9680.92 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.41 | U418, Kappa 1, | SANTOS LIMITED | Kappa 1, Coonatie 18, Moorari 23, WOOLKINA 003 | Rigless Australia - 1 | J.23.008528 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-01-05 01:00 | 2023-01-05 |  | 2023-01-05 | 2023-01-07 23:59 |  | 2023-01-08 00:59 | Moomba WL | IWahbi | 2022-12-29 13:14 | KKeese |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.73 | Dullingari 62/Dullingari North 23/Beckler 7 | SANTOS LIMITED | Dullingari 62, DULLINGARI NORTH 23, Beckler 7 | Rigless Australia - 1 | J.21.108791 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-21 | 2021-11-20 |  | 2021-11-21 | 2021-11-22 23:59 |  | 2022-11-22 23:59 | Moomba WL | ADuong4 | 2022-10-03 11:51 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 3898.64 | 1 |  |  |  | 83.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.72 | Moon 4 | SANTOS LIMITED | Moon 4 | Rigless Australia - 1 | J.21.108789 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-16 10:00 | 2021-11-16 |  | 2021-11-16 10:00 | 2021-11-19 23:59 |  | 2022-11-19 23:59 | Moomba WL | ADuong4 | 2022-10-03 11:51 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 4 |  |  |  | 91.7 | 50 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.71 | Dullingari 43DW1 | SANTOS LIMITED | DULLINGARI 43 | Rigless Australia - 1 | J.21.108788 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-14 08:00 | 2021-11-14 |  | 2021-11-14 08:00 | 2021-11-16 23:59 |  | 2022-11-16 23:59 | Moomba WL | ADuong4 | 2022-10-03 11:51 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 10893.92 | 16 |  |  |  | 91.7 | 50 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.70 | Koree South 1 | SANTOS LIMITED | Koree South 1 | Rigless Australia - 1 | J.21.108787 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-11 07:00 | 2021-11-11 |  | 2021-11-11 07:00 | 2021-11-13 23:59 |  | 2022-11-13 23:59 | Moomba WL | ADuong4 | 2022-10-03 11:51 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6263.81 | 1 |  |  |  | 91.7 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.69 | Well #66 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008555 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-27 01:00 | 2023-03-27 | 2023-03-27 12:00 | 2023-03-27 | 2023-03-29 23:59 | 2023-03-30 12:00 | 2023-03-30 00:59 | Moomba WL | IWahbi | 2022-10-03 11:43 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.68 | Well #65 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008554 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-24 01:00 | 2023-03-24 | 2023-03-24 12:00 | 2023-03-24 | 2023-03-26 23:59 | 2023-03-27 12:00 | 2023-03-27 00:59 | Moomba WL | IWahbi | 2022-10-03 11:43 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.67 | Well #64 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008553 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-21 01:00 | 2023-03-21 | 2023-03-21 12:00 | 2023-03-21 | 2023-03-23 23:59 | 2023-03-24 12:00 | 2023-03-24 00:59 | Moomba WL | IWahbi | 2022-10-03 11:43 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.66 | Well #63 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008552 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-18 01:00 | 2023-03-18 | 2023-03-18 12:00 | 2023-03-18 | 2023-03-20 23:59 | 2023-03-21 12:00 | 2023-03-21 00:59 | Moomba WL | IWahbi | 2022-10-03 11:43 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.65 | Well #62 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008551 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-15 01:00 | 2023-03-15 | 2023-03-15 12:00 | 2023-03-15 | 2023-03-17 23:59 | 2023-03-18 12:00 | 2023-03-18 00:59 | Moomba WL | IWahbi | 2022-10-03 11:43 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.64 | Well #61 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008550 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-12 01:00 | 2023-03-12 | 2023-03-12 12:00 | 2023-03-12 | 2023-03-14 23:59 | 2023-03-15 12:00 | 2023-03-15 00:59 | Moomba WL | IWahbi | 2022-10-03 11:43 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.63 | Well #60 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008549 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-09 01:00 | 2023-03-09 | 2023-03-09 12:00 | 2023-03-09 | 2023-03-11 23:59 | 2023-03-12 12:00 | 2023-03-12 00:59 | Moomba WL | IWahbi | 2022-10-03 11:43 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.62 | Well #59 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008548 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-06 01:00 | 2023-03-06 | 2023-03-06 12:00 | 2023-03-06 | 2023-03-08 23:59 | 2023-03-09 12:00 | 2023-03-09 00:59 | Moomba WL | IWahbi | 2022-10-03 11:43 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.61 | Well #58 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008547 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-03 01:00 | 2023-03-03 | 2023-03-03 12:00 | 2023-03-03 | 2023-03-05 23:59 | 2023-03-06 12:00 | 2023-03-06 00:59 | Moomba WL | IWahbi | 2022-10-03 11:43 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.60 | Well #57 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008546 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-02-28 01:00 | 2023-02-28 | 2023-02-28 12:00 | 2023-02-28 | 2023-03-02 23:59 | 2023-03-03 12:00 | 2023-03-03 00:59 | Moomba WL | IWahbi | 2022-10-03 11:42 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.59 | Well #56 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008545 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-02-25 01:00 | 2023-02-25 | 2023-02-25 12:00 | 2023-02-25 | 2023-02-27 23:59 | 2023-02-28 12:00 | 2023-02-28 00:59 | Moomba WL | IWahbi | 2022-10-03 11:42 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.58 | Well #55 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008544 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-02-22 01:00 | 2023-02-22 | 2023-02-22 12:00 | 2023-02-22 | 2023-02-24 23:59 | 2023-02-25 12:00 | 2023-02-25 00:59 | Moomba WL | IWahbi | 2022-10-03 11:42 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.57 | Well #54 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008543 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-02-19 01:00 | 2023-02-19 | 2023-02-19 12:00 | 2023-02-19 | 2023-02-21 23:59 | 2023-02-22 12:00 | 2023-02-22 00:59 | Moomba WL | IWahbi | 2022-10-03 11:42 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.56 | Well #53 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008542 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-02-16 01:00 | 2023-02-16 | 2023-02-16 12:00 | 2023-02-16 | 2023-02-18 23:59 | 2023-02-19 12:00 | 2023-02-19 00:59 | Moomba WL | IWahbi | 2022-10-03 11:42 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.55 | Well #52 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008541 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-02-13 01:00 | 2023-02-13 | 2023-02-13 12:00 | 2023-02-13 | 2023-02-15 23:59 | 2023-02-16 12:00 | 2023-02-16 00:59 | Moomba WL | IWahbi | 2022-10-03 11:42 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.54 | Well #51 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008540 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-02-10 01:00 | 2023-02-10 | 2023-02-10 12:00 | 2023-02-10 | 2023-02-12 23:59 | 2023-02-13 12:00 | 2023-02-13 00:59 | Moomba WL | IWahbi | 2022-10-03 11:42 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.53 | Well #50 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008539 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-02-07 01:00 | 2023-02-07 | 2023-02-07 12:00 | 2023-02-07 | 2023-02-09 23:59 | 2023-02-10 12:00 | 2023-02-10 00:59 | Moomba WL | IWahbi | 2022-10-03 11:42 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.52 | Well #49 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008538 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-02-04 01:00 | 2023-02-04 | 2023-02-04 12:00 | 2023-02-04 | 2023-02-06 23:59 | 2023-02-07 12:00 | 2023-02-07 00:59 | Moomba WL | IWahbi | 2022-10-03 11:42 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.51 | Well #48 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008537 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-02-01 01:00 | 2023-02-01 | 2023-02-01 12:00 | 2023-02-01 | 2023-02-03 23:59 | 2023-02-04 12:00 | 2023-02-04 00:59 | Moomba WL | IWahbi | 2022-10-03 11:42 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.50 | Well #47 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008536 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-01-29 01:00 | 2023-01-29 | 2023-01-29 12:00 | 2023-01-29 | 2023-01-31 23:59 | 2023-02-01 12:00 | 2023-02-01 00:59 | Moomba WL | IWahbi | 2022-10-03 11:42 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.49 | Well #46 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008535 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-01-26 01:00 | 2023-01-26 | 2023-01-26 12:00 | 2023-01-26 | 2023-01-28 23:59 | 2023-01-29 12:00 | 2023-01-29 00:59 | Moomba WL | IWahbi | 2022-10-03 11:42 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.48 | Well #45 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008534 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-01-23 01:00 | 2023-01-23 | 2023-01-23 12:00 | 2023-01-23 | 2023-01-25 23:59 | 2023-01-26 12:00 | 2023-01-26 00:59 | Moomba WL | IWahbi | 2022-10-03 11:42 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.47 | Well #44 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008533 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-01-20 01:00 | 2023-01-20 | 2023-01-20 12:00 | 2023-01-20 | 2023-01-22 23:59 | 2023-01-23 12:00 | 2023-01-23 00:59 | Moomba WL | IWahbi | 2022-10-03 11:41 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.46 | Well #43 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008532 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-01-17 01:00 | 2023-01-17 | 2023-01-17 12:00 | 2023-01-17 | 2023-01-19 23:59 | 2023-01-20 12:00 | 2023-01-20 00:59 | Moomba WL | IWahbi | 2022-10-03 11:41 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.45 | Well #42 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008531 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-01-14 01:00 | 2023-01-14 | 2023-01-14 12:00 | 2023-01-14 | 2023-01-16 23:59 | 2023-01-17 12:00 | 2023-01-17 00:59 | Moomba WL | IWahbi | 2022-10-03 11:41 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.44 | Well #41 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008530 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-01-11 01:00 | 2023-01-11 | 2023-01-11 12:00 | 2023-01-11 | 2023-01-13 23:59 | 2023-01-14 12:00 | 2023-01-14 00:59 | Moomba WL | IWahbi | 2022-10-03 11:41 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.43 | Well #40 | SANTOS LIMITED |  | Rigless Australia - 1 | J.23.008529 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-01-08 01:00 | 2023-01-08 | 2023-01-08 12:00 | 2023-01-08 | 2023-01-10 23:59 | 2023-01-11 12:00 | 2023-01-11 00:59 | Moomba WL | IWahbi | 2022-10-03 11:41 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.42 | Kidman North 2_Tubing Cutter | SANTOS LIMITED | Kidman North 2 | Rigless Australia - 1 | J.22.109528 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-17 14:00 | 2022-01-16 13:00 | 2022-01-17 | 2022-01-17 14:00 | 2022-01-20 13:59 | 2022-01-21 | 2022-01-20 13:59 | Moomba WL | IWahbi | 2022-10-03 11:41 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  |  |  | 83.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.40 | Coonatie 18 perf | SANTOS LIMITED | Coonatie 18 | Rigless Australia - 1 | J.22.109527 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-14 01:00 | 2022-01-14 | 2022-01-14 | 2022-01-14 | 2022-01-16 23:59 | 2022-01-17 | 2022-01-17 00:59 | Moomba WL | IWahbi | 2022-10-03 11:41 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  |  |  | 83.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.39 | Meranji 2 | SANTOS LIMITED | Meranji 2 | Rigless Australia - 1 | J.21.108779 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-04 06:00 | 2021-11-04 | 2022-11-04 11:00 | 2021-11-04 06:00 | 2021-11-07 23:59 | 2022-11-08 11:00 | 2022-11-07 23:59 | Moomba WL | ADuong4 | 2022-10-03 11:40 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 91.7 | 50 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.38 | Moorari 3 | SANTOS LIMITED | MOOMBA 250 | Rigless Australia - 1 | J.21.108777 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-11-01 06:00 | 2021-11-01 | 2022-11-01 11:00 | 2021-11-01 06:00 | 2021-11-03 23:59 | 2022-11-04 11:00 | 2022-11-03 23:59 | Moomba WL | ADuong4 | 2022-10-03 11:40 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 91.7 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.37 | Kurunda 3 | SANTOS LIMITED | Kurunda 3 | Rigless Australia - 1 | J.21.108774 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-29 06:00 | 2021-10-29 | 2022-10-29 | 2021-10-29 06:00 | 2021-11-03 23:59 | 2022-11-04 11:00 | 2022-11-03 23:59 | Moomba WL | ADuong4 | 2022-10-03 11:40 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6822.61 | 1 |  |  |  | 91.7 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.36 | Well #36 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109526 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-27 01:00 | 2022-12-27 | 2022-12-27 12:00 | 2022-12-27 | 2022-12-29 23:59 | 2022-12-30 12:00 | 2022-12-30 00:59 | Moomba WL | IWahbi | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.35 | Well #35 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109525 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-24 01:00 | 2022-12-24 | 2022-12-24 12:00 | 2022-12-24 | 2022-12-26 23:59 | 2022-12-27 12:00 | 2022-12-27 00:59 | Moomba WL | IWahbi | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.34 | Well #34 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109524 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-21 01:00 | 2022-12-21 | 2022-12-21 12:00 | 2022-12-21 | 2022-12-23 23:59 | 2022-12-24 12:00 | 2022-12-24 00:59 | Moomba WL | IWahbi | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.33 | Well #33 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109523 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-18 01:00 | 2022-12-18 | 2022-12-18 12:00 | 2022-12-18 | 2022-12-20 23:59 | 2022-12-21 12:00 | 2022-12-21 00:59 | Moomba WL | IWahbi | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.32 | Well #32 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109522 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-15 01:00 | 2022-12-15 | 2022-12-15 12:00 | 2022-12-15 | 2022-12-17 23:59 | 2022-12-18 12:00 | 2022-12-18 00:59 | Moomba WL | IWahbi | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.31 | Well #31 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109521 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-12 01:00 | 2022-12-12 | 2022-12-12 12:00 | 2022-12-12 | 2022-12-14 23:59 | 2022-12-15 12:00 | 2022-12-15 00:59 | Moomba WL | IWahbi | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.30 | Well #30 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109520 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-09 01:00 | 2022-12-09 | 2022-12-09 12:00 | 2022-12-09 | 2022-12-11 23:59 | 2022-12-12 12:00 | 2022-12-12 00:59 | Moomba WL | IWahbi | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.29 | Well #29 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109519 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-06 01:00 | 2022-12-06 | 2022-12-06 12:00 | 2022-12-06 | 2022-12-08 23:59 | 2022-12-09 12:00 | 2022-12-09 00:59 | Moomba WL | IWahbi | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.28 | Well #28 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109518 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-03 01:00 | 2022-12-03 | 2022-12-03 12:00 | 2022-12-03 | 2022-12-05 23:59 | 2022-12-06 12:00 | 2022-12-06 00:59 | Moomba WL | IWahbi | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.27 | Well #27 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109517 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-11-30 01:00 | 2022-11-30 | 2022-11-30 12:00 | 2022-11-30 | 2022-12-02 23:59 | 2022-12-03 12:00 | 2022-12-03 00:59 | Moomba WL | IWahbi | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.26 | Well #26 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109516 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-11-27 01:00 | 2022-11-27 | 2022-11-27 12:00 | 2022-11-27 | 2022-11-29 23:59 | 2022-11-30 12:00 | 2022-11-30 00:59 | Moomba WL | IWahbi | 2022-10-03 11:36 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.25 | Well #25 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109515 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-11-24 01:00 | 2022-11-24 | 2022-11-24 12:00 | 2022-11-24 | 2022-11-26 23:59 | 2022-11-27 12:00 | 2022-11-27 00:59 | Moomba WL | IWahbi | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.24 | Well #24 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109514 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-11-21 01:00 | 2022-11-21 | 2022-11-21 12:00 | 2022-11-21 | 2022-11-23 23:59 | 2022-11-24 12:00 | 2022-11-24 00:59 | Moomba WL | IWahbi | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.23 | Well #23 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109513 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-11-18 01:00 | 2022-11-18 | 2022-11-18 12:00 | 2022-11-18 | 2022-11-20 23:59 | 2022-11-21 12:00 | 2022-11-21 00:59 | Moomba WL | IWahbi | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.22 | Well #22 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109512 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-11-15 01:00 | 2022-11-15 | 2022-11-15 12:00 | 2022-11-15 | 2022-11-17 23:59 | 2022-11-18 12:00 | 2022-11-18 00:59 | Moomba WL | IWahbi | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.21 | Well #21 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109511 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-11-12 01:00 | 2022-11-12 | 2022-11-12 12:00 | 2022-11-12 | 2022-11-14 23:59 | 2022-11-15 12:00 | 2022-11-15 00:59 | Moomba WL | IWahbi | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.20 | Well #20 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109510 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-11-09 01:00 | 2022-11-09 | 2022-11-09 12:00 | 2022-11-09 | 2022-11-11 23:59 | 2022-11-12 12:00 | 2022-11-12 00:59 | Moomba WL | IWahbi | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.19 | Well #19 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109509 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-11-06 01:00 | 2022-11-06 | 2022-11-06 12:00 | 2022-11-06 | 2022-11-08 23:59 | 2022-11-09 12:00 | 2022-11-09 00:59 | Moomba WL | IWahbi | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.18 | Well #18 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109508 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-11-03 01:00 | 2022-11-03 | 2022-11-03 12:00 | 2022-11-03 | 2022-11-05 23:59 | 2022-11-06 12:00 | 2022-11-06 00:59 | Moomba WL | IWahbi | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.17 | Well #17 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109507 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-10-31 01:00 | 2022-10-31 | 2022-10-31 12:00 | 2022-10-31 | 2022-11-02 23:59 | 2022-11-03 12:00 | 2022-11-03 00:59 | Moomba WL | IWahbi | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.16 | Well #16 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109506 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-10-28 01:00 | 2022-10-28 | 2022-10-28 12:00 | 2022-10-28 | 2022-10-30 23:59 | 2022-10-31 12:00 | 2022-10-31 00:59 | Moomba WL | IWahbi | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.15 | Well #15 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109505 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-10-25 01:00 | 2022-10-25 | 2022-10-25 12:00 | 2022-10-25 | 2022-10-27 23:59 | 2022-10-28 12:00 | 2022-10-28 00:59 | Moomba WL | IWahbi | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.14 | Well #14 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109504 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-10-22 01:00 | 2022-10-22 | 2022-10-22 12:00 | 2022-10-22 | 2022-10-24 23:59 | 2022-10-25 12:00 | 2022-10-25 00:59 | Moomba WL | IWahbi | 2022-10-03 11:35 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.13 | Well #13 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109503 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-10-19 01:00 | 2022-10-19 | 2022-10-19 12:00 | 2022-10-19 | 2022-10-21 23:59 | 2022-10-22 12:00 | 2022-10-22 00:59 | Moomba WL | IWahbi | 2022-10-03 11:34 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.12 | Well #12 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109502 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-10-16 01:00 | 2022-10-16 | 2022-10-16 12:00 | 2022-10-16 | 2022-10-18 23:59 | 2022-10-19 12:00 | 2022-10-19 00:59 | Moomba WL | IWahbi | 2022-10-03 11:34 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.11 | Well #11 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109501 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-10-13 01:00 | 2022-10-13 | 2022-10-13 12:00 | 2022-10-13 | 2022-10-15 23:59 | 2022-10-16 12:00 | 2022-10-16 00:59 | Moomba WL | IWahbi | 2022-10-03 11:34 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.10 | Well #10 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109500 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-10-10 01:00 | 2022-10-10 | 2022-10-10 12:00 | 2022-10-10 | 2022-10-12 23:59 | 2022-10-13 12:00 | 2022-10-13 00:59 | Moomba WL | IWahbi | 2022-10-03 11:34 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.09 | Well #9 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109499 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-10-07 01:00 | 2022-10-07 | 2022-10-07 12:00 | 2022-10-07 | 2022-10-09 23:59 | 2022-10-10 12:00 | 2022-10-10 00:59 | Moomba WL | IWahbi | 2022-10-03 11:34 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.08 | SA Campagn-Big Lake 110, Moomba 250 | SANTOS LIMITED | MOOMBA 250, Big Lake 110, Brumby 14, Dilchee 5 | Rigless Australia - 1 | J.21.108735 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-07 01:00 | 2021-10-07 | 2022-10-07 12:00 | 2021-10-07 | 2021-10-09 23:59 | 2022-10-10 12:00 | 2022-10-10 00:59 | Moomba WL | IWahbi | 2022-10-03 11:34 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.07 | Well #7 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109498 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-09-30 | 2022-09-30 | 2022-09-30 11:00 | 2022-09-30 | 2022-10-03 00:59 | 2022-10-03 12:00 | 2022-10-03 00:59 | Moomba WL | IWahbi | 2022-10-03 11:34 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.06 | Well #6 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109497 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-09-27 | 2022-09-27 | 2022-09-27 10:00 | 2022-09-27 | 2022-09-29 23:59 | 2022-09-30 11:00 | 2022-09-29 23:59 | Moomba WL | IWahbi | 2022-10-03 11:34 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.05 | Well #5 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109496 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-09-24 | 2022-09-24 | 2022-09-24 10:00 | 2022-09-24 | 2022-09-26 23:59 | 2022-09-27 10:00 | 2022-09-26 23:59 | Moomba WL | IWahbi | 2022-10-03 11:34 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.04 | Well #4 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109495 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-09-21 | 2022-09-21 | 2022-09-21 10:00 | 2022-09-21 | 2022-09-23 23:59 | 2022-09-24 10:00 | 2022-09-23 23:59 | Moomba WL | IWahbi | 2022-10-03 11:34 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.03 | Well #3 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109494 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-09-18 | 2022-09-18 | 2022-09-18 10:00 | 2022-09-18 | 2022-09-20 23:59 | 2022-09-21 10:00 | 2022-09-20 23:59 | Moomba WL | IWahbi | 2022-10-03 11:34 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.02 | Well #2 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109493 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-09-15 | 2022-09-15 | 2022-09-15 10:00 | 2022-09-15 | 2022-09-17 23:59 | 2022-09-18 10:00 | 2022-09-17 23:59 | Moomba WL | IWahbi | 2022-10-03 11:33 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.06 | A.1001570.06.01 | Psyche 6 | SANTOS LIMITED | Psyche 6 | Rigless Australia - 1 | J.21.108734 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-10-02 | 2021-10-01 | 2022-10-02 11:00 | 2021-10-02 | 2021-10-05 00:59 | 2022-10-05 12:00 | 2022-10-05 00:59 | Moomba WL | IWahbi | 2022-10-03 11:33 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.142 | Well #128 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109559 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-03-27 22:00 | 2022-03-28 | 2022-03-28 01:00 | 2022-03-28 | 2022-03-30 23:59 | 2022-03-31 01:00 | 2022-03-30 23:59 | Moomba WL | IWahbi | 2022-10-03 11:46 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.141 | Well #127 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109557 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-03-24 22:00 | 2022-03-25 | 2022-03-25 01:00 | 2022-03-25 | 2022-03-27 23:59 | 2022-03-28 01:00 | 2022-03-27 23:59 | Moomba WL | IWahbi | 2022-10-03 11:46 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.140 | Well #126 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109555 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-03-21 22:00 | 2022-03-22 | 2022-03-22 01:00 | 2022-03-22 | 2022-03-24 23:59 | 2022-03-25 01:00 | 2022-03-24 23:59 | Moomba WL | IWahbi | 2022-10-03 11:45 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.139 | Well #125 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109554 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-03-18 22:00 | 2022-03-19 | 2022-03-19 01:00 | 2022-03-19 | 2022-03-21 23:59 | 2022-03-22 01:00 | 2022-03-21 23:59 | Moomba WL | IWahbi | 2022-10-03 11:45 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.138 | Well #124 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109553 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-03-15 22:00 | 2022-03-16 | 2022-03-16 01:00 | 2022-03-16 | 2022-03-18 23:59 | 2022-03-19 01:00 | 2022-03-18 23:59 | Moomba WL | IWahbi | 2022-10-03 11:45 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.137 | Well #123 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109552 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-03-12 22:00 | 2022-03-13 | 2022-03-13 01:00 | 2022-03-13 | 2022-03-15 23:59 | 2022-03-16 01:00 | 2022-03-15 23:59 | Moomba WL | IWahbi | 2022-10-03 11:45 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.136 | Well #122 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109551 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-03-09 22:00 | 2022-03-10 | 2022-03-10 01:00 | 2022-03-10 | 2022-03-12 23:59 | 2022-03-13 01:00 | 2022-03-12 23:59 | Moomba WL | IWahbi | 2022-10-03 11:45 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.135 | Well #121 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109550 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-03-06 22:00 | 2022-03-07 | 2022-03-07 01:00 | 2022-03-07 | 2022-03-09 23:59 | 2022-03-10 01:00 | 2022-03-09 23:59 | Moomba WL | IWahbi | 2022-10-03 11:45 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.134 | Well #120 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109549 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-03-03 22:00 | 2022-03-04 | 2022-03-04 01:00 | 2022-03-04 | 2022-03-06 23:59 | 2022-03-07 01:00 | 2022-03-06 23:59 | Moomba WL | IWahbi | 2022-10-03 11:45 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.133 | Well #119 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109548 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-02-28 22:00 | 2022-03-01 | 2022-03-01 01:00 | 2022-03-01 | 2022-03-03 23:59 | 2022-03-04 01:00 | 2022-03-03 23:59 | Moomba WL | IWahbi | 2022-10-03 11:45 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.132 | Well #118 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109547 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-02-25 22:00 | 2022-02-26 | 2022-02-26 01:00 | 2022-02-26 | 2022-02-28 23:59 | 2022-03-01 01:00 | 2022-02-28 23:59 | Moomba WL | IWahbi | 2022-10-03 11:45 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.131 | Well #117 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109546 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-02-22 22:00 | 2022-02-23 | 2022-02-23 01:00 | 2022-02-23 | 2022-02-25 23:59 | 2022-02-26 01:00 | 2022-02-25 23:59 | Moomba WL | IWahbi | 2022-10-03 11:45 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.130 | Well #116 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109545 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-02-19 22:00 | 2022-02-20 | 2022-02-20 01:00 | 2022-02-20 | 2022-02-22 23:59 | 2022-02-23 01:00 | 2022-02-22 23:59 | Moomba WL | IWahbi | 2022-10-03 11:45 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.129 | Well #115 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109544 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-02-16 22:00 | 2022-02-17 | 2022-02-17 01:00 | 2022-02-17 | 2022-02-19 23:59 | 2022-02-20 01:00 | 2022-02-19 23:59 | Moomba WL | IWahbi | 2022-10-03 11:45 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.128 | Well #114 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109543 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-02-13 22:00 | 2022-02-14 | 2022-02-14 01:00 | 2022-02-14 | 2022-02-16 23:59 | 2022-02-17 01:00 | 2022-02-16 23:59 | Moomba WL | IWahbi | 2022-10-03 11:44 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.127 | Well #113 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109542 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-02-10 22:00 | 2022-02-11 | 2022-02-11 01:00 | 2022-02-11 | 2022-02-13 23:59 | 2022-02-14 01:00 | 2022-02-13 23:59 | Moomba WL | IWahbi | 2022-10-03 11:44 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.126 | Well #112 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109541 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-02-07 22:00 | 2022-02-08 | 2022-02-08 01:00 | 2022-02-08 | 2022-02-10 23:59 | 2022-02-11 01:00 | 2022-02-10 23:59 | Moomba WL | IWahbi | 2022-10-03 11:44 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.125 | Well #111 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109540 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-02-04 22:00 | 2022-02-05 | 2022-02-05 01:00 | 2022-02-05 | 2022-02-07 23:59 | 2022-02-08 01:00 | 2022-02-07 23:59 | Moomba WL | IWahbi | 2022-10-03 11:44 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.124 | Well #110 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109539 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-02-01 22:00 | 2022-02-02 | 2022-02-02 01:00 | 2022-02-02 | 2022-02-04 23:59 | 2022-02-05 01:00 | 2022-02-04 23:59 | Moomba WL | IWahbi | 2022-10-03 11:44 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.123 | Well #109 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109538 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-01-29 22:00 | 2022-01-30 | 2022-01-30 01:00 | 2022-01-30 | 2022-02-01 23:59 | 2022-02-02 01:00 | 2022-02-01 23:59 | Moomba WL | IWahbi | 2022-10-03 11:44 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.122 | Well #108 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109537 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-01-26 22:00 | 2022-01-27 | 2022-01-27 01:00 | 2022-01-27 | 2022-01-29 23:59 | 2022-01-30 01:00 | 2022-01-29 23:59 | Moomba WL | IWahbi | 2022-10-03 11:44 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.121 | Well #107 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109536 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-01-23 22:00 | 2022-01-24 | 2022-01-24 01:00 | 2022-01-24 | 2022-01-26 23:59 | 2022-01-27 01:00 | 2022-01-26 23:59 | Moomba WL | IWahbi | 2022-10-03 11:44 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.120 | Well #106 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109535 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-01-20 22:00 | 2022-01-21 | 2022-01-21 01:00 | 2022-01-21 | 2022-01-23 23:59 | 2022-01-24 01:00 | 2022-01-23 23:59 | Moomba WL | IWahbi | 2022-10-03 11:44 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.119 | Well #105 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109534 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-01-17 22:00 | 2022-01-18 | 2022-01-18 01:00 | 2022-01-18 | 2022-01-20 23:59 | 2022-01-21 01:00 | 2022-01-20 23:59 | Moomba WL | IWahbi | 2022-10-03 11:44 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.118 | Well #104 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109533 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-01-14 22:00 | 2022-01-15 | 2022-01-15 01:00 | 2022-01-15 | 2022-01-17 23:59 | 2022-01-18 01:00 | 2022-01-17 23:59 | Moomba WL | IWahbi | 2022-10-03 11:44 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.117 | Well #103 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109532 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-01-11 22:00 | 2022-01-12 | 2022-01-12 01:00 | 2022-01-12 | 2022-01-14 23:59 | 2022-01-15 01:00 | 2022-01-14 23:59 | Moomba WL | IWahbi | 2022-10-03 11:44 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.116 | Well #102 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109531 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-01-08 22:00 | 2022-01-09 | 2022-01-09 01:00 | 2022-01-09 | 2022-01-11 23:59 | 2022-01-12 01:00 | 2022-01-11 23:59 | Moomba WL | IWahbi | 2022-10-03 11:43 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.115 | Well #101 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109530 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-01-05 22:00 | 2022-01-06 | 2022-01-06 01:00 | 2022-01-06 | 2022-01-08 23:59 | 2022-01-09 01:00 | 2022-01-08 23:59 | Moomba WL | IWahbi | 2022-10-03 11:43 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.114 | Well #100 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109529 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-01-02 22:00 | 2022-01-03 | 2022-01-03 01:00 | 2022-01-03 | 2022-01-05 23:59 | 2022-01-06 01:00 | 2022-01-05 23:59 | Moomba WL | IWahbi | 2022-10-03 11:43 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.113 | Well #99 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108784 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-12-30 22:00 | 2021-12-31 | 2021-12-31 01:00 | 2021-12-31 | 2022-01-02 23:59 | 2022-01-03 01:00 | 2022-01-02 23:59 | Moomba WL | IWahbi | 2022-10-03 11:43 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.112 | Judga 3 | SANTOS LIMITED | Judga 4 (App A) | Rigless Australia - 1 | J.21.108752 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-30 12:00 | 2021-09-22 | 2021-09-30 02:00 | 2021-09-30 12:00 | 2021-10-02 12:59 | 2021-10-03 02:00 | 2021-10-02 12:59 | Moomba WL | KKeese | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.111 | Barrolka 9 | SANTOS LIMITED | Barrolka 9 | Rigless Australia - 1 | J.21.108751 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-28 12:00 | 2021-09-22 | 2021-09-28 02:00 | 2021-09-28 12:00 | 2021-09-30 12:59 | 2021-10-01 02:00 | 2021-09-30 12:59 | Moomba WL | KKeese | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.110 | Barolka 11 | SANTOS LIMITED | Barrolka 9 | Rigless Australia - 1 | J.21.108749 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-28 12:00 | 2021-09-22 | 2021-09-28 02:00 | 2021-09-28 12:00 | 2021-09-30 12:59 | 2021-10-01 02:00 | 2021-09-30 12:59 | Moomba WL | KKeese | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.109 | Wackett South 1 | SANTOS LIMITED | Wackett South 1 | Rigless Australia - 1 | J.21.108745 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-25 12:00 | 2021-09-19 | 2021-09-25 02:00 | 2021-09-25 12:00 | 2021-09-27 12:59 | 2021-09-28 02:00 | 2021-09-27 12:59 | Moomba WL | KKeese | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.108 | Well #98 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108695 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-12-27 22:00 | 2021-12-28 | 2021-12-28 01:00 | 2021-12-28 | 2021-12-30 23:59 | 2021-12-31 01:00 | 2021-12-30 23:59 | Moomba WL | IWahbi | 2022-10-03 11:30 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.107 | Well #97 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108694 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-12-24 22:00 | 2021-12-25 | 2021-12-25 01:00 | 2021-12-25 | 2021-12-27 23:59 | 2021-12-28 01:00 | 2021-12-27 23:59 | Moomba WL | IWahbi | 2022-10-03 11:30 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.106 | Well #96 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108693 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-12-21 22:00 | 2021-12-22 | 2021-12-22 01:00 | 2021-12-22 | 2021-12-24 23:59 | 2021-12-25 01:00 | 2021-12-24 23:59 | Moomba WL | IWahbi | 2022-10-03 11:30 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.105 | Well #95 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108692 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-12-18 22:00 | 2021-12-19 | 2021-12-19 01:00 | 2021-12-19 | 2021-12-21 23:59 | 2021-12-22 01:00 | 2021-12-21 23:59 | Moomba WL | IWahbi | 2022-10-03 11:30 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.104 | Well #94 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108691 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-12-15 22:00 | 2021-12-16 | 2021-12-16 01:00 | 2021-12-16 | 2021-12-18 23:59 | 2021-12-19 01:00 | 2021-12-18 23:59 | Moomba WL | IWahbi | 2022-10-03 11:29 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.103 | Well #93 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108690 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-12-12 22:00 | 2021-12-13 | 2021-12-13 01:00 | 2021-12-13 | 2021-12-15 23:59 | 2021-12-16 01:00 | 2021-12-15 23:59 | Moomba WL | IWahbi | 2022-10-03 11:29 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.102 | Well #92 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108689 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-12-09 22:00 | 2021-12-10 | 2021-12-10 01:00 | 2021-12-10 | 2021-12-12 23:59 | 2021-12-13 01:00 | 2021-12-12 23:59 | Moomba WL | IWahbi | 2022-10-03 11:29 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.101 | Well #91 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108688 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-12-06 22:00 | 2021-12-07 | 2021-12-07 01:00 | 2021-12-07 | 2021-12-09 23:59 | 2021-12-10 01:00 | 2021-12-09 23:59 | Moomba WL | IWahbi | 2022-10-03 11:29 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.100 | Well #90 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108687 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-12-03 22:00 | 2021-12-04 | 2021-12-04 01:00 | 2021-12-04 | 2021-12-06 23:59 | 2021-12-07 01:00 | 2021-12-06 23:59 | Moomba WL | IWahbi | 2022-10-03 11:29 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.99 | Well #89 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108686 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-11-30 22:00 | 2021-12-01 | 2021-12-01 01:00 | 2021-12-01 | 2021-12-03 23:59 | 2021-12-04 01:00 | 2021-12-03 23:59 | Moomba WL | IWahbi | 2022-10-03 11:29 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.98 | Well #88 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108685 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-11-27 22:00 | 2021-11-28 | 2021-11-28 01:00 | 2021-11-28 | 2021-11-30 23:59 | 2021-12-01 01:00 | 2021-11-30 23:59 | Moomba WL | IWahbi | 2022-10-03 11:29 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.97 | Well #87 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108684 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-11-24 22:00 | 2021-11-25 | 2021-11-25 01:00 | 2021-11-25 | 2021-11-27 23:59 | 2021-11-28 01:00 | 2021-11-27 23:59 | Moomba WL | IWahbi | 2022-10-03 11:29 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.96 | Well #86 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108683 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-11-21 22:00 | 2021-11-22 | 2021-11-22 01:00 | 2021-11-22 | 2021-11-24 23:59 | 2021-11-25 01:00 | 2021-11-24 23:59 | Moomba WL | IWahbi | 2022-10-03 11:29 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.95 | Well #85 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108682 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-11-18 22:00 | 2021-11-19 | 2021-11-19 01:00 | 2021-11-19 | 2021-11-21 23:59 | 2021-11-22 01:00 | 2021-11-21 23:59 | Moomba WL | IWahbi | 2022-10-03 11:29 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.94 | Well #84 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108681 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-11-15 22:00 | 2021-11-16 | 2021-11-16 01:00 | 2021-11-16 | 2021-11-18 23:59 | 2021-11-19 01:00 | 2021-11-18 23:59 | Moomba WL | IWahbi | 2022-10-03 11:29 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.93 | Well #83 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108680 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-11-12 22:00 | 2021-11-13 | 2021-11-13 01:00 | 2021-11-13 | 2021-11-15 23:59 | 2021-11-16 01:00 | 2021-11-15 23:59 | Moomba WL | IWahbi | 2022-10-03 11:29 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.92 | Well #82 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108679 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-11-09 22:00 | 2021-11-10 | 2021-11-10 01:00 | 2021-11-10 | 2021-11-12 23:59 | 2021-11-13 01:00 | 2021-11-12 23:59 | Moomba WL | IWahbi | 2022-10-03 11:28 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.91 | Well #81 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108678 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-11-06 22:00 | 2021-11-07 | 2021-11-07 01:00 | 2021-11-07 | 2021-11-09 23:59 | 2021-11-10 01:00 | 2021-11-09 23:59 | Moomba WL | IWahbi | 2022-10-03 11:28 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.90 | Well #80 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108677 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-11-03 22:00 | 2021-11-04 | 2021-11-04 01:00 | 2021-11-04 | 2021-11-06 23:59 | 2021-11-07 01:00 | 2021-11-06 23:59 | Moomba WL | IWahbi | 2022-10-03 11:28 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.89 | Well #79 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108676 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-10-31 22:00 | 2021-11-01 | 2021-11-01 01:00 | 2021-11-01 | 2021-11-03 23:59 | 2021-11-04 01:00 | 2021-11-03 23:59 | Moomba WL | IWahbi | 2022-10-03 11:28 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.88 | Well #78 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108675 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-10-28 22:00 | 2021-10-29 | 2021-10-29 01:00 | 2021-10-29 | 2021-10-31 23:59 | 2021-11-01 01:00 | 2021-10-31 23:59 | Moomba WL | IWahbi | 2022-10-03 11:28 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.87 | Well #77 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108674 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-10-25 22:00 | 2021-10-26 | 2021-10-26 01:00 | 2021-10-26 | 2021-10-28 23:59 | 2021-10-29 01:00 | 2021-10-28 23:59 | Moomba WL | IWahbi | 2022-10-03 11:28 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.86 | Well #76 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108673 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-10-22 22:00 | 2021-10-23 | 2021-10-23 01:00 | 2021-10-23 | 2021-10-25 23:59 | 2021-10-26 01:00 | 2021-10-25 23:59 | Moomba WL | IWahbi | 2022-10-03 11:28 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.85 | Well #75 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108672 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-10-19 22:00 | 2021-10-20 | 2021-10-20 01:00 | 2021-10-20 | 2021-10-22 23:59 | 2021-10-23 01:00 | 2021-10-22 23:59 | Moomba WL | IWahbi | 2022-10-03 11:28 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.84 | Well #74 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108671 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-10-16 22:00 | 2021-10-17 | 2021-10-17 01:00 | 2021-10-17 | 2021-10-19 23:59 | 2021-10-20 01:00 | 2021-10-19 23:59 | Moomba WL | IWahbi | 2022-10-03 11:28 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.83 | Well #73 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108670 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-10-13 22:00 | 2021-10-14 | 2021-10-14 01:00 | 2021-10-14 | 2021-10-16 23:59 | 2021-10-17 01:00 | 2021-10-16 23:59 | Moomba WL | IWahbi | 2022-10-03 11:28 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.82 | Well #72 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108669 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-10-10 22:00 | 2021-10-11 | 2021-10-11 01:00 | 2021-10-11 | 2021-10-13 23:59 | 2021-10-14 01:00 | 2021-10-13 23:59 | Moomba WL | IWahbi | 2022-10-03 11:27 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.81 | Well #71 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108668 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-10-07 22:00 | 2021-10-08 | 2021-10-08 01:00 | 2021-10-08 | 2021-10-10 23:59 | 2021-10-11 01:00 | 2021-10-10 23:59 | Moomba WL | IWahbi | 2022-10-03 11:27 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.80 | Well #70 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108667 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-10-04 22:00 | 2021-10-05 | 2021-10-05 01:00 | 2021-10-05 | 2021-10-07 23:59 | 2021-10-08 01:00 | 2021-10-07 23:59 | Moomba WL | IWahbi | 2022-10-03 11:27 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.79 | Well #69 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108666 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-09-30 23:00 | 2021-10-01 | 2021-10-01 | 2021-10-01 | 2021-10-04 00:59 | 2021-10-04 01:00 | 2021-10-04 00:59 | Moomba WL | IWahbi | 2022-10-03 11:27 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.78 | Houby 1 | SANTOS LIMITED | Houby 1 | Rigless Australia - 1 | J.21.108655 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-06 | 2021-08-06 | 2021-08-06 | 2021-08-06 | 2021-08-08 23:59 | 2021-08-09 | 2021-08-14 | Moomba WL | KKeese | 2022-10-03 11:26 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.77 | Well #68 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108591 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-09-27 23:00 | 2021-09-28 | 2021-09-28 | 2021-09-28 | 2021-09-30 23:59 | 2021-10-01 | 2021-10-01 00:59 | Moomba WL | IWahbi | 2022-10-03 11:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.76 | Well #67 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108590 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-09-24 23:00 | 2021-09-25 | 2021-09-25 | 2021-09-25 | 2021-09-27 23:59 | 2021-09-28 | 2021-09-28 00:59 | Moomba WL | IWahbi | 2022-10-03 11:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.75 | Well #66 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108589 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-09-21 23:00 | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2021-09-24 23:59 | 2021-09-25 | 2021-09-25 00:59 | Moomba WL | IWahbi | 2022-10-03 11:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.74 | Well #65 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108588 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-09-18 23:00 | 2021-09-19 | 2021-09-19 | 2021-09-19 | 2021-09-21 23:59 | 2021-09-22 | 2021-09-22 00:59 | Moomba WL | IWahbi | 2022-10-03 11:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.73 | Well #64 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108587 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-09-15 23:00 | 2021-09-16 | 2021-09-16 | 2021-09-16 | 2021-09-18 23:59 | 2021-09-19 | 2021-09-19 00:59 | Moomba WL | IWahbi | 2022-10-03 11:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.72 | Well #63 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108586 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-09-12 23:00 | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-15 23:59 | 2021-09-16 | 2021-09-16 00:59 | Moomba WL | IWahbi | 2022-10-03 11:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.71 | Well #62 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108585 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-09-09 23:00 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-12 23:59 | 2021-09-13 | 2021-09-13 00:59 | Moomba WL | IWahbi | 2022-10-03 11:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.70 | Well #61 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108584 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-09-06 23:00 | 2021-09-07 | 2021-09-07 | 2021-09-07 | 2021-09-09 23:59 | 2021-09-10 | 2021-09-10 00:59 | Moomba WL | IWahbi | 2022-10-03 11:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.69 | Well #60 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108583 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-09-03 23:00 | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-09-06 23:59 | 2021-09-07 | 2021-09-07 00:59 | Moomba WL | IWahbi | 2022-10-03 11:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.68 | Well #59 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108582 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-08-31 23:00 | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-03 23:59 | 2021-09-04 | 2021-09-04 00:59 | Moomba WL | IWahbi | 2022-10-03 11:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.67 | Well #58 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108581 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-08-28 23:00 | 2021-08-29 | 2021-08-29 | 2021-08-29 | 2021-08-31 23:59 | 2021-09-01 | 2021-09-01 00:59 | Moomba WL | IWahbi | 2022-10-03 11:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.66 | Well #57 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108580 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-08-25 23:00 | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-08-28 23:59 | 2021-08-29 | 2021-08-29 00:59 | Moomba WL | IWahbi | 2022-10-03 11:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.65 | Well #56 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108579 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-08-22 23:00 | 2021-08-23 | 2021-08-23 | 2021-08-23 | 2021-08-25 23:59 | 2021-08-26 | 2021-08-26 00:59 | Moomba WL | IWahbi | 2022-10-03 11:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.64 | Well #55 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108578 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-08-19 23:00 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-22 23:59 | 2021-08-23 | 2021-08-23 00:59 | Moomba WL | IWahbi | 2022-10-03 11:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.63 | Well #54 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108577 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-08-16 23:00 | 2021-08-17 | 2021-08-17 | 2021-08-17 | 2021-08-19 23:59 | 2021-08-20 | 2021-08-20 00:59 | Moomba WL | IWahbi | 2022-10-03 11:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.62 | SWQ campaign, Dilchee 5, Pira 4, Tirra 61, Meranji 7 | SANTOS LIMITED | Tirrawarra 61, Dilchee 5, Pira 4, Big Lake 154, Swan Lake 5, Meranji 1, Big Lake 119 | Rigless Australia - 1 | J.21.108576 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-08-13 23:00 | 2021-08-14 | 2021-08-14 | 2021-08-14 | 2021-08-16 23:59 | 2021-08-17 | 2021-08-16 22:59 | Moomba WL | IWahbi | 2022-10-03 11:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.61 | Well #52 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108575 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-08-10 23:00 | 2021-08-11 | 2021-08-11 | 2021-08-11 | 2021-08-13 23:59 | 2021-08-14 | 2021-08-14 00:59 | Moomba WL | IWahbi | 2022-10-03 11:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.60 | Well #51 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108574 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-08-07 23:00 | 2021-08-08 | 2021-08-08 | 2021-08-08 | 2021-08-10 23:59 | 2021-08-11 | 2021-08-11 00:59 | Moomba WL | IWahbi | 2022-10-03 11:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.59 | Well #50 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108573 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-08-04 23:00 | 2021-08-05 | 2021-08-05 | 2021-08-05 | 2021-08-07 23:59 | 2021-08-08 | 2021-08-08 00:59 | Moomba WL | IWahbi | 2022-10-03 11:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.58 | Well #49 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108572 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-08-01 23:00 | 2021-08-02 | 2021-08-02 | 2021-08-02 | 2021-08-04 23:59 | 2021-08-05 | 2021-08-05 00:59 | Moomba WL | IWahbi | 2022-10-03 11:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.57 | Well #48 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108571 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-07-29 23:00 | 2021-07-30 | 2021-07-30 | 2021-07-30 | 2021-08-01 23:59 | 2021-08-02 | 2021-08-02 00:59 | Moomba WL | IWahbi | 2022-10-03 11:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.56 | Well #47 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108570 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-07-26 23:00 | 2021-07-27 | 2021-07-27 | 2021-07-27 | 2021-07-29 23:59 | 2021-07-30 | 2021-07-30 00:59 | Moomba WL | IWahbi | 2022-10-03 11:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.55 | Well #46 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108569 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-07-23 23:00 | 2021-07-24 | 2021-07-24 | 2021-07-24 | 2021-07-26 23:59 | 2021-07-27 | 2021-07-27 00:59 | Moomba WL | IWahbi | 2022-10-03 11:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.54 | Well #45 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108568 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-07-20 23:00 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-23 23:59 | 2021-07-24 | 2021-07-24 00:59 | Moomba WL | IWahbi | 2022-10-03 11:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.53 | Well #44 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108567 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-07-17 23:00 | 2021-07-18 | 2021-07-18 | 2021-07-18 | 2021-07-20 23:59 | 2021-07-21 | 2021-07-21 00:59 | Moomba WL | IWahbi | 2022-10-03 11:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.52 | Well #43 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108566 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-07-14 23:00 | 2021-07-15 | 2021-07-15 | 2021-07-15 | 2021-07-17 23:59 | 2021-07-18 | 2021-07-18 00:59 | Moomba WL | IWahbi | 2022-10-03 11:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.51 | Well #42 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108565 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-07-11 23:00 | 2021-07-12 | 2021-07-12 | 2021-07-12 | 2021-07-14 23:59 | 2021-07-15 | 2021-07-15 00:59 | Moomba WL | IWahbi | 2022-10-03 11:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.50 | SWPT 418 SWQ campaign | SANTOS LIMITED | Koree South 1, Anna North 3, Bearcat 1(NFE A), Cocinero 12, Okotoko North 2 | Rigless Australia - 1 | J.21.108564 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-08 23:00 | 2021-07-09 | 2021-07-09 | 2021-07-09 | 2021-07-11 23:59 | 2021-07-12 | 2021-07-11 22:59 | Moomba WL | IWahbi | 2022-10-03 11:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.49 | Well #40 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108563 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-07-05 23:00 | 2021-07-06 | 2021-07-06 | 2021-07-06 | 2021-07-08 23:59 | 2021-07-09 | 2021-07-09 00:59 | Moomba WL | IWahbi | 2022-10-03 11:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.48 | Okotoko North 2 | SANTOS LIMITED | Okotoko North 2 | Rigless Australia - 1 | J.21.108562 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-03 | 2021-08-02 | 2021-08-03 | 2021-08-03 | 2021-08-05 23:59 | 2021-08-06 | 2021-08-05 23:59 | Moomba WL | IWahbi | 2022-10-03 11:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.47 | Moomba 259 | SANTOS LIMITED | Moomba 259 | Rigless Australia - 1 | J.21.108537 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-21 | 2021-04-20 | 2021-04-21 | 2021-04-21 | 2021-04-23 22:59 | 2021-04-23 23:00 | 2021-04-23 22:59 | Moomba WL | KKeese | 2022-10-03 11:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.46 | Moomba 260 | SANTOS LIMITED | Moomba 260 | Rigless Australia - 1 | J.21.108536 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-19 | 2021-04-18 | 2021-04-19 | 2021-04-19 | 2021-04-21 22:59 | 2021-04-21 23:00 | 2021-04-21 22:59 | Moomba WL | KKeese | 2022-10-03 11:14 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.45 | Moomba 261 | SANTOS LIMITED | Moomba 261 | Rigless Australia - 1 | J.21.108535 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-17 | 2021-04-16 | 2021-04-17 | 2021-04-17 | 2021-04-19 22:59 | 2021-04-19 23:00 | 2021-04-19 22:59 | Moomba WL | KKeese | 2022-10-03 11:14 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.44 | Moomba 22 | SANTOS LIMITED | Moomba 22 | Rigless Australia - 1 | J.21.108534 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-16 | 2021-04-15 | 2021-04-14 | 2021-04-16 | 2021-04-18 22:59 | 2021-04-16 23:00 | 2021-04-18 22:59 | Moomba WL | KKeese | 2022-10-03 11:14 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.43 | Moomba 264 | SANTOS LIMITED | MOOMBA 264 | Rigless Australia - 1 | J.21.108533 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-14 | 2021-04-08 | 2021-04-14 | 2021-04-14 | 2021-04-16 22:59 | 2021-04-16 23:00 | 2021-04-16 22:59 | Moomba WL | KKeese | 2022-10-03 11:14 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.42 | Winninia North 3 | SANTOS LIMITED | Winninia North 2 | Rigless Australia - 1 | J.21.108532 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-04-12 | 2021-04-12 | 2021-04-12 | 2021-04-12 | 2021-04-14 23:59 | 2021-04-15 | 2021-04-14 23:59 | Moomba WL | KKeese | 2022-10-03 11:14 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.41 | Psyche 3 | SANTOS LIMITED | Psyche 3 | Rigless Australia - 1 | J.21.108531 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-10 | 2021-04-08 | 2021-04-10 | 2021-04-10 | 2021-04-12 22:59 | 2021-04-12 23:00 | 2021-04-12 22:59 | Moomba WL | KKeese | 2022-10-03 11:14 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.40 | Munkah 10 | SANTOS LIMITED | MUNKAH 10 | Rigless Australia - 1 | J.21.108530 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-07 | 2021-04-05 | 2021-04-07 | 2021-04-07 | 2021-04-09 22:59 | 2021-04-09 23:00 | 2021-04-09 22:59 | Moomba WL | KKeese | 2022-10-03 11:14 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.39 | Dullingari 63 | SANTOS LIMITED | Dullingari 63 | Rigless Australia - 1 | J.21.108527 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-04-04 | 2021-04-02 | 2021-04-04 | 2021-04-04 | 2021-04-06 22:59 | 2021-04-06 23:00 | 2021-04-06 22:59 | Moomba WL | KKeese | 2022-10-03 11:13 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.38 | Well #38 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108469 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-06-29 23:00 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 2021-07-02 23:59 | 2021-07-03 | 2021-07-03 00:59 | Moomba WL | IWahbi | 2022-10-03 11:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.37 | Well #37 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108468 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-06-26 23:00 | 2021-06-27 | 2021-06-27 | 2021-06-27 | 2021-06-29 23:59 | 2021-06-30 | 2021-06-30 00:59 | Moomba WL | IWahbi | 2022-10-03 11:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.36 | Well #36 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108467 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-06-23 23:00 | 2021-06-24 | 2021-06-24 | 2021-06-24 | 2021-06-26 23:59 | 2021-06-27 | 2021-06-27 00:59 | Moomba WL | IWahbi | 2022-10-03 11:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.35 | Well #35 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108466 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-06-20 23:00 | 2021-06-21 | 2021-06-21 | 2021-06-21 | 2021-06-23 23:59 | 2021-06-24 | 2021-06-24 00:59 | Moomba WL | IWahbi | 2022-10-03 11:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.34 | Well #34 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108465 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-06-17 23:00 | 2021-06-18 | 2021-06-18 | 2021-06-18 | 2021-06-20 23:59 | 2021-06-21 | 2021-06-21 00:59 | Moomba WL | IWahbi | 2022-10-03 11:07 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.33 | Well #33 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108464 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-06-14 23:00 | 2021-06-15 | 2021-06-15 | 2021-06-15 | 2021-06-17 23:59 | 2021-06-18 | 2021-06-18 00:59 | Moomba WL | IWahbi | 2022-10-03 11:07 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.32 | Well #32 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108463 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-06-11 23:00 | 2021-06-12 | 2021-06-12 | 2021-06-12 | 2021-06-14 23:59 | 2021-06-15 | 2021-06-15 00:59 | Moomba WL | IWahbi | 2022-10-03 11:07 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.31 | Well #31 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108462 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-06-08 23:00 | 2021-06-09 | 2021-06-09 | 2021-06-09 | 2021-06-11 23:59 | 2021-06-12 | 2021-06-12 00:59 | Moomba WL | IWahbi | 2022-10-03 11:07 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.30 | Well #30 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108461 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-06-05 23:00 | 2021-06-06 | 2021-06-06 | 2021-06-06 | 2021-06-08 23:59 | 2021-06-09 | 2021-06-09 00:59 | Moomba WL | IWahbi | 2022-10-03 11:07 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.29 | Well #29 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108460 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-06-02 23:00 | 2021-06-03 | 2021-06-03 | 2021-06-03 | 2021-06-05 23:59 | 2021-06-06 | 2021-06-06 00:59 | Moomba WL | IWahbi | 2022-10-03 11:07 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.28 | Well #28 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108459 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-05-30 23:00 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-06-02 23:59 | 2021-06-03 | 2021-06-03 00:59 | Moomba WL | IWahbi | 2022-10-03 11:07 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.27 | Well #27 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108458 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-05-27 23:00 | 2021-05-28 | 2021-05-28 | 2021-05-28 | 2021-05-30 23:59 | 2021-05-31 | 2021-05-31 00:59 | Moomba WL | IWahbi | 2022-10-03 11:07 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.26 | Houby 1 -; Cement Evaluation Log | SANTOS LIMITED | Houby 1 | Rigless Australia - 1 | J.21.108457 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-05-24 23:00 | 2021-05-25 | 2021-05-25 | 2021-05-25 | 2021-05-27 23:59 | 2021-05-28 | 2021-05-27 22:59 | Moomba WL | IWahbi | 2022-10-03 11:07 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.25 | SA Campaign: Moomba 264 - ; Post Frac Perforations / Packer Set | SANTOS LIMITED | Houby 1, MOOMBA 257, Amyema 2, Moonanga 2 | Rigless Australia - 1 | J.21.108456 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-05-21 23:00 | 2021-05-22 | 2021-05-22 | 2021-05-22 | 2021-05-24 23:59 | 2021-05-25 | 2021-05-24 22:59 | Moomba WL | IWahbi | 2022-10-03 11:07 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.24 | Well #24 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108455 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-05-18 23:00 | 2021-05-19 | 2021-05-19 | 2021-05-19 | 2021-05-21 23:59 | 2021-05-22 | 2021-05-22 00:59 | Moomba WL | IWahbi | 2022-10-03 11:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.23 | Well #23 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108454 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-05-15 23:00 | 2021-05-16 | 2021-05-16 | 2021-05-16 | 2021-05-18 23:59 | 2021-05-19 | 2021-05-19 00:59 | Moomba WL | IWahbi | 2022-10-03 11:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.22 | Well #22 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108453 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-05-12 23:00 | 2021-05-13 | 2021-05-13 | 2021-05-13 | 2021-05-15 23:59 | 2021-05-16 | 2021-05-16 00:59 | Moomba WL | IWahbi | 2022-10-03 11:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.21 | Well #21 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108452 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-05-09 23:00 | 2021-05-10 | 2021-05-10 | 2021-05-10 | 2021-05-12 23:59 | 2021-05-13 | 2021-05-13 00:59 | Moomba WL | IWahbi | 2022-10-03 11:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.20 | Well #20 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108451 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-05-06 23:00 | 2021-05-07 | 2021-05-07 | 2021-05-07 | 2021-05-09 23:59 | 2021-05-10 | 2021-05-10 00:59 | Moomba WL | IWahbi | 2022-10-03 11:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.19 | Well #19 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108450 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-05-03 23:00 | 2021-05-04 | 2021-05-04 | 2021-05-04 | 2021-05-06 23:59 | 2021-05-07 | 2021-05-07 00:59 | Moomba WL | IWahbi | 2022-10-03 11:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.18 | Well #18 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108449 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-04-30 23:00 | 2021-05-01 | 2021-05-01 | 2021-05-01 | 2021-05-03 23:59 | 2021-05-04 | 2021-05-04 00:59 | Moomba WL | IWahbi | 2022-10-03 11:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.17 | Well #17 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108448 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-04-27 23:00 | 2021-04-28 | 2021-04-28 | 2021-04-28 | 2021-04-30 23:59 | 2021-05-01 | 2021-05-01 00:59 | Moomba WL | IWahbi | 2022-10-03 11:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.16 | Well #16 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108447 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-04-24 23:00 | 2021-04-25 | 2021-04-25 | 2021-04-25 | 2021-04-27 23:59 | 2021-04-28 | 2021-04-28 00:59 | Moomba WL | IWahbi | 2022-10-03 11:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.15 | Well #15 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108446 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-04-21 23:00 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-24 23:59 | 2021-04-25 | 2021-04-25 00:59 | Moomba WL | IWahbi | 2022-10-03 11:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.14 | Tirrawarra 61 | SANTOS LIMITED | Tirrawarra 61 | Rigless Australia - 1 | J.21.108445 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-17 12:00 | 2021-09-11 | 2021-09-17 02:00 | 2021-09-17 12:00 | 2021-09-19 12:59 | 2021-09-20 02:00 | 2021-09-19 12:59 | Moomba WL | IWahbi | 2022-10-03 11:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.13 | Seccante 5 CBL-VDL log | SANTOS LIMITED | Seccante 5 | Rigless Australia - 1 | J.21.108444 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-06-24 09:00 | 2021-06-24 08:00 | 2021-06-25 10:00 | 2021-06-24 10:00 | 2021-06-26 10:00 | 2021-06-28 10:00 | 2021-06-27 08:59 | Moomba WL | IWahbi | 2022-10-03 11:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 16755.52 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.12 | Cooroo 7- Post Frac Perfs | SANTOS LIMITED | Cooroo 7 (APP A) | Rigless Australia - 1 | J.21.108443 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-16 10:00 | 2021-05-16 07:30 | 2021-05-16 10:00 | 2021-05-16 10:00 | 2021-05-19 09:59 | 2021-05-19 10:00 | 2021-05-19 09:59 | Moomba WL | IWahbi | 2022-10-03 11:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 8265.11 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.11 | Anna North 2- Post Frac Perf | SANTOS LIMITED | Anna North 2 | Rigless Australia - 1 | J.21.108442 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-14 10:00 | 2021-05-14 06:00 | 2021-05-14 10:00 | 2021-05-14 10:00 | 2021-05-17 09:59 | 2021-05-17 10:00 | 2021-05-17 09:59 | Moomba WL | IWahbi | 2022-10-03 11:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.10 | Tarwonga 6- Packer Setting | SANTOS LIMITED | Tarwonga 6 | Rigless Australia - 1 | J.21.108441 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-10 12:00 | 2021-05-10 10:00 | 2021-05-10 12:00 | 2021-05-10 12:00 | 2021-05-13 11:59 | 2021-05-13 13:00 | 2021-05-13 11:59 | Moomba WL | IWahbi | 2022-10-03 11:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 5730.99 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.09 | Juno 8 | SANTOS LIMITED | Juno 8 | Rigless Australia - 1 | J.21.108440 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-03 16:00 | 2021-05-03 14:00 | 2021-05-03 16:00 | 2021-05-03 16:00 | 2021-05-06 14:59 | 2021-05-06 16:00 | 2021-05-06 15:59 | Moomba WL | IWahbi | 2022-10-03 11:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.08 | Tarwonga 6- Post Frac Perf | SANTOS LIMITED | Tarwonga 6 | Rigless Australia - 1 | J.21.108439 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-06 10:00 | 2021-05-06 06:00 | 2021-05-05 23:00 | 2021-05-06 10:00 | 2021-05-09 09:59 | 2021-05-08 23:00 | 2021-05-09 09:59 | Moomba WL | IWahbi | 2022-10-03 11:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 11647.56 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.07 | Ruby 3- Perforation | SANTOS LIMITED | RUBY 3 | Rigless Australia - 1 | J.21.108438 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-01 10:00 | 2021-05-01 08:00 | 2021-05-01 10:00 | 2021-05-01 10:00 | 2021-05-04 09:59 | 2021-05-04 10:00 | 2021-05-04 09:59 | Moomba WL | IWahbi | 2022-10-03 11:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Owen Bass | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.06 | Windigo 3- Perf | SANTOS LIMITED | WINDIGO 3 | Rigless Australia - 1 | J.21.108437 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-28 06:00 | 2021-04-27 14:00 | 2021-04-28 06:00 | 2021-04-28 06:00 | 2021-05-01 05:59 | 2021-05-01 06:00 | 2021-05-01 05:59 | Moomba WL | IWahbi | 2022-10-03 11:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 15628.33 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.05 | Cooroo 7- Perf | SANTOS LIMITED | Cooroo 7 (APP A) | Rigless Australia - 1 | J.21.108436 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-27 06:00 | 2021-04-26 12:00 | 2021-04-27 06:00 | 2021-04-27 06:00 | 2021-04-30 05:59 | 2021-04-30 06:00 | 2021-04-30 05:59 | Moomba WL | IWahbi | 2022-10-03 11:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Owen Bass | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.04 | Dullingari North 25 | SANTOS LIMITED | Dullingari North 25 | Rigless Australia - 1 | J.21.108435 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-03-31 | 2021-03-30 | 2021-03-31 | 2021-03-31 | 2021-04-02 23:59 | 2021-04-03 | 2021-04-02 23:59 | Moomba WL | IWahbi | 2022-10-03 11:04 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.03 | Mulberry 37- CBL & PERF | SANTOS LIMITED | Mulberry 37 (App D) | Rigless Australia - 1 | J.21.108434 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-04-22 12:30 | 2021-04-22 10:00 | 2021-04-22 12:30 | 2021-04-22 12:30 | 2021-04-25 12:29 | 2021-04-25 12:30 | 2021-04-25 12:29 | Moomba WL | IWahbi | 2022-10-03 11:04 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 16755.52 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.02 | Brompton 1; Set CIBP & Dump Bail Cement ; | SANTOS LIMITED | Brompton 1 | Rigless Australia - 1 | J.21.108433 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-03-17 06:00 | 2021-03-17 06:00 | 2021-03-17 | 2021-03-17 06:00 | 2021-03-20 05:59 | 2021-03-20 | 2021-03-20 05:59 | Moomba WL | IWahbi | 2022-10-03 11:04 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001570 | O.1001570.05 | A.1001570.05.01 | Psyche 2 -Puncher, cutter | SANTOS LIMITED | Psyche 2 | Rigless Australia - 1 | J.21.108432 | RPI | PS-WL-Ops | Medium | Operationally Complete | Execute - PSD |  | Design Completed | In Progress | In Progress | 2021-03-15 12:00 | 2021-03-09 12:00 | 2021-03-15 | 2021-03-15 12:00 | 2021-03-18 11:59 | 2021-03-18 | 2021-03-18 11:59 | Moomba WL | IWahbi | 2022-10-03 11:04 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.37 | Big Lake 119 | SANTOS LIMITED | Big Lake 119 | Rigless Australia - 1 | J.22.109624 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-01-21 | 2022-01-20 |  | 2022-01-21 | 2022-01-22 23:59 |  | 2022-01-22 23:59 | Moomba WL | ADuong4 | 2022-10-03 11:54 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.36 | Roti 2 | SANTOS LIMITED | Roti 2, Big Lake 11 | Rigless Australia - 1 | J.21.108806 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-16 | 2021-12-15 |  | 2021-12-16 | 2021-12-18 23:59 |  | 2021-12-18 23:59 | Moomba WL | ADuong4 | 2022-10-03 11:52 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 6 |  |  |  | 91.7 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.35 | Roti 3 | SANTOS LIMITED | Roti 3 | Rigless Australia - 1 | J.21.108803 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-13 09:00 | 2021-12-12 17:00 |  | 2021-12-13 09:00 | 2021-12-14 23:59 |  | 2021-12-14 23:59 | Moomba WL | ADuong4 | 2022-10-03 11:52 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 14113.06 | 3 |  |  |  | 91.7 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.34 | Genoa 3 | SANTOS LIMITED | Genoa 3 | Rigless Australia - 1 | J.21.108802 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-12 10:00 | 2021-12-11 |  | 2021-12-12 10:00 | 2021-12-13 23:59 |  | 2021-12-13 23:59 | Moomba WL | ADuong4 | 2022-10-03 11:52 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 91.7 | 50 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.33 | Karmona 4 | SANTOS LIMITED | Karmona 4 | Rigless Australia - 1 | J.21.108799 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-10 | 2021-12-09 |  | 2021-12-10 | 2021-12-12 23:59 |  | 2021-12-12 23:59 | Moomba WL | ADuong4 | 2022-10-03 11:52 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 24119.56 | 16 |  |  |  | 91.7 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.32 | Toolachee 55 - Perforate ; Perforate [0.6m x 1-11/16" & 12.6m x 2"] | SANTOS LIMITED | Toolachee 55 | Rigless Australia - 1 | J.21.108428 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-03-08 | 2021-03-06 | 2021-03-07 | 2021-03-07 | 2021-03-09 | 2021-03-10 | 2021-03-09 23:00 | Moomba WL | ymoradi2 | 2022-10-03 11:04 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7428.72 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.25 | Napowie 9_Links | SANTOS LIMITED | NAPOWIE 009 | Rigless Australia - 1 | J.21.108391 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-01-26 15:00 | 2021-01-25 13:30 |  | 2021-01-26 15:00 | 2021-01-28 |  | 2021-01-28 | Moomba WL | DKitney | 2022-10-03 10:37 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 11360.1 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.20 | Coopers Creek 9 | SANTOS LIMITED | Coopers Creek 9 | Rigless Australia - 1 | J.21.108390 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-05 | 2021-01-04 |  | 2021-01-07 06:00 | 2021-01-09 06:00 |  | 2021-01-07 | Moomba WL | KKeese | 2022-10-03 10:36 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.10 | Moomba 215 ; Reperforate [35' x 2-1/8"] | SANTOS LIMITED | MOOMBA 215 | Rigless Australia - 1 | J.20.062757 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-12-11 | 2020-12-10 |  | 2020-12-11 | 2020-12-13 |  | 2020-12-13 | Moomba WL | OBass | 2022-10-03 10:35 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7428.72 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.07 | Moorari 20 ; Post Frac Perforations / Packer Set | SANTOS LIMITED | Moorari 20 | Rigless Australia - 1 | J.20.062756 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-11-14 | 2020-11-14 |  | 2020-11-14 | 2020-11-16 |  | 2020-11-16 | Moomba WL | OBass | 2022-10-03 10:35 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7428.72 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.17 | Coopers Creek 7 | SANTOS LIMITED | Coopers Creek 7 | Rigless Australia - 1 | J.21.108389 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-31 | 2020-12-28 |  | 2021-01-02 06:00 | 2021-01-04 06:00 |  | 2021-01-02 | Moomba WL | KKeese | 2022-10-03 10:34 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 7428.72 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.16 | Cooper Creek 6 | SANTOS LIMITED | Coopers Creek 6 | Rigless Australia - 1 | J.20.062748 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-29 | 2020-12-28 |  | 2020-12-31 06:00 | 2021-01-02 06:00 |  | 2020-12-31 | Moomba WL | KKeese | 2022-10-03 10:34 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 7428.72 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.11 | Bindah 4-PFP's Set Packer | SANTOS LIMITED | Bindah 4 | Rigless Australia - 1 | J.20.062747 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-12-20 06:00 | 2020-12-08 |  | 2020-12-20 06:00 | 2020-12-22 06:00 |  | 2020-12-22 06:00 | Moomba WL | OBass | 2022-10-03 10:34 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7428.72 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.22 | Moomba 40 | SANTOS LIMITED | Moomba 40 | Rigless Australia - 1 | J.21.108387 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-18 | 2021-01-17 |  | 2021-01-18 | 2021-01-20 23:59 |  | 2021-01-20 23:59 | Moomba WL | KKeese | 2022-10-03 10:33 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.05 | Beckler 6-Perfo | SANTOS LIMITED | Beckler 6 | Rigless Australia - 1 | J.21.108386 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-02-10 | 2021-02-08 |  | 2021-02-10 | 2021-02-12 |  | 2021-03-03 | Moomba WL | OBass | 2022-10-03 10:33 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7428.72 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.31 | Mettika 5- Perforation | SANTOS LIMITED | Mettika 5 | Rigless Australia - 1 | J.21.108384 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-27 | 2021-02-23 12:00 |  | 2021-02-25 12:00 | 2021-02-27 12:00 |  | 2021-02-28 23:00 | Moomba WL | DKitney | 2022-10-03 10:31 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 17154.78 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.29 | Brumby 14- Perforations | SANTOS LIMITED | Brumby 14 | Rigless Australia - 1 | J.21.108383 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-24 | 2021-02-21 12:00 |  | 2021-02-22 12:00 | 2021-02-24 12:00 |  | 2021-02-25 23:00 | Moomba WL | DKitney | 2022-10-03 10:31 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6406.76 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.23 | Bagundi 7- CIS | SANTOS LIMITED | Bagundi 7 | Rigless Australia - 1 | J.21.108382 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-23 12:00 | 2021-01-21 06:00 |  | 2021-01-23 12:00 | 2021-01-26 11:59 |  | 2021-01-26 11:59 | Moomba WL | DKitney | 2022-10-03 10:31 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 14830.54 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.15 | Ficus 3 | SANTOS LIMITED | Ficus 3 | Rigless Australia - 1 | J.20.062724 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-29 | 2020-12-28 |  | 2020-12-29 | 2020-12-31 |  | 2020-12-31 | Moomba WL | KKeese | 2022-10-03 10:31 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 7428.72 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.08 | Moorari5 ; Post Frac Perforations | SANTOS LIMITED | Moorari 5 | Rigless Australia - 1 | J.20.062689 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-11-20 | 2020-11-20 |  | 2020-11-20 | 2020-11-22 |  | 2020-11-22 | Moomba WL | OBass | 2022-10-03 10:27 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7428.72 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.04 | Gidgealpa 15 - Reperforate ; Perforate 10ft 2-1/8" expandable Enerjet ; | SANTOS LIMITED | Gidgealpa 15 | Rigless Australia - 1 | J.20.062676 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-12-23 | 2020-10-27 |  | 2020-12-23 | 2020-12-25 |  | 2020-12-25 | Moomba WL | OBass | 2022-10-03 10:26 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7428.72 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.02 | Moolion North 2 - Drift / Perforate ; Perforate | SANTOS LIMITED | Moolion North 2 | Rigless Australia - 1 | J.20.062675 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-11-13 | 2020-11-12 |  | 2020-11-13 | 2020-11-15 |  | 2020-11-15 | Moomba WL | OBass | 2022-10-03 10:26 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7428.72 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.01 | Merchant 1 | SANTOS LIMITED | Merchant 1 | Rigless Australia - 1 | J.21.108380 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-02-19 06:00 | 2021-02-11 |  | 2021-02-11 07:00 | 2021-03-03 07:00 |  | 2021-02-23 06:00 | Moomba WL | OBass | 2022-10-03 10:26 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7428.72 |  |  |  |  | 66.7 | 50 | 0 | 50 | 50 |  | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.03 | Ficus 2 | SANTOS LIMITED | Ficus 2 | Rigless Australia - 1 | J.20.062667 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-27 06:00 | 2020-12-24 |  | 2020-12-27 06:00 | 2020-12-29 06:00 |  | 2020-12-29 06:00 | Moomba WL | OBass | 2022-10-03 10:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7428.72 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.27 | Toolachee 55 | SANTOS LIMITED | Toolachee 55 | Rigless Australia - 1 | J.21.108379 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-02-11 | 2021-02-09 |  | 2021-02-10 | 2021-02-12 |  | 2021-02-12 23:00 | Moomba WL | ymoradi2 | 2022-10-03 10:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7428.72 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.14 | Well TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062655 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-12-27 | 2020-12-27 |  | 2020-12-27 | 2020-12-29 |  | 2020-12-29 | Moomba WL | OBass | 2022-10-03 10:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.19 | Coopers Creek 8. | SANTOS LIMITED | Coopers Creek 8 | Rigless Australia - 1 | J.21.108376 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-03 | 2021-01-04 |  | 2021-01-05 06:00 | 2021-01-07 06:00 |  | 2021-01-05 | Moomba WL | KKeese | 2022-10-03 10:22 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.18 | Coopers Creek 8 | SANTOS LIMITED | Coopers Creek 7 | Rigless Australia - 1 | J.21.108375 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-03 | 2021-01-04 |  | 2021-01-05 06:00 | 2021-01-07 06:00 |  | 2021-01-05 | Moomba WL | KKeese | 2022-10-03 10:22 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.13 | Well TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062642 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-12-21 | 2020-12-21 |  | 2020-12-21 | 2020-12-23 |  | 2020-12-23 | Moomba WL | OBass | 2022-10-03 10:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.24 | Moon 5- Perforating | SANTOS LIMITED | Moon 5 | Rigless Australia - 1 | J.21.108374 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-22 08:00 | 2021-01-21 13:30 |  | 2021-01-22 08:00 | 2021-01-23 17:00 |  | 2021-01-23 17:00 | Moomba WL | DKitney | 2022-10-03 10:21 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 18262.13 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.12 | Napowie 10_perfo_packer | SANTOS LIMITED | NAPOWIE 10 | Rigless Australia - 1 | J.21.108373 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-02-08 12:00 | 2021-02-04 |  | 2021-02-08 12:00 | 2021-02-10 12:00 |  | 2021-03-03 11:00 | Moomba WL | OBass | 2022-10-03 10:21 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7428.72 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.26 | TBA | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108372 | RPI | PS-WL-Ops | Medium | Confirmed | Prepare - Mob |  | Design Completed | In Progress | In Progress | 2021-01-31 | 2021-01-30 |  | 2021-01-31 | 2021-02-01 23:59 |  | 2021-02-01 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.06 | Moorari 19 - (DEV) ; Packer Set | SANTOS LIMITED | Moorari 19 | Rigless Australia - 1 | J.20.062623 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-11-08 | 2020-11-08 |  | 2020-11-08 | 2020-11-10 |  | 2020-11-10 | Moomba WL | OBass | 2022-10-03 10:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7428.72 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.09 | Big Lake 146 -Drift & Perforate [53ft x 1- 11/16"] | SANTOS LIMITED | Big Lake 146 | Rigless Australia - 1 |  | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-11-06 |  | 2020-11-07 | 2020-11-09 |  |  | Moomba WL | OBass | 2022-09-03 07:59 | walfaro |  | No |  |  |  |  | Rob Twigg |  | 7428.72 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.30 | Test | SANTOS LIMITED | Lane (NFE A) | Rigless Australia - 1 |  | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2021-02-19 06:00 |  | 2021-02-20 06:00 | 2021-02-22 06:00 |  |  | Moomba WL | ymoradi2 | 2021-03-14 11:40 | IWahbi |  | No |  |  |  |  | Rob Twigg |  | 12397.73 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.28 | Lane 1- Perforation | SANTOS LIMITED | Lane (NFE A) | Rigless Australia - 1 |  | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-02-19 06:00 |  | 2021-02-20 06:00 | 2021-02-22 06:00 |  |  | Moomba WL | DKitney | 2021-02-22 22:13 | DKitney |  | No |  |  |  |  | Rob Twigg |  | 12397.73 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001570 | O.1001570.04 | A.1001570.04.21 | Big Lake 152 | SANTOS LIMITED | Big Lake 151 (Dev V) Gas DXCF Pad 5 | Rigless Australia - 1 |  | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2021-01-04 |  | 2021-01-10 06:00 | 2021-01-12 06:00 |  |  | Moomba WL | KKeese | 2021-01-13 20:57 | KKeese |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.44 | Koree South 1 | SANTOS LIMITED | Koree South 1 | Rigless Australia - 1 | J.21.108639 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-04 06:00 | 2021-07-03 06:00 | 2021-07-04 | 2021-07-04 06:00 | 2021-07-05 23:59 | 2021-07-06 | 2021-07-05 23:59 | Moomba WL | ADuong4 | 2022-10-03 11:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 79.2 | 0 | 0 | 0 | 23.8 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.43 | Fly Lake 1 | SANTOS LIMITED | Fly Lake 1 | Rigless Australia - 1 | J.21.108637 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-06-28 06:00 | 2021-06-27 | 2021-06-28 | 2021-06-28 06:00 | 2021-06-29 18:00 | 2021-06-30 | 2021-06-29 18:00 | Moomba WL | ADuong4 | 2022-10-03 11:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 58.3 | 16.7 | 0 | 12.5 | 26.3 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.42 | Brompton 1 | SANTOS LIMITED | Brompton 1 | Rigless Australia - 1 | J.21.108636 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-06-24 09:00 | 2021-06-23 09:00 | 2021-06-24 | 2021-06-24 09:00 | 2021-06-25 18:00 | 2021-06-26 | 2021-06-25 18:00 | Moomba WL | ADuong4 | 2022-10-03 11:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.41 | Moomba 261_SCMT | SANTOS LIMITED | Moomba 261 | Rigless Australia - 1 | J.21.108526 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-03-30 06:00 | 2021-03-30 06:00 | 2021-03-29 | 2021-03-30 06:00 | 2021-03-31 17:00 | 2021-04-01 | 2021-03-31 17:00 | Moomba WL | PLima7 | 2022-10-03 11:13 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.25 | TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062773 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-05-27 08:01 | 2020-05-27 09:01 |  | 2020-05-27 09:01 | 2020-05-28 09:01 |  | 2020-05-28 08:01 | Moomba WL | AGamero | 2022-10-03 10:38 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.38 | Toolachee 56 SCMT | SANTOS LIMITED | Toolachee 56 | Rigless Australia - 1 | J.20.062767 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-07-09 12:00 | 2020-07-09 |  | 2020-07-09 12:00 | 2020-07-10 23:59 |  | 2020-07-10 23:59 | Moomba WL | AHermawan | 2022-10-03 10:37 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.23 | Moomba 256_Drift, Dummy Gun, SCMT | SANTOS LIMITED | Moomba 256 | Rigless Australia - 1 | J.20.062766 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-08-23 12:00 | 2020-05-15 10:01 |  | 2020-08-23 12:00 | 2020-08-24 12:00 |  | 2020-08-24 12:00 | Moomba WL | AGamero | 2022-10-03 10:37 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 11566.12 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.32 | TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062755 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-06-16 08:01 | 2020-06-16 09:01 |  | 2020-06-16 09:01 | 2020-06-17 09:01 |  | 2020-06-17 08:01 | Moomba WL | AGamero | 2022-10-03 10:35 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.26 | TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062746 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-05-30 08:01 | 2020-05-30 09:01 |  | 2020-05-30 09:01 | 2020-05-31 09:01 |  | 2020-05-31 08:01 | Moomba WL | AGamero | 2022-10-03 10:34 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.05 | Cancelled | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062745 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-02-29 | 2020-02-29 |  | 2020-02-29 | 2020-03-01 |  | 2020-03-01 | Moomba WL | AGamero | 2022-10-03 10:34 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.12 | Moomba 253_Drift, SCMT | SANTOS LIMITED | Moomba 253 | Rigless Australia - 1 | J.20.062740 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-08-22 07:30 | 2020-04-16 |  | 2020-08-23 12:00 | 2020-08-25 12:00 |  | 2020-08-25 03:00 | Moomba WL | AGamero | 2022-10-03 10:33 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 11566.12 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.10 | TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062739 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2020-03-03 | 2020-03-25 |  | 2020-03-25 | 2020-03-26 |  | 2020-04-01 | Moomba WL | AGamero | 2022-10-03 10:33 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 11566.12 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.02 | Moomba_250_Setting Packer Tailpipe | SANTOS LIMITED | MOOMBA 250 | Rigless Australia - 1 | J.20.062738 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress | 2020-02-23 06:00 | 2020-02-23 |  | 2020-02-23 06:00 | 2020-02-26 06:00 |  | 2020-02-27 06:00 | Moomba WL | AGamero | 2022-10-03 10:33 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 11566.12 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.39 | Moorari 19 | SANTOS LIMITED | Moorari 19 | Rigless Australia - 1 | J.20.062723 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-08-05 | 2020-07-14 13:01 |  | 2020-08-05 | 2020-08-07 |  | 2020-08-07 | Moomba WL | DKitney | 2022-10-03 10:31 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 17664.14 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.34 | Brumby 10 | SANTOS LIMITED | Brumby 10 | Rigless Australia - 1 | J.20.062722 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-06-25 06:00 | 2020-06-23 09:01 |  | 2020-06-25 06:00 | 2020-06-26 06:00 |  | 2020-06-26 06:00 | Moomba WL | AGamero | 2022-10-03 10:31 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.31 | TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062721 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-06-13 08:01 | 2020-06-13 09:01 |  | 2020-06-13 09:01 | 2020-06-14 09:01 |  | 2020-06-14 08:01 | Moomba WL | AGamero | 2022-10-03 10:31 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.21 | Moomba 254_Drift, Dummy Gun, SCMT | SANTOS LIMITED | Moomba 254 | Rigless Australia - 1 | J.20.062720 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-08-23 12:00 | 2020-05-12 10:00 |  | 2020-08-23 12:00 | 2020-08-24 12:00 |  | 2020-08-24 12:00 | Moomba WL | AGamero | 2022-10-03 10:31 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 11566.12 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.28 | TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062710 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-06-04 08:01 | 2020-06-04 09:01 |  | 2020-06-04 09:01 | 2020-06-05 09:01 |  | 2020-06-05 08:01 | Moomba WL | AGamero | 2022-10-03 10:30 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.35 | TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062701 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-06-27 08:01 | 2020-06-27 09:01 |  | 2020-06-27 09:01 | 2020-06-28 09:01 |  | 2020-06-28 08:01 | Moomba WL | AGamero | 2022-10-03 10:29 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.18 | Pondrinie 18_Drift, SCMT | SANTOS LIMITED | Pondrinie 18 | Rigless Australia - 1 | J.20.062700 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-08-09 03:00 | 2020-05-05 09:01 |  | 2020-08-10 12:00 | 2020-08-11 12:00 |  | 2020-08-10 11:30 | Moomba WL | AGamero | 2022-10-03 10:28 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 11566.12 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.22 | Moomba 255_Drift, Dummy Gun, CBL | SANTOS LIMITED | Moomba 255 | Rigless Australia - 1 | J.20.062688 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-08-23 12:00 | 2020-05-14 09:01 |  | 2020-08-23 12:00 | 2020-08-24 12:00 |  | 2020-08-24 12:00 | Moomba WL | AGamero | 2022-10-03 10:27 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 11566.12 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.15 | TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062687 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-04-26 | 2020-04-26 01:00 |  | 2020-04-26 01:00 | 2020-04-27 01:00 |  | 2020-04-27 | Moomba WL | AGamero | 2022-10-03 10:27 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.13 | TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062686 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-04-20 01:00 | 2020-04-20 01:00 |  | 2020-04-20 01:00 | 2020-04-21 01:00 |  | 2020-04-21 01:00 | Moomba WL | AGamero | 2022-10-03 10:27 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.40 | Goyder 6_PNX | SANTOS LIMITED | Goyder 6 | Rigless Australia - 1 | J.20.062674 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-08-15 12:00 | 2020-07-23 |  | 2020-08-15 12:00 | 2020-08-20 13:00 |  | 2020-08-21 12:00 | Moomba WL | MSchvartz | 2022-10-03 10:26 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.06 | Moomba 238_SCMT-HD | SANTOS LIMITED | MOOMBA 238 | Rigless Australia - 1 | J.20.062673 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-03-26 06:00 | 2020-03-12 |  | 2020-03-23 06:00 | 2020-03-25 05:00 |  | 2020-03-29 05:00 | Moomba WL | AGamero | 2022-10-03 10:25 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 11566.12 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.37 | Toolache 55 SCMT | SANTOS LIMITED | Toolachee 55 | Rigless Australia - 1 | J.20.062666 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-07-04 13:00 | 2020-07-04 12:00 |  | 2020-07-04 13:00 | 2020-07-07 17:00 |  | 2020-07-07 17:00 | Moomba WL | AHermawan | 2022-10-03 10:25 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.36 | TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062665 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-07-01 08:01 | 2020-07-01 09:01 |  | 2020-07-01 09:01 | 2020-07-02 09:01 |  | 2020-07-02 08:01 | Moomba WL | AGamero | 2022-10-03 10:25 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.27 | TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062664 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-06-02 08:01 | 2020-06-02 09:01 |  | 2020-06-02 09:01 | 2020-06-03 09:01 |  | 2020-06-03 08:01 | Moomba WL | AGamero | 2022-10-03 10:25 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.24 | TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062663 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-05-24 08:01 | 2020-05-24 09:01 |  | 2020-05-24 09:01 | 2020-05-25 09:01 |  | 2020-05-25 08:01 | Moomba WL | AGamero | 2022-10-03 10:24 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.19 | Pondrinie 20_ Drift, Dummy Gun, CBL | SANTOS LIMITED | Pondrinie 20 | Rigless Australia - 1 | J.20.062662 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-08-23 12:00 | 2020-05-10 08:00 |  | 2020-08-23 12:00 | 2020-08-24 12:00 |  | 2020-08-24 12:00 | Moomba WL | AGamero | 2022-10-03 10:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 11566.12 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.11 | Merchant 1 | SANTOS LIMITED | Merchant 1 | Rigless Australia - 1 | J.20.062661 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-02-25 23:00 | 2020-03-27 12:00 |  | 2020-03-28 14:00 | 2020-03-31 14:00 |  | 2020-03-01 13:00 | Moomba WL | AGamero | 2022-10-03 10:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 11566.12 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.08 | TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062654 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2020-02-29 | 2020-03-16 |  | 2020-03-16 | 2020-03-17 |  | 2020-03-01 | Moomba WL | AGamero | 2022-10-03 10:23 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Alonso Alejandro Gamero Acuna |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.03 | Drift_Setting Packer Tailpipe Moomba 236 | SANTOS LIMITED | MOOMBA 236 | Rigless Australia - 1 | J.20.062649 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | In Progress | In Progress | In Progress | 2020-02-23 06:00 | 2020-02-25 05:30 |  | 2020-02-26 06:00 | 2020-02-28 06:00 |  | 2020-02-27 09:00 | Moomba WL | AGamero | 2022-10-03 10:23 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 11566.12 |  |  | L0 - No RO |  | 50 | 0 | 0 | 50 | 30 |  | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.01 | Raworth 1 Tubing Puncher | SANTOS LIMITED | Raworth 1 | Rigless Australia - 1 | J.20.062648 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-02-23 20:00 | 2020-02-15 20:00 |  | 2020-02-23 20:00 | 2020-02-24 20:00 |  | 2020-02-26 20:00 | Moomba WL | AGamero | 2022-10-03 10:23 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 8336.05 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.33 | PNX-CBL | SANTOS LIMITED | Moon 4 | Rigless Australia - 1 | J.20.062641 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress | 2020-06-27 | 2020-06-18 12:00 |  | 2020-06-27 | 2020-06-28 |  | 2020-06-28 | Moomba WL | AGamero | 2022-10-03 10:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 11566.12 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.30 | TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062640 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-06-09 08:01 | 2020-06-09 09:01 |  | 2020-06-09 09:01 | 2020-06-10 09:01 |  | 2020-06-10 08:01 | Moomba WL | AGamero | 2022-10-03 10:22 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.16 | TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062639 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-04-29 | 2020-04-29 01:00 |  | 2020-04-29 01:00 | 2020-04-30 01:00 |  | 2020-04-30 | Moomba WL | AGamero | 2022-10-03 10:22 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.07 | Moomba-239 SCMT | SANTOS LIMITED | MOOMBA 239 | Rigless Australia - 1 | J.20.062638 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-03-25 06:00 | 2020-03-19 |  | 2020-03-25 06:00 | 2020-03-25 22:00 |  | 2020-03-26 22:06 | Moomba WL | AGamero | 2022-10-03 10:21 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 11566.12 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.04 | 3 3/8 HSD, Drift, Packer_Moomba 237 | SANTOS LIMITED | Moomba 237 | Rigless Australia - 1 | J.20.062637 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-02-27 21:30 | 2020-02-27 20:30 |  | 2020-02-28 08:00 | 2020-03-25 08:00 |  | 2020-03-16 09:00 | Moomba WL | AGamero | 2022-10-03 10:21 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 11566.12 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.29 | TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062633 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-06-06 08:01 | 2020-06-06 09:01 |  | 2020-06-06 09:01 | 2020-06-07 09:01 |  | 2020-06-07 08:01 | Moomba WL | AGamero | 2022-10-03 10:21 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.20 | Pondrinie 19_Drift, Dummy Gun, CBL | SANTOS LIMITED | Pondrinie 19 | Rigless Australia - 1 | J.20.062632 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-08-10 12:00 | 2020-05-09 13:01 |  | 2020-08-10 12:00 | 2020-08-11 12:00 |  | 2020-08-11 12:00 | Moomba WL | AGamero | 2022-10-03 10:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.17 | TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062631 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-05-02 | 2020-05-02 01:00 |  | 2020-05-02 01:00 | 2020-05-03 01:00 |  | 2020-05-03 | Moomba WL | AGamero | 2022-10-03 10:20 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.14 | TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062630 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-04-23 | 2020-04-23 01:00 |  | 2020-04-23 01:00 | 2020-04-24 01:00 |  | 2020-04-24 | Moomba WL | AGamero | 2022-10-03 10:20 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.03 | A.1001570.03.09 | TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062622 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2020-03-01 | 2020-03-20 |  | 2020-03-20 | 2020-03-21 |  | 2020-03-02 | Moomba WL | AGamero | 2022-10-03 10:19 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Alonso Alejandro Gamero Acuna |  | 0 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.02 | A.1001570.02.03 | Challum 3 Link 2 1/8" | SANTOS LIMITED | CHALLUM 3 | Rigless Australia - 1 | J.19.060491 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | In Progress | Design Completed | In Progress | 2019-10-30 15:00 | 2019-10-30 14:00 |  | 2019-10-30 15:00 | 2019-11-01 |  | 2019-11-01 | Moomba WL | ymoradi2 | 2022-10-03 10:37 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.02 | A.1001570.02.02 | Challum 3 Link 2 1/8" | SANTOS LIMITED | CHALLUM 3 | Rigless Australia - 1 | J.19.060490 | RPI | PS-WL-Ops | InComplete | Confirmed | Execute - PSD |  | Not Started | Not Started | In Progress |  | 2019-10-30 14:00 |  | 2019-10-30 15:00 | 2019-11-01 |  |  | Moomba WL | ymoradi2 | 2022-10-03 10:37 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.02 | A.1001570.02.01 | Costa Central 1 - 2" HSD Perforation | SANTOS LIMITED | COSTA CENTRAL 1 | Rigless Australia - 1 | J.19.060488 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Design Completed | In Progress | 2019-10-26 21:36 | 2019-10-26 06:00 |  | 2019-10-26 07:00 | 2019-10-31 01:00 |  | 2019-10-31 01:00 | Moomba WL | ymoradi2 | 2022-10-03 10:36 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 58.3 | 0 | 0 | 25 | 25 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.02 | A.1001570.02.04 | Raworth 1 Puncher | SANTOS LIMITED | Raworth 1 | Rigless Australia - 1 | J.20.062647 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Required | Not Started | In Progress | 2020-02-13 20:00 | 2020-02-13 20:00 |  | 2020-02-13 20:00 | 2020-02-14 20:00 |  | 2020-02-14 20:00 | Moomba WL | crowand | 2022-10-03 10:23 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.40 | Raworth 1 Puncher | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062772 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Required | Not Started | In Progress |  | 2020-02-13 18:00 |  | 2020-02-13 18:00 | 2020-02-14 18:00 |  |  | Moomba WL | crowand | 2022-10-03 10:37 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.20 | Well 19 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060489 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-07 | 2019-11-19 |  | 2019-11-19 | 2019-11-20 |  | 2019-10-08 | Moomba WL | AGamero | 2022-10-03 10:37 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.36 | Vega 6-Puncher | SANTOS LIMITED | Vega 6 | Rigless Australia - 1 | J.20.062765 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-01-30 19:00 | 2020-01-30 14:00 |  | 2020-01-30 19:00 | 2020-02-01 |  | 2020-02-01 | Moomba WL | ymoradi2 | 2022-10-03 10:36 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.35 | Moomba 249 | SANTOS LIMITED | MOOMBA 249 | Rigless Australia - 1 | J.20.062764 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2020-01-27 06:00 | 2020-01-25 |  | 2020-01-27 06:00 | 2020-01-29 06:00 |  | 2020-01-29 06:00 | Moomba WL | KKeese | 2022-10-03 10:36 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.34 | Moomba 105 | SANTOS LIMITED | Moomba 105 | Rigless Australia - 1 | J.20.062763 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-01-29 12:00 | 2020-01-20 |  | 2020-01-29 12:00 | 2020-01-31 12:00 |  | 2020-01-31 12:00 | Moomba WL | KKeese | 2022-10-03 10:36 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.32 | Perforation and Packer Setting Gooranie 12 | SANTOS LIMITED | GOORANIE 12 | Rigless Australia - 1 | J.20.062762 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-01-08 13:00 | 2020-01-08 10:00 |  | 2020-01-08 13:00 | 2020-01-10 18:00 |  | 2020-01-10 18:00 | Moomba WL | ASetya | 2022-10-03 10:36 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6160.1 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.09 | Well 8 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060487 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-07 | 2019-10-24 |  | 2019-10-24 | 2019-10-25 |  | 2019-10-08 | Moomba WL | AGamero | 2022-10-03 10:36 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.29 | Lepard 1 | SANTOS LIMITED | Lepard 1 | Rigless Australia - 1 | J.19.060486 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2019-12-14 12:00 | 2019-12-13 |  | 2019-12-14 12:00 | 2019-12-21 12:00 |  | 2019-12-21 12:00 | Moomba WL | KKeese | 2022-10-03 10:35 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.24 | Well 23 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060485 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-07 | 2019-11-28 |  | 2019-11-28 | 2019-11-29 |  | 2019-10-08 | Moomba WL | AGamero | 2022-10-03 10:35 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.03 | Meranji 8 | SANTOS LIMITED | Meranji 8 | Rigless Australia - 1 | J.19.060484 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2019-11-20 14:00 | 2019-11-19 |  | 2019-11-20 14:00 | 2019-11-21 14:00 |  | 2019-11-21 14:00 | Moomba WL | AGamero | 2022-10-03 10:35 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 8596.49 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.11 | Well 10 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060483 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-07 | 2019-10-29 |  | 2019-10-29 | 2019-10-30 |  | 2019-10-08 | Moomba WL | AGamero | 2022-10-03 10:34 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.10 | Well 9 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060482 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-07 | 2019-10-27 |  | 2019-10-27 | 2019-10-28 |  | 2019-10-08 | Moomba WL | AGamero | 2022-10-03 10:34 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.07 | Well 6 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060481 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-07 | 2019-10-20 |  | 2019-10-20 | 2019-10-21 |  | 2019-10-08 | Moomba WL | AGamero | 2022-10-03 10:34 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.38 | Surlow 2-Perfo Plug | SANTOS LIMITED | SURLOW 2 | Rigless Australia - 1 | J.20.062737 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Design Completed | In Progress | 2020-02-15 11:00 | 2020-02-15 06:00 |  | 2020-02-15 11:00 | 2020-02-16 |  | 2020-02-16 | Moomba WL | ymoradi2 | 2022-10-03 10:33 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.17 | Well 16 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060480 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-07 | 2019-11-12 |  | 2019-11-12 | 2019-11-13 |  | 2019-10-08 | Moomba WL | AGamero | 2022-10-03 10:33 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.04 | Coopers Creek 5 | SANTOS LIMITED | Coopers Creek 5 | Rigless Australia - 1 | J.19.060479 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2019-11-25 12:02 | 2019-11-24 08:00 |  | 2019-11-25 12:02 | 2019-11-26 12:02 |  | 2019-11-26 12:02 | Moomba WL | AGamero | 2022-10-03 10:33 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 5730.99 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.01 | Big Lake 1 | SANTOS LIMITED | BIG LAKE 11 | Rigless Australia - 1 | J.19.060478 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2019-10-04 06:00 | 2019-10-04 05:00 |  | 2019-10-04 06:00 | 2019-10-05 11:30 |  | 2019-10-07 00:51 | Moomba WL | DParker16 | 2022-10-03 10:33 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 18797.66 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.39 | Costa Central 1 Perfo | SANTOS LIMITED | COSTA CENTRAL 1 | Rigless Australia - 1 | J.20.062719 | RPI | PS-WL-NO | Low | Confirmed | Execute - PSD |  | In Progress | Design Completed | In Progress | 2020-02-14 12:03 | 2020-02-14 10:00 |  | 2020-02-14 12:03 | 2020-02-18 |  | 2020-02-20 05:59 | Moomba WL | ymoradi2 | 2022-10-03 10:31 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 5845.61 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.30 | Marana 2 | SANTOS LIMITED | Marana 2 | Rigless Australia - 1 | J.19.060477 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2019-12-23 15:00 | 2019-12-22 |  | 2019-12-23 15:00 | 2019-12-26 15:00 |  | 2019-12-26 15:00 | Moomba WL | KKeese | 2022-10-03 10:30 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.05 | Coopers Creek 4 | SANTOS LIMITED | COOPERS CREEK 004 | Rigless Australia - 1 | J.19.060476 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Design Completed | In Progress | 2019-11-29 12:00 | 2019-11-25 06:00 |  | 2019-12-07 12:00 | 2019-12-08 12:00 |  | 2019-12-14 06:21 | Moomba WL | AGamero | 2022-10-03 10:30 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 5730.99 |  |  | L0 - No RO |  | 58.3 | 0 | 0 | 50 | 32.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.33 | Perforation and Packer Setting Gooranie 13 | SANTOS LIMITED | GOORANIE 13 | Rigless Australia - 1 | J.20.062709 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-01-18 13:00 | 2020-01-10 10:00 |  | 2020-01-18 13:00 | 2020-01-20 18:00 |  | 2020-01-20 18:00 | Moomba WL | ASetya | 2022-10-03 10:29 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6220.05 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.23 | Well 22 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060475 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-07 | 2019-11-26 |  | 2019-11-26 | 2019-11-27 |  | 2019-10-08 | Moomba WL | AGamero | 2022-10-03 10:29 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.06 | Coopers Creek 4 | SANTOS LIMITED | COOPERS CREEK 004 | Rigless Australia - 1 | J.19.060474 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Design Completed | In Progress | 2019-11-30 12:10 | 2019-12-04 06:00 |  | 2019-12-10 12:10 | 2019-12-11 12:10 |  | 2019-12-11 12:10 | Moomba WL | AGamero | 2022-10-03 10:29 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 5730.99 |  |  | L0 - No RO |  | 58.3 | 0 | 0 | 25 | 25 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.16 | Well 15 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060473 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-07 | 2019-11-10 |  | 2019-11-10 | 2019-11-11 |  | 2019-10-08 | Moomba WL | AGamero | 2022-10-03 10:28 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.27 | Napowie 4 | SANTOS LIMITED | NAPOWIE 004 | Rigless Australia - 1 | J.19.060472 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | In Progress | Design Completed | In Progress | 2019-12-14 16:51 | 2019-12-05 |  | 2019-12-14 | 2019-12-18 |  | 2019-12-18 | Moomba WL | KKeese | 2022-10-03 10:27 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 58.3 | 0 | 0 | 25 | 25 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.15 | Well 14 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060471 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-07 | 2019-11-07 |  | 2019-11-07 | 2019-11-08 |  | 2019-10-08 | Moomba WL | AGamero | 2022-10-03 10:27 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.02 | Costa Central 1 | SANTOS LIMITED | Costa Central 1 | Rigless Australia - 1 | J.19.060470 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2019-11-15 12:00 | 2019-11-15 06:00 |  | 2019-11-15 12:00 | 2019-11-17 12:00 |  | 2019-11-17 12:00 | Moomba WL | AGamero | 2022-10-03 10:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 17494.81 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.18 | Well 17 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060469 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-07 | 2019-11-14 |  | 2019-11-14 | 2019-11-15 |  | 2019-10-08 | Moomba WL | AGamero | 2022-10-03 10:24 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.25 | Well 24 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060468 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-07 | 2019-12-01 |  | 2019-12-01 | 2019-12-02 |  | 2019-10-08 | Moomba WL | AGamero | 2022-10-03 10:23 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.26 | Well 25 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060467 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-07 | 2019-12-03 |  | 2019-12-03 | 2019-12-04 |  | 2019-10-08 | Moomba WL | AGamero | 2022-10-03 10:23 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.22 | Well 21 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060466 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-07 | 2019-11-24 |  | 2019-11-24 | 2019-11-25 |  | 2019-10-08 | Moomba WL | AGamero | 2022-10-03 10:23 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.14 | Well 13 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060465 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-07 | 2019-11-05 |  | 2019-11-05 | 2019-11-06 |  | 2019-10-08 | Moomba WL | AGamero | 2022-10-03 10:21 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.08 | Well 7 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060464 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-07 | 2019-10-22 |  | 2019-10-22 | 2019-10-23 |  | 2019-10-08 | Moomba WL | AGamero | 2022-10-03 10:21 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.19 | Well 18 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060463 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-07 | 2019-11-17 |  | 2019-11-17 | 2019-11-18 |  | 2019-10-08 | Moomba WL | AGamero | 2022-10-03 10:20 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.12 | Well 11 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060462 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-07 | 2019-10-31 |  | 2019-10-31 | 2019-11-01 |  | 2019-10-08 | Moomba WL | AGamero | 2022-10-03 10:20 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.37 | Ute 1 -2" HSD Perf | SANTOS LIMITED | Ute Gas 1 | Rigless Australia - 1 | J.20.062621 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-02-12 08:00 | 2020-02-12 |  | 2020-02-12 08:00 | 2020-02-14 |  | 2020-02-14 | Moomba WL | ymoradi2 | 2022-10-03 10:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.31 | Baryulah 14 | SANTOS LIMITED | Baryulah 14 | Rigless Australia - 1 | J.20.062620 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-01-23 12:00 | 2020-01-02 11:00 |  | 2020-01-23 12:00 | 2020-01-25 12:00 |  | 2020-01-25 12:00 | Moomba WL | KKeese | 2022-10-03 10:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.28 | Moomba 10 | SANTOS LIMITED | Napowie 4 | Rigless Australia - 1 | J.19.060461 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2019-12-13 | 2019-12-11 |  | 2019-12-13 | 2019-12-15 |  | 2019-12-15 | Moomba WL | KKeese | 2022-10-03 10:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.21 | Well 20 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060460 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-07 | 2019-11-21 |  | 2019-11-21 | 2019-11-22 |  | 2019-10-08 | Moomba WL | AGamero | 2022-10-03 10:19 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001570 | O.1001570.01 | A.1001570.01.13 | Well 12 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060459 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-07 | 2019-11-03 |  | 2019-11-03 | 2019-11-04 |  | 2019-10-08 | Moomba WL | AGamero | 2022-10-03 10:19 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.09 | A.1001569.09.16 | CH_Logging_Well_16 | SANTOS LIMITED | Well #3 | Rigless Australia - 1 | J.22.109745 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-22 11:00 | 2022-06-22 10:00 |  | 2022-06-22 10:00 | 2022-06-25 09:59 |  | 2022-06-25 10:59 | Moomba WL | KKeese | 2022-10-03 12:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001569 | O.1001569.09 | A.1001569.09.15 | CH_Logging_Well_15 | SANTOS LIMITED | Well #3 | Rigless Australia - 1 | J.22.109744 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-10 11:00 | 2022-06-10 10:00 |  | 2022-06-10 10:00 | 2022-06-13 09:59 |  | 2022-06-13 10:59 | Moomba WL | KKeese | 2022-10-03 12:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001569 | O.1001569.09 | A.1001569.09.14 | CH_Logging_Well_14 | SANTOS LIMITED | Well #3 | Rigless Australia - 1 | J.22.109743 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-19 11:00 | 2022-06-19 10:00 |  | 2022-06-19 10:00 | 2022-06-22 09:59 |  | 2022-06-22 10:59 | Moomba WL | KKeese | 2022-10-03 12:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001569 | O.1001569.09 | A.1001569.09.13 | CH_Logging_Well_13 | SANTOS LIMITED | Well #3 | Rigless Australia - 1 | J.22.109742 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-16 11:00 | 2022-06-16 10:00 |  | 2022-06-16 10:00 | 2022-06-19 09:59 |  | 2022-06-19 10:59 | Moomba WL | KKeese | 2022-10-03 12:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001569 | O.1001569.09 | A.1001569.09.12 | CH_Logging_Well_12 | SANTOS LIMITED | Well #3 | Rigless Australia - 1 | J.22.109741 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-13 11:00 | 2022-06-13 10:00 |  | 2022-06-13 10:00 | 2022-06-16 09:59 |  | 2022-06-16 10:59 | Moomba WL | KKeese | 2022-10-03 12:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001569 | O.1001569.09 | A.1001569.09.11 | CH_Logging_Well_10 | SANTOS LIMITED | Well #3 | Rigless Australia - 1 | J.22.109740 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-05-07 11:00 | 2022-05-07 10:00 |  | 2022-05-07 10:00 | 2022-05-10 09:59 |  | 2022-05-10 10:59 | Moomba WL | KKeese | 2022-10-03 12:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001569 | O.1001569.09 | A.1001569.09.10 | CH_Logging_Well_9 | SANTOS LIMITED | Well #3 | Rigless Australia - 1 | J.22.109739 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-05-04 11:00 | 2022-05-04 10:00 |  | 2022-05-04 10:00 | 2022-05-07 09:59 |  | 2022-05-07 10:59 | Moomba WL | KKeese | 2022-10-03 12:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001569 | O.1001569.09 | A.1001569.09.09 | CH_Logging_Well_8 | SANTOS LIMITED | Well #3 | Rigless Australia - 1 | J.22.109738 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-05-01 11:00 | 2022-05-01 10:00 |  | 2022-05-01 10:00 | 2022-05-04 09:59 |  | 2022-05-04 10:59 | Moomba WL | KKeese | 2022-10-03 12:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001569 | O.1001569.09 | A.1001569.09.08 | CH_Logging_Well_7 | SANTOS LIMITED | Well #3 | Rigless Australia - 1 | J.22.109737 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-04-28 11:00 | 2022-04-28 10:00 |  | 2022-04-28 10:00 | 2022-05-01 09:59 |  | 2022-05-01 10:59 | Moomba WL | KKeese | 2022-10-03 12:04 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001569 | O.1001569.09 | A.1001569.09.07 | CH_Logging_Well_5 | SANTOS LIMITED | Well #3 | Rigless Australia - 1 | J.22.109736 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-04-25 11:00 | 2022-04-25 10:00 |  | 2022-04-25 10:00 | 2022-04-28 09:59 |  | 2022-04-28 10:59 | Moomba WL | KKeese | 2022-10-03 12:04 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001569 | O.1001569.09 | A.1001569.09.06 | CH_Logging_Well_5 | SANTOS LIMITED | Well #3 | Rigless Australia - 1 | J.22.109735 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-04-10 11:00 | 2022-04-10 10:00 |  | 2022-04-10 10:00 | 2022-04-13 09:59 |  | 2022-04-13 10:59 | Moomba WL | KKeese | 2022-10-03 12:04 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001569 | O.1001569.09 | A.1001569.09.05 | CH_Logging_Well_4 | SANTOS LIMITED | Well #3 | Rigless Australia - 1 | J.22.109734 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-04-22 11:00 | 2022-04-22 10:00 |  | 2022-04-22 10:00 | 2022-04-25 09:59 |  | 2022-04-25 10:59 | Moomba WL | KKeese | 2022-10-03 12:04 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001569 | O.1001569.09 | A.1001569.09.04 | CH_Logging_Well_3 | SANTOS LIMITED | Well #3 | Rigless Australia - 1 | J.22.109733 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-04-19 11:00 | 2022-04-19 10:00 |  | 2022-04-19 10:00 | 2022-04-22 09:59 |  | 2022-04-22 10:59 | Moomba WL | KKeese | 2022-10-03 12:04 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001569 | O.1001569.09 | A.1001569.09.03 | CH_Logging_Well_2 | SANTOS LIMITED | Well #3 | Rigless Australia - 1 | J.22.109732 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-04-16 11:00 | 2022-04-16 10:00 |  | 2022-04-16 10:00 | 2022-04-19 09:59 |  | 2022-04-19 10:59 | Moomba WL | KKeese | 2022-10-03 12:04 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001569 | O.1001569.09 | A.1001569.09.02 | CH_Logging_Well_1 | SANTOS LIMITED | Well #3 | Rigless Australia - 1 | J.22.109731 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-04-13 11:00 | 2022-04-13 10:00 |  | 2022-04-13 10:00 | 2022-04-16 09:59 |  | 2022-04-16 10:59 | Moomba WL | KKeese | 2022-10-03 12:04 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001569 | O.1001569.09 | A.1001569.09.01 | Napowie 2 | SANTOS LIMITED | Well #3 | Rigless Australia - 1 | J.22.109730 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-07-14 11:00 | 2022-07-14 09:00 |  | 2022-07-14 10:00 | 2022-07-17 09:59 |  | 2022-07-17 10:59 | Moomba WL | KKeese | 2022-10-03 12:04 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | 0 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Owen Bass | WL Production Services
P.1001569 | O.1001569.08 | A.1001569.08.10 | Bolah 8-9-10 | SANTOS LIMITED | BOLAH 8, BOLAH 9, BOLAH 10 | Rigless Australia - 1 | J.22.109823 | RPI | PS-WL-NO | Low | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2022-05-22 |  | 2022-05-22 | 2022-06-04 23:59 |  |  | Moomba WL | YPouryan | 2022-10-03 12:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | 0 |  | L3 - Full RO | [7 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001569 | O.1001569.08 | A.1001569.08.09 | Bolah 8-9-10 | SANTOS LIMITED | Bolah 10, Bolah 9, Bolah 8 | Rigless Australia - 1 | J.22.109822 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-05-29 09:00 | 2022-05-28 |  | 2022-05-28 09:00 | 2022-06-08 08:59 |  | 2022-06-08 08:59 | Moomba WL | YPouryan | 2022-10-03 12:13 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001569 | O.1001569.08 | A.1001569.08.08 | Moomba 272 CBL | SANTOS LIMITED | Moomba 272 | Rigless Australia - 1 | J.22.109810 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-05-08 10:00 | 2022-05-06 |  | 2022-05-08 10:00 | 2022-05-10 09:59 |  | 2022-05-09 09:59 | Moomba WL | zauzar | 2022-10-03 12:12 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  |  |  | 66.7 | 83.3 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001569 | O.1001569.08 | A.1001569.08.07 | Moomba 271 cbl | SANTOS LIMITED | MOOMBA 271, MOOMBA 272 | Rigless Australia - 1 | J.22.109809 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2022-05-16 03:58 | 2022-05-14 |  | 2022-05-14 09:00 | 2022-05-16 08:59 |  | 2022-05-16 08:59 | Moomba WL | zauzar | 2022-10-03 12:12 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 79.2 | 75 | 0 | 62.5 | 65 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001569 | O.1001569.08 | A.1001569.08.06 | Moomba 226 CBL | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109802 | RPI | PS-WL-NO | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2022-04-26 20:01 | 2022-04-22 |  | 2022-04-24 10:00 | 2022-04-26 09:59 |  | 2022-04-27 20:06 | Moomba WL | zauzar | 2022-10-03 12:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 83.3 | 100 | 100 | 75 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001569 | O.1001569.08 | A.1001569.08.05 | Meranji 27 PFP and Packer set | SANTOS LIMITED | MERANJI 027, MOOMBA 226 | Rigless Australia - 1 | J.22.109800 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2022-04-26 08:00 | 2022-04-19 |  | 2022-04-26 08:00 | 2022-05-04 07:59 |  | 2022-05-04 07:59 | Moomba WL | zauzar | 2022-10-03 12:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 12 |  | L0 - No RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001569 | O.1001569.08 | A.1001569.08.04 | Meranji 27 / Meranji 24 / Kudrieke 3 / Moomba 227 | SANTOS LIMITED | Meranji 27, Meranji 24, Kudrieke 3, Moomba 227(Dev AD) | Rigless Australia - 1 | J.22.109762 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-23 12:00 | 2021-12-12 01:00 |  | 2022-03-23 12:00 | 2022-03-29 11:59 |  | 2022-03-29 11:59 | Moomba WL | zauzar | 2022-10-03 12:07 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001569 | O.1001569.08 | A.1001569.08.03 | Tirrawarra 93 | SANTOS LIMITED | Tirrawarra 93 | Rigless Australia - 1 | J.22.109758 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2022-03-18 12:00 | 2021-12-08 01:00 |  | 2022-03-18 12:00 | 2022-03-22 11:59 |  | 2022-03-22 11:59 | Moomba WL | KKeese | 2022-10-03 12:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001569 | O.1001569.08 | A.1001569.08.02 | Napowie 2 | SANTOS LIMITED | Napowie 2 | Rigless Australia - 1 | J.20.062629 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-27 12:00 | 2020-11-13 |  | 2020-12-27 12:00 | 2020-12-30 11:59 |  | 2020-12-30 11:59 | Moomba WL | KKeese | 2022-10-03 10:20 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001569 | O.1001569.08 | A.1001569.08.01 | TBA | SANTOS LIMITED | Well-1 | Rigless Australia - 1 |  | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress |  | 2020-09-18 |  | 2020-12-27 12:00 | 2020-12-31 11:59 |  |  | Moomba WL | ymoradi2 | 2020-12-27 13:55 | IWahbi |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.19 | Gooranie 15 | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062771 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress | 2020-09-08 07:00 | 2020-09-15 02:00 |  | 2020-09-16 02:00 | 2020-09-18 02:00 |  | 2020-09-08 16:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:37 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.39 | Brolga 6 - PFPs & Set Packer | SANTOS LIMITED | Brolga 6 | Rigless Australia - 1 | J.20.062761 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-09-24 07:00 | 2020-09-23 |  | 2020-09-24 07:00 | 2020-09-26 23:59 |  | 2020-09-26 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:36 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.29 | Moomba 241 Packer Set | SANTOS LIMITED | Moomba MS 241 | Rigless Australia - 1 | J.20.062760 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-09-02 | 2020-09-01 |  | 2020-09-02 | 2020-09-04 23:59 |  | 2020-09-04 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:36 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.42 | Cougar East 1 | SANTOS LIMITED | Cougar East 1 | Rigless Australia - 1 | J.20.062754 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-09-22 07:00 | 2020-09-22 |  | 2020-09-22 07:00 | 2020-09-24 23:59 |  | 2020-09-24 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:35 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.36 | Moorari 5 ; Post Frac Perforations | SANTOS LIMITED | Moorari 5 | Rigless Australia - 1 | J.20.062753 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-09-09 12:00 | 2020-09-07 |  | 2020-09-09 12:00 | 2020-09-12 11:59 |  | 2020-09-12 11:59 | Moomba WL | ymoradi2 | 2022-10-03 10:35 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.08 | Gooranie 16 | SANTOS LIMITED | GOORANIE 16 | Rigless Australia - 1 | J.20.062752 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-08-02 09:00 | 2020-08-02 06:00 |  | 2020-08-02 09:00 | 2020-08-04 08:00 |  | 2020-08-05 08:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:35 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 15843.5 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.44 | Derwin 1- CIBP Cement | SANTOS LIMITED | Derwin 1 | Rigless Australia - 1 | J.21.108388 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-03-04 13:00 | 2021-03-03 |  | 2021-03-04 12:00 | 2021-03-08 03:59 |  | 2021-03-06 04:59 | Moomba WL | DKitney | 2022-10-03 10:34 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.40 | Brolga 7 - PFPs & Set Packer | SANTOS LIMITED | Brolga 7 | Rigless Australia - 1 | J.20.062744 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-09-25 10:00 | 2020-09-25 |  | 2020-09-25 10:00 | 2020-09-28 02:59 |  | 2020-09-28 02:59 | Moomba WL | ymoradi2 | 2022-10-03 10:34 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.06 | Moorari 20 | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062743 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-07-28 23:00 | 2020-07-29 |  | 2020-07-29 | 2020-07-31 |  | 2020-07-30 23:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:34 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.04 | Pooraka 2 | SANTOS LIMITED | Pooraka 2(App A) | Rigless Australia - 1 | J.20.062742 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-08-21 12:00 | 2020-08-21 |  | 2020-08-21 12:00 | 2020-08-23 12:00 |  | 2020-08-23 12:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:33 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6138.53 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.43 | Napowie 6_2" HSD Perforation | SANTOS LIMITED | Napowie 6 | Rigless Australia - 1 | J.20.062736 | RPI | PS-WL-Ops | Medium | Operationally Complete | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-23 | 2020-11-28 06:00 |  | 2020-12-23 | 2021-01-18 03:59 |  | 2021-01-18 03:59 | Moomba WL | ymoradi2 | 2022-10-03 10:32 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.18 | Gooranie 17 | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062735 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress | 2020-09-11 19:00 | 2020-09-11 02:00 |  | 2020-09-13 12:00 | 2020-09-15 12:00 |  | 2020-09-14 15:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:32 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.16 | Moomba 247 | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062734 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-09-05 05:00 | 2020-09-05 02:00 |  | 2020-09-06 02:00 | 2020-09-08 02:00 |  | 2020-09-07 05:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:32 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.37 | Moomba 242-Packer Set | SANTOS LIMITED | MOOMBA 242 | Rigless Australia - 1 | J.20.062718 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress | 2020-09-17 | 2020-09-16 |  | 2020-09-17 | 2020-09-19 23:59 |  | 2020-09-19 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:30 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.21 | Dullingari 42 | SANTOS LIMITED | Well #24 | Rigless Australia - 1 | J.20.062717 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-09-23 01:00 | 2020-09-22 02:00 |  | 2020-09-23 02:00 | 2020-09-25 02:00 |  | 2020-09-25 01:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:30 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.20 | Gooranie 14 | SANTOS LIMITED | Well #21 | Rigless Australia - 1 | J.20.062716 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-09-17 01:00 | 2020-09-16 02:00 |  | 2020-09-17 02:00 | 2020-09-19 02:00 |  | 2020-09-19 01:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:30 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.31 | Moomba 245 -Set Packer/perfs | SANTOS LIMITED | Moomba 245 | Rigless Australia - 1 | J.20.062708 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress | 2020-09-06 | 2020-09-05 |  | 2020-09-06 | 2020-09-10 23:59 |  | 2020-09-10 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:29 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.25 | Cooba 2 -Post Frac Perforations/Packer Set ; | SANTOS LIMITED | Cooba 2 | Rigless Australia - 1 | J.20.062707 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-08-26 | 2020-08-25 |  | 2020-08-26 | 2020-08-28 23:59 |  | 2020-08-28 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:29 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.09 | Cooba 2 | SANTOS LIMITED | Cooba 2 | Rigless Australia - 1 | J.20.062706 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-08-13 12:00 | 2020-08-07 01:00 |  | 2020-08-13 12:00 | 2020-08-17 12:00 |  | 2020-08-17 12:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:29 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 22053.66 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.07 | Seccante 7 | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062705 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-08-04 11:00 | 2020-08-04 |  | 2020-08-04 12:00 | 2020-08-13 13:00 |  | 2020-08-13 12:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:29 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.32 | Moomba 252-Packer Set | SANTOS LIMITED | Moomba 252 | Rigless Australia - 1 | J.20.062699 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-09-05 | 2020-09-02 |  | 2020-09-05 | 2020-09-07 23:59 |  | 2020-09-07 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:28 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.12 | Montegue 1_Drift, Dummy Gun, SCMT | SANTOS LIMITED | Montegue 1 | Rigless Australia - 1 | J.20.062698 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress | 2020-08-21 05:00 | 2020-08-20 01:00 |  | 2020-08-22 01:00 | 2020-08-23 01:00 |  | 2020-08-23 05:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:28 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 8596.49 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.11 | Moon 5 | SANTOS LIMITED | Moon 5 | Rigless Australia - 1 | J.20.062697 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-08-15 18:00 | 2020-08-15 10:00 |  | 2020-08-15 18:00 | 2020-08-17 18:00 |  | 2020-08-17 18:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:28 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 14550.36 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.26 | Moomba 238 Post Frac Perfs / Packer Set | SANTOS LIMITED | MOOMBA 238 | Rigless Australia - 1 | J.20.062685 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-08-27 | 2020-08-26 |  | 2020-08-27 | 2020-08-30 23:59 |  | 2020-08-30 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:27 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.14 | Inglewood 1_Drift, Dummy Gun, PNX | SANTOS LIMITED | Inglewood 1 | Rigless Australia - 1 | J.20.062684 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress | 2020-12-23 | 2020-08-28 02:00 |  | 2020-12-23 | 2020-12-25 |  | 2020-12-25 | Moomba WL | FDPSystemUser | 2022-10-03 10:27 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.10 | Moon 4 | SANTOS LIMITED | Moon 4 | Rigless Australia - 1 | J.20.062683 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-08-13 12:00 | 2020-08-12 |  | 2020-08-13 12:00 | 2020-08-15 12:00 |  | 2020-08-15 12:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:26 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 10251.35 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.02 | Big Lake 102- Tubing Cutter-TCP Correlation | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062682 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-08-03 23:00 | 2020-08-04 |  | 2020-08-04 | 2020-08-06 |  | 2020-08-05 23:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:26 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.01 | Moomba 251 3 3/8 HSD and Packer Tailpipe | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062681 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-08-05 15:00 | 2020-08-05 |  | 2020-08-05 | 2020-08-15 |  | 2020-08-12 23:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:26 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.41 | Okotoko North 2 ; CBL / Set CIBP | SANTOS LIMITED | Okotoko North 2 | Rigless Australia - 1 | J.20.062672 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-27 12:00 | 2020-09-28 |  | 2020-12-27 12:00 | 2020-12-30 04:59 |  | 2020-12-30 04:59 | Moomba WL | ymoradi2 | 2022-10-03 10:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.38 | Big Lake 146 ; Drift & Perforate [53ft x 1- 11/16"] | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062671 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-12-29 | 2020-12-29 |  | 2020-12-29 | 2020-12-31 16:59 |  | 2020-12-31 16:59 | Moomba WL | ymoradi2 | 2022-10-03 10:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.17 | Moomba 253 | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062660 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress | 2020-09-09 17:00 | 2020-09-08 02:00 |  | 2020-09-10 14:00 | 2020-09-12 14:00 |  | 2020-09-11 17:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:24 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.33 | Moolion North 2 | SANTOS LIMITED | Moolion North 2 | Rigless Australia - 1 | J.20.062653 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-12-30 | 2020-12-30 |  | 2020-12-30 | 2020-12-31 23:59 |  | 2020-12-31 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:23 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.27 | Moomba 239 Packer Set | SANTOS LIMITED | MOOMBA 239 | Rigless Australia - 1 | J.20.062652 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-12-23 | 2020-08-29 |  | 2020-12-23 | 2020-12-24 23:59 |  | 2020-12-24 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:23 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.24 | Moorari 19 | SANTOS LIMITED | Derwin 1 | Rigless Australia - 1 | J.20.062651 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-07-25 23:00 | 2020-07-25 |  | 2020-07-26 | 2020-07-28 |  | 2020-07-27 23:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:23 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.34 | Taylor South 1 | SANTOS LIMITED | Taylor South 2 | Rigless Australia - 1 | J.20.062646 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-09-09 | 2020-09-07 |  | 2020-09-09 | 2020-09-10 23:59 |  | 2020-09-10 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.28 | Moomba 240 Packer Set | SANTOS LIMITED | MOOMBA 240 | Rigless Australia - 1 | J.20.062645 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-12-23 | 2020-08-31 |  | 2020-12-23 | 2020-12-25 23:59 |  | 2020-12-25 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.22 | Coonatie 8 | SANTOS LIMITED | Well #25 | Rigless Australia - 1 | J.20.062636 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-09-21 | 2020-09-20 02:00 |  | 2020-09-21 02:00 | 2020-09-23 02:00 |  | 2020-09-23 | Moomba WL | FDPSystemUser | 2022-10-03 10:21 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.13 | Moomba 96 | SANTOS LIMITED | Moomba 96 | Rigless Australia - 1 | J.20.062635 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-08-23 07:00 | 2020-08-22 01:00 |  | 2020-08-23 07:00 | 2020-08-26 07:00 |  | 2020-08-26 07:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:21 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 11621.18 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.30 | Moomba 243- Set Packer | SANTOS LIMITED | MOOMBA 243 | Rigless Australia - 1 | J.20.062628 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress | 2020-09-14 07:00 | 2020-09-14 |  | 2020-09-14 07:00 | 2020-09-18 06:59 |  | 2020-09-18 06:59 | Moomba WL | ymoradi2 | 2022-10-03 10:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.23 | Juno 8 | SANTOS LIMITED | Well #14 | Rigless Australia - 1 | J.20.062627 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-09-28 01:00 | 2020-09-27 02:00 |  | 2020-09-28 02:00 | 2020-09-30 02:00 |  | 2020-09-30 01:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:20 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.05 | BigLake102RiglessTubingCutter | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062626 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-09-04 23:00 | 2020-09-05 |  | 2020-09-05 | 2020-09-07 |  | 2020-09-06 23:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:20 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.35 | Moomba 244-Drift / Post Frac Perf . Packer Set | SANTOS LIMITED | MOOMBA 244 | Rigless Australia - 1 | J.20.062619 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress | 2020-09-09 12:00 | 2020-09-07 |  | 2020-09-09 12:00 | 2020-09-12 11:59 |  | 2020-09-12 11:59 | Moomba WL | ymoradi2 | 2022-10-03 10:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.15 | Moomba 249 | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062618 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Not Started | In Progress | In Progress | 2020-08-30 19:00 | 2020-08-31 02:00 |  | 2020-09-01 02:00 | 2020-09-03 02:00 |  | 2020-09-01 19:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:19 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.07 | A.1001569.07.03 | Moorari 5 | SANTOS LIMITED | Moorari 5 | Rigless Australia - 1 | J.20.062617 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-08-04 14:00 | 2020-08-04 |  | 2020-08-04 14:00 | 2020-08-06 14:00 |  | 2020-08-06 14:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:19 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 9680.92 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.01 | Brompton 1 | SANTOS LIMITED | Brompton 1 | Rigless Australia - 1 | J.20.062770 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-10-02 06:00 | 2020-10-01 |  | 2020-10-02 06:00 | 2020-10-04 07:00 |  | 2020-10-04 07:00 | Moomba WL | OBass | 2022-10-03 10:37 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 51228.72 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.25 | Amyema 2_SCMT | SANTOS LIMITED | Amyema 2 | Rigless Australia - 1 | J.20.062751 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2020-12-27 06:00 | 2020-12-26 06:00 |  | 2020-12-27 06:00 | 2020-12-29 06:00 |  | 2020-12-29 06:00 | Moomba WL | OBass | 2022-10-03 10:35 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.13 | Alwyn 8 | SANTOS LIMITED | Alwyn 8 | Rigless Australia - 1 | J.20.062750 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2020-11-14 12:00 | 2020-11-14 |  | 2020-11-14 12:00 | 2020-11-16 12:00 |  | 2020-11-16 12:00 | Moomba WL | OBass | 2022-10-03 10:35 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.29 | Well TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108385 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-10-25 15:00 | 2020-10-25 12:00 |  | 2021-10-25 15:00 | 2021-10-27 15:00 |  | 2020-10-27 15:00 | Moomba WL | AHermawan | 2022-10-03 10:32 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7428.72 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.18 | Meranji 2 | SANTOS LIMITED | Meranji 2 | Rigless Australia - 1 | J.20.062733 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-11-29 18:00 | 2020-11-26 |  | 2020-11-29 18:00 | 2020-12-01 18:00 |  | 2020-12-01 18:00 | Moomba WL | OBass | 2022-10-03 10:32 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7428.72 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.07 | Goyder 6 | SANTOS LIMITED | Goyder 6 | Rigless Australia - 1 | J.20.062732 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-10-30 15:00 | 2020-10-29 15:00 |  | 2020-10-30 15:00 | 2020-11-01 15:00 |  | 2020-11-01 15:00 | Moomba WL | OBass | 2022-10-03 10:32 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7428.72 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.06 | Moomba 225 | SANTOS LIMITED | MOOMBA 225 | Rigless Australia - 1 | J.20.062731 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-12 | 2020-12-07 |  | 2020-12-12 | 2020-12-14 |  | 2020-12-14 | Moomba WL | OBass | 2022-10-03 10:32 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7428.72 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.04 | Toolachee 12 | SANTOS LIMITED | Toolachee 12 | Rigless Australia - 1 | J.20.062725 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-10-16 | 2020-10-15 |  | 2020-10-16 | 2020-10-18 |  | 2020-10-18 | Moomba WL | OBass | 2022-10-03 10:31 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6686.16 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.22 | Well TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062715 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-12-13 | 2020-12-13 |  | 2020-12-13 | 2020-12-15 |  | 2020-12-15 | Moomba WL | OBass | 2022-10-03 10:30 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.17 | Taylor South 1 | SANTOS LIMITED | TAYLOR SOUTH 1 | Rigless Australia - 1 | J.20.062714 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-23 | 2020-11-24 |  | 2020-12-23 | 2020-12-25 |  | 2020-12-25 | Moomba WL | OBass | 2022-10-03 10:30 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 16492.53 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.09 | Pondrinie 13 | SANTOS LIMITED | Pondrinie 13 | Rigless Australia - 1 | J.20.062713 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-10-30 15:00 | 2020-10-28 12:00 |  | 2020-10-30 15:00 | 2020-11-01 15:00 |  | 2020-11-01 15:00 | Moomba WL | OBass | 2022-10-03 10:30 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7428.72 |  |  |  |  | 75 | 50 | 0 | 62.5 | 56.3 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.16 | Moolion North 2 | SANTOS LIMITED | Moolion North 2 | Rigless Australia - 1 | J.20.062704 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-23 | 2020-11-24 |  | 2020-12-23 | 2020-12-25 |  | 2020-12-25 | Moomba WL | OBass | 2022-10-03 10:29 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 9806.37 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.15 | Alwyn North 2 | SANTOS LIMITED | Alwyn North 2 | Rigless Australia - 1 | J.20.062703 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-11-22 | 2020-11-22 |  | 2020-11-22 | 2020-11-24 |  | 2020-11-24 | Moomba WL | OBass | 2022-10-03 10:29 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.26 | Brumby 14_SCMT | SANTOS LIMITED | Brumby 14 | Rigless Australia - 1 | J.21.108381 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-01-08 06:00 | 2020-12-28 |  | 2021-01-08 06:00 | 2021-01-10 06:00 |  | 2021-01-10 06:00 | Moomba WL | OBass | 2022-10-03 10:28 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.28 | Well TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062680 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-09-30 23:00 | 2020-10-01 |  | 2020-10-01 | 2020-10-03 |  | 2020-10-02 23:00 | Moomba WL | OBass | 2022-10-03 10:26 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.20 | Merupa 3 | SANTOS LIMITED | Merupa 3 | Rigless Australia - 1 | J.20.062679 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-07 | 2020-12-07 |  | 2020-12-07 | 2020-12-09 |  | 2020-12-09 | Moomba WL | OBass | 2022-10-03 10:26 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7428.72 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.14 | Alwyn North 2 | SANTOS LIMITED | Alwyn North 2 | Rigless Australia - 1 | J.20.062678 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2020-11-17 12:00 | 2020-11-17 |  | 2020-11-17 12:00 | 2020-11-19 12:00 |  | 2020-11-19 12:00 | Moomba WL | OBass | 2022-10-03 10:26 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.08 | Wippo South 2 | SANTOS LIMITED | Wippo South 2 | Rigless Australia - 1 | J.20.062677 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2020-11-06 | 2020-11-05 |  | 2020-11-06 | 2020-11-08 |  | 2020-11-08 | Moomba WL | OBass | 2022-10-03 10:26 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7428.72 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.19 | Napowie 9 | SANTOS LIMITED | NAPOWIE 009 | Rigless Australia - 1 | J.20.062670 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-01 12:00 | 2020-12-01 |  | 2020-12-01 12:00 | 2020-12-03 12:00 |  | 2020-12-03 12:00 | Moomba WL | OBass | 2022-10-03 10:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7428.72 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.02 | Hector South East 1 | SANTOS LIMITED | Hector South East 1 | Rigless Australia - 1 | J.20.062669 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-10-04 | 2020-10-04 |  | 2020-10-04 | 2020-10-07 |  | 2020-10-07 | Moomba WL | OBass | 2022-10-03 10:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7428.72 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.12 | Yanda South 1 | SANTOS LIMITED | Yanda South 1 | Rigless Australia - 1 | J.20.062659 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2020-11-07 18:00 | 2020-11-07 |  | 2020-11-07 18:00 | 2020-11-09 18:00 |  | 2020-11-09 18:00 | Moomba WL | OBass | 2022-10-03 10:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.30 | Taylor South 1 | SANTOS LIMITED | TAYLOR SOUTH 1 | Rigless Australia - 1 | J.21.108378 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress | 2021-01-26 15:00 | 2020-12-27 15:00 |  | 2021-01-26 06:00 | 2021-01-28 06:00 |  | 2021-01-28 15:00 | Moomba WL | DParker16 | 2022-10-03 10:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 32985.06 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.24 | Tantanna 12- CIBP Cement | SANTOS LIMITED | TANTANNA 12 | Rigless Australia - 1 | J.21.108377 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-01-04 06:00 | 2021-01-02 |  | 2021-01-04 06:00 | 2021-01-17 06:00 |  | 2021-01-06 06:00 | Moomba WL | OBass | 2022-10-03 10:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 10612.61 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.23 | Big Lake 152 | SANTOS LIMITED | Big Lake 152 (Dev V) Gas DXCF Pad 5 | Rigless Australia - 1 | J.20.062644 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-14 12:00 | 2020-12-12 10:00 |  | 2020-12-14 12:00 | 2020-12-16 12:00 |  | 2020-12-16 12:00 | Moomba WL | OBass | 2022-10-03 10:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 51647.72 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.05 | Moon 5 | SANTOS LIMITED | Moon 5 | Rigless Australia - 1 | J.20.062643 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-11-05 | 2020-11-04 |  | 2020-11-05 | 2020-11-07 |  | 2020-11-07 | Moomba WL | OBass | 2022-10-03 10:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 17402.74 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.27 | Well TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062634 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-12-28 | 2020-12-28 |  | 2020-12-28 | 2020-12-30 |  | 2020-12-30 | Moomba WL | OBass | 2022-10-03 10:21 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.21 | Well TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062625 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-12-10 | 2020-12-10 |  | 2020-12-10 | 2020-12-12 |  | 2020-12-12 | Moomba WL | OBass | 2022-10-03 10:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.10 | Pondrinie 16 | SANTOS LIMITED | Pondrinie 16 | Rigless Australia - 1 | J.20.062616 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-10-25 15:00 | 2020-10-25 12:00 |  | 2020-10-25 15:00 | 2020-10-27 15:00 |  | 2020-10-27 15:00 | Moomba WL | OBass | 2022-10-03 10:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7428.72 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.03 | Moon 1 | SANTOS LIMITED | Moon 1 | Rigless Australia - 1 | J.20.062615 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-10-12 12:00 | 2020-10-11 |  | 2020-10-12 12:00 | 2020-10-14 12:00 |  | 2020-10-14 12:00 | Moomba WL | OBass | 2022-10-03 10:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 25845.61 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.06 | A.1001569.06.11 | Okotoko North 2 | SANTOS LIMITED | Okotoko North 2 | Rigless Australia - 1 | J.20.062610 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2020-11-04 06:00 | 2020-11-03 12:00 |  | 2020-11-04 06:00 | 2020-11-06 06:00 |  | 2020-11-05 06:00 | Moomba WL | OBass | 2022-10-03 10:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.22 | Toolachee 56 2 in HSD Perfo | SANTOS LIMITED | Toolachee 56 | Rigless Australia - 1 | J.20.062769 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-07-21 | 2020-07-20 |  | 2020-07-21 | 2020-07-23 23:59 |  | 2020-07-23 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:37 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.15 | Toolachee 1- 1 11/16" Link | SANTOS LIMITED | Toolachee 1 | Rigless Australia - 1 | J.20.062768 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress | 2020-07-07 | 2020-07-06 |  | 2020-07-07 | 2020-07-08 23:59 |  | 2020-07-08 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:37 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.11 | Moomba 255 | SANTOS LIMITED | Moomba 255 | Rigless Australia - 1 | J.20.062759 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-06-20 11:00 | 2020-06-20 10:00 |  | 2020-06-20 11:00 | 2020-06-25 11:00 |  | 2020-06-25 11:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:36 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.10 | Moomba 248 - Packer | SANTOS LIMITED | MOOMBA 248 | Rigless Australia - 1 | J.20.062758 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-06-15 01:00 | 2020-06-14 10:00 |  | 2020-06-15 01:00 | 2020-06-17 01:00 |  | 2020-06-17 01:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:36 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6984.17 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.02 | Vega 7 | SANTOS LIMITED | VEGA 7 | Rigless Australia - 1 | J.20.062741 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-06-25 10:00 | 2020-06-25 |  | 2020-06-25 10:00 | 2020-06-27 10:00 |  | 2020-06-27 10:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:33 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 23083.17 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.20 | Pondrinie 20- 2in HSD Perfo | SANTOS LIMITED | Pondrinie 20 | Rigless Australia - 1 | J.20.062730 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress | 2020-08-10 12:00 | 2020-07-14 |  | 2020-08-10 12:00 | 2020-08-14 11:59 |  | 2020-08-14 11:59 | Moomba WL | ymoradi2 | 2022-10-03 10:32 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.14 | Coonatie 8- 1 11/16" Link | SANTOS LIMITED | Coonatie 8 | Rigless Australia - 1 | J.20.062729 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress | 2020-07-04 | 2020-07-03 |  | 2020-07-04 | 2020-07-07 23:59 |  | 2020-07-07 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:32 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.09 | TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062728 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-07-19 23:00 | 2020-07-20 01:00 |  | 2020-07-20 01:00 | 2020-07-22 01:00 |  | 2020-07-21 23:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:32 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.08 | Moomba 254 | SANTOS LIMITED | Moomba 254 | Rigless Australia - 1 | J.20.062727 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-06-16 01:00 | 2020-06-15 18:00 |  | 2020-06-16 01:00 | 2020-06-20 |  | 2020-06-20 | Moomba WL | FDPSystemUser | 2022-10-03 10:32 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 28248.45 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.04 | Barrolka North East 3 | SANTOS LIMITED | BARROLKA NORTH EAST 3 | Rigless Australia - 1 | J.20.062712 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-06-28 10:00 | 2020-06-28 |  | 2020-06-28 10:00 | 2020-06-30 10:00 |  | 2020-06-30 10:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:30 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 22764.78 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.03 | big Lake 6-2 1/8" Link perfo | SANTOS LIMITED | Well #9 | Rigless Australia - 1 | J.20.062711 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-07-12 13:00 | 2020-07-08 |  | 2020-07-12 14:00 | 2020-07-14 14:00 |  | 2020-07-14 13:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:30 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.24 | Costa Central 1 | SANTOS LIMITED | Costa Central 1 | Rigless Australia - 1 | J.20.062702 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-07-25 | 2020-07-24 |  | 2020-07-25 | 2020-07-26 23:59 |  | 2020-07-26 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:29 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.25 | Vega 7-CPST-Cement | SANTOS LIMITED | VEGA 7 | Rigless Australia - 1 | J.20.062696 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-07-27 | 2020-07-26 |  | 2020-07-27 | 2020-07-28 23:59 |  | 2020-07-28 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:28 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.23 | Costa Central 1-Stage 3-2in HSD | SANTOS LIMITED | Costa Central 1 | Rigless Australia - 1 | J.20.062695 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-08-10 06:00 | 2020-07-22 |  | 2020-08-10 06:00 | 2020-08-13 05:59 |  | 2020-08-13 05:59 | Moomba WL | ymoradi2 | 2022-10-03 10:28 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.16 | Bagundi 7 -2" HSD | SANTOS LIMITED | Bagundi 7 | Rigless Australia - 1 | J.20.062694 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress | 2020-07-08 | 2020-07-07 |  | 2020-07-08 | 2020-07-10 23:59 |  | 2020-07-10 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:28 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.13 | Roti North 2- 2" HSD | SANTOS LIMITED | ROTI NORTH 2 (APP A) GAS | Rigless Australia - 1 | J.20.062691 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress | 2020-07-03 | 2020-07-02 |  | 2020-07-03 | 2020-07-06 23:59 |  | 2020-07-06 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:27 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.21 | Toolachee 55- 2in HSD Perforation | SANTOS LIMITED | Toolachee 55 | Rigless Australia - 1 | J.20.062668 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress | 2020-07-18 | 2020-07-17 |  | 2020-07-18 | 2020-07-20 23:59 |  | 2020-07-20 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.27 | Vega-2_Link 2 1/8" perforation | SANTOS LIMITED | Vega 2 | Rigless Australia - 1 | J.20.062658 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-07-29 10:00 | 2020-07-29 |  | 2020-07-29 10:00 | 2020-07-31 23:59 |  | 2020-07-31 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.26 | Dullingari 16 | SANTOS LIMITED | Dullingari 17 | Rigless Australia - 1 | J.20.062657 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-08-04 | 2020-07-27 |  | 2020-08-04 | 2020-08-06 23:59 |  | 2020-08-06 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.07 | Seccante 7 | SANTOS LIMITED | Well #6 | Rigless Australia - 1 | J.20.062656 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-07-10 11:00 | 2020-07-10 |  | 2020-07-10 12:00 | 2020-07-19 13:00 |  | 2020-07-19 12:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.12 | Moomba 256 | SANTOS LIMITED | Moomba 256 | Rigless Australia - 1 | J.20.062650 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-06-22 16:00 | 2020-06-22 |  | 2020-06-22 16:00 | 2020-06-24 16:00 |  | 2020-06-24 16:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:23 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 5730.99 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.06 | Napowie 3 | SANTOS LIMITED | Napowie 3 | Rigless Australia - 1 | J.20.062624 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-06-12 06:00 | 2020-06-12 |  | 2020-06-12 06:00 | 2020-06-14 06:00 |  | 2020-06-14 06:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 9551.66 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.01 | Moomba 251 3 3/8 HSD and Packer Tailpipe | SANTOS LIMITED | Well #12 | Rigless Australia - 1 | J.20.062613 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-07-08 15:00 | 2020-07-06 |  | 2020-07-08 | 2020-07-18 |  | 2020-07-15 23:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:18 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.17 | Dullingari 42- 1.56" HSD Perfo | SANTOS LIMITED | Dullingari 42 | Rigless Australia - 1 | J.20.062612 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress | 2020-07-10 | 2020-07-09 |  | 2020-07-10 | 2020-07-11 23:59 |  | 2020-07-11 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:18 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.18 | Vega-7_Plug Setting | SANTOS LIMITED | VEGA 7 | Rigless Australia - 1 | J.20.062609 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-07-11 | 2020-07-10 |  | 2020-07-11 | 2020-07-12 23:59 |  | 2020-07-12 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.19 | Pndrinie 19 1.56 HSD Perf | SANTOS LIMITED | Pondrinie 19 | Rigless Australia - 1 | J.20.062608 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress | 2020-07-13 | 2020-07-12 |  | 2020-07-13 | 2020-07-22 |  | 2020-07-26 00:01 | Moomba WL | ymoradi2 | 2022-10-03 10:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.05 | A.1001569.05.05 | BigLake102RiglessTubingCutter | SANTOS LIMITED | Well #10 | Rigless Australia - 1 | J.20.062606 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-07-19 14:00 | 2020-07-17 14:00 |  | 2020-07-19 15:00 | 2020-07-21 15:00 |  | 2020-07-21 14:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:17 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.24 | Lepard 3 | SANTOS LIMITED | Lepard 3 | Rigless Australia - 1 | J.20.062749 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-05-30 18:00 | 2020-05-29 |  | 2020-05-30 18:00 | 2020-06-04 12:00 |  | 2020-06-04 12:00 | Moomba WL | AGamero | 2022-10-03 10:35 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 3183.89 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.22 | Coonatie 8 | SANTOS LIMITED | Coonatie 8 | Rigless Australia - 1 | J.20.062726 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-05-19 23:00 | 2020-05-19 |  | 2020-05-20 | 2020-05-22 |  | 2020-05-21 23:00 | Moomba WL | AGamero | 2022-10-03 10:31 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.26 | Moomba 248 | SANTOS LIMITED | MOOMBA 248 | Rigless Australia - 1 | J.20.062693 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-06-06 06:00 | 2020-06-05 |  | 2020-06-06 06:00 | 2020-06-10 06:00 |  | 2020-06-10 06:00 | Moomba WL | AGamero | 2022-10-03 10:28 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 23550.57 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.23 | Juno 8 | SANTOS LIMITED | Juno 8 | Rigless Australia - 1 | J.20.062692 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-05-29 06:00 | 2020-05-25 |  | 2020-05-29 06:00 | 2020-05-31 06:00 |  | 2020-05-31 06:00 | Moomba WL | AGamero | 2022-10-03 10:27 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.20 | Gooranie 14 | SANTOS LIMITED | GOORANIE 14 | Rigless Australia - 1 | J.20.062690 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-05-16 | 2020-05-15 |  | 2020-05-16 | 2020-05-18 |  | 2020-05-18 | Moomba WL | AGamero | 2022-10-03 10:27 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 7428.72 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.27 | Moorari 19 | SANTOS LIMITED | Moorari 19 | Rigless Australia - 1 | J.20.062614 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2020-03-24 | 2020-03-23 |  | 2020-03-24 | 2020-03-26 |  | 2020-03-26 | Moomba WL | KKeese | 2022-10-03 10:18 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.21 | Dullingari 42 | SANTOS LIMITED | Dullingari 42 | Rigless Australia - 1 | J.20.062611 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-05-22 | 2020-05-21 |  | 2020-05-22 | 2020-05-24 |  | 2020-05-24 | Moomba WL | AGamero | 2022-10-03 10:18 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 7428.72 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.25 | Toolachee 1 | SANTOS LIMITED | Toolachee 5 | Rigless Australia - 1 | J.20.062607 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-06-05 10:00 | 2020-06-05 06:00 |  | 2020-06-05 10:00 | 2020-06-07 10:00 |  | 2020-06-07 10:00 | Moomba WL | AGamero | 2022-10-03 10:18 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.18 | Gooranie 17 | SANTOS LIMITED | GOORANIE 17 | Rigless Australia - 1 | J.20.062605 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-07-01 08:00 | 2020-05-10 |  | 2020-07-03 | 2020-07-05 |  | 2020-07-04 04:00 | Moomba WL | AGamero | 2022-10-03 10:17 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.17 | Moomba 253 | SANTOS LIMITED | Moomba 253 | Rigless Australia - 1 | J.20.062604 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-05-08 16:00 | 2020-05-07 |  | 2020-05-09 12:00 | 2020-05-11 12:00 |  | 2020-05-10 16:00 | Moomba WL | AGamero | 2022-10-03 10:17 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.16 | Moomba 247 | SANTOS LIMITED | MOOMBA 247 | Rigless Australia - 1 | J.20.062603 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-07-02 04:00 | 2020-05-04 |  | 2020-07-03 | 2020-07-05 |  | 2020-07-04 04:00 | Moomba WL | AGamero | 2022-10-03 10:17 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 6778.95 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.14 | Moomba 106 | SANTOS LIMITED | Moomba 106 | Rigless Australia - 1 | J.20.062574 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-04-28 |  | 2020-04-29 | 2020-05-01 |  |  | Moomba WL | AGamero | 2022-10-03 10:13 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.13 | Namur 19 | SANTOS LIMITED | NAMUR 19 GAS PA (DEV J) DXCF | Rigless Australia - 1 | J.20.062573 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Design Completed | In Progress |  | 2020-04-20 |  | 2020-04-21 06:00 | 2020-04-24 06:00 |  |  | Moomba WL | AGamero | 2022-10-03 10:13 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 11551.14 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.19 | Gooranie 15 | SANTOS LIMITED | GOORANIE 15 | Rigless Australia - 1 | J.20.062557 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-05-14 |  | 2020-05-15 | 2020-05-17 |  |  | Moomba WL | AGamero | 2022-10-03 10:12 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 7428.72 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.09 | TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062556 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-09 |  | 2020-04-09 | 2020-04-11 |  |  | Moomba WL | AGamero | 2022-10-03 10:11 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.15 | Moomba 249 | SANTOS LIMITED | MOOMBA 249 | Rigless Australia - 1 | J.20.062510 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-04-29 |  | 2020-04-30 | 2020-05-02 |  |  | Moomba WL | AGamero | 2022-10-03 10:06 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 6778.95 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.04 | TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062509 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-11 |  | 2020-03-11 | 2020-03-13 |  |  | Moomba WL | AGamero | 2022-10-03 10:06 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.11 | Moomba 34 | SANTOS LIMITED | Moomba 34 | Rigless Australia - 1 | J.20.062492 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-04-15 09:00 |  | 2020-04-15 10:00 | 2020-04-17 10:00 |  |  | Moomba WL | AGamero | 2022-10-03 10:04 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 14550.36 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.07 | Seccante 7 | SANTOS LIMITED | Seccante 7 | Rigless Australia - 1 | J.20.062491 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-04-01 |  | 2020-04-01 12:00 | 2020-04-10 12:00 |  |  | Moomba WL | AGamero | 2022-10-03 10:04 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 7428.72 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.10 | TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062452 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-12 |  | 2020-04-12 | 2020-04-14 |  |  | Moomba WL | AGamero | 2022-10-03 09:51 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.08 | TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062451 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-06 |  | 2020-04-06 | 2020-04-07 23:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:51 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.06 | Moorari 20 | SANTOS LIMITED | Moorari 20 | Rigless Australia - 1 | J.20.062450 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2020-03-26 |  | 2020-03-26 | 2020-03-28 |  |  | Moomba WL | AGamero | 2022-10-03 09:51 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.05 | BigLake102RiglessTubingCutter | SANTOS LIMITED | Big Lake 102 | Rigless Australia - 1 | J.20.062422 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-03-10 14:00 |  | 2020-03-12 15:00 | 2020-03-14 15:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:46 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.02 | Big Lake 102- Tubing Cutter-TCP Correlation | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062421 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-02-27 |  | 2020-02-27 | 2020-02-29 |  |  | Moomba WL | AGamero | 2022-10-03 09:46 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.03 | big Lake 6-2 1/8" Link perfo | SANTOS LIMITED | Big Lake 6 | Rigless Australia - 1 | J.20.062412 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-03-01 |  | 2020-03-05 14:00 | 2020-03-07 14:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:45 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 7428.72 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.01 | Moomba 251 3 3/8 HSD and Packer Tailpipe | SANTOS LIMITED | Moomba 251 | Rigless Australia - 1 |  | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-02-28 |  | 2020-02-28 | 2020-03-09 |  |  | Moomba WL | AGamero | 2022-09-03 07:59 | walfaro |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.03 | A.1001569.03.12 | Munkarie 1 | SANTOS LIMITED | Munkarie Dev A | Rigless Australia - 1 |  | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Design Completed | In Progress | 2020-04-19 05:00 | 2020-04-19 |  | 2020-04-20 | 2020-04-22 |  | 2020-04-21 14:30 | Moomba WL | AGamero | 2022-09-03 07:59 | walfaro |  | No |  |  |  |  | Rob Twigg |  | 17192.98 |  |  | L0 - No RO |  | 58.3 | 0 | 0 | 25 | 25 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.02 | A.1001569.02.01 | Coolah-7_Plug-setting | SANTOS LIMITED | COOLAH 7 | Rigless Australia - 1 | J.19.060451 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2019-09-21 07:47 | 2019-09-19 09:00 |  | 2019-09-19 09:15 | 2019-09-20 06:00 |  | 2019-09-22 07:49 | Moomba WL | ymoradi2 | 2022-10-03 10:09 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.33 | Wackett 21 | SANTOS LIMITED | WACKETT 21 | Rigless Australia - 1 | J.19.060458 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2019-11-19 | 2019-11-17 |  | 2019-11-19 | 2019-11-21 |  | 2019-11-21 | Moomba WL | KKeese | 2022-10-03 10:17 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.28 | Well 23 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060457 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-09 | 2019-12-08 |  | 2019-12-08 | 2019-12-09 |  | 2019-10-10 | Moomba WL | AGamero | 2022-10-03 10:17 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.01 | Coolah 5_2"Perfo | SANTOS LIMITED | Coolah 5 | Rigless Australia - 1 | J.19.060456 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress | 2019-09-18 | 2019-09-18 |  | 2019-09-18 | 2019-09-21 |  | 2019-09-21 | Moomba WL | KKeese | 2022-10-03 10:17 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.42 | Mudera 21 -2" HSD | SANTOS LIMITED | Mudera 21 | Rigless Australia - 1 | J.20.062592 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-01-25 07:00 | 2020-01-25 |  | 2020-01-25 07:00 | 2020-01-26 |  | 2020-01-26 | Moomba WL | ymoradi2 | 2022-10-03 10:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.03 | Coolah-7_Plug-setting | SANTOS LIMITED | Coolah 7 | Rigless Australia - 1 | J.19.060455 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2019-09-19 11:15 | 2019-09-19 09:00 |  | 2019-09-19 09:15 | 2019-09-19 17:00 |  | 2019-09-19 15:30 | Moomba WL | ymoradi2 | 2022-10-03 10:15 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 32488.63 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.39 | Swan Lake 12 | SANTOS LIMITED | Swan Lake 12 | Rigless Australia - 1 | J.20.062572 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-01-14 10:00 |  | 2020-01-29 12:00 | 2020-02-01 15:00 |  |  | Moomba WL | DParker16 | 2022-10-03 10:13 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.34 | Wackett East 1 NFE A Gas DCF ; Drift & Cement Evaluation Log | SANTOS LIMITED | Wackett East 1 | Rigless Australia - 1 | J.20.062561 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-11-19 06:00 |  | 2020-01-19 18:00 | 2020-01-21 05:00 |  |  | Moomba WL | ymoradi2 | 2022-10-03 10:12 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.15 | Wackett 20-Perfo-2" HSD | SANTOS LIMITED | WACKETT 20 | Rigless Australia - 1 | J.19.060454 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Design Completed | In Progress | 2019-11-08 07:00 | 2019-12-07 06:00 |  | 2019-12-07 07:00 | 2019-12-08 07:00 |  | 2019-11-09 07:00 | Moomba WL | AGamero | 2022-10-03 10:12 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.02 | Coolah 6_2"Perfo | SANTOS LIMITED | COOLAH 6 | Rigless Australia - 1 | J.19.060453 | RPI | PS-WL-Ops | Medium | Confirmed | Prepare - Mob |  | In Progress | In Progress | In Progress | 2019-10-14 18:00 | 2019-10-13 |  | 2019-10-14 18:00 | 2019-10-17 18:00 |  | 2019-10-17 18:00 | Moomba WL | KKeese | 2022-10-03 10:12 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6138.53 |  |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.37 | Cascade 1 | SANTOS LIMITED | Cascade 1 | Rigless Australia - 1 | J.20.062555 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-01-01 14:00 |  | 2020-01-01 17:00 | 2020-01-04 10:00 |  |  | Moomba WL | DParker16 | 2022-10-03 10:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.24 | Well 19 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060452 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-09 | 2019-11-28 |  | 2019-11-28 | 2019-11-29 |  | 2019-10-10 | Moomba WL | AGamero | 2022-10-03 10:11 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.17 | Moomba 247 SCMT | SANTOS LIMITED | MOOMBA 247 | Rigless Australia - 1 | J.19.060450 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2019-11-10 07:00 | 2019-12-11 06:00 |  | 2019-12-14 07:00 | 2019-12-15 07:00 |  | 2019-11-11 07:00 | Moomba WL | AGamero | 2022-10-03 10:09 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.07 | Vega North 2 | SANTOS LIMITED | Vega North 2 | Rigless Australia - 1 | J.19.060449 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2019-11-07 |  | 2019-11-10 | 2019-11-11 |  |  | Moomba WL | AGamero | 2022-10-03 10:09 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.46 | Vega 6 | SANTOS LIMITED | Vega 6 | Rigless Australia - 1 | J.20.062527 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-02-05 10:04 |  | 2020-02-07 06:00 | 2020-02-10 20:00 |  |  | Moomba WL | DParker16 | 2022-10-03 10:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.36 | Mudera 2 | SANTOS LIMITED | Mudera 2 | Rigless Australia - 1 | J.19.060447 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2019-12-26 06:00 |  | 2019-12-27 07:00 | 2019-12-28 07:00 |  |  | Moomba WL | ymoradi2 | 2022-10-03 10:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.32 | Challum West 1 | SANTOS LIMITED | CHALLUM WEST 1 | Rigless Australia - 1 | J.19.060446 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Design Completed | In Progress | 2019-11-01 | 2019-11-01 |  | 2019-11-01 | 2019-11-03 |  | 2019-11-03 | Moomba WL | KKeese | 2022-10-03 10:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.29 | Well 24 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060445 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-09 | 2019-12-10 |  | 2019-12-10 | 2019-12-11 |  | 2019-10-10 | Moomba WL | AGamero | 2022-10-03 10:08 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.21 | Well 16 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060444 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-09 | 2019-11-21 |  | 2019-11-21 | 2019-11-22 |  | 2019-10-10 | Moomba WL | AGamero | 2022-10-03 10:08 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.48 | Cherokee 1 | SANTOS LIMITED | Cherokee 1 | Rigless Australia - 1 | J.20.062508 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-02-10 06:00 |  | 2020-02-11 06:00 | 2020-02-18 18:00 |  |  | Moomba WL | JAnderson60 | 2022-10-03 10:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.05 | Juno 7- 27/8" Perforation | SANTOS LIMITED | JUNO 7 | Rigless Australia - 1 | J.19.060442 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Design Completed | In Progress | 2019-09-29 | 2019-09-29 |  | 2019-09-29 | 2019-09-30 |  | 2019-09-30 | Moomba WL | KKeese | 2022-10-03 10:05 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 8052.63 |  |  | L0 - No RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.44 | Kerna 6- 1 11/16 Link Perfo | SANTOS LIMITED | Kerna 6 | Rigless Australia - 1 | J.20.062490 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-01-29 |  | 2020-02-02 07:00 | 2020-02-04 |  |  | Moomba WL | ymoradi2 | 2022-10-03 10:03 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.43 | Mckinlay 19-Perfo 3 3/8" | SANTOS LIMITED | Mckinlay 19 | Rigless Australia - 1 | J.20.062489 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-01-27 16:00 |  | 2020-01-29 10:00 | 2020-02-06 |  |  | Moomba WL | ymoradi2 | 2022-10-03 10:03 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.38 | Gooranie 12 | SANTOS LIMITED | GOORANIE 12 | Rigless Australia - 1 | J.20.062488 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-01-10 05:39 |  | 2020-01-18 12:09 | 2020-01-20 12:39 |  |  | Moomba WL | DParker16 | 2022-10-03 10:03 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.27 | Well 22 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060440 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-09 | 2019-12-05 |  | 2019-12-05 | 2019-12-06 |  | 2019-10-10 | Moomba WL | AGamero | 2022-10-03 10:03 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.26 | Well 21 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060439 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-09 | 2019-12-03 |  | 2019-12-03 | 2019-12-04 |  | 2019-10-10 | Moomba WL | AGamero | 2022-10-03 10:03 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.08 | Wackett South 1 App A Gas DCF ; Drift & Cement Evaluation Log ; | SANTOS LIMITED | Wackett South 1 | Rigless Australia - 1 | J.19.060438 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-11-21 06:00 |  | 2019-11-21 07:00 | 2019-11-22 07:00 |  |  | Moomba WL | AGamero | 2022-10-03 10:03 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.45 | Post frac perforation at Vega 7 | SANTOS LIMITED | Vega 7 | Rigless Australia - 1 | J.20.062468 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-01-30 |  | 2020-02-01 06:00 | 2020-02-08 06:00 |  |  | Moomba WL | AKharisma | 2022-10-03 09:53 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.30 | Well 25 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060437 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-09 | 2019-12-12 |  | 2019-12-12 | 2019-12-13 |  | 2019-10-10 | Moomba WL | AGamero | 2022-10-03 09:53 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.22 | Well 17 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060436 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-09 | 2019-11-24 |  | 2019-11-24 | 2019-11-25 |  | 2019-10-10 | Moomba WL | AGamero | 2022-10-03 09:53 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.18 | Moomba 248 SCMT | SANTOS LIMITED | MOOMBA 248 | Rigless Australia - 1 | J.19.060435 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2019-11-06 | 2019-12-12 |  | 2019-12-12 | 2019-12-13 |  | 2019-11-07 | Moomba WL | AGamero | 2022-10-03 09:52 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.31 | Juno 5 | SANTOS LIMITED | JUNO 7 | Rigless Australia - 1 | J.19.060433 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | In Progress | Design Completed | In Progress | 2019-11-12 | 2019-10-30 |  | 2019-11-12 | 2019-11-14 |  | 2019-11-14 | Moomba WL | KKeese | 2022-10-03 09:51 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 11621.18 |  |  | L0 - No RO |  | 58.3 | 0 | 0 | 25 | 25 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.16 | Moomba 246 | SANTOS LIMITED | MOOMBA 246 | Rigless Australia - 1 | J.19.060432 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2019-11-11 07:00 | 2019-12-10 06:00 |  | 2019-12-13 07:00 | 2019-12-14 07:00 |  | 2019-11-12 07:00 | Moomba WL | AGamero | 2022-10-03 09:50 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 50 | 27.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.12 | Leghorn 1; Drift & CBL ; | SANTOS LIMITED | LEGHORN 1 | Rigless Australia - 1 | J.19.060431 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2019-11-30 |  | 2019-11-30 | 2019-12-01 |  |  | Moomba WL | AGamero | 2022-10-03 09:50 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.47 | Toltec 1 | SANTOS LIMITED | Toltec 1 | Rigless Australia - 1 | J.20.062441 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-02-12 |  | 2020-02-12 08:00 | 2020-02-14 |  |  | Moomba WL | ymoradi2 | 2022-10-03 09:49 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.40 | Piute 1 Perofration | SANTOS LIMITED | Piute Gas 1 | Rigless Australia - 1 | J.20.062440 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-01-20 12:00 |  | 2020-01-29 14:00 | 2020-01-31 |  |  | Moomba WL | ymoradi2 | 2022-10-03 09:49 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.35 | Moomba-10-Puncher-Cutter | SANTOS LIMITED | Moomba 10 | Rigless Australia - 1 | J.19.060430 | RPI | PS-WL-Ops | High | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2019-12-20 06:00 |  | 2019-12-21 07:00 | 2019-12-22 19:41 |  |  | Moomba WL | ymoradi2 | 2022-10-03 09:49 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.19 | Moomba 249 SCMT | SANTOS LIMITED | MOOMBA 249 | Rigless Australia - 1 | J.19.060429 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2019-11-08 07:00 | 2019-12-13 06:00 |  | 2019-12-17 07:00 | 2019-12-18 07:00 |  | 2019-11-09 07:00 | Moomba WL | AGamero | 2022-10-03 09:49 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.14 | Wacket 21-2" HSD Perforation | SANTOS LIMITED | WACKETT 21 | Rigless Australia - 1 | J.19.060428 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2019-12-05 |  | 2019-12-05 | 2019-12-06 |  |  | Moomba WL | AGamero | 2022-10-03 09:49 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.13 | Tartulla 9-SCMT | SANTOS LIMITED | TARTULLA 9 | Rigless Australia - 1 | J.19.060427 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-01 06:00 |  | 2019-12-01 07:00 | 2019-12-02 07:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:49 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.11 | Vega-6_2 7/8" perforation | SANTOS LIMITED | Vega 6 | Rigless Australia - 1 | J.19.060426 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2019-11-27 06:00 |  | 2019-11-27 08:00 | 2019-11-30 15:09 |  |  | Moomba WL | AGamero | 2022-10-03 09:49 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.41 | Moomba 236 SCMT | SANTOS LIMITED | Moomba 236 | Rigless Australia - 1 | J.20.062420 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-22 |  | 2020-01-23 | 2020-01-25 |  |  | Moomba WL | ymoradi2 | 2022-10-03 09:46 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.23 | Well 18 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060425 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-09 | 2019-11-26 |  | 2019-11-26 | 2019-11-27 |  | 2019-10-10 | Moomba WL | AGamero | 2022-10-03 09:46 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.10 | Juno-7_2 7/8" HSD | SANTOS LIMITED | Juno 7 | Rigless Australia - 1 | J.19.060424 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2019-11-20 09:00 |  | 2019-11-21 10:00 | 2019-11-22 10:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:45 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.09 | Wacket 19-SCMT | SANTOS LIMITED | WACKETT 19 | Rigless Australia - 1 | J.19.060423 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-11-20 |  | 2019-11-20 11:00 | 2019-11-22 04:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:45 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.25 | Well 20 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060422 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-09 | 2019-12-01 |  | 2019-12-01 | 2019-12-02 |  | 2019-10-10 | Moomba WL | AGamero | 2022-10-03 09:44 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.06 | Coolah 8 | SANTOS LIMITED | COOLAH 8 | Rigless Australia - 1 | J.19.060421 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2019-10-11 14:00 | 2019-10-09 |  | 2019-10-11 14:00 | 2019-10-13 14:00 |  | 2019-10-13 14:00 | Moomba WL | AGamero | 2022-10-03 09:44 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 1620.57 |  |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.04 | Costa Central 1 | SANTOS LIMITED | COSTA CENTRAL 1 | Rigless Australia - 1 | J.19.060420 | RPI | PS-WL-Ops | Medium | Confirmed | Prepare - Mob |  | In Progress | Not Started | In Progress | 2019-10-07 15:00 | 2019-10-07 12:00 |  | 2019-10-07 15:00 | 2019-10-08 15:00 |  | 2019-10-08 15:00 | Moomba WL | KKeese | 2022-10-03 09:44 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001569 | O.1001569.01 | A.1001569.01.20 | Jack Lake 2 | SANTOS LIMITED | Jack Lake Dev A | Rigless Australia - 1 |  | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-01-07 14:00 |  | 2020-01-16 15:00 | 2020-01-17 15:00 |  |  | Moomba WL | AGamero | 2022-09-03 07:59 | walfaro |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.13 | A.1001568.13.09 | Packer Set (Bolah 8,9,10 & Moomba 271) | SANTOS LIMITED | BOLAH 8, BOLAH 9, BOLAH 10, MOOMBA 271, BARROLKA 25, BARROLKA 26, MOOMBA 261 | Rigless Australia - 1 | J.22.109946 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | Design Completed | 2022-09-22 09:30 | 2022-06-25 09:30 |  | 2022-06-25 11:00 | 2022-06-28 10:59 |  | 2022-09-25 09:29 | Moomba WL | JMoraes2 | 2022-10-03 12:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 5730.99 | 1 |  | L0 - No RO |  | 75 | 16.7 | 0 | 75 | 50 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.13 | A.1001568.13.08 | Dullingari 18 | SANTOS LIMITED | Dullingari 18, MOON NORTH WEST 1 | Rigless Australia - 1 | J.22.109933 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-08-31 19:00 | 2022-06-03 |  | 2022-06-04 | 2022-06-06 23:59 |  | 2022-09-03 18:59 | Moomba WL | ADuong4 | 2022-10-03 12:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 34360.49 | 6 |  |  |  | 66.7 | 83.3 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.13 | A.1001568.13.07 | Moomba 226/ Moomba 227 | SANTOS LIMITED | MOOMBA 226, MOOMBA 227, BIG LAKE 77, MOOMBA 271, MOOMBA 272 | Rigless Australia - 1 | J.22.109824 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-08-26 07:00 | 2022-08-26 03:00 |  | 2022-08-26 07:00 | 2022-08-29 18:59 |  | 2022-08-29 18:59 | Moomba WL | ADuong4 | 2022-10-03 12:13 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 5730.99 | 1 |  | L0 - No RO |  | 66.7 | 100 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.13 | A.1001568.13.06 | Pelican 14 Set Packer | SANTOS LIMITED | Pelican 14 | Rigless Australia - 1 | J.22.109806 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-07-29 08:30 | 2022-05-01 |  | 2022-05-01 13:30 | 2022-05-04 13:29 |  | 2022-08-01 08:29 | Moomba WL | zauzar | 2022-10-03 12:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 8204.55 | 1 |  |  |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001568 | O.1001568.13 | A.1001568.13.05 | Post Frac Perf Campaign | SANTOS LIMITED | Kudrieke 3, Meranji 24, Meranji 27 | Rigless Australia - 1 | J.22.109799 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-07-15 07:00 | 2022-04-17 08:00 |  | 2022-04-17 12:00 | 2022-04-24 23:59 |  | 2022-07-22 18:59 | Moomba WL | DKitney | 2022-10-03 12:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 2473.56 | 18 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.13 | A.1001568.13.04 | Link Campaign | SANTOS LIMITED | Big Lake 99, Big Lake 138, Pira 4, Tellus 1 | Rigless Australia - 1 | J.22.109796 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-07-10 05:00 | 2022-04-12 06:00 |  | 2022-04-12 10:00 | 2022-04-19 23:59 |  | 2022-07-17 18:59 | Moomba WL | DKitney | 2022-10-03 12:10 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 21090.06 | 20 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.13 | A.1001568.13.03 | Big Lake 119- PFP/Packer | SANTOS LIMITED | Big Lake 119 | Rigless Australia - 1 | J.22.109790 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-07-07 03:00 | 2022-04-09 07:00 |  | 2022-04-09 08:00 | 2022-04-11 18:00 |  | 2022-07-09 13:00 | Moomba WL | DKitney | 2022-10-03 12:10 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 18317.05 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.13 | A.1001568.13.02 | Kappa 2- Packer Set | SANTOS LIMITED | Kappa 2 | Rigless Australia - 1 | J.22.109787 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-07-04 06:00 | 2022-04-06 10:00 |  | 2022-04-06 11:00 | 2022-04-07 14:00 |  | 2022-07-05 09:00 | Moomba WL | DKitney | 2022-10-03 12:09 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 5730.99 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.13 | A.1001568.13.01 | Pelican 14- SCMT | SANTOS LIMITED | Pelican 14 | Rigless Australia - 1 | J.22.109763 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-07-01 22:00 | 2022-04-04 08:00 |  | 2022-04-04 09:00 | 2022-04-09 20:59 |  | 2022-07-07 09:59 | Moomba WL | zauzar | 2022-10-03 12:07 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  |  |  | 83.3 | 16.7 | 0 | 75 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.27 | Moomba 195 Packer set | SANTOS LIMITED | Moomba 195 | Rigless Australia - 1 | J.22.109767 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-28 22:00 | 2022-03-28 22:00 |  | 2022-03-28 22:00 | 2022-03-31 14:59 |  | 2022-03-31 14:59 | Moomba WL | zauzar | 2022-10-03 12:07 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.26 | Big lake 96 1-11/16 Link Gun | SANTOS LIMITED | Big Lake 96 | Rigless Australia - 1 | J.22.109766 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-27 22:00 | 2022-03-27 22:00 |  | 2022-03-27 22:00 | 2022-03-30 14:59 |  | 2022-03-30 14:59 | Moomba WL | zauzar | 2022-10-03 12:07 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 4 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.25 | Moomba 244_1-11/16 Link Gun | SANTOS LIMITED | MOOMBA 244 | Rigless Australia - 1 | J.22.109764 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-23 06:00 | 2022-03-23 06:00 |  | 2022-03-23 06:00 | 2022-03-25 23:59 |  | 2022-03-25 23:59 | Moomba WL | zauzar | 2022-10-03 12:07 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 19 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.24 | Big Lake 97/Moomba North 1 | SANTOS LIMITED | Big Lake 97, Moomba 197, Moomba North 1 | Rigless Australia - 1 | J.22.109760 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-18 12:00 | 2022-03-17 |  | 2022-03-18 12:00 | 2022-03-23 23:59 |  | 2022-03-23 23:59 | Moomba WL | ADuong4 | 2022-10-03 12:07 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.23 | Moomba 151 | SANTOS LIMITED | Moomba 151 | Rigless Australia - 1 | J.22.109759 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-16 12:00 | 2022-03-15 |  | 2022-03-16 12:00 | 2022-03-20 23:59 |  | 2022-03-20 23:59 | Moomba WL | ADuong4 | 2022-10-03 12:07 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.22 | Correa 1/Meranji 15/Toolachee 29 | SANTOS LIMITED | Meranji 15, Correa 1, Toolachee 29, Hector South East 1 | Rigless Australia - 1 | J.22.109757 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-10 12:00 | 2022-03-09 |  | 2022-03-10 12:00 | 2022-03-14 23:59 |  | 2022-03-14 23:59 | Moomba WL | ADuong4 | 2022-10-03 12:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.21 | Beckler 2/Della 5A | SANTOS LIMITED | Beckler 2, Della 5 | Rigless Australia - 1 | J.22.109728 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-02 | 2022-03-01 |  | 2022-03-02 | 2022-03-05 23:59 |  | 2022-03-05 23:59 | Moomba WL | ADuong4 | 2022-10-03 12:04 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 8807.02 | 16 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.20 | Big Lake 124, Woolkina 3, Moorari 23 | SANTOS LIMITED | Big Lake 124, WOOLKINA 003, Moorari 23, Kappa 1 | Rigless Australia - 1 | J.22.109694 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-02-17 07:00 | 2022-02-14 |  | 2022-02-17 07:00 | 2022-02-19 23:59 |  | 2022-02-19 23:59 | Moomba WL | ymoradi2 | 2022-10-03 12:00 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.19 | Moorari 22 Packer set | SANTOS LIMITED | Moorari 22 | Rigless Australia - 1 | J.22.109628 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-02-14 07:00 | 2022-02-11 |  | 2022-02-14 07:00 | 2022-02-16 23:59 |  | 2022-02-16 23:59 | Moomba WL | zauzar | 2022-10-03 11:54 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.18 | Moorari 21 Packer set | SANTOS LIMITED | Moorari 21 | Rigless Australia - 1 | J.22.109627 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-02-09 09:00 | 2022-02-09 08:00 |  | 2022-02-09 09:00 | 2022-02-11 23:59 |  | 2022-02-11 23:59 | Moomba WL | zauzar | 2022-10-03 11:54 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.17 | Moorari 23/ Woolkina 3- Stage 1 FRAC | SANTOS LIMITED | Moorari 23, WOOLKINA 003, Moorari 6 | Rigless Australia - 1 | J.22.109625 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-21 12:00 | 2022-01-21 10:00 |  | 2022-01-21 12:00 | 2022-01-23 23:59 |  | 2022-01-23 23:59 | Moomba WL | DKitney | 2022-10-03 11:54 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 5820.14 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.16 | Moomba 91- Perf | SANTOS LIMITED | Moomba 91 | Rigless Australia - 1 | J.22.109621 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-21 12:00 | 2022-01-20 09:00 |  | 2022-01-21 12:00 | 2022-01-22 12:00 |  | 2022-01-22 12:00 | Moomba WL | DKitney | 2022-10-03 11:54 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 10205.31 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.15 | Tirrawarra South 1- Perf | SANTOS LIMITED | Tirrawarra South 1 | Rigless Australia - 1 | J.22.109617 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-07 12:00 | 2022-01-07 09:00 |  | 2022-01-07 12:00 | 2022-01-08 12:00 |  | 2022-01-08 12:00 | Moomba WL | DKitney | 2022-10-03 11:54 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  |  |  | 83.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.14 | Koree South 1- Perf | SANTOS LIMITED | Koree South 1 | Rigless Australia - 1 | J.22.109616 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-05 12:00 | 2022-01-05 09:00 |  | 2022-01-05 12:00 | 2022-01-06 12:00 |  | 2022-01-06 12:00 | Moomba WL | DKitney | 2022-10-03 11:53 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6138.53 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.13 | Moorari 21/22- SCMT | SANTOS LIMITED | Moorari 21, Moorari 22 | Rigless Australia - 1 | J.22.109615 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-01-02 08:00 | 2022-01-02 |  | 2022-01-02 08:00 | 2022-01-04 08:00 |  | 2022-01-04 08:00 | Moomba WL | DKitney | 2022-10-03 11:53 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 9680.92 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.11 | Tirrawarra 88 | SANTOS LIMITED | Tirrawarra 88 | Rigless Australia - 1 | J.21.108808 | RPI | PS-WL-NO | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-24 | 2021-12-23 |  | 2021-12-24 | 2021-12-26 23:59 |  | 2021-12-26 23:59 | Moomba WL | KKeese | 2022-10-03 11:53 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 19441.2 | 2 |  |  |  | 91.7 | 66.7 | 100 | 75 | 80 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.10 | Kappa 1 | SANTOS LIMITED | KAPPA 1 | Rigless Australia - 1 | J.21.108807 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Not Required | In Progress | 2021-12-21 | 2021-12-21 |  | 2021-12-21 | 2021-12-23 23:59 |  | 2021-12-23 23:59 | Moomba WL | KKeese | 2022-10-03 11:53 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 19441.2 | 2 |  | L0 - No RO |  | 83.3 | 50 | 0 | 0 | 40 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.08 | SWQ-420H1Nov | SANTOS LIMITED | Vega 4, Mt Howitt 3 DW1, Kaiden 1, Mt Howitt 2, Genoa 3, Roti 3, Karmona 4, Kurunda 4, Beckler 7, DULLINGARI NORTH 23, Epsilon 6 | Rigless Australia - 1 | J.21.108781 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-08 | 2021-11-07 | 2021-11-07 | 2021-11-08 | 2021-11-10 23:59 | 2021-11-11 | 2021-11-10 23:59 | Moomba WL | ymoradi2 | 2022-10-03 11:41 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 15629.06 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.07 | Juno 3 | SANTOS LIMITED | Juno 3 | Rigless Australia - 1 | J.21.108778 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-11-02 | 2021-11-01 | 2021-11-01 | 2021-11-02 | 2021-11-04 23:59 | 2021-11-05 | 2021-11-04 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 11:40 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 15629.06 | 1 |  |  |  | 83.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.06 | Perf | SANTOS LIMITED | JUNO 5 | Rigless Australia - 1 | J.21.108772 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-11-02 | 2021-11-01 09:00 | 2021-11-02 | 2021-11-02 | 2021-11-03 23:59 | 2021-11-04 | 2021-11-03 23:59 | Moomba WL | DKitney | 2022-10-03 11:40 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.05 | Juno 4 | SANTOS LIMITED | JUNO 5 | Rigless Australia - 1 | J.21.108771 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-10-31 | 2021-10-30 09:00 | 2021-10-31 | 2021-10-31 | 2021-11-01 23:59 | 2021-11-02 | 2021-11-01 23:59 | Moomba WL | DKitney | 2022-10-03 11:40 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.04 | Vega 4 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108770 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | In Progress | In Progress | 2021-10-31 | 2021-10-30 09:00 | 2021-10-31 | 2021-10-31 | 2021-11-01 23:59 | 2021-11-02 | 2021-11-01 23:59 | Moomba WL | DKitney | 2022-10-03 11:40 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 58.3 | 16.7 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.03 | Juno 4 | SANTOS LIMITED | Juno 4 | Rigless Australia - 1 | J.21.108769 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-31 08:00 | 2021-10-30 11:00 | 2021-10-31 | 2021-10-31 08:00 | 2021-11-02 07:59 | 2021-11-03 | 2021-11-02 07:59 | Moomba WL | DKitney | 2022-10-03 11:40 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 23178.69 | 1 |  |  |  | 83.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.02 | Challum 7 | SANTOS LIMITED | Challum 7 | Rigless Australia - 1 | J.21.108768 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-27 11:00 | 2021-10-27 09:00 | 2021-10-27 11:00 | 2021-10-27 11:00 | 2021-10-29 10:59 | 2021-10-29 11:00 | 2021-10-29 10:59 | Moomba WL | DKitney | 2022-10-03 11:39 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.01 | Juno 5- 2in PERF | SANTOS LIMITED | Juno 5 | Rigless Australia - 1 | J.21.108766 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-27 | 2021-10-26 09:00 | 2021-10-27 | 2021-10-27 | 2021-10-28 23:59 | 2021-10-29 | 2021-10-28 23:59 | Moomba WL | DKitney | 2022-10-03 11:39 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.12 | Moomba 35 | SANTOS LIMITED | Moomba | Rigless Australia - 1 |  | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-12-23 |  | 2021-12-24 | 2021-12-26 23:59 |  |  | Moomba WL | KKeese | 2021-12-25 11:43 | KKeese |  | No |  |  |  |  | Rob Twigg |  | 19441.2 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.12 | A.1001568.12.09 | Moomba 41 | SANTOS LIMITED | Moomba | Rigless Australia - 1 |  | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-12-12 |  | 2021-12-12 | 2021-12-14 23:59 |  |  | Moomba WL | KKeese | 2021-12-14 11:19 | KKeese |  | No |  |  |  |  | Rob Twigg |  | 19441.2 | 4 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.173 | Tirrawarra 96, 97, 98 (Perf/Packer) | SANTOS LIMITED | Tirrawarra 97, Tirrawarra 96, Tirrawarra 98 | Rigless Australia - 1 | J.22.109941 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-06-16 09:00 | 2022-06-15 10:00 |  | 2022-06-16 09:00 | 2022-06-19 08:59 |  | 2022-06-19 08:59 | Moomba WL | JMoraes2 | 2022-10-03 12:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 9680.92 | 1 |  |  |  | 75 | 33.3 | 0 | 50 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.172 | Meranji 19 Perf | SANTOS LIMITED | Meranji 19 | Rigless Australia - 1 | J.22.109808 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-05-10 08:00 | 2022-05-03 |  | 2022-05-10 08:00 | 2022-05-12 07:59 |  | 2022-05-12 07:59 | Moomba WL | zauzar | 2022-10-03 12:12 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 66.7 | 83.3 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.171 | Well # 161 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109693 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-07-01 23:00 | 2022-07-02 |  | 2022-07-02 | 2022-07-04 23:59 |  | 2022-07-05 00:59 | Moomba WL | KKeese | 2022-10-03 12:00 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.170 | Well # 160 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109692 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-28 23:00 | 2022-06-29 |  | 2022-06-29 | 2022-07-01 23:59 |  | 2022-07-02 00:59 | Moomba WL | KKeese | 2022-10-03 12:00 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.169 | Well # 159 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109691 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-25 23:00 | 2022-06-26 |  | 2022-06-26 | 2022-06-28 23:59 |  | 2022-06-29 00:59 | Moomba WL | KKeese | 2022-10-03 12:00 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.168 | Well # 158 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109690 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-22 23:00 | 2022-06-23 |  | 2022-06-23 | 2022-06-25 23:59 |  | 2022-06-26 00:59 | Moomba WL | KKeese | 2022-10-03 12:00 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.167 | Well # 157 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109689 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-19 23:00 | 2022-06-20 |  | 2022-06-20 | 2022-06-22 23:59 |  | 2022-06-23 00:59 | Moomba WL | KKeese | 2022-10-03 12:00 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.166 | Well # 156 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109688 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-16 23:00 | 2022-06-17 |  | 2022-06-17 | 2022-06-19 23:59 |  | 2022-06-20 00:59 | Moomba WL | KKeese | 2022-10-03 12:00 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.165 | Well # 155 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109687 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-13 23:00 | 2022-06-14 |  | 2022-06-14 | 2022-06-16 23:59 |  | 2022-06-17 00:59 | Moomba WL | KKeese | 2022-10-03 12:00 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.164 | Well # 154 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109686 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-10 23:00 | 2022-06-11 |  | 2022-06-11 | 2022-06-13 23:59 |  | 2022-06-14 00:59 | Moomba WL | KKeese | 2022-10-03 11:59 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.163 | Well # 153 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109685 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-07 23:00 | 2022-06-08 |  | 2022-06-08 | 2022-06-10 23:59 |  | 2022-06-11 00:59 | Moomba WL | KKeese | 2022-10-03 11:59 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.162 | Well # 152 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109684 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-04 23:00 | 2022-06-05 |  | 2022-06-05 | 2022-06-07 23:59 |  | 2022-06-08 00:59 | Moomba WL | KKeese | 2022-10-03 11:59 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.161 | Well # 151 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109683 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-06-01 23:00 | 2022-06-02 |  | 2022-06-02 | 2022-06-04 23:59 |  | 2022-06-05 00:59 | Moomba WL | KKeese | 2022-10-03 11:59 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.160 | Well # 150 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109682 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-05-29 23:00 | 2022-05-30 |  | 2022-05-30 | 2022-06-01 23:59 |  | 2022-06-02 00:59 | Moomba WL | KKeese | 2022-10-03 11:59 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.159 | Well # 149 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109681 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-05-26 23:00 | 2022-05-27 |  | 2022-05-27 | 2022-05-29 23:59 |  | 2022-05-30 00:59 | Moomba WL | KKeese | 2022-10-03 11:59 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.158 | Well # 148 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109680 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-05-23 23:00 | 2022-05-24 |  | 2022-05-24 | 2022-05-26 23:59 |  | 2022-05-27 00:59 | Moomba WL | KKeese | 2022-10-03 11:59 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.157 | Well # 147 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109679 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-05-20 23:00 | 2022-05-21 |  | 2022-05-21 | 2022-05-23 23:59 |  | 2022-05-24 00:59 | Moomba WL | KKeese | 2022-10-03 11:59 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.156 | Well # 146 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109678 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-05-17 23:00 | 2022-05-18 |  | 2022-05-18 | 2022-05-20 23:59 |  | 2022-05-21 00:59 | Moomba WL | KKeese | 2022-10-03 11:59 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.155 | SWPT 420 (1-11/16" Links) | SANTOS LIMITED | Pelican 10, Tirrawarra 78, Tirrawarra 85, Moorari 3, Moorari 21, Moorari 22, Moorari 23 | Rigless Australia - 1 | J.22.109677 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-05-15 05:00 | 2022-05-14 16:00 |  | 2022-05-15 06:00 | 2022-05-18 05:59 |  | 2022-05-18 04:59 | Moomba WL | KKeese | 2022-10-03 11:59 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.154 | Tirrawarra 97, 96, 98 (CBL) | SANTOS LIMITED | Tirrawarra 97, Tirrawarra 96, Tirrawarra 98 | Rigless Australia - 1 | J.22.109676 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-05-11 13:00 | 2022-05-11 12:00 |  | 2022-05-11 14:00 | 2022-05-14 13:59 |  | 2022-05-14 12:59 | Moomba WL | KKeese | 2022-10-03 11:59 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 9680.92 | 1 |  |  |  | 83.3 | 50 | 0 | 25 | 47.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.153 | Well # 143 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109675 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-05-08 23:00 | 2022-05-09 |  | 2022-05-09 | 2022-05-11 23:59 |  | 2022-05-12 00:59 | Moomba WL | KKeese | 2022-10-03 11:59 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.152 | Well # 142 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109674 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-05-05 23:00 | 2022-05-06 |  | 2022-05-06 | 2022-05-08 23:59 |  | 2022-05-09 00:59 | Moomba WL | KKeese | 2022-10-03 11:59 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.151 | Well # 141 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109673 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-05-02 23:00 | 2022-05-03 |  | 2022-05-03 | 2022-05-05 23:59 |  | 2022-05-06 00:59 | Moomba WL | KKeese | 2022-10-03 11:58 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.150 | Well # 140 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109672 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-04-29 23:00 | 2022-04-30 |  | 2022-04-30 | 2022-05-02 23:59 |  | 2022-05-03 00:59 | Moomba WL | KKeese | 2022-10-03 11:58 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.149 | Well # 138 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109671 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-04-26 23:00 | 2022-04-27 |  | 2022-04-27 | 2022-04-29 23:59 |  | 2022-04-30 00:59 | Moomba WL | KKeese | 2022-10-03 11:58 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.148 | Well # 137 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109670 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-04-23 23:00 | 2022-04-24 |  | 2022-04-24 | 2022-04-26 23:59 |  | 2022-04-27 00:59 | Moomba WL | KKeese | 2022-10-03 11:58 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.147 | Well # 136 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109669 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-04-20 23:00 | 2022-04-21 |  | 2022-04-21 | 2022-04-23 23:59 |  | 2022-04-24 00:59 | Moomba WL | KKeese | 2022-10-03 11:58 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.146 | Well # 135 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109668 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-04-17 23:00 | 2022-04-18 |  | 2022-04-18 | 2022-04-20 23:59 |  | 2022-04-21 00:59 | Moomba WL | KKeese | 2022-10-03 11:58 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.145 | Well # 134 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109667 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-04-14 23:00 | 2022-04-15 |  | 2022-04-15 | 2022-04-17 23:59 |  | 2022-04-18 00:59 | Moomba WL | KKeese | 2022-10-03 11:58 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.144 | Well # 133 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109666 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-04-11 23:00 | 2022-04-12 |  | 2022-04-12 | 2022-04-14 23:59 |  | 2022-04-15 00:59 | Moomba WL | KKeese | 2022-10-03 11:58 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.143 | Well # 132 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109665 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-04-08 23:00 | 2022-04-09 |  | 2022-04-09 | 2022-04-11 23:59 |  | 2022-04-12 00:59 | Moomba WL | KKeese | 2022-10-03 11:58 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.142 | Well # 131 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109664 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-04-05 23:00 | 2022-04-06 |  | 2022-04-06 | 2022-04-08 23:59 |  | 2022-04-09 00:59 | Moomba WL | KKeese | 2022-10-03 11:58 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.141 | Well # 130 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109663 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-04-04 22:00 | 2022-04-03 |  | 2022-04-03 | 2022-04-05 22:59 |  | 2022-04-05 23:59 | Moomba WL | KKeese | 2022-10-03 11:58 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.140 | Well # 129 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109662 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-04-01 22:00 | 2022-03-31 |  | 2022-03-31 | 2022-04-02 23:59 |  | 2022-04-03 00:59 | Moomba WL | KKeese | 2022-10-03 11:58 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.139 | Well #128 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109588 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-03-27 22:00 | 2022-03-28 |  | 2022-03-28 | 2022-03-30 23:59 |  | 2022-03-31 00:59 | Moomba WL | IWahbi | 2022-10-03 11:48 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.138 | Well #127 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109587 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-03-24 22:00 | 2022-03-25 |  | 2022-03-25 | 2022-03-27 23:59 |  | 2022-03-28 00:59 | Moomba WL | IWahbi | 2022-10-03 11:48 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.137 | Well #126 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109586 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-03-21 22:00 | 2022-03-22 |  | 2022-03-22 | 2022-03-24 23:59 |  | 2022-03-25 00:59 | Moomba WL | IWahbi | 2022-10-03 11:48 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.136 | Well #125 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109585 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-03-18 22:00 | 2022-03-19 |  | 2022-03-19 | 2022-03-21 23:59 |  | 2022-03-21 23:59 | Moomba WL | IWahbi | 2022-10-03 11:48 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.135 | Well #124 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109584 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-03-15 22:00 | 2022-03-16 |  | 2022-03-16 | 2022-03-18 23:59 |  | 2022-03-18 23:59 | Moomba WL | IWahbi | 2022-10-03 11:48 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.134 | Well #123 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109583 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-03-12 22:00 | 2022-03-13 |  | 2022-03-13 | 2022-03-15 23:59 |  | 2022-03-15 23:59 | Moomba WL | IWahbi | 2022-10-03 11:48 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.133 | Well #122 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109582 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-03-09 22:00 | 2022-03-10 |  | 2022-03-10 | 2022-03-12 23:59 |  | 2022-03-12 23:59 | Moomba WL | IWahbi | 2022-10-03 11:48 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.132 | Well #121 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109581 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-03-06 22:00 | 2022-03-07 |  | 2022-03-07 | 2022-03-09 23:59 |  | 2022-03-09 23:59 | Moomba WL | IWahbi | 2022-10-03 11:48 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.131 | Well #120 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109580 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-03-03 22:00 | 2022-03-04 |  | 2022-03-04 | 2022-03-06 23:59 |  | 2022-03-06 23:59 | Moomba WL | IWahbi | 2022-10-03 11:48 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.130 | Well #119 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109579 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-02-28 22:00 | 2022-03-01 |  | 2022-03-01 | 2022-03-03 23:59 |  | 2022-03-03 23:59 | Moomba WL | IWahbi | 2022-10-03 11:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.129 | Well #118 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109578 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-02-25 22:00 | 2022-02-26 |  | 2022-02-26 | 2022-02-28 23:59 |  | 2022-02-28 23:59 | Moomba WL | IWahbi | 2022-10-03 11:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.128 | Well #117 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109577 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-02-22 22:00 | 2022-02-23 |  | 2022-02-23 | 2022-02-25 23:59 |  | 2022-02-25 23:59 | Moomba WL | IWahbi | 2022-10-03 11:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.127 | Well #116 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109576 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-02-19 22:00 | 2022-02-20 |  | 2022-02-20 | 2022-02-22 23:59 |  | 2022-02-22 23:59 | Moomba WL | IWahbi | 2022-10-03 11:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.126 | Well #115 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109575 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-02-16 22:00 | 2022-02-17 |  | 2022-02-17 | 2022-02-19 23:59 |  | 2022-02-19 23:59 | Moomba WL | IWahbi | 2022-10-03 11:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.125 | Well #114 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109574 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-02-13 22:00 | 2022-02-14 |  | 2022-02-14 | 2022-02-16 23:59 |  | 2022-02-16 23:59 | Moomba WL | IWahbi | 2022-10-03 11:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.124 | Well #113 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109573 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-02-10 22:00 | 2022-02-11 |  | 2022-02-11 | 2022-02-13 23:59 |  | 2022-02-13 23:59 | Moomba WL | IWahbi | 2022-10-03 11:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.123 | Well #112 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109572 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-02-07 22:00 | 2022-02-08 |  | 2022-02-08 | 2022-02-10 23:59 |  | 2022-02-10 23:59 | Moomba WL | IWahbi | 2022-10-03 11:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.122 | Well #111 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109571 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-02-04 22:00 | 2022-02-05 |  | 2022-02-05 | 2022-02-07 23:59 |  | 2022-02-07 23:59 | Moomba WL | IWahbi | 2022-10-03 11:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.121 | Well #110 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109570 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-02-01 22:00 | 2022-02-02 | 2022-02-02 01:00 | 2022-02-02 | 2022-02-04 23:59 | 2022-02-05 01:00 | 2022-02-04 23:59 | Moomba WL | IWahbi | 2022-10-03 11:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.120 | Well #109 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109569 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-01-29 22:00 | 2022-01-30 | 2022-01-30 01:00 | 2022-01-30 | 2022-02-01 23:59 | 2022-02-02 01:00 | 2022-02-01 23:59 | Moomba WL | IWahbi | 2022-10-03 11:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.119 | Well #108 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109568 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-01-26 22:00 | 2022-01-27 | 2022-01-27 01:00 | 2022-01-27 | 2022-01-29 23:59 | 2022-01-30 01:00 | 2022-01-29 23:59 | Moomba WL | IWahbi | 2022-10-03 11:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.118 | Well #107 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109567 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-01-23 22:00 | 2022-01-24 | 2022-01-24 01:00 | 2022-01-24 | 2022-01-26 23:59 | 2022-01-27 01:00 | 2022-01-26 23:59 | Moomba WL | IWahbi | 2022-10-03 11:46 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.117 | Well #106 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109566 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-01-20 22:00 | 2022-01-21 | 2022-01-21 01:00 | 2022-01-21 | 2022-01-23 23:59 | 2022-01-24 01:00 | 2022-01-23 23:59 | Moomba WL | IWahbi | 2022-10-03 11:46 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.116 | Well #105 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109565 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-01-17 22:00 | 2022-01-18 | 2022-01-18 01:00 | 2022-01-18 | 2022-01-20 23:59 | 2022-01-21 01:00 | 2022-01-20 23:59 | Moomba WL | IWahbi | 2022-10-03 11:46 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.115 | Well #104 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109564 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-01-14 22:00 | 2022-01-15 | 2022-01-15 01:00 | 2022-01-15 | 2022-01-17 23:59 | 2022-01-18 01:00 | 2022-01-17 23:59 | Moomba WL | IWahbi | 2022-10-03 11:46 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.114 | Well #103 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109563 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-01-11 22:00 | 2022-01-12 | 2022-01-12 01:00 | 2022-01-12 | 2022-01-14 23:59 | 2022-01-15 01:00 | 2022-01-14 23:59 | Moomba WL | IWahbi | 2022-10-03 11:46 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.113 | Well #102 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109562 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-01-08 22:00 | 2022-01-09 | 2022-01-09 01:00 | 2022-01-09 | 2022-01-11 23:59 | 2022-01-12 01:00 | 2022-01-11 23:59 | Moomba WL | IWahbi | 2022-10-03 11:46 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.112 | Well #101 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109561 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-01-05 22:00 | 2022-01-06 | 2022-01-06 01:00 | 2022-01-06 | 2022-01-08 23:59 | 2022-01-09 01:00 | 2022-01-08 23:59 | Moomba WL | IWahbi | 2022-10-03 11:46 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.111 | Well #100 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109560 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2022-01-02 22:00 | 2022-01-03 | 2022-01-03 01:00 | 2022-01-03 | 2022-01-05 23:59 | 2022-01-06 01:00 | 2022-01-05 23:59 | Moomba WL | IWahbi | 2022-10-03 11:46 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.110 | Well #99 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108785 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-12-30 22:00 | 2021-12-31 | 2021-12-31 01:00 | 2021-12-31 | 2022-01-02 23:59 | 2022-01-03 01:00 | 2022-01-02 23:59 | Moomba WL | IWahbi | 2022-10-03 11:46 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.109 | Well #98 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108725 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-12-27 22:00 | 2021-12-28 | 2021-12-28 01:00 | 2021-12-28 | 2021-12-30 23:59 | 2021-12-31 01:00 | 2021-12-30 23:59 | Moomba WL | IWahbi | 2022-10-03 11:33 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.108 | Well #97 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108724 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-12-24 22:00 | 2021-12-25 | 2021-12-25 01:00 | 2021-12-25 | 2021-12-27 23:59 | 2021-12-28 01:00 | 2021-12-27 23:59 | Moomba WL | IWahbi | 2022-10-03 11:32 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.107 | Well #96 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108723 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-12-21 22:00 | 2021-12-22 | 2021-12-22 01:00 | 2021-12-22 | 2021-12-24 23:59 | 2021-12-25 01:00 | 2021-12-25 00:59 | Moomba WL | IWahbi | 2022-10-03 11:32 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.106 | Well #95 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108722 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-12-18 22:00 | 2021-12-19 | 2021-12-19 01:00 | 2021-12-19 | 2021-12-21 23:59 | 2021-12-22 01:00 | 2021-12-22 00:59 | Moomba WL | IWahbi | 2022-10-03 11:32 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.105 | Well #94 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108721 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-12-15 22:00 | 2021-12-16 | 2021-12-16 01:00 | 2021-12-16 | 2021-12-18 23:59 | 2021-12-19 01:00 | 2021-12-18 23:59 | Moomba WL | IWahbi | 2022-10-03 11:32 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.104 | Well #93 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108720 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-12-12 22:00 | 2021-12-13 | 2021-12-13 01:00 | 2021-12-13 | 2021-12-15 23:59 | 2021-12-16 01:00 | 2021-12-16 00:59 | Moomba WL | IWahbi | 2022-10-03 11:32 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.103 | Well #92 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108719 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-12-09 22:00 | 2021-12-10 | 2021-12-10 01:00 | 2021-12-10 | 2021-12-12 23:59 | 2021-12-13 01:00 | 2021-12-13 00:59 | Moomba WL | IWahbi | 2022-10-03 11:32 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.102 | Well #91 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108718 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-12-06 22:00 | 2021-12-07 | 2021-12-07 01:00 | 2021-12-07 | 2021-12-09 23:59 | 2021-12-10 01:00 | 2021-12-09 23:59 | Moomba WL | IWahbi | 2022-10-03 11:32 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.101 | Well #90 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108717 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-12-03 22:00 | 2021-12-04 | 2021-12-04 01:00 | 2021-12-04 | 2021-12-06 23:59 | 2021-12-07 01:00 | 2021-12-07 00:59 | Moomba WL | IWahbi | 2022-10-03 11:32 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.100 | Well #89 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108716 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-11-30 22:00 | 2021-12-01 | 2021-12-01 01:00 | 2021-12-01 | 2021-12-03 23:59 | 2021-12-04 01:00 | 2021-12-04 00:59 | Moomba WL | IWahbi | 2022-10-03 11:32 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.99 | Well #88 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108715 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-11-27 22:00 | 2021-11-28 | 2021-11-28 01:00 | 2021-11-28 | 2021-11-30 23:59 | 2021-12-01 01:00 | 2021-11-30 23:59 | Moomba WL | IWahbi | 2022-10-03 11:32 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.98 | Well #87 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108714 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-11-24 22:00 | 2021-11-25 | 2021-11-25 01:00 | 2021-11-25 | 2021-11-27 23:59 | 2021-11-28 01:00 | 2021-11-28 00:59 | Moomba WL | IWahbi | 2022-10-03 11:32 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.97 | Well #86 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108713 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-11-21 22:00 | 2021-11-22 | 2021-11-22 01:00 | 2021-11-22 | 2021-11-24 23:59 | 2021-11-25 01:00 | 2021-11-25 00:59 | Moomba WL | IWahbi | 2022-10-03 11:31 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.96 | Well #85 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108712 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-11-18 22:00 | 2021-11-19 | 2021-11-19 01:00 | 2021-11-19 | 2021-11-21 23:59 | 2021-11-22 01:00 | 2021-11-21 23:59 | Moomba WL | IWahbi | 2022-10-03 11:31 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.95 | Well #84 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108711 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-11-15 22:00 | 2021-11-16 | 2021-11-16 01:00 | 2021-11-16 | 2021-11-18 23:59 | 2021-11-19 01:00 | 2021-11-19 00:59 | Moomba WL | IWahbi | 2022-10-03 11:31 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.94 | Well #83 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108710 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-11-12 22:00 | 2021-11-13 | 2021-11-13 01:00 | 2021-11-13 | 2021-11-15 23:59 | 2021-11-16 01:00 | 2021-11-16 00:59 | Moomba WL | IWahbi | 2022-10-03 11:31 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.93 | Well #82 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108709 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-11-09 22:00 | 2021-11-10 | 2021-11-10 01:00 | 2021-11-10 | 2021-11-12 23:59 | 2021-11-13 01:00 | 2021-11-12 23:59 | Moomba WL | IWahbi | 2022-10-03 11:31 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.92 | Well #81 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108708 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-11-06 22:00 | 2021-11-07 | 2021-11-07 01:00 | 2021-11-07 | 2021-11-09 23:59 | 2021-11-10 01:00 | 2021-11-10 00:59 | Moomba WL | IWahbi | 2022-10-03 11:31 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.91 | Well #80 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108707 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-11-03 22:00 | 2021-11-04 | 2021-11-04 01:00 | 2021-11-04 | 2021-11-06 23:59 | 2021-11-07 01:00 | 2021-11-07 00:59 | Moomba WL | IWahbi | 2022-10-03 11:31 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.90 | Well #79 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108706 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-10-31 22:00 | 2021-11-01 | 2021-11-01 01:00 | 2021-11-01 | 2021-11-03 23:59 | 2021-11-04 01:00 | 2021-11-03 23:59 | Moomba WL | IWahbi | 2022-10-03 11:31 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.89 | Well #78 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108705 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-10-28 22:00 | 2021-10-29 | 2021-10-29 01:00 | 2021-10-29 | 2021-10-31 23:59 | 2021-11-01 01:00 | 2021-11-01 00:59 | Moomba WL | IWahbi | 2022-10-03 11:31 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.88 | Well #77 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108704 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-10-25 22:00 | 2021-10-26 | 2021-10-26 01:00 | 2021-10-26 | 2021-10-28 23:59 | 2021-10-29 01:00 | 2021-10-29 00:59 | Moomba WL | IWahbi | 2022-10-03 11:31 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.87 | Well #76 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108703 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-10-22 22:00 | 2021-10-23 | 2021-10-23 01:00 | 2021-10-23 | 2021-10-25 23:59 | 2021-10-26 01:00 | 2021-10-25 23:59 | Moomba WL | IWahbi | 2022-10-03 11:31 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.86 | Well #75 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108702 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-10-19 22:00 | 2021-10-20 | 2021-10-20 01:00 | 2021-10-20 | 2021-10-22 23:59 | 2021-10-23 01:00 | 2021-10-23 00:59 | Moomba WL | IWahbi | 2022-10-03 11:30 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.85 | Well #74 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108701 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-10-16 22:00 | 2021-10-17 | 2021-10-17 01:00 | 2021-10-17 | 2021-10-19 23:59 | 2021-10-20 01:00 | 2021-10-20 00:59 | Moomba WL | IWahbi | 2022-10-03 11:30 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.84 | Well #73 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108700 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-10-13 22:00 | 2021-10-14 | 2021-10-14 01:00 | 2021-10-14 | 2021-10-16 23:59 | 2021-10-17 01:00 | 2021-10-16 23:59 | Moomba WL | IWahbi | 2022-10-03 11:30 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.83 | Well #72 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108699 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-10-10 22:00 | 2021-10-11 | 2021-10-11 01:00 | 2021-10-11 | 2021-10-13 23:59 | 2021-10-14 01:00 | 2021-10-14 00:59 | Moomba WL | IWahbi | 2022-10-03 11:30 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.82 | Well #71 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108698 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-10-07 22:00 | 2021-10-08 | 2021-10-08 01:00 | 2021-10-08 | 2021-10-10 23:59 | 2021-10-11 01:00 | 2021-10-11 00:59 | Moomba WL | IWahbi | 2022-10-03 11:30 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.81 | Well #70 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108697 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-10-04 22:00 | 2021-10-05 | 2021-10-05 01:00 | 2021-10-05 | 2021-10-07 23:59 | 2021-10-08 01:00 | 2021-10-07 23:59 | Moomba WL | IWahbi | 2022-10-03 11:30 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.80 | Well #69 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108696 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-09-30 23:00 | 2021-10-01 | 2021-10-01 | 2021-10-01 | 2021-10-04 00:59 | 2021-10-04 01:00 | 2021-10-04 00:59 | Moomba WL | IWahbi | 2022-10-03 11:30 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.79 | Durham Downs North 1 | SANTOS LIMITED | Durham Downs North 1 | Rigless Australia - 1 | J.21.108659 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-22 | 2021-08-21 | 2021-08-22 | 2021-08-22 | 2021-08-24 23:59 | 2021-08-25 | 2021-08-24 23:59 | Moomba WL | KKeese | 2022-10-03 11:27 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 75 | 16.7 | 0 | 0 | 27.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.78 | Daralingie 13- PowerCutter | SANTOS LIMITED | Daralingie 13 | Rigless Australia - 1 | J.21.108654 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-08-03 08:00 | 2021-08-02 09:00 | 2021-08-02 09:00 | 2021-08-02 12:00 | 2021-08-05 11:59 | 2021-08-05 09:00 | 2021-08-06 07:59 | Moomba WL | DKitney | 2022-10-03 11:26 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6686.16 | 0 |  |  |  | 83.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.77 | Tirrawarra 33 | SANTOS LIMITED | TIRRAWARRA 33 | Rigless Australia - 1 | J.21.108643 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | In Progress | In Progress | 2021-07-08 06:00 | 2021-07-07 | 2021-07-08 | 2021-07-08 06:00 | 2021-07-14 23:59 | 2021-07-15 | 2021-07-14 23:59 | Moomba WL | ADuong4 | 2022-10-03 11:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 9 |  | L0 - No RO |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.76 | Tirrawarra 15 | SANTOS LIMITED | Tirrawarra 15 | Rigless Australia - 1 | J.21.108641 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-06 | 2021-07-05 | 2021-07-05 14:00 | 2021-07-06 | 2021-07-18 23:59 | 2021-07-19 | 2021-07-18 23:59 | Moomba WL | ADuong4 | 2022-10-03 11:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.75 | Swan Lake 14 | SANTOS LIMITED | Swan Lake 14 | Rigless Australia - 1 | J.21.108640 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-07-03 06:00 | 2021-07-02 06:00 | 2021-07-03 14:00 | 2021-07-03 06:00 | 2021-07-05 23:59 | 2021-07-07 | 2021-07-05 23:59 | Moomba WL | ADuong4 | 2022-10-03 11:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.74 | Well #68 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108621 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-09-27 23:00 | 2021-09-28 | 2021-09-28 | 2021-09-28 | 2021-09-30 23:59 | 2021-10-01 | 2021-10-01 00:59 | Moomba WL | IWahbi | 2022-10-03 11:23 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.73 | Well #67 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108620 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-09-24 23:00 | 2021-09-25 | 2021-09-25 | 2021-09-25 | 2021-09-27 23:59 | 2021-09-28 | 2021-09-28 00:59 | Moomba WL | IWahbi | 2022-10-03 11:23 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.72 | Well #66 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108619 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-09-21 23:00 | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2021-09-24 23:59 | 2021-09-25 | 2021-09-25 00:59 | Moomba WL | IWahbi | 2022-10-03 11:23 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.71 | Well #65 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108618 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-09-18 23:00 | 2021-09-19 | 2021-09-19 | 2021-09-19 | 2021-09-21 23:59 | 2021-09-22 | 2021-09-22 00:59 | Moomba WL | IWahbi | 2022-10-03 11:23 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.70 | Well #64 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108617 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-09-15 23:00 | 2021-09-16 | 2021-09-16 | 2021-09-16 | 2021-09-18 23:59 | 2021-09-19 | 2021-09-19 00:59 | Moomba WL | IWahbi | 2022-10-03 11:23 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.69 | Well #63 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108616 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-09-12 23:00 | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-15 23:59 | 2021-09-16 | 2021-09-16 00:59 | Moomba WL | IWahbi | 2022-10-03 11:23 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.68 | Well #62 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108615 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-09-09 23:00 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-12 23:59 | 2021-09-13 | 2021-09-13 00:59 | Moomba WL | IWahbi | 2022-10-03 11:23 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.67 | Well #61 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108614 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-09-06 23:00 | 2021-09-07 | 2021-09-07 | 2021-09-07 | 2021-09-09 23:59 | 2021-09-10 | 2021-09-10 00:59 | Moomba WL | IWahbi | 2022-10-03 11:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.66 | Well #60 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108613 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-09-03 23:00 | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-09-06 23:59 | 2021-09-07 | 2021-09-07 00:59 | Moomba WL | IWahbi | 2022-10-03 11:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.65 | Well #59 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108612 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-08-31 23:00 | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-03 23:59 | 2021-09-04 | 2021-09-04 00:59 | Moomba WL | IWahbi | 2022-10-03 11:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.64 | Well #58 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108611 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-08-28 23:00 | 2021-08-29 | 2021-08-29 | 2021-08-29 | 2021-08-31 23:59 | 2021-09-01 | 2021-09-01 00:59 | Moomba WL | IWahbi | 2022-10-03 11:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.63 | Well #57 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108610 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-08-25 23:00 | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-08-28 23:59 | 2021-08-29 | 2021-08-29 00:59 | Moomba WL | IWahbi | 2022-10-03 11:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.62 | Well #56 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108609 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-08-22 23:00 | 2021-08-23 | 2021-08-23 | 2021-08-23 | 2021-08-25 23:59 | 2021-08-26 | 2021-08-26 00:59 | Moomba WL | IWahbi | 2022-10-03 11:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.61 | Well #55 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108608 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-08-19 23:00 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-22 23:59 | 2021-08-23 | 2021-08-23 00:59 | Moomba WL | IWahbi | 2022-10-03 11:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.60 | Well #54 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108607 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-08-16 23:00 | 2021-08-17 | 2021-08-17 | 2021-08-17 | 2021-08-19 23:59 | 2021-08-20 | 2021-08-20 00:59 | Moomba WL | IWahbi | 2022-10-03 11:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.59 | Well #53 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108606 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-08-13 23:00 | 2021-08-14 | 2021-08-14 | 2021-08-14 | 2021-08-16 23:59 | 2021-08-17 | 2021-08-17 00:59 | Moomba WL | IWahbi | 2022-10-03 11:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.58 | Well #52 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108605 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-08-10 23:00 | 2021-08-11 | 2021-08-11 | 2021-08-11 | 2021-08-13 23:59 | 2021-08-14 | 2021-08-14 00:59 | Moomba WL | IWahbi | 2022-10-03 11:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.57 | Juno 5 | SANTOS LIMITED | Juno 7 | Rigless Australia - 1 | J.21.108604 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-22 | 2021-08-21 | 2021-08-22 | 2021-08-22 | 2021-08-24 23:59 | 2021-08-25 | 2021-08-24 23:59 | Moomba WL | IWahbi | 2022-10-03 11:22 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.56 | Psyche 5 | SANTOS LIMITED | PSYCH 5 | Rigless Australia - 1 | J.21.108603 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-18 | 2021-08-17 | 2021-08-18 | 2021-08-18 | 2021-08-20 23:59 | 2021-08-21 | 2021-08-20 23:59 | Moomba WL | IWahbi | 2022-10-03 11:21 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.55 | Well #49 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108602 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-08-01 23:00 | 2021-08-02 | 2021-08-02 | 2021-08-02 | 2021-08-04 23:59 | 2021-08-05 | 2021-08-05 00:59 | Moomba WL | IWahbi | 2022-10-03 11:21 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.54 | Well #48 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108601 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-07-29 23:00 | 2021-07-30 | 2021-07-30 | 2021-07-30 | 2021-08-01 23:59 | 2021-08-02 | 2021-08-02 00:59 | Moomba WL | IWahbi | 2022-10-03 11:21 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.53 | Well #47 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108600 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-07-26 23:00 | 2021-07-27 | 2021-07-27 | 2021-07-27 | 2021-07-29 23:59 | 2021-07-30 | 2021-07-30 00:59 | Moomba WL | IWahbi | 2022-10-03 11:21 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.52 | Well #46 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108599 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-07-23 23:00 | 2021-07-24 | 2021-07-24 | 2021-07-24 | 2021-07-26 23:59 | 2021-07-27 | 2021-07-27 00:59 | Moomba WL | IWahbi | 2022-10-03 11:21 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.51 | Well #45 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108598 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-07-20 23:00 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-23 23:59 | 2021-07-24 | 2021-07-24 00:59 | Moomba WL | IWahbi | 2022-10-03 11:21 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.50 | Well #44 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108597 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-07-17 23:00 | 2021-07-18 | 2021-07-18 | 2021-07-18 | 2021-07-20 23:59 | 2021-07-21 | 2021-07-21 00:59 | Moomba WL | IWahbi | 2022-10-03 11:21 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.49 | Well #43 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108596 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-07-14 23:00 | 2021-07-15 | 2021-07-15 | 2021-07-15 | 2021-07-17 23:59 | 2021-07-18 | 2021-07-18 00:59 | Moomba WL | IWahbi | 2022-10-03 11:21 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.48 | Well #42 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108595 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-07-11 23:00 | 2021-07-12 | 2021-07-12 | 2021-07-12 | 2021-07-14 23:59 | 2021-07-15 | 2021-07-15 00:59 | Moomba WL | IWahbi | 2022-10-03 11:21 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.47 | Well #41 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108594 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-07-08 23:00 | 2021-07-09 | 2021-07-09 | 2021-07-09 | 2021-07-11 23:59 | 2021-07-12 | 2021-07-12 00:59 | Moomba WL | IWahbi | 2022-10-03 11:21 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.46 | Well #40 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108593 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-07-05 23:00 | 2021-07-06 | 2021-07-06 | 2021-07-06 | 2021-07-08 23:59 | 2021-07-09 | 2021-07-09 00:59 | Moomba WL | IWahbi | 2022-10-03 11:21 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.45 | Well #39 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108592 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-07-02 23:00 | 2021-07-03 | 2021-07-03 | 2021-07-03 | 2021-07-05 23:59 | 2021-07-06 | 2021-07-06 00:59 | Moomba WL | IWahbi | 2022-10-03 11:20 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.44 | Moomba 261 | SANTOS LIMITED | Moomba 261 | Rigless Australia - 1 | J.21.108549 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-31 23:00 | 2021-06-01 | 2021-06-01 | 2021-06-01 | 2021-06-03 23:59 | 2021-06-04 | 2021-06-03 22:59 | Moomba WL | KKeese | 2022-10-03 11:16 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.43 | Moomba 264 | SANTOS LIMITED | MOOMBA 264 | Rigless Australia - 1 | J.21.108548 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-29 23:00 | 2021-05-30 | 2021-05-30 | 2021-05-30 | 2021-06-01 23:59 | 2021-06-02 | 2021-06-01 22:59 | Moomba WL | KKeese | 2022-10-03 11:16 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.42 | Moomba 264 | SANTOS LIMITED | MOOMBA 264 | Rigless Australia - 1 | J.21.108547 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-05-26 23:00 | 2021-05-27 | 2021-05-27 | 2021-05-27 | 2021-05-29 23:59 | 2021-05-30 | 2021-05-29 22:59 | Moomba WL | KKeese | 2022-10-03 11:16 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 54.2 | 0 | 0 | 0 | 16.3 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.41 | Amyema 2 | SANTOS LIMITED | AMYEMA 002 | Rigless Australia - 1 | J.21.108543 | RPI | PS-WL-NO | Medium | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2021-05-16 23:00 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-19 23:59 | 2021-05-20 | 2021-05-20 00:59 | Moomba WL | KKeese | 2022-10-03 11:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 75 | 33.3 | 100 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.40 | Big Lake 30 | SANTOS LIMITED | Big Lake 30 | Rigless Australia - 1 | J.21.108542 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-16 23:00 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-19 23:59 | 2021-05-20 | 2021-05-19 22:59 | Moomba WL | KKeese | 2022-10-03 11:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.39 | Inglewood 1 | SANTOS LIMITED | Inglewood 1 | Rigless Australia - 1 | J.21.108540 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-05-09 23:00 | 2021-05-10 | 2021-05-10 | 2021-05-10 | 2021-05-12 23:59 | 2021-05-13 | 2021-05-12 23:59 | Moomba WL | KKeese | 2022-10-03 11:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.38 | Well #38 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108506 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-06-29 23:00 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 2021-07-02 23:59 | 2021-07-03 | 2021-07-03 00:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.37 | MSLC 3148 Campaign | SANTOS LIMITED | Moomba 185, Tirrawarra 33 | Rigless Australia - 1 | J.21.108505 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-06-29 09:00 | 2021-06-29 | 2021-06-29 | 2021-06-29 10:00 | 2021-07-02 09:59 | 2021-07-02 | 2021-07-02 08:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.36 | Well #36 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108504 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-06-23 23:00 | 2021-06-24 | 2021-06-24 | 2021-06-24 | 2021-06-26 23:59 | 2021-06-27 | 2021-06-27 00:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 3 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.35 | Well #35 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108503 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-06-20 23:00 | 2021-06-21 | 2021-06-21 | 2021-06-21 | 2021-06-23 23:59 | 2021-06-24 | 2021-06-24 00:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.34 | Well #34 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108502 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-06-17 23:00 | 2021-06-18 | 2021-06-18 | 2021-06-18 | 2021-06-20 23:59 | 2021-06-21 | 2021-06-21 00:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.33 | Well #33 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108501 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-06-14 23:00 | 2021-06-15 | 2021-06-15 | 2021-06-15 | 2021-06-17 23:59 | 2021-06-18 | 2021-06-18 00:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.32 | Well #32 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108500 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-06-11 23:00 | 2021-06-12 | 2021-06-12 | 2021-06-12 | 2021-06-14 23:59 | 2021-06-15 | 2021-06-15 00:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.31 | Well #31 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108499 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-06-08 23:00 | 2021-06-09 | 2021-06-09 | 2021-06-09 | 2021-06-11 23:59 | 2021-06-12 | 2021-06-12 00:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.30 | Well #30 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108498 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-06-05 23:00 | 2021-06-06 | 2021-06-06 | 2021-06-06 | 2021-06-08 23:59 | 2021-06-09 | 2021-06-09 00:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.29 | Well #29 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108497 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-06-02 23:00 | 2021-06-03 | 2021-06-03 | 2021-06-03 | 2021-06-05 23:59 | 2021-06-06 | 2021-06-06 00:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.28 | Well #28 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108496 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-05-30 23:00 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-06-02 23:59 | 2021-06-03 | 2021-06-03 00:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:10 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.27 | Well #27 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108495 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-05-27 23:00 | 2021-05-28 | 2021-05-28 | 2021-05-28 | 2021-05-30 23:59 | 2021-05-31 | 2021-05-31 00:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:10 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.26 | Juno 5- 2in PERF | SANTOS LIMITED | JUNO 5 | Rigless Australia - 1 | J.21.108494 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-05-24 23:00 | 2021-10-21 06:00 | 2021-05-25 | 2021-10-22 | 2021-11-03 08:59 | 2021-05-28 | 2021-05-28 00:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:10 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.25 | Juno 5- 2in Re-perf | SANTOS LIMITED | JUNO 5 | Rigless Australia - 1 | J.21.108493 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | In Progress | Design Completed | In Progress | 2021-10-22 08:00 | 2021-10-21 06:00 | 2021-10-21 | 2021-10-22 09:00 | 2021-10-23 17:59 | 2021-12-18 | 2022-03-26 16:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:10 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.24 | Bearcat 2- Packer Setting | SANTOS LIMITED | BEARCAT 2 | Rigless Australia - 1 | J.21.108492 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-20 07:00 | 2021-10-19 14:00 | 2021-10-20 08:00 | 2021-10-20 08:00 | 2021-10-23 07:59 | 2021-10-23 08:00 | 2021-10-23 06:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:10 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.23 | Daralingie 13 | SANTOS LIMITED | DARALINGIE 13 | Rigless Australia - 1 | J.21.108491 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2021-08-01 19:43 | 2021-05-16 | 2021-05-16 | 2021-05-16 | 2021-05-18 23:59 | 2021-05-19 | 2021-08-02 19:48 | Moomba WL | FDPSystemUser | 2022-10-03 11:10 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 75 | 0 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.22 | Tcikalara 26- Cutter | SANTOS LIMITED | Tickalara 26 | Rigless Australia - 1 | J.21.108490 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-01 08:00 | 2021-08-01 06:00 | 2021-08-01 09:00 | 2021-08-01 09:00 | 2021-08-04 08:59 | 2021-08-04 09:00 | 2021-08-04 07:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:10 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6686.16 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.21 | Brompton 1- CIBP | SANTOS LIMITED | Brompton 1 | Rigless Australia - 1 | J.21.108489 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-06-12 12:00 | 2021-06-12 10:00 | 2021-06-12 12:00 | 2021-06-12 12:00 | 2021-06-15 11:59 | 2021-06-15 12:00 | 2021-06-15 11:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:10 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Owen Bass | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.20 | Tirrawarra 78 - Drift / ; Reperforate [1- 11/16" Links] ; | SANTOS LIMITED | Tirrawarra 78 | Rigless Australia - 1 | J.21.108488 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-05-06 23:00 | 2021-05-07 | 2021-05-07 | 2021-05-07 | 2021-05-09 23:59 | 2021-05-10 | 2021-05-09 22:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:10 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.19 | Napowie 1 - ; Perforate ; | SANTOS LIMITED | Napowie 1 | Rigless Australia - 1 | J.21.108487 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-05-03 23:00 | 2021-05-04 | 2021-05-04 | 2021-05-04 | 2021-05-06 23:59 | 2021-05-07 | 2021-05-06 22:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:10 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.18 | Dullingari 56 ; Conduct GR-CCL ; | SANTOS LIMITED | Dullingari 56 | Rigless Australia - 1 | J.21.108486 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-04-30 23:00 | 2021-05-01 | 2021-05-01 | 2021-05-01 | 2021-05-03 23:59 | 2021-05-04 | 2021-05-03 22:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:10 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.17 | Toolachee 55-2" HSD Perf | SANTOS LIMITED | Toolachee 55 | Rigless Australia - 1 | J.21.108485 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-04-27 23:00 | 2021-04-28 | 2021-04-28 | 2021-04-28 | 2021-04-30 23:59 | 2021-05-01 | 2021-04-30 22:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:09 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.16 | Moon North West 1-Perfo-packer | SANTOS LIMITED | MOON NORTH WEST 1 | Rigless Australia - 1 | J.21.108484 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-04-24 23:00 | 2021-04-25 | 2021-04-25 | 2021-04-25 | 2021-04-27 23:59 | 2021-04-28 | 2021-04-27 22:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:09 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.15 | Well #15 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108483 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-04-21 23:00 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-24 23:59 | 2021-04-25 | 2021-04-25 00:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:09 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.14 | Inglewood 1 - Set CIBP & Reperforate | SANTOS LIMITED | Inglewood 1 | Rigless Australia - 1 | J.21.108482 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-04-18 23:00 | 2021-04-19 | 2021-04-19 | 2021-04-19 | 2021-04-21 23:59 | 2021-04-22 | 2021-04-21 22:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:09 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.13 | Cooroo 7-Plug perforation | SANTOS LIMITED | Cooroo 7 (APP A) | Rigless Australia - 1 | J.21.108481 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-04-15 23:00 | 2021-04-16 | 2021-04-16 | 2021-04-16 | 2021-04-18 23:59 | 2021-04-19 | 2021-04-18 22:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:09 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.12 | Jackson 27-Plug Perf | SANTOS LIMITED | JACKSON 14 | Rigless Australia - 1 | J.21.108480 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-04-16 23:00 | 2021-04-16 | 2021-04-17 | 2021-04-17 | 2021-04-19 23:59 | 2021-04-20 | 2021-04-19 22:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:09 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.11 | Fly Lake 1 ,Tubing Cut | SANTOS LIMITED | Fly Lake 1 | Rigless Australia - 1 | J.21.108479 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-04-09 23:00 | 2021-04-10 | 2021-04-10 | 2021-04-10 | 2021-04-12 23:59 | 2021-04-13 | 2021-04-12 22:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:09 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.10 | Well #10 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108478 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-04-06 23:00 | 2021-04-06 23:00 | 2021-04-06 23:00 | 2021-04-06 23:00 | 2021-04-09 22:59 | 2021-04-10 | 2021-04-09 23:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:09 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.09 | Well #9 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108477 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-04-04 | 2021-04-04 | 2021-04-04 | 2021-04-04 | 2021-04-06 22:59 | 2021-04-06 23:00 | 2021-04-06 22:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:09 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.08 | Well #8 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108476 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-03 23:59 | 2021-04-04 | 2021-04-03 23:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:09 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.07 | Well #7 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108475 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-31 23:59 | 2021-04-01 | 2021-03-31 23:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.06 | Well #6 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108474 | RPI | PS-WL-Ops | Medium | Unconfirmed - 90% | Design - CEC |  | In Progress | In Progress | In Progress | 2021-03-26 | 2021-03-26 | 2021-03-26 | 2021-03-26 | 2021-03-28 23:59 | 2021-03-29 | 2021-03-28 23:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.05 | Bolah 8,9,10, Moomba 271 | SANTOS LIMITED |  | Rigless Australia - 1 | J.22.109490 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-06-25 10:00 | 2022-06-25 08:00 | 2022-06-24 14:00 | 2022-06-25 10:00 | 2022-06-28 09:59 | 2022-06-28 10:00 | 2022-06-28 09:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 58.3 | 66.7 | 0 | 0 | 37.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.04 | Big Lake 95 | SANTOS LIMITED | Big Lake 95 | Rigless Australia - 1 | J.21.108473 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-31 23:59 | 2021-04-03 | 2021-04-02 23:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 26198.83 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.03 | Big Lake 146 | SANTOS LIMITED | BIG LAKE 146 | Rigless Australia - 1 | J.21.108472 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-11 06:00 | 2021-03-11 | 2021-03-11 06:00 | 2021-03-11 06:00 | 2021-03-14 05:59 | 2021-03-14 06:00 | 2021-03-14 05:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 24299.42 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.02 | Moomba 245 | SANTOS LIMITED | Moomba 245 | Rigless Australia - 1 | J.21.108471 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-10 | 2021-03-09 | 2021-03-10 | 2021-03-10 | 2021-03-12 23:59 | 2021-03-13 | 2021-03-12 23:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 14550.36 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.11 | A.1001568.11.01 | Moomba 121 | SANTOS LIMITED | Moomba 121 | Rigless Australia - 1 | J.21.108470 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-09 | 2021-03-08 12:55 | 2021-03-09 | 2021-03-09 | 2021-03-11 23:59 | 2021-03-12 | 2021-03-11 23:59 | Moomba WL | FDPSystemUser | 2022-10-03 11:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6138.53 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.10 | A.1001568.10.01 | Okotoko North 2 | SANTOS LIMITED | Well #17 | Rigless Australia - 1 | J.21.108363 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2021-03-21 17:20 |  | 2021-03-21 17:21 | 2021-03-23 17:21 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 09:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.37 | Moorari 18 | SANTOS LIMITED | Moorari 18 (DEV B) Gas DXCF- PAD 2 | Rigless Australia - 1 | J.21.108761 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-17 08:00 | 2021-10-17 06:00 | 2021-10-17 | 2021-10-17 08:00 | 2021-10-21 01:59 | 2021-10-22 | 2021-10-21 01:59 | Moomba WL | ADuong4 | 2022-10-03 11:39 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.36 | Merchant 1 | SANTOS LIMITED | Merchant 1 | Rigless Australia - 1 | J.21.108758 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-11 06:00 | 2021-10-10 | 2021-10-11 | 2021-10-11 06:00 | 2021-10-14 23:59 | 2021-10-15 | 2021-10-14 23:59 | Moomba WL | ADuong4 | 2022-10-03 11:39 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.35 | Swan Lake 15 | SANTOS LIMITED | Swan Lake 15 | Rigless Australia - 1 | J.21.108756 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-09 06:00 | 2021-10-08 | 2021-10-09 | 2021-10-09 06:00 | 2021-10-12 23:59 | 2021-10-13 | 2021-10-12 23:59 | Moomba WL | ADuong4 | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.34 | Della 19 | SANTOS LIMITED | Della 19 | Rigless Australia - 1 | J.21.108753 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-30 | 2021-09-29 | 2021-09-29 14:00 | 2021-09-30 | 2021-10-06 01:59 | 2021-10-07 | 2021-10-06 01:59 | Moomba WL | ADuong4 | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 91.7 | 50 | 0 | 75 | 65 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.33 | Lane 1 | SANTOS LIMITED | Lane 1 | Rigless Australia - 1 | J.21.108750 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2021-09-27 | 2021-09-26 | 2021-09-27 | 2021-09-27 | 2021-10-01 00:59 | 2021-10-02 | 2021-10-11 00:59 | Moomba WL | ADuong4 | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 66.7 | 0 | 75 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.32 | Big Lake 13 | SANTOS LIMITED | Big Lake 13 | Rigless Australia - 1 | J.21.108741 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-14 | 2021-09-13 | 2021-09-13 14:00 | 2021-09-14 | 2021-09-27 23:59 | 2021-09-28 | 2021-09-27 23:59 | Moomba WL | ADuong4 | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 91.7 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.31 | Cowralli 8 | SANTOS LIMITED | COWRALLI 8 | Rigless Australia - 1 | J.21.108427 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-03 12:28 | 2021-03-03 07:28 | 2021-03-03 | 2021-03-03 12:28 | 2021-03-05 07:28 | 2021-03-06 | 2021-03-05 07:28 | Moomba WL | DParker16 | 2022-10-03 11:04 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 25471.09 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.30 | Raven 1 | SANTOS LIMITED | Raven-1 | Rigless Australia - 1 | J.21.108426 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-01 12:12 | 2021-03-01 | 2021-03-01 | 2021-03-01 12:12 | 2021-03-03 23:59 | 2021-03-04 | 2021-03-03 23:59 | Moomba WL | DParker16 | 2022-10-03 11:04 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6138.53 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.29 | Moomba 262 | SANTOS LIMITED | MOOMBA 262 | Rigless Australia - 1 | J.21.108423 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-01 | 2021-02-25 | 2021-02-26 | 2021-03-01 | 2021-03-03 23:59 | 2021-03-01 | 2021-03-03 23:59 | Moomba WL | DParker16 | 2022-10-03 11:03 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.25 | Baryulah 8 | SANTOS LIMITED | BARYULAH 8 | Rigless Australia - 1 | J.21.108371 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-01-19 17:21 | 2021-01-18 17:20 |  | 2021-01-19 17:21 | 2021-01-21 17:21 |  | 2021-01-21 17:21 | Moomba WL | DParker16 | 2022-10-03 10:17 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.19 | Montegue 1-Post Frac Perforations | SANTOS LIMITED | Montegue 1 | Rigless Australia - 1 | J.20.062602 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-31 | 2020-12-25 |  | 2020-12-31 | 2021-01-01 23:59 |  | 2021-01-01 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:17 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.16 | Moon 5 - 2" HSD Perforate | SANTOS LIMITED | Moon 5 | Rigless Australia - 1 | J.20.062591 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-29 | 2020-12-29 |  | 2020-12-29 | 2020-12-30 23:59 |  | 2020-12-30 23:59 | Moomba WL | ymoradi2 | 2022-10-03 10:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  |  |  | 70.8 | 8.3 | 0 | 0 | 23.8 |  | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.14 | Strzelecki 30-CPST-DB | SANTOS LIMITED | STRZELECKI 30 | Rigless Australia - 1 | J.20.062571 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-12-11 |  | 2020-12-20 06:00 | 2020-12-23 05:59 |  |  | Moomba WL | ymoradi2 | 2022-10-03 10:13 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.01 | Gudnuki 3 | SANTOS LIMITED | Dullingari 17 | Rigless Australia - 1 | J.20.062560 | RPI | PS-WL-Ops | Low | Operationally Complete | Execute - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-11-23 |  | 2020-12-23 | 2021-01-23 23:59 |  |  | Moomba WL | KKeese | 2022-10-03 10:12 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.23 | Wippo South 2 | SANTOS LIMITED | WIPPO SOUTH 2 | Rigless Australia - 1 | J.21.108370 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | In Progress | In Progress | 2021-01-16 | 2021-01-15 12:00 |  | 2021-01-16 | 2021-01-20 15:57 |  | 2021-01-20 | Moomba WL | ymoradi2 | 2022-10-03 10:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 8596.49 | 0 |  | L0 - No RO |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Owen Bass | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.09 | Moon 3 | SANTOS LIMITED | Brumby 10 | Rigless Australia - 1 | J.20.062554 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-12-20 |  | 2020-12-20 | 2020-12-22 23:59 |  |  | Moomba WL | KKeese | 2022-10-03 10:11 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 66.7 | 0 | 0 | 0 | 20 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.07 | Dullingari 55 | SANTOS LIMITED | DULLINGARI 55 | Rigless Australia - 1 | J.20.062553 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-12-02 |  | 2020-12-07 | 2020-12-09 23:59 |  |  | Moomba WL | KKeese | 2022-10-03 10:11 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.27 | Bindah 5 | SANTOS LIMITED | Bindah 5 | Rigless Australia - 1 | J.21.108369 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-02-05 |  | 2021-02-06 15:00 | 2021-02-08 19:20 |  |  | Moomba WL | DParker16 | 2022-10-03 10:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.17 | Amyema 2 -Cement Evaluation Log ; | SANTOS LIMITED | Amyema 2 | Rigless Australia - 1 | J.20.062507 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-12-15 |  | 2020-12-15 09:00 | 2020-12-16 23:59 |  |  | Moomba WL | ymoradi2 | 2022-10-03 10:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  |  |  | 54.2 | 8.3 | 0 | 0 | 18.8 |  | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.06 | Dullingari North 13ST1 | SANTOS LIMITED | DULLINGARI NORTH 13ST1 | Rigless Australia - 1 | J.20.062506 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-11-29 |  | 2020-12-23 | 2020-12-25 23:59 |  |  | Moomba WL | KKeese | 2022-10-03 10:06 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.26 | Psyche 3 | SANTOS LIMITED | Psyche 3 | Rigless Australia - 1 | J.21.108368 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-01-28 06:01 |  | 2021-01-28 12:51 | 2021-01-30 19:51 |  |  | Moomba WL | DParker16 | 2022-10-03 10:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.24 | Okotoko North 2 | SANTOS LIMITED | Okotoko North 2 | Rigless Australia - 1 | J.21.108367 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-01-18 17:20 |  | 2021-01-18 17:21 | 2021-01-20 17:21 |  |  | Moomba WL | DParker16 | 2022-10-03 10:04 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.15 | Kidman 12- Owen Casing Patch | SANTOS LIMITED | Kidman 12 | Rigless Australia - 1 | J.20.062487 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-12-18 06:00 |  | 2020-12-19 12:00 | 2020-12-22 11:59 |  |  | Moomba WL | ymoradi2 | 2022-10-03 10:03 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 17192.98 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.10 | Moon 3 | SANTOS LIMITED | Burke East 1 | Rigless Australia - 1 | J.20.062486 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-12-03 |  | 2020-12-04 | 2020-12-06 23:59 |  |  | Moomba WL | KKeese | 2022-10-03 10:03 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.08 | Burke East 1 | SANTOS LIMITED | Burke East 1 | Rigless Australia - 1 | J.20.062485 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-12-03 |  | 2020-12-04 | 2020-12-06 23:59 |  |  | Moomba WL | KKeese | 2022-10-03 10:03 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.04 | Dullingari North 17 | SANTOS LIMITED | Dullingari North 17 | Rigless Australia - 1 | J.20.062484 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-11-27 |  | 2020-11-29 06:00 | 2020-12-02 05:59 |  |  | Moomba WL | KKeese | 2022-10-03 10:03 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.12 | Moon 3 | SANTOS LIMITED | Moon 3 | Rigless Australia - 1 | J.20.062467 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-12-07 |  | 2020-12-08 12:00 | 2020-12-10 11:59 |  |  | Moomba WL | KKeese | 2022-10-03 09:52 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.05 | Dullingari North 11 | SANTOS LIMITED | DULLINGARI NORTH 11 | Rigless Australia - 1 | J.20.062466 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-11-26 12:00 |  | 2020-11-29 12:00 | 2020-12-01 11:59 |  |  | Moomba WL | DKitney | 2022-10-03 09:52 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.02 | Dullingari North 15 | SANTOS LIMITED | DULLINGARI NORTH 15 | Rigless Australia - 1 | J.20.062465 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2020-11-25 | 2020-11-24 |  | 2020-11-25 | 2020-11-27 23:59 |  | 2020-11-27 23:59 | Moomba WL | KKeese | 2022-10-03 09:52 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 75 | 50 | 0 | 50 | 52.5 |  | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.28 | Favela 1 | SANTOS LIMITED | Favela 1 | Rigless Australia - 1 | J.21.108366 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-02-25 |  | 2021-02-25 12:00 | 2021-02-27 06:53 |  |  | Moomba WL | DParker16 | 2022-10-03 09:50 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.21 | Psyche 2- Tubing Cut | SANTOS LIMITED | Psyche 2 | Rigless Australia - 1 | J.21.108365 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-01-09 06:00 |  | 2021-01-09 10:30 | 2021-01-12 10:29 |  |  | Moomba WL | ymoradi2 | 2022-10-03 09:50 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6686.16 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.13 | Kidman 10 -CPST-DB | SANTOS LIMITED | KIDMAN 10 | Rigless Australia - 1 | J.20.062449 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-12-09 |  | 2020-12-11 12:00 | 2020-12-14 11:59 |  |  | Moomba WL | ymoradi2 | 2022-10-03 09:50 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.18 | Namur 4-Tubing Cut | SANTOS LIMITED | NAMUR 004 | Rigless Australia - 1 | J.21.108364 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2021-01-03 |  | 2021-01-03 07:00 | 2021-01-06 06:59 |  |  | Moomba WL | ymoradi2 | 2022-10-03 09:48 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.20 | Okotoko North 2 ; Perforations | SANTOS LIMITED | OKOTOKO NORTH 2 | Rigless Australia - 1 | J.20.062429 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2020-12-30 | 2020-12-29 |  | 2020-12-30 | 2021-01-01 23:59 |  | 2021-01-01 23:59 | Moomba WL | ymoradi2 | 2022-10-03 09:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 75 | 50 | 0 | 0 | 37.5 |  | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.22 | TBA2 | SANTOS LIMITED |  | Rigless Australia - 1 | J.21.108362 | RPI | PS-WL-Ops | Medium | Confirmed | Prepare - Mob |  | Design Completed | In Progress | In Progress | 2021-01-04 | 2020-12-28 |  | 2021-01-04 | 2021-01-06 23:59 |  | 2021-01-06 23:59 | Moomba WL | ymoradi2 | 2022-10-03 09:44 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 66.7 | 50 | 0 | 0 | 35 |  | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.11 | Brumby 10 | SANTOS LIMITED | Brumby 10 | Rigless Australia - 1 | J.20.062411 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-12-05 |  | 2020-12-06 | 2020-12-07 23:59 |  |  | Moomba WL | KKeese | 2022-10-03 09:44 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.09 | A.1001568.09.03 | Dullingari North 16 | SANTOS LIMITED | DULLINGARI NORTH 16 | Rigless Australia - 1 | J.20.062410 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-11-26 |  | 2020-11-29 06:00 | 2020-12-01 05:59 |  |  | Moomba WL | KKeese | 2022-10-03 09:44 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.36 | Well TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062601 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-12-21 01:00 | 2020-12-21 |  | 2020-12-21 | 2020-12-22 23:59 |  | 2020-12-23 00:59 | Moomba WL | OBass | 2022-10-03 10:17 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.37 | Well TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062590 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-12-25 01:00 | 2020-12-25 |  | 2020-12-25 | 2020-12-26 23:59 |  | 2020-12-27 00:59 | Moomba WL | OBass | 2022-10-03 10:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.35 | Well TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062589 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-12-18 01:00 | 2020-12-18 |  | 2020-12-18 | 2020-12-19 23:59 |  | 2020-12-20 00:59 | Moomba WL | OBass | 2022-10-03 10:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.31 | Well TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062588 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-12-05 01:00 | 2020-12-05 |  | 2020-12-05 | 2020-12-06 23:59 |  | 2020-12-07 00:59 | Moomba WL | OBass | 2022-10-03 10:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.30 | Beckler 6- SCMT | SANTOS LIMITED | Beckler 6 | Rigless Australia - 1 | J.20.062587 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2020-12-23 01:00 | 2020-11-29 08:00 |  | 2020-12-23 | 2020-12-24 23:59 |  | 2020-12-25 00:59 | Moomba WL | OBass | 2022-10-03 10:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.12 | Strezlecki 17 | SANTOS LIMITED | Strzelecki 15 | Rigless Australia - 1 | J.20.062586 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress | 2020-09-24 | 2020-09-24 |  | 2020-09-24 | 2020-09-25 23:59 |  | 2020-09-25 23:59 | Moomba WL | OBass | 2022-10-03 10:14 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.11 | Wolgolla 5 | SANTOS LIMITED | Walgolla 5 | Rigless Australia - 1 | J.20.062585 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-09-01 | 2020-08-31 |  | 2020-09-01 | 2020-09-02 23:59 |  | 2020-09-02 23:59 | Moomba WL | KKeese | 2022-10-03 10:14 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.01 | Dullingari 42 DW 1 | SANTOS LIMITED | Dullingari 42DW1 | Rigless Australia - 1 | J.20.062584 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress | 2020-07-29 06:00 | 2020-07-28 17:00 |  | 2020-07-29 06:00 | 2020-07-31 10:00 |  | 2020-07-31 10:00 | Moomba WL | DKitney | 2022-10-03 10:14 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 9039.72 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.14 | Hera 5 | SANTOS LIMITED | Hera 5 | Rigless Australia - 1 | J.20.062570 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-10-01 |  | 2020-10-02 12:00 | 2020-10-04 11:59 |  |  | Moomba WL | OBass | 2022-10-03 10:13 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.13 | Alisma 2 | SANTOS LIMITED | Alisma 2 | Rigless Australia - 1 | J.20.062569 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-08-31 14:00 |  | 2020-12-27 12:00 | 2020-12-29 11:59 |  |  | Moomba WL | DKitney | 2022-10-03 10:13 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.21 | Strzelecki 5- Links | SANTOS LIMITED | Strzelecki 5 | Rigless Australia - 1 | J.20.062559 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-10-29 |  | 2020-10-29 07:00 | 2020-10-31 06:59 |  |  | Moomba WL | OBass | 2022-10-03 10:12 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.38 | Well TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062552 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-12-29 |  | 2020-12-29 | 2020-12-30 23:59 |  |  | Moomba WL | OBass | 2022-10-03 10:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.20 | Toolachee 30- Links | SANTOS LIMITED | Toolachee 30 | Rigless Australia - 1 | J.20.062551 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-10-29 |  | 2020-10-29 | 2020-10-30 23:59 |  |  | Moomba WL | OBass | 2022-10-03 10:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 9356.73 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.15 | Hera 6 | SANTOS LIMITED | Hera 6 | Rigless Australia - 1 | J.20.062550 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-10-09 |  | 2020-10-10 | 2020-10-11 23:59 |  |  | Moomba WL | OBass | 2022-10-03 10:11 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.04 | Moomba 197 DD, Punch or Cut | SANTOS LIMITED | Moomba 197 | Rigless Australia - 1 | J.20.062549 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-08-04 23:00 |  | 2020-08-23 12:00 | 2020-08-25 16:00 |  |  | Moomba WL | DKitney | 2022-10-03 10:11 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.03 | Dullingari 53 | SANTOS LIMITED | Dullingari 53 | Rigless Australia - 1 | J.20.062548 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-07-31 23:00 |  | 2020-08-01 13:00 | 2020-08-03 17:00 |  |  | Moomba WL | DKitney | 2022-10-03 10:11 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 5730.99 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.34 | Well TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062536 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-12-15 |  | 2020-12-15 | 2020-12-16 23:59 |  |  | Moomba WL | OBass | 2022-10-03 10:09 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.32 | Well TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062535 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-12-08 |  | 2020-12-08 | 2020-12-09 23:59 |  |  | Moomba WL | OBass | 2022-10-03 10:09 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.08 | Moomba 125 | SANTOS LIMITED | Moomba 125 | Rigless Australia - 1 | J.20.062534 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-08-26 |  | 2020-08-27 | 2020-08-28 23:59 |  |  | Moomba WL | KKeese | 2022-10-03 10:09 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.06 | Gooranie 14 | SANTOS LIMITED | GOORANIE 14 | Rigless Australia - 1 | J.20.062533 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-08-16 |  | 2020-08-17 | 2020-08-18 23:59 |  |  | Moomba WL | KKeese | 2022-10-03 10:09 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.40 | Well TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062526 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-09-28 |  | 2020-09-28 | 2020-09-29 23:59 |  |  | Moomba WL | OBass | 2022-10-03 10:08 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.39 | Well TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062525 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2021-01-01 |  | 2021-01-01 | 2021-01-02 23:59 |  |  | Moomba WL | OBass | 2022-10-03 10:07 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.33 | Well TBD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062524 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-12-11 |  | 2020-12-11 | 2020-12-12 23:59 |  |  | Moomba WL | OBass | 2022-10-03 10:07 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.28 | Beckler 5 | SANTOS LIMITED | Beckler 5 | Rigless Australia - 1 | J.20.062523 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-11-19 |  | 2020-12-23 | 2020-12-24 23:59 |  |  | Moomba WL | OBass | 2022-10-03 10:07 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.27 | Beckler 4 | SANTOS LIMITED | BECKLER 4 | Rigless Australia - 1 | J.20.062522 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-11-19 |  | 2020-12-27 12:00 | 2020-12-29 11:59 |  |  | Moomba WL | OBass | 2022-10-03 10:07 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.18 | Beckler 2 | SANTOS LIMITED | Beckler 2 | Rigless Australia - 1 | J.20.062521 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-10-23 |  | 2020-10-26 | 2020-10-27 23:59 |  |  | Moomba WL | OBass | 2022-10-03 10:07 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.17 | Beckler 3 | SANTOS LIMITED | Beckler 2 | Rigless Australia - 1 | J.20.062520 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-10-15 |  | 2020-10-16 | 2020-10-17 23:59 |  |  | Moomba WL | OBass | 2022-10-03 10:07 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.16 | Maverick 1 | SANTOS LIMITED | Maverick 1 | Rigless Australia - 1 | J.20.062519 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2020-10-13 |  | 2020-10-14 | 2020-10-15 23:59 |  |  | Moomba WL | OBass | 2022-10-03 10:07 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.25 | Okotoko 3- CIBP | SANTOS LIMITED | OKOTOKO 3 | Rigless Australia - 1 | J.20.062505 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-11-14 12:00 |  | 2020-11-14 12:00 | 2020-11-16 11:59 |  |  | Moomba WL | OBass | 2022-10-03 10:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.09 | Moomba 145 | SANTOS LIMITED | Moomba 145 | Rigless Australia - 1 | J.20.062498 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-08-26 |  | 2020-08-28 06:00 | 2020-08-30 05:59 |  |  | Moomba WL | KKeese | 2022-10-03 10:04 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.26 | Bow 1 | SANTOS LIMITED | Bow 1 | Rigless Australia - 1 | J.20.062483 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-11-18 |  | 2020-11-18 | 2020-11-19 23:59 |  |  | Moomba WL | OBass | 2022-10-03 09:54 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.22 | Okotoko North 2 CIBP | SANTOS LIMITED | Okotoko North 2 | Rigless Australia - 1 | J.20.062482 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-11-05 |  | 2020-11-06 12:00 | 2020-11-08 |  |  | Moomba WL | OBass | 2022-10-03 09:54 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 5730.99 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.02 | Dullingari 16 | SANTOS LIMITED | DULLINGARI NORTH 010 | Rigless Australia - 1 | J.20.062464 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-07-30 16:00 |  | 2020-08-05 | 2020-08-07 04:00 |  |  | Moomba WL | DKitney | 2022-10-03 09:52 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 12703.7 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.19 | Dullingari North 6 | SANTOS LIMITED | Dullingari north 6 | Rigless Australia - 1 | J.20.062448 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-10-26 |  | 2020-10-28 12:00 | 2020-10-31 11:59 |  |  | Moomba WL | OBass | 2022-10-03 09:50 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 14747.76 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.29 | Brompton 1 | SANTOS LIMITED | Brompton 1 | Rigless Australia - 1 | J.20.062439 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-11-20 |  | 2020-11-21 | 2020-11-22 23:59 |  |  | Moomba WL | OBass | 2022-10-03 09:48 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.07 | Moomba 109 | SANTOS LIMITED | Moomba 109 | Rigless Australia - 1 | J.20.062438 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-08-24 |  | 2020-08-25 | 2020-08-27 23:59 |  |  | Moomba WL | KKeese | 2022-10-03 09:48 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 11533.46 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.23 | Okotoko West 2 | SANTOS LIMITED | OKOTOKO WEST 2 | Rigless Australia - 1 | J.20.062419 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-11-12 |  | 2020-11-12 | 2020-11-13 23:59 |  |  | Moomba WL | OBass | 2022-10-03 09:45 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.10 | Ashby 3 | SANTOS LIMITED | Ashby 3 | Rigless Australia - 1 | J.20.062418 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-08-29 |  | 2020-09-01 06:00 | 2020-09-03 05:59 |  |  | Moomba WL | KKeese | 2022-10-03 09:45 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.05 | Tindilpie 9 | SANTOS LIMITED | Tindilpie 13 | Rigless Australia - 1 | J.20.062417 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-08-12 |  | 2020-08-13 | 2020-08-14 23:59 |  |  | Moomba WL | KKeese | 2022-10-03 09:45 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.08 | A.1001568.08.24 | Surlow 2 | SANTOS LIMITED | Surlow 2 | Rigless Australia - 1 | J.20.062409 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-11-08 06:00 |  | 2020-12-27 12:00 | 2020-12-29 11:59 |  |  | Moomba WL | OBass | 2022-10-03 09:44 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.49 | Big Lake 125 | SANTOS LIMITED | Big Lake 125 | Rigless Australia - 1 | J.20.062600 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress | 2020-08-05 | 2020-07-25 |  | 2020-08-05 | 2020-08-08 23:59 |  | 2020-08-08 23:59 | Moomba WL | DKitney | 2022-10-03 10:17 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 25341.13 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.15 | Seccante 6 GR-CCL Log | SANTOS LIMITED | Well #18 | Rigless Australia - 1 | J.20.062599 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-07-31 23:00 | 2020-07-31 14:30 |  | 2020-07-31 14:30 | 2020-08-13 14:30 |  | 2020-08-08 23:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:16 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.09 | Marabooka 6 Perforation | SANTOS LIMITED | MOOMBA 230 | Rigless Australia - 1 | J.20.062598 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-07-12 23:00 | 2020-07-12 14:30 |  | 2020-07-12 14:30 | 2020-07-16 02:30 |  | 2020-07-16 11:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:16 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.06 | Isoptera 2 SCMT | SANTOS LIMITED | Moorari 19 | Rigless Australia - 1 | J.20.062597 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-07-12 05:00 | 2020-07-08 20:30 |  | 2020-07-11 20:30 | 2020-07-13 08:30 |  | 2020-07-13 17:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:16 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.45 | Lake Macmillan 3 | SANTOS LIMITED | Lake McMillan 3 | Rigless Australia - 1 | J.20.062583 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-07-16 | 2020-07-15 |  | 2020-07-16 | 2020-07-18 23:59 |  | 2020-07-18 23:59 | Moomba WL | KKeese | 2022-10-03 10:14 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.42 | Big Lake 126 | SANTOS LIMITED | Big Lake 126 | Rigless Australia - 1 | J.20.062582 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2020-07-09 | 2020-07-08 |  | 2020-07-09 | 2020-07-11 23:59 |  | 2020-07-11 23:59 | Moomba WL | KKeese | 2022-10-03 10:14 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.34 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062581 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-09-07 23:00 | 2020-09-07 15:30 |  | 2020-09-07 15:30 | 2020-09-09 15:30 |  | 2020-09-09 23:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:14 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.16 | Seccante 4 GR-CCL Logging | SANTOS LIMITED | Well #19 | Rigless Australia - 1 | J.20.062580 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-08-01 23:00 | 2020-08-01 14:30 |  | 2020-08-01 14:30 | 2020-08-13 14:30 |  | 2020-08-13 23:00 | Moomba WL | FDPSystemUser | 2022-10-03 10:14 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.43 | Moomba 230 | SANTOS LIMITED | MOOMBA 230 | Rigless Australia - 1 | J.20.062568 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Design Completed | In Progress |  | 2020-07-09 |  | 2020-07-10 13:00 | 2020-07-13 12:59 |  |  | Moomba WL | MSchvartz | 2022-10-03 10:13 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.11 | Chookoo 4 | SANTOS LIMITED | Crowsnest 1 | Rigless Australia - 1 | J.20.062558 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-07-20 20:30 |  | 2020-07-20 20:30 | 2020-08-25 21:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 10:12 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.50 | Pondrinie 20-reperf | SANTOS LIMITED | Pondrinie 20 | Rigless Australia - 1 | J.20.062547 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-07-26 14:30 |  | 2020-07-26 14:30 | 2020-07-30 02:30 |  |  | Moomba WL | DKitney | 2022-10-03 10:10 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 16344.32 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.47 | Crowsnest 1 | SANTOS LIMITED | Crowsnest 1 | Rigless Australia - 1 | J.20.062546 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-07-20 |  | 2020-07-21 | 2020-07-22 23:59 |  |  | Moomba WL | KKeese | 2022-10-03 10:10 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.32 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062545 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-09-24 15:30 |  | 2020-09-24 15:30 | 2020-09-26 15:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 10:10 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.21 | Vega 5 Link Perforations | SANTOS LIMITED | Well #27 | Rigless Australia - 1 | J.20.062544 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-09-06 15:30 |  | 2020-09-07 15:30 | 2020-09-10 15:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 10:10 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.02 | Dullingari 43 2inHSD | SANTOS LIMITED | Moomba 256 | Rigless Australia - 1 | J.20.062543 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-07-02 14:30 |  | 2020-07-02 14:30 | 2020-07-06 02:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 10:10 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.46 | Moorari 17 | SANTOS LIMITED | Moorari 17 (DEV A) Gas DXCF- PAD 2 | Rigless Australia - 1 | J.20.062518 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-07-16 |  | 2020-07-17 | 2020-07-20 23:59 |  |  | Moomba WL | KKeese | 2022-10-03 10:07 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 23001.95 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.29 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062517 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-09-15 15:30 |  | 2020-09-15 15:30 | 2020-09-17 15:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 10:07 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.37 | Moomba 256 | SANTOS LIMITED | Moomba 256 | Rigless Australia - 1 | J.20.062504 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-06-14 |  | 2020-06-27 | 2020-06-29 23:59 |  |  | Moomba WL | KKeese | 2022-10-03 10:05 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.31 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062503 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-09-21 15:30 |  | 2020-09-21 15:30 | 2020-09-23 15:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 10:05 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.25 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062502 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-09-03 15:30 |  | 2020-09-03 15:30 | 2020-09-05 15:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 10:05 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.20 | Chookoo 9 MPBT | SANTOS LIMITED | Well #26 | Rigless Australia - 1 | J.20.062501 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-08-18 14:30 |  | 2020-08-19 14:30 | 2020-08-21 14:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 10:05 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.07 | Isoptera 3 SCMT | SANTOS LIMITED | Moorari 17 (DEV A) Gas DXCF- PAD 2 | Rigless Australia - 1 | J.20.062500 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-08 20:30 |  | 2020-07-11 20:30 | 2020-07-13 08:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 10:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.22 | Moomba 249 post frac | SANTOS LIMITED | Well #31 | Rigless Australia - 1 | J.20.062497 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-08-25 15:30 |  | 2020-09-15 03:30 | 2020-09-19 03:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 10:04 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.41 | Gooranie 14 | SANTOS LIMITED | GOORANIE 14 | Rigless Australia - 1 | J.20.062481 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-06-30 |  | 2020-07-01 | 2020-07-03 23:59 |  |  | Moomba WL | KKeese | 2022-10-03 09:54 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.39 | Hera 5 | SANTOS LIMITED | Hera 5 | Rigless Australia - 1 | J.20.062480 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-06-21 |  | 2020-06-22 | 2020-06-25 23:59 |  |  | Moomba WL | KKeese | 2022-10-03 09:54 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.35 | Dullingari 42-Perforation | SANTOS LIMITED | Well #35 | Rigless Australia - 1 | J.20.062479 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-09-10 16:30 |  | 2020-09-11 22:30 | 2020-09-13 22:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 09:54 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.30 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062478 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-09-18 15:30 |  | 2020-09-18 15:30 | 2020-09-20 15:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 09:54 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.26 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062477 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-09-06 15:30 |  | 2020-09-06 15:30 | 2020-09-08 15:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 09:54 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.18 | Barina 4 | SANTOS LIMITED | Well #16 | Rigless Australia - 1 | J.20.062476 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-08-08 14:30 |  | 2020-08-10 20:30 | 2020-08-12 20:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 09:54 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.17 | Charo 12 | SANTOS LIMITED | Well #23 | Rigless Australia - 1 | J.20.062475 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-08-07 14:30 |  | 2020-08-07 14:30 | 2020-08-12 14:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 09:53 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.14 | Seccante 3 GR-CCL Log | SANTOS LIMITED | Well #17 | Rigless Australia - 1 | J.20.062474 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-07-29 14:30 |  | 2020-07-31 14:30 | 2020-08-12 14:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 09:53 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.12 | Jena 24 SCMT | SANTOS LIMITED | Well #15 | Rigless Australia - 1 | J.20.062473 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-07-29 14:30 |  | 2020-07-30 14:30 | 2020-08-01 14:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 09:53 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.03 | Toolachee 42 Drift/2inHSD | SANTOS LIMITED | Hera 5 | Rigless Australia - 1 | J.20.062472 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-06-29 20:30 |  | 2020-06-29 20:30 | 2020-07-01 08:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 09:53 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.28 | Moomba 248 post frac | SANTOS LIMITED | Well #32 | Rigless Australia - 1 | J.20.062463 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-09-12 15:30 |  | 2020-09-15 15:30 | 2020-09-17 15:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 09:52 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.04 | Merchant 1 SCMT | SANTOS LIMITED | GOORANIE 14 | Rigless Australia - 1 | J.20.062462 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-08 20:30 |  | 2020-07-11 20:30 | 2020-07-13 08:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 09:52 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.48 | Pondrinie 20 | SANTOS LIMITED | Pondrinie 20 | Rigless Australia - 1 | J.20.062447 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-22 |  | 2020-07-26 | 2020-07-29 23:59 |  |  | Moomba WL | DKitney | 2022-10-03 09:50 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.36 | Chookoo 9- Angelique | SANTOS LIMITED | Well #26 | Rigless Australia - 1 | J.20.062446 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-08-08 20:30 |  | 2020-08-08 20:30 | 2020-08-17 20:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 09:50 | FDPSystemUser |  | No |  |  |  |  | Angelique Singer |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.27 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062445 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-09-09 15:30 |  | 2020-09-09 15:30 | 2020-09-11 15:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 09:50 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.10 | Stokes 9 2.125" Link perforation | SANTOS LIMITED | Merrimelia 10 | Rigless Australia - 1 | J.20.062444 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-07-14 14:30 |  | 2020-07-14 14:30 | 2020-07-16 14:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 09:50 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 15122.18 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.08 | Bugito 3 SCMT | SANTOS LIMITED | Moorari 20 | Rigless Australia - 1 | J.20.062443 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-08 20:30 |  | 2020-07-11 20:30 | 2020-07-14 08:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 09:49 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.38 | Moomba 255 | SANTOS LIMITED | Moomba 255 | Rigless Australia - 1 | J.20.062437 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-06-15 |  | 2020-06-16 | 2020-06-18 23:59 |  |  | Moomba WL | KKeese | 2022-10-03 09:48 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.33 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062436 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-09-04 15:30 |  | 2020-09-04 15:30 | 2020-09-06 15:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 09:48 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.24 | Moomba 246 Post frac | SANTOS LIMITED | Well #34 | Rigless Australia - 1 | J.20.062435 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-09-17 15:30 |  | 2020-09-17 15:30 | 2020-09-23 15:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 09:48 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.13 | Charo 3 | SANTOS LIMITED | Well #22 | Rigless Australia - 1 | J.20.062434 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-08-03 14:30 |  | 2020-08-03 14:30 | 2020-08-12 14:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 09:48 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.44 | Moomba 132 | SANTOS LIMITED | MOOMBA 230 | Rigless Australia - 1 | J.20.062428 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-07-11 |  | 2020-07-12 | 2020-07-14 23:59 |  |  | Moomba WL | KKeese | 2022-10-03 09:47 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.40 | Hera 6 | SANTOS LIMITED | Hera 6 | Rigless Australia - 1 | J.20.062427 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-06-21 |  | 2020-06-25 | 2020-06-29 23:59 |  |  | Moomba WL | KKeese | 2022-10-03 09:47 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.19 | Arrona 2 | SANTOS LIMITED | Well #25 | Rigless Australia - 1 | J.20.062426 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-08-09 14:30 |  | 2020-08-10 20:30 | 2020-08-12 20:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 09:47 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.05 | Moomba 133 Plug and Cement | SANTOS LIMITED | Hera 6 | Rigless Australia - 1 | J.20.062425 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-07-06 14:30 |  | 2020-07-08 14:30 | 2020-07-09 14:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 09:46 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.23 | Moomba 247 post frac | SANTOS LIMITED | Well #33 | Rigless Australia - 1 | J.20.062416 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-09-16 15:30 |  | 2020-09-17 15:30 | 2020-09-19 15:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 09:45 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.07 | A.1001568.07.01 | Moomba 109 2inHSD | SANTOS LIMITED | Cooroo 7 (APP A) | Rigless Australia - 1 | J.20.062408 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-06-26 21:30 |  | 2020-06-26 23:30 | 2020-06-28 08:30 |  |  | Moomba WL | FDPSystemUser | 2022-10-03 09:44 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.06 | A.1001568.06.01 | Chookoo 9 - Rental - Mechanical Plug Back Tool, 4.5 - | SANTOS LIMITED | Fixed Rental | Rigless Australia - 1 |  | RPI | PS-WL-NO | InComplete | Confirmed | Execute - PSD |  | Not Started | Not Started | In Progress |  | 2020-03-23 |  | 2020-03-30 18:00 | 2020-03-31 18:00 |  |  | Moomba WL | AGamero | 2020-11-13 10:25 | JColeman |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.05 | A.1001568.05.11 | U420 SQW Jobs | SANTOS LIMITED | ACRUS 1, LEPARD 3, WINDIGO 3 | Rigless Australia - 1 | J.23.168382 | RPI | PS-WL-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Not Started | In Progress | 2023-11-22 09:00 | 2023-11-21 15:00 |  | 2023-11-22 09:00 | 2023-12-01 23:59 |  | 2023-12-01 23:59 | Moomba WL | ADuong4 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 3 |  | L0 - No RO |  | 45.8 | 75 | 0 | 0 | 36.3 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Adel Mohammad Alhashemi | WL Production Services
P.1001568 | O.1001568.05 | A.1001568.05.01 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062579 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2020-06-01 | 2020-06-01 |  | 2020-06-01 | 2020-06-03 |  | 2020-06-03 | Moomba WL | AGamero | 2022-10-03 10:14 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.05 | A.1001568.05.08 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062542 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-22 |  | 2020-06-22 | 2020-06-24 |  |  | Moomba WL | OBass | 2022-10-03 10:10 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.05 | A.1001568.05.09 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062532 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-25 |  | 2020-06-25 | 2020-06-27 |  |  | Moomba WL | OBass | 2022-10-03 10:09 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.05 | A.1001568.05.07 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062531 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-19 |  | 2020-06-19 | 2020-06-21 |  |  | Moomba WL | OBass | 2022-10-03 10:09 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.05 | A.1001568.05.02 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062496 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-04 |  | 2020-06-04 | 2020-06-06 |  |  | Moomba WL | OBass | 2022-10-03 10:04 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.05 | A.1001568.05.10 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062471 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-28 |  | 2020-06-28 | 2020-06-30 |  |  | Moomba WL | OBass | 2022-10-03 09:53 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.05 | A.1001568.05.05 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062433 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-13 |  | 2020-06-13 | 2020-06-15 |  |  | Moomba WL | OBass | 2022-10-03 09:48 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.05 | A.1001568.05.04 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062432 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-10 |  | 2020-06-10 | 2020-06-12 |  |  | Moomba WL | OBass | 2022-10-03 09:47 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.05 | A.1001568.05.06 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062424 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-16 |  | 2020-06-16 | 2020-06-18 |  |  | Moomba WL | OBass | 2022-10-03 09:46 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.05 | A.1001568.05.03 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062415 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-07 |  | 2020-06-07 | 2020-06-09 |  |  | Moomba WL | OBass | 2022-10-03 09:45 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.39 | Merupa 3 | SANTOS LIMITED | Merupa 3 | Rigless Australia - 1 | J.20.062596 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-05-25 05:00 | 2020-05-25 |  | 2020-05-25 06:00 | 2020-05-27 06:00 |  | 2020-05-27 05:00 | Moomba WL | OBass | 2022-10-03 10:16 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.29 | Moomba 248 post frac | SANTOS LIMITED | MOOMBA 248 | Rigless Australia - 1 | J.20.062595 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-04-27 13:30 | 2020-04-25 |  | 2020-04-28 | 2020-04-30 |  | 2020-04-29 13:30 | Moomba WL | OBass | 2022-10-03 10:15 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 19844.52 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.24 | Moomba 247 post frac | SANTOS LIMITED | MOOMBA 247 | Rigless Australia - 1 | J.20.062594 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-04-29 23:00 | 2020-04-29 |  | 2020-04-30 | 2020-05-02 |  | 2020-05-01 23:00 | Moomba WL | OBass | 2022-10-03 10:15 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.04 | Merchant 1 SCMT | SANTOS LIMITED | Merchant 1 | Rigless Australia - 1 | J.20.062593 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-02-22 06:00 | 2020-02-19 06:00 |  | 2020-02-22 06:00 | 2020-02-23 18:00 |  | 2020-02-23 18:00 | Moomba WL | JAnderson60 | 2022-10-03 10:15 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 5478.19 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.27 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062578 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress | 2020-04-18 23:00 | 2020-04-19 |  | 2020-04-19 | 2020-04-21 |  | 2020-04-20 23:00 | Moomba WL | OBass | 2022-10-03 10:14 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.19 | Arrona 2 | SANTOS LIMITED | Aroona 2 | Rigless Australia - 1 | J.20.062577 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-03-23 06:00 | 2020-03-22 |  | 2020-03-23 06:00 | 2020-03-25 06:00 |  | 2020-03-25 06:00 | Moomba WL | OBass | 2022-10-03 10:14 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.14 | Seccante 3 GR-CCL Log | SANTOS LIMITED | Seccante 3 | Rigless Australia - 1 | J.20.062576 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress | 2020-03-13 | 2020-03-11 |  | 2020-03-13 | 2020-03-25 |  | 2020-03-18 | Moomba WL | OBass | 2022-10-03 10:14 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.38 | Lepard 3-Perfo | SANTOS LIMITED | LEPARD 3 | Rigless Australia - 1 | J.20.062567 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-05-22 |  | 2020-05-22 | 2020-05-24 |  |  | Moomba WL | OBass | 2022-10-03 10:13 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.33 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062566 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-05-07 |  | 2020-05-07 | 2020-05-09 |  |  | Moomba WL | OBass | 2022-10-03 10:13 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.30 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062565 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-04-28 |  | 2020-04-28 | 2020-04-30 |  |  | Moomba WL | OBass | 2022-10-03 10:12 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.22 | Vega 5 Link Perforations | SANTOS LIMITED | Vega 5 | Rigless Australia - 1 | J.20.062564 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-04-19 |  | 2020-04-20 | 2020-04-23 |  |  | Moomba WL | OBass | 2022-10-03 10:12 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.35 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062541 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-05-13 |  | 2020-05-13 | 2020-05-15 |  |  | Moomba WL | OBass | 2022-10-03 10:10 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.34 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062540 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-05-10 |  | 2020-05-10 | 2020-05-12 |  |  | Moomba WL | OBass | 2022-10-03 10:10 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.25 | Moomba 246 Post frac | SANTOS LIMITED | MOOMBA 246 | Rigless Australia - 1 | J.20.062539 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-04-30 |  | 2020-04-30 | 2020-05-06 |  |  | Moomba WL | OBass | 2022-10-03 10:10 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.15 | Seccante 6 GR-CCL Log | SANTOS LIMITED | Seccante 6 | Rigless Australia - 1 | J.20.062538 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-03-13 |  | 2020-03-13 | 2020-03-26 |  |  | Moomba WL | OBass | 2022-10-03 10:10 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.03 | Toolachee 42 Drift/2inHSD | SANTOS LIMITED | Toolachee 42 | Rigless Australia - 1 | J.20.062537 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-02-14 06:00 |  | 2020-02-14 06:00 | 2020-02-15 18:00 |  |  | Moomba WL | JAnderson60 | 2022-10-03 10:09 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 10799.74 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.37 | Cooroo North West 3 -SCMT | SANTOS LIMITED | Cooroo North West 3 | Rigless Australia - 1 | J.20.062530 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-05-19 |  | 2020-05-19 | 2020-05-21 |  |  | Moomba WL | OBass | 2022-10-03 10:09 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.17 | Charo 12 | SANTOS LIMITED | Charo 12 | Rigless Australia - 1 | J.20.062529 | RPI | PS-WL-Ops | Low | Operationally Complete | Execute - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-03-20 |  | 2020-03-20 | 2020-03-25 |  |  | Moomba WL | OBass | 2022-10-03 10:08 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 37355.58 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.13 | Charo 3 | SANTOS LIMITED | Charo 3 | Rigless Australia - 1 | J.20.062528 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-03-16 |  | 2020-03-16 | 2020-03-25 |  |  | Moomba WL | OBass | 2022-10-03 10:08 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 28683.63 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.36 | Coonatie 8 | SANTOS LIMITED | Coonatie 8 | Rigless Australia - 1 | J.20.062516 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-05-16 |  | 2020-05-17 06:00 | 2020-05-19 06:00 |  |  | Moomba WL | OBass | 2022-10-03 10:07 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.23 | Moomba 249 post frac | SANTOS LIMITED | MOOMBA 249 | Rigless Australia - 1 | J.20.062515 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-04-07 |  | 2020-08-23 12:00 | 2020-08-25 12:00 |  |  | Moomba WL | OBass | 2022-10-03 10:06 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 25825.28 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.12 | Jena 24 SCMT | SANTOS LIMITED | Jena 24 | Rigless Australia - 1 | J.20.062514 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-03-11 |  | 2020-03-12 | 2020-03-14 |  |  | Moomba WL | OBass | 2022-10-03 10:06 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.05 | Moomba 133 Plug and Cement | SANTOS LIMITED | Moomba 133 | Rigless Australia - 1 | J.20.062513 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-02-17 |  | 2020-02-19 | 2020-02-20 |  |  | Moomba WL | JAnderson60 | 2022-10-03 10:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.02 | Dullingari 43 2inHSD | SANTOS LIMITED | DULLINGARI 43 | Rigless Australia - 1 | J.20.062512 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-02-15 |  | 2020-02-15 | 2020-02-18 12:00 |  |  | Moomba WL | JAnderson60 | 2022-10-03 10:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 27120.27 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.11 | Chookoo 4 | SANTOS LIMITED | Chookoo 4 | Rigless Australia - 1 | J.20.062499 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-03-02 06:00 |  | 2020-03-02 06:00 | 2020-04-07 06:00 |  |  | Moomba WL | OBass | 2022-10-03 10:05 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 164178.97 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.41 | Chookoo 9- Angelique | SANTOS LIMITED | CHOOKOO 9 | Rigless Australia - 1 | J.20.062495 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | In Progress | In Progress | In Progress | 2020-02-26 06:00 | 2020-03-21 06:00 |  | 2020-03-21 06:00 | 2020-03-30 06:00 |  | 2020-03-15 19:30 | Moomba WL | ASinger2 | 2022-10-03 10:04 | FDPSystemUser |  | No |  |  |  |  | Angelique Singer |  | 79988.12 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.40 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062494 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-05-28 |  | 2020-05-28 | 2020-05-30 |  |  | Moomba WL | OBass | 2022-10-03 10:04 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.32 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062470 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-05-04 |  | 2020-05-04 | 2020-05-06 |  |  | Moomba WL | OBass | 2022-10-03 09:53 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.31 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062461 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-05-01 |  | 2020-05-01 | 2020-05-03 |  |  | Moomba WL | OBass | 2022-10-03 09:52 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.28 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062460 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-04-22 |  | 2020-04-22 | 2020-04-24 |  |  | Moomba WL | OBass | 2022-10-03 09:52 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.20 | Chookoo 9 MPBT | SANTOS LIMITED | Chookoo 9 | Rigless Australia - 1 | J.20.062459 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-03-31 |  | 2020-04-01 | 2020-04-03 |  |  | Moomba WL | OBass | 2022-10-03 09:52 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 73301.96 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.10 | Stokes 9 2.125" Link perforation | SANTOS LIMITED | Stokes 9 | Rigless Australia - 1 | J.20.062458 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-02-26 |  | 2020-02-26 | 2020-02-28 |  |  | Moomba WL | OBass | 2022-10-03 09:51 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 15122.18 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.08 | Bugito 3 SCMT | SANTOS LIMITED | BUGITO 003 | Rigless Australia - 1 | J.20.062457 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-19 06:00 |  | 2020-02-22 06:00 | 2020-02-24 18:00 |  |  | Moomba WL | SGilbert | 2022-10-03 09:51 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 5478.19 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.07 | Isoptera 3 SCMT | SANTOS LIMITED | Isoptera 3 | Rigless Australia - 1 | J.20.062442 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-19 06:00 |  | 2020-02-22 06:00 | 2020-02-23 18:00 |  |  | Moomba WL | SGilbert | 2022-10-03 09:49 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 5478.19 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.06 | Isoptera 2 SCMT | SANTOS LIMITED | Isoptera 2 | Rigless Australia - 1 | J.20.062431 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-19 06:00 |  | 2020-02-22 06:00 | 2020-02-23 18:00 |  |  | Moomba WL | SGilbert | 2022-10-03 09:47 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 5478.19 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.01 | Moomba 109 2inHSD | SANTOS LIMITED | Moomba 109 | Rigless Australia - 1 | J.20.062430 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-02-11 07:00 |  | 2020-02-14 09:00 | 2020-02-15 18:00 |  |  | Moomba WL | crowand | 2022-10-03 09:47 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 10420.38 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.16 | Seccante 4 GR-CCL Logging | SANTOS LIMITED | Seccante 4 | Rigless Australia - 1 | J.20.062423 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-03-14 |  | 2020-03-14 | 2020-03-26 |  |  | Moomba WL | OBass | 2022-10-03 09:46 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.26 | Well TBC | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062414 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | In Progress | In Progress | In Progress |  | 2020-04-16 |  | 2020-04-16 | 2020-04-18 |  |  | Moomba WL | OBass | 2022-10-03 09:45 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.21 | Namur 19 Post frac | SANTOS LIMITED | NAMUR 19 GAS PA (DEV J) DXCF | Rigless Australia - 1 | J.20.062407 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-04-25 |  | 2020-04-26 | 2020-05-27 |  |  | Moomba WL | OBass | 2022-10-03 09:44 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 12128.69 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.09 | Marabooka 6 Perforation | SANTOS LIMITED | Marabooka 6 | Rigless Australia - 1 | J.20.062405 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-02-23 |  | 2020-02-23 | 2020-02-26 12:00 |  |  | Moomba WL | SGilbert | 2022-10-03 09:43 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 6138.53 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.04 | A.1001568.04.18 | Barina 4 | SANTOS LIMITED | Barina | Rigless Australia - 1 |  | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-03-21 |  | 2020-03-23 06:00 | 2020-03-25 06:00 |  |  | Moomba WL | OBass | 2022-09-03 07:59 | walfaro |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.03 | A.1001568.03.01 | Munkarie 4_Cutter | SANTOS LIMITED | Munkarie Dev A | Rigless Australia - 1 |  | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2019-09-23 06:00 | 2019-09-22 20:00 | 2019-09-23 | 2019-09-23 06:00 | 2019-09-28 | 2019-09-29 | 2019-09-28 | Moomba WL | KKeese | 2019-10-01 01:11 | KKeese |  | No |  |  |  |  | Ihab Wahbi |  | 12550.88 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.34 | Well 34 | SANTOS LIMITED | Coolah 11 | Rigless Australia - 1 | J.20.062575 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2020-01-20 07:00 | 2020-01-20 |  | 2020-01-20 07:00 | 2020-01-21 13:00 |  | 2020-01-21 13:00 | Moomba WL | SGilbert | 2022-10-03 10:13 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.36 | Seccante 4_SCMT | SANTOS LIMITED | Seccante 4 | Rigless Australia - 1 | J.20.062563 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-03 09:00 |  | 2020-02-04 06:00 | 2020-02-08 16:00 |  |  | Moomba WL | AKharisma | 2022-10-03 10:12 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.30 | Coolah 11 SCMT | SANTOS LIMITED | Coolah 11 | Rigless Australia - 1 | J.20.062562 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-15 |  | 2020-01-18 18:00 | 2020-01-20 |  |  | Moomba WL | ymoradi2 | 2022-10-03 10:12 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.26 | Dullingari North 7_2 In HSD | SANTOS LIMITED | Dullingari North 7 | Rigless Australia - 1 | J.19.060448 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2019-12-29 |  | 2019-12-30 15:00 | 2020-01-01 12:00 |  |  | Moomba WL | ASetya | 2022-10-03 10:08 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 392.4 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.27 | Bow 1 | SANTOS LIMITED | Bow 1 | Rigless Australia - 1 | J.19.060443 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2019-12-31 |  | 2020-01-01 | 2020-01-04 |  |  | Moomba WL | KKeese | 2022-10-03 10:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  |  |  | 66.7 | 33.3 | 0 | 37.5 | 41.3 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.41 | Dullingari 43_Perf | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062511 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-13 |  | 2020-02-13 | 2020-02-14 18:00 |  |  | Moomba WL | JAnderson60 | 2022-10-03 10:06 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.38 | Seccante 6_SCMT | SANTOS LIMITED | Seccante 6 | Rigless Australia - 1 | J.20.062493 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-12 06:00 |  | 2020-02-12 15:00 | 2020-02-14 03:00 |  |  | Moomba WL | APutra7 | 2022-10-03 10:04 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.22 | Challum 3 Perfo | SANTOS LIMITED | Challum 3 | Rigless Australia - 1 | J.19.060441 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2019-12-17 13:00 |  | 2019-12-17 14:00 | 2019-12-19 12:00 |  |  | Moomba WL | ASetya | 2022-10-03 10:04 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 1168.45 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.28 | Wolgolla 6 | SANTOS LIMITED | Wolgolla 6 | Rigless Australia - 1 | J.20.062469 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-01-02 |  | 2020-01-02 | 2020-01-03 |  |  | Moomba WL | KKeese | 2022-10-03 09:53 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.40 | U420 Moomba 109 2in HSD | SANTOS LIMITED |  | Rigless Australia - 1 | J.20.062456 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-02-08 |  | 2020-02-09 15:00 | 2020-02-11 12:00 |  |  | Moomba WL | crowand | 2022-10-03 09:51 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.39 | Seccante 7_SCMT | SANTOS LIMITED | Seccante 7 | Rigless Australia - 1 | J.20.062455 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-12 08:00 |  | 2020-02-12 13:00 | 2020-02-14 11:00 |  |  | Moomba WL | APutra7 | 2022-10-03 09:51 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.37 | Seccante 3_SCMT | SANTOS LIMITED | SECCANTE 003 | Rigless Australia - 1 | J.20.062454 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Not Started | In Progress | 2020-02-06 18:00 | 2020-02-05 08:00 |  | 2020-02-06 18:00 | 2020-02-08 01:00 |  | 2020-02-08 01:00 | Moomba WL | AKharisma | 2022-10-03 09:51 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 37.5 | 23.8 |  | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.29 | Tartulla 9 plug setting | SANTOS LIMITED | Tartulla 9 | Rigless Australia - 1 | J.20.062453 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2020-01-13 07:00 |  | 2020-01-18 18:00 | 2020-01-19 21:00 |  |  | Moomba WL | ymoradi2 | 2022-10-03 09:51 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.25 | Plug and Bailer | SANTOS LIMITED | Cascade 1 | Rigless Australia - 1 | J.19.060434 | RPI | PS-WL-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2019-12-26 |  | 2019-12-26 | 2019-12-28 |  |  | Moomba WL | ASetya | 2022-10-03 09:51 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 11858.35 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.35 | Cherokee 1 | SANTOS LIMITED | Cherokee 1 | Rigless Australia - 1 | J.20.062413 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-30 |  | 2020-02-01 07:00 | 2020-02-06 13:00 |  |  | Moomba WL | SGilbert | 2022-10-03 09:45 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.21 | Well 15 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060419 | RPI | PS-WL-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-09 | 2019-12-04 |  | 2019-12-04 | 2019-12-05 |  | 2019-10-10 | Moomba WL | SGilbert | 2022-10-03 09:44 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.31 | Dilkera 4 SCMT | SANTOS LIMITED | Dilkera 4 | Rigless Australia - 1 | J.20.062406 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-15 |  | 2020-01-18 07:00 | 2020-01-21 13:00 |  |  | Moomba WL | SGilbert | 2022-10-03 09:44 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.20 | Well 14 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060418 | RPI | PS-WL-Ops | Low | Unconfirmed - 90% | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-09 | 2019-12-04 |  | 2019-12-04 | 2019-12-05 |  | 2019-10-10 | Moomba WL | SGilbert | 2022-10-03 09:43 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.23 | Challum West 1 Perfo | SANTOS LIMITED | CHALLUM WEST 1 | Rigless Australia - 1 | J.19.060417 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2019-12-20 |  | 2019-12-21 | 2019-12-23 |  |  | Moomba WL | ASetya | 2022-10-03 09:43 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 5835.87 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.33 | Toltec 1 SCMT | SANTOS LIMITED | Toltec 1 | Rigless Australia - 1 | J.20.062404 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-20 |  | 2020-01-20 07:00 | 2020-01-21 13:00 |  |  | Moomba WL | SGilbert | 2022-10-03 09:43 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 5752.11 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.19 | Juno 7 Packer Setting | SANTOS LIMITED | Juno 7 | Rigless Australia - 1 | J.19.060416 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-01 |  | 2019-12-01 | 2019-12-02 |  |  | Moomba WL | SGilbert | 2022-10-03 09:43 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 10077.97 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.07 | Milluna NorthEast 1 2" HSD | SANTOS LIMITED | MILLUNA NORTHEAST 1 | Rigless Australia - 1 | J.19.060415 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | In Progress | In Progress | In Progress | 2019-11-12 | 2019-10-26 |  | 2019-11-12 | 2019-11-13 |  | 2019-11-14 | Moomba WL | AGamero | 2022-10-03 09:43 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 8692.01 |  |  | L0 - No RO |  | 50 | 0 | 0 | 25 | 22.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.01 | Burke 7 | SANTOS LIMITED | Burke 3 | Rigless Australia - 1 | J.19.060414 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-09-18 09:00 |  | 2019-09-19 | 2019-09-22 |  |  | Moomba WL | JAnnear | 2022-10-03 09:43 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.18 | Lepard 2 Tubing Punch | SANTOS LIMITED | Lepard 2 | Rigless Australia - 1 | J.19.060413 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2019-11-29 |  | 2019-11-29 | 2019-12-01 |  |  | Moomba WL | SGilbert | 2022-10-03 09:43 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 8257.41 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.15 | Wackett East 1 Perfo | SANTOS LIMITED | WACKETT EAST 1 | Rigless Australia - 1 | J.19.060412 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | In Progress | In Progress | In Progress | 2019-10-03 23:00 | 2019-11-27 |  | 2019-11-29 | 2019-12-02 |  | 2019-12-02 | Moomba WL | AGamero | 2022-10-03 09:43 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 16021.57 |  |  | L0 - No RO |  | 50 | 0 | 0 | 25 | 22.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.09 | Namur 19 post frac | SANTOS LIMITED | NAMUR 19 GAS PA (DEV J) DXCF | Rigless Australia - 1 | J.19.060411 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2019-10-29 |  | 2019-10-29 | 2019-10-31 |  |  | Moomba WL | AGamero | 2022-10-03 09:43 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 12222.3 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.05 | Moomba 28 Packer Setting | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060410 | RPI | PS-WL-Ops | Low | Confirmed | Design - CEC |  | In Progress | In Progress | In Progress | 2019-09-29 11:00 | 2019-09-29 09:00 |  | 2019-09-29 11:00 | 2019-09-30 |  | 2019-09-30 | Moomba WL | SGilbert | 2022-10-03 09:42 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.17 | PlugSetting | SANTOS LIMITED | Big Lake 57 | Rigless Australia - 1 | J.19.060409 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2019-11-14 09:00 |  | 2019-11-14 10:00 | 2019-11-15 |  |  | Moomba WL | ymoradi2 | 2022-10-03 09:42 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.04 | Gidgealpa 64 PCR 3 | SANTOS LIMITED | GIDGEALPA 64 | Rigless Australia - 1 | J.19.060408 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2019-10-31 09:00 |  | 2019-10-31 11:00 | 2019-11-01 |  |  | Moomba WL | SGilbert | 2022-10-03 09:42 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.14 | Wackett 19 Plug Setting | SANTOS LIMITED | WACKETT 19 | Rigless Australia - 1 | J.19.060407 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2019-11-24 |  | 2019-11-25 20:00 | 2019-11-26 20:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:42 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 6017.54 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.12 | Della 19 WSO | SANTOS LIMITED | Della 19 | Rigless Australia - 1 | J.19.060406 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2019-11-05 |  | 2019-11-06 | 2019-11-07 |  |  | Moomba WL | AGamero | 2022-10-03 09:42 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 6017.54 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.10 | Gidgealpa 63 CBL / PNX | SANTOS LIMITED | GIDGEALPA 063 | Rigless Australia - 1 | J.19.060405 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-11-02 |  | 2019-11-02 | 2019-11-06 |  |  | Moomba WL | AGamero | 2022-10-03 09:42 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 33544.51 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.08 | Surlow 2 CPST | SANTOS LIMITED | Napowie 8 | Rigless Australia - 1 | J.19.060404 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2019-10-23 |  | 2019-10-23 | 2019-10-24 |  |  | Moomba WL | AGamero | 2022-10-03 09:42 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 5730.99 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.13 | Curri 1 Tubing Puncher | SANTOS LIMITED | Curri 1 | Rigless Australia - 1 | J.19.060403 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2019-11-24 |  | 2019-11-25 20:00 | 2019-11-25 22:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:42 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.02 | Roti 5-MPBT | SANTOS LIMITED | ROTI 5 | Rigless Australia - 1 | J.19.060402 | RPI | PS-WL-Ops | Low | Confirmed | Design - PSD |  | In Progress | In Progress | In Progress | 2019-10-15 11:00 | 2019-10-14 09:00 |  | 2019-10-15 11:00 | 2019-10-22 |  | 2019-10-22 | Moomba WL | JAnnear | 2022-10-03 09:42 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.11 | Mudera 1 Post frac perforations | SANTOS LIMITED | MUDERA 024 | Rigless Australia - 1 | J.19.060400 | RPI | PS-WL-Ops | Low | Confirmed | Execute - PSD |  | In Progress | Design Completed | In Progress | 2019-10-15 | 2019-11-04 |  | 2019-11-12 | 2019-11-13 |  | 2019-11-13 | Moomba WL | AGamero | 2022-10-03 09:41 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 6445.46 |  |  | L0 - No RO |  | 58.3 | 0 | 0 | 25 | 25 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.16 | Wackett South 1 Perfo . | SANTOS LIMITED | Wackett South 1 | Rigless Australia - 1 | J.19.060398 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2019-11-26 |  | 2019-11-26 | 2019-11-27 |  |  | Moomba WL | AGamero | 2022-10-03 09:41 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 2929.17 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.06 | Dullingari-22_Plug-Setting | SANTOS LIMITED | DULLINGARI 42 | Rigless Australia - 1 | J.19.060397 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | In Progress | Design Completed | In Progress | 2019-10-05 15:00 | 2019-10-05 14:00 |  | 2019-10-05 15:00 | 2019-10-08 08:00 |  | 2019-10-08 08:00 | Moomba WL | ymoradi2 | 2022-10-03 09:41 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  | L0 - No RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.32 | Ute 1 | SANTOS LIMITED | Ute (NFE) | Rigless Australia - 1 |  | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-01-29 |  | 2020-01-29 07:00 | 2020-02-04 13:00 |  |  | Moomba WL | SGilbert | 2020-11-13 10:25 | JColeman |  | No |  |  |  |  | Rob Twigg |  | 15664.72 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.24 | SCMT PNX | SANTOS LIMITED | Piute (NFE) | Rigless Australia - 1 |  | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-22 08:00 |  | 2019-12-22 16:00 | 2019-12-25 |  |  | Moomba WL | ASetya | 2020-11-13 10:25 | JColeman |  | No |  |  |  |  | Ihab Wahbi |  | 34115.89 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.02 | A.1001568.02.03 | Raffle North West 1 | SANTOS LIMITED | Raffle Northwest (NFE) | Rigless Australia - 1 |  | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2019-10-03 01:00 | 2019-10-03 | 2019-10-03 | 2019-10-03 01:00 | 2019-10-05 01:00 | 2019-10-06 | 2019-10-05 17:00 | Moomba WL | JAnnear | 2019-10-05 17:46 | SGilbert |  | No |  |  |  |  | Ihab Wahbi |  | 16113.65 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.01 | A.1001568.01.02 | Hera 3 | SANTOS LIMITED |  | Rigless Australia - 1 | J.19.060401 | RPI | PS-WL-Ops | InComplete | Confirmed | Design - CEC |  | Not Started | Not Started | In Progress |  | 2019-09-12 |  | 2019-09-12 | 2019-09-13 |  |  | Moomba WL | IWahbi | 2022-10-03 09:42 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001568 | O.1001568.01 | A.1001568.01.01 | Wellington 4 | SANTOS LIMITED | WELLINGTON 4 | Rigless Australia - 1 | J.19.060399 | RPI | PS-WL-Ops | Low | Confirmed | Prepare - Mob |  | In Progress | Not Started | In Progress | 2019-09-11 | 2019-09-11 |  | 2019-09-11 | 2019-09-12 |  | 2019-09-12 | Moomba WL | IWahbi | 2022-10-03 09:41 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO | [7 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Production Services
P.1001559 | O.1001559.01 | A.1001559.01.36 | Sceale 2 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.20.062403 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-23 02:00 |  | 2020-06-23 02:00 | 2020-06-27 02:00 |  |  | Moomba WL | OBass | 2022-10-03 09:41 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.20 | Parsons 11 | BEACH ENERGY LTD | Parsons 9 | Saxon Rig 184 | J.20.062402 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-06 02:00 |  | 2020-03-06 02:00 | 2020-03-10 02:00 |  |  | Moomba WL | OBass | 2022-10-03 09:41 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.08 | Butlers 11 | BEACH ENERGY LTD | Butlers 11 | Saxon Rig 184 | J.19.060396 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-11 06:00 |  | 2019-12-13 12:00 | 2019-12-16 12:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:41 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.34 | Kalladeina North 3 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.20.062401 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-05 02:00 |  | 2020-06-05 02:00 | 2020-06-09 02:00 |  |  | Moomba WL | OBass | 2022-10-03 09:41 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.28 | Bauer App 5 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.20.062400 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-08-10 02:00 |  | 2020-08-10 02:00 | 2020-08-14 02:00 |  |  | Moomba WL | OBass | 2022-10-03 09:40 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.26 | Bauer App 3 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.20.062399 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-07-20 02:00 |  | 2020-07-20 02:00 | 2020-07-24 02:00 |  |  | Moomba WL | OBass | 2022-10-03 09:40 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.25 | Bauer App 2 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.20.062398 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-07-11 02:00 |  | 2020-07-11 02:00 | 2020-07-15 02:00 |  |  | Moomba WL | OBass | 2022-10-03 09:40 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.02 | ARNO 2 | BEACH ENERGY LTD | ARNO 2 | Saxon Rig 184 | J.19.060394 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-09-25 |  | 2019-09-26 | 2019-10-01 |  |  | Moomba WL | AGamero | 2022-10-03 09:40 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 29629.63 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.31 | Kalladeina 12 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.20.062394 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-06 02:00 |  | 2020-05-06 02:00 | 2020-05-10 02:00 |  |  | Moomba WL | OBass | 2022-10-03 09:40 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.18 | Parsons 9 | BEACH ENERGY LTD | Parsons 9 | Saxon Rig 184 | J.20.062393 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-19 15:00 |  | 2020-02-22 02:00 | 2020-02-25 02:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:39 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.15 | Balgowan 2 | BEACH ENERGY LTD | BALgowan 1 | Saxon Rig 184 | J.20.062392 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-26 15:00 |  | 2020-01-29 02:00 | 2020-02-06 02:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:39 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.35 | Congony 6 | BEACH ENERGY LTD | Congony 6 | Saxon Rig 184 | J.20.062391 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-13 13:00 |  | 2020-05-13 13:00 | 2020-05-17 13:00 |  |  | Moomba WL | OBass | 2022-10-03 09:39 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.03 | ES Logging | BEACH ENERGY LTD | ARNO 3 | Saxon Rig 184 | J.19.060391 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-10-05 11:00 |  | 2019-10-06 12:00 | 2019-10-09 12:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:39 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 3573.75 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.17 | Balgowan 3 | BEACH ENERGY LTD | Balgowan 3 | Saxon Rig 184 | J.20.062388 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-13 15:00 |  | 2020-02-17 06:00 | 2020-02-20 06:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:39 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.14 | Rincon 3 | BEACH ENERGY LTD | Rincon 3 | Saxon Rig 184 | J.20.062387 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-16 15:00 |  | 2020-01-18 18:00 | 2020-01-21 18:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:39 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.11 | Callawonga 20 | BEACH ENERGY LTD | CALLAWONGA 20 | Saxon Rig 184 | J.19.060390 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-11-23 |  | 2019-11-24 | 2019-11-25 21:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:38 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.12 | Callawonga 21 | BEACH ENERGY LTD | CALLAWONGA 21 | Saxon Rig 184 | J.19.060389 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-11-28 |  | 2019-11-29 22:00 | 2019-12-01 22:00 |  |  | Moomba WL | CXu16 | 2022-10-03 09:38 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.32 | Kalladeina 11 | BEACH ENERGY LTD | Kalladeina 11 | Saxon Rig 184 | J.20.062383 | RPE | ES-OH-Ops | Low | Operationally Complete | Execute - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-23 09:00 |  | 2020-04-23 09:00 | 2020-04-25 09:00 |  |  | Moomba WL | OBass | 2022-10-03 09:38 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 115497.08 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.27 | Bauer App 4 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.20.062382 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-07-29 02:00 |  | 2020-07-29 02:00 | 2020-08-02 02:00 |  |  | Moomba WL | OBass | 2022-10-03 09:38 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.16 | Balgowan 4 | BEACH ENERGY LTD | Balgowan 4 | Saxon Rig 184 | J.20.062381 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-03 15:00 |  | 2020-02-07 02:00 | 2020-02-09 02:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:38 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.06 | ES Logging | BEACH ENERGY LTD | BAUER NORTH 3 | Saxon Rig 184 | J.19.060388 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-10-30 12:00 |  | 2019-10-31 02:00 | 2019-11-03 02:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:38 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.29 | Kalladeina 10 | BEACH ENERGY LTD | Kalladeina 10 | Saxon Rig 184 | J.20.062379 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-01 15:00 |  | 2020-06-28 | 2020-07-02 |  |  | Moomba WL | OBass | 2022-10-03 09:37 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 78752.44 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.07 | Butlers 10 | BEACH ENERGY LTD | Butlers 10 | Saxon Rig 184 | J.19.060387 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-04 06:00 |  | 2019-12-13 06:00 | 2019-12-16 06:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:37 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.05 | ES Logging | BEACH ENERGY LTD | BAUER NORTH 2 | Saxon Rig 184 | J.19.060386 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-10-21 18:00 |  | 2019-10-23 17:00 | 2019-10-26 17:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:37 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.37 | Kalladeina North 2 | BEACH ENERGY LTD | Kalladeina North 2 | Saxon Rig 184 | J.20.062377 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-06 13:00 |  | 2020-04-18 | 2020-04-22 |  |  | Moomba WL | ASinger2 | 2022-10-03 09:37 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 115497.08 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.22 | Sellicks South 1 | BEACH ENERGY LTD | Sellicks South 1 | Saxon Rig 184 | J.20.062376 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-16 11:00 |  | 2020-03-28 10:00 | 2020-04-11 09:00 |  |  | Moomba WL | OBass | 2022-10-03 09:37 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 166276.8 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.13 | Rincon 2_QuadCombo_MDT_DST | BEACH ENERGY LTD | Rincon 2 | Saxon Rig 184 | J.20.062375 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-08 15:00 |  | 2020-01-19 18:00 | 2020-01-22 18:00 |  |  | Moomba WL | ASteinbach2 | 2022-10-03 09:37 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.10 | Butlers 13 | BEACH ENERGY LTD | Butlers 13 | Saxon Rig 184 | J.19.060385 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-28 06:00 |  | 2019-12-28 06:00 | 2019-12-31 06:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:37 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.33 | Bauer North 5 | BEACH ENERGY LTD | Bauer North 5 | Saxon Rig 184 | J.20.062369 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-21 02:00 |  | 2020-05-21 02:00 | 2020-05-24 02:00 |  |  | Moomba WL | OBass | 2022-10-03 09:36 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 32131.25 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.21 | Glenelg North 1 | BEACH ENERGY LTD | Glenelg North 1 | Saxon Rig 184 | J.20.062368 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-03-02 18:00 |  | 2020-04-10 18:00 | 2020-04-14 18:00 |  |  | Moomba WL | OBass | 2022-10-03 09:36 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 66471.73 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.19 | Parsons 10 | BEACH ENERGY LTD | Parsons 9 | Saxon Rig 184 | J.20.062367 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-26 15:00 |  | 2020-02-29 02:00 | 2020-03-03 02:00 |  |  | Moomba WL | OBass | 2022-10-03 09:36 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.09 | Butlers 12 | BEACH ENERGY LTD | Butlers 12 | Saxon Rig 184 | J.19.060380 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-20 18:00 |  | 2019-12-21 20:00 | 2019-12-24 20:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:36 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 50 | 33.3 | 0 | 25 | 32.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.24 | Bauer App 1 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.20.062362 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-07-02 02:00 |  | 2020-07-02 02:00 | 2020-07-06 02:00 |  |  | Moomba WL | OBass | 2022-10-03 09:35 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.23 | Kalladeina 9- 8.5in OH Section | BEACH ENERGY LTD | Kalladeina 9 | Saxon Rig 184 | J.20.062353 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-24 02:00 |  | 2020-03-28 13:00 | 2020-04-01 13:00 |  |  | Moomba WL | OBass | 2022-10-03 09:34 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 115497.08 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.01 | ES Logging | BEACH ENERGY LTD | ARNO 4 | Saxon Rig 184 | J.19.060378 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-09-16 |  | 2019-09-17 | 2019-09-20 |  |  | Moomba WL | miqbal13 | 2022-10-03 09:34 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 59974.01 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.30 | Kalladeina North 2 | BEACH ENERGY LTD |  | Saxon Rig 184 | J.20.062349 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-10 02:00 |  | 2020-04-11 02:00 | 2020-04-15 02:00 |  |  | Moomba WL | OBass | 2022-10-03 09:33 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001559 | O.1001559.01 | A.1001559.01.04 | ES Logging | BEACH ENERGY LTD | BAUER NORTHWEST 002 | Saxon Rig 184 | J.19.060375 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-10-10 12:00 |  | 2019-10-13 07:00 | 2019-10-16 07:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:33 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001557 | O.1001557.01 | A.1001557.01.02 | ES Logging (QC-FMI-Sampling) | BEACH ENERGY LTD | BAUER 049 | Saxon Rig 185 | J.19.060393 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2019-10-24 16:22 | 2019-10-31 07:00 |  | 2019-11-02 07:00 | 2019-11-05 07:00 |  | 2019-10-27 07:00 | Moomba WL | AGamero | 2022-10-03 09:40 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 41.7 | 0 | 0 | 25 | 20 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001557 | O.1001557.01 | A.1001557.01.01 | ES Logging | BEACH ENERGY LTD | BAUER 45 | Saxon Rig 185 | J.19.060392 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-10-14 |  | 2019-10-14 | 2019-10-17 |  |  | Moomba WL | miqbal13 | 2022-10-03 09:40 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 59974.01 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001557 | O.1001557.01 | A.1001557.01.03 | ES Logging | BEACH ENERGY LTD | BAUER 50 | Saxon Rig 185 | J.19.060384 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-10-24 01:00 |  | 2019-10-25 01:00 | 2019-10-28 01:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:37 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001557 | O.1001557.01 | A.1001557.01.04 | Butlers App 1 | BEACH ENERGY LTD |  | Saxon Rig 185 | J.20.062366 | RPE | ES-OH-Ops | InComplete | Cancelled | Close - PSD |  | Not Required | Not Started | In Progress |  | 2020-01-03 |  | 2020-01-04 | 2020-01-05 |  |  | Moomba WL | OBass | 2022-10-03 09:35 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001556 | O.1001556.08 | A.1001556.08.01 | MERANJI 33 | SANTOS LIMITED | MERANJI 33 | ENSIGN 974 | J.24.117182 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-06-15 | 2024-06-14 |  | 2024-06-15 | 2024-06-26 23:59 |  | 2024-06-26 23:59 | Moomba WL | FShallal | 2024-08-13 16:38 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.07 | A.1001556.07.01 | Nephrite South 15 (GAS DEV A) DXCF | SANTOS LIMITED | Well #1 | ENSIGN 974 | J.24.117180 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-06-18 18:00 | 2024-06-16 |  | 2024-06-18 18:00 | 2024-06-22 17:59 |  | 2024-06-22 17:59 | Moomba WL | FShallal | 2024-06-26 14:53 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.06 | A.1001556.06.01 | Gidgealpa 69 | SANTOS LIMITED | GIDGEALPA 69 | ENSIGN 974 | J.24.039324 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-01-10 22:00 | 2024-01-10 09:00 |  | 2024-01-10 22:00 | 2024-01-14 23:59 |  | 2024-01-14 23:59 | Moomba WL | HChapman3 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Jakarta | Shameer Mumtaz Ali |  | 0 | 2 |  | L2 - Shift RO |  | 79.2 | 16.7 | 0 | 0 | 28.7 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.05 | A.1001556.05.01 | Nephrite South 15 (GAS DEV A) DXCF | SANTOS LIMITED | NEPHRITE SOUTH 15 | ENSIGN 974 | J.23.171992 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-12-04 18:00 | 2023-12-02 |  | 2023-12-04 18:00 | 2023-12-08 17:59 |  | 2023-12-08 17:59 | Moomba WL | JDagdag | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 44787.27 | 1 |  | L3 - Full RO |  | 75 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.05 | A.1001556.05.02 | Tindilpie 19 | SANTOS LIMITED | TINDILPIE 19 | ENSIGN 974 | J.23.175289 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-12-19 09:00 | 2023-12-19 05:00 |  | 2023-12-19 09:00 | 2023-12-23 08:59 |  | 2023-12-23 08:59 | Moomba WL | JDagdag | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 44787.27 | 2 |  | L3 - Full RO |  | 91.7 | 83.3 | 0 | 100 | 82.5 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Adel Mohammad Alhashemi | WL Evaluation Services
P.1001556 | O.1001556.05 | A.1001556.05.03 | Gidgealpa 69 | SANTOS LIMITED | GIDGEALPA 69 | ENSIGN 974 | J.24.039357 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-01-10 22:00 | 2024-01-10 09:00 |  | 2024-01-10 22:00 | 2024-01-14 21:59 |  | 2024-01-14 21:59 | Moomba WL | HChapman3 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 46783.57 | 0 |  | L2 - Shift RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.05 | A.1001556.05.04 | Gidgealpa 70 | SANTOS LIMITED | GIDGEALPA 70 | ENSIGN 974 | J.24.043706 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-01-21 | 2024-01-21 |  | 2024-01-21 | 2024-01-25 23:59 |  | 2024-01-25 23:59 | Moomba WL | JDagdag | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L2 - Shift RO |  | 83.3 | 100 | 0 | 100 | 85 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.05 | A.1001556.05.05 | Gidgealpa 71 | SANTOS LIMITED | GIDGEALPA 71 | ENSIGN 974 | J.24.049395 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2024-02-03 15:00 | 2024-02-03 07:00 |  | 2024-02-03 15:00 | 2024-02-08 14:59 |  | 2024-02-08 14:59 | Moomba WL | HChapman3 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Jakarta | Shameer Mumtaz Ali |  | 0 | 2 |  | L2 - Shift RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Evaluation Services
P.1001556 | O.1001556.05 | A.1001556.05.06 | Gidgealpa 72 | SANTOS LIMITED | GIDGEALPA 72 | ENSIGN 974 | J.24.058750 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-02-22 10:00 | 2024-02-22 02:00 |  | 2024-02-22 10:00 | 2024-02-27 09:59 |  | 2024-02-27 09:59 | Moomba WL | HChapman3 | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Jakarta | Shameer Mumtaz Ali |  | 0 | 2 |  | L2 - Shift RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.48 | Napowie 13 | SANTOS LIMITED | NAPOWIE 13 | ENSIGN 974 | J.23.083610 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-07-08 08:00 | 2023-07-08 06:00 |  | 2023-07-08 08:00 | 2023-07-12 07:59 |  | 2023-07-12 07:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Jakarta | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 75 | 80 |  | 0 |  |  |  | 0 |  |  |  | Mohammad Adel Mohammad Alhashemi | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.50 | Meranji 30 | SANTOS LIMITED | MERANJI 30 | ENSIGN 974 | J.23.083612 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-08-18 12:00 | 2023-08-18 10:00 |  | 2023-08-18 12:00 | 2023-08-22 11:59 |  | 2023-08-22 11:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Jakarta | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.52 | Meranji 28 | SANTOS LIMITED | MERANJI 28 | ENSIGN 974 | J.23.083614 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-07-26 23:30 | 2023-07-26 23:00 |  | 2023-07-26 23:30 | 2023-07-30 23:29 |  | 2023-07-30 23:29 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Abu Dhabi | Mazhar Iqbal |  | 71336.56 | 4 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.51 | Meranji 31 | SANTOS LIMITED | MERANJI 31 | ENSIGN 974 | J.23.083613 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-08-29 12:00 | 2023-08-29 12:00 |  | 2023-08-29 12:00 | 2023-09-02 11:59 |  | 2023-09-02 11:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Abu Dhabi | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 83.3 | 100 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.53 | Meranji 29 | SANTOS LIMITED | MERANJI 29 | ENSIGN 974 | J.23.085653 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-08-05 08:00 | 2023-08-05 06:00 | 2023-08-04 03:00 | 2023-08-05 08:00 | 2023-08-13 07:59 | 2023-08-14 | 2023-08-13 07:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 71336.56 | 2 |  | L3 - Full RO |  | 83.3 | 100 | 0 | 100 | 85 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.59 | Meranji 32 | SANTOS LIMITED | MERANJI 32 | ENSIGN 974 | J.23.119976 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2023-09-09 08:00 | 2023-09-07 06:00 | 2023-09-08 13:00 | 2023-09-09 08:00 | 2023-09-13 07:59 | 2023-09-13 23:00 | 2023-09-13 07:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 1 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.60 | Adzuki 1 (GAS NFE A) DXCF | SANTOS LIMITED | ADZUKI 1 | ENSIGN 974 | J.23.122627 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-10-14 08:00 | 2023-10-11 06:00 | 2023-10-13 | 2023-10-14 08:00 | 2023-10-18 07:59 | 2023-10-19 | 2023-10-18 07:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 1 |  | L3 - Full RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 2 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.61 | Nephrite South 14 (GAS DEV B) DXCF | SANTOS LIMITED | NEPHRITE SOUTH 14 | ENSIGN 974 | J.23.122628 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-11-18 21:00 | 2023-11-09 08:00 | 2023-11-06 | 2023-11-10 05:00 | 2023-11-14 04:59 | 2023-11-15 | 2023-11-20 21:00 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 3 |  | L3 - Full RO |  | 100 | 100 | 0 | 87.5 | 86.3 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.64 | TINDILPIE 19 | SANTOS LIMITED |  | ENSIGN 974 | J.23.122631 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress | 2023-12-16 21:00 | 2023-12-12 06:00 | 2023-12-16 14:00 | 2023-12-17 08:00 | 2023-12-21 07:59 | 2023-12-22 | 2023-12-20 20:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 2 |  | L3 - Full RO |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.62 | Nephrite South 15 (GAS DEV A) DXCF | SANTOS LIMITED |  | ENSIGN 974 | J.23.122629 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-12-04 08:00 | 2023-11-13 06:00 | 2023-12-03 14:00 | 2023-12-04 08:00 | 2023-12-08 07:59 | 2023-12-09 | 2023-12-08 07:59 | Moomba WL | KKeese | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.71 | Tindilpie 19 | SANTOS LIMITED |  | ENSIGN 974 | J.23.175303 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | Not Started | Not Started | Not Started |  | 2023-12-16 |  | 2023-12-17 | 2023-12-21 23:59 |  |  | Moomba WL | JDagdag | 2024-08-21 15:52 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 0 |  | L3 - Full RO |  | 8.3 | 0 | 0 | 0 | 2.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.76 | Mearnji 6 | SANTOS LIMITED | TIRRAWARRA 101 | ENSIGN 974 | J.24.050660 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-06-03 08:00 | 2024-06-03 06:00 | 2024-06-02 13:00 | 2024-06-03 08:00 | 2024-06-07 07:59 | 2024-06-07 23:00 | 2024-06-07 07:59 | Moomba WL | KKeese | 2024-05-08 08:24 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.75 | Meranji 4 | SANTOS LIMITED | TIRRAWARRA 101 | ENSIGN 974 | J.24.050659 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-05-20 08:00 | 2024-05-20 06:00 | 2024-05-19 13:00 | 2024-05-20 08:00 | 2024-05-24 07:59 | 2024-05-24 23:00 | 2024-05-24 07:59 | Moomba WL | KKeese | 2024-04-24 09:58 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.74 | Meranji 3 | SANTOS LIMITED | TIRRAWARRA 101 | ENSIGN 974 | J.24.050661 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-05-01 08:00 | 2024-05-01 06:00 | 2024-04-30 13:00 | 2024-05-01 08:00 | 2024-05-05 07:59 | 2024-05-05 23:00 | 2024-05-05 07:59 | Moomba WL | KKeese | 2024-04-24 09:58 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.70 | 974 Sub Well 2 | SANTOS LIMITED | TIRRAWARRA 101 | ENSIGN 974 | J.24.022178 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-03-24 08:00 | 2024-03-24 06:00 | 2024-03-23 14:00 | 2024-03-24 08:00 | 2024-03-28 07:59 | 2024-03-29 | 2024-03-28 07:59 | Moomba WL | KKeese | 2024-04-02 15:01 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.69 | 974 Sub Well 1 | SANTOS LIMITED | TIRRAWARRA 101 | ENSIGN 974 | J.24.022177 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-03-12 08:00 | 2024-03-12 06:00 | 2024-03-11 14:00 | 2024-03-12 08:00 | 2024-03-16 07:59 | 2024-03-17 | 2024-03-16 07:59 | Moomba WL | KKeese | 2024-04-02 15:01 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.68 | Gidgealpa 4 | SANTOS LIMITED | TIRRAWARRA 101 | ENSIGN 974 | J.24.021442 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-03-01 08:00 | 2024-03-01 06:00 | 2024-02-29 14:00 | 2024-03-01 08:00 | 2024-03-05 07:59 | 2024-03-06 | 2024-03-05 07:59 | Moomba WL | KKeese | 2024-04-02 15:01 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.67 | Gidgealpa 3 | SANTOS LIMITED | TIRRAWARRA 101 | ENSIGN 974 | J.24.021441 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-02-19 08:00 | 2024-02-19 06:00 |  | 2024-02-19 08:00 | 2024-02-23 07:59 |  | 2024-02-23 07:59 | Moomba WL | KKeese | 2024-04-02 14:58 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.73 | Meranji 2 | SANTOS LIMITED | TIRRAWARRA 101 | ENSIGN 974 | J.24.050658 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-04-22 08:00 | 2024-04-22 06:00 |  | 2024-04-22 08:00 | 2024-04-26 07:59 |  | 2024-04-26 07:59 | Moomba WL | KKeese | 2024-04-02 12:52 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.72 | Meranji 1 | SANTOS LIMITED | TIRRAWARRA 101 | ENSIGN 974 | J.24.050657 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-04-08 08:00 | 2024-04-08 06:00 |  | 2024-04-08 08:00 | 2024-04-12 07:59 |  | 2024-04-12 07:59 | Moomba WL | KKeese | 2024-04-02 12:52 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.66 | Gidgealpa 2 | SANTOS LIMITED | TIRRAWARRA 101 | ENSIGN 974 | J.24.021440 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-02-01 08:00 | 2024-02-01 06:00 |  | 2024-02-01 08:00 | 2024-02-05 07:59 |  | 2024-02-05 07:59 | Moomba WL | KKeese | 2024-02-28 09:41 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.65 | Gidgealpa 1 | SANTOS LIMITED | TIRRAWARRA 101 | ENSIGN 974 | J.24.021439 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2024-01-12 08:00 | 2024-01-12 06:00 |  | 2024-01-12 08:00 | 2024-01-16 07:59 |  | 2024-01-16 07:59 | Moomba WL | KKeese | 2024-01-10 10:44 | KKeese |  | No |  |  |  | ROE WL Mumbai | Shameer Mumtaz Ali |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 2 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.58 | Tindilpie North Gas 2 | SANTOS LIMITED | TIRRAWARRA 101 | ENSIGN 974 | J.23.087859 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-11-28 08:00 | 2023-11-28 06:00 |  | 2023-11-28 08:00 | 2023-12-02 07:59 |  | 2023-12-02 07:59 | Moomba WL | KKeese | 2023-12-30 08:21 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.63 | Nephrite South 16 (GAS DEV C) DXCF | SANTOS LIMITED | TIRRAWARRA 101 | ENSIGN 974 | J.23.122630 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-12-25 08:00 | 2023-12-25 06:00 |  | 2023-12-25 08:00 | 2023-12-29 07:59 |  | 2023-12-29 07:59 | Moomba WL | KKeese | 2023-12-30 08:21 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 1 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.55 | Nepherite South 15 | SANTOS LIMITED | TIRRAWARRA 101 | ENSIGN 974 | J.23.085655 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-30 08:00 | 2023-10-30 06:00 | 2023-10-29 14:00 | 2023-10-30 08:00 | 2023-11-03 07:59 | 2023-11-04 | 2023-11-03 07:59 | Moomba WL | KKeese | 2023-08-17 17:25 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mohammad Rashed Al Rony |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.57 | Tindilpie North Gas | SANTOS LIMITED | TIRRAWARRA 101 | ENSIGN 974 | J.23.085657 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-11-08 08:00 | 2023-11-08 06:00 | 2023-11-07 14:00 | 2023-11-08 08:00 | 2023-11-12 07:59 | 2023-11-13 | 2023-11-12 07:59 | Moomba WL | KKeese | 2023-08-17 17:25 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.56 | Nepherit South 16 | SANTOS LIMITED | TIRRAWARRA 101 | ENSIGN 974 | J.23.085656 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-13 08:00 | 2023-10-13 06:00 | 2023-10-12 14:00 | 2023-10-13 08:00 | 2023-10-17 07:59 | 2023-10-18 | 2023-10-17 07:59 | Moomba WL | KKeese | 2023-08-17 17:24 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.49 | Adzuki | SANTOS LIMITED | TIRRAWARRA 101 | ENSIGN 974 | J.23.083611 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-07-20 08:00 | 2023-07-20 06:00 | 2023-07-19 13:00 | 2023-07-20 08:00 | 2023-07-24 07:59 | 2023-07-24 23:00 | 2023-07-24 07:59 | Moomba WL | KKeese | 2023-07-31 08:10 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 3 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.45 | Merupa 5 | SANTOS LIMITED | MERUPA 5 | ENSIGN 974 | J.23.041197 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-06-22 08:00 | 2023-06-20 06:00 |  | 2023-06-22 08:00 | 2023-06-27 07:59 |  | 2023-06-27 07:59 | Moomba WL | KKeese | 2023-06-26 22:13 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 45701.3 | 1 |  | L0 - No RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.46 | Merupa 4 | SANTOS LIMITED | MERUPA 4 | ENSIGN 974 | J.23.041198 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-06-10 17:00 | 2023-06-09 06:00 |  | 2023-06-10 17:00 | 2023-06-14 16:59 |  | 2023-06-14 16:59 | Moomba WL | KKeese | 2023-06-17 13:53 | YPouryan |  | No |  |  |  |  | Mazhar Iqbal |  | 45701.3 | 1 |  | L0 - No RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.43 | Tirrawarra 105 | SANTOS LIMITED | TIRRAWARRA 105 | ENSIGN 974 | J.23.041195 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-09 09:00 | 2023-04-09 06:00 |  | 2023-04-09 08:00 | 2023-04-13 06:59 |  | 2023-04-13 07:59 | Moomba WL | KKeese | 2023-06-13 10:03 | DYanagawa |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 45701.3 | 2 |  | L2 - Shift RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.47 | Napowie 11 | SANTOS LIMITED | NAPOWIE 11 | ENSIGN 974 | J.23.041199 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-05-11 08:00 | 2023-05-11 06:00 |  | 2023-05-11 08:00 | 2023-05-18 07:59 |  | 2023-05-18 07:59 | Moomba WL | KKeese | 2023-06-13 09:10 | DYanagawa |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 45701.3 | 2 |  | L2 - Shift RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.27 | Napowie 12 | SANTOS LIMITED | NAPOWIE 12 | ENSIGN 974 | J.22.110010 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-05-28 22:00 | 2023-05-28 |  | 2023-05-29 | 2023-06-01 23:59 |  | 2023-06-01 23:59 | Moomba WL | KKeese | 2023-06-13 08:35 | DYanagawa |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 45701.3 | 2 |  | L1 - Support RO |  | 91.7 | 66.7 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.54 | Nephrite South 14 | SANTOS LIMITED | TIRRAWARRA 101 | ENSIGN 974 | J.23.085654 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-10-17 08:00 | 2023-10-17 06:00 |  | 2023-10-17 08:00 | 2023-10-21 07:59 |  | 2023-10-21 07:59 | Moomba WL | KKeese | 2023-05-21 17:35 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  | L3 - Full RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.44 | Tirrawarra 107 | SANTOS LIMITED | TIRRAWARRA 107 | ENSIGN 974 | J.23.041196 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-04-29 12:00 | 2023-04-28 06:00 |  | 2023-04-29 12:00 | 2023-05-03 11:59 |  | 2023-05-06 | Moomba WL | KKeese | 2023-05-06 12:36 | ysaeedabadian |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 50728.44 | 4 |  | L3 - Full RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.36 | Tirrawarra 101 - QC-XPT | SANTOS LIMITED | TIRRAWARRA 101 | ENSIGN 974 | J.23.011742 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-01-25 08:00 | 2023-01-25 06:00 |  | 2023-01-25 08:00 | 2023-01-29 07:59 |  | 2023-01-29 07:59 | Moomba WL | KKeese | 2023-03-23 08:45 | eismail |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 44787.27 | 2 |  | L3 - Full RO |  | 91.7 | 100 | 0 | 50 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.39 | Tirrawarra 109 | SANTOS LIMITED | TIRRAWARRA 109 | ENSIGN 974 | J.23.012004 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | In Progress | Not Required | In Progress | 2023-03-10 16:00 | 2023-03-09 |  | 2023-03-10 18:00 | 2023-03-14 17:59 |  | 2023-03-14 17:59 | Moomba WL | eismail | 2023-03-12 17:30 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 44787.27 | 2 |  | L0 - No RO |  | 66.7 | 83.3 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.40 | Tirrawarra 104 | SANTOS LIMITED |  | ENSIGN 974 | J.23.012005 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-03-24 16:00 | 2023-03-23 |  | 2023-03-24 18:00 | 2023-03-28 17:59 |  | 2023-03-28 17:59 | Moomba WL | eismail | 2023-03-10 10:39 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.32 | Napowie 11 | SANTOS LIMITED | Dullingari 62 | ENSIGN 974 | J.22.110028 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-14 16:00 | 2022-12-14 |  | 2022-12-14 18:00 | 2022-12-18 17:59 |  | 2022-12-18 17:59 | Moomba WL | KKeese | 2023-03-07 18:30 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.33 | Napowie 12 | SANTOS LIMITED | Dullingari 62 | ENSIGN 974 | J.22.121236 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2022-12-27 16:00 | 2022-12-27 |  | 2022-12-27 18:00 | 2022-12-31 17:59 |  | 2022-12-31 17:59 | Moomba WL | KKeese | 2023-03-07 18:18 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.38 | Nephrite South Gas DEV A | SANTOS LIMITED |  | ENSIGN 974 | J.23.012003 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-02-24 16:00 | 2023-02-23 |  | 2023-02-24 18:00 | 2023-02-28 17:59 |  | 2023-02-28 17:59 | Moomba WL | eismail | 2023-02-10 07:22 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.37 | Nephrite South Gas Dev B | SANTOS LIMITED | Dullingari 62 | ENSIGN 974 | J.23.011743 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-02-12 16:00 | 2023-02-12 |  | 2023-02-12 18:00 | 2023-02-16 17:59 |  | 2023-02-16 17:59 | Moomba WL | KKeese | 2023-02-10 07:22 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 3 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.34 | Tirrawarra 100 Triple Combo | SANTOS LIMITED | TIRRAWARRA 100 | ENSIGN 974 | J.23.011740 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2023-01-02 18:00 | 2023-01-02 |  | 2023-01-02 18:00 | 2023-01-06 17:59 |  | 2023-01-06 17:59 | Moomba WL | KKeese | 2023-01-07 18:47 | YPouryan |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 28369.69 | 1 |  | L2 - Shift RO |  | 83.3 | 66.7 | 0 | 100 | 75 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.42 | Tirrawarra 99 | SANTOS LIMITED | TIRRAWARRA 99 | ENSIGN 974 | J.22.134686 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-12-19 18:00 | 2022-12-18 |  | 2022-12-19 18:00 | 2022-12-26 17:59 |  | 2022-12-26 17:59 | Moomba WL | eismail | 2023-01-03 10:19 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 44787.27 | 2 |  | L3 - Full RO | [7 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.35 | Merupa 5 | SANTOS LIMITED | Dullingari 62 | ENSIGN 974 | J.23.011741 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress | 2023-01-13 18:00 | 2023-01-13 |  | 2023-01-13 18:00 | 2023-01-17 17:59 |  | 2023-01-17 17:59 | Moomba WL | KKeese | 2022-12-29 13:12 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.31 | Quartpot 2 | SANTOS LIMITED | QUARTPOT 2 | ENSIGN 974 | J.22.110027 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-12-05 18:00 | 2022-12-04 |  | 2022-12-05 18:00 | 2022-12-12 17:59 |  | 2022-12-12 17:59 | Moomba WL | KKeese | 2022-12-13 21:22 | YPouryan |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 44787.27 | 2 |  |  |  | 75 | 83.3 | 0 | 100 | 77.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.30 | Brolga 9 | SANTOS LIMITED | BROLGA 9 | ENSIGN 974 | J.22.110013 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-11-19 18:00 | 2022-11-19 |  | 2022-11-19 18:00 | 2022-11-23 17:59 |  | 2022-11-23 17:59 | Moomba WL | KKeese | 2022-11-23 17:40 | JDagdag |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 44787.27 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.41 | Brolga 8 QC-XPT | SANTOS LIMITED | BROLGA 8 | ENSIGN 974 | J.22.124048 | RPE | ES-OH-Ops | Low | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2022-11-07 11:08 | 2022-11-02 |  | 2022-11-06 | 2022-11-13 23:59 |  | 2022-11-13 23:59 | Moomba WL | YPouryan | 2022-11-17 07:23 | KKeese |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 93341.22 | 2 |  | L2 - Shift RO |  | 83.3 | 83.3 | 0 | 100 | 80 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.29 | Brolga 8 | SANTOS LIMITED | Dullingari 62 | ENSIGN 974 | J.22.110012 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-11-05 |  | 2022-11-05 18:00 | 2022-11-09 17:59 |  |  | Moomba WL | KKeese | 2022-11-05 22:03 | eismail |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.28 | Napowie 12 | SANTOS LIMITED | Dullingari 62 | ENSIGN 974 | J.22.110011 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Started | In Progress |  | 2022-10-24 |  | 2022-10-24 18:00 | 2022-10-28 17:59 |  |  | Moomba WL | KKeese | 2022-10-23 12:41 | KKeese |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 2 |  |  |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.26 | Yarrow 3 | SANTOS LIMITED | Yarrow 003 | ENSIGN 974 | J.22.110009 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-09-20 07:00 | 2022-09-18 |  | 2022-09-20 08:00 | 2022-09-29 07:59 |  | 2022-09-29 06:59 | Moomba WL | KKeese | 2022-10-03 12:31 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Mazhar Iqbal |  | 0 | 2 |  |  |  | 75 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.25 | Dullingari 67- QCombo | SANTOS LIMITED | Dullingari 67 | ENSIGN 974 | J.22.109967 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-08-04 | 2022-08-03 14:00 |  | 2022-08-04 06:00 | 2022-08-08 05:59 |  | 2022-08-07 23:59 | Moomba WL | DKitney | 2022-10-03 12:27 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.24 | Dullingari 68 | SANTOS LIMITED | Dullingari 68 | ENSIGN 974 | J.22.109956 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-07-17 | 2022-07-16 |  | 2022-07-17 | 2022-07-20 23:59 |  | 2022-07-20 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 12:26 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.23 | Dullingari 66 | SANTOS LIMITED | Dullingari 66 | ENSIGN 974 | J.22.109947 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-06-27 | 2022-06-26 |  | 2022-06-27 | 2022-06-30 23:59 |  | 2022-06-30 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 12:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.22 | QC Q3 Well 5 | SANTOS LIMITED | DULLINGARI 062 | ENSIGN 974 | J.22.109904 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-09-12 17:00 | 2022-09-12 |  | 2022-09-12 18:00 | 2022-09-16 17:59 |  | 2022-09-16 18:59 | Moomba WL | KKeese | 2022-10-03 12:21 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.21 | QC Q3 Well 4 | SANTOS LIMITED | DULLINGARI 062 | ENSIGN 974 | J.22.109903 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-08-28 17:00 | 2022-08-28 |  | 2022-08-28 18:00 | 2022-09-01 17:59 |  | 2022-09-01 18:59 | Moomba WL | KKeese | 2022-10-03 12:21 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.20 | QC Q3 Well 3 | SANTOS LIMITED | DULLINGARI 062 | ENSIGN 974 | J.22.109902 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-08-07 17:00 | 2022-08-07 |  | 2022-08-07 18:00 | 2022-08-11 17:59 |  | 2022-08-11 18:59 | Moomba WL | KKeese | 2022-10-03 12:21 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.19 | QC Q3 Well 2 | SANTOS LIMITED | DULLINGARI 062 | ENSIGN 974 | J.22.109901 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-07-16 17:00 | 2022-07-16 |  | 2022-07-16 18:00 | 2022-07-20 17:59 |  | 2022-07-20 18:59 | Moomba WL | KKeese | 2022-10-03 12:21 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.18 | QC Q3 Well 1 | SANTOS LIMITED | DULLINGARI 062 | ENSIGN 974 | J.22.109900 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-06-27 17:00 | 2022-06-27 |  | 2022-06-27 18:00 | 2022-07-01 17:59 |  | 2022-07-01 18:59 | Moomba WL | KKeese | 2022-10-03 12:21 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.17 | Dullingari 65 | SANTOS LIMITED | Dullingari 65 | ENSIGN 974 | J.22.109818 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-05-25 17:00 | 2022-05-24 |  | 2022-05-25 18:00 | 2022-05-29 17:59 |  | 2022-05-29 16:59 | Moomba WL | KKeese | 2022-10-03 12:13 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 40415.85 | 0 |  |  |  | 75 | 66.7 | 0 | 100 | 72.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.16 | Beckler 8 | SANTOS LIMITED | Beckler 8 | ENSIGN 974 | J.22.109788 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-04-07 | 2022-04-07 |  | 2022-04-07 | 2022-04-12 23:59 |  | 2022-04-12 23:59 | Moomba WL | SYalamanchi2 | 2022-10-03 12:10 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.15 | Santos OH Logging # 5 | SANTOS LIMITED | DULLINGARI 062 | ENSIGN 974 | J.22.109656 | RPE | ES-OH-Ops | Low | Confirmed | Design - CEC |  | In Progress | Not Started | In Progress | 2022-06-06 17:00 | 2022-06-06 |  | 2022-06-06 18:00 | 2022-06-10 17:59 |  | 2022-06-10 18:59 | Moomba WL | KKeese | 2022-10-03 11:57 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 33.3 | 0 | 0 | 0 | 10 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.14 | Dullingari 64 | SANTOS LIMITED | Dullingari 64 | ENSIGN 974 | J.22.109655 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2022-06-09 07:00 | 2022-05-18 16:00 |  | 2022-06-09 08:00 | 2022-06-13 07:59 |  | 2022-06-13 06:59 | Moomba WL | KKeese | 2022-10-03 11:57 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 26770.73 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.13 | Bow 3 | SANTOS LIMITED | Bow 3 | ENSIGN 974 | J.22.109654 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2022-04-29 17:00 | 2022-04-26 |  | 2022-04-29 18:00 | 2022-05-03 17:59 |  | 2022-05-03 16:59 | Moomba WL | KKeese | 2022-10-03 11:57 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 40415.85 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.12 | Meranji 26_QC | SANTOS LIMITED | Meranji 26 | ENSIGN 974 | J.22.109653 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2022-03-16 17:00 | 2022-03-15 |  | 2022-03-16 18:00 | 2022-03-20 17:59 |  | 2022-03-20 16:59 | Moomba WL | KKeese | 2022-10-03 11:57 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 44211.44 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.11 | Meranji 25_QC | SANTOS LIMITED | MERANJI 025 | ENSIGN 974 | J.22.109652 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2022-02-23 17:00 | 2022-02-23 10:00 |  | 2022-02-23 18:00 | 2022-02-27 17:59 |  | 2022-02-27 18:59 | Moomba WL | KKeese | 2022-10-03 11:57 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | 0 |  | L3 - Full RO |  | 75 | 33.3 | 0 | 75 | 55 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.10 | Barrolka-21-QC | SANTOS LIMITED | Barrolka 21 | ENSIGN 974 | J.21.108813 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-12-29 13:00 | 2021-12-29 12:00 |  | 2021-12-29 12:00 | 2022-01-22 06:00 |  | 2022-01-22 07:00 | Moomba WL | ymoradi2 | 2022-10-03 11:53 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.09 | Coolah 17 | SANTOS LIMITED | Coolah 17 | ENSIGN 974 | J.21.108736 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress | 2021-10-09 13:00 | 2021-10-09 12:00 | 2021-10-09 | 2021-10-09 12:00 | 2021-10-13 06:00 | 2021-10-14 | 2021-10-13 07:00 | Moomba WL | IWahbi | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 0 | 1 |  |  |  | 66.7 | 33.3 | 0 | 75 | 52.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.08 | Coolah 15- QC | SANTOS LIMITED | Coolah 15 | ENSIGN 974 | J.21.108665 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-09-03 18:00 | 2021-09-02 06:00 | 2021-09-03 | 2021-09-03 18:00 | 2021-09-04 12:00 | 2021-09-05 | 2021-09-04 12:00 | Moomba WL | DKitney | 2022-10-03 11:27 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 26235.22 | 1 |  |  |  | 83.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.07 | Coolah 13- QC/XPT | SANTOS LIMITED | Coolah 13 | ENSIGN 974 | J.21.108647 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2021-07-25 18:00 | 2021-07-25 06:00 | 2021-07-25 | 2021-07-25 18:00 | 2021-07-26 12:00 | 2021-07-27 | 2021-07-26 12:00 | Moomba WL | DKitney | 2022-10-03 11:26 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 41708.9 | 2 |  |  |  | 83.3 | 33.3 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.03 | Dullingari 62 | SANTOS LIMITED | Dullingari 62 | ENSIGN 974 | J.21.108361 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-03-03 |  | 2021-03-03 18:00 | 2021-03-07 17:59 |  |  | Moomba WL | OBass | 2022-10-03 09:41 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 44211.44 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.01 | Dullingari North 25 | SANTOS LIMITED | Dullingari North 25 | ENSIGN 974 | J.21.108360 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-01-23 10:00 |  | 2021-01-24 06:00 | 2021-01-28 05:59 |  |  | Moomba WL | OBass | 2022-10-03 09:40 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 27809.33 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.04 | Dullingari 56 | SANTOS LIMITED | Dullingari 56 | ENSIGN 974 | J.21.108358 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-03-20 12:00 |  | 2021-03-22 | 2021-03-31 23:59 |  |  | Moomba WL | OBass | 2022-10-03 09:39 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 59494.09 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.02 | Dullingari 63 | SANTOS LIMITED | Dullingari 63 | ENSIGN 974 | J.21.108356 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-02-15 |  | 2021-02-15 | 2021-02-18 23:59 |  |  | Moomba WL | OBass | 2022-10-03 09:38 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 27809.33 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.06 | Dullingari North 25 - CBL | SANTOS LIMITED | Dullingari North 25 | ENSIGN 974 | J.21.108354 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-01-24 10:00 |  | 2021-01-27 06:00 | 2021-01-31 05:59 |  |  | Moomba WL | AHermawan | 2022-10-03 09:35 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 27809.33 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.04 | A.1001556.04.05 | Beckler 7 | SANTOS LIMITED | Beckler 7 | ENSIGN 974 | J.21.108352 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-04-14 |  | 2021-04-14 | 2021-04-17 23:59 |  |  | Moomba WL | OBass | 2022-10-03 09:34 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 27809.33 | 0 |  |  |  | 66.7 | 50 | 0 | 75 | 57.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.03 | A.1001556.03.26 | Dullingari 67-Pre-UBD perforation-SCMT | SANTOS LIMITED | Dullingari 67 | ENSIGN 974 | J.22.109969 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-08-07 18:00 | 2022-08-06 12:00 |  | 2022-08-07 18:00 | 2022-08-08 12:00 |  | 2022-08-08 12:00 | Moomba WL | ymoradi2 | 2022-10-03 12:27 | FDPSystemUser |  | No |  |  |  |  | Mazhar Iqbal |  | 18598.44 | 1 |  |  |  | 75 | 50 | 0 | 75 | 60 |  | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001556 | O.1001556.03 | A.1001556.03.25 | Dullingari 66-UBD | SANTOS LIMITED | Dullingari 66 | ENSIGN 974 | J.22.109949 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-06-30 18:00 | 2022-06-29 12:00 |  | 2022-06-30 18:00 | 2022-07-01 12:00 |  | 2022-07-01 12:00 | Moomba WL | DKitney | 2022-10-03 12:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 18598.44 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001556 | O.1001556.03 | A.1001556.03.24 | Dullingari 64 SCMT, Perf | SANTOS LIMITED | Dullingari 64 | ENSIGN 974 | J.22.109938 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-06-12 12:00 | 2022-06-11 |  | 2022-06-12 12:00 | 2022-06-13 06:00 |  | 2022-06-13 06:00 | Moomba WL | JMoraes2 | 2022-10-03 12:24 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 18226.47 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001556 | O.1001556.03 | A.1001556.03.23 | Dullingari 65- UBD Perf | SANTOS LIMITED | Dullingari 65 | ENSIGN 974 | J.22.109821 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-05-26 | 2022-05-24 14:00 |  | 2022-05-26 | 2022-05-26 14:00 |  | 2022-05-26 14:00 | Moomba WL | DKitney | 2022-10-03 12:13 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 18226.47 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001556 | O.1001556.03 | A.1001556.03.22 | BOW 3 _CBL_PERF | SANTOS LIMITED | Bow 3 | ENSIGN 974 | J.22.109804 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2022-05-11 12:00 | 2022-04-28 |  | 2022-05-11 12:00 | 2022-05-16 11:59 |  | 2022-05-16 11:59 | Moomba WL | zauzar | 2022-10-03 12:11 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 19320.06 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Elsamawal Mohamedelhassan Awadalla Ismail | WL Production Services
P.1001556 | O.1001556.03 | A.1001556.03.21 | Beckler 8 - SCMT Perf | SANTOS LIMITED | BECKLER 008 | ENSIGN 974 | J.22.109791 | RPI | PS-WL-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Design Completed | In Progress | 2022-04-11 | 2022-04-10 |  | 2022-04-11 | 2022-04-13 23:59 |  | 2022-04-13 23:59 | Moomba WL | ADuong4 | 2022-10-03 12:10 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 2 |  | L0 - No RO |  | 91.7 | 100 | 0 | 100 | 87.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001556 | O.1001556.03 | A.1001556.03.20 | Meranji 26-Pre UBD SCMT, Perf | SANTOS LIMITED | Meranji 26 | ENSIGN 974 | J.22.109761 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-03-19 14:00 | 2022-03-19 10:00 |  | 2022-03-19 14:00 | 2022-03-21 10:59 |  | 2022-03-21 10:59 | Moomba WL | ymoradi2 | 2022-10-03 12:07 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 18441.71 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001556 | O.1001556.03 | A.1001556.03.19 | Meranji 25- Perf | SANTOS LIMITED | Meranji 25 | ENSIGN 974 | J.22.109727 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-02-27 03:00 | 2022-02-26 10:00 |  | 2022-02-27 03:00 | 2022-02-28 23:59 |  | 2022-02-28 23:59 | Moomba WL | DKitney | 2022-10-03 12:04 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 18441.71 | 2 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001556 | O.1001556.03 | A.1001556.03.18 | UBD | SANTOS LIMITED | COOLAH 18 | ENSIGN 974 | J.22.109626 | RPI | PS-WL-NO | Low | Confirmed | Design - CEC |  | Design Completed | Design Completed | In Progress | 2022-02-10 17:00 | 2022-02-09 17:00 |  | 2022-02-10 17:00 | 2022-02-14 16:59 |  | 2022-02-14 16:59 | Moomba WL | KKeese | 2022-10-03 11:54 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  | L0 - No RO |  | 75 | 66.7 | 100 | 50 | 67.5 |  | 0 |  |  |  | 0 |  |  |  | Kelly Keese | WL Production Services
P.1001556 | O.1001556.03 | A.1001556.03.17 | Coolah18-OH Logging | SANTOS LIMITED | Coolah 18 | ENSIGN 974 | J.22.109620 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-21 | 2022-01-20 17:00 |  | 2022-01-20 17:00 | 2022-01-28 16:59 |  | 2022-01-28 23:59 | Moomba WL | DKitney | 2022-10-03 11:54 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.03 | A.1001556.03.16 | Coolah18-UBD | SANTOS LIMITED | Coolah 18 | ENSIGN 974 | J.22.109619 | RPI | PS-WL-NO | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2022-01-17 | 2022-01-15 17:00 |  | 2022-01-16 17:00 | 2022-01-20 16:59 |  | 2022-01-20 23:59 | Moomba WL | DKitney | 2022-10-03 11:54 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 5730.99 | 1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001556 | O.1001556.03 | A.1001556.03.15 | Barrolka 21 | SANTOS LIMITED | Barrolka 21 | ENSIGN 974 | J.21.108810 | RPI | PS-WL-NO | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-23 | 2021-12-22 |  | 2021-12-23 | 2021-12-26 23:59 |  | 2021-12-26 23:59 | Moomba WL | ADuong4 | 2022-10-03 11:53 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 5730.99 | 1 |  |  |  | 91.7 | 66.7 | 100 | 75 | 80 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001556 | O.1001556.03 | A.1001556.03.14 | Barrolka 24 | SANTOS LIMITED | Barrolka 24 | ENSIGN 974 | J.21.108794 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-12-02 19:00 | 2021-11-23 |  | 2021-12-03 | 2021-12-04 23:59 |  | 2021-12-03 04:00 | Moomba WL | RTwigg | 2022-10-03 11:51 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 27109.56 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001556 | O.1001556.03 | A.1001556.03.13 | Barrolka 22 | SANTOS LIMITED | Barrolka 22 | ENSIGN 974 | J.21.108786 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-11-13 19:00 | 2021-11-13 06:00 |  | 2021-11-13 18:00 | 2021-11-22 23:59 |  | 2021-11-23 00:59 | Moomba WL | KKeese | 2022-10-03 11:51 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001556 | O.1001556.03 | A.1001556.03.12 | Barrolka 23 | SANTOS LIMITED | Barrolka 23 | ENSIGN 974 | J.21.108773 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-28 19:00 | 2021-10-28 06:00 | 2021-10-27 05:00 | 2021-10-28 18:00 | 2021-11-06 23:59 | 2021-11-07 01:00 | 2021-11-07 00:59 | Moomba WL | KKeese | 2022-10-03 11:40 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001556 | O.1001556.03 | A.1001556.03.11 | Coolah 17 | SANTOS LIMITED | Coolah 17 | ENSIGN 974 | J.21.108754 | RPI | PS-WL-NO | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-10-08 | 2021-10-05 | 2021-10-08 | 2021-10-08 | 2021-10-13 23:59 | 2021-10-14 | 2021-10-13 23:59 | Moomba WL | ADuong4 | 2022-10-03 11:38 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 91.7 | 66.7 | 100 | 75 | 80 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001556 | O.1001556.03 | A.1001556.03.10 | Coolah 16 | SANTOS LIMITED | Coolah 16 | ENSIGN 974 | J.21.108742 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-09-21 18:00 | 2021-09-21 06:00 | 2021-09-20 04:00 | 2021-09-21 18:00 | 2021-09-30 23:59 | 2021-10-01 | 2021-09-30 23:59 | Moomba WL | KKeese | 2022-10-03 11:37 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 83.3 | 50 | 0 | 75 | 62.5 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001556 | O.1001556.03 | A.1001556.03.09 | Coolah 15 | SANTOS LIMITED | Coolah 15 | ENSIGN 974 | J.21.108660 | RPI | PS-WL-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-24 18:00 | 2021-08-24 06:00 | 2021-08-23 04:00 | 2021-08-24 18:00 | 2021-09-02 23:59 | 2021-09-03 | 2021-09-02 23:59 | Moomba WL | ADuong4 | 2022-10-03 11:27 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 91.7 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001556 | O.1001556.03 | A.1001556.03.08 | Coolah 14 | SANTOS LIMITED | Coolah 14 | ENSIGN 974 | J.21.108656 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-08-10 10:00 | 2021-08-10 06:00 | 2021-08-10 | 2021-08-10 10:00 | 2021-08-14 23:59 | 2021-08-15 | 2021-08-14 23:59 | Moomba WL | ADuong4 | 2022-10-03 11:26 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 1 |  |  |  | 91.7 | 66.7 | 0 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001556 | O.1001556.03 | A.1001556.03.07 | Coolah 13- UBD Packer Setting | SANTOS LIMITED | COOLAH 13 | ENSIGN 974 | J.21.108644 | RPI | PS-WL-NO | Medium | Confirmed | Design - CEC |  | Not Required | Not Required | In Progress |  | 2021-07-20 19:00 | 2021-07-22 | 2021-07-22 01:00 | 2021-07-23 23:59 | 2021-07-24 |  | Moomba WL | DKitney | 2022-10-03 11:25 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | 0 |  | L0 - No RO |  | 91.7 | 33.3 | 100 | 75 | 70 |  | 0 |  |  |  | 0 |  |  |  | Ihab Wahbi | WL Production Services
P.1001556 | O.1001556.03 | A.1001556.03.06 | Dullingari 56 | SANTOS LIMITED | Dullingari 56 | ENSIGN 974 | J.21.108525 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-26 12:00 | 2021-03-26 | 2021-03-26 | 2021-03-26 12:00 | 2021-03-28 23:59 | 2021-03-29 | 2021-03-28 23:59 | Moomba WL | KKeese | 2022-10-03 11:13 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 39038.04 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001556 | O.1001556.03 | A.1001556.03.05 | Dullingari 62 | SANTOS LIMITED | Dullingari 62 | ENSIGN 974 | J.21.108429 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress | 2021-03-06 12:00 | 2021-03-06 | 2021-03-06 | 2021-03-06 12:00 | 2021-03-08 23:59 | 2021-03-09 | 2021-03-08 23:59 | Moomba WL | DParker16 | 2022-10-03 11:04 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 39038.04 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001556 | O.1001556.03 | A.1001556.03.01 | Dullingari North 24_Underbalance drilling | SANTOS LIMITED | Dullingari North 24 | ENSIGN 974 | J.20.062397 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2020-12-13 |  | 2020-12-17 | 2020-12-20 23:59 |  |  | Moomba WL | ymoradi2 | 2022-10-03 09:40 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Production Services
P.1001556 | O.1001556.03 | A.1001556.03.02 | Dullingari North 23 | SANTOS LIMITED | DULLINGARI NORTH 23 | ENSIGN 974 | J.21.108359 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-01-09 |  | 2021-01-13 | 2021-01-16 23:59 |  |  | Moomba WL | KKeese | 2022-10-03 09:39 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001556 | O.1001556.03 | A.1001556.03.03 | Dullingari 25_Perfo Packer Set | SANTOS LIMITED | Dullingari North 25 | ENSIGN 974 | J.21.108357 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | In Progress | In Progress |  | 2021-01-29 |  | 2021-01-30 | 2021-03-03 23:59 |  |  | Moomba WL | ymoradi2 | 2022-10-03 09:39 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001556 | O.1001556.03 | A.1001556.03.04 | Dullingari 63 | SANTOS LIMITED | Dullingari 63 | ENSIGN 974 | J.21.108355 | RPI | PS-WL-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | In Progress |  | 2021-03-16 |  | 2021-03-16 | 2021-03-18 23:59 |  |  | Moomba WL | KKeese | 2022-10-03 09:38 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Owen Bass | WL Production Services
P.1001556 | O.1001556.02 | A.1001556.02.01 | Moomba 237 MSCT-HT | SANTOS LIMITED | Fixed Rental | ENSIGN 974 |  | RPE | ES-OH-NO | InComplete | Confirmed | Execute - PSD |  | Not Started | Not Started | In Progress |  | 2020-02-20 |  | 2020-02-20 | 2020-02-24 |  |  | Moomba WL | AGamero | 2020-02-24 10:31 | AGamero |  | No |  |  |  | ROE WL Mumbai | Rob Twigg |  | 3291.9 |  |  | L3 - Full RO | [7 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.06 | Gooranie 17 | SANTOS LIMITED | GOORANIE 17 | ENSIGN 974 | J.19.060395 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-11-11 14:00 |  | 2019-11-13 14:00 | 2019-11-17 14:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:41 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.36 | Bindah 5 | SANTOS LIMITED | Bindah 5 | ENSIGN 974 | J.20.062396 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-27 21:00 |  | 2020-08-28 06:00 | 2020-09-01 06:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:40 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.15 | Brolga 6 | SANTOS LIMITED | Brolga 6 | ENSIGN 974 | J.20.062395 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-05-31 |  | 2020-06-28 | 2020-07-02 |  |  | Moomba WL | AGamero | 2022-10-03 09:40 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 96856.67 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.40 | Dullingari North 24_CBL | SANTOS LIMITED | Dullingari North 24 | ENSIGN 974 | J.20.062390 | RPE | ES-CH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-12-09 08:00 |  | 2020-12-09 10:00 | 2020-12-10 23:59 |  |  | Moomba WL | MAl-wakeel | 2022-10-03 09:39 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 10124.76 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.35 | Bindah 4 | SANTOS LIMITED | Bindah 4 | ENSIGN 974 | J.20.062389 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-08-17 |  | 2020-08-17 | 2020-08-21 |  |  | Moomba WL | AGamero | 2022-10-03 09:39 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 56537.53 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.37 | Ficus 3 | SANTOS LIMITED | Ficus 3 | ENSIGN 974 | J.20.062386 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-11-17 09:00 |  | 2020-11-18 16:00 | 2020-11-22 16:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:38 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.21 | Well TBD | SANTOS LIMITED |  | ENSIGN 974 | J.20.062385 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-06-26 01:00 |  | 2020-06-27 | 2020-07-01 |  |  | Moomba WL | AGamero | 2022-10-03 09:38 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.28 | Dullingari North 24 | SANTOS LIMITED | Dullingari North 24 | ENSIGN 974 | J.20.062384 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-12-01 20:00 |  | 2020-12-02 20:00 | 2020-12-06 20:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:38 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.24 | Well TBD | SANTOS LIMITED |  | ENSIGN 974 | J.20.062380 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-08-14 01:00 |  | 2020-08-15 | 2020-08-19 |  |  | Moomba WL | AGamero | 2022-10-03 09:37 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.39 | Coopers Creek 8 | SANTOS LIMITED | Coopers Creek 8 | ENSIGN 974 | J.20.062378 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-10-01 21:00 |  | 2020-10-01 21:00 | 2020-10-06 22:00 |  |  | Moomba WL | MSchvartz | 2022-10-03 09:37 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.27 | Coopers Creek 8 | SANTOS LIMITED |  | ENSIGN 974 | J.20.062374 | RPE | ES-OH-Ops | Medium | Cancelled | Execute - PSD |  | Design Completed | Not Started | In Progress |  | 2020-09-27 |  | 2020-09-27 | 2020-09-30 23:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:37 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.12 | Moorari 20 | SANTOS LIMITED | Moorari Dev 20 | ENSIGN 974 | J.20.062373 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-03-07 08:00 |  | 2020-03-09 08:00 | 2020-03-13 08:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:36 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 26235.22 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.03 | ES Logging | SANTOS LIMITED | GOORANIE 14 | ENSIGN 974 | J.19.060383 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-10-11 15:00 |  | 2019-10-13 14:00 | 2019-10-17 14:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:36 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.34 | Favela 1 | SANTOS LIMITED | Favela 1 | ENSIGN 974 | J.20.062372 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-17 14:00 |  | 2020-05-17 14:00 | 2020-05-21 14:00 |  |  | Moomba WL | MSchvartz | 2022-10-03 09:36 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.22 | Well TBD | SANTOS LIMITED |  | ENSIGN 974 | J.20.062371 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-07-17 01:00 |  | 2020-07-18 | 2020-07-22 |  |  | Moomba WL | AGamero | 2022-10-03 09:36 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.13 | Moomba 255 | SANTOS LIMITED | Moomba 255 | ENSIGN 974 | J.20.062370 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-04-10 13:00 |  | 2020-08-25 | 2020-08-29 |  |  | Moomba WL | AGamero | 2022-10-03 09:36 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 16973.68 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.08 | Bugsy 1 | SANTOS LIMITED | Moomba 236 | ENSIGN 974 | J.19.060382 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-28 15:00 |  | 2019-12-29 14:00 | 2020-01-02 14:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:36 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.05 | Moomba 237 | SANTOS LIMITED | Moomba 237 | ENSIGN 974 | J.19.060381 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-12-13 15:00 |  | 2019-12-14 14:00 | 2019-12-18 14:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:36 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.25 | Coopers Creek 6 | SANTOS LIMITED | Coopers Creek 6 | ENSIGN 974 | J.20.062365 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-09-06 22:00 |  | 2020-09-07 21:00 | 2020-09-11 21:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:35 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.20 | Well TBD | SANTOS LIMITED |  | ENSIGN 974 | J.20.062364 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-06-12 01:00 |  | 2020-06-13 | 2020-06-17 |  |  | Moomba WL | AGamero | 2022-10-03 09:35 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.16 | Brolga 7 | SANTOS LIMITED | Brolga 7 | ENSIGN 974 | J.20.062363 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-06-15 |  | 2020-06-15 | 2020-06-20 |  |  | Moomba WL | AGamero | 2022-10-03 09:35 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 26235.22 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.38 | Ficus 2 | SANTOS LIMITED | Ficus 2 | ENSIGN 974 | J.20.062361 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-11-05 21:00 |  | 2020-11-05 21:00 | 2020-11-09 21:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:35 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.32 | Well TBD | SANTOS LIMITED |  | ENSIGN 974 | J.20.062360 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-12-18 01:00 |  | 2020-12-19 | 2020-12-23 |  |  | Moomba WL | AGamero | 2022-10-03 09:35 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.31 | Well TBD | SANTOS LIMITED |  | ENSIGN 974 | J.20.062359 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-12-04 01:00 |  | 2020-12-05 | 2020-12-09 |  |  | Moomba WL | AGamero | 2022-10-03 09:35 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.23 | Well TBD | SANTOS LIMITED |  | ENSIGN 974 | J.20.062358 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-07-31 01:00 |  | 2020-08-01 | 2020-08-05 |  |  | Moomba WL | AGamero | 2022-10-03 09:35 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.19 | Dullingari North 25 | SANTOS LIMITED |  | ENSIGN 974 | J.21.108353 | RPE | ES-OH-Ops | Medium | Cancelled | Design - PSD |  | Design Completed | Not Started | In Progress |  | 2021-01-11 |  | 2021-01-11 | 2021-01-15 |  |  | Moomba WL | AGamero | 2022-10-03 09:34 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.09 | Bugsy 1 | SANTOS LIMITED | Bugsy 1 | ENSIGN 974 | J.20.062357 | RPE | ES-OH-Ops | Low | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-01-25 07:00 |  | 2020-01-25 08:00 | 2020-02-06 08:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:34 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.07 | Moomba 236 | SANTOS LIMITED | MOOMBA 236 | ENSIGN 974 | J.20.062356 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2019-10-28 02:37 | 2020-01-07 12:00 |  | 2020-01-18 14:00 | 2020-01-22 14:00 |  | 2020-01-25 07:11 | Moomba WL | AGamero | 2022-10-03 09:34 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 26235.22 |  |  | L0 - No RO |  | 50 | 16.7 | 0 | 25 | 27.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.33 | Well TBD | SANTOS LIMITED |  | ENSIGN 974 | J.21.108351 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2021-01-01 01:00 |  | 2021-01-02 | 2021-01-06 |  |  | Moomba WL | AGamero | 2022-10-03 09:34 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.14 | Moomba 253 | SANTOS LIMITED |  | ENSIGN 974 | J.20.062355 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-05-09 14:00 |  | 2020-05-09 14:00 | 2020-05-13 14:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:34 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.10 | Merchant 1 | SANTOS LIMITED | MERCHANT 001 | ENSIGN 974 | J.20.062354 | RPE | ES-OH-Ops | Medium | Confirmed | Execute - PSD |  | Design Completed | Not Started | In Progress | 2019-10-30 03:13 | 2020-02-17 16:00 |  | 2020-02-18 15:00 | 2020-02-21 15:00 |  | 2020-03-07 16:00 | Moomba WL | AGamero | 2022-10-03 09:34 | FDPSystemUser |  | No |  |  |  |  | Alonso Alejandro Gamero Acuna |  | 0 |  |  | L0 - No RO |  | 50 | 16.7 | 0 | 37.5 | 31.3 |  | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.30 | Well TBD | SANTOS LIMITED |  | ENSIGN 974 | J.20.062352 | RPE | ES-OH-Ops | Medium | Cancelled | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-11-13 01:00 |  | 2020-11-14 | 2020-11-18 |  |  | Moomba WL | AGamero | 2022-10-03 09:34 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  |  |  | 41.7 | 0 | 0 | 0 | 12.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.26 | Coopers Creek 7 | SANTOS LIMITED | Coopers Creek 7 | ENSIGN 974 | J.20.062351 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-09-20 21:00 |  | 2020-09-20 21:00 | 2020-09-24 21:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:33 | FDPSystemUser |  | No |  |  |  |  | Rob Twigg |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.18 | Derwin 1 | SANTOS LIMITED | DERWIN 1 | ENSIGN 974 | J.20.062350 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Started | In Progress |  | 2020-07-30 |  | 2020-08-10 | 2020-08-14 |  |  | Moomba WL | AGamero | 2022-10-03 09:33 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 188300.73 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.04 | Moomba South 250 | SANTOS LIMITED | Moomba South 250 | ENSIGN 974 | J.19.060377 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-11-28 15:00 |  | 2019-11-30 14:00 | 2019-12-04 14:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:33 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.02 | ES Logging | SANTOS LIMITED | GOORANIE 13 | ENSIGN 974 | J.19.060376 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-10-01 02:00 |  | 2019-10-01 20:00 | 2019-10-05 20:00 |  |  | Moomba WL | AGamero | 2022-10-03 09:33 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.29 | Dullingari North 23 | SANTOS LIMITED | DULLINGARI NORTH 23 | ENSIGN 974 | J.21.108350 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress |  | 2021-01-03 |  | 2021-01-04 | 2021-01-08 |  |  | Moomba WL | AGamero | 2022-10-03 09:33 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 5730.99 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.11 | Moorari 19 | SANTOS LIMITED | Moorari 19 | ENSIGN 974 | J.20.062348 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-02-24 01:00 |  | 2020-02-25 | 2020-02-29 |  |  | Moomba WL | AGamero | 2022-10-03 09:33 | FDPSystemUser |  | No |  |  |  |  | Owen Bass |  | 0 | [10 empty] | 0 | [7 empty] | Ihab Wahbi | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.01 | OH Logging | SANTOS LIMITED | GOORANIE 12 | ENSIGN 974 | J.19.060374 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2019-09-13 |  | 2019-09-15 | 2019-09-19 |  |  | Moomba WL | miqbal13 | 2022-10-03 09:33 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 32488.63 | [10 empty] | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001556 | O.1001556.01 | A.1001556.01.17 | Napowie 9 | SANTOS LIMITED | Napowie APP A | ENSIGN 974 |  | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Started | In Progress |  | 2020-06-27 22:00 |  | 2020-06-29 20:00 | 2020-07-03 20:00 |  |  | Moomba WL | AGamero | 2022-09-03 07:59 | walfaro |  | No |  |  |  |  | Ihab Wahbi |  | 82394.1 | [10 empty] | 0 | [7 empty] | Alonso Alejandro Gamero Acuna | WL Evaluation Services
P.1001555 | O.1001555.01 | A.1001555.01.01 | OH Logging | SANTOS LIMITED | VEGA NORTH 2 | Ensign 967 | J.19.060379 | RPE | ES-OH-Ops | Medium | Confirmed | Design - PSD |  | In Progress | Not Started | In Progress | 2019-09-18 | 2019-09-18 |  | 2019-09-18 | 2019-09-22 |  | 2019-09-22 | Moomba WL | miqbal13 | 2022-10-03 09:35 | FDPSystemUser |  | No |  |  |  |  | Ihab Wahbi |  | 0 |  |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 | [7 empty] | Mazhar Iqbal | WL Evaluation Services
P.1001189 | O.1001189.03 | A.1001189.03.17 | TMO-C4 | GREYMOUTH PETROLEUM | TMO-C3, TMO C4 | Tiger-246 | J.25.101948 | RPE | ES-OH-Ops | InComplete | Confirmed | Execute - PSD |  | Design Completed | Not Required | Design Completed | 2023-11-08 | 2025-10-23 | 2025-10-08 | 2025-10-23 | 2025-11-02 23:59 | 2025-11-09 | 2025-11-02 23:59 | New Plymouth WL | CKok3 | 2025-10-30 14:11 | ESchmidtke |  | No |  |  |  |  | Cheryl Kok |  | 396918.96 | 7 |  | L0 - No RO |  | 100 | 66.7 | 100 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001189 | O.1001189.03 | A.1001189.03.18 | Kaimiro 22 | GREYMOUTH PETROLEUM | KAIMIRO-21 | Tiger-246 | J.25.157771 | RPE | ES-OH-Ops | Medium | Confirmed | Design - CEC |  | Design Completed | Not Started | In Progress | 2023-09-22 | 2025-10-01 |  | 2025-10-15 | 2025-10-25 23:59 |  | 2025-10-25 23:59 | New Plymouth WL | CKok3 | 2025-09-26 13:08 | CKok3 |  | No |  |  |  |  | Cheryl Kok |  | 0 | 5 |  | L0 - No RO |  | 50 | 0 | 0 | 0 | 15 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001189 | O.1001189.03 | A.1001189.03.16 | Kaimiro 21 | GREYMOUTH PETROLEUM | KAIMIRO-21 | Tiger-246 | J.25.100560 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Design Completed | Design Completed | 2024-01-14 | 2025-07-01 | 2025-07-01 | 2025-07-04 | 2025-08-06 23:59 | 2025-08-28 | 2025-08-12 | New Plymouth WL | CKok3 | 2025-08-03 15:52 | ysaeedabadian |  | Yes |  |  |  | ROE WL Mumbai | Cheryl Kok |  | 462108.8 | 10 |  | L3 - Full RO |  | 100 | 83.3 | 100 | 100 | 95 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001189 | O.1001189.03 | A.1001189.03.14 | TMO-C3 6-3/4" OH | GREYMOUTH PETROLEUM | TMO-C3 | Tiger-246 | J.25.054847 | RPE | ES-OH-Ops | High | Confirmed | Execute - PSD |  | Design Completed | Not Required | In Progress | 2023-10-23 | 2025-04-27 01:00 | 2025-04-25 12:00 | 2025-04-29 | 2025-05-15 23:59 | 2025-05-17 | 2025-05-16 01:59 | New Plymouth WL | CKok3 | 2025-05-21 14:01 | CKok3 |  | No |  |  |  |  | Cheryl Kok |  | 0 | 8 |  | L0 - No RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001189 | O.1001189.03 | A.1001189.03.15 | TMO-C3 9-1/2" | GREYMOUTH PETROLEUM | TMO-C3 | Tiger-246 | J.25.054856 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2023-09-08 | 2025-03-08 01:00 | 2025-03-12 | 2025-03-15 | 2025-03-26 00:59 | 2025-03-27 01:00 | 2025-03-26 02:59 | New Plymouth WL | CKok3 | 2025-05-21 13:59 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Cheryl Kok |  | 403938.32 | 5 |  | L2 - Shift RO |  | 100 | 100 | 100 | 100 | 100 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001189 | O.1001189.03 | A.1001189.03.03 | Turangi-21 PNX | GREYMOUTH PETROLEUM | TURANGI 21 | Tiger-246 | J.24.019767 | RPI | PS-WL-Ops | Low | Cancelled | Close - PSD |  | Design Completed | Not Required | Design Completed | 2025-04-10 | 2025-04-01 01:00 | 2025-04-09 12:00 | 2025-04-10 | 2025-05-01 23:59 | 2025-05-02 | 2025-05-01 23:59 | New Plymouth WL | CKok3 | 2025-05-21 13:56 | CKok3 |  | No |  |  |  |  | Cheryl Kok |  | 0 | 1 |  | L0 - No RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1001189 | O.1001189.03 | A.1001189.03.04 | Turangi 17 PNX | GREYMOUTH PETROLEUM | TURANGI 17 | Tiger-246 | J.24.019768 | RPI | PS-WL-NO | Low | Cancelled | Close - PSD |  | Design Completed | Not Required | Not Started | 2024-11-14 | 2024-11-07 |  | 2024-11-14 | 2024-11-24 23:59 |  | 2024-11-24 23:59 | New Plymouth WL | CKok3 | 2025-05-21 13:56 | CKok3 |  | No |  |  |  |  | Cheryl Kok |  | 0 | 1 |  | L0 - No RO |  | 58.3 | 33.3 | 100 | 50 | 52.5 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Production Services
P.1001189 | O.1001189.03 | A.1001189.03.11 | TMO-C2 | GREYMOUTH PETROLEUM | TMO C-1 | Tiger-246 | J.24.186576 | RPE | ES-OH-Ops | Low | Cancelled | Close - PSD |  | In Progress | Not Required | In Progress | 2024-01-31 | 2024-11-12 01:00 | 2024-12-12 | 2024-12-15 | 2024-12-25 23:59 | 2024-12-27 | 2024-12-26 01:59 | New Plymouth WL | CKok3 | 2025-05-21 13:56 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Cheryl Kok |  | 0 | 5 |  | L2 - Shift RO |  | 58.3 | 0 | 0 | 0 | 17.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001189 | O.1001189.03 | A.1001189.03.10 | Well 1 | GREYMOUTH PETROLEUM | TMO C-1 | Tiger-246 | J.24.144496 | RPE | ES-OH-Ops | High | Cancelled | Close - PSD |  | In Progress | Not Started | Not Started | 2024-10-16 | 2025-01-19 |  | 2025-01-26 | 2025-02-02 23:59 |  | 2024-10-23 23:59 | New Plymouth WL | YLee25 | 2025-05-19 14:05 | CKok3 |  | No |  |  |  |  | Shameer Mumtaz Ali |  | 0 | 4 |  | L0 - No RO |  | 25 | 0 | 0 | 0 | 7.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001189 | O.1001189.03 | A.1001189.03.13 | TMO-B3 | GREYMOUTH PETROLEUM | TMO-B1 | Tiger-246 | J.25.037315 | RPE | ES-OH-Ops | InComplete | Cancelled | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-03-16 10:00 | 2025-03-01 |  | 2025-03-01 10:00 | 2025-03-08 09:59 |  | 2025-03-08 09:59 | New Plymouth WL | CKok3 | 2025-03-03 15:42 | CKok3 |  | No |  |  |  | ROE WL Mumbai | Cheryl Kok |  | 0 | 5 |  | L2 - Shift RO |  | 75 | 0 | 0 | 0 | 22.5 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001189 | O.1001189.03 | A.1001189.03.12 | TMO-B1 | GREYMOUTH PETROLEUM | TMO-B1 | Tiger-246 | J.25.028677 | RPE | ES-OH-Ops | InComplete | Operationally Complete | Close - PSD |  | Design Completed | Not Required | Design Completed | 2024-01-24 10:00 | 2025-01-08 |  | 2025-01-08 10:00 | 2025-01-15 09:59 |  | 2025-01-15 09:59 | New Plymouth WL | CKok3 | 2025-01-20 19:22 | SMccauley |  | No |  |  |  | ROE WL Mumbai | Cheryl Kok |  | 657818.28 | 5 |  | L2 - Shift RO |  | 100 | 100 | 0 | 100 | 90 |  | 0 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001189 | O.1001189.03 | A.1001189.03.09 | TMO-C1 | GREYMOUTH PETROLEUM | TMO C-1 | Tiger-246 | J.24.140933 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | In Progress | Not Required | Design Completed | 2024-10-11 | 2024-09-28 |  | 2024-10-31 | 2024-11-10 23:59 |  | 2024-11-11 01:59 | New Plymouth WL | CKok3 | 2024-11-21 16:41 | SNiang |  | No |  |  |  | ROE WL Mumbai | Cheryl Kok |  | 988194.52 | 6 |  | L2 - Shift RO |  | 91.7 | 100 | 100 | 100 | 97.5 |  | 2 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services
P.1001189 | O.1001189.03 | A.1001189.03.02 | Kaimiro-20 | GREYMOUTH PETROLEUM | KAIMIRO-20 | Tiger-246 | J.24.019766 | RPE | ES-OH-Ops | Medium | Operationally Complete | Close - PSD |  | Design Completed | Not Required | In Progress | 2024-02-25 | 2024-02-21 |  | 2024-02-25 | 2024-03-06 23:59 |  | 2024-03-06 23:59 | New Plymouth WL | CKok3 | 2024-08-21 17:52 | FDPSystemUser |  | No |  |  |  |  | Cheryl Kok |  | 1341291.38 | 6 |  | L0 - No RO |  | 87.5 | 100 | 100 | 100 | 96.3 |  | 1 |  |  |  | 0 |  |  |  | Cheryl Kok | WL Evaluation Services